GAVI Alliance

Application Form for Country Proposals

For Support to New and Under-Used Vaccines (NVS)

Submitted by

The Government of

Rwanda

Date of submission: 01.06.2011 11:35:44

Deadline for submission: 1 Jun 2011

Select Start and End Year of your Comprehensive Multi-Year Plan (cMYP)

| Start Year | 2011 | End Year | 2015 |
| --- | --- | --- | --- |

Revised in January 2011

(To be used with Guidelines of December 2010)

Please submit the Proposal using the online platform https://AppsPortal.gavialliance.org/PDExtranet.

Enquiries to: proposals@gavialliance.org or representatives of a GAVI partner agency. The documents can be shared with GAVI partners, collaborators and general public. The Proposal and attachments must be submitted in English, French, Spanish, or Russian.

Note: Please ensure that the application has been received by the GAVI Secretariat on or before the day of the deadline.

The GAVI Secretariat is unable to return submitted documents and attachments to countries. Unless otherwise specified, documents will be shared with the GAVI Alliance partners and the general public.

GAVI ALLIANCE GRANT TERMS AND CONDITIONS FUNDING USED SOLELY FOR APPROVED PROGRAMMES The applicant country (“Country”) confirms that all funding provided by the GAVI Alliance will be used and applied for the sole purpose of fulfilling the programme(s) described in the Country’s application. Any significant change from the approved programme(s) must be reviewed and approved in advance by the GAVI Alliance. All funding decisions for the application are made at the discretion of the GAVI Alliance Board and are subject to IRC processes and the availability of funds. AMENDMENT TO THE APPLICATION The Country will notify the GAVI Alliance in its Annual Progress Report if it wishes to propose any change to the programme(s) description in its application. The GAVI Alliance will document any change approved by the GAVI Alliance, and the Country’s application will be amended. RETURN OF FUNDS The Country agrees to reimburse to the GAVI Alliance all funding amounts that are not used for the programme(s) described in its application. The country’s reimbursement must be in US dollars and be provided, unless otherwise decided by the GAVI Alliance, within sixty (60) days after the Country receives the GAVI Alliance’s request for a reimbursement and be paid to the account or accounts as directed by the GAVI Alliance. SUSPENSION/ TERMINATION The GAVI Alliance may suspend all or part of its funding to the Country if it has reason to suspect that funds have been used for purpose other than for the programmes described in the Country’s application, or any GAVI Alliance-approved amendment to the application. The GAVI Alliance retains the right to terminate its support to the Country for the programmes described in its application if a misuse of GAVI Alliance funds is confirmed. ANTICORRUPTION The Country confirms that funds provided by the GAVI Alliance shall not be offered by the Country to any third person, nor will the Country seek in connection with its application any gift, payment or benefit directly or indirectly that could be construed as an illegal or corrupt practice. AUDITS AND RECORDS The Country will conduct annual financial audits, and share these with the GAVI Alliance, as requested. The GAVI Alliance reserves the right, on its own or through an agent, to perform audits or other financial management assessment to ensure the accountability of funds disbursed to the Country. The Country will maintain accurate accounting records documenting how GAVI Alliance funds are used. The Country will maintain its accounting records in accordance with its government-approved accounting standards for at least three years after the date of last disbursement of GAVI Alliance funds. If there is any claims of misuse of funds, Country will maintain such records until the audit findings are final. The Country agrees not to assert any documentary privilege against the GAVI Alliance in connection with any audit. CONFIRMATION OF LEGAL VALIDITY The Country and the signatories for the Country confirm that its application, and Annual Progress Report, are accurate and correct and form legally binding obligations on the Country, under the Country’s law, to perform the programmes described in its application, as amended, if applicable, in the APR. CONFIRMATION OF COMPLIANCE WITH THE GAVI ALLIANCE TRANSPARANCY AND ACCOUNTABILITY POLICY The Country confirms that it is familiar with the GAVI Alliance Transparency and Accountability Policy (TAP) and complies with the requirements therein. USE OF COMMERCIAL BANK ACCOUNTS The Country is responsible for undertaking the necessary due diligence on all commercial banks used to manage GAVI cash-based support. The Country confirms that it will take all responsibility for replenishing GAVI cash support lost due to bank insolvency, fraud or any other unforeseen event. ARBITRATION Any dispute between the Country and the GAVI Alliance arising out of or relating to its application that is not settled amicably within a reasonable period of time, will be submitted to arbitration at the request of either the GAVI Alliance or the Country. The arbitration will be conducted in accordance with the then-current UNCITRAL Arbitration Rules. The parties agree to be bound by the arbitration award, as the final adjudication of any such dispute. The place of arbitration will be Geneva, Switzerland. The language of the arbitration will be English. For any dispute for which the amount at issue is US$ 100,000 or less, there will be one arbitrator appointed by the GAVI Alliance. For any dispute for which the amount at issue is greater than US $100,000 there will be three arbitrators appointed as follows: The GAVI Alliance and the Country will each appoint one arbitrator, and the two arbitrators so appointed will jointly appoint a third arbitrator who shall be the chairperson. The GAVI Alliance will not be liable to the country for any claim or loss relating to the programmes described in the application, including without limitation, any financial loss, reliance claims, any harm to property, or personal injury or death. Country is solely responsible for all aspects of managing and implementing the programmes described in its application.

# Application Specification

Please specify for which type of GAVI support you would like to apply to.

Important note: To enable proper functioning of the form, please first select the cMYP years on the previous page.

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Type of Support | Vaccine | Start Year | End Year | Preferred second presentation[1] | Action |
| --- | --- | --- | --- | --- | --- |
| New Vaccines Support | Rotavirus 3-dose schedule | 2012 | 2015 | Rotavirus 2-dose schedule |  |

[1] This "Preferred second presentation" will be used in case there is no supply available for the preferred presentation of the selected vaccine ("Vaccine" column). If left blank, it will be assumed that the country will prefer waiting until the selected vaccine becomes available.

# Table of Contents

Sections

Main

Cover Page

GAVI Alliance Grants Terms and Conditions

1. Application Specification

2. Table of Contents

3. Executive Summary

4. Signatures

4.1. Signatures of the Government and National Coordinating Bodies

4.1.1. Government and the Inter-Agency Coordinating Committee for Immunisation

4.1.2. National Coordinating Body - Inter-Agency Coordinating Committee for Immunisation

4.1.3. The Inter-Agency Coordinating Committee for Immunisation

4.2. National Immunization Technical Advisory Group for Immunisation

4.2.1. The NITAG Group for Immunisation

5. Immunisation Programme Data

5.1. Basic facts

5.2. Current vaccination schedule

5.3. Trends of immunisation coverage and disease burden

5.4. Baseline and Annual Targets

Table 1: baseline figures

5.5. Summary of current and future immunisation budget

5.6. Summary of current and future financing and sources of funds

6. NVS

6.1. Capacity and cost (for positive storage)

6.2. Assessment of burden of relevant diseases (if available)

6.3.1. Requested vaccine ( Rotavirus 3-dose schedule )

6.3.2. Co-financing information

6.3.3. Wastage factor

6.3.4. Specifications of vaccinations with new vaccine

6.3.5. Portion of supply to be procured by the country (and cost estimate, US$)

6.3.6. Portion of supply to be procured by the GAVI Alliance (and cost estimate, US$)

6.3.7. New and Under-Used Vaccine Introduction Grant

7. Procurement and Management of New and Under-Used Vaccines

7.1. Vaccine management (EVSM/EVM/VMA)

8. Additional Comments and Recommendations

9. Annexes

Annex 1

Annex 1.1 - Rotavirus 3-dose schedule

Table 1.1  A - Rounded up portion of supply that is procured by the country and estimate of related cost in US$

Table 1.1  B - Rounded up portion of supply that is procured by GAVI and estimate of related cost in US$.

Table 1.1  C - Summary table for vaccine Rotavirus 3-dose schedule

Table 1.1  D - Estimated number of doses for vaccine Rotavirus 3-dose schedule associated injection safety material and related co-financing budget

Annex 2

10. Attachments

10.1 Documents required for NVS support

10.2 Attachments

Banking Form

# Executive Summary

Rwandan EPI has a goal, the one to contribute to a better child survival by reducing the morbidity and the mortality among < 5 years old children due to immunization preventable diseases. 

Vaccine preventable diseases remain one of the leading causes of death among children < 5 years of age in Rwanda. In 2002, Rwanda put in place a paediatric bacterial meningitis surveillance (PBMS) site in one of the University teaching hospitals (Kigali). The same year, the National Immunization Program introduced the Haemophilus influenzae type b (Hib) and Hepatitis B (HepB) vaccines, combined to DTP vaccine (Pentavalent vaccine). 


In 2008, data from HIMS has shown that diarrheal diseases were the third leading cause of death among children under 5 years of age in Rwanda, after pneumonia and neonatal infections.

From September 2010 to April 2011, data from Kigali University teaching hospital laboratory has shown that, of the 43 stool samples collected from different sentinel centers, 13 cases were reported as positive for rotavirus (30%).

The Government of Rwanda (GOR) is fully committed to reach MDG 4 and 5 by 2015. For this reason, it takes all the available opportunities to reduce significantly the infant mortality rates. The GOR already contributes, with payment of vaccine and operational related costs. In fact, in 2007 and 2008, Government of Rwanda financed 24% and 25% of routine EPI vaccine costs respectively. In addition, GOR has committed and is effectively paying more than the GAVI minimum co-financing level for pentavalent vaccine and will continue to co-pay at this level for this vaccine. For pneumococcal conjugate vaccine, Rwanda started to co-finance at GAVI minimum level since 2010. 

WHO recommends the introduction of rotavirus vaccine in all national immunization programs in all regions, especially where immunization data can have a potential public health impact and where appropriate infrastructures and financing mechanisms are available to sustain the vaccine use.

Given the prevalence and the severity of diarrheal diseases in the country and the WHO recommendation which encourages all national EPI programs in all regions to introduce the rotavirus vaccine, the Government of Rwanda has decided, to take the opportunity of the availability of this life-saving vaccine and introduce it in its routine immunization program to protect the majority of children less than 1 year of age. 

In this context, GOR, with support of its traditional and new partners, requests assistance from Global Alliance for Vaccines and Immunization (GAVI Alliance) to introduce this life-saving vaccine, during the period of the revised cMYP cycle, in its National Immunization Program (NIP). If this proposal is approved and recommended to GAVI Secretariat by Independent Review Committee (IRC) and prioritized by GAVI board, Rwandan EPI will use its previous experience for new vaccine introduction from 2002 (pentavalent vaccine) and 2009 (pneumococcal vaccine) to maximize the chance of a smooth introduction, protect high proportion of infants and improve child survival situation in the country. 

Rwandan EPI experiences some major issues related to this application:

1. Decline of immunization coverage over time. In fact, from 2009 to 2010, immunization coverage has started to decline over time for all antigens. The introduction of rotavirus vaccine may not have the expected impact if the same immunization coverage trends continue. Given this situation, in August 2010, a joint team from the Ministry of health and WHO conducted a survey in 4 health districts located in the northern province where the immunization coverage was the lowest. The findings from the survey were as follows:

a. The proportion of under one year children was 2.6% (survey) instead of 4.1% used by the health management information system (HMIS);
b. The number of children < 1 years old was 31 588 (survey) instead of 53 336, estimated by HMIS ;
c. Pentavalent 3 vaccination coverage was 100% (survey) compared to the 66% reported by HMIS;

The conclusion from this survey showed that the denominator used to calculate the administrative coverage data was over estimated (4.1% of the total , obtained from the projection from the 2002 census, around 9 years after). The low proportion of children < 1 year of age (2.6% of the total population) is probably the result of the improvement of Family Planning indicators, specifically the coverage of the contraceptive method use which passed from 5% in 2002 to 51% in 2010.

2. Little likelihood for procurement of the additional cold chain equipment and their supply to districts and health facilities prior to the new vaccine target arrival date. Up to now, though the commitment from some partners to procure additional cold chain equipment to accommodate new vaccines planned to be introduce in 2011 and in 2012 (rotavirus and HPV vaccines), no purchase order has been made so far to expect the reception of those equipment prior to the new vaccine target arrival date. Advocacy meetings are being intensified through ICC to convince partners who have committed and to the new ones to do so before the end of this year. During the last ICC meeting held on 05 May 2011, Government of Rwanda and UNICEF have committed to fill the gap in cold chain equipments which was estimeted to be USD 424,578.

# Signatures

# Signatures of the Government and National Coordinating Bodies

# Government and the Inter-Agency Coordinating Committee for Immunisation

The Government of Rwanda would like to expand the existing partnership with the GAVI Alliance for the improvement of the infants routine immunisation programme of the country, and specifically hereby requests for GAVI support for Rotavirus 3-dose schedule introduction.

The Government of Rwanda commits itself to developing national immunisation services on a sustainable basis in accordance with the Comprehensive Multi-Year Plan (cMYP) presented with this document. The Government requests that the GAVI Alliance and its partners contribute financial and technical assistance to support immunisation of children as outlined in this application.

Tables 6.(n).5. (where (n) depends on the vaccine) in the NVS section of this application shows the amount of support in either supply or cash that is required from the GAVI Alliance. Tables 6.(n).4. of this application shows the Government financial commitment for the procurement of this new vaccine (NVS support only).

Following the regulations of the internal budgeting and financing cycles the Government will annually release its portion of the co-financing funds in the month of September .

Please note that this application will not be reviewed or approved by the Independent Review Committee (IRC) without the signatures of both the Minister of Health & Minister of Finance or their delegated authority.

Enter the family name in capital letters.

| Minister of Health (or delegated authority) |  | Minister of Finance (or delegated authority) |  |
| --- | --- | --- | --- |
| Name |  | Name |  |
| Date |  | Date |  |
| Signature |  | Signature |  |

This report has been compiled by

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

Enter the family name in capital letters.

| Full name | Position | Telephone | Email | Action |
| --- | --- | --- | --- | --- |
| Dr Fidele NGABO, MD,MSc | MCH/ EPI Coordinator | + 250 788 304 750 | ngabog@yahoo.fr |  |

# National Coordinating Body - Inter-Agency Coordinating Committee for Immunisation

We the members of the ICC, HSCC, or equivalent committee[1] met on the 05.05.2011 to review this proposal. At that meeting we endorsed this proposal on the basis of the supporting documentation which is attached.

[1] Inter-agency Coordinating Committee or Health Sector Coordinating Committee, or equivalent committee which has the authority to endorse this application in the country in question.

The endorsed minutes of this meeting are attached as DOCUMENT NUMBER: 11.

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

Enter the family name in capital letters.

| Name/Title | Agency/Organisation | Signature | Action |
| --- | --- | --- | --- |

In case the GAVI Secretariat has queries on this submission, please contact

Enter the family name in capital letters.

| Name | Dr Fidele NGABO | Title | MCH / EPI Coordinator |
| --- | --- | --- | --- |
| Tel no | +250 788 304750 |  |  |
| Fax no |  | Address | Ministry of Health MCH Department PO Box 84 Kigali, RWANDA |
| Email | ngabog@yahoo.fr |  |  |

# The Inter-Agency Coordinating Committee for Immunisation

Agencies and partners (including development partners and NGOs) supporting immunisation services are co-ordinated and organised through an inter-agency coordinating mechanism (ICC, HSCC, or equivalent committee). The ICC, HSCC, or equivalent committee is responsible for coordinating and guiding the use of the GAVI NVS support. Please provide information about the ICC, HSCC, or equivalent committee in your country in the table below.

Profile of the ICC, HSCC, or equivalent committee

| Name of the committee | ICC / HSCC |
| --- | --- |
| Year of constitution of the current committee | 1996 |
| Organisational structure (e.g., sub-committee, stand-alone) | Stand alone |
| Frequency of meetings | Quarterly |

Composition

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

Enter the family name in capital letters.

| Function | Title / Organisation | Name |  |
| --- | --- | --- | --- |
| Chair | Permanent Secretary / Ministry of Health | Dr Agnes BINAGWAHO |  |
| Secretary | EPI manager | Dr Fidele NGABO |  |
| Members | WHO Representative Rwanda | Dr Lamine CISSE SARR | Action |
|  | UNICEF Representative Rwanda | Dr Joseph FOUMBI |  |
|  | USAID-Mission Rwanda | Dr Dennis WELLER |  |
|  | Ministry of Finance (MOF) | Mr John RWANGOMBWA |  |
|  | MO/EPI, WHO | Dr Malifa BALDE |  |
|  | Rotary International | Dr Antoin MUYOMBANO |  |
|  | USAID Rwanda | Mr Eric KAGAME |  |
|  | MCHIP/USAID | Mr Jeremie ZOUNGRANA |  |
|  | RISP/JSI | Dr Mamadou DIALLO |  |
|  | UNICEF Rwanda | Dr Friday NWAIGWE |  |
|  | URUNANA DEVELOPMENT COMMUNICATION | Mr George GAHENDA |  |

Major functions and responsibilities of the committee

1. Share technical and financial information related to immunization services among partners 2. Coordinate and guide the use of GAVI and other partners'funds for immunization activities 3, Coordinate partners’ interventions to better support Immunization Program 4. Support technically and financially the national EPI in order to meet the target goals 5. Advocacy and resource mobilization to support EPI

Three major strategies to enhance the committee's role and functions in the next 12 months

| 1. | 1. The thematic working groups is in place to hold regular meetings on monthly basis to monitor the performance of the program |
| --- | --- |
| 2. | 2. The ICC, comprised of the Heads of Agencies and higher officials from MOH and MOF, has to meet on quarterly basis to evaluate the level of EPI plan implementation and to give orientation to improve the EPI performance |
| 3. | 3. The ICC has to strengthen internal and external advocacy for financial resources mobilization |

# National Immunization Technical Advisory Group for Immunisation

(If it has been established in the country)

We the members of the NITAG met on the to review this proposal. At that meeting we endorsed this proposal on the basis of the supporting documentation which is attached.

The endorsed minutes of this meeting are attached as DOCUMENT NUMBER: .

In case the GAVI Secretariat has queries on this submission, please contact

Enter the family name in capital letters.

| Name |  | Title |  |
| --- | --- | --- | --- |
| Tel no |  |  |  |
| Fax no |  | Address |  |
| Email |  |  |  |

# The NITAG Group for Immunisation

Profile of the NITAG

| Name of the NITAG |  |
| --- | --- |
| Year of constitution of the current NITAG |  |
| Organisational structure (e.g., sub-committee, stand-alone) |  |
| Frequency of meetings |  |

Composition

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

Enter the family name in capital letters.

| Function | Title / Organisation | Name |  |
| --- | --- | --- | --- |
| Chair |  |  |  |
| Secretary |  |  |  |
| Members |  |  | Action |

Major functions and responsibilities of the NITAG

Three major strategies to enhance the NITAG’s role and functions in the next 12 months

| 1. |  |
| --- | --- |
| 2. |  |
| 3. |  |

# Immunisation Programme Data

Please complete the tables below, using data from available sources. Please identify the source of the data, and the date. Where possible use the most recent data and attach the source document.

- Please refer to the Comprehensive Multi-Year Plan for Immunisation (cMYP) (or equivalent plan) and attach a complete copy (with an Executive Summary) as DOCUMENT NUMBER 2

- Please refer to the two most recent annual WHO/UNICEF Joint Reporting Forms (JRF) on Vaccine Preventable Diseases.

- Please refer to Health Sector Strategy documents, budgetary documents, and other reports, surveys etc, as appropriate.

# Basic facts

For the year 2010 (most recent; specify dates of data provided)

|  | Figure |  | Year | Source |
| --- | --- | --- | --- | --- |
| Total population | 9,981,415 |  | 2010 | Projection from 2002 census with pop growth rate of 2.6% |
| Infant mortality rate (per 1000) | 62 |  | 2008 | DHS |
| Surviving Infants[1] | 376,202 |  | 2010 | Projection |
| GNI per capita (US$) | 460 |  | 2009 | Word Bank |
| Total Health Expenditure (THE) as a percentage of GDP | 8.00 | % | 2010 | MOF |
| General government expenditure on health (GGHE) as % of General government expenditure | 12.00 | % | 2010 | MOF |

[1] Surviving infants = Infants surviving the first 12 months of life

Please provide some additional information on the planning and budgeting context in your country; also indicate the name and date of the relevant planning document for health

1) National Health Development Plan 2009-2012 2) cMYP 2011-2015 3) Annual EPI plan 2011 4) Rotavirus vaccine introduction plan 2011 5) Mid Term Expenditure Framework (MTEF) 6) Sector Wide Approach (SWAP) 7) Poverty Reduction Strategy Paper (PRSP II)

Is the cMYP (or updated Multi-Year Plan) aligned with this document (timing, content, etc.)?

Yes, cMYP 2008-2012 was updated in December 2010 to cMYP 2011-2015. Information for rotavirus vaccine and HPV vaccine have been incorporated

Please indicate the national planning budgeting cycle for health

National planning in Rwanda goes from July to June in the following year (this is for each year)

Please indicate the national planning cycle for immunisation

Immunization program follows the same planning cycle: from June to July of the next year (every year)

Please indicate if sex disaggregated data (SDD) is used in immunisation routine reporting systems

In the introduction of new vaccine, there is no sex differences, but in the existing reporting form for health information system, data are disaggregated by sex.

Please indicate if gender aspects relating to introduction of a new vaccine have been addressed in the introduction plan

In the introduction of new vaccine, there is no sex differences, but in the existing reporting form for health information system, data are disaggregated by sex.

# Current vaccination schedule

Traditional, New Vaccines and Vitamin A supplement (refer to cMYP pages)

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Vaccine (do not use trade name) | Ages of administration (by routine immunisation services) | Given in entire country | Comments | Action |
| --- | --- | --- | --- | --- |
| BCG | At birth | Yes | Up to 14 days after birth |  |
| Polio | At birth, 6 weeks, 10 weeks and 14 weeks | Yes | 4 weeks between dose 1 and 2, between dose 2 and 3 |  |
| DTP | 6 weeks, 10 weeks and 14 weeks | Yes | 4 weeks between the doses |  |
| HepB | 6 weeks, 10 weeks and 14 weeks | Yes | 4 weeks between doses |  |
| Hib | 6 weeks, 10 weeks and 14 weeks | Yes | 4 weeks between doses |  |
| Measles | 9 months | Yes |  |  |
| TT | first contact, 4 weeks after 1st dose, 6 months after the 2nd dose, one year after the 3rd dose and one year after the 4th dose | Yes | Pregnant women are targeted |  |
| Other: HPV | 1st dose at 1st contact, 2nd dose, two months after the first dose and 3rd dose 4 months after the 2nd dose | Yes | Agolescent girls 10-14 years old |  |
| PCV | 6 weeks, 10 weeks and 14 weeks | Yes | 4 weeks between doses |  |
| Vitamin A | Vitamin A is given to children from 9 months to 59 months | Yes | Vitamin A is supplemented during the MCHW, twice a year |  |

# Trends of immunisation coverage and disease burden

(as per last two annual WHO/UNICEF Joint Reporting Form on Vaccine Preventable Diseases)

| Trends of immunisation coverage (percentage) |  |  |  |  |  | Vaccine preventable disease burden |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Vaccine |  | Reported |  | Survey |  | Disease | Number of reported cases |  |
|  |  | 2009 | 2010 | 2003 | 2007 |  | 2009 | 2010 |
| BCG |  | 85 | 75 |  | 97 | Tuberculosis |  |  |
| DTP | DTP1 | 90 | 79 |  | 99 | Diphtheria |  |  |
|  | DTP3 | 90 | 80 |  | 97 | Pertussis |  |  |
| Polio 3 |  | 90 | 80 |  | 97 | Polio | 0 | 0 |
| Measles (first dose) |  | 93 | 82 |  | 96 | Measles | 4 | 107 |
| TT2+ (Pregnant women) |  | 59 | 58 |  | 34 | NN Tetanus | 0 | 0 |
| Hib3 |  | 90 | 80 |  |  | Hib[2] |  |  |
| Yellow Fever |  |  |  |  |  | Yellow fever |  |  |
| HepB3 |  | 90 | 80 |  |  | HepBsero-prevalence[1] |  |  |
| Vitamin A supplement Mothers (< 6 weeks post-delivery) |  |  |  |  |  |  |  |  |
| Vitamin A supplement Infants (>6 months) |  |  |  |  |  |  |  |  |

[1] If available

[2] Note: JRF asks for Hib meningitis

If survey data is included in the table above, please indicate the years the surveys were conducted, the full title and if available, the age groups the data refers to

The Immunization coverage survey (the WHO standard method was conducted in 2007. Children of 12-23 months old and mothers with children aged 0-11 months were targeted by this survey. The document is available.

# Baseline and Annual Targets

(refer to cMYP pages)

Table 1: baseline figures

| Number | Base Year | Baseline and Targets |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2010 | 2012 | 2013 | 2014 | 2015 |  |  |
| Total births | 401,068 | 420,288 | 431,215 | 442,427 | 453,930 |  |  |
| Total infants' deaths | 24,866 | 21,014 | 21,560 | 19,909 | 20,427 |  |  |
| Total surviving infants | 376,202 | 399,274 | 409,655 | 422,518 | 433,503 |  |  |
| Total pregnant women | 401,068 | 420,288 | 431,215 | 442,427 | 453,930 |  |  |
| Number of infants vaccinated (to be vaccinated) with BCG | 299,041 | 399,273 | 422,591 | 433,578 | 444,851 |  |  |
| BCG coverage (%)[1] | 75% | 95% | 98% | 98% | 98% |  |  |
| Number of infants vaccinated (to be vaccinated) with OPV3 | 299,157 | 375,317 | 393,268 | 414,067 | 424,833 |  |  |
| OPV3 coverage (%)[2] | 80% | 94% | 96% | 98% | 98% |  |  |
| Number of infants vaccinated (or to be vaccinated) with DTP1[3] | 297,709 | 382,823 | 401,133 | 422,348 | 433,330 |  |  |
| Number of infants vaccinated (to be vaccinated) with DTP3[3] | 300,242 | 375,317 | 393,268 | 414,067 | 424,833 |  |  |
| DTP3 coverage (%)[2] | 80% | 94% | 96% | 98% | 98% |  |  |
| Wastage[1] rate in base-year and planned thereafter for DTP (%) | 5% | 5% | 5% | 5% | 5% |  |  |
| Wastage[1] factor in base-year and planned thereafter for DTP | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 |  |  |
| Target population vaccinated with 1st dose of Rotavirus |  | 339,382 | 393,269 | 414,068 | 424,833 |  |  |
| Target population vaccinated with last dose of Rotavirus |  | 319,418 | 393,269 | 414,068 | 424,833 |  |  |
| Rotavirus coverage (%)[2] | 0% | 80% | 96% | 98% | 98% |  |  |
| Infants vaccinated (to be vaccinated) with 1st dose of Measles | 308,336 | 379,310 | 401,461 | 414,067 | 424,833 |  |  |
| Measles coverage (%)[2] | 82% | 95% | 98% | 98% | 98% |  |  |
| Pregnant women vaccinated with TT+ | 233,429 | 336,230 | 388,094 | 420,306 | 431,234 |  |  |
| TT+ coverage (%)[4] | 58% | 80% | 90% | 95% | 95% |  |  |
| Vit A supplement to mothers within 6 weeks from delivery |  |  |  |  |  |  |  |
| Vit A supplement to infants after 6 months |  |  |  |  |  |  |  |
| Annual DTP Drop-out rate[ ( DTP1 - DTP3 ) / DTP1 ] x 100[5] | -1% | 2% | 2% | 2% | 2% |  |  |

[1] Number of infants vaccinated out of total births

[2] Number of infants vaccinated out of total surviving infants

[3] Indicate total number of children vaccinated with either DTP alone or combined

[4] Number of pregnant women vaccinated with TT+ out of total pregnant women

[5] The formula to calculate a vaccine wastage rate (in percentage):[ ( A – B ) / A ] x 100. Whereby: A = the number of doses distributed for use according to the supply records with correction for stock balance at the end of the supply period; B = the number of vaccinations with the same vaccine in the same period.

# Summary of current and future immunisation budget

(or refer to cMYP pages)

|  | Estimated costs per annum in US$ (in thousand US$) |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Cost category | Base Year | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |  |
|  | 2010 | 2012 | 2013 | 2014 | 2015 |  |  |  |  |  |
| Routine Recurrent Cost |  |  |  |  |  |  |  |  |  |  |
| Vaccines (routine vaccines only) | 6,381 | 37,721 | 39,882 | 41,910 | 43,804 |  |  |  |  |  |
| Traditional vaccines | 291 | 572 | 625 | 663 | 692 |  |  |  |  |  |
| New and underused vaccines | 6,090 | 37,149 | 39,257 | 41,247 | 43,112 |  |  |  |  |  |
| Injection supplies | 191 | 357 | 380 | 401 | 421 |  |  |  |  |  |
| Personnel | 197 | 215 | 219 | 223 | 227 |  |  |  |  |  |
| Salaries of full-time NIP health workers (immunisation specific) | 160 | 176 | 179 | 183 | 186 |  |  |  |  |  |
| Per-diems for outreach vaccinators / mobile teams | 37 | 39 | 40 | 40 | 41 |  |  |  |  |  |
| Transportation | 154 | 165 | 168 | 155 | 158 |  |  |  |  |  |
| Maintenance and overheads | 88 | 62 | 62 | 63 | 66 |  |  |  |  |  |
| Training | 10 | 175 | 183 | 192 | 200 |  |  |  |  |  |
| Social mobilisation and IEC | 10 | 219 | 229 | 239 | 251 |  |  |  |  |  |
| Disease surveillance | 188 | 350 | 366 | 383 | 401 |  |  |  |  |  |
| Program management | 321 | 394 | 412 | 431 | 451 |  |  |  |  |  |
| Other |  |  |  |  |  |  |  |  |  |  |
| Subtotal Recurrent Costs | 7,540 | 39,658 | 41,901 | 43,997 | 45,979 |  |  |  |  |  |
| Routine Capital Costs |  |  |  |  |  |  |  |  |  |  |
| Vehicle | 22 | 30 | 31 | 8 | 8 |  |  |  |  |  |
| Cold chain equipment | 128 |  |  |  |  |  |  |  |  |  |
| Other capital equipment | 28 | 29 | 29 | 29 | 29 |  |  |  |  |  |
| Subtotal Capital Costs | 178 | 59 | 60 | 37 | 37 |  |  |  |  |  |
| Campaigns |  |  |  |  |  |  |  |  |  |  |
| Polio | 473 |  |  |  | 1,072 |  |  |  |  |  |
| Measles |  | 1,253 |  |  | 1,340 |  |  |  |  |  |
| Yellow Fever |  |  |  |  |  |  |  |  |  |  |
| MNT campaigns |  |  |  |  |  |  |  |  |  |  |
| Other campaigns |  |  |  |  |  |  |  |  |  |  |
| Subtotal Campaign Costs | 473 | 1,253 | 0 | 0 | 2,412 |  |  |  |  |  |
| GRAND TOTAL | 8,191 | 40,970 | 41,961 | 44,034 | 48,428 |  |  |  |  |  |

# Summary of current and future financing and sources of funds

Please list in the tables below the funding sources for each type of cost category (if known). Please try and indicate which immunisation program costs are covered from the Government budget, and which costs are covered by development partners (or the GAVI Alliance), and name the partners (or refer to cMYP).

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

|  |  | Estimated costs per annum in US$ (in thousand US$) |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Cost category | Funding source | Base Year | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |  |
|  |  | 2010 | 2012 | 2013 | 2014 | 2015 |  |  |  |  |  |
| Routine Recurrent Cost |  |  |  |  |  |  |  |  |  |  |  |
| Traditional vaccines | Government | 291 | 572 | 625 | 664 | 692 |  |  |  |  |  |
| New /Under use vaccines | Government and GAVI | 6,090 | 37,149 | 39,257 | 41,247 | 43,112 |  |  |  |  |  |
| Injection supplies | Government | 191 | 357 | 380 | 401 | 421 |  |  |  |  |  |
| Personnel | Government | 216 | 237 | 242 | 247 | 252 |  |  |  |  |  |
| Salaries | Government | 160 | 176 | 179 | 183 | 186 |  |  |  |  |  |
| Perdiems | Government & partners | 37 | 39 | 40 | 40 | 41 |  |  |  |  |  |
| Transportation | Government & partners | 154 | 165 | 168 | 155 | 158 |  |  |  |  |  |
| Maintenance and Overhead | Government | 88 | 62 | 62 | 63 | 66 |  |  |  |  |  |
| Training | Government & partners | 10 | 175 | 183 | 191 | 200 |  |  |  |  |  |
| IEC / Soc mobilization | UNICEF | 10 | 219 | 229 | 239 | 251 |  |  |  |  |  |
| Disease surveillance | WHO & Government | 188 | 350 | 366 | 383 | 401 |  |  |  |  |  |
| Program management | Government & partners | 321 | 394 | 412 | 431 | 451 |  |  |  |  |  |
| Routine Capital Costs |  |  |  |  |  |  |  |  |  |  |  |
| Vehicles | GAVI and government | 22 | 30 | 31 | 8 | 8 |  |  |  |  |  |
| Cold chain equipment | Government & GAVI | 128 |  |  |  |  |  |  |  |  |  |
| Other capital equipment | Government | 28 | 29 | 29 | 29 | 29 |  |  |  |  |  |
| Campaigns |  |  |  |  |  |  |  |  |  |  |  |
| Polio | WHO | 473 |  |  |  | 1,072 |  |  |  |  |  |
| Measles | Government and partners |  | 1,253 |  |  | 1,340 |  |  |  |  |  |
| GRAND TOTAL |  | 8,407 | 41,207 | 42,203 | 44,281 | 48,680 |  |  |  |  |  |

# New and Under-Used Vaccines (NVS)

Please summarise the cold chain capacity and readiness to accommodate new vaccines, stating how the cold chain expansion (if required) will be financed, and when it will be in place. Please indicate the additional cost, if capacity is not available and the source of funding to close the gap.

In 2007, Rwandan EPI, with support from WHO, conducted a cold chain and logistics assessment (VMA)and developed a plan for cold chain expansion to accommodate pneumococcal vaccine, planned and introduced in 2009. Taking into account the cold chain equipment received in 2009 and the switch of PCV7 vaccine presentation (in 2010 – from pre-filled syringes, to one single-dose vial, switch which liberated more space for additional new vaccine), Rwandan EPI started to plan the introduction of more new vaccines (HPV and rotavirus vaccine) to protect more people and achieve MDG 4 and 5 by year 2015. Because of the preparation of the introduction of HPV vaccine in 2011 and of the rotavirus vaccine in 2012, cold chain equipment inventory was updated (2010). WHO Forecasting Tool was used to assess cold chain storage capacity and vaccine stock management at different levels in order to accommodate both the two new vaccines. Findings from this assessment were as follows: a) At central level, no additional cold chain equipment was found to be in need. b) At the district level, out of 30 existing districts, 29 districts were in need of having additional cold chain equipment. In total 87 refrigerators (TCW 1152)were needed in 2012, of which 9 to be supplied in 2011 c) At health facility level, out of 426 existing health centers, 11 health centers were in need of 2 refrigerators each and 109 health centers of 1 refrigerators each (131 refrigerators in total). As in 2008, Government of Rwanda and some of its partners committed to procure additional cold chain equipments and fill the gap before the end of this year (2011). During the last ICC meeting held on 05 May 2011, Government of Rwanda and UNICEF have committed to fill the gap in cold chain equipments which was estimated to be USD 424,578.

Please give a summary of the cMYP sections that refer to the introduction of new and under-used vaccines. Outline the key points that informed the decision-making process (data considered etc)

Government of Rwanda is committed to achieve the MDG goals by the year 2015. For this reason, it takes all available opportunities to reduce mortality and morbidity among children less than 5 years of age. In fact, review of data from HIMS, in 2008, has demonstrated that diarrheal diseases were the third leading cause of child deaths in Rwanda, after pneumonia and neonatal infections. In addition, from December 2010 to April 2011, out of 43 stool samples obtained from patients with severe diarrhea who came at the lab of University teaching hospital of Kigali, about 30% of them (13 cases) were found infected with rotavirus strain. Given the fact that rotavirus remains the leading cause of severe diarrhea among children in the world, WHO has made a recommendation to all national EPI of all regions to introduce rotavirus vaccine already available. Rwanda has a long experience with new vaccine introduction process. For this reason, national EPI would like to use the opportunity of the available life-saving vaccine (rotavirus vaccine) and introduce it into the routine immunization program. Introduction plan, which defined key activities and budget was developed. Cold chain inventory conducted in 2007 was updated in 2010; vaccine stock management and cold storage capacity were assessed using the WHO logistics and planning tool. The gap for cold chain to accommodate new vaccine was identified. Key EPI partners were informed during the ICC meeting to obtain their commitment. As in 2008 for pneumococcal vaccine preparation, partners are committed to fill the gap before the introduction date. During the last ICC meeting held on 05 May 2011, Government of Rwanda and UNICEF have committed to fill the gap in cold chain equipments which was estimated to be USD 424,578.

# Capacity and cost (for positive storage)

|  |  | Formula | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| A | Annual positive volume requirement, including new vaccine (litres or m3) Litres | Sum-product of total vaccine doses multiplied by unit packed volume of the vaccine | 96,495 | 110,480 | 115,176 | 118,139 |  |  |  |  |
| B | Existing net positive cold chain capacity (litres or m3) Litres | # | 126,000 | 126,000 | 126,000 | 126,000 |  |  |  |  |
| C | Estimated minimum number of shipments per year required for the actual cold chain capacity | A / B | 1 | 1 | 1 | 1 |  |  |  |  |
| D | Number of consignments / shipments per year | Based on national vaccine shipment plan | 4 | 4 | 4 | 4 |  |  |  |  |
| E | Gap (if any) | ((A / D) - B) | -101,876 | -98,380 | -97,206 | -96,465 |  |  |  |  |
| F | Estimated additional cost of cold chain | US$ | 0 | 0 | 0 | 0 |  |  |  |  |

Please briefly describe how your country plans to move towards attaining financial sustainability for the new vaccines you intend to introduce, how the country will meet the co-financing payments, and any other issues regarding financial sustainability you have considered (refer to the cMYP)

a)GoR is already committed to pay for vaccination costs. All traditional vaccines are fully financed by the Government. For the Underused vaccine (pentavalent vaccine), Government pay more than the required minimum contribution from its regular budget. Given the fact that pneumococcal conjugate and rotavirus vaccines are expensive, advocacy toward the high political authorities should be reinforced so that Government will continue to pay and even to increase its contribution for vaccine costs; b)Country has already key partners involved in the immunization activities (GAVI, WHO, UNICEF, USAID, measles partners, etc.). However, those partners alone will not cover the gap of the total program costs. Country will need to look for and identify additional partners through effective advocacy; c)Regular coordination of partner’s contribution through ICC combined to transparency in resource management will be important.. During the last ICC meeting held on 05 May 2011, Government of Rwanda and UNICEF have committed to fill the gap in cold chain equipments which was estimated to be USD 424,578.

# Assessment of burden of relevant diseases (if available)

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Disease | Title of the assessment | Date | Results |  |
| --- | --- | --- | --- | --- |
| No assessment conducted |  |  |  |  |

If new or under-used vaccines have already been introduced in your country, please give details of the lessons learned from storage capacity, protection from accidental freezing, staff training, cold chain, logistics, drop-out rate, wastage rate etc., and suggest action points to address them

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Lessons Learned | Action Points |  |
| --- | --- | --- |
| 1. Cold chain expansion and management remains key areas to address for any new vaccine introduction 2. Planning cold chain storage, transport and vaccine handling are very important in order to minimize the wastage (vaccine damaged by heat and accident freezing for vaccines which can’t be frozen) | 1. Cold chain assessment was conducted to estimate needs for new vaccine introduction; 2. Government and one EPI partner (USAID) purchased additional EPI cold chain equipment; 3. Training of logisticians prior to distribution of new equipment was done. Additional cold chain equipment was procured, specific training of health workers on vaccine handling, conditioning ice packs before vaccine transportation and use of vaccine freezing monitor were undertaken |  |
| Training of health workers is another important area to consider while planning for new vaccine introduction | Technical support was provided to update training materials; Training of trainers conducted at central and district levels; Training of health workers at peripheral level using a phased approach |  |
| Development of key messages which address the concerns of parents and health workers can improve the acceptability of new vaccine | Focus group discussions were conducted in the community to identify concerns of parents with respect to new vaccine; Interviews with health workers conducted to assess their willingness to give two injections the same day during the same immunization session (one for penta and another for pneumococcal vaccine); Specific key messages developed, pre-tested and used |  |
| Revision of management tools used in immunization program is another area of interest | All management tools were revised and included new vaccine information; The revised management tools were printed and distributed to all health facility units; |  |
| Waste management and disposal for PCV7 (in its pre-filled glass syringe presentation) was a very specific area to address | Specific safety boxes, different from others, were ordered; High temperature incinerator was installed and health staff instructed to send used glass syringes to this incinerator |  |

Please list the vaccines to be introduced with support from the GAVI Alliance (and presentation)

Rotavirus vaccine, Rota Teq (R5), the oral no preservative vaccine will be introduced

# 6.3.1. Requested vaccine ( Rotavirus 3-dose schedule )

As reported in the cMYP, the country plans to introduce Rotavirus 3-dose schedule vaccine.

# 6.3.2. Co-financing information

If you would like to co-finance higher amount than minimum, please overwrite information in the “Your co-financing” row.

Note: Selection of this field has direct impact on automatic calculations of support you are requesting and should not be left empty.

| Country group | Low |
| --- | --- |

|  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| Minimum co-financing | 0.13 | 0.13 | 0.13 | 0.13 |  |  |  |  |
| Your co-financing (please change if higher) | 0.20 | 0.20 | 0.20 | 0.20 |  |  |  |  |

# 6.3.3. Wastage factor

Please indicate wastage rate:

Countries are expected to plan for a maximal wastage rate of:

- 50% - for a lyophilised vaccine in 10 or 20-dose vial,

- 25% - for a liquid vaccine in 10 or 20-dose vial or a lyophilised vaccine in 5-dose vial,

- 10% - for a lyophilised/liquid vaccine in 2-dose vial, and

- 5% - for a liquid vaccine in 1-dose vial

Note: Selection of this field has direct impact on automatic calculations of support you are requesting and should not be left empty.

|  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| Vaccine wastage rate in % | 5% | 5% | 5% | 5% |  |  |  |  |
| Equivalent wastage factor | 1.05 | 1.05 | 1.05 | 1.05 |  |  |  |  |

# 6.3.4. Specifications of vaccinations with new vaccine

|  | Data from |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| Number of children to be vaccinated with the first dose | Table 1 | # | 339,382 | 393,269 | 414,068 | 424,833 |  |  |  |  |
| Number of children to be vaccinated with the third dose[1] | Table 1 | # | 319,418 | 393,269 | 414,068 | 424,833 |  |  |  |  |
| Immunisation coverage with the third dose | Table 1 | # | 80.00% | 96.00% | 98.00% | 98.00% |  |  |  |  |
| Estimated vaccine wastage factor | Table 6.(n).3[3] | # | 1.05 | 1.05 | 1.05 | 1.05 |  |  |  |  |
| Country co-financing per dose[2] | Table 6.(n).2[3] | $ | 0.20 | 0.20 | 0.20 | 0.20 |  |  |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Total price per-dose includes vaccine cost, plus freight, supplies, insurance, visa costs etc.

[3] Where (n) depends on the vaccine

# 6.3.5. Portion of supply to be procured by the country (and cost estimate, US$)

|  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| Number of vaccine doses | # | 63,600 | 73,100 | 94,100 | 106,600 |  |  |  |  |
| Number of AD syringes | # |  |  |  |  |  |  |  |  |
| Number of re-constitution syringes | # |  |  |  |  |  |  |  |  |
| Number of safety boxes | # | 725 | 825 | 1,050 | 1,200 |  |  |  |  |
| Total value to be co-financed by country | $ | 267,500 | 256,500 | 264,500 | 269,500 |  |  |  |  |

# 6.3.6. Portion of supply to be procured by the GAVI Alliance (and cost estimate, US$)

|  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| Number of vaccine doses | # | 1,272,900 | 1,208,200 | 1,226,700 | 1,240,200 |  |  |  |  |
| Number of AD syringes | # |  |  |  |  |  |  |  |  |
| Number of re-constitution syringes | # |  |  |  |  |  |  |  |  |
| Number of safety boxes | # | 14,150 | 13,425 | 13,625 | 13,775 |  |  |  |  |
| Total value to be co-financed by GAVI | $ | 5,356,000 | 4,238,000 | 3,445,000 | 3,135,000 |  |  |  |  |

# 6.3.7. New and Under-Used Vaccine Introduction Grant

Please indicate in the tables below how the one-time Introduction Grant[1] will be used to support the costs of vaccine introduction and critical pre-introduction activities (refer to the cMYP).

Calculation of lump-sum for the Rotavirus 3-dose schedule

If the total is lower than US$100,000, it is automatically rounded up to US$100,000

| Year of New Vaccine Introduction | Births (from Table 1) | Share per Birth in US$ | Total in US$ |
| --- | --- | --- | --- |
| 2012 | 420,288 | 0.30 | 126,500 |

[1] The Grant will be based on a maximum award of $0.30 per infant in the birth cohort with a minimum starting grant award of $100,000

Cost (and finance) to introduce the Rotavirus 3-dose schedule (US$)

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Cost Category | Full needs for new vaccine introduction in US$ | Funded with new vaccine introduction grant in US$ |  |
| --- | --- | --- | --- |
| Training | 151,500 | 24,080 |  |
| Social Mobilization, IEC and Advocacy | 22,500 | 22,500 |  |
| Cold Chain Equipment & Maintenance | 424,579 | 0 |  |
| Vehicles and Transportation | 72,420 | 36,210 |  |
| Programme Management | 128,820 | 41,500 |  |
| Surveillance and Monitoring | 2,200 | 2,200 |  |
| Human Resources | 0 | 0 |  |
| Waste Management | 0 | 0 |  |
| Technical assistance | 3,500 | 0 |  |
| Totals | 805,519 | 126,490 |  |

# Procurement and Management of New and Under-Used Vaccines

Note: The PCV vaccine must be procured through UNICEF

- Please show how the support will operate and be managed including procurement of vaccines (GAVI expects that most countries will procure vaccine and injection supplies through UNICEF)

For vaccine and other supplies, UNICEF channels will be used as usual For one cash Grant, management will be done according to the GAVI principle through ICC.

- If an alternative mechanism for procurement and delivery of supply (financed by the country or the GAVI Alliance) is requested, please document

- Other vaccines or immunisation commodities procured by the country and descriptions of the mechanism used.

- The functions of the National Regulatory Authority (as evaluated by WHO) to show they comply with WHO requirements for procurement of vaccines and supply of assured quality.

N/A

- Please describe the introduction of the vaccines (refer to cMYP)

In 2002, Rwanda introduced successfully Hib and Hepatitis B vaccines combined to DTP vaccine (pentavalent). In 2009, the program introduced successfully the PCV7 vaccine. The introduction approaches used were, for one part, nation wide introduction approach (pentavalent vaccine) and for other part, a phased approach (for PCV7 vaccine, given the complexity of this vaccine presentation). From those experiences, the following key lessons were learned and will be used to improve the introduction of rotavirus vaccine in routine EPI program: - New vaccine introduction requires at least 12 months of preparation, a decentralized health system with well trained staff and responsible at the operational level; - New vaccine introduction requires always additional cold storage capacity to accommodate new vaccine. For this reason, a cold chain assessment was conducted, identified storage needs was addresses in the ICC meeting where partners and the government committed to to cover the gap. - New vaccine introduction requires a specific training for all health workers involved in the immunization activities at all levels. This training should take into account all the operational components of immunization services in order to improve the quality of service. - New vaccine introduction requires the development of key messages to address concerns of parents and of health workers with respect to the new vaccine and help them to accept the new vaccine. - Taking into account the high cost of new vaccines, good advocacy would be made to target the political authorities and potential donors.

- Please indicate how funds should be transferred by the GAVI Alliance (if applicable)

A Banking Account for GAVI support already exists at the Central Bank of Rwanda (BCR). GAVI Alliance will, as in the past, transfer funds directly to this Banking Account. Country accepts and agrees to the outlined GAVI terms and conditions in the application form.

- Please indicate how the co-financing amounts will be paid (and who is responsible for this)

Amount of fund for rotavirus vaccine co-financing for low income countries (case of Rwanda with GNI of 460) has been acknowledged by GAVI Alliance to Rwandan EPI / Ministry of Health, which is $0.20 per dose and fixed. Ministry of Health will instruct Ministry of Finance to transfer funds to UNICEF Copenhagen based on GAVI Alliance estimates (Government's resources).

- Please outline how coverage of the new vaccine will be monitored and reported (refer to cMYP)

a)All the current EPI management tools in use at different levels will be revised to incorporate specific information related to rotavirus vaccine, printed and be distributed to all levels. This will include: •Supports for data collection and reporting system (tally sheet, immunization register, monthly reporting forms, and immunization cards for infants, etc.) •Supports for surveillance information system for vaccine preventable diseases •Management supports for program resource management (Registers for vaccine stock management, and other printing forms, etc.). All old management tools will be removed and replaced by the new ones; all the health professionals will be trained on the use of the new management tools. National and district data base will also be updated. All the revised tools will be printed and distributed at all levels. b)Annually, data will be reported to GAVI Secretariat in MOH/WHO/UNICEF Joint Reporting Form c)Country will need to submit timely to GAVI the annual progress report (APR)

# Vaccine Management (EVSM/EVM/VMA)

When was the last Effective Vaccine Store Management (EVSM) conducted?   -

When was the last Effective Vaccine Management (EVM) or Vaccine Management Assessment (VMA) conducted? October  - 2007

- If your country conducted either EVSM, EVM, or VMA in the past three years, please attach relevant reports. (Document N°)

- A VMA report must be attached from those countries which have introduced a New and Underused Vaccine with GAVI support before 2008.

- Please note that EVSM and VMA tools have been replaced by an integrated Effective Vaccine Management (EVM) tool. The information on EVM tool can be found at http://www.who.int/immunization_delivery/systems_policy/logistics/en/index6.html

- For countries which conducted EVSM, VMA or EVM in the past, please report on activities carried out as part of either action plan or improvement plan prepared after the EVSM/VMA/EVM.

1. Cold chain equipments were procured and distributed to districts and health facilities 2. Logistics Officers for the districts were trained prior to the distribution of vaccines and of the cold chain equipments 3. Supervision of districts and health facilities.

- When is the next Effective Vaccine Management (EVM) Assessment planned? July   - 2011

- Under new guidelines, it will be mandatory for the countries to conduct an EVM prior to an application for introduction of new vaccine.

# Additional Comments and Recommendations

Comments and Recommendations from the National Coordinating Body (ICC/HSCC)

Refer the comments and recommendations of ICC meeting attached.

# Annexes

# Annex 1

# Annex 1.1 – Rotavirus 3-dose schedule

Table 1.1 A - Rounded up portion of supply that is procured by the country and estimate of related cost in US$

| Required supply item |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of vaccine doses | # | 63,600 | 73,100 | 94,100 | 106,600 |  |  |  |  |
| Number of AD syringes | # |  |  |  |  |  |  |  |  |
| Number of re-constitution syringes | # |  |  |  |  |  |  |  |  |
| Number of safety boxes | # | 725 | 825 | 1,050 | 1,200 |  |  |  |  |
| Total value to be co-financed by the country | $ | 267,500 | 256,500 | 264,500 | 269,500 |  |  |  |  |

Table 1.1  B - Rounded up portion of supply that is procured by GAVI and estimate of related cost in US$.

| Required supply item |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of vaccine doses | # | 1,272,900 | 1,208,200 | 1,226,700 | 1,240,200 |  |  |  |  |
| Number of AD syringes | # |  |  |  |  |  |  |  |  |
| Number of re-constitution syringes | # |  |  |  |  |  |  |  |  |
| Number of safety boxes | # | 14,150 | 13,425 | 13,625 | 13,775 |  |  |  |  |
| Total value to be co-financed by the country | $ | 5,356,000 | 4,238,000 | 3,445,000 | 3,135,000 |  |  |  |  |

Table 1.1  C - Summary table for Rotavirus 3-dose schedule

|  | Data from |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of Surviving infants | Table 1 | # | 399,274 | 409,655 | 422,518 | 433,503 |  |  |  |  |
| Number of children to be vaccinated with the third dose[1] | Table 1 | # | 319,418 | 393,269 | 414,068 | 424,833 |  |  |  |  |
| Immunisation coverage with the last dose | Table 1 | # | 80.00% | 96.00% | 98.00% | 98.00% |  |  |  |  |
| Number of children to be vaccinated with the first dose | Table 1 | # | 339,382 | 393,269 | 414,068 | 424,833 |  |  |  |  |
| Number of doses per child |  | # | 3 | 3 | 3 | 3 |  |  |  |  |
| Estimated vaccine wastage factor | Table 6.(n).3[2] | # | 1.05 | 1.05 | 1.05 | 1.05 |  |  |  |  |
| Number of doses per vial |  | # | 1 | 1 | 1 | 1 |  |  |  |  |
| AD syringes required |  | # | No | No | No | No |  |  |  |  |
| Reconstitution syringes required |  | # | No | No | No | No |  |  |  |  |
| Safety boxes required |  | # | Yes | Yes | Yes | Yes |  |  |  |  |
| Vaccine price per dose |  | $ | 4.000 | 3.333 | 2.667 | 2.400 |  |  |  |  |
| Country co-financing per dose | Table 6.(n).2[2] | $ | 0.20 | 0.20 | 0.20 | 0.20 |  |  |  |  |
| AD syringe price per unit |  | $ | 0.053 | 0.053 | 0.053 | 0.053 |  |  |  |  |
| Reconstitution syringe price per unit |  | $ |  |  |  |  |  |  |  |  |
| Safety box price per unit |  | $ | 0.640 | 0.640 | 0.640 | 0.640 |  |  |  |  |
| Freight cost as % of vaccines value |  | % | 5.00 | 5.00 | 5.00 | 5.00 |  |  |  |  |
| Freight cost as % of devices value |  | % | 10.00 | 10.00 | 10.00 | 10.00 |  |  |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Where (n) depends on the vaccine

# Table 1.1 D - Estimated number of doses for Rotavirus 3-dose schedule associated injection safety material and related co-financing budget (page 1)

|  |  | Formula | 2012 |  |  | 2013 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Total | Government | GAVI | Total | Government | GAVI |
| A | Country Co-finance |  | 4.75% |  |  | 5.70% |  |  |
| B | Number of children to be vaccinated with the first dose[1] | Table 1 (baseline & annual targets) | 339,382 | 16,132 | 323,250 | 393,269 | 22,425 | 370,844 |
| C | Number of doses per child | Vaccine parameter | 3 | 3 | 3 | 3 | 3 | 3 |
| D | Number of doses needed | B * C | 1,018,146 | 48,394 | 969,752 | 1,179,807 | 67,275 | 1,112,532 |
| E | Estimated vaccine wastage factor | Table 6.(n).3. in NVS section[2] | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 |
| F | Number of doses needed including wastage | D * E | 1,069,054 | 50,813 | 1,018,241 | 1,238,798 | 70,638 | 1,168,160 |
| G | Vaccines buffer stock | (F - F of previous year) * 0.25 | 267,264 | 12,704 | 254,560 | 42,436 | 2,420 | 40,016 |
| I | Total vaccine doses needed | F + G | 1,336,318 | 63,517 | 1,272,801 | 1,281,234 | 73,058 | 1,208,176 |
| J | Number of doses per vial | Vaccine parameter | 1 | 1 | 1 | 1 | 1 | 1 |
| K | Number of AD syringes (+ 10% wastage) needed | (D + G) * 1.11 |  |  |  |  |  |  |
| L | Reconstitution syringes (+ 10% wastage) needed | I / J * 1.11 |  |  |  |  |  |  |
| M | Total of safety boxes (+ 10% of extra need) needed | I / 100 x 1.11 | 14,834 | 706 | 14,128 | 14,222 | 811 | 13,411 |
| N | Cost of vaccines needed | I * vaccine price per dose | 5,345,272 | 254,065 | 5,091,207 | 4,270,353 | 243,501 | 4,026,852 |
| O | Cost of AD syringes needed | K * AD syringe price per unit |  |  |  |  |  |  |
| P | Cost of reconstitution syringes needed | L * reconstitution price per unit |  |  |  |  |  |  |
| Q | Cost of safety boxes needed | M * safety box price per unit | 9,494 | 452 | 9,042 | 9,103 | 520 | 8,583 |
| R | Freight cost for vaccines needed | N * freight cost as % of vaccines value | 267,264 | 12,704 | 254,560 | 213,518 | 12,176 | 201,342 |
| S | Freight cost for devices needed | (O + P + Q) * freight cost as % of devices value | 950 | 46 | 904 | 911 | 52 | 859 |
| T | Total fund needed | (N + O + P + Q + R + S) | 5,622,980 | 267,264 | 5,355,716 | 4,493,885 | 256,247 | 4,237,638 |
| U | Total country co-financing | I * country co-financing per dose | 267,264 |  |  | 256,247 |  |  |
| V | Country co-financing % of GAVI supported proportion | U / T | 4.75% |  |  | 5.70% |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Where (n) depends on the vaccine

# Table 1.1 D - Estimated number of doses for Rotavirus 3-dose schedule associated injection safety material and related co-financing budget (page 2)

|  |  | Formula | 2014 |  |  | 2015 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Total | Government | GAVI | Total | Government | GAVI |
| A | Country Co-finance |  | 7.12% |  |  | 7.91% |  |  |
| B | Number of children to be vaccinated with the first dose[1] | Table 1 (baseline & annual targets) | 414,068 | 29,491 | 384,577 | 424,833 | 33,613 | 391,220 |
| C | Number of doses per child | Vaccine parameter (schedule) | 3 | 3 | 3 | 3 | 3 | 3 |
| D | Number of doses needed | B * C | 1,242,204 | 88,471 | 1,153,733 | 1,274,499 | 100,839 | 1,173,660 |
| E | Estimated vaccine wastage factor | Table 6.(n).3. in NVS section[2] | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 |
| F | Number of doses needed including wastage | D * E | 1,304,315 | 92,895 | 1,211,420 | 1,338,224 | 105,881 | 1,232,343 |
| G | Vaccines buffer stock | (F - F of previous year) * 0.25 | 16,380 | 1,167 | 15,213 | 8,478 | 671 | 7,807 |
| I | Total vaccine doses needed | F + G | 1,320,695 | 94,062 | 1,226,633 | 1,346,702 | 106,551 | 1,240,151 |
| J | Number of doses per vial | Vaccine parameter | 1 | 1 | 1 | 1 | 1 | 1 |
| K | Number of AD syringes (+ 10% wastage) needed | (D + G) * 1.11 |  |  |  |  |  |  |
| L | Reconstitution syringes (+ 10% wastage) needed | I / J * 1.11 |  |  |  |  |  |  |
| M | Total of safety boxes (+ 10% of extra need) needed | I / 100 x 1.11 | 14,660 | 1,045 | 13,615 | 14,949 | 1,183 | 13,766 |
| N | Cost of vaccines needed | I * vaccine price per dose | 3,522,294 | 250,861 | 3,271,433 | 3,232,085 | 255,723 | 2,976,362 |
| O | Cost of AD syringes needed | K * AD syringe price per unit |  |  |  |  |  |  |
| P | Cost of reconstitution syringes needed | L * reconstitution price per unit |  |  |  |  |  |  |
| Q | Cost of safety boxes needed | M * safety box price per unit | 9,383 | 669 | 8,714 | 9,568 | 758 | 8,810 |
| R | Freight cost for vaccines needed | N * freight cost as % of vaccines value | 176,115 | 12,544 | 163,571 | 161,605 | 12,787 | 148,818 |
| S | Freight cost for devices needed | (O + P + Q) * freight cost as % of devices value | 939 | 67 | 872 | 957 | 76 | 881 |
| T | Total fund needed | (N + O + P + Q + R + S) | 3,708,731 | 264,139 | 3,444,592 | 3,404,215 | 269,341 | 3,134,874 |
| U | Total country co-financing | I * country co-financing per dose | 264,139 |  |  | 269,341 |  |  |
| V | Country co-financing % of GAVI supported proportion | U / T | 7.12% |  |  | 7.91% |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Where (n) depends on the vaccine

# Annex 2

Estimated prices of supply and related freight cost: 2011 from UNICEF Supply Division; 2012 onwards: GAVI Secretariat

Table A - Commodities Cost

| Vaccine | Presentation | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| AD syringe | 0 | 0.053 | 0.053 | 0.053 | 0.053 | 0.053 | 0.053 | 0.053 |
| DTP-HepB | 2 | 1.600 |  |  |  |  |  |  |
| DTP-HepB | 10 | 0.620 | 0.620 | 0.620 | 0.620 | 0.620 | 0.620 | 0.620 |
| DTP-HepB-Hib | WAP | 2.580 | 2.470 | 2.320 | 2.030 | 1.850 | 1.850 | 1.850 |
| DTP-HepB-Hib | WAP | 2.580 | 2.470 | 2.320 | 2.030 | 1.850 | 1.850 | 1.850 |
| DTP-HepB-Hib | WAP | 2.580 | 2.470 | 2.320 | 2.030 | 1.850 | 1.850 | 1.850 |
| DTP-Hib | 10 | 3.400 | 3.400 | 3.400 | 3.400 | 3.400 | 3.200 | 3.200 |
| HepB monoval | 1 |  |  |  |  |  |  |  |
| HepB monoval | 2 |  |  |  |  |  |  |  |
| Hib monoval | 1 | 3.400 |  |  |  |  |  |  |
| Measles | 10 | 0.240 | 0.240 | 0.240 | 0.240 | 0.240 | 0.240 | 0.240 |
| Pneumococcal(PCV10) | 2 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 |
| Pneumococcal(PCV13) | 1 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 |
| Reconstit syringe for Pentaval (2ml) | 0 | 0.032 | 0.032 | 0.032 | 0.032 | 0.032 | 0.032 | 0.032 |
| Reconstit syringe for YF | 0 | 0.038 | 0.038 | 0.038 | 0.038 | 0.038 | 0.038 | 0.038 |
| Rotavirus 2-dose schedule | 1 | 7.500 | 6.000 | 5.000 | 4.000 | 3.600 | 3.600 | 3.600 |
| Rotavirus 3-dose schedule | 1 | 5.500 | 4.000 | 3.333 | 2.667 | 2.400 | 2.400 | 2.400 |
| Safety box | 0 | 0.640 | 0.640 | 0.640 | 0.640 | 0.640 | 0.640 | 0.640 |
| Yellow Fever | WAP | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 |
| Yellow Fever | WAP | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 |

Note: WAP - weighted average price (to be used for any presentation: For DTP-HepB-Hib, it applies to 1 dose liquid, 2 dose lyophilised and 10 dose liquid. For Yellow Fever, it applies to 5 dose lyophilised and 10 dose lyophilised)

Table B - Commodities Freight Cost

| Vaccines | Group | No Threshold | 200’000 $ |  | 250’000 $ |  | 2’000’000 $ |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | <= | > | <= | > | <= | > |
| Yellow Fever | Yellow Fever |  | 20% |  |  |  | 10% | 5% |
| DTP+HepB | HepB and or Hib | 2% |  |  |  |  |  |  |
| DTP-HepB-Hib | HepB and or Hib |  |  |  | 15% | 3,50% |  |  |
| Pneumococcal vaccine (PCV10) | Pneumococcal | 5% |  |  |  |  |  |  |
| Pneumococcal vaccine (PCV13) | Pneumococcal | 5% |  |  |  |  |  |  |
| Rotavirus | Rotavirus | 5% |  |  |  |  |  |  |
| Measles | Measles | 10% |  |  |  |  |  |  |

Table C - Low - Minimum country's co-payment per dose of co-financed vaccine.

| vaccine | 2012 | 2013 | 2014 | 2015 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Rotavirus 3-dose schedule | 0.13 | 0.13 | 0.13 | 0.13 |  |  |  |

Table D - Wastage rates and factors

Countries are expected to plan for a maximal wastage rate of:

- 50% - for a lyophilised vaccine in 10 or 20-dose vial,

- 25% - for a liquid vaccine in 10 or 20-dose vial or a lyophilised vaccine in 5-dose vial,

- 10% - for a lyophilised/liquid vaccine in 2-dose vial, and

- 5% - for a liquid vaccine in 1-dose vial

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2 | 2.22 | 2.5 |

WHO International shipping guidelines: maximum packed volumes of vaccines

Table E - Vaccine maximum packed volumes

| Vaccine product | Designation | Vaccine formulation | Admin route | No. Of doses in the schedule | Presentation (doses/vial, prefilled) | Packed volume vaccine (cm3/dose) | Packed volume diluents (cm3/dose) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| BCG | BCG | lyophilized | ID | 1 | 20 | 1.2 | 0.7 |
| Diphtheria-Tetanus-Pertussis | DTP | liquid | IM | 3 | 20 | 2.5 |  |
| Diphtheria-Tetanus-Pertussis | DTP | liquid | IM | 3 | 10 | 3.0 |  |
| Diphtheria-Tetanus | DT | liquid | IM | 3 | 10 | 3.0 |  |
| Tetanus-Diphtheria | Td | liquid | IM | 2 | 10 | 3.0 |  |
| Tetanus Toxoid | TT | liquid | IM | 2 | 10 | 3.0 |  |
| Tetanus Toxoid | TT | liquid | IM | 2 | 20 | 2.5 |  |
| Tetanus Toxoid UniJect | TT | liquid | IM | 2 | Uniject | 12.0 |  |
| Measles | Measles | lyophilized | SC | 1 | 1 | 26.1 | 20.0 |
| Measles | Measles | lyophilized | SC | 1 | 2 | 13.1 | 13.1 |
| Measles | Measles | lyophilized | SC | 1 | 5 | 5.2 | 7.0 |
| Measles | Measles | lyophilized | SC | 1 | 10 | 3.5 | 4.0 |
| Measles-Rubella freeze dried | MR | lyophilized | SC | 1 | 1 | 26.1 | 26.1 |
| Measles-Rubella freeze dried | MR | lyophilized | SC | 1 | 2 | 13.1 | 13.1 |
| Measles-Rubella freeze dried | MR | lyophilized | SC | 1 | 5 | 5.2 | 7.0 |
| Measles-Rubella freeze dried | MR | lyophilized | SC | 1 | 10 | 2.5 | 4.0 |
| Measles-Mumps-Rubella freeze dried | MMR | lyophilized | SC | 1 | 1 | 26.1 | 26.1 |
| Measles-Mumps-Rubella freeze dried | MMR | lyophilized | SC | 1 | 2 | 13.1 | 13.1 |
| Measles-Mumps-Rubella freeze dried | MMR | lyophilized | SC | 1 | 5 | 5.2 | 7.0 |
| Measles-Mumps-Rubella freeze dried | MMR | lyophilized | SC | 1 | 10 | 3.0 | 4.0 |
| Polio | OPV | liquid | Oral | 4 | 10 | 2.0 |  |
| Polio | OPV | liquid | Oral | 4 | 20 | 1.0 |  |
| Yellow fever | YF | lyophilized | SC | 1 | 5 | 6.5 | 7.0 |
| Yellow fever | YF | lyophilized | SC | 1 | 10 | 2.5 | 3.0 |
| Yellow fever | YF | lyophilized | SC | 1 | 20 | 1.5 | 2.0 |
| Yellow fever | YF | lyophilized | SC | 1 | 50 | 0.7 | 1.0 |
| DTP-HepB combined | DTP-HepB | liquid | IM | 3 | 1 | 9.7 |  |
| DTP-HepB combined | DTP-HepB | liquid | IM | 3 | 2 | 6.0 |  |
| DTP-HepB combined | DTP-HepB | liquid | IM | 3 | 10 | 3.0 |  |
| Hepatitis B | HepB | liquid | IM | 3 | 1 | 18.0 |  |
| Hepatitis B | HepB | liquid | IM | 3 | 2 | 13.0 |  |
| Hepatitis B | HepB | liquid | IM | 3 | 6 | 4.5 |  |
| Hepatitis B | HepB | liquid | IM | 3 | 10 | 4.0 |  |
| Hepatitis B UniJect | HepB | liquid | IM | 3 | Uniject | 12.0 |  |
| Hib liquid | Hib_liq | liquid | IM | 3 | 1 | 15.0 |  |
| Hib liquid | Hib_liq | liquid | IM | 3 | 10 | 2.5 |  |
| Hib freeze-dried | Hib_lyo | lyophilized | IM | 3 | 1 | 13.0 | 35.0 |
| Hib freeze-dried | Hib_lyo | lyophilized | IM | 3 | 2 | 6.0 |  |
| Hib freeze-dried | Hib_lyo | lyophilized | IM | 3 | 10 | 2.5 | 3.0 |
| DTP liquid + Hib freeze-dried | DTP+Hib | liquid+lyop. | IM | 3 | 1 | 45.0 |  |
| DTP-Hib combined liquid | DTP+Hib | liquid+lyop. | IM | 3 | 10 | 12.0 |  |
| DTP-Hib combined liquid | DTP-Hib | liquid | IM | 3 | 1 | 32.3 |  |
| DTP-HepB liquid + Hib freeze-dried | DTP-Hib | liquid | IM | 3 | 10 | 2.5 |  |
| DTP-HepB liquid + Hib freeze-dried | DTP-HepB+Hib | liquid+lyop. | IM | 3 | 1 | 22.0 |  |
| DTP-HepB-Hib liquid | DTP-HepB+Hib | liquid+lyop. | IM | 3 | 2 | 11.0 |  |
| DTP-HepB-Hib liquid | DTP-HepB-Hib | liquid | IM | 3 | 10 | 4.4 |  |
| DTP-HepB-Hib liquid | DTP-HepB-Hib | liquid | IM | 3 | 2 | 13.1 |  |
| DTP-HepB-Hib liquid | DTP-HepB-Hib | liquid | IM | 3 | 1 | 19.2 |  |
| Meningitis A/C | MV_A/C | lyophilized | SC | 1 | 10 | 2.5 | 4.0 |
| Meningitis A/C | MV_A/C | lyophilized | SC | 1 | 50 | 1.5 | 3.0 |
| Meningococcal A/C/W/ | MV_A/C/W | lyophilized | SC | 1 | 50 | 1.5 | 3.0 |
| Meningococcal A/C/W/Y | MV_A/C/W/Y | lyophilized | SC | 1 | 10 | 2.5 | 4.0 |
| Meningitis W135 | MV_W135 | lyophilized | SC | 1 | 10 | 2.5 | 4.0 |
| Meningitis A conjugate | Men_A | lyophilized | SC | 2 | 10 | 2.6 | 4.0 |
| Japanese Encephalitis | JE_lyo | lyophilized | SC | 3 | 10 | 15.0 |  |
| Japanese Encephalitis | JE_lyo | lyophilized | SC | 3 | 10 | 8.1 | 8.1 |
| Japanese Encephalitis | JE_lyo | lyophilized | SC | 3 | 5 | 2.5 | 2.9 |
| Japanese Encephalitis | JE_lyo | lyophilized | SC | 3 | 1 | 12.6 | 11.5 |
| Japanese Encephalitis | JE_liq | liquid | SC | 3 | 10 | 3.4 |  |
| Rota vaccine | Rota_lyo | lyophilized | Oral | 2 | 1 | 156.0 |  |
| Rota vaccine | Rota_liq | liquid | Oral | 2 | 1 | 17.1 |  |
| Rota vaccine | Rota_liq | liquid | Oral | 3 | 1 | 45.9 |  |
| Pneumo. conjugate vaccine 7-valent | PCV-7 | liquid | IM | 3 | PFS | 55.9 |  |
| Pneumo. conjugate vaccine 7-valent | PCV-7 | liquid | IM | 3 | 1 | 21.0 |  |
| Pneumo. conjugate vaccine 10-valent | PCV-10 | liquid | IM | 3 | 1 | 11.5 |  |
| Pneumo. conjugate vaccine 10-valent | PCV-10 | liquid | IM | 3 | 2 | 4.8 |  |
| Pneumo. conjugate vaccine 13-valent | PCV-13 | liquid | IM | 3 | 1 | 12.0 |  |
| Polio inactivated | IPV | liquid | IM | 3 | PFS | 107.4 |  |
| Polio inactivated | IPV | liquid | IM | 3 | 10 | 2.5 |  |
| Polio inactivated | IPV | liquid | IM | 3 | 1 | 15.7 |  |
| Human Papilomavirus vaccine | HPV | liquid | IM | 3 | 1 | 15.0 |  |
| Human Papilomavirus vaccine | HPV | liquid | IM | 3 | 2 | 5.7 |  |
| Monovalent OPV-1 | mOPV1 | liquid | Oral |  | 20 | 1.5 |  |
| Monovalent OPV-3 | mOPV3 | liquid | Oral |  | 20 | 1.5 |  |

# Attachments

# List of Supporting Documents Attached to this Proposal

| Document | Section | Document Number | Mandatory[1] |
| --- | --- | --- | --- |
| MoH Signature (or delegated authority) of Proposal |  | 12 | Yes |
| MoF Signature (or delegated authority) of Proposal |  | 13 | Yes |
| Signatures of ICC or HSCC or equivalent in Proposal |  | 8 | Yes |
| Minutes of ICC/HSCC meeting endorsing Proposal |  | 9 | Yes |
| comprehensive Multi Year Plan - cMYP |  | 2 | Yes |
| cMYP Costing tool for financial analysis |  | 1 | Yes |
| Minutes of last three ICC/HSCC meetings |  | 10 | Yes |
| Improvement plan based on EVM |  | 11 | Yes |
| WHO/UNICEF Joint Reporting Form (JRF) |  | 3 |  |
| ICC/HSCC workplan for forthcoming 12 months |  |  |  |
| National policy on injection safety |  | 4 |  |
| Action plans for improving injection safety |  | 5 |  |
| Plan for NVS introduction (if not part of cMYP) |  | 6 |  |
| Banking details |  | 7 |  |

[1] Please indicate the duration of the plan / assessment / document where appropriate

# Attachments

List of all the mandatory and optional documents attached to this form

Note: Use the Upload file arrow icon to upload the document. Use the Delete item icon to delete a line. To add new lines click on the New item icon in the Action column.

| ID | File type | File name |  | New file | Actions |
| --- | --- | --- | --- | --- | --- |
|  | Description | Date and Time | Size |  |  |
| 1 | File Type: cMYP Costing tool for financial analysis * File Desc: File number 01 | File name: RWANDA-cMYP_Costing_Tool_Vs 2.5_En.xls Date/Time: 26.05.2011 05:36:39 Size: 3 MB |  |  |  |
| 2 | File Type: comprehensive Multi Year Plan - cMYP * File Desc: File number 02 | File name: cMYP_RWANDA 2011.doc Date/Time: 26.05.2011 05:39:06 Size: 711 KB |  |  |  |
| 3 | File Type: WHO/UNICEF Joint Reporting Form (JRF) File Desc: File number 03 | File name: RWANDA JRF_2010_AFRO_en-1.xls Date/Time: 26.05.2011 05:40:16 Size: 474 KB |  |  |  |
| 4 | File Type: National policy on injection safety File Desc: File number 04 | File name: IS&HCWM National Policy.pdf Date/Time: 26.05.2011 05:41:19 Size: 613 KB |  |  |  |
| 5 | File Type: Action plans for improving injection safety File Desc: File number 05 | File name: IS&HCWM National Policy.pdf Date/Time: 26.05.2011 05:42:31 Size: 613 KB |  |  |  |
| 6 | File Type: Plan for NVS introduction (if not part of cMYP) File Desc: File number 06 | File name: ROTAVIRUS VACCINE INTRODUCTION PLAN-RWANDA.doc Date/Time: 26.05.2011 05:46:32 Size: 5 MB |  |  |  |
| 7 | File Type: Banking details File Desc: File number 09 | File name: Banking form signed Docs.pdf Date/Time: 27.05.2011 07:20:50 Size: 922 KB |  |  |  |
| 8 | File Type: Signatures of ICC or HSCC or equivalent in Proposal * File Desc: File number 10 | File name: Rotavirus proposal signed docs.pdf Date/Time: 27.05.2011 07:24:51 Size: 1 MB |  |  |  |
| 9 | File Type: Minutes of ICC/HSCC meeting endorsing Proposal * File Desc: File number 11 | File name: May ICC Minutes 2011.pdf Date/Time: 31.05.2011 13:28:18 Size: 1 MB |  |  |  |
| 10 | File Type: Minutes of last three ICC/HSCC meetings * File Desc: File number 12 | File name: last 3 ICC minutes.zip Date/Time: 31.05.2011 13:31:44 Size: 4 MB |  |  |  |
| 11 | File Type: Improvement plan based on EVM * File Desc: File number 13 | File name: Rapport Evaluation Gestion GDBM-ISA-VMA Rwanda 13-25Oct07.doc Date/Time: 31.05.2011 14:02:38 Size: 2 MB |  |  |  |
| 12 | File Type: MoH Signature (or delegated authority) of Proposal * File Desc: | File name: ROTA Signatures.pdf Date/Time: 01.06.2011 11:27:22 Size: 1 MB |  |  |  |
| 13 | File Type: MoF Signature (or delegated authority) of Proposal * File Desc: | File name: ROTA Signatures.pdf Date/Time: 01.06.2011 11:32:37 Size: 1 MB |  |  |  |
| 14 | File Type: other File Desc: Justification for change in target | File name: Rwanda - Justification for downwards target.docx Date/Time: 17.06.2011 07:53:46 Size: 28 KB |  |  |  |