|  |  |  |  |  | [V2.7] |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| GAVI Alliance |  |  |  |  |  |  |  |
| Application Form for Country Proposals |  |  |  |  |  |  |  |
| For Support to: |  |  |  |  |  |  |  |
| Routine New Vaccines Support |  |  |  |  |  |  |  |
| Submitted by |  |  |  |  |  |  |  |
| The Government of |  |  |  |  |  |  |  |
| Uzbekistan |  |  |  |  |  |  |  |
| Date of submission: 8/31/2012 |  |  |  |  |  |  |  |
| Deadline for submission: 8/31/2012 |  |  |  |  |  |  |  |
| Select Start and End Year of your Comprehensive Multi-Year Plan (cMYP) |  |  |  |  |  |  |  |
| Start Year | 2011 |  |  |  |  |  |  |
|  |  |  | End Year | 2015 |  |  |  |
| Form revised in 2012 |  |  |  |  |  |  |  |
| (To be used with Guidelines of September 2012) |  |  |  |  |  |  |  |
| Please submit the Proposal using the online platform https://AppsPortal.gavialliance.org/PDExtranet |  |  |  |  |  |  |  |
| Enquiries to: proposals@gavialliance.org or representatives of a GAVI partner agency. The documents can be shared with GAVI partners, collaborators and general public. The Proposal and attachments must be submitted in English, French, Spanish, or Russian. Note: Please ensure that the application has been received by the GAVI Secretariat on or before the day of the deadline. The GAVI Secretariat is unable to return submitted documents and attachments to countries. Unless otherwise specified, documents will be shared with the GAVI Alliance partners and the general public. |  |  |  |  |  |  |  |

GAVI ALLIANCE GRANT TERMS AND CONDITIONS FUNDING USED SOLELY FOR APPROVED PROGRAMMES The applicant country ("Country") confirms that all funding provided by the GAVI Alliance will be used and applied for the sole purpose of fulfilling the programme(s) described in the Country's application. Any significant change from the approved programme(s) must be reviewed and approved in advance by the GAVI Alliance. All funding decisions for the application are made at the discretion of the GAVI Alliance Board and are subject to IRC processes and the availability of funds. AMENDMENT TO THE APPLICATION The Country will notify the GAVI Alliance in its Annual Progress Report if it wishes to propose any change to the programme(s) description in its application.The GAVI Alliance will document any change approved by the GAVI Alliance, and the Country's application will be amended. RETURN OF FUNDS The Country agrees to reimburse to the GAVI Alliance all funding amounts that are not used for the programme(s) described in its application. The country's reimbursement must be in US dollars and be provided, unless otherwise decided by the GAVI Alliance, within sixty (60) days after the Country receives the GAVI Alliance's request for a reimbursement and be paid to the account or accounts as directed by the GAVI Alliance. SUSPENSION/ TERMINATION The GAVI Alliance may suspend all or part of its funding to the Country if it has reason to suspect that funds have been used for purpose other than for the programmes described in the Country's application, or any GAVI Alliance-approved amendment to the application.The GAVI Alliance retains the right to terminate its support to the Country for the programmes described in its application if a misuse of GAVI Alliance funds is confirmed. ANTICORRUPTION The Country confirms that funds provided by the GAVI Alliance shall not be offered by the Country to any third person, nor will the Country seek in connection with its application any gift, payment or benefit directly or indirectly that could be construed as an illegal or corrupt practice. AUDITS AND RECORDS The Country will conduct annual financial audits, and share these with the GAVI Alliance, as requested. The GAVI Alliance reserves the right, on its own or through an agent, to perform audits or other financial management assessment to ensure the accountability of funds disbursed to the Country. The Country will maintain accurate accounting records documenting how GAVI Alliance funds are used. The Country will maintain its accounting records in accordance with its government-approved accounting standards for at least three years after the date of last disbursement of GAVI Alliance funds. If there is any claims of misuse of funds, Country will maintain such records until the audit findings are final. The Country agrees not to assert any documentary privilege against the GAVI Alliance in connection with any audit. CONFIRMATION OF LEGAL VALIDITY The Country and the signatories for the Country confirm that its application, and Annual Progress Report, are accurate and correct and form legally binding obligations on the Country, under the Country's law, to perform the programmes described in its application, as amended, if applicable, in the APR. CONFIRMATION OF COMPLIANCE WITH THE GAVI ALLIANCE TRANSPARANCY AND ACCOUNTABILITY POLICY The Country confirms that it is familiar with the GAVI Alliance Transparency and Accountability Policy (TAP) and complies with the requirements therein. USE OF COMMERCIAL BANK ACCOUNTS The Country is responsible for undertaking the necessary due diligence on all commercial banks used to manage GAVI cash-based support. The Country confirms that it will take all responsibility for replenishing GAVI cash support lost due to bank insolvency, fraud or any other unforeseen event. ARBITRATION Any dispute between the Country and the GAVI Alliance arising out of or relating to its application that is not settled amicably within a reasonable period of time, will be submitted to arbitration at the request of either the GAVI Alliance or the Country. The arbitration will be conducted in accordance with the then-current UNCITRAL Arbitration Rules. The parties agree to be bound by the arbitration award, as the final adjudication of any such dispute. The place of arbitration will be Geneva, Switzerland . The languages of the arbitration will be English or French. For any dispute for which the amount at issue is US$ 100,000 or less, there will be one arbitrator appointed by the GAVI Alliance. For any dispute for which the amount at issue is greater than US $100,000 there will be three arbitrators appointed as follows: The GAVI Alliance and the Country will each appoint one arbitrator, and the two arbitrators so appointed will jointly appoint a third arbitrator who shall be the chairperson. The GAVI Alliance will not be liable to the country for any claim or loss relating to the programmes described in the application, including without limitation, any financial loss, reliance claims, any harm to property, or personal injury or death. Country is solely responsible for all aspects of managing and implementing the programmes described in its application.

1. Application Specification Please specify for which type of GAVI support you would like to apply to.

Type of Support Vaccine Start Year End Year Preferred second presentation[1] Routine New Vaccines Support Rotavirus, 2 -dose schedule 2013 2015 Rotavirus, 3 -dose schedule

[1] This "Preferred second presentation" will be used in case there is no supply available for the preferred presentation of the selected vaccine ("Vaccine" column). If left blank, it will be assumed that the country will prefer waiting until the selected vaccine becomes available.

2. Table of Contents

1. Application Specification 2. Table of Contents 3. Executive Summary 4. Signatures 4.1. Signatures of the Government and National Coordinating Bodies 4.1.1. Government and the Inter-Agency Coordinating Committee for Immunisation 4.1.2. National Coordinating Body - Inter-Agency Coordinating Committee for Immunisation 4.1.3. The Inter-Agency Coordinating Committee for Immunisation 4.2. National Immunization Technical Advisory Group for Immunisation 4.2.1. The NITAG Group for Immunisation 5. Immunisation Programme Data 5.1. Basic facts 5.2. Baseline and Annual Targets (NVS Routine Support) 5.3. Baseline and Annual Targets for Preventive Campaign(s) 6. New and Under-Used Vaccines (NVS Routine) 6.1. Assessment of burden of relevant diseases (if available) 6.2 Requested vaccine (Rotavirus, 2 -dose schedule) 6.2.1 Co-financing information 6.2.2 Specifications of vaccinations with new vaccine 6.2.3 Portion of supply to be procured by the country (and cost estimate, US$) 6.2.4 Portion of supply to be procured by the GAVI Alliance (and cost estimate, US$) 6.2.5 New and Under-Used Vaccine Introduction Grant 7. NVS Preventive Campains 8. Procurement and Management 8.1. Procurement and Management of New and Under-Used Vaccines Routine 8.2. Procurement and Management for NVS Preventive Campaign(s) 8.3. Vaccine Management (EVSM/EVM/VMA) 9. Additional Comments and Recommendations from the National Coordinating Body (ICC/HSCC) 10. Attachments 11. Annexes Annex 1 - NVS Routine Support Annex 1.1 Rotavirus, 2 -dose schedule Table Annex 1.1 A Rounded up portion of supply that is procured by the country and estimate of relative costs in US$ Table Annex 1.1 B Rounded up portion of supply that is procured by GAVI and estimate of relative costs in US$ Table Annex 1.1 C Summary table for vaccine Rotavirus, 2 -dose schedule Table Annex 1.1 D Estimated numbers for Rotavirus, 2 -dose schedule, associated injection safety material and related co-financing budget (page 1) Annex 2 - NVS Routine – Preferred Second Presentation Annex 2.1 Rotavirus, 3 -dose schedule Table Annex 2.1 A Rounded up portion of supply that is procured by the country and estimate of relative costs in US$ Table Annex 2.1 B Rounded up portion of supply that is procured by GAVI and estimate of relative costs in US$ Table Annex 2.1 C Summary table for vaccine Rotavirus, 3 -dose schedule Table Annex 2.1 D Estimated numbers for Rotavirus, 3 -dose schedule, associated injection safety material and related co-financing budget (page 1) Annex 3 - NVS Preventive campaign(s) Annex 4 Table Annex 4A: Commodities Cost Table Annex 4B: Freight cost as percentage of value Table Annex 4C: Intermediate - Minimum country's co-payment per dose of co-financed vaccine. Table Annex 4D: Wastage rates and factors Table Annex 4E: Vaccine maximum packed volumes 12. Banking Form

3. Executive Summary

Please provide a summary of your country's proposal, including the following the information: l For each specific request, NVS routine support or NVS campaign : ¡ The duration of support ¡ The total amount of funds ¡ Details of the vaccine(s), if applicable l Relevant baseline data, including: ¡ DTP3 and Measles coverage data (as reported on the WHO/UNICEF Joint Reporting Form) ¡ Birth cohort, targets and immunisation coverage by vaccines l Country preparedness ¡ Summary of EVM assessment l The nature of stakeholders' participation in developing this proposal ¡ Inter-Agency Coordinating Committee The Republic of Uzbekistan applies for support in introduction of rotavirus vaccine into the routine immunization. The support is requested for the duration of the current cMYP until the end of 2015. Uzbekistan understands the current tight situation with availability of rotavirus vaccine on the international market. However, taking into account the high burden of the disease in the country and strong political support to rotavirus vaccine introduction and allocation of necessary funds into the NIP budget, the MoH would like to introduce rotavirus vaccine in June 2013 and requests the GAVI Secretariat to review Uzbekistan application at September 2012 IRCsession . This application was co-signed by the Minister of Health of the Republic of Uzbekistan and the Head of MOH Planning, Financing and Economic Department, who has the delegated authority from the Ministry of Finance. The application was reviewed by the newly established NITAG and approved by the ICC. Two-dose schedule rotavirus vaccine presentation is the one preferred by the country. Therefore, the total support requested isUS$8,546,500 for two and half years, and the country pledges co-financing in the amount of US$820,000. The total number of children benefited from this support will be 1,572,830. Uzbekistan is a low middle-income country (the World Bank) eligible for GAVI support (included in the intermediate group of countries) with the total population of 29,764,594 people as of 1 January 2012. Seventy percent of the population live in rural areas. The current birth cohort is 614.5 thousand births with tendency to increase. Uzbekistan has long standing traditions in the control of vaccine-preventable diseases. Good immunization reporting and disease surveillance systems are in place. Overall performance of national immunization programme is above satisfactory as indicated by continuous high immunization coverage, immediate and effective response to outbreaks, and great progress in reaching disease elimination and control objectives. AEFI surveillance system is established and functioning well. Immunization coverages for major antigens for children under 1 and under 2 years of age exceed 95% nationally and at province level (second administrative level) for the last 5 years. Only 2% of districts (the third administrative level) reported DTP3 coverage below 90% in 2011; the Reaching Every District activities are being implemented in low performing areas in 2012. The health reform project is progressing at levels, and currently the country is already in the third stage of health care reform implementation. There is a continuous increase in state funding for health as a result of sound economic and fiscal policies. During 2011-2012, significant progress was achieved by the national immunization programme in ensuring financial sustainability of vaccine supply: based on WHO assessments and recommendations, the procurement of EPI vaccines was centralized, agreement reached with the state finance authorities on full and timely disbursement of funds, and all procedures were optimized. The last stock-out of routine vaccine was reported in 2009. In preparation to the application for vaccine introduction, the Effective Vaccine Management assessment was carried out in May 2012, and the evidence-based plan to improve management, monitoring and supervision of the country immunization supply chain was developed. The country immediately started implementationof recommendations in the EVM improvement plan. The MoH has already started procurement of additional cold chainequipment to increase volume capacity of the National Vaccine Store. Later thisyear the MoH is going to purchase three cold rooms and refrigerators for the Nationaland three regional vaccine stores. The GAVI Introduction Grant and theGovermental funds will be utilized for this procurement. The cold chaincapacity of the country at national and regional levels will be sufficient toaccommodate rotavirus vaccine in June 2013 . Several studies were conducted in Uzbekistan to assess the rotavirus disease burden. The two-year sentinel surveillance project in two major urban areas found that one third of all hospitalizations for gastroenteritis and almost 5% of all deaths among children under 5 years of age in Uzbekistan may be attributable to rotavirus. The cost-effectiveness estimate suggested that the introduction of rotavirus vaccines into the national immunization program at the current subsidized prices could be very cost-effective. The 2011 study demonstrated that the rotavirus infection was dominant (31%) among all children’s diarrheal diseases, particularly in autumn season (34.5%). The most susceptible age group was children under two years (68%). All these studies are in line with the WHO rotavirus mortality estimates of 2008, according to which approximately 1100 children under 5 years of age die from rotavirus diarrhea in Uzbekistan every year. The rotavirus mortality rate is estimated at 41 cases per 100,000 children under 5 and rotavirus is responsible for 3.4% of all deaths in this age group. This proposal was developed with participation of all relevant stakeholders. The special Working Group was established at the Ministry of Health for compilation of necessary data and information; the proposal was thoroughly discussed at the meeting of the National Immunization Technical Advisory Group, and with NITAG’s recommendation were approved by the Inter-Agency Coordination Committee for Immunization.

| 4. Signatures |  |  |
| --- | --- | --- |
| 4.1. Signatures of the Government and National Coordinating Bodies |  |  |
| 4.1.1. Government and the Inter-Agency Coordinating Committee for Immunisation |  |  |
| The Government of Uzbekistan would like to expand the existing partnership with the GAVI Alliance for the improvement of the infants routine immunisation programme of the country, and specifically hereby requests for GAVI support for |  |  |
|  | Rotavirus, 1 dose(s) per vial, ORAL routine introduction |  |
| The Government of Uzbekistan commits itself to developing national immunisation services on a sustainable basis in accordance with the Comprehensive Multi-Year Plan presented with this document. The Government requests that the GAVI Alliance and its partners contribute financial and technical assistance to support immunisation of children as outlined in this application. |  |  |
| Table(s) 6.2.4 in the NVS Routine section of this application shows the amount of support in either supply or cash that is required from the GAVI Alliance. Table(s) 6.2.3 of this application shows the Government financial commitment for the procurement of this new vaccine (NVS support only). |  |  |
| Following the regulations of the internal budgeting and financing cycles the Government will annually release its portion of the co-financing funds in the month of March. |  |  |
| The payment for the first year of co-financed support will be around April 2013 for Rotavirus, 1 dose(s) per vial, ORAL. |  |  |
| Please note that this application will not be reviewed or approved by the Independent Review Committee (IRC) without the signatures of both the Minister of Health and Minister of Finance or their delegated authority. |  |  |
| Minister of Health (or delegated authority) Minister of Finance (or delegated authority) Name Prof. Anvar Alimov, Minister of Health Name Bakhtiyor Khashimov, Head of Economic, Financing and Forecasting Department Date Date Signature Signature |  |  |
| This report has been compiled by (these persons may be contacted in case the GAVI Secretatiat has queries on this document): |  |  |
| Full name Position Telephone Email Dilorom Tursunova NIP Manager, Lead Specialist, MOH +998712394721 dilorom.tursunova@minzdrav.uz |  |  |
| 4.1.2. National Coordinating Body - Inter-Agency Coordinating Committee for Immunisation |  |  |
| We the members of the ICC, HSCC, or equivalent committee [1] met on the 27/07/2012 to review this proposal. At that meeting we endorsed this proposal on the basis of the supporting documentation which is attached. |  |  |
| [1] Inter-agency Coordinating Committee or Health Sector Coordinating Committee, or equivalent committee which has the authority to endorse this application in the country in question. |  |  |
| The endorsed minutes of this meeting are attached as document number 4. |  |  |
| Name/Title* Agency/Organisation* Signature Akhmedova D., Director Institute of pediatrics Ambartsumova L., Head of department MOF Huseynov Sh., Technical Officer WHO Ismailov S., Head of MCH Department MOH Kim L., Head of Department RCSSES Musabaev E., Director Institute of Virology Safaeva K., Health Officer UNICEF Saidaliev S., Deputy Minister MOH Tajibaev G., Deputy Chief Doctor RCSSES Tursunova D., NIP Manager MOH Tuychiev L., Head of CDSES MOH Umirzakov B., Chief Doctor RCSSES Zadorozhnaya R., Head of Department MOE |  |  |
| 4.1.3. The Inter-Agency Coordinating Committee for Immunisation |  |  |
| Agencies and partners (including development partners and NGOs) supporting immunisation services are co-ordinated and organised through an inter-agency coordinating mechanism (ICC, HSCC, or equivalent committee). The ICC, HSCC, or equivalent committee is responsible for coordinating and guiding the use of the GAVI NVS routine support and/or campaign support. Please provide information about the ICC, HSCC, or equivalent committee in your country in the table below. |  |  |
| Profile of the ICC, HSCC, or equivalent committee |  |  |
| Name of the committee The Inter-Agency Coordination Committee on Immunization Year of constitution of the current committee 1999 Organisational structure (e.g., sub-committee, stand-alone) The ICC is a stand-alone committee under the MOH Frequency of meetings The ICC meets regularly quarterly and ad hoc when necessary |  |  |
| Composition |  |  |
| Function Title / Organisation Name Chair Deputy Minister of Health Saidaliev Saidmurad Secretary NIP Manager, MOH Tursunova Dilorom Members Head of CDSES Tuychiev Laziz Technical Officer, WHO Huseynov Shahin Health Officer, UNICEF Safaeva Kamola Director, Institute of Virology Musabaev Erkin Chief Doctor, RCSSES Umirzakov Bakhtiyor Deputy Chief Doctor, RCSSES Tajibaev Gafur Head of Immunization Department, RCSSES Kim Lyutsiya Head of MCH Department, MOH Ismailov Said Director, Institute of Pediatrics Akhmedova Dilorom Head of department, MOF Ambartsumova L. Head of Department, MOE Zadorozhnaya R |  |  |
| Major functions and responsibilities of the ICC/HSCC: |  |  |
| - Coordination of all matters related toimmunization and vaccine-preventable diseases in the Republic of Uzbekistan - Coordination and facilitation of National ImmunizationProgramme implementation; strengthening management of the NIP - Review of national EPI policy and strategies - Fostering partnership in immunization field and mobilization of resources |  |  |
| Three major strategies to enhance the committee's role and functions in the next 12 months |  |  |
| 1. Increase high-level commitment to immunizationprogramme through further advocacy and resource mobilization 2. Increase the role of ICC in health sector throughfurther collaboration with sectors beyond immunization, particularly healthsystems, health information, and health planning and financing. 3. Ensure regular information sharing and feedback of ICCto national authorities as well as to regional and district levels |  |  |
| 4.2. National Immunization Technical Advisory Group for Immunisation |  |  |
| (If it has been established in the country) |  |  |
| We the members of the NITAG met on the 27/07/2012 to review this proposal. At that meeting we endorsed this proposal on the basis of the supporting documentation which is attached. |  |  |
| The endorsed minutes of this meeting are attached as document number 4. |  |  |

4.2.1. The NITAG Group for Immunisation

Profile of the NITAG

Name of the NITAG National Immunization Technical Advisory Group Year of constitution of the current NITAG 2012 Organisational structure (e.g., sub-committee, stand-alone) stand-alone Frequency of meetings three times a year (planned)

Composition

Function Title / Organisation Name Chair Head of Department of pediatrics and infectious diseases, TMA Academician Daminov T.A. Secretary Lead Specialist of Chief Department of Sanitary Surveillance Tursunova D.A Members Head of Chief Department of Sanitary Surveillance Tuychiev L.N. Head of MCH Department Prof. Akhmedova D.I. Head of Finance Department Khashimov B.A Head of NRA Jalilov Kh.K Director of Institute of Immunology Prof. Aripova T.U Director of National AIDS Center Prof. Atabekov N.S Director of Institute of Virology Prof. Musabaev E.I Chief child infectionist of MOH Khudaykulova G.K. Chief pediatrician Prof. Jubatova R.S Chief phisiatrist Prof. Parpieva N.N Chief Epidemiologist Prof. Mamatkulov I.X Adviser, Institute of pediatrics Prof. Makhmudova D.I. Head of Immunization Department, Institute of pediatrics Khalilova G.M. Head of Child neurology department, TMA Prof Shomansurov Sh.Sh Head of Epidemiology department, TMA Umirov S.E.

Major functions and responsibilities of the NITAG

Advising the Ministry of Health of the Republic of Uzbekistan on - Policy analysis and strategy formulation for the control of vaccinepreventable diseases through immunization; - Monitoring of the National Immunization Programme performance, and collection and identification of important data for policy decisions; - Provision of the optimal scientific recommendations for the use of vaccines and control of vaccine preventable diseases (including immunization schedules) based on the particular circumstances of the country.

Three major strategies to enhance the NITAG's role and functions in the next 12 months

1. Ensure development and adoption of standard operating procedures for the NITAG and formalize reporting lines 2. Ensure reflecting NITAG activities in the annual NIP workplans 3. Ensure that theMOH requests NITAG's advice prior to making decisions on immunization policies and practices.

5. Immunisation Programme Data

5.1. Basic facts

Please complete the tables below, using data from available sources. Please identify the source of the data, and the date. Where possible use the most recent data and attach the source document.

▪ Please refer to the Comprehensive Multi-Year Plan for Immunisation (cMYP) (or equivalent plan) and attach a complete copy (with an Executive Summary) as DOCUMENT NUMBER : 6 ▪ Please attach relevant Vaccine Introduction Plans as DOCUMENT NUMBER : 7 ▪ Please refer to the two most recent annual WHO/UNICEF Joint Reporting Forms (JRF) on Vaccine Preventable Diseases ▪ Please refer to Health Sector Strategy documents, budgetary documents, and other reports, surveys etc, as appropriate.

For the year 2011 (most recent; specify dates of data provided)

Figure Year Source Total population 29,764,594 2011 State Statistics Committee Infant mortality rate (per 1000) 11 2011 State Statistics Committee Surviving infants[1] 604,030 2011 State Statistics Committee GNI per capita (US$) 800 2011 State Statistics Committee Total Health Expenditure (THE) as a percentage of GDP 3 % 2011 State Statistics Committee General government expenditure on health (GGHE) as % of General government expenditure 11 % 2011 State Statistics Committee

[1] Surviving infants = Infants surviving the first 12 months of life

Please provide some additional information on the planning and budgeting context in your country A comprehensive long-term planning document for health does not exist in Uzbekistan. The strategic objectives for health are defined by the Law on Health Protection of 1996, the Presidential Decrees of 1998 and 2002, and the President's Decree on "Further strengthening the Reforms of Health Care System" of 29 November 2011. Planning and budget allocation for health are done annually by the Ministry of Finance in coordination with MOH. Please indicate the name and date of the relevant planning document for health Currently, the strategic objectives for health are defined by the Presidential Decree of 2011 on Further strengthening the reforming of the health care. This is a directive document rather than multi-year planning; the actual financial planning is done by the MOH on annual basis. Several health programmes, including immunization and MCH, do have their own multi-year planning documents, which are revised annually based on the negotiation with the MoF and actual financial situation Is the CMYP (or updated Multi-Year Plan) aligned with the document (timing, content, etc.) The cMYP (for the period from 2011 until 2015) was endorsed in 2010. The document is fully aligned with the strategic objectives defined by the Presidential Decree and other national planning documents. Decision to introduce rotavirus vaccine with GAVI support in 2013 was elaborated in cMYP. The multi-year plan was revised and updated in 2011 and 2012 to accommodate new GAVI policy on co-financing. Please indicate the national planning budgeting cycle for health The MoH develops annual plan and budget andsubmits it to the MoF in September each year. After the MoF agreement the MoH budget is included into the State Budget and submitted to the Parlament forapproval. Please indicate the national planning cycle for immunisation The NIP develops its annual budget based on the cMYP. The NIP budget is an integrated part of the MoH budget for health and is submitted to and approved by the Parliament as a part of the State budget. After approval the MoF allocates funds to the MoH and the MoH allocates funds to NIP, including funds for procurement of vaccines, which are defined by the separate budget line. Until 2012, the budgetary allocations for vaccine procurement were done on quarterly basis. Since 2012, the MOH, supported by ICC, was able to ensure total annual disbursement of funds by the MOF in the beginning of each year to provide for sustainable implementation of immunization program. Please indicate if sex disaggregated data (SDD) is used in immunisation routine reporting systems National immunization routine reporting system does not use sex disaggregated data. Please indicate if gender aspects relating to introduction of a new vaccine have been addressed in the introduction plan In Uzbekistan, males and females have an equalaccess to immunization services and no significant differences in immunization coverage have been observed between girls and boys. Uzbekistan does not plan to introduce sex-disaggregated reporting in routine immunization Please describe any recent evidence of socio-economic and/or gender barriers to the immunisation programme through studies or surveys? The latest study that looked at socio-economic and gender differences in immunization status of children was Demography and Health Survey conducted in Uzbekistan in 1996. The survey did not reveal any differences in immunization status between boys and girls at the age between 12and 23 months. Around 86% males and 84% females have received specific vaccinations by the time of the survey. Country should provide an outline of all preparatory activities for vaccine(s) introduction 1. Revision of regulatorydocuments 2. Strengthening capacity of immunizationstaff 3. Improving vaccinemanagement and logistics 4. Strengthening the monitoring and supervision system 5. Strengthening surveillance 6. Advocacy and communication

| 5.2. Baseline and Annual Targets (NVS Routine Support) |  |
| --- | --- |
| Please refer to cMYP pages to assist in filling-in this section. |  |
| Number Base Year Baseline and Targets Baseline and Targets Baseline and Targets 2011 2013 2014 2015 Total births 614,472 667,211 674,550 681,970 Total infants’ deaths 14,168 40,033 40,473 40,918 Total surviving infants 600,304 627,178 634,077 641,052 Total pregnant women 675,920 733,932 742,005 750,167 Target population vaccinated with BCG 612,282 660,539 667,804 675,150 BCG coverage 100 % 99 % 99 % 99 % Target population vaccinated with OPV3 OPV3 coverage 100 % 99 % 99 % 99 % Number of infants vaccinated (to be vaccinated) with DTP1 592,464 620,906 627,736 634,641 Number of infants vaccinated (to be vaccinated) with DTP3 596,086 620,906 627,736 634,641 DTP3 coverage 99 % 99 % 99 % 99 % Wastage[1] rate in base-year and planned thereafter (%) for DTP 6 13 13 13 Wastage[1] factor in base-year and planned thereafter for DTP 1.06 1.15 1.15 1.15 Target population vaccinated with 1st dose of Rotavirus 1 310,453 627,736 634,641 Target population vaccinated with 2nd dose of Rotavirus 1 310,453 627,736 634,641 Rotavirus coverage 0 % 49 % 99 % 99 % First Presentation: Rotavirus, 2-dose schedule Wastage[1] rate in base-year and planned thereafter (%) 1 1 1 1 Wastage[1] factor in base-year and planned thereafter (%) 1.01 1.01 1.01 1.01 Maximum wastage rate value for Rotavirus, 2-dose schedule 5 % 5 % 5 % 5 % Second Presentation: Rotavirus, 3-dose schedule Wastage[1] rate in base-year and planned thereafter (%) 1 1 1 1 Wastage[1] factor in base-year and planned thereafter (%) 1.01 1.01 1.01 1.01 Maximum wastage rate value for Rotavirus, 3-dose schedule 5 % 5 % 5 % 5 % Target population vaccinated with 1st dose of Measles 603,300 620,906 627,736 634,641 Measles coverage 100 % 99 % 99 % 99 % Number of infants vaccinated (to be vaccinated) with 1st dose of TT+ 1 1 1 1 TT+ coverage 0 % 0 % 0 % 0 % Annual DTP Drop out rate [ ( DTP1 – DTP3 ) / DTP1 ] x 100 -1 % 0 % 0 % 0 % [1] Number of infants vaccinated out of total births [2] Number of infants vaccinated out of total surviving infants [3] Indicate total number of children vaccinated with either DTP alone or combined [4] Number of pregnant women vaccinated with TT+ out of total pregnant women [5] The formula to calculate a vaccine wastage rate (in percentage): [ ( A - B ) / A ] x 100. Whereby: A = the number of doses distributed for use according to the supply records with correction for stock balance at the end of the supply period; B = the number of vaccinations with the same vaccine in the same period. |  |

5.3. Baseline and Annual Targets for Preventive Campaign(s)

No NVS Prevention Campaign Support this year

6. New and Under-Used Vaccines (NVS Routine)

6.1. Assessment of burden of relevant diseases (if available)

Disease Title of the assessment Date Results Rotavirus Rotavirus disease in Uzbekistan: Cost-effectiveness of a new vaccine 2005 Disease burden was estimated using national statistics on hospitalizations and deaths, and international estimates of under-five mortality. Without vaccination, the risk for rotavirus hospitalization by age 5 is 10 per 1000 children. Rotavirus hospitalizations cost US$ 406,000 annually, of which US$ 360,000 (89%) is for medical expenses and US$ 46,000 (11%) is for non-medical and indirect costs. Rotavirus mortality rate at 0.7 per 1000 derived from national data was three-fold lower than the same rate calculated from international estimates of under-five mortality. Rotavirus vaccination could reduce hospitalizations and deaths by 91% and avert US$ 370,000 in hospitalization costs alone. Vaccination would be cost-effective with vaccine prices in a range of US$ 2–25 per child. However, the cost-effectiveness is greatly influenced by mortality, vaccine price and vaccine efficacy. Rotavirus Sentinel site surveillance project for rotavirus infection 2005 - 2006 One-third of all hospitalizations for gastroenteritis and almost 5% of all deaths among children age under 5 years in Uzbekistan may be attributable to rotavirus. Introduction of rotavirus vaccines into the national immunization program at the current subsidized prices could be cost-effective Rotavirus Epidemiological characteristics of rotavirus infection in children in Tashkent city 2011 Rotavirus infection is dominant (31%) among children’s diarrheal diseases, particularly in autumn season (34.5%). The most susceptible age group is children under two years (68%). 74.6% of rotavirus infection cases are admitted during 2nd-3rd days after onset of the disease, and in 60% cases the route of transmission is epidemiologically confirmed as fecal-oral. Rotavirus WHO Rotavirus mortality estimate 2008 Annually approximately 1100 children under 5 years of age die from rotavirus diarrhea in Uzbekistan. The rotavirus mortality rate is 41 cases per 100,000 children under 5 and rotavirus is responsible for 3.4% of all death in this age group

If new or under-used vaccines have already been introduced in your country, please give details of the lessons learned from previous introduction(s) specifically for: storage capacity, protection from accidental freezing, staff training, cold chain, logistics, coverage and drop-out rates, wastage rate, etc., and suggest action points to address them.

Lessons Learned Action Points Pentavalent vaccine introduction experience was positive. Structure of current immunization system ensured smooth introduction of vaccine, and it was well accepted by the population (high coverage and low drop-out rate) Differences between pentavalent vaccine and rotavirus vaccine will warrant special attention to certain areas of the immunization system, e.g. cold chain capacity, age restrictions for vaccine administration, oral administration Little to no knowledge about rotavirus disease and rotavirus vaccines at district and health facility level. Diarrheal diseases perceived as mild and seasonal. Plan and conduct training prior to vaccine introduction Ensure that guidelines and training materials are available in Uzbek language Establish a community awareness program with health education materials prior to vaccine introduction Multiple sources of immunization data available Potential discrepancies between different sources of data Existing mechanism for inspection visits are not used for supportive supervision Performance assessments limited to few indicators and does not include data review Strong relationships between healthcare workers and communities Various modes of communication exist that can be used to inform the community about rotavirus disease and vaccines Critically review reporting Form 6 and improve prior to vaccine introduction Ensure that updated form is distributed to provinces prior to introduction Provide training for staff at all levels on analysis and use of immunization data for performance monitoring

Please list the vaccines to be introduced with support from the GAVI Alliance (and presentation)

Vaccine of choice: Rotavirus vaccine, one-dose presentation, two-dose schedule. If the primary-choice presentation is not available or is unavailable in sufficient quantity, Uzbekistan is requesting Rotavirus vaccine, one-dose presentation, three-dose schedule as the second preference.

| 6.2. Requested vaccine (Rotavirus, 2 -dose schedule) As reported in the cMYP, the country plans to introduce Rotavirus, using Rotavirus, 2 -dose schedule. 6.2.1. Co-financing information If you would like to co-finance higher amount than minimum, please overwrite information in the Your co-financing row. Country group Intermediate Year 1 Year 2 Year 3 2013 2014 2015 Minimum co-financing 0.20 0.23 0.26 Your co-financing (please change if higher) 0.20 0.23 0.26 6.2.2. Specifications of vaccinations with new vaccine Data from Year 1 Year 2 Year 3 2013 2014 2015 Number of children to be vaccinated with the first dose Table 5.2 # 310,453 627,736 634,641 Number of children to be vaccinated with the second dose Table 5.2 # 310,453 627,736 634,641 Immunisation coverage with the second dose Table 5.2 # 49.50 % 99.00 % 99.00 % Country co-financing per dose [1] Table 6.2.1 $ 0.2 0.23 0.26 [1]Total price per-dose includes vaccine cost, plus freight, supplies, insurance, visa costs etc. |  |
| --- | --- |

6.2.3. Portion of supply to be procured by the country (and cost estimate, US$) 2013 2014 2015 Number of vaccine doses # 58,600 122,700 124,900 Number of AD syringes # 0 0 0 Number of re-constitution syringes # 0 0 0 Number of safety boxes # 0 0 0 Total value to be co-financed by country $ 157,000 328,500 334,500 6.2.4. Portion of supply to be procured by the GAVI Alliance (and cost estimate, US$) 2013 2014 2015 Number of vaccine doses # 725,400 1,305,600 1,160,700 Number of AD syringes # 0 0 0 Number of re-constitution syringes # 0 0 0 Number of safety boxes # 0 0 0 Total value to be co-financed by country $ 1,942,500 3,496,000 3,108,000

6.2.5. New and Under-Used Vaccine Introduction Grant Please indicate in the tables below the full costs/needs and how the one-time Introduction Grant [1] will be used to support the costs of vaccine introduction and critical pre-introduction activities (refer to the cMYP). GAVI’s support may not be enough to cover the full needs so please indicate in the table below how much and who will be complementing the funds needed Calculation of lump-sum for the Rotavirus, 2 -dose schedule Year of New Vaccine Introduction Births (from Table 5.2) Share per Birth in US$ Total in US$ 2013 667,211 0.80 533,769 [1] The Grant will be based on a maximum award of $0.80 per infant in the birth cohort with a minimum starting grant award of $100,000 Cost (and finance) to introduce the Rotavirus, 2 -dose schedule US$ Cost Category Full needs for new vaccine introduction in US$ Funded with GAVI introduction grant in US$ Training 80,000 62,000 Social Mobilization, IEC and advocacy 75,000 50,000 Cold Chain Equipment & Maintenance 1,000,000 293,769 Vehicles and Transportation 70,000 45,000 Programme Management 25,000 18,000 Surveillance and Monitoring 30,000 20,000 Human Resources 8,000 8,000 Waste Management 30,000 20,000 Technical Assistance 27,000 17,000 Other (please specify) Total 1,345,000 533,769 Please describe others sources of funding if available to cover your full needs The WHO Regional Office for Europe is going to contribute to Waste Management and Technical Assistance components. The relevant activities are included into the Regional Office Workplan for 2013. The Norwegian Institute of Public Health is going to contribute into Surveillance component to monitor an impact of rotavirus vaccine in Uzbekistan. Currently, negotiations with the Government of Japan facilitated by UNICEF are underway on provision of support to cold chain equipment procurement. If the negotiations yield the best expected result, the cold chain component of the GAVI grant may be reduced in favor of other components. The remaining cost of pre-introduction activities will be covered by the Government of Uzbekistan. The MOH included necessary funds in its 2012 and 2013 budgets that were approved as an integrated part of the MOH budgets for health.

7. NVS Preventive Campains

No NVS Prevention Campaign Support this year

8. Procurement and Management

8.1. Procurement and Management of New and Under-Used Vaccines Routine

Note: The PCV vaccine must be procured through UNICEF to be able to access the price awarded by the Advance Market Commitment (AMC).

a) Please show how the support will operate and be managed including procurement of vaccines (GAVI expects that most countries will procure vaccine and injection supplies through UNICEF): Since 2011, Uzbekistan resumed procurement of all vaccines included in the routine immunization calendar through UNICEF Supply Division. The Memorandum of Understanding between MOH and UNICEF on procurement of vaccines is current. The support for introduction of rotavirus vaccine will operate through the usual GAVI-UNICEF collaboration mechanisms. b) If an alternative mechanism for procurement and delivery of vaccine supply (financed by the country or the GAVI Alliance) is requested, please document l Other vaccines or immunisation commodities procured by the country and descriptions of the mechanism used. l The functions of the National Regulatory Authority (as evaluated by WHO) to show they comply with WHO requirements for procurement of vaccines and supply of assured quality. No alternative mechanism for procurement and delivery of vaccine isrequested. The current system of procuring routine vaccines through UNICEF is well-functioning and effective as proven by pentavalent vaccine support c) Please describe the introduction of the vaccines (refer to cMYP) The cMYP suggests introduction of rotavirus vaccine into National Immunization Calendar to reduce morbidity and mortality associated with rotavirus gastroenteritis. In order to achieve the high vaccination of infants within a year after introduction of vaccine with 2 doses of rotavirus vaccine, the following objectives are set: 1. Discussion at the meeting of National Immunization Technical Advisory Group for Immunisation 2. Decision of Working Group and approval by ICC. 3. Submission of the application to GAVI. 4. Update of the national immunization schedule and National Immunization Programme policy guidelines 5. Strengthening capacity of vaccination staff and medical professionals at all levels 6. Strengthening monitoring and supportive supervision from national and regional levels 7. Conducting wide public awareness campaign on the new vaccine 8. Surveillance for the disease and thorough monitoring of coverage 9. Improving cold chain management, injection safety, vaccine management systems 10.Update of immunizationforms and vaccination cards 11. Revision of AEFI monitoring system to accommodate rotavirus vaccine. 12. Coordination of activities with the Ministry of Finance and UNICEF d) Please indicate how funds should be transferred by the GAVI Alliance (if applicable) GAVI will pay directly to UNICEF for procurementof vaccines. GAVI funds to facilitate the introduction of Rota vaccine shouldbe transferred to MOH to the account indicated in this application. e) Please indicate how the co-financing amounts will be paid (and who is responsible for this) The co-financing amount will betransferred to UNICEF country office by the Ministry of Finance of Uzbekistanin coordination with the Ministry of Health. The Ministry of Health, the Republican Center for State Sanitary and Epidemiological Surveillance (RCSSES) and UNICEF Country Office will be responsible for money reaching the Supply Division. f) Please outline how coverage of the new vaccine will be monitored and reported (refer to cMYP) Monitoring of the coverage of rotavirus vaccine will be incorporated into routine coverage monitoring system. All vaccination points in Uzbekistan send monthly reports to the district level public health centers on number of doses of each vaccine included into the National Immunization Schedule administered to infants and young children by age. The aggregated data are then sent to the Regional and the National levels. These reports are used for on-going monitoring of immunization coverage. The data on number of doses administered to children under 1 year of age are used as nominator; the data on the number of children under 1 year of age obtained from the National Statistics are used as denominator. The medical personnel of vaccination points, the immunization personnel of district, regional and National public health centers estimate coverage monthly and implement correction measures in case of low coverage rates including supervisory visits. At the end of calendar year the vaccination points submit an annual report in the number of doses of vaccines administered to children under 1 year of age which is a summary of monthly reports revised and corrected if nessesary. The annual coverage estimate is reported to the MoH, Ministry of Statistics, and to WHO and UNICEF through the Joint Reporting Form on Immunization. The timeliness and completeness of monthly and annual reports at all levels is high. The NIP is confident that rotavirus vaccine can be accommodated into the existing reporting system after modification of reporting forms and databases. The existing system will allow on-going monitoring and annual estimate of coverage with two doses of rotavirus vaccine in children under 1 year of age.

8.2. Procurement and Management for NVS Preventive Campaign(s)

No NVS Prevention Campaign Support this year

8.3. Vaccine Management (EVSM/EVM/VMA)

Did the country have Effective Vaccine Management Assessment (VMA) in the past? No Did the country have Effective Vaccine Store Management (EVSM) in the past? Yes When was the last EVSM conducted? May 2008 Did the country have Effective Vaccine Management (EVM) in the past? Yes When was the EVM conducted? May 2012 If your country conducted either EVSM or VMA in the past two years, please attach relevant reports. (Document N°13) A VMA report must be attached from those countries which have introduced a New and Underused Vaccine with GAVI support before 2008. Please note that Effective Vaccine Store Management (EVSM) and Vaccine Management Assessment(VMA) tools have been replaced by an integrated Effective Vaccine Management (EVM) tool. The information on EVM tool can be found at http://www.who.int/immunization_delivery/systems_policy/logistics/en/index6.html For countries which conducted EVSM, VMA or EVM in the past, please report on activities carried out as part of either action plan or improvement plan prepared after the EVSM/VMA/EVM. The Ministry of Health positively accepted findings and recommendations of the EVM 2012 and started implementation immediately. Within a month after receipt of the improvement plan the following activities have been implemented: · - The MoH started process of procurement of additional cold room for the National Vaccine Store (30m3). The cold room will be supplied to the country and installed by November 2012 · - The MoH initiated procurement of additional freezer for the national Vaccine Store (20m3). The freezer will be supplied to the country and installed by November 2012. · - The NIP started procurement of two additional power generators, 18KWt each. The generators will be supplied to the country by November 2012 · - The NIP replaced generator exhaust pipe in the cold store at the National level and replaced fuses in the electric service panel. · - The NIP repaired refrigerator truck that is used to deliver vaccines from the national to regional levels and procured fire extinguishers. · - The monthly physical inventory system was established to improve the stock management The MoH plans to procure additional three cold rooms for the National Vaccine Store and five additional refrigerators for the regional vaccine stores in Kashkadaria, Surhandaria, and Tashkent provinces prior to introduction of rotavirus vaccine. The MoH allocated the state funds and is going to use funds from GAVI Introduction Grant for this procurement. Currently, negotiations with the Government of Japan facilitated by UNICEF are underway on provision of support to cold chain equipment procurement. If the negotiations yield the best expected result, the cold chain component of the GAVI grant may be reduced in favour of other components. Does the country plan to conduct an Effective Vaccine Management (EVM) Assessment in the future? No

9. Additional Comments and Recommendations from the National Coordinating Body (ICC/HSCC)

Comments and Recommendations from the National Coordinating Body (ICC/HSCC)

The ICC commends the Ministry of Health and the National Immunization Programme of Uzbekistan for significant progress in ensuring financial sustainability for vaccine supply in the past two years, solving underlying problems with stock-outs caused by insufficient procurement mechanisms, and implementation of WHO recommendations in optimizing immunization financing and improving disease surveillance and vaccination coverage. Establishment of NITAG in 2012 is an important step to assuring independent in-country technical advice on immunization policies and practices. The ICC fully supports the country's application for introduction of rotavirus vaccine into the routine immunization schedule with GAVI support.

10. Attachments

10.1. List of documents attached to this proposal

Document Number Document Section Mandatory File Signature of Minister.pdf 1 MoH Signature (or delegated authority) of Proposal File desc: Date/time: 8/29/2012 8:09:41 AM Size: 61789 Signature of Minister.pdf 2 MoF Signature (or delegated authority) of Proposal File desc: Date/time: 8/29/2012 8:10:01 AM Size: 61789 Signatures of ICC.pdf 3 Signatures of ICC or HSCC or equivalent in Proposal File desc: Date/time: 8/29/2012 8:10:24 AM Size: 165421 протокол ГАВИ 2012 год..doc 4 Minutes of ICC/HSCC meeting endorsing Proposal File desc: Date/time: 8/27/2012 4:38:55 AM Size: 73728 UZB_cMYP_2011-2015 - revised 01.08.12.doc 5 comprehensive Multi Year Plan - cMYP File desc: Date/time: 8/27/2012 4:30:34 AM Size: 2334208 UZB_cMYP_Scenario_A_revised 01.08.12.xls 6 cMYP Costing tool for financial analysis File desc: Date/time: 8/27/2012 4:35:12 AM Size: 3555840 Introduction Plan Rota UZB.doc 7 Plan for NVS introduction (if not part of cMYP) 5.1 File desc: Date/time: 8/31/2012 8:27:37 AM Size: 299008 EVM_improvement plan.doc 8 Improvement plan based on EVM File desc: Date/time: 8/27/2012 4:28:41 AM Size: 128000

11. Annexes

Annex 1 - NVS Routine Support

Annex 1.1 - NVS Routine Support (Rotavirus, 2 -dose schedule) Table Annex 1.1 A: Rounded up portion of supply that is procured by the country and estimate of relative costs in US$ 2013 2014 2015 Number of vaccine doses # 58,600 122,700 124,900 Number of AD syringes # 0 0 0 Number of re-constitution syringes # 0 0 0 Number of safety boxes # 0 0 0 Total value to be co-financed by country $ 157,000 328,500 334,500 Table Annex 1.1 B: Rounded up portion of supply that is procured by GAVI and estimate of relative costs in US$ 2013 2014 2015 Number of vaccine doses # 725,400 1,305,600 1,160,700 Number of AD syringes # 0 0 0 Number of re-constitution syringes # 0 0 0 Number of safety boxes # 0 0 0 Total value to be co-financed by country $ 1,942,500 3,496,000 3,108,000

Table Annex 1.1 C: Summary table for vaccine Rotavirus, 2 -dose schedule ID Data from 2013 2014 2015 Number of surviving infants Table 5.2 # 627,178 634,077 641,052 Number of children to be vaccinated with the first dose Table 5.2 # 310,453 627,736 634,641 Number of children to be vaccinated with the second dose Table 5.2 # 310,453 627,736 634,641 Immunisation coverage with the second dose Table 5.2 % 49.00 % 99.00 % 99.00 % Number of doses per child Parameter # 2 2 2 Estimated vaccine wastage factor Table 5.2 # 1.01 1.01 1.01 Number of doses per vial Parameter # 1 1 1 AD syringes required Parameter # No No No Reconstitution syringes required Parameter # No No No Safety boxes required Parameter # No No No g Vaccine price per dose Table Annexes 4A $ 2.55 2.55 2.55 cc Country co-financing per dose Table 6.4.1 $ 0.2 0.23 0.26 ca AD syringe price per unit Table Annexes 4A $ 0.0465 0.0465 0.0465 cr Reconstitution syringe price per unit Table Annexes 4A $ 0 0 0 cs Safety box price per unit Table Annexes 4A $ 0.0058 0.0058 0.0058 fv Freight cost as % of vaccines value Table Annexes 4B % 5.00 % 5.00 % 5.00 % fd Freight cost as % of devices value Parameter % 10.00 % 10.00 % 10.00 %

Table Annex 1.1 D: Estimated numbers for Rotavirus, 2 -dose schedule, associated injection safety material and related co-financing budget (page 1) Formula 2013 Total Government GAVI A Country co-finance 7.47 % B Number of children to be vaccinated with the first dose Table 1 310,453 23,190 287,263 C Number of doses per child Vaccine parameter (schedule) 2.00 D Number of doses needed B x C 620,906 46,380 574,526 E Estimated vaccine wastage factor Wastage factor table 1.01 F Number of doses needed including wastage D x E 627,116 46,844 580,272 G Vaccines buffer stock (F – F of previous year) * 0.25 156,779 11,711 145,068 I Total vaccine doses needed F + G 783,895 58,555 725,340 J Number of doses per vial Vaccine parameter 1.00 K Number of AD syringes (+ 10% wastage) needed (D + G) x 1.11 0 0 0 L Reconstitution syringes (+ 10% wastage) needed I / J * 1.11 0 0 0 M Total of safety boxes (+ 10% of extra need) needed (K + L) /100 * 1.11 0 0 0 N Cost of vaccines needed I x g 1,998,933 149,314 1,849,619 O Cost of AD syringes needed K x ca 0 0 0 P Cost of reconstitution syringes needed L x cr 0 0 0 Q Cost of safety boxes needed M x cs 0.00 0 0 R Freight cost for vaccines needed N x fv 99,947 7,466 92,481 S Freight cost for devices needed (O+P+Q) x fd 0 0 0 T Total fund needed (N+O+P+Q+R+S) 2,098,880 156,779 1,942,101 U Total country co-financing I 3 cc 156,779 V Country co-financing % of GAVI supported proportion U / T 7.47 % Table Annex 1.1 D: Estimated numbers for Rotavirus, 2 -dose schedule, associated injection safety material and related co-financing budget (page 2) Formula 2014 Total Government GAVI A Country co-finance 8.59 % B Number of children to be vaccinated with the first dose Table 1 627,736 53,924 573,812 C Number of doses per child Vaccine parameter (schedule) 2.00 D Number of doses needed B x C 1,255,472 107,847 1,147,625 E Estimated vaccine wastage factor Wastage factor table 1.01 F Number of doses needed including wastage D x E 1,268,027 108,925 1,159,102 G Vaccines buffer stock (F – F of previous year) * 0.25 160,228 13,764 146,464 I Total vaccine doses needed F + G 1,428,255 122,689 1,305,566 J Number of doses per vial Vaccine parameter 1.00 K Number of AD syringes (+ 10% wastage) needed (D + G) x 1.11 0 0 0 L Reconstitution syringes (+ 10% wastage) needed I / J * 1.11 0 0 0 M Total of safety boxes (+ 10% of extra need) needed (K + L) /100 * 1.11 0 0 0 N Cost of vaccines needed I x g 3,642,051 312,857 3,329,194 O Cost of AD syringes needed K x ca 0 0 0 P Cost of reconstitution syringes needed L x cr 0 0 0 Q Cost of safety boxes needed M x cs 0.00 0 0 R Freight cost for vaccines needed N x fv 182,103 15,643 166,460 S Freight cost for devices needed (O+P+Q) x fd 0 0 0 T Total fund needed (N+O+P+Q+R+S) 3,824,154 328,499 3,495,655 U Total country co-financing I 3 cc 328,499 V Country co-financing % of GAVI supported proportion U / T 8.59 % Table Annex 1.1 D: Estimated numbers for Rotavirus, 2 -dose schedule, associated injection safety material and related co-financing budget (page 3) Formula 2015 Total Government GAVI A Country co-finance 9.71 % B Number of children to be vaccinated with the first dose Table 1 634,641 61,628 573,013 C Number of doses per child Vaccine parameter (schedule) 2.00 D Number of doses needed B x C 1,269,282 123,255 1,146,027 E Estimated vaccine wastage factor Wastage factor table 1.01 F Number of doses needed including wastage D x E 1,281,975 124,488 1,157,487 G Vaccines buffer stock (F – F of previous year) * 0.25 3,487 339 3,148 I Total vaccine doses needed F + G 1,285,462 124,826 1,160,636 J Number of doses per vial Vaccine parameter 1.00 K Number of AD syringes (+ 10% wastage) needed (D + G) x 1.11 0 0 0 L Reconstitution syringes (+ 10% wastage) needed I / J * 1.11 0 0 0 M Total of safety boxes (+ 10% of extra need) needed (K + L) /100 * 1.11 0 0 0 N Cost of vaccines needed I x g 3,277,929 318,306 2,959,623 O Cost of AD syringes needed K x ca 0 0 0 P Cost of reconstitution syringes needed L x cr 0 0 0 Q Cost of safety boxes needed M x cs 0.00 0 0 R Freight cost for vaccines needed N x fv 163,897 15,916 147,981 S Freight cost for devices needed (O+P+Q) x fd 0 0 0 T Total fund needed (N+O+P+Q+R+S) 3,441,826 334,221 3,107,605 U Total country co-financing I 3 cc 334,221 V Country co-financing % of GAVI supported proportion U / T 9.71 %

Annex 2 - NVS Routine – Preferred Second Presentation

Annex 2.1 - NVS Routine Support (Rotavirus, 3 -dose schedule) Table Annex 2.1 A: Rounded up portion of supply that is procured by the country and estimate of relative costs in US$ 2013 2014 2015 Number of vaccine doses # 58,600 122,700 124,900 Number of AD syringes # 0 0 0 Number of re-constitution syringes # 0 0 0 Number of safety boxes # 0 0 0 Total value to be co-financed by country $ 157,000 328,500 334,500

Table Annex 2.1 B: Rounded up portion of supply that is procured by GAVI and estimate of relative costs in US$ 2013 2014 2015 Number of vaccine doses # 725,400 1,305,600 1,160,700 Number of AD syringes # 0 0 0 Number of re-constitution syringes # 0 0 0 Number of safety boxes # 0 0 0 Total value to be co-financed by country $ 1,942,500 3,496,000 3,108,000

Table Annex 2.1 C: Summary table for vaccine Rotavirus, 3 -dose schedule ID Data from 2013 2014 2015 Number of surviving infants Table 5.2 # 627,178 634,077 641,052 Number of children to be vaccinated with the first dose Table 5.2 # 310,453 627,736 634,641 Number of children to be vaccinated with the third dose Table 5.2 # 310,453 627,736 634,641 Immunisation coverage with the third dose Table 5.2 % 49.00 % 99.00 % 99.00 % Number of doses per child Parameter # 3 3 3 Estimated vaccine wastage factor Table 5.2 # 1.01 1.01 1.01 Number of doses per vial Parameter # 1 1 1 AD syringes required Parameter # No No No Reconstitution syringes required Parameter # No No No Safety boxes required Parameter # No No No g Vaccine price per dose Table Annexes 4A $ 3.5 3.5 3.5 cc Country co-financing per dose Table 6.4.1 $ 0.2 0.23 0.26 ca AD syringe price per unit Table Annexes 4A $ 0.0465 0.0465 0.0465 cr Reconstitution syringe price per unit Table Annexes 4A $ 0 0 0 cs Safety box price per unit Table Annexes 4A $ 0.0058 0.0058 0.0058 fv Freight cost as % of vaccines value Table Annexes 4B % 5.00 % 5.00 % 5.00 % fd Freight cost as % of devices value Parameter % 10.00 % 10.00 % 10.00 %

Table Annex 2.1 D: Estimated numbers for Rotavirus, 3 -dose schedule, associated injection safety material and related co-financing budget (page 1) Formula 2013 Total Government GAVI A Country co-finance 7.47 % B Number of children to be vaccinated with the first dose Table 1 310,453 23,190 287,263 C Number of doses per child Vaccine parameter (schedule) 2.00 D Number of doses needed B x C 620,906 46,380 574,526 E Estimated vaccine wastage factor Wastage factor table 1.01 F Number of doses needed including wastage D x E 627,116 46,844 580,272 G Vaccines buffer stock (F – F of previous year) * 0.25 156,779 11,711 145,068 I Total vaccine doses needed F + G 783,895 58,555 725,340 J Number of doses per vial Vaccine parameter 1.00 K Number of AD syringes (+ 10% wastage) needed (D + G) x 1.11 0 0 0 L Reconstitution syringes (+ 10% wastage) needed I / J * 1.11 0 0 0 M Total of safety boxes (+ 10% of extra need) needed (K + L) /100 * 1.11 0 0 0 N Cost of vaccines needed I x g 1,998,933 149,314 1,849,619 O Cost of AD syringes needed K x ca 0 0 0 P Cost of reconstitution syringes needed L x cr 0 0 0 Q Cost of safety boxes needed M x cs 0.00 0 0 R Freight cost for vaccines needed N x fv 99,947 7,466 92,481 S Freight cost for devices needed (O+P+Q) x fd 0 0 0 T Total fund needed (N+O+P+Q+R+S) 2,098,880 156,779 1,942,101 U Total country co-financing I 3 cc 156,779 V Country co-financing % of GAVI supported proportion U / T 7.47 % Table Annex 2.1 D: Estimated numbers for Rotavirus, 3 -dose schedule, associated injection safety material and related co-financing budget (page 2) Formula 2014 Total Government GAVI A Country co-finance 8.59 % B Number of children to be vaccinated with the first dose Table 1 627,736 53,924 573,812 C Number of doses per child Vaccine parameter (schedule) 2.00 D Number of doses needed B x C 1,255,472 107,847 1,147,625 E Estimated vaccine wastage factor Wastage factor table 1.01 F Number of doses needed including wastage D x E 1,268,027 108,925 1,159,102 G Vaccines buffer stock (F – F of previous year) * 0.25 160,228 13,764 146,464 I Total vaccine doses needed F + G 1,428,255 122,689 1,305,566 J Number of doses per vial Vaccine parameter 1.00 K Number of AD syringes (+ 10% wastage) needed (D + G) x 1.11 0 0 0 L Reconstitution syringes (+ 10% wastage) needed I / J * 1.11 0 0 0 M Total of safety boxes (+ 10% of extra need) needed (K + L) /100 * 1.11 0 0 0 N Cost of vaccines needed I x g 3,642,051 312,857 3,329,194 O Cost of AD syringes needed K x ca 0 0 0 P Cost of reconstitution syringes needed L x cr 0 0 0 Q Cost of safety boxes needed M x cs 0.00 0 0 R Freight cost for vaccines needed N x fv 182,103 15,643 166,460 S Freight cost for devices needed (O+P+Q) x fd 0 0 0 T Total fund needed (N+O+P+Q+R+S) 3,824,154 328,499 3,495,655 U Total country co-financing I 3 cc 328,499 V Country co-financing % of GAVI supported proportion U / T 8.59 % Table Annex 2.1 D: Estimated numbers for Rotavirus, 3 -dose schedule, associated injection safety material and related co-financing budget (page 3) Formula 2015 Total Government GAVI A Country co-finance 9.71 % B Number of children to be vaccinated with the first dose Table 1 634,641 61,628 573,013 C Number of doses per child Vaccine parameter (schedule) 2.00 D Number of doses needed B x C 1,269,282 123,255 1,146,027 E Estimated vaccine wastage factor Wastage factor table 1.01 F Number of doses needed including wastage D x E 1,281,975 124,488 1,157,487 G Vaccines buffer stock (F – F of previous year) * 0.25 3,487 339 3,148 I Total vaccine doses needed F + G 1,285,462 124,826 1,160,636 J Number of doses per vial Vaccine parameter 1.00 K Number of AD syringes (+ 10% wastage) needed (D + G) x 1.11 0 0 0 L Reconstitution syringes (+ 10% wastage) needed I / J * 1.11 0 0 0 M Total of safety boxes (+ 10% of extra need) needed (K + L) /100 * 1.11 0 0 0 N Cost of vaccines needed I x g 3,277,929 318,306 2,959,623 O Cost of AD syringes needed K x ca 0 0 0 P Cost of reconstitution syringes needed L x cr 0 0 0 Q Cost of safety boxes needed M x cs 0.00 0 0 R Freight cost for vaccines needed N x fv 163,897 15,916 147,981 S Freight cost for devices needed (O+P+Q) x fd 0 0 0 T Total fund needed (N+O+P+Q+R+S) 3,441,826 334,221 3,107,605 U Total country co-financing I 3 cc 334,221 V Country co-financing % of GAVI supported proportion U / T 9.71 %

Annex 3 - NVS Preventive campaign(s)

No NVS Prevention Campaign Support this year

| Annex 4 |  |  |
| --- | --- | --- |
| Table Annex 4A: Commodities Cost |  |  |
| Vaccine Presentation 2013 2014 2015 2016 DTP-HepB, 10 dose(s) per vial, LIQUID 10 DTP-HepB-Hib, 1 dose(s) per vial, LIQUID 1 2.017 1.986 1.933 1.927 DTP-HepB-Hib, 10 dose(s) per vial, LIQUID 10 2.017 1.986 1.933 1.927 DTP-HepB-Hib, 2 dose(s) per vial, LYOPHILISED 2 2.017 1.986 1.933 1.927 HPV bivalent, 2 dose(s) per vial, LIQUID 2 5.000 5.000 5.000 5.000 HPV quadrivalent, 1 dose(s) per vial, LIQUID 1 5.000 5.000 5.000 5.000 Measles, 10 dose(s) per vial, LYOPHILISED 10 0.242 0.242 0.242 0.242 Meningogoccal, 10 dose(s) per vial, LIQUID 10 0.520 0.520 0.520 0.520 MR, 10 dose(s) per vial, LYOPHILISED 10 0.494 0.494 0.494 0.494 Pneumococcal (PCV10), 2 dose(s) per vial, LIQUID 2 3.500 3.500 3.500 3.500 Pneumococcal (PCV13), 1 dose(s) per vial, LIQUID 1 3.500 3.500 3.500 3.500 Rotavirus, 2-dose schedule 1 2.550 2.550 2.550 2.550 Rotavirus, 3-dose schedule 1 3.500 3.500 3.500 3.500 Yellow Fever, 10 dose(s) per vial, LYOPHILISED 10 0.900 0.900 0.900 0.900 Yellow Fever, 5 dose(s) per vial, LYOPHILISED 5 0.900 0.900 0.900 0.900 |  |  |
| Note for HPV and MR: These prices are indicative only as GAVI has not procured HPV and MR vaccines for GAVI countries yet. Prices will be finalised through tender processes in Q3. GAVI will only fund HPV vaccines if an acceptable price reduction is secured from the current price indicated. The MR price is based on the current price to UNICEF |  |  |
| Supply Form 2013 2014 2015 2016 AD-SYRINGE SYRINGE 0.047 0.047 0.047 0.047 RECONSTIT-SYRINGE-PENTAVAL SYRINGE 0.047 0.047 0.047 0.047 RECONSTIT-SYRINGE-YF SYRINGE 0.004 0.004 0.004 0.004 SAFETY-BOX SAFETYBOX 0.006 0.006 0.006 0.006 |  |  |
| Note: WAP - weighted average price (to be used for any presentation: For DTP-HepB-Hib, it applies to 1 dose liquid, 2 dose lyophilised and 10 dose liquid. For Yellow Fever, it applies to 5 dose lyophilised and 10 dose lyophilised) |  |  |
| Table Annex 4B: Freight cost as percentage of value |  |  |
| Vaccine Antigen Vaccine Type No Threshold 500,000$ <= > DTP-HepB HEPBHIB 2.00 % DTP-HepB-Hib HEPBHIB 23.80 % 6.00 % HPV bivalent HPV 3.50 % HPV quadrivalent HPV 3.50 % Measles MEASLES 14.00 % Meningogoccal MENINACONJUGATE 10.20 % MR MR 13.20 % Pneumococcal (PCV10) PNEUMO 3.00 % Pneumococcal (PCV13) PNEUMO 6.00 % Rotavirus ROTA 5.00 % Yellow Fever YF 7.80 % |  |  |
| Table Annex 4C: Intermediate - Minimum country's co-payment per dose of co-financed vaccine. |  |  |
| Vaccine 2013 2014 2015 Rotavirus, 1 dose(s) per vial, ORAL 0.2 0.23 0.26 |  |  |
| Table Annex 4D: Wastage rates and factors |  |  |
| Countries are expected to plan for a maximal wastage rate of: |  |  |
| • 50% - for a lyophilised vaccine in 10 or 20-dose vial, |  |  |
| • 25% - for a liquid vaccine in 10 or 20-dose vial or a lyophilised vaccine in 5-dose vial, |  |  |
| • 10% - for a lyophilised/liquid vaccine in 2-dose vial, and |  |  |
| • 5% - for a liquid vaccine in 1-dose vial |  |  |
| Vaccine wastage rate 5% 10% 15% 20% 25% 30% 35% 40% 45% 50% 55% 60% Equivalent wastage factor 1.05 1.11 1.18 1.25 1.33 1.43 1.54 1.67 1.82 2 2.22 2.5 |  |  |
| Vaccine Vaccine wastage rate VaccineWastageFactor |  |  |
| Table Annex 4E: Vaccine maximum packed volumes |  |  |
| Vaccine product Designation Vaccine formulation Admin route No. Of doses in the schedule Presentation (doses/vial, prefilled) Packed volume vaccine (cm3/dose) Packed volume diluents (cm3/dose) BCG BCG lyophilized ID 1 20 1.2 0.7 Diphtheria-Tetanus-Pertussis DTP liquid IM 3 20 2.5 Diphtheria-Tetanus-Pertussis DTP liquid IM 3 10 3 Diphtheria-Tetanus DT liquid IM 3 10 3 Tetanus-Diphtheria Td liquid IM 2 10 3 Tetanus Toxoid TT liquid IM 2 10 3 Tetanus Toxoid TT liquid IM 2 20 2.5 Tetanus Toxoid UniJect TT liquid IM 2 Uniject 12 Measles Measles lyophilized SC 1 1 26.1 20 Measles Measles lyophilized SC 1 2 13.1 13.1 Measles Measles lyophilized SC 1 5 5.2 7 Measles Measles lyophilized SC 1 10 3.5 4 Measles-Rubella freeze dried MR lyophilized SC 1 1 26.1 26.1 Measles-Rubella freeze dried MR lyophilized SC 1 2 13.1 13.1 Measles-Rubella freeze dried MR lyophilized SC 1 5 5.2 7 Measles-Rubella freeze dried MR lyophilized SC 1 10 2.5 4 Measles-Mumps-Rubella freeze dried MMR lyophilized SC 1 1 26.1 26.1 Measles-Mumps-Rubella freeze dried MMR lyophilized SC 1 2 13.1 13.1 Measles-Mumps-Rubella freeze dried MMR lyophilized SC 1 5 5.2 7 Measles-Mumps-Rubella freeze dried MMR lyophilized SC 1 10 3 4 Polio OPV liquid Oral 4 10 2 Polio OPV liquid Oral 4 20 1 Yellow fever YF lyophilized SC 1 5 6.5 7 Yellow fever YF lyophilized SC 1 10 2.5 3 Yellow fever YF lyophilized SC 1 20 1.5 2 Yellow fever YF lyophilized SC 1 50 0.7 1 DTP-HepB combined DTP-HepB liquid IM 3 1 9.7 DTP-HepB combined DTP-HepB liquid IM 3 2 6 DTP-HepB combined DTP-HepB liquid IM 3 10 3 Hepatitis B HepB liquid IM 3 1 18 Hepatitis B HepB liquid IM 3 2 13 Hepatitis B HepB liquid IM 3 6 4.5 Hepatitis B HepB liquid IM 3 10 4 Hepatitis B UniJect HepB liquid IM 3 Uniject 12 Hib liquid Hib_liq liquid IM 3 1 15 Hib liquid Hib_liq liquid IM 3 10 2.5 Hib freeze-dried Hib_lyo lyophilized IM 3 1 13 35 Hib freeze-dried Hib_lyo lyophilized IM 3 2 6 Hib freeze-dried Hib_lyo lyophilized IM 3 10 2.5 3 DTP liquid + Hib freeze-dried DTP+Hib liquid+lyop. IM 3 1 45 DTP-Hib combined liquid DTP+Hib liquid+lyop. IM 3 10 12 DTP-Hib combined liquid DTP-Hib liquid IM 3 1 32.3 DTP-HepB liquid + Hib freeze-dried DTP-Hib liquid IM 3 10 2.5 DTP-HepB liquid + Hib freeze-dried DTP-HepB+Hib liquid+lyop. IM 3 1 22 DTP-HepB-Hib liquid DTP-HepB+Hib liquid+lyop. IM 3 2 11 DTP-HepB-Hib liquid DTP-HepB-Hib liquid IM 3 10 4.4 DTP-HepB-Hib liquid DTP-HepB-Hib liquid IM 3 2 13.1 DTP-HepB-Hib liquid DTP-HepB-Hib liquid IM 3 1 19.2 Meningitis A/C MV_A/C lyophilized SC 1 10 2.5 4 Meningitis A/C MV_A/C lyophilized SC 1 50 1.5 3 Meningococcal A/C/W/ MV_A/C/W lyophilized SC 1 50 1.5 3 Meningococcal A/C/W/Y MV_A/C/W/Y lyophilized SC 1 10 2.5 4 Meningitis W135 MV_W135 lyophilized SC 1 10 2.5 4 Meningitis A conjugate Men_A lyophilized SC 2 10 2.6 4 Japanese Encephalitis JE_lyo lyophilized SC 3 10 15 Japanese Encephalitis JE_lyo lyophilized SC 3 10 8.1 8.1 Japanese Encephalitis JE_lyo lyophilized SC 3 5 2.5 2.9 Japanese Encephalitis JE_lyo lyophilized SC 3 1 12.6 11.5 Japanese Encephalitis JE_liq liquid SC 3 10 3.4 Rota vaccine Rota_lyo lyophilized Oral 2 1 156 Rota vaccine Rota_liq liquid Oral 2 1 17.1 Rota vaccine Rota_liq liquid Oral 3 1 45.9 Pneumo. conjugate vaccine 7-valent PCV-7 liquid IM 3 PFS 55.9 Pneumo. conjugate vaccine 7-valent PCV-7 liquid IM 3 1 21 Pneumo. conjugate vaccine 10-valent PCV-10 liquid IM 3 1 11.5 Pneumo. conjugate vaccine 10-valent PCV-10 liquid IM 3 2 4.8 Pneumo. conjugate vaccine 13-valent PCV-13 liquid IM 3 1 12 Polio inactivated IPV liquid IM 3 PFS 107.4 Polio inactivated IPV liquid IM 3 10 2.5 Polio inactivated IPV liquid IM 3 1 15.7 Human Papilomavirus vaccine HPV liquid IM 3 1 15 Human Papilomavirus vaccine HPV liquid IM 3 2 5.7 Monovalent OPV-1 mOPV1 liquid Oral 20 1.5 Monovalent OPV-3 mOPV3 liquid Oral 20 1.5 |  |  |

| 12. Banking Form |  |
| --- | --- |
| In accordance with the decision on financial support made by the GAVI Alliance, the Government of Uzbekistan hereby requests that a payment be made via electronic bank transfer as detailed below: Name of Institution (Account Holder): Ministry of Health of the Republic of Uzbekistan Address: 12 Navoiy St City Country: Tashkent, 100011, Uzbekistan Telephone no.: +998 71 2394218 Fax no.: Currency of the bank account: USD For credit to: Bank account's title: Ministry of Health Bank account no.: 22696840000102144005 Bank's name: National Bank for Foreign Economic Activity of the Republic of Uzbekistan |  |
| Is the bank account exclusively to be used by this program? False |  |
| By who is the account audited? Ministry of Finance |  |
| Signature of Government's authorizing official |  |
| Seal Name: Anvar Alimov Title: Minister of Health Signature: Date: 30/08/2012 |  |
| FINANCIAL INSTITUTION Bank Name: National Bank for Foreign Economic Activity of the Republic of Uzbekistan Branch Name: Tashkent City Branch Address: City Country: Tashkent, Uzbekistan Swift Code: NBFA UZ 2X Sort Code: ABA No.: Telephone No.: +998712336412 FAX No.: +998711320172 | CORRESPONDENT BANK (In the United States) CITIBANK N.A., NEW YORK, NY; CITIUS33; Acc. 36016987 BANK OF NEW YORK, NY; IRVTUS3N; Acc. 8900056576 CAHSE MANHATTAN BANK, NY; CHASUS33; Acc. 0011388352 |
| I certify that the account No 22696840000102144005 is held by Ministry of Health at this banking institution The account is to be signed jointly by at least 2 (number of signatories) of the following authorized signatories: 1 Name: Anvar Alimov Title: Minister of Health 2 Name: Bakhtiyor Khashimov Title: Head of Finance, Economic and Planning Department, MOH 3 Name: Title: |  |
| Name of bank's authorizing official Signature: Date: 8/30/2012 12:00:00 AM Seal: |  |