January 2005 (revised)

Progress Report

Partnering with The Vaccine Fund

to the

Global Alliance for Vaccines and Immunization (GAVI)

and

The Vaccine Fund

by the Government of

COUNTRY: AZERBAIJAN

Date of submission: …………………………… Reporting period: 2005 ( Information provided in this report MUST refer to 2005 activities ) ( Tick only one ) : Inception report  First annual progress report  Second annual progress report  Third annual progress report  Fourth annual progress report  Fifth annual progress report X Text boxes supplied in this report are meant only to be used as guides. Please feel free to add text beyond the space provided. *Unless otherwise specified, documents may be shared with GAVI partners and collaborators

# Progress Report Form:  Table of Contents

# Report on progress made during 2005

  - Immunization Services Support (ISS)

1.1.1	Management of ISS Funds

  - Use of Immunization Services Support

1.1.3	Immunization Data Quality Audit

  - GAVI/Vaccine Fund New and Under-used Vaccines

1.2.1	Receipt of new and under-used vaccines

1.2.2	Major activities

    - Use if GAVI/The Vaccine Fund financial support (US$100,000) for introduction of the new vaccine

1.3	Injection Safety

    - Receipt of injection safety support

    - Progress of transition plan for safe injections and safe management of sharps waste

    - Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

2.  Financial Sustainability

3.  Request for new and under-used vaccine for 2007

  - Up-dated immunization targets

  - Confirmed/revised request for new vaccine (to be shared with UNICEF Supply Division) for year…

  - Confirmed/revised request for injection safety support for the year…

- Please report on progress since submission of the last Progress Report based on the indicators

selected by your country in the proposal for GAVI/VF support

5.  Checklist

6.  Comments

7.  Signatures

# 1.  	Report on progress made during 2005

To be filled in by the country for each type of support received from GAVI/The Vaccine Fund.

## Immunization Services Support (ISS)

#### 1.1.1	Management of ISS Funds

Please describe the mechanism for management of ISS funds, including the role of the Inter-Agency Co-ordinating Committee (ICC).

Please report on any problems that have been encountered involving the use of those funds, such as delay in availability for programme use.

MOH manages of ISS funds with consideration and discussion on ICC. No problems met in utilization of ISS funds.

#### 1.1.2	Use of Immunization Services Support

In 2005, the following major areas of activities have been funded with the GAVI/Vaccine Fund Immunization Services Support contribution.

Funds received during 2005 60.000 USD

Remaining funds (carry over) from 2004  0

Table 1: Use of funds during 2005

| Area of Immunization Services Support | Total amount in US $ | AMOUNT OF FUNDS |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | PUBLIC SECTOR |  |  | PRIVATE SECTOR & Other |
|  |  | Central | Region/State/Province | District |  |
| Vaccines |  |  |  |  |  |
| Injection supplies | 39.200 |  | 1.960 | 37.240 |  |
| Personnel |  |  |  |  |  |
| Transportation |  |  |  |  |  |
| Maintenance and overheads |  |  |  |  |  |
| Training |  |  |  |  |  |
| IEC / social mobilization |  |  |  |  |  |
| Outreach |  |  |  |  |  |
| Supervision |  |  |  |  |  |
| Monitoring and evaluation | 17.550 |  | 1.870 | 15.680 |  |
| Epidemiological surveillance |  |  |  |  |  |
| Vehicles |  |  |  |  |  |
| Cold chain equipment |  |  |  |  |  |
| Other (equipment) | 3.250 |  | 650 | 2.600 |  |
| Total: | 60.000 |  | 4.480 | 55.520 |  |
| Remaining funds for next year: | 0 |  |  |  |  |

*If no information is available because of block grants, please indicate under ‘other’.

Please attach the minutes of the ICC meeting(s) when the allocation of funds was discussed.

Please report on major activities conducted to strengthen immunization, as well as, problems encountered in relation to your multi-year plan.

- Cold chain monitoring was conducted and needs of treatment prevention facilities (medical facilities) in the cold chain equipment were determined. - Preparation to measles/rubella Supplementary Immunization Activity (MR SIA) - In frame of MR SIA hygiene epidemiological centers and medical facilities were provided with cold chain equipments. - In frame of MR SIA trainings for doctors and vaccinators involved in campaign were conducted.

#### Immunization Data Quality Audit (DQA) (If it has been implemented in your country)

Has a plan of action to improve the reporting system based on the recommendations from the DQA been prepared?

If yes, please attach the plan.

YES                              NO

X

## If yes, please report on the degree of its implementation.

## Please attach the minutes of the ICC meeting where the plan of action for the DQA was discussed and endorsed by the ICC.

Please report on studies conducted regarding EPI issues during 2005 (for example, coverage surveys).

- Analysis of immunization coverage at the cities and districts level and injection safety n the 2004 were discussed on the meeting of board of MOH. - In framework of MR SIA with participation of WHO experts were conducted evaluation of: 1 ) injection safety; 2) epidemiological surveillance on Adverse Events Following Immunization; Results were discussed with doctors and vaccinators during trainings.

## GAVI/Vaccine Fund New & Under-used Vaccines Support

#### 1.2.1	Receipt of new and under-used vaccines during 2005

Start of vaccinations with the new and under-used vaccine:           MONTH October           YEAR 2001

Please report on receipt of vaccines provided by GAVI/VF, including problems encountered.

| In 2005 was received hepatitis B vaccine: 2 doses- 98.000 10 doses- 289.500 No problems met. |  |
| --- | --- |

#### 1.2.2	Major activities

Please outline major activities that have been or will be undertaken, in relation to, introduction, phasing-in, service strengthening, etc. and report on problems encountered.

- In 2005 routine immunization was financed by Government budget, except MRR and HB vaccines. - In frame of measles/rubella elimination strengthening of case based epidemiological surveillance and AEFI control - Conduction of MR SIA among 7-29 age population of Azerbaijan (February-March 2006) - MR SIA among women till 35 years old is planned (October - November 2006)

#### 1.2.3	Use of GAVI/The Vaccine Fund financial support (US$100,000) for the introduction of the new vaccine

Please report on the proportion of 100,000 US$ used, activities undertaken, and problems encountered such as delay in availability of funds for programme use.

Not applicable

## Injection Safety

#### 1.3.1	Receipt of injection safety support

Please report on receipt of injection safety support provided by GAVI/VF, including problems encountered

AD syringes were purchased. No problems met.

#### Progress of transition plan for safe injections and safe management of sharps waste.

#### Please report problems encountered during the implementation of the transitional plan for safe injection and sharp waste

We still have problem with safety disposals of waste materials in cities, especially in Baku city. There are no specialized plants for processing of waste materials and no incinerators at the medical facilities.

Please report on the progress based on the indicators chosen by your country in the proposal for GAVI/VF support.

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| - Provision with AD syringes - Availability of safety boxes for waste materials collection - Availability of utilization system for safety disposal of waste materials - Provision with cold chain equipments | 100% 100% 100% 100% | 100% 100% 70% 80% | Safety disposal of waste materials in the cities In frame of MR SIA the medical facilities were provided with cold chain equipments. |  |

#### 1.3.3	Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

The following major areas of activities have been funded (specify the amount) with the GAVI/The Vaccine Fund injection safety support in the past year:

- Purchase of AD syringes for total USD 39.200 - Cold chain monitoring for total USD 17.550

# 2.  	Financial sustainability

Inception Report:	Outline timetable and process for the development of a financial sustainability plan . Describe assistance that may be needed for developing a financial sustainability plan.

First Annual Progress Report: 	Submit completed financial sustainability plan by given deadline. Describe major strategies for improving financial sustainability.

Subsequent Progress Reports:	According to current GAVI rules, support for new and under-used vaccines is covering the total quantity required to meet country targets (assumed to be equal to DTP3 targets) over a five year period (100% x 5 years = 500%).  If the requested amount of new vaccines does not target the full country in a given year (for example, a phasing in of 25%), the country is allowed to request the remaining (in that same example: 75%) in a later year.  In an attempt to help countries find sources of funding in order to attain financial sustainability by slowly phasing out GAVI/VF support, they are encouraged to begin contributing a portion of the vaccine quantity required.  Therefore, GAVI/VF support can be spread out over a maximum of ten years after the initial approval, but will not exceed the 500% limit (see figure 4 in the GAVI Handbook for further clarification).  In table 2.1, specify the annual proportion of five year GAVI/VF support for new vaccines that is planned to be spread-out over a maximum of ten years and co-funded with other sources. Please add the three rows (Proportion funded by GAVI/VF (%), Proportion funded by the Government and other sources (%), Total funding for VHB  (new vaccine)) for each new vaccine.

| Table 2.1: Sources (planned) of financing of new vaccine VHB (specify) |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Proportion of vaccines supported by * | Annual proportion of vaccines |  |  |  |  |  |  |  |  |  |
|  | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 |
| A: Proportion funded by GAVI/VF (%)*** | 100 | 100 | 100 | 100 | 100 | 100++ | 60 | 40 | - | - |
| B: Proportion funded by the Government and other sources (%) | - | - | - | - | - | - | 40 | 60 | 100 | 100 |
| C: Total funding for VHB (new vaccine) | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 |

++ Azerbaijan is requesting to utilize 50% of the 150% additional Hepatitis B support for 2007 and 2008 for 2006 as Azerbaijan was entitled to receive only 50% of GAVI support for Hepatitis B in 2006 as part of Phase 1 support.

* Percentage of DTP3 coverage (or measles coverage in case of Yellow Fever) that is target for vaccination with a new and under-used vaccine.

** The first year should be the year of GAVI/VF new vaccine introduction

*** Row A should total 500% at the end of GAVI/VF support

In table 2.2 below, describe progress made against major financial sustainability strategies and corresponding indicators.

Table 2.2:	Progress against major financial sustainability strategies and corresponding indicators

| Financial Sustainability Strategy | Specific Actions Taken Towards Achieving Strategy | Progress Achieved | Problems Encountered | Baseline Value of Progress Indicator | Current Value of Progress Indicator | Proposed Changes To Financial Sustainability Strategy |
| --- | --- | --- | --- | --- | --- | --- |
| 1. Current finance of Immunization Service Development |  |  |  |  |  |  |
| 2.Totality financing executed |  |  |  |  |  |  |
| 3. Purchase of vaccine at effective cost |  |  |  |  |  |  |
| 4. Percentage of wastage towards to decrease |  |  |  |  |  |  |
| 5. |  |  |  |  |  |  |

The implementation index of major financial sustainability strategies the same as in 2004.

# 3.  	Request for new and under-used vaccines for year 2007

Section 3 is related to the request for new and under used vaccines and injection safety for 2007.

- Up-dated immunization targets

Confirm/update basic data approved with country application: figures are expected to be consistent with those reported in the WHO/UNICEF Joint

Reporting Forms.  Any changes and/or discrepancies MUST be justified in the space provided (page 12). Targets for future years MUST be provided.

| Table 3 : Update of immunization achievements and annual targets |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of | Achievements and targets |  |  |  |  |  |  |  |  |
|  | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 |
| DENOMINATORS |  |  |  |  |  |  |  |  |  |
| Births | 115.620 | 116.975 | 117.922 | 118.878 | 119.841 | 120.811 | 121.790 | 122.776 | 123.771 |
| Infants’ deaths | 2.206 | 3.416 | 3.443 | 3.471 | 3.499 | 3.528 | 3.556 | 3.585 | 3.614 |
| Surviving infants | 113.414 | 113.559 | 114.479 | 115.406 | 116.342 | 117.283 | 118.234 | 119.191 | 120.157 |
| Infants vaccinated in 2005 (JRF) / to be vaccinated in 2006 and beyond with 1st dose of DTP (DTP1)* | 110.574 | 111.287 | 112.189 | 113.097 |  |  |  |  |  |
| Infants vaccinated 2005 (JRF) / to be vaccinated in 2006 and beyond with 3rd dose of DTP (DTP3)* | 108.769 | 111.287 | 112.189 | 113.097 |  |  |  |  |  |
| NEW VACCINES ** |  |  |  |  |  |  |  |  |  |
| Infants vaccinated 2005 (JRF) / to be vaccinated in 2006 and beyond with 1st dose of VHB (new vaccine) | 113.530 | 114.635 | 115.563 | 116.500 |  |  |  |  |  |
| Infants vaccinated 2005 (JRF) / to be vaccinated in 2006 and beyond with 3rd dose of VHB ( new vaccine) | 111.419 | 111.287 | 112.189 | 113.097 |  |  |  |  |  |
| Wastage rate in 2005 and plan for 2006 beyond*** VHB ( new vaccine) | For 2 dose vial -1.05 For 10 dose vial -1.25 | For 2 dose vial -1.05 For 10 dose vial -1.25 | For 2 dose vial -1.05 For 10 dose vial -1.25 | For 2 dose vial -1.05 For 10 dose vial -1.25 |  |  |  |  |  |
| INJECTION SAFETY**** |  |  |  |  |  |  |  |  |  |
| Pregnant women vaccinated in 2005 (JRF) / to be vaccinated in 2006 and beyond with TT2 | 113.341 |  |  |  |  |  |  |  |  |
| Infants vaccinated in 2005 (JRF) / to be vaccinated in 2006 and beyond with BCG * | 115.530 | 114.635 | 115.563 | 116.500 |  |  |  |  |  |
| Infants vaccinated in 2005 (JRF) / to be vaccinated in 2006 and beyond with Measles * | 110.991 | 111.287 | 112.189 | 113.097 |  |  |  |  |  |

* Indicate actual number of children vaccinated in 2005 and updated targets (with either DTP alone or combined)

** Use 3 rows (as indicated under the heading NEW VACCINES) for every new vaccine introduced

*** Indicate actual wastage rate obtained in past years

**** Insert any row as necessary

Please provide justification on changes to baseline, targets, wastage rate, vaccine presentation, etc. from the previously approved plan, and on reported figures which differ from those reported in the WHO/UNICEF Joint Reporting Form in the space provided below.

The number of births and surviving infants indicated in this report, has been provided by Statistical Department of The Ministry of Health, based on calculations by special formula and is more correct than data by JRF. Taking into consideration that reported coverage data around 95%,, but the aimed goal is 98%, we indicated our target as for 98% coverage. According to routine immunization schedule for hep B1 it is 98% of births, but for hep B 2-nd and 3-rd dose it is 98% of surviving children. The first dose of Hepatitis B is given at 1 week of age and the target is therefore higher than for DTP1. There are no differences between DTP1 and DTP3 target groups. The number of infants targeted for measles indicate only number of children for 1-st dose of MMR (1 year old).

3.2	Availability of revised request for new vaccine (to be shared with UNICEF Supply Division) for 2007

In case you are changing the presentation of the vaccine, or increasing your request; please indicate below if UNICEF Supply Division has assured the availability of the new quantity/presentation of supply.

Table 4: Estimated number of doses of  HB vaccine (specify for one presentation only): Please repeat this table for any other vaccine presentation requested from GAVI/The Vaccine Fund

Azerbaijan utilizes two different vial sizes for hep B vaccine -2 doses (30%) and 10 doses (70%). Taking into consideration these conditions request is calculated in two separate tables, according to vials presentation. Please note that actually vaccine buffer stock at National level by the end of year is 0 for both 2006 and 2007. We also include calculations for 2006 to clarify the IRC queries from the APR 2004 and have calculated 100% GAVI support for 2006 based on the 50% support from GAVI Phase 1 and the request to utilize 50% support from the 150% additional support for Hepatitis B for 2007 and 2008 for the year 2006.

For 2 doses vial’s we calculated request for 30% of target population.

|  |  | Formula | For 2006 | For 2007 |
| --- | --- | --- | --- | --- |
| A | Infants vaccinated/to be vaccinated with 1st dose of VHB | Hep B 1 target | 114,635 | 115,563 |
|  |  | 30% for 2-dose vial | 34,391 | 34,669 |
| B | Percentage of vaccines requested from The Vaccine Fund taking into consideration the Financial Sustainability Plan | % | 100 | 60 |
| C | Number of doses per child |  | 3 | 3 |
| D | Number of doses | A x B/100 x C | 103,172 | 62,404 |
| E | Estimated wastage factor | (see table.3) | 1.05 | 1.05 |
| F | Number of doses (including wastage) | A x C x E x B/100 | 108,330 | 65,524 |
| G | Vaccine buffers tock | F x 0.25 | 27,083 | 16,381 |
| H | Anticipated vaccines in stock at start of year 2007 (including balance of buffer stock) |  | 0 | 0 |
| I | Total vaccine doses requested | F + G - H | 135,413 | 81,905 |
| J | Number of doses per vial | For 2 dose | 67,706 | 40,953 |
| K | Number of AD syringes (+ 10% wastage) | ( D + G – H ) x 1,11 | 144,582 | 87,451 |
| L | Reconstitution syringes (+ 10% wastage) | I / J x 1,11 | 0 | 0 |
| M | Total safety boxes (+ 10% of extra needs) | ( K + L) / 100 x 1,11 | 1,605 | 971 |

For 10 doses vial’s we calculate request for 70% of target population.

|  |  | Formula | For 2006 | For 2007 |
| --- | --- | --- | --- | --- |
| A | Infants vaccinated/to be vaccinated with 1st dose of VHB | Hep B 1 target | 114,635 | 115,563 |
|  |  | 70% for 10-dose vial | 80,245 | 80,894 |
| B | Percentage of vaccines requested from The Vaccine Fund taking into consideration the Financial Sustainability Plan | 100% from GAVI for 2006, 60% for 2007 % | 100 | 60 |
| C | Number of doses per child |  | 3 | 3 |
| D | Number of doses | A x B/100 x C | 240,734 | 145,609 |
| E | Estimated wastage factor | (see table.3) | 1.33 | 1.33 |
| F | Number of doses (including wastage) | A x C x E x B/100 | 320,176 | 193,660 |
| G | Vaccine buffers tock | F x 0.25 | 80,044 | 48,415 |
| H | Anticipated vaccines in stock at start of year 2007 (including balance of buffer stock) |  | 0 | 0 |
| I | Total vaccine doses requested | F + G - H | 400,219 | 242,076 |
| J | Number of doses per vial | For 10 dose | 40,022 | 24,208 |
| K | Number of AD syringes (+ 10% wastage) | ( D + G – H ) x 1,11 | 356,063 | 215,367 |
| L | Reconstitution syringes (+ 10% wastage) | I / J x 1,11 | 0 | 0 |
| M | Total safety boxes (+ 10% of extra needs) | ( K + L) / 100 x 1,11 | 3,952 | 2,391 |

Please report the same figure as in table 3.

Table 5: Wastage rates and factors

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

Remarks

- Phasing: Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided - Wastage of vaccines: Countries are expected to plan for a maximum of: 50% wastage rate for a lyophilized vaccine in 10 or 20-dose vial; 25% for a liquid vaccine in a10 or 20-dose vial; 10% for any vaccine (either liquid or lyophilized) in 1 or 2-dose vial. - Buffer stock: The buffer stock is recalculated every year as 25% the current vaccine requirement - Anticipated vaccines in stock at start of year 2007: It is calculated by counting the current balance of vaccines in stock, including the balance of buffer stock. Write zero if all vaccines supplied for the current year (including the buffer stock) are expected to be consumed before the start of next year. Countries with very low or no vaccines in stock must provide an explanation of the use of the vaccines. - AD syringes: A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines. - Reconstitution syringes: it applies only for lyophilized vaccines. Write zero for other vaccines. - Safety boxes: A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes

#### 3.3	Confirmed/revised request for injection safety support for the years 2007 -2008

Table 6: Estimated supplies for safety of vaccination for the next two years with DTP (Use one table for each vaccine BCG, DTP, measles and TT, and number them from 4 to 8)

|  |  | Formula | For 2007 | For 2008 |
| --- | --- | --- | --- | --- |
| A | Target if children for DTP vaccination (for TT target of pregnant women)1 | # |  |  |
| B | Number of doses per child (for TT target of pregnant women)1 | # |  |  |
| C | Number of DTP doses | A x B |  |  |
| D | Number of AD syringes (+ 10% wastage) | C x 1,11 |  |  |
| E | AD syringes buffer stock 2 | D x 0,25 |  |  |
| F | Total AD syringes | D + E |  |  |
| G | Number of doses per vial | # |  |  |
| H | Vaccine wastage factor 4 | 2 |  |  |
| I | Number of reconstitution syringes (+10% wastage) 3 | C x H x 1,11 / G |  |  |
| J | Number of safety boxes (+10% of extra needs) | ( F + I ) x 1,11 / 100 |  |  |

#### If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference.

# 4. 	Please report on progress since submission of the last Progress Report based on the indicators selected 	by your country in the proposal for GAVI/VF support

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| - Provision with AD syringes - Availability of safety boxes for waste materials collection - Availability of utilization system for safety disposal of waste materials - Provision with cold chain equipments | 100% 100% 100% 100% | 100% 100% 70% 80% | Safety disposal of waste materials in the cities |  |

# Checklist

Checklist of completed form:

| Form Requirement: | Completed | Comments |
| --- | --- | --- |
| Date of submission |  |  |
| Reporting Period (consistent with previous calendar year) |  |  |
| Table 1 filled-in |  |  |
| DQA reported on |  |  |
| Reported on use of 100,000 US$ |  |  |
| Injection Safety Reported on |  |  |
| FSP Reported on (progress against country FSP indicators) |  |  |
| Table 2 filled-in |  |  |
| New Vaccine Request completed |  |  |
| Revised request for injection safety completed (where applicable) |  |  |
| ICC minutes attached to the report |  |  |
| Government signatures |  |  |
| ICC endorsed |  |  |

6.  	Comments

ICC/RWG comments:

7.	Signatures

For the Government of ………………..…………………………………

Signature:	……………………………………………...……………...

Title:	………………………………………….………………….

Date:	………………………………………….………………….

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this report. Signature of endorsement of this document does not imply any financial (or legal) commitment on the part of the partner agency or individual.

Financial accountability forms an integral part of GAVI/The Vaccine Fund monitoring of reporting of country performance.  It is based on the regular government audit requirements as detailed in the Banking form.  The ICC Members confirm that the funds received have been audited and accounted for according to standard government or partner requirements.

| Agency/Organisation | Name/Title | Date Signature | Agency/Organisation | Name/Title | Date Signature |
| --- | --- | --- | --- | --- | --- |

~ End ~

1 Contribute to a maximum of 2 doses for Pregnant Women (estimated as total birth)

1

2	 The buffer stock for vaccines and AD syringes is set at 25%. This is added to the first stock of doses required to introduce the vaccination in any given geographic area.

Write zero for other years.

3 Only for lyophilized vaccines. Write zero for other vaccines.

4 Standard wastage factors will be used for calculation of reconstitution syringes. It will be 2 for BCG, 1.6 for measles and YF.