May 2006

Progress Report

to the

Global Alliance for Vaccines and Immunization (GAVI)

and

The Vaccine Fund

by the Government of

COUNTRY BOLIVIA

Date of submission: 15 May 2006 Reporting period: Jan –Dec 2005 ( Tick only one ) : Inception report ( First annual progress report √ Second annual progress report ( Third annual progress report ( Fourth annual progress report ( Fifth annual progress report ( Text boxes supplied in this report are meant only to be used as guides. Please feel free to add text beyond the space provided. *Unless otherwise specified, documents may be shared with GAVI partners and collaborators

# Progress Report Form:  Table of Contents

# Report on progress made during 2004

  - Immunization Services Support (ISS)

1.1.1	Management of ISS Funds

  - Use of Immunization Services Support

1.1.3	Immunization Data Quality Audit

  - GAVI/Vaccine Fund New and Under-used Vaccines

1.2.1	Receipt of new and under-used vaccines

1.2.2	Major activities

    - Use if GAVI/The Vaccine Fund financial support (US$100,000) for introduction of the new vaccine

1.3	Injection Safety

    - Receipt of injection safety support

    - Progress of transition plan for safe injections and safe management of sharps waste

    - Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

2.  Financial Sustainability

3.  Request for new and under-used vaccine for 2007

  - Up-dated immunization targets

  - Confirmed/revised request for new vaccine (to be shared with UNICEF Supply Division) for year…

  - Confirmed/revised request for injection safety support for the year…

- Please report on progress since submission of the last Progress Report based on the indicators

selected by your country in the proposal for GAVI/VF support

5.  Checklist

6.  Comments

7.  Signatures

# 1.  	Report on progress made during 2005

To be filled in by the country for each type of support received from GAVI/The Vaccine Fund.

## Immunization Services Support (ISS)

#### 1.1.1	Management of ISS Funds

Please describe the mechanism for management of ISS funds, including the role of the Inter-Agency Co-ordinating Committee (ICC).

Please report on any problems that have been encountered involving the use of those funds, such as delay in availability for programme use.

No funds received for immunization support services ( Not applicable)

#### 1.1.2	Use of Immunization Services Support (Not applicable )

In 2004, the following major areas of activities have been funded with the GAVI/Vaccine Fund Immunization Services Support contribution.

Funds received during 2005

Remaining funds (carry over) from 2004 ________________

Table 1: Use of funds during 2005

| Area of Immunization Services Support | Total amount in US $ | AMOUNT OF FUNDS |
| --- | --- | --- |
|  |  | PUBLIC SECTOR | PRIVATE SECTOR & Other |
|  |  | Central | Region/State/Province | District |  |
| Vaccines |  |  |  |  |  |
| Injection Supplies |  |  |  |  |  |
| Personnel |  |  |  |  |  |
| Transportation |  |  |  |  |  |
| Maintenance and overheads |  |  |  |  |  |
| Training |  |  |  |  |  |
| IEC / social mobilization |  |  |  |  |  |
| Outreach |  |  |  |  |  |
| Supervision |  |  |  |  |  |
| Monitoring and evaluation |  |  |  |  |  |
| Epidemiological surveillance |  |  |  |  |  |
| Vehicles |  |  |  |  |  |
| Cold chain equipment |  |  |  |  |  |
| Other …………. (specify) |  |  |  |  |  |
| Total: |  |  |  |  |  |
| Remaining funds for next year: |  |  |  |  |  |

Please attach the minutes of the ICC meeting(s) when the allocation of funds was discussed.

Please report on major activities conducted to strengthen immunization, as well as, problems encountered in relation to your multi-year plan.

#### Immunization Data Quality Audit (DQA) (If it has been implemented in your country) NOT APPLICABLE

Has a plan of action to improve the reporting system based on the recommendations from the DQA been prepared?

If yes, please attach the plan.

## YES                              NO

## If yes, please report on the degree of its implementation.

Not applicable

## Please attach the minutes of the ICC meeting where the plan of action for the DQA was discussed and endorsed by the ICC.

Please report on studies conducted regarding EPI issues during 2005 (for example, coverage surveys).

Not applicable

## GAVI/Vaccine Fund New & Under-used Vaccines Support

#### 1.2.1	Receipt of new and under-used vaccines during 2005

Start of vaccinations with the new and under-used vaccine:           MONTH…December          YEAR…2005……….

Please report on receipt of vaccines provided by GAVI/VF, including problems encountered.

#### 1.2.2	Major activities

Please outline major activities that have been or will be undertaken, in relation to, introduction, phasing-in, service strengthening, etc. and report on problems encountered.

#### 1.2.3	Use of GAVI/The Vaccine Fund financial support (US$100,000) for the introduction of the new vaccine

Please report on the proportion of 100,000 US$ used, activities undertaken, and problems encountered such as delay in availability of funds for programme use.

Category in 2005 Actual Expenditure

## Injection Safety

#### 1.3.1	Receipt of injection safety support

Please report on receipt of injection safety support provided by GAVI/VF, including problems encountered

In May 2004, Bolivia was accepted in order to receive a support for safe injections for a sum of $ US 665,000 for three years. This support consists of a donation of auto-disable syringes and safety boxes; the first shipment was received in November 2005. The country had to negotiate additional funds with GAVI, through PAHO, in order to compensate for the changes in supply prices from the moment of approval to the moment of implementation of GAVI’s support. Besides the arrival of the shipment at the end of the year, a problem is that the received boxes have English-written signs and instructions (drawings) for burning that are not adequate for Bolivia, due to (1) the elevation of our country (at 4000 meters above sea level, the box does not burn) and (2) the environmental guidelines of the country that do not recommend the burning in open areas.

#### Progress of transition plan for safe injections and safe management of sharps waste.

#### Please report problems encountered during the implementation of the transitional plan for safe injection and sharp waste

The syringes AD are now used in all the municipalities of the country, and the supervision indicates that practices like recapping of syringes and keeping safety boxes full for several days are improving; however these indicators could be improved. An additional problem is the lack of consensus in the recommendations of the agencies that deal with biosafety within the country (including the use of safety boxes, etc). The EPI in collaboration with the agencies of the ICC is working to standardize the practices and to implement them into a national plan of action.

Please report on the progress based on the indicators chosen by your country in the proposal for GAVI/VF support.

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| percentage of vaccination sites that use AD syringes | 90% of vaccination sites use AD syringes | With the support of GAVI and the will of the country, Bolivia has totally introduced AD syringes. In 2005, 100% of the vaccination centers use AD syringes. | - the adequate use of AD syringes needs training. We have to make a guide for proper management in the application of the syringe. | Keep the 100%. |
| 2 Percentage of vaccination sites that use safety boxes. | 100% of the vaccination centers using biosafety boxes. | 50% of the health units use boxes of safety. | Due to the delayed arrival of the boxes from GAVI, it has not been possible to provide safety boxes to all the health facilities of the country as initially planned. | The initial goals are kept. |
| 3. Number of adverse events attributable to inappropriate injection techniques or to operational errors. | No adverse event attributable to immunizations due to incorrect injection safety practices. | No serious adverse event has been reported and investigated in 2005. | The country has a trained crisis management team (national and departmental), but the surveillance system is still not operating to 100% (it is not timely) | The initial goals are kept. |

#### 1.3.3	Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

The following major areas of activities have been funded (specify the amount) with the GAVI/The  Vaccine Fund injection safety support in the past year:

N/A

# 2.  	Financial sustainability

Inception Report:	Outline timetable and process for the development of a financial sustainability plan. Describe assistance that may be needed for developing a financial sustainability plan.

First Annual Progress Report: 	Submit completed financial sustainability plan by given deadline. Describe major strategies for improving financial sustainability.

The sources of financing of 2005 for the basic schedule (50%) was the General Treasury of the Nation, with the resources from the transfer of funds established by the Article 27 of the Law 2042 and its Regulatory Decree No. 27488. In December 2005, the country has managed to promulgate the vaccine legislation. Its regulations will make it possible to identify the financing entity for the program’s purchases, and ensure its financial sustainability, particularly for the purchase of vaccines and syringes (to 100%). These regulations are currently in process of development.

Subsequent Progress Reports:	According to current GAVI rules, support for new and under-used vaccines is covering the total quantity required to meet country targets (assumed to be equal to DTP3 targets) over a five year period (100% x 5 years = 500%).  If the requested amount of new vaccines does not target the full country in a given year (for example, a phasing in of 25%), the country is allowed to request the remaining (in that same example: 75%) in a later year.  In an attempt to help countries find sources of funding in order to attain financial sustainability by slowly phasing out GAVI/VF support, they are encouraged to begin contributing a portion of the vaccine quantity required.  Therefore, GAVI/VF support can be spread out over a maximum of ten years after the initial approval, but will not exceed the 500% limit (see figure 4 in the GAVI Handbook for further clarification).  In table 2.1, specify the annual proportion of five year GAVI/VF support for new vaccines that is planned to be spread-out over a maximum of ten years and co-funded with other sources. Please add the three rows (Proportion funded by GAVI/VF (%), Proportion funded by the Government and other sources (%), Total funding for ………….  (new vaccine)) for each new vaccine.

| Table 2.1: Sources (planned) of financing of new vaccine …………………… (specify) |
| --- |
| Proportion of vaccines supported by * | Annual proportion of vaccines |
|  | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 20.. | 20.. | 20.. | 20.. |
| A: Proportion funded by GAVI/VF (%)*** |  |  |  |  |  |  |  |  |  |  |
| B: Proportion funded by the Government and other sources (%) |  |  |  |  |  |  |  |  |  |  |

NB: GAVI has granted the government the rest of funds from vaccines and syringes for immunization support services from 2006. The government will finance the pentavelent, syringes and safety boxes from 2006.

* Percentage of DTP3 coverage (or measles coverage in case of Yellow Fever) that is target for vaccination with a new and under-used vaccine.

** The first year should be the year of GAVI/VF new vaccine introduction

*** Row A should total 500% at the end of GAVI/VF support

In table 2.2 below, describe progress made against major financial sustainability strategies and corresponding indicators.

Table 2.2:	Progress against major financial sustainability strategies and corresponding indicators (same indicators chosen to be reported on in 2003 ARP report, annually)

| Financial Sustainability Strategy | Specific Actions Taken Towards Achieving Strategy | Progress Achieved | Problems Encountered | Baseline Value of Progress Indicator | Current Value of Progress Indicator | Proposed Changes To Financial Sustainability Strategy |
| --- | --- | --- | --- | --- | --- | --- |

# 3.  	Request for new and under-used vaccines for year 2006

Section 3 is related to the request for new and under used vaccines and injection safety for 2007.

- Up-dated immunization targets

Confirm/update basic data approved with country application: figures are expected to be consistent with those reported in the WHO/UNICEF Joint

Reporting Forms.  Any changes and/or discrepancies MUST be justified in the space provided (page 12). Targets for future years MUST be provided.

| Number of | Achievements and targets |
| --- | --- |
|  | 2004 | 2005 | 2006 | 2007 | 2008 | 2010 | 2011 | 2012 |
| DENOMINATORS |  |  |  |  |  |  |  |  |
| Births (live) | 280,583 | 260,428 | 297,671 | 306,601 | 315,799 |  |  |  |
| Infants’ deaths | 18,799 | 1,656 | 19,944 | 20,542 | 21,158 |  |  |  |
| Surviving infants | 261,784 | 258,772 | 277,727 | 286,059 | 294,641 |  |  |  |
| Infants vaccinated in 2005 (JRF) / to be vaccinated in 2006 and beyond with 1st dose of Pentavalent* | 261,784 | 241,659 | 277,727 | 286,059 | 294,641 |  |  |  |
| Infants vaccinated in 2005 (JRF) / to be vaccinated in 2006 and beyond with 1st dose of Pentavalent* | 261,784 | 220,022 | 277,727 | 286,059 | 294,641 |  |  |  |
| NEW VACCINES ** |  |  |  |  |  |  |  |  |
| Infants vaccinated 2005 (JRF) / to be vaccinated in 2006 and beyond with 1st dose of DTP (DTP1) ( percentage %) |  |  |  |  |  |  |  |  |
| Infants vaccinated 2005 (JRF) / to be vaccinated in 2006 and beyond with 3rd dose of ___ ( Percentage) |  |  |  |  |  |  |  |  |
| Wastage rate in 2005 and plan for 2006 beyond*** ………….. ( new vaccine) |  |  |  |  |  |  |  |  |
| INJECTION SAFETY**** |  |  |  |  |  |  |  |  |
| WCBA vaccinated in 2005 (JRF) / to be vaccinated in 2006 and beyond with dT2 | 273,988 | 332,010 | 474,748 | 488,990 | 503,660 |  |  |  |
| Infants vaccinated in 2005 (JRF) / to be vaccinated in 2006 and beyond with BCG * | 280,583 | 228,137 | 297,671 | 306,601 | 315,799 |  |  |  |
| Children 12-23 months of age vaccinated in 2005 (JRF) / to be vaccinated in 2006 and beyond with MMR | 261,784 | 230,099 | 277,727 | 286,059 | 294,641 |  |  |  |
| Infants vaccinated in 2005 (JRF) / to be vaccinated in 2006 and beyond with Yellow Fever | 128,874 | 189,431 | 277,727 | 286,059 | 294,641 |  |  |  |

* Indicate actual number of children vaccinated in 2005 and updated targets (with either DTP alone or combined)

Please provide justification on changes to baseline, targets, wastage rate, vaccine presentation, etc. from the previously approved plan, and on reported figures which differ from those reported in the WHO/UNICEF Joint Reporting Form in the space provided below.

3.2	Availability of revised request for new vaccine (to be shared with UNICEF Supply Division) for 2007

In case you are changing the presentation of the vaccine, or increasing your request; please indicate below if UNICEF Supply Division has assured the availability of the new quantity/presentation of supply.

The achievements of 2005 correspond to the ones reported in WHO/UNICEF JRF of 2005.

Table 4: Estimated number of doses of pentavalent vaccine (specify for one presentation only): Please repeat this table for any other vaccine presentation requested from GAVI/The Vaccine Fund ( Not applicable)

*Please report the same figure as in table 3.

Table 5: Wastage rates and factors

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

#### 3.3	Confirmed/revised request for injection safety support for the years 2007 -2008

Table 6.1: Estimated supplies for safety of vaccination for the next two years with Pentavalent

#### If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference.

Table 6.2: Estimated supplies for safety of vaccination for the next two years with BCG

#### If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference.

Table 6.3: Estimated supplies for safety of vaccination for the next two years with MMR

#### If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference.

Table 6.4: Estimated supplies for safety of vaccination for the next two years with Yellow Fever

#### If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference.

Table 6: Estimated supplies for safety of vaccination for the next two years with dT

#### If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference.

# 4. 	Please report on progress since submission of the last Progress Report based on the indicators selected by your country in the proposal for GAVI/VF support

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| Percentage of vaccination sites that use AD syringes. | 90% of vaccination sites use AD syringes | With the support of GAVI and the will of the country, Bolivia has totally introduced AD syringes. In 2005, 100% of the vaccination centers use AD syringes. | The adequate use of AD syringes needs training. We have to make a guide for proper management in the application of the syringe. | Keep 100%. |
| 2 Percentage of vaccination sites that use safety boxes. | 100% of the vaccination centers using safety boxes. | 50% of the health units use safety boxes. | Due to the delayed arrival of the boxes from GAVI, it has not been possible to provide safety boxes to all the health facilities of the country as initially planned. | The initial goals are kept. |
| 3. Number of adverse events attributable to inappropriate injection techniques or to operational errors. | No adverse event attributable to immunizations due to incorrect injection safety practices. | No serious adverse event has been reported and investigated in 2005. | The country has a trained crisis management team (national and departmental), but the surveillance system is still not operating to 100% (it is not timely) | The initial goals are kept. |

# Checklist

Checklist of completed form:

| Form Requirement: | Completed | Comments |
| --- | --- | --- |
| Date of submission | yes |  |
| Reporting Period (consistent with previous calendar year) | 2005 |  |
| Table 1 filled-in | no |  |
| DQA reported on | no |  |
| Reported on use of 100,000 US$ | no |  |
| Injection Safety Reported on | yes |  |
| FSP Reported on (progress against country FSP indicators) | yes |  |
| Table 2 filled-in | no |  |
| New Vaccine Request completed | no |  |
| Revised request for injection safety completed (where applicable) | yes |  |
| ICC minutes attached to the report | yes |  |
| Government signatures | yes |  |
| ICC endorsed | yes |  |

6.  	Comments

ICC/RWG comments:

The country is considering the introduction of the rotavirus vaccine. The fiscal cycle of the country runs from January 2 to December 31.

7.	Signatures

For the Government of Bolivia: …Dr. Nilda Heredia Miranda, Minister of Health and Sports………

Signature:	……………………………………………...……………...

Date:	………………15 May 2006……………………….

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this report. Signature of endorsement of this document does not imply any financial (or legal) commitment on the part of the partner agency or individual.

Financial accountability forms an integral part of GAVI/The Vaccine Fund monitoring of reporting of country performance.  It is based on the regular government audit requirements as detailed in the Banking form.  The ICC Members confirm that the funds received have been audited and accounted for according to standard government or partner requirements.

| Agency/Organisation | Name/Title | Date Signature | Agency/Organisation | Name/Title | Date Signature |
| --- | --- | --- | --- | --- | --- |
| UNICEF | Guido Cornale UNICEF Representative - Bolivia | 25May06 |  |  |  |
| PAHO/WHO | Dr. Christian Darras PAHO/WHO Representative - Bolivia | 23May06 |  |  |  |

~ End ~

# Text boxes

Partnering with The Vaccine Fund

Remarks

Phasing: Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided Wastage of vaccines: Countries are expected to plan for a maximum of: 50% wastage rate for a lyophilized vaccine in 10 or 20-dose vial; 25% for a liquid vaccine in a10 or 20-dose vial; 10% for any vaccine (either liquid or lyophilized) in 1 or 2-dose vial. Buffer stock: The buffer stock is recalculated every year as 25% the current vaccine requirement Anticipated vaccines in stock at start of year 2006: It is calculated by counting the current balance of vaccines in stock, including the balance of buffer stock. Write zero if all vaccines supplied for the current year (including the buffer stock) are expected to be consumed before the start of next year. Countries with very low or no vaccines in stock must provide an explanation of the use of the vaccines. AD syringes: A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines. Reconstitution syringes: it applies only for lyophilized vaccines. Write zero for other vaccines. Safety boxes: A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes