Annual Progress Report 2006

Submitted by

The Government of

Bosnia and Herzegovina

to the

# Date of submission:  XX MAY 2007

Annual progress report (this report reports on activities in 2006 and specifies requests for 2008, Jan.-Dec.)

*Unless otherwise specified, documents may be shared with GAVI partners and collaborators as well as the general public.

Signatures Page for ISS, INS and NVS

For the Government of …… Bosnia and Herzegovina

| Ministry of Health: | Ministry of Finance: |
| --- | --- |
| Title: …………………………………… | Title: …………………………………… |
| Signature: …………………………………… | Signature: …………………………………… |
| Date: …………………………………… | Date: …………………………………… |

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this report. Signature of endorsement of this document does not imply any financial (or legal) commitment on the part of the partner agency or individual.

Financial accountability forms an integral part of GAVI Alliance monitoring of reporting of country performance.  It is based on the regular government audit requirements as detailed in the Banking form.

The ICC Members confirm that the funds received from the GAVI Funding Entity have been audited and accounted for according to standard government or partner requirements.

| Name/Title | Agency/Organisation | Signature | Date |
| --- | --- | --- | --- |
| Dr. Safet Omerović, Minister, | Federal Ministry of Health |  |  |
| Prof. Ranko Škrbić, Minister, | Ministry of Health and SW RS |  |  |
| Dr. Rankica Bahtijarevic, | Ministry of Civil Affairs |  |  |
| Dr. Mitar Tešanović, EPI Coordinator | Public Health Institute RS |  |  |
| Dr.Dragana Stojisavljevic,Director | Public Health Institute RS |  |  |
| Dr. Fani Majkić, EPI Coordinator | Federal Ministry of Health |  |  |
| Dr. Jasna Šadić, Epidemiologist, | Health department Brcko District |  |  |
| Dr. Zlatko Vučina, Director | Federal Public Health Institute |  |  |
| Dr. Aida Ćemerlić, Deputy Director | Federal Public Health Institute |  |  |
| Prof. Dr. Zlatko Puvačić | Federal Public Health Institute |  |  |
| Dr. Mirsada Mulaomerović | Federal Public Health Institute |  |  |
| Mr. Haris Hajrulahović,Head of WHO Office | WHO |  |  |
| Dr. Selena Bajraktarevic,Project Officer | UNICEF |  |  |

Signatures Page for HSS   Not applicable for B&H

For the Government of ……

| Ministry of Health: | Ministry of Finance: |
| --- | --- |
| Title: …………………………………… | Title: …………………………………… |
| Signature: …………………………………… | Signature: …………………………………… |
| Date: …………………………………… | Date: …………………………………… |

We, the undersigned members of the National Health Sector Coordinating Committee, ……………………………………… (insert name) endorse this report on the Health Systems Strengthening Programme. Signature of endorsement of this document does not imply any financial (or legal) commitment on the part of the partner agency or individual.

Financial accountability forms an integral part of GAVI Alliance monitoring of reporting of country performance.  It is based on the regular government audit requirements as detailed in the Banking form.

The HSCC Members confirm that the funds received from the GAVI Funding Entity have been audited and accounted for according to standard government or partner requirements.

| Name/Title | Agency/Organisation | Signature | Date |
| --- | --- | --- | --- |

# Progress Report Form:  Table of Contents

# Report on progress made during 2006

  - Immunization Services Support (ISS)

1.1.1	Management of ISS Funds

  - Use of Immunization Services Support

    - Immunization Data Quality Audit

    - ICC Meetings

  - GAVI Alliance New and Under-used Vaccines (NVS)

1.2.1	Receipt of new and under-used vaccines

1.2.2	Major activities

    - Use if GAVI Alliance financial support (US$100,000) for introduction of the new vaccine

    - Evaluation of Vaccine Management System

1.3		Injection Safety (INS)

    - Receipt of injection safety support

    - Progress of transition plan for safe injections and safe management of sharps waste

    - Statement on use of GAVI Alliance injection safety support (if received in the form of a cash contribution)

2.  Vaccine Co-financing, Immunization Financing and Financial Sustainability

3.  Request for new and under-used vaccine for 2008

  - Up-dated immunization targets

  - Confirmed/revised request for new vaccine (to be shared with UNICEF Supply Division) for year 2008 and projections for 2009 and 2010

  - Confirmed/revised request for injection safety support for the year 2008 and 2009

- Health System Strengthening (HSS)

- Checklist

- Comments

Text boxes supplied in this report are meant only to be used as guides.  Please feel free to add text beyond the space provided.

# 1.  	Report on progress made during 2006

## Immunization Services Support (ISS)

Are the funds received for ISS on-budget (reflected in Ministry of Health and Ministry of Finance budget): Yes/No

If yes, please explain in detail how it is reflected as MoH budget in the box below.

If not, explain why not and whether there is an intention to get them on-budget in the near future?

#### 1.1.1	Management of ISS Funds

Please describe the mechanism for management of ISS funds, including the role of the Inter-Agency Co-ordinating Committee (ICC).

Please report on any problems that have been encountered involving the use of those funds, such as delay in availability for programme use.

#### 1.1.2	Use of Immunization Services Support

In 2006, the following major areas of activities have been funded with the GAVI Alliance Immunization Services Support contribution.

Funds received during 2006 _______________

Remaining funds (carry over) from 2005 ________________

Balance to be carried over to 2007 __________________

Table 1: Use of funds during 2006*

| Area of Immunization Services Support | Total amount in US $ | AMOUNT OF FUNDS |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | PUBLIC SECTOR |  |  | PRIVATE SECTOR & Other |
|  |  | Central | Region/State/Province | District |  |
| Vaccines |  |  |  |  |  |
| Injection supplies |  |  |  |  |  |
| Personnel |  |  |  |  |  |
| Transportation |  |  |  |  |  |
| Maintenance and overheads |  |  |  |  |  |
| Training |  |  |  |  |  |
| IEC / social mobilization |  |  |  |  |  |
| Outreach |  |  |  |  |  |
| Supervision |  |  |  |  |  |
| Monitoring and evaluation |  |  |  |  |  |
| Epidemiological surveillance |  |  |  |  |  |
| Vehicles |  |  |  |  |  |
| Cold chain equipment |  |  |  |  |  |
| Other …………. (specify) |  |  |  |  |  |
| Total: |  |  |  |  |  |
| Remaining funds for next year: |  |  |  |  |  |

*If no information is available because of block grants, please indicate under ‘other’.

Please attach the minutes of the ICC meeting(s) when the allocation and utilization of funds were discussed.

Please report on major activities conducted to strengthen immunization, as well as problems encountered in relation to implementing your multi-year plan.

#### Immunization Data Quality Audit (DQA)   not applicable for B&H

Next* DQA scheduled for _________

*If no DQA has been passed, when will the DQA be conducted?

*If the DQA has been passed, the next DQA will be in the 5th year after the passed DQA

*If no DQA has been conducted, when will the first DQA be conducted?

What were the major recommendations of the DQA ?

Has a plan of action to improve the reporting system based on the recommendations from the DQA been prepared?

YES                              NO

## If yes, please report on the degree of its implementation and attach the plan.

## Please highlight in which  ICC meeting  the plan of action for the DQA was discussed and endorsed by the ICC.

Please report on studies conducted regarding EPI issues during 2006 (for example, coverage surveys).

1.1.4. ICC meetings

How many times did the ICC meet in 2006 ? Please attach all minutes.

Are any Civil Society Organizations members of the ICC and if yes, which ones ?

A Minutes Interagency Coordination Committee Meeting ### Sarajevo, 5 April 2006 Present: Dr Aida Ćemerlić, Deputy Director Federal PHI Dr. Mitar Tesanović, EPI Coordinator, RS Dr. Fani Majkic, EPI Coordinator, Federal Ministry of Health Dr. Mirsada Mulaomerović, Federal Public Health Institute Mr. Haris Hajrulahović, WHO B&H Dr. Rankica Bahtijarević, MOCA Kerry Neal, Project Officer IBCPS UNICEF B&H Dr Selena Bajraktarević, UNICEF B&H Other invited members of the GAVI entity committees or invitees who could not attend the meeting: Dr. Vjekoslav Mandić, Minister, Federal Ministry of Health Dr. Ranko Skrbić, Minister, Ministry of Health and Social Welfare, RS Dr. Milorad Balaban, Director, RS Public Health Institute Ms Mirjana Karahasanović, World Bank Dr. Šerifa Godinjak, Ministry of Civil Affairs, B&H Dr. Jasna Šadić, Epidemiologist, Brcko District Dr. Zlatko Vučina, Director, Federal Public Health Institute Prof. Dr. Zlatko Puvačić, Federal Public Health Institute Agenda - Vaccines Procurement Plan for 2006 and Action Plan for custom and vaccines transportation (Kerry, Selena, Srdjan) - Timetable of main GAVI related activities in 2006: Annual Progress Report (APR) towards sustainable introduction of HepB and injection safety -deadline 15 May; (Selena, Haris) Update and revision of Proposal to GAVI for Hib vaccines – deadline 6 June; (Selena, Haris) - Other Conclusions: - Due to lack of funds for vaccines procurement UNICEF BiH ordered 65% of OPV vaccines required by entity/district governments for year 2006, if money arrive required DTP and OPV will be ordered later ( UNICEF BiH) - The official letter with exact number of OPV doses ordered by UNICEF will be sent to EPI coordinators ( Dr. Selena Bajraktarevic) - MoCA will check who was the coordinating and proposing Ministry involved in procedure of signing the UNICEF’s Country Programme Action Plan 2005-2008 signed by Mr. A.Terzic. That information is needed for getting the approval for custom clearance from Ministry of Finance required for vaccines and syringes donated by GAVI ( Dr. Rankica Bahtijarevic) - Federal Ministry of Health will inform ICC members how they overcome the problem related to the custom clearance documents (Dr. Fani Majkic) - For the first time entity governments toke over custom clearance and internal transportation of vaccines and devices provided by UNICEF/GAVI. Due to complex administrative structure of the country many difficulties occurred and delay in getting all papers needed for import of syringes which are already stored in central warehouse of transportation company Lagermax. UNICEF agreed if necessary to pay for storage of syringes on the exceptionally basis but no longer than 15 days of storage. It means that UNICEF will pay for storage only till 15 April no longer then that date. - ICC members proposed instead of three to put only one consignee address for vaccines and devices in order to simplify very complicated procedure in getting all papers for custom clearance. Also, ICC members proposed to invite both Ministers of Health on the next ICC meeting to discuss that issue with them. ( UNICEF BiH ) - According to the Low on VAT article 29, By low on VAT low enforcement articles 52 and 62 entity governments can ask for VAT to be paid back - WHO consultant Dr. Patrick Olin is coming on 25 April to Bosnia and he will provide assistance to immunizations entities team in preparation of the Annual Progress GAVI Report (APR) on HepB and injection safety. Also, the application for Hib introduction will be revised and updated in order to be submitted to GAVI by 6 June. The deadline for the submission of APR is 15 May. - The next ICC meeting will be organized on the end of Patrick’s mission mid of May. (UNICEF BiH) B Minutes 2nd Interagency Coordination Committee Meeting ### Sarajevo, 4 May 2006 Present: Dr. Milorad Balaban, Director PHI RS Dr. Mitar Tesanović, EPI Coordinator, RS Dr. Fani Majkic, EPI Coordinator, Federal Ministry of Health Dr. Mirsada Mulaomerović, Federal Public Health Institute Prof. Dr. Zlatko Puvacic, Federal PHI Dr. Patrick Olin, Consultant WHO Dr. Selena Bajraktarević, UNICEF B&H Other invited members of the GAVI entity committees or invitees who could not attend the meeting: Dr. Vjekoslav Mandić, Minister, Federal Ministry of Health Dr. Ranko Skrbić, Minister, Ministry of Health and Social Welfare, RS Dr. Zlatko Vucina, Director, Federal PHI Ms. Mirjana Karahasanović, World Bank Dr. Šerifa Godinjak, Ministry of Civil Affairs, B&H Dr. Jasna Šadić, Epidemiologist, Brcko District Dr. Aida Cemerlic, Deputy Director, Federal PHI Mr. Haris Hajrulahovic, WHO LO Agenda - Review of WHO/UNICEF Joint Reporting Immunization Form for the year 2005 (Dr. S. Bajraktarevic; UNICEF, Dr. P.Olin; WHO) - Presentation of the Annual Progress Report (APR) towards sustainable introduction of HepB and injection safety ; (Dr. P. Olin; WHO) - Presentation of Bosnia and Herzegovina’s proposal for Hib vaccine revised according to the GAVI request (Dr. P. Olin; WHO) - Other Conclusions: - The members of ICC agreed to submit required amendments/changes to Joint Reporting Immunization Form and Annual Progress GAVI Report for BiH for 2005 by tomorrow, Friday, 5 May - Dr. Majkic and Dr. Tesanovic will update financial report within APR as well as detailed description of legislation related to vaccines purchase procedure. - The Annual Progress Report to GAVI is approved and accepted by ICC members and will be signed by both entity Ministers of Health before submission to GAVI Secretariat - With regards to Hib vaccine proposal, it was agreed to add estimated coverage for Hib1 and Hib2 into the existing table. - The Immunization Advisory Body will meet on 10May to discuss the piloted Hib vaccination in Federation of BiH. After that meeting Federal Minister of Health will be able to complete the Hib proposal and to provide required explanation for the GAVI. - All ICC members agreed that Hib vaccine proposal will be submitted to GAVI by 6th June, with required explanation and hope that GAVI will accept and approve the support for introduction of Hib vaccination for the whole country, since governments of BiH is not able to afford sustainable Hib vaccination from their funds. C Minutes 3rd Interagency Coordination Committee Meeting ### Sarajevo, 5 June 2006 Present: Dr. Aida Cemerlic, Deputy Director PHI FBIH Dr. Senka Dimitrijevic, on behalf of Dr. Balaban and Dr. Tesanovic Dr. Fani Majkic, EPI Coordinator, Federal Ministry of Health Dr. Mirsada Mulaomerović, Federal Public Health Institute Dr. Brankica Bahtijarevic, Ministry of Civil Affairs BiH Dr. Patrick Olin, Consultant WHO (conference call) Mr. Haris Hajrulahovic, WHO Dr. Selena Bajraktarević, UNICEF B&H Other invited members of the GAVI entity committees or invitees who could not attend the meeting: Dr. Vjekoslav Mandić, Minister, Federal Ministry of Health Dr. Ranko Skrbić, Minister, Ministry of Health & Social Welfare, RS Dr. Zlatko Vucina, Director, Federal PHI Ms. Mirjana Karahasanović, World Bank Dr. Šerifa Godinjak, Ministry of Civil Affairs, B&H Dr. Jasna Šadić, Epidemiologist, Brcko District Dr. Milorad Balaban, Director, RS PHI Dr. Mitar Tesanovic, EPI Coordinator, RS Agenda - Approval of HIB Proposal revised by BH Governments according to the GAVI letter Conclusions: The members of ICC have approved revised Proposal for introduction of Hib vaccine in accordance with GAVI requirements, and will forward electronic copy to GAVI Secretariat by COB today. The signed copy of the document will be forwarded to GAVI Secretariat by the Minister of Civil Affairs of BiH as soon as possible. D Minutes Subject: Minutes from GAVI (Global Alliance for Vaccines and Immunization) Interagency Coordination Committee Meeting, 05/09/2006 Present: Dr. Zlatko Vucina, Director, Federal PHI Dr. Aida Cemerlic, Dy Director, Federal PHI Dr. Jasminka Vuckovic, RS MoHSW Prof. Dr. Zlatko Puvacic, Federal PHI Dr. Rankica Bahtijarevic, MoCA BiH Dr. Mirsada Mulaomerovic, Federal PHI Dr. Mitar Tesanovic, EPI coordinator RS (on phone) Dr. Selena Bajraktarevic, UNICEF Agenda: - Additional clarifications required by GAVI for Hib introduction Conclusions: The response to GAVI containing additional clarifications requested in GAVI Executive Director’s letter to B&H Minister of Civil Affairs dated 18 August 2006, should be prepared by Dr. Mirsada Mulaomerovic and Dr. Selena Bajraktarevic by Friday, 8 September and forwarded to the Minister of Civil Affairs for signature and submission to GAVI Secretariat. The members of the ICC agreed that the existing capacities of the cold chain in both entities are sufficient for storage of Hib vaccine, and response will be based on WHO reports on Cold chain capacities in B&H as well as governments’ assessment of cold chain capacity. The government representatives have opted for twice a year supplies of Hib vaccine. It was also agreed that cold chain indicators should be added to the Action Plan.

1.2. GAVI Alliance New & Under-used Vaccines Support (NVS)

#### Receipt of new and under-used vaccines during 2006

When was the new and under-used vaccine introduced? Please include change in doses per vial and change in presentation, (e.g. DTP + HepB mono to DTP-HepB) and dates shipment were received in 2006.

| Vaccine | Vials size | Doses | Date of Introduction | Date shipment received (2006) |
| --- | --- | --- | --- | --- |
| HepB for Srpska | 10 dose vial | 16,200 |  | 09-Jun-06 |
| HepB for Federation of B&H | (10 dose vial) | 31,400 | 1.5.2004. | 09-Jun-06 |
| HepB for Brcko | (10 dose vial) | 1,500 |  | 09-Jun-06 |
| HepB for Srpska | (1 dose vial) | 26,250 |  | 09-Jun-06 |
| HepB for Federation of B&H | (1 dose vial) | 25,760 | 1.5.2004. | 09-Jun-06 |
| HepB for Brcko | (1 dose vial) | 1,610 |  | 09-Jun-06 |
| AD syringes for Srpska |  | 32,700 |  | 24-Mar-06 |
| AD syringes for Federation of B&H |  | 63,500 |  | 24-Mar-06 |
| AD syringes for Brcko |  | 3,000 |  | 24-Mar-06 |
| Safety Boxes for Srpska |  | 375 |  | 24-Mar-06 |
| Safety boxes for Federation of B&H |  | 700 |  | 24-Mar-06 |
| Safety boxes for Brcko |  | 50 |  | 24-Mar-06 |

Please report on any problems encountered.

F-BiH: Problems with customs procedures, which caused delay in vaccine delivery. Thanks to existing buffer stock, there were no interruptions in the program RS: Didn’t have any major problems. Brcko: “

#### Major activities

Please outline major activities that have been or will be undertaken, in relation to, introduction, phasing-in, service strengthening, etc. and report on problems encountered.

BiH, national level. A revised proposal for support of Hib introduction was submitted to GAVI and approved by the Gavi Board in October 2006. The pilot Hib introduction in F-BiH was phased out to be replaced in 2007 by national introduction of GAVI funded Hib vaccine provided by Unicef. F-BiH: Public Health Institute of the Federation of BiH implemented the following activities in 2006: - Harmonization of the Decree on mandatory immunization program implementation, for the year 2006; - Monitoring of the program – monthly/annually, pertaining to EPI vaccines coverage, vaccine consumption and wastage, immunization adverse effects – continuous and timely; - Quarterly reporting of Cantonal EPI Coordinators on immunization coverage and vaccine consumption – analysis and discussions; - Data quality control – analysis, discussions; - Several educational meetings/consultations were organized for program personnel, with focus on the following topics: - Importance of quality enhancement of immunization program - New methods in active investigation of reasons for low coverage (Professor Zlatko Puvačić) - List of indicators for immunization program quality monitoring - Current problems - Intensifying activities on increasing immunization coverage :Monitoring of unvaccinated children“ (based on proposal of National EPI Coordinator for FBiH and evaluated as important for assessment of FBiH immunization program quality by epidemiologists and paediatricians); - Identification of Roma and refugee settlements; - Supplementary immunization campaigns in Roma settlements; - Supplementary OPV immunization campaign in the Federation of BiH; - During the Congress of Epidemiologists, which was organized in Neum in 2006, a number of current immunization issues was discussed, including a number of presentations focused on success and acceptance of Hepatitis B vaccine; - Two successful TV programs dedicated to immunization, with one of their segments focusing on “new” Hepatitis B vaccine; - Number of activities pertaining to application of Hib vaccines, supplied by GAVI; - Central-level cold storage control (work with the consultant); - Work with Professor V. Zlobin on reporting and development of plan of action in relation to acute flaccid paralysis surveillance. There were no reported severe adverse effects in relation to Hib vaccine or refusal to administer / receive Hib vaccine by health professionals/parents! RS During 2006 the EPI-manager held 8 seminars in all regions of Republika Srpska on immunization with special attention to vaccination against Hepatitis B Brcko Monitoring of the program and reporting.

#### Use of GAVI funding entity support (US$100,000) for the introduction of the new vaccine

These funds were received on : GAVI/VF financial support was distributed between Federation of Bosnia and Herzegovina, Republic of Srpska and Brcko District based on an ICC decision in 2003, as 52%, 44% and 3% respectively

Please report on the proportion of 100,000 US$ used, activities undertaken, and problems encountered such as delay in availability of funds for programme use.

Entities and national Distributed amount %; Received amount in local currency (BAM); Utilized amount BAM (% in 2004); Utilized amount BAM (% in 2005); Utilized amount BAM (% in 2006); Remaining amount BAM (% by end of 2006). Federation of Bosnia and Herzegovina; 52%; 86,373.98 (100%); 32,171.76 (37%); 20,212 (24%); 16,440,28 (19%); 17 549,94 (20%). Republic of Srpska; 44%; 72,968.65 (100%); 36332.6 (50%); 3,000 4%; 16,100 22; 17,536.05 KM 24.%. Brcko District; 3%; 5,000 (100%); 2,500 (50%); 2,500 (50%); 0; 0. Bank charges; 1%; Not relevant; Not relevant; Not relevant; Not relevant; Not relevant. BiH; 100%; 164,342.63; 71004.36; 25,712; 32,540,28; 35085,99 (21%). In 2006, financial support were used for following activities; - Federation of Bosnia and Herzegovina (16,440.28 BAM, 19% of total allocated amount to FBiH) There were 7 educational seminars in FBiH PHI and 11 technical meetings in Sarajevo, Srednja Bosna and Zapadna Hercegovina cantons in 2006, aimed at providing technical assistance. There were 8 consultation meetings, which included visits to the field in Tuzla, Zenica-Doboj, Srednja Bosna, Sarajevo and Bosansko Podrinje cantons. Seminars were organized with assistance of either consultants and local experts or local experts only and were focused on the following topics: evaluation of Hepatitis B immunization, introduction of Hib vaccine into immunization of children program in FBiH, planning, reporting, cold chain, injection safety, counter-indications, communication and current problems. - Republic of Srpska (14 100 BAM, 4 % of total allocated amount to RS) for 8 training seminars Brcko No allocated funds left for 2006

    - Effective Vaccine Store Management/Vaccine Management Assessment

The last Effective Vaccine Store Management (EVSM)/Vaccine Management Assessment (VMA) was conducted in June 200

Please summarize the major recommendations from the EVSM/VMA F-BiH PHI

Effective Vaccine Store Management Assessment of National Store 12-30 June 2006 Major Recommendations (adopted from report by Dr Ahmet Afşar, WHO Consultant) - Redesign the vaccine and logistics management as a requisition system or an allocation system for each level with clear guidelines of forecasting and certain minimum and maximum stock levels. - Use different forecasting methods such as historical logistics data analysis for validating forecasts by logistic managers at al levels. - Train Canton/municipality health service staff on vaccine and logistics management and forecasting - Develop and document Standard operating procedures - Increase quality and number of supervisory visits to canton/municipality stores and health centres - Reorganise Vaccine Stores and Dry Stores for syringes etc. according to proper storage guidelines - Record and report Minimum logistics information at all levels. - Record and report Diluents separately at all levels. - Collect and report All data on standard forms and reports. - Process and analyse Data at all levels. - Establish a feedback reporting system to increase data quality and services - A Supervised Delivery System may help solving many of the distribution, data collection and supervision problems. A tentative agenda for further activities was suggested

Was an action plan prepared following the EVSM/VMA : Yes/No

If so, please summarize main activities under the EVSM plan and the activities to address the recommendations.

F-BiH: no formal action plan has been prepared, however the following activities are ongoing to address the recommendations - Education of health professionals in the areas of planning and cold chain logistics - Publishing guidelines - Recommendations for replacement of refrigerators in accordance with FSP RS Inadequate capacity of cold chain due to outdated refrigerators needs to be addressed A reserve system of cold chain should be established Brcko

The next EVSM/VMA* will be conducted in : Follow-up is planned for May 2007

## *All countries will need to conduct an EVSM/VMA in the second year of new vaccine support approved under GAVI Phase 2.

## 1.3 Injection Safety

#### Receipt of injection safety support

Received in cash/kind

Please report on receipt of injection safety support provided by the GAVI Alliance during 2006 (add rows as applicable).

| Injection Safety Material | Quantity | Date received |
| --- | --- | --- |
| BCG Syringes (AD) for Srpska | 15,300 | 24-Mar-06 |
| BCG Syringes (AD) for Federation of B&H | 29,700 | 24-Mar-06 |
| BCG Syringes (AD) for Brcko | 1,400 | 24-Mar-06 |
| AD Syringes for Srpska | 59,000 | 24-Mar-06 |
| AD Syringes for Federation of B&H | 114,400 | 24-Mar-06 |
| AD Syringes for Brcko | 5,400 | 24-Mar-06 |
| Reconstitution Syringes 2.0 ml (BCG) for Srpska | 3,100 | 24-Mar-06 |
| Reconstitution Syringes 2.0 ml (BCG) for Federation of B&H | 5,900 | 24-Mar-06 |
| Reconstitution Syringes 2.0 ml (BCG) for Brcko | 300 | 24-Mar-06 |
| Reconstitution Syringes 5.0 ml (Measles) for Srpska | 2,400 | 24-Mar-06 |
| Reconstitution Syringes 5.0 ml (Measles) for Federation of B&H | 4,700 | 24-Mar-06 |
| Reconstitution Syringes 5.0 ml (Measles) for Brcko | 200 | 24-Mar-06 |
| Safety Boxes for Srpska | 900 | 24-Mar-06 |
| Safety Boxes for Federation of B&H | 1,725 | 24-Mar-06 |
| Safety Boxes for Brcko | 75 | 24-Mar-06 |

Please report on any problems encountered.

F-BiH Customs procedure took too long and caused delay in delivery of syringes and safety boxes. Health professionals which use AD syringes complained that needles were not sharp enough and that needle-tip diameter makes vaccine administration difficult. BCG AD syringes are being used. RS AD syringes and injections and safety boxes for waste we get from GAVI. Brcko

#### Progress of transition plan for safe injections and safe management of sharps waste.

If support has ended, please report how injection safety supplies are funded.

#### F-BiH #### Cantonal Health Insurance and Re-Insurance Funds still provide funds for injection safety (FSP). #### RS In RS sharps waste are placed in safety boxes and transported to waste collection posts. #### In 2006 the Government of Republika Srpska has initiated a pilot study to resolve final disposal of medical waste including sharps waste. New chemico-physical destruction equipments are tested at a few health clinics. A entity-wide introduction is planned during 2007-8

#### Please report how sharps waste is being disposed of.

#### Since 2006 all scarps waste from vaccines administered in the national immunization programme is placed in safety boxes in accordance with GAVI injection support obligations. #### The final disposal of filled safety boxes is mainly not satisfactory at present. Incinerators or other means of chemical or physical destruction have so far only occasionally been used

#### Please report problems encountered during the implementation of the transitional plan for safe injection and sharps waste.

#### Some vaccination centres complain that AD injections are not good and not from same manufacturer, so they get injections and needles for vaccination from other sources.

#### Statement on use of GAVI Alliance injection safety support in 2006 (if received in the form of a cash contribution)

The following major areas of activities have been funded (specify the amount) with the GAVI Alliance injection safety support in the past year:

Not applicable

# 2. 	Vaccine Co-financing, Immunization Financing and Financial Sustainability

Important note: Under Phase 2 of the GAVI Alliance, all countries are expected to co-finance the introduction of new vaccines from the start of Phase 2 (except for the introduction of measles second dose into routine immunization). The Annual Progress Report has been modified to help monitor the experiences of countries with the new GAVI Alliance policies of vaccine co-financing. We are asking countries to complete three new tables of information and answer some questions about your experience.

The purpose of Table 2 is to understand trends in overall immunization expenditure and financing context. It provides key updated cMYP information on an annual basis.

Table 3 is designed to help the GAVI Alliance understand country level co-financing of GAVI awarded vaccines - both in terms of doses and in terms of monetary amounts. If your country has been awarded more than one new vaccine in Phase 2 through GAVI Alliance, please complete a separate table for each new vaccine being co-financed.

The purpose of Table 4 is to understand the country-level processes related to integration of co-financing requirements into national planning and budgeting.

Much of the information for all three tables can be extracted from the comprehensive multi-year plan, as well as the country proposal to GAVI, and the confirmation letter from the Alliance. For 2006, the figures recorded should be actual updated expenditures, not projections. Please report for the years till the end of your cMYP. Total co-financing can be calculated with the XL sheet provided for calculating the vaccine request.

| Table 2: Total Immunization Expenditures and Financing Trends in US $ |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Total Immunization Expenditures and Financing | 2006 | 2007 | 2008 | 2009 | 2010 |
| Immunization Expenditures |  |  |  |  |  |
| Vaccines |  |  |  |  |  |
| Injection supplies |  |  |  |  |  |
| Personnel |  |  |  |  |  |
| Other operational expenditures |  |  |  |  |  |
| Cold Chain equipment |  |  |  |  |  |
| Vehicles |  |  |  |  |  |
| Other |  |  |  |  |  |
| Total Immunization Expenditures |  |  |  |  |  |
| Total Government Health Expenditures |  |  |  |  |  |
| Immunization Financing |  |  |  |  |  |
| Government (incl. WB loans) |  |  |  |  |  |
| GAVI |  |  |  |  |  |
| UNICEF |  |  |  |  |  |
| WHO |  |  |  |  |  |
| World Bank (grant) |  |  |  |  |  |
| Other (please specify) |  |  |  |  |  |
| Other (please specify) |  |  |  |  |  |
| Total Financing |  |  |  |  |  |

| Table 3a: Country Vaccine Co-Financing in US $ |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| For 1st GAVI awarded vaccine. Please specify which vaccine (ex: DTP-HepB) |  |  |  |  |  |
| Actual and Expected Country Co-Financing | 2006 | 2007 | 2008 | 2009 | 2010 |
| Total number of doses co-financed by country |  |  |  |  |  |
| Total co-financing by country |  |  |  |  |  |
| Of which by |  |  |  |  |  |
| Government |  |  |  |  |  |
| Basket/Pooled Funding |  |  |  |  |  |
| Other (please specify) |  |  |  |  |  |
| Other (please specify) |  |  |  |  |  |
| Other (please specify) |  |  |  |  |  |
| Total Co-Financing |  |  |  |  |  |

| Table 3b: Country Vaccine Co-Financing in US $ |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| For 2nd GAVI awarded vaccine. Please specify which vaccine (ex: DTP-HepB) |  |  |  |  |  |
| Actual and Expected Country Co-Financing | 2006 | 2007 | 2008 | 2009 | 2010 |
| Total number of doses co-financed by country |  |  |  |  |  |
| Total co-financing by country |  |  |  |  |  |
| Of which by |  |  |  |  |  |
| Government |  |  |  |  |  |
| Basket/Pooled Funding |  |  |  |  |  |
| Other (please specify) |  |  |  |  |  |
| Other (please specify) |  |  |  |  |  |
| Other (please specify) |  |  |  |  |  |
| Total Co-Financing |  |  |  |  |  |

| Table 3c: Country Vaccine Co-Financing in US$ |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| For 3rd GAVI awarded vaccine. Please specify which vaccine (ex: DTP-HepB) |  |  |  |  |  |
| Actual and Expected Country Co-Financing | 2006 | 2007 | 2008 | 2009 | 2010 |
| Total number of doses co-financed by country |  |  |  |  |  |
| Total co-financing by country |  |  |  |  |  |
| Of which by |  |  |  |  |  |
| Government |  |  |  |  |  |
| Basket/Pooled Funding |  |  |  |  |  |
| Other (please specify) |  |  |  |  |  |
| Other (please specify) |  |  |  |  |  |
| Other (please specify) |  |  |  |  |  |
| Total Co-Financing |  |  |  |  |  |

| Table 4: Questions on Vaccine Co-Financing Implementation |  |  |  |
| --- | --- | --- | --- |
| Q. 1: What mechanisms are currently used by the Ministry of Health in your country for procuring EPI vaccines? |  |  |  |
|  | Tick for Yes | List Relevant Vaccines | Sources of Funds |
| Government Procurement- International Competitive Bidding |  |  |  |
| Government Procurement- Other |  |  |  |
| UNICEF |  |  |  |
| PAHO Revolving Fund |  |  |  |
| Donations |  |  |  |
| Other (specify) |  |  |  |
| Q. 2: How have the proposed payment schedules and actual schedules differed in the reporting year? |  |  |  |
| Schedule of Co-Financing Payments | Proposed Payment Schedule | Date of Actual Payments Made in Reporting Year | Delay in Co-Financing Payments |
|  | (month/year) | (day/month) | (days) |
| 1st Awarded Vaccine (specify) |  |  |  |
| 2nd Awarded Vaccine (specify) |  |  |  |
| 3rd Awarded Vaccine (specify) |  |  |  |
| Q. 3: Have the co-financing requirements been incorporated into the following national planning and budgeting systems ? |  |  |  |
|  | Tick for Yes | List Relevant Vaccines |  |
| Budget line item for vaccine purchasing |  |  |  |
| National health sector plan |  |  |  |
| National health budget |  |  |  |
| Medium-term expenditure framework |  |  |  |
| SWAp |  |  |  |
| cMYP Cost & Financing Analysis |  |  |  |
| Annual immunization plan |  |  |  |
| Other |  |  |  |

| Q. 4: What factors have slowed and/or hindered mobilization of resources for vaccine co-financing ? |  |
| --- | --- |
| 1. |  |
| 2. |  |
| 3. |  |
| 4. |  |
| 5. |  |
| Q. 5: Do you foresee future challenges with vaccine co-financing in the future? What are these ? |  |
| 1. |  |
| 2. |  |
| 3. |  |
| 4. |  |
| 5. |  |

3.  	Request for new and under-used vaccines for year 2008

Section 3 is related to the request for new and under-used vaccines and injection safety for 2008.

- Up-dated immunization targets

Confirm/update basic data approved with country application: figures are expected to be consistent with those reported in the WHO/UNICEF Joint Reporting Forms.  Any changes and/or discrepancies MUST be justified in the space provided. Targets for future years MUST be provided.

Please provide justification on changes to baseline, targets, wastage rate, vaccine presentation, etc. from the previously approved plan, and on reported figures which differ from those reported in the WHO/UNICEF Joint Reporting Form in the space provided below.

The number of births in the JRF for 2005 and 2006 are based on the reported number of births from the maternity wards. Estimated birth cohorts for 2007 to 2013 are based on data from the Bureau of statistics in the two entities. Thus the source of data differs for 2005-6 and 2007-13 explaining the slight change in reported birth rates in 2006 and predicted rate in 2007.

| Table 5 : Update of immunization achievements and annual targets. Provide figures as reported in the JRF in 2006 and projections from 2007 onwards. |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of | Achievements and targets |  |  |  |  |  |  |  |  |
|  | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 |
| DENOMINATORS |  |  |  |  |  |  |  |  |  |
| Births | 33,973 | 31,790 | 32,520 | 32,658 | 32,777 | 33,036 | 33,115 | 33,205 | 33,300 |
| Infants’ deaths | 233 | 215 | 220 | 221 | 222 | 223 | 224 | 225 | 225 |
| Surviving infants | 34,093 | 32,438 | 32,256 | 32,399 | 32,521 | 32,785 | 32,865 | 32,956 | 33,052 |
| Infants vaccinated till 2006 (JRF) / to be vaccinated in 2007 and beyond with 1st dose of DTP (DTP1)* | 32,049 | 30,550 | 30,643 | 30,779 | 30,895 | 31,145 | 31,222 | 31,308 | 31,399 |
| Infants vaccinated till 2006 (JRF) / to be vaccinated in 2007 and beyond with 3rd dose of DTP (DTP3)* | 30,642 | 28,373 | 30,643 | 30,779 | 30,895 | 31,145 | 31,222 | 31,308 | 31,399 |
| NEW VACCINES ** |  |  |  |  |  |  |  |  |  |
| Infants vaccinated till 2006 (JRF) / to be vaccinated in 2007 and beyond with 1st dose of HepB (HepB1)* …......... (new vaccine) | 32,940 | 30,948 | 31,544 | 31,678 | 31,793 | 32,045 | 32,122 | 32,209 | 32,301 |
| Infants vaccinated till 2006 (JRF) / to be vaccinated in 2007 and beyond with 3rd dose of HepB3 (new vaccine) | 30,162 | 29,130 | 30,643 | 30,779 | 30,895 | 31,145 | 31,222 | 31,308 | 31,399 |
| Wastage rate till 2006 and plan for 2007 beyond*** HepB1 and Hep2, monodose vial ( new vaccine) | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 |
| Wastage rate till 2006 and plan for 2007 beyond*** HepB3, 10-dose vial ( new vaccine) | 1.33 | 1.33 | 1.33 | 1.33 | 1.33 | 1.33 | 1.33 | 1.33 | 1.33 |
| Infants vaccinated till 2006 (JRF) / to be vaccinated in 2007 and beyond with 1st dose of Hib (Hib1)* |  | 20,095 | 30,643 | 30,779 | 30,895 | 31,145 | 31,222 | 31,308 | 31,399 |
| Infants vaccinated till 2006 (JRF) / to be vaccinated in 2007 and beyond with 3rd dose of…Hib3 (new vaccine) |  | 18,839 | 31,104 | 29,775 | 29,664 | 29,608 | 29,579 | 29,565 | 29,558 |
| Wastage rate till 2006 and plan for 2007 beyond*** Hib ( | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 |
| INJECTION SAFETY**** |  |  |  |  |  |  |  |  |  |
| Infants vaccinated / to be vaccinated with BCG | 32,353 | 30,948 | 31,544 | 31,678 | 31,793 | 32,045 | 32,122 | 32,209 | 32,301 |
| Infants vaccinated / to be vaccinated with Measles (1st dose) | 31,243 | 27,459 | 29,998 | 29,775 | 29,664 | 29,608 | 29,579 | 29,565 | 29,558 |

* Indicate actual number of children vaccinated in past years and updated targets (with either DTP alone or combined)

** Use 3 rows (as indicated under the heading NEW VACCINES) for every new vaccine introduced

*** Indicate actual wastage rate obtained in past years

**** Insert any row as necessary

  - Confirmed/Revised request for new vaccine (to be shared with UNICEF Supply Division)

for 2008

In case you are changing the presentation of the vaccine, or increasing your request; please indicate below if UNICEF Supply Division has assured the availability of the new quantity/presentation of supply.

#### Please provide the XL sheet for calculating vaccine request duly completed and summarize in table 6 below. For calculations, please use same targets as in table 5.

Table 6a.  Estimated number of doses of Hep B vaccine, monodose presentation.  (Please provide additional tables for additional vaccines and number them 6a, 6b, 6c etc)

| Vaccine : | 2008 | 2009 | 2010 |
| --- | --- | --- | --- |
| Total doses required | 66524 | 66765 |  |
| Doses to be funded by GAVI | 45298 | 45651 |  |
| Doses to be funded by country | 21226 | 21146 |  |
| Country co-pay in US$/dose* |  |  |  |
| Total co-pay | 13417 | 13816 |  |

*As per GAVI co-financing policy, country grouping and order of vaccine introduction

Table 6b.  Estimated number of doses of Hep B  vaccine 10-dose presentation.  (Please provide additional tables for additional vaccines and number them 6a, 6b, 6c etc)

| Vaccine : | 2008 | 2009 | 2010 |
| --- | --- | --- | --- |
| Total doses required | 40936 | 41090 |  |
| Doses to be funded by GAVI | 40936 | 41090 |  |
| Doses to be funded by country | 0 | 0 |  |
| Country co-pay in US$/dose* |  |  |  |
| Total co-pay | 0 | 0 |  |

*As per GAVI co-financing policy, country grouping and order of vaccine introduction

Table 6c.  Estimated number of doses of Hib vaccine, monodose presentation.  (Please provide additional tables for additional vaccines and number them 6a, 6b, 6c etc)

| Vaccine : | 2008 | 2009 | 2010 |
| --- | --- | --- | --- |
| Total doses required | 96864 | 97319 | 98106 |
| Doses to be funded by GAVI | 96864 | 97319 | 98106 |
| Doses to be funded by country | 0 | 0 | 0 |
| Country co-pay in US$/dose* |  |  |  |
| Total co-pay | 0 | 0 | 0 |

*As per GAVI co-financing policy, country grouping and order of vaccine introduction

Remarks

- Phasing: Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided

- Wastage of vaccines: Countries are expected to plan for a maximum of 50% wastage rate for a lyophilized vaccine in 10 or 20-dose vial; 25% for a liquid vaccine in a10 or 20-dose vial; 10% for any vaccine (either liquid or lyophilized) in a 2-dose vial, 5% for any vaccine in 1 dose vial liquid.

- Buffer stock: The buffer stock is recalculated every year as 25% the current  vaccine requirement

- Anticipated vaccines in stock at start of year 2008: It is calculated by counting the current balance of vaccines in stock, including the balance of buffer stock.  Write zero if all vaccines supplied for the current year (including the buffer stock) are expected to be consumed before the start of next year. Countries with very low or no vaccines in stock must provide an explanation of the use of the vaccines.

- AD syringes: A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines.

- Reconstitution syringes: it applies only for lyophilized vaccines. Write zero for other vaccines.

- Safety boxes: A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes

Table 7: Wastage rates and factors

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

#### 3.3   Confirmed/revised request for injection safety support for the year 2008

Table 8a: Estimated supplies for safety of vaccination for the next two years with BCG (Use one table for each vaccine BCG, DTP, measles and TT, and number them from 8a, 8b, 8c, etc. Please use same targets as in Table 5)

Table 8b: Estimated supplies for safety of vaccination for the next two years with DTP (Use one table for each vaccine BCG, DTP, measles and TT, and number them from 8a, 8b, 8c, etc. Please use same targets as in Table 5)

Table 8c: Estimated supplies for safety of vaccination for the next two years with MMR (Use one table for each vaccine BCG, DTP, measles and TT, and number them from 8a, 8b, 8c, etc. Please use same targets as in Table 5)

#### If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference.

The wastage factor for BCG in 20-dose vial presentation is set at 9 (nine) to permit immunization of a single infant within 24 hours of birth in the 50% of the maternity delivery facilities with less than one birth per day. This wastage rate was introduced in 2004 in order to ensure timely neonatal immunization of BCG and Hep B. Since then coverage of both neonatal doses has been above 95% - during the last two years at 97%

4. Health Systems Strengthening (HSS)  not applicable for B&H

This section only needs to be completed by those countries that have received approval for their HSS proposal. This will serve as an inception report in order to enable release of funds for 2008. Countries are therefore asked to report on any activity in 2007.

# Health Systems Support started in : _________________

Current Health Systems Support will end in : _____________

# Funds received in 2007 : 	Yes/No

If yes, date received : (dd/mm/yyyy)

If Yes, total amount : 	US$ ___________

Funds disbursed to date :  				US$ ___________

Balance of installment left: 				US$ ___________

Requested amount to be disbursed for 2008 	US$ ___________

Are funds on-budget (reflected in the Ministry of Health and Ministry of Finance budget) : Yes/No

If not, why not ? How will it be ensured that funds will be on-budget ? Please provide details.

Please provide a brief narrative on the HSS program that covers the main activities performed, whether funds were disbursed according to the  implementation plan, major accomplishments (especially impacts on health service programs, notably the immunization program), problems encountered and solutions found or proposed, and any other salient information that the country would like GAVI to know about. More detailed information on activities such as whether activities were implemented according to the implementation plan can be provided in Table 10.

Are any Civil Society Organizations involved in the implementation of the HSS proposal ? If so, describe their participation?

In case any change in the implementation plan and disbursement schedule as per the proposal is requested, please explain in the section below and justify the change in disbursement request. More detailed breakdown of expenditure can be provided in Table 9.

Please attach minutes of the Health Sector Coordinating Committee meeting(s) in which fund disbursement and request for next tranche were discussed. Kindly attach the latest Health Sector Review Report and audit report of the account HSS funds are being transferred to. This is a requirement for release of funds for 2008.

| Table 9. HSS Expenditure in 2007 (Please fill in expenditure on HSS activities and request for 2008. In case there is a change in the 2008 request, please justify in the narrative above) |  |  |  |
| --- | --- | --- | --- |
| Area for support | 2007 (Expenditure) | 2007 (Balance) | 2008 (Request) |
| Activity costs |  |  |  |
| Objective 1 |  |  |  |
| Activity 1.1 |  |  |  |
| Activity 1.2 |  |  |  |
| Activity 1.3 |  |  |  |
| Activity 1.4 |  |  |  |
| Objective 2 |  |  |  |
| Activity 2.1 |  |  |  |
| Activity 2.2 |  |  |  |
| Activity 2.3 |  |  |  |
| Activity 2.4 |  |  |  |
| Objective 3 |  |  |  |
| Activity 3.1 |  |  |  |
| Activity 3.2 |  |  |  |
| Activity 3.3 |  |  |  |
| Activity 3.4 |  |  |  |
| Support costs |  |  |  |
| Management costs |  |  |  |
| M&E support costs |  |  |  |
| Technical support |  |  |  |
| TOTAL COSTS |  |  |  |

| Table 10. HSS Activities in 2007 (Please report on activities conducted in 2007) |  |
| --- | --- |
| Major Activities | 2007 |
| Objective 1: |  |
| Activity 1.1: |  |
| Activity 1.2: |  |
| Activity 1.3: |  |
| Activity 1.4: |  |
| Objective 2: |  |
| Activity 2.1: |  |
| Activity 2.2: |  |
| Activity 2.3: |  |
| Activity 2.4: |  |
| Objective 3: |  |
| Activity 3.1: |  |
| Activity 3.2: |  |
| Activity 3.3: |  |
| Activity 3.4: |  |

| Table 11. Please update baseline indicators. Add other indicators according to the HSS proposal. |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Indicator | Data Source | Baseline Value | Source | Date of Baseline | Target | Date for Target |
| 1. National DTP3 coverage (%) |  |  |  |  |  |  |
| 2. Number / % of districts achieving ≥80% DTP3 coverage |  |  |  |  |  |  |
| 3. Under five mortality rate (per 1000) |  |  |  |  |  |  |
| 4. |  |  |  |  |  |  |
| 5. |  |  |  |  |  |  |
| 6. |  |  |  |  |  |  |

Please describe whether targets have been met, what kind of problems have occurred in measuring the indicators, how the monitoring process has been strengthened and whether any changes are proposed.

# 5.	Checklist

Checklist of completed form:

| Form Requirement: | Completed | Comments |
| --- | --- | --- |
| Date of submission |  |  |
| Reporting Period (consistent with previous calendar year) |  |  |
| Government signatures |  |  |
| ICC endorsed |  |  |
| ISS reported on |  |  |
| DQA reported on |  |  |
| Reported on use of 100,000 US$ |  |  |
| Injection Safety Reported on |  |  |
| Immunisation Financing & Sustainability Reported on (progress against country IF&S indicators) |  |  |
| New Vaccine Request including co-financing completed and XL sheet attached |  |  |
| Revised request for injection safety completed (where applicable) |  |  |
| HSS reported on |  |  |
| ICC minutes attached to the report |  |  |
| HSCC minutes, audit report of account for HSS funds and annual health sector evaluation report attached to report |  |  |

6.  	Comments

ICC/HSCC comments:

~ End ~

If baseline data is not available indicate whether baseline data collection is planned and when

Important for easy accessing and cross referencing