January 2005

Progress Report

to the

Global Alliance for Vaccines and Immunization (GAVI)

and

The Vaccine Fund

by the Government of

COUNTRY: Kenya

Date of submission: 11th May 2005 Reporting period: 2004 ( Information provided in this report MUST refer to 2004 activities ) ( Tick only one ) : Inception report ( First annual progress report ( Second annual progress report ( Third annual progress report ( Fourth annual progress report √ Fifth annual progress report ( Text boxes supplied in this report are meant only to be used as guides. Please feel free to add text beyond the space provided. *Unless otherwise specified, documents may be shared with GAVI partners and collaborators

# Progress Report Form:  Table of Contents

# Report on progress made during 2004

  - Immunization Services Support (ISS)

1.1.1	Management of ISS Funds

  - Use of Immunization Services Support

1.1.3	Immunization Data Quality Audit

  - GAVI/Vaccine Fund New and Under-used Vaccines

1.2.1	Receipt of new and under-used vaccines

1.2.2	Major activities

    - Use if GAVI/The Vaccine Fund financial support (US$100,000) for introduction of the new vaccine

1.3	Injection Safety

    - Receipt of injection safety support

    - Progress of transition plan for safe injections and safe management of sharps waste

    - Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

2.  Financial Sustainability

3.  Request for new and under-used vaccine for 2006

  - Up-dated immunization targets

  - Confirmed/revised request for new vaccine (to be shared with UNICEF Supply Division) for year…

  - Confirmed/revised request for injection safety support for the year…

- Please report on progress since submission of the last Progress Report based on the indicators

selected by your country in the proposal for GAVI/VF support

5.  Checklist

6.  Comments

7.  Signatures

# 1.  	Report on progress made during 2004

To be filled in by the country for each type of support received from GAVI/The Vaccine Fund.

## Immunization Services Support (ISS)

#### 1.1.1	Management of ISS Funds

Please describe the mechanism for management of ISS funds, including the role of the Inter-Agency Co-ordinating Committee (ICC).

Please report on any problems that have been encountered involving the use of those funds, such as delay in availability for programme use.

The mechanism for the management of ISS funds remains similar to previous years in that proposal is drawn up at national level for disbursement to provinces, districts and regional vaccine deports,( based on general feedback and advice from these levels) the proposal is discussed & approved with I.C.C – latest proposal tabled and approved on 17.08.2004 The proposal is forwarded by the Accounting Officer of the Ministry of Health for final approval for disbursement for disbursement. Most recent proposal is still pending. The final approval which has been withheld pending appropriate accounting for previous funds released to districts and provinces. The bone of contention is that recipients have not been sending even technical reports of how the moneys were utilised and service outputs do not reflect the significant financial support disbursed to them.

#### 1.1.2	Use of Immunization Services Support

In 2004, the following major areas of activities have been funded with the GAVI/Vaccine Fund Immunization Services Support contribution.

Funds received during 2004  US$ 644,475.00 on 7th April 2004

Remaining funds (carry over) from 2003  US $ 365,113

Table 1: Use of funds during 2004

| Area of Immunization Services Support | Total amount in US $ | AMOUNT OF FUNDS |
| --- | --- | --- |
|  |  | PUBLIC SECTOR | PRIVATE SECTOR & Other |
|  |  | Central | Region/State/Province | District |  |
| Vaccines |  | Nil | Nil | Nil | Nil |
| Injection supplies | Expenditure returns not complete therefore difficult to quantify. | Nil | Nil | Unknown | Nil |
| Personnel |  |  | Unknown | Unknown | Nil |
| Transportation |  |  | Unknown | Unknown | Unknown |
| Maintenance and overheads |  |  | Unknown | Unknown | Unknown |
| Training |  | ~ US$ 135,000 | Nil | Unknown | Nil |
| IEC / social mobilization |  |  | Nil | Unknown | Nil |
| Outreach |  |  | Nil | Unknown | Unknown |
| Supervision |  |  | Nil | Unknown |  |
| Monitoring and evaluation |  |  |  |  |  |
| Epidemiological surveillance |  |  |  |  |  |
| Vehicles |  |  |  |  |  |
| Cold chain equipment |  |  |  |  |  |
| Other …………. (specify) |  |  |  |  |  |
| Total: |  |  |  |  |  |
| Remaining funds for next year: | Approx. US$ 1,000,000 |  |  |  |  |

*If no information is available because of block grants, please indicate under ‘other’.

Please attach the minutes of the ICC meeting(s) when the allocation of funds was discussed.

Please report on major activities conducted to strengthen immunization, as well as, problems encountered in relation to your multi-year plan.

Find attached a copy of I.C.C. minutes of the meeting of 17th August 2004.

#### Immunization Data Quality Audit (DQA) (If it has been implemented in your country)

Has a plan of action to improve the reporting system based on the recommendations from the DQA been prepared?

If yes, please attach the plan.

## YES                              NO           √

## If yes, please report on the degree of its implementation.

## Please attach the minutes of the ICC meeting where the plan of action for the DQA was discussed and endorsed by the ICC.

Please report on studies conducted regarding EPI issues during 2004 (for example, coverage surveys).

Baseline survey was conducted in 3districts and 3 controls under the MOH/CDC/WHO immunization project to improve immunization coverage in the low performing district in Kenya. Program objective is identify best practices to improve in Kenya.

## GAVI/Vaccine Fund New & Under-used Vaccines Support

#### 1.2.1	Receipt of new and under-used vaccines during 2004

Start of vaccinations with the new and under-used vaccine:  DPT/HEPB/HIB         MONTH Jan - December     YEAR2004

Please report on receipt of vaccines provided by GAVI/VF, including problems encountered.

Pemtavalent vaccine received as per schedule. No problem. Yellow fever 03/03/2004 17,600 3/4/04 - 997,400 27/10/2004 - 201,400 26/05/04 - 560,200 27/10/2004 - 536,400 30/06/04 - 560,200 24/12/2004 - 1,000,000 20/7/04 - 706,200 total 4,561,800

Stock out at national level occurred in the country for one month (March2004) due to delay in shipment.

#### 1.2.2	Major activities

Please outline major activities that have been or will be undertaken, in relation to, introduction, phasing-in, service strengthening, etc. and report on problems encountered.

No major activities planned. However on-going advocacy for national funding for pentavalent beyond 2005 is being enhanced.

#### 1.2.3	Use of GAVI/The Vaccine Fund financial support (US$100,000) for the introduction of the new vaccine

Please report on the proportion of 100,000 US$ used, activities undertaken, and problems encountered such as delay in availability of funds for programme use.

## Injection Safety

#### 1.3.1	Receipt of injection safety support

Please report on receipt of injection safety support provided by GAVI/VF, including problems encountered

Kenya has received one injection safety support in cash (2002) and two supports in kind (injection equipment. We sincerely appreciate this support.

#### Progress of transition plan for safe injections and safe management of sharps waste.

#### Please report problems encountered during the implementation of the transitional plan for safe injection and sharp waste

No problems encountered.

Please report on the progress based on the indicators chosen by your country in the proposal for GAVI/VF support.

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| Revision of medical training curricula to include injection safety. Develop guideline on health care waste mgt. Vaccines bundling Nation policy on HCWM. Choice of technology for HCWM | All syllabus for medical workers By 2005. All SDPs By 2005 | Training material developed National draft developed Building incinerators Use of demon fort | Integration is proving difficult Finding for AEFI guideline Sometimes distribution is interrupted Training of DHMT Limited choice of technology | Pursue integration Sink funding and develop guideline Ensure mini-max stocking levels always Update document and move copies Search of technology |

#### 1.3.3	Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

The following major areas of activities have been funded (specify the amount) with the GAVI/The Vaccine Fund injection safety support in the past year:

The support was set aside to procure the intended quantities of injection safety equipment required.

# 2.  	Financial sustainability

Inception Report:	Outline timetable and process for the development of a financial sustainability plan . Describe assistance that may be needed for developing a financial sustainability plan.

First Annual Progress Report: 	Submit completed financial sustainability plan by given deadline. Describe major strategies for improving financial sustainability.

Subsequent Progress Reports:	According to current GAVI rules, support for new and under-used vaccines is covering the total quantity required to meet country targets (assumed to be equal to DTP3 targets) over a five year period (100% x 5 years = 500%).  If the requested amount of new vaccines does not target the full country in a given year (for example, a phasing in of 25%), the country is allowed to request the remaining (in that same example: 75%) in a later year.  In an attempt to help countries find sources of funding in order to attain financial sustainability by slowly phasing out GAVI/VF support, they are encouraged to begin contributing a portion of the vaccine quantity required.  Therefore, GAVI/VF support can be spread out over a maximum of ten years after the initial approval, but will not exceed the 500% limit (see figure 4 in the GAVI Handbook for further clarification).  In table 2.1, specify the annual proportion of five year GAVI/VF support for new vaccines that is planned to be spread-out over a maximum of ten years and co-funded with other sources. Please add the three rows (Proportion funded by GAVI/VF (%), Proportion funded by the Government and other sources (%), Total funding for ………….  (new vaccine)) for each new vaccine.

| Table 2.1: Sources (planned) of financing of new vaccine Pentavalent. |
| --- |
| Proportion of vaccines supported by * | Annual proportion of vaccines |
|  | 2005 | 2006 | 20.. | 20.. | 20.. | 20.. | 20.. | 20.. | 20.. | 20.. |
| A: Proportion funded by GAVI/VF (%)*** | 91.1% | 0% |  |  |  |  |  |  |  |  |
| B: Proportion funded by the Government and other sources (%) | Not secured | ? |  |  |  |  |  |  |  |  |
| C: Total funding for pentavalent (new vaccine) | 91.1% | ? |  |  |  |  |  |  |  |  |

| Table 2.1 B: Sources (planned) of financing of new vaccine Yellow fever (specify) |
| --- |
| Proportion of vaccines supported by * | Annual proportion of vaccines |
|  | 2005 | 2006 | 20.. | 20.. | 20.. | 20.. | 20.. | 20.. | 20.. | 20.. |
| A: Proportion funded by GAVI/VF (%)*** | 100% | 0% |  |  |  |  |  |  |  |  |
| B: Proportion funded by the Government and other sources (%) | 0% | Not secured |  |  |  |  |  |  |  |  |
| C: Total funding for Yellow fever (new vaccine) | 100% | Unknown |  |  |  |  |  |  |  |  |

* Percentage of DTP3 coverage (or measles coverage in case of Yellow Fever) that is target for vaccination with a new and under-used vaccine.

** The first year should be the year of GAVI/VF new vaccine introduction

*** Row A should total 500% at the end of GAVI/VF support

In table 2.2 below, describe progress made against major financial sustainability strategies and corresponding indicators.

Table 2.2:	Progress against major financial sustainability strategies and corresponding indicators

| Financial Sustainability Strategy | Specific Actions Taken Towards Achieving Strategy | Progress Achieved | Problems Encountered | Baseline Value of Progress Indicator | Current Value of Progress Indicator | Proposed Changes To Financial Sustainability Strategy |
| --- | --- | --- | --- | --- | --- | --- |
| 1.Advocacy for additional financing by Ministry of Health for vaccine procurement from G.O.K allocation | Proposal written and discussed with director of medical services and accounting officer. | Not clear | High competition for resources | 3% per | 1% | Needs to rewritten and owned by Ministry of Health and Ministry of Finance. |
| 2. Request for annual support from DARE (WB Project) funds for vaccines and other equipment. | Submitted comprehensive procurement plan. | Not clear |  |  |  |  |
| 3.Request for donor support for vaccines | Requests for specific vaccine support sent to DFID & JICA. | Confirmed approval for procurement of the measles doses for 2005 and part of OPV doses for 2005. | Nil |  |  |  |

# 3.  	Request for new and under-used vaccines for year 2006

Section 3 is related to the request for new and under used vaccines and injection safety for 2006.

- Up-dated immunization targets

Confirm/update basic data approved with country application: figures are expected to be consistent with those reported in the WHO/UNICEF Joint

Reporting Forms.  Any changes and/or discrepancies MUST be justified in the space provided (page 12). Targets for future years MUST be provided.

| Table 3 : Update of immunization achievements and annual targets Revised per Vol VII & Data sheet population and dev. 1999 |
| --- |
| Number of | Achievements and targets |
|  | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 |
| DENOMINATORS |  |  |  |  |  |  |  |  |  |
| Births | 1349169 | 1377386 | 1402126 | 1427113 | 1452346 | 1477822 | 1503537 | 1529323 | 1555421 |
| Infants’ deaths | 104445 | 106472 | 108384 | 110316 | 112266 | 114236 | 116223 | 118217 | 120234 |
| Surviving infants | 1254608 | 1270915 | 1293742 | 1316798 | 1340080 | 1363586 | 1387314 | 1411106 | 1435187 |
| Infants vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with 1st dose of DTP (DTP1)* | 1057981 (84) | 1169241 (92%) | 1216118 (94%) | 1250958 (95) | 1273076 (95%) | 1295407 ((95%) | 1317948 ((95%) | 1340551 (95%) | 1363428 (95%) |
| Infants vaccinated 2004 (JRF) / to be vaccinated in 2005 and beyond with 3rd dose of DTP (DTP3)* | 938,299 (75%) | 1080277 (85%) | 1164368 (9%0) | 1250958 (95%) | 1273076 (95%) | 1295407 (95%) | 1317948 (95%) | 1340551 (95%) | 1363428 (95%0 |
| NEW VACCINES ** |  |  |  |  |  |  |  |  |  |
| Infants vaccinated 2004 (JRF) / to be vaccinated in 2005 and beyond with 1st dose of yellow fever....... (new vaccine) | 16281 (52%) | 24371 (78%) | 28183 (84%) | 29674 (90%) | 30196 (90%) | 30715 (90) | 31246 (90%) | 31816 (90%) | 32287 (90%) |
| Infants vaccinated 2004 (JRF) / to be vaccinated in 2005 and beyond with 3rd dose of DPT/HepB/Hip…….… | 938,299 (75%) | 1080277 (85%) | 1164368 (9%0) | 1250958 (95%) | 1273076 (95%) | 1295407 (95%) | 1317948 (95%) | 1340551 (95%) | 1363428 (95%0 |
| Wastage rate in 2004 and plan for 2005 beyond*** ………….. ( new vaccine) | 5 – 19% |  |  |  |  |  |  |  |  |
| INJECTION SAFETY**** |  |  |  |  |  |  |  |  |  |
| Pregnant women vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with TT2 | 923552 (68%) | 1101909 (80%) | 1191807 (85%) | 1213047 85%) | 1234495(85%) | 1256149 (85%) | 1278007 (85%) | 1299925 (85%) | 1322108 (85%) |
| Infants vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with BCG * | 1165451 (86%) | 1294743 (94%) | 1332020 (95%) | 1398572 98%) | 1423300(98%) | 1448266 (98%) | 1473466 (98%) | 1498737 (98%) | 1524313 (98%) |
| Infants vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with Measles * | 810364 (65%) | 991313 (78%) | 1086743 (84%) | 1185118 (90%) | 1206072 (90%) | 1227228 (90%) | 1248582 (90% | 1269996 (90%) | 1291668 (90%) |

* Indicate actual number of children vaccinated in 2004 and updated targets (with either DTP alone or combined)

** Use 3 rows (as indicated under the heading NEW VACCINES) for every new vaccine introduced

*** Indicate actual wastage rate obtained in past years

**** Insert any row as necessary

* Indicate actual number of children vaccinated in 2004 and updated targets (with either DTP alone or combined)

** Use 3 rows (as indicated under the heading NEW VACCINES) for every new vaccine introduced

*** Indicate actual wastage rate obtained in past years

**** Insert any row as necessary

Please provide justification on changes to baseline, targets, wastage rate, vaccine presentation, etc. from the previously approved plan, and on reported figures which differ from those reported in the WHO/UNICEF Joint Reporting Form in the space provided below.

The 2004 to 2008 denominators in this report are different from last year report due to revision of target population with population indicator released in July 2004 in final version of the Kenya Demographic and Household Survey Report (KDHSt, and the Datasheet on Population and Development Indicator from the 1999 Kenya Population and housing Census that was released later. Please note also that the denominator in the Joint Reporting Form is different from the denominator given in the Progress Report submitted in April 2005 due to rounding-off of the projected populations of children under one year extracted from the official population projection contained in the 1999 Kenya Population and Housing Census, Population Analytical report (Vol. VII).

3.2	Availability of revised request for new vaccine (to be shared with UNICEF Supply Division) for 2006

In case you are changing the presentation of the vaccine, or increasing your request; please indicate below if UNICEF Supply Division has assured the availability of the new quantity/presentation of supply.

Table 4: Estimated number of doses of  Pentavallent vaccine  (specify for one presentation only): Please repeat this table for any other vaccine presentation requested from

GAVI/The Vaccine Fund

|  | YELLOW FEVER | Formula | For 2006 |
| --- | --- | --- | --- |
| A | Infants vaccinated/to be vaccinated with dose of Yellow Fever (new vaccine)* | 84% of 32142 | 32,142 |
| B | Percentage of vaccines requested from The Vaccine Fund taking into consideration the Financial Sustainability Plan |  | 100% |
| C | Number of doses per child |  | 1 |
| D | Number of doses | A x Bx C | 32,142 |
| E | Estimated wastage factor 1.11 | (see list in table 3) | 2.50 |
| F | Number of doses (incl. Wastage) | A x C x E x B/100 | 80,355 |
| G | Vaccines buffer stock | F x 0.25 | 20,089 |
| H | Anticipated vaccines in stock at start of year 2006 (including balance of buffer stock) |  | 1000 |
| I | Total vaccine doses requested | F + G - H | 99,444 |
| J | Number of doses per vial |  | 10 |
| K | Number of AD syringes (+10% wastage) | ( D + G – H ) x 1.11 | 56,866 |
| L | Reconstitution syringes(+10% wastage) | I / J x 1.11 | 11,038 |
| M | Total safety boxes (+10% of extra need) | ( K + L ) / 100 x 1.11 | 754 |

*Please report the same figure as in table 3.

Table 5: Wastage rates and factors

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

#### 3.3	Confirmed/revised request for injection safety support for the years 2006 -2007

Table 6: Estimated supplies for safety of vaccination for the next two years with …… (Use one table for each vaccine BCG, DTP, measles and TT, and number them from 4 to 8)

#### If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference.

# 4. 	Please report on progress since submission of the last Progress Report based on the indicators selected 	by your country in the proposal for GAVI/VF support

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| Sustained improved reporting of immunization activities from districts and provinces Increasing full immunization coverage and reducing drop out rates Increasing full immunization coverage | 80% completeness 75% timeliness 10% increase in coverage in every districts and reduction of DPT1 – Measles from (28.8 % to 20% ) from 58% to 70 | 99.9% completeness 80% timeliness DPT1 coverage 84% DPT/HepB/Hip 3 coverage of 75 23% DPT1 – measles drop out 58% full immunization | Competing activities at provincial level for entering and forwarding of the reports to National level Conflicting priority Frequent stock out of pentavalent during 1st and 3rd quarter of the 2004 | Above 80 % timeliness of all reports by end of 2005 Sustain report completeness at 100% Increase immunization coverage by 10% by all districts by end of 2005 Reduction of DPT1 - Measles drop out by 3% |

# Checklist

Checklist of completed form:

| Form Requirement: | Completed | Comments |
| --- | --- | --- |
| Date of submission | 11th May 05 |  |
| Reporting Period (consistent with previous calendar year) | 2004 |  |
| Table 1 filled-in | Yes |  |
| DQA reported on | 2003 |  |
| Reported on use of 100,000 US$ | Yes |  |
| Injection Safety Reported on | Yes |  |
| FSP Reported on (progress against country FSP indicators) | Yes |  |
| Table 2 filled-in | Yes |  |
| New Vaccine Request completed | Yes |  |
| Revised request for injection safety completed (where applicable) | N/A |  |
| ICC minutes attached to the report | Yes |  |
| Government signatures | Yes |  |
| ICC endorsed | Yes |  |

6.  	Comments

ICC/RWG comments:

7.	Signatures

FOR THE GOVERNMENT OF KENYA

Signature:	……………………………………………...……………...

Title:	THE DIRECTOR OF MEDICAL SERVICES

Date:	11th May 2005

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this report. Signature of endorsement of this document does not imply any financial (or legal) commitment on the part of the partner agency or individual.

Financial accountability forms an integral part of GAVI/The Vaccine Fund monitoring of reporting of country performance.  It is based on the regular government audit requirements as detailed in the Banking form.  The ICC Members confirm that the funds received have been audited and accounted for according to standard government or partner requirements.

| Agency/Organisation | Name/Title | Date Signature | Agency/Organisation | Name/Title | Date Signature |
| --- | --- | --- | --- | --- | --- |
| Ministry of Health | Dr. James Nyikal |  | Church Health Organizations of Kenya | Dr. Beatrice Alavanda |  |
| World Health Organization - Kenya | Dr. Peter Eriki Country Representative |  | British Department for International Development | MS. Marilyn McDonagh Health Advisor |  |
| UNICEF - Kenya | Mr. Heimo Laakkonnen Country Representative |  |  |  |  |
| JICA - Kenya | Mr. Yoshiaki Kano Resident Representative |  |  |  |  |

NB: The statement above on financial accountability has been noted for the first time with this Annual Reporting Form & previously GAVI only audited outputs of the funding (e.g. increased immunization coverage). Therefore no financial audit has been conducted to date. – Dr. Tatu Kamau, KEPI Manager

~ End ~

# Text boxes

Partnering with The Vaccine Fund

Remarks

Phasing: Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided Wastage of vaccines: Countries are expected to plan for a maximum of: 50% wastage rate for a lyophilized vaccine in 10 or 20-dose vial; 25% for a liquid vaccine in a10 or 20-dose vial; 10% for any vaccine (either liquid or lyophilized) in 1 or 2-dose vial. Buffer stock: The buffer stock is recalculated every year as 25% the current vaccine requirement Anticipated vaccines in stock at start of year 2006: It is calculated by counting the current balance of vaccines in stock, including the balance of buffer stock. Write zero if all vaccines supplied for the current year (including the buffer stock) are expected to be consumed before the start of next year. Countries with very low or no vaccines in stock must provide an explanation of the use of the vaccines. AD syringes: A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines. Reconstitution syringes: it applies only for lyophilized vaccines. Write zero for other vaccines. Safety boxes: A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes