January 2005

Progress Report

REVISED AUGUST 2006

to the

Global Alliance for Vaccines and Immunization (GAVI)

and

The Vaccine Fund

by the Government of

COUNTRY: Kenya

Date of submission: 9th June 2006 Reporting period: 2005 ( Information provided in this report MUST refer to 2005 activities ) ( Tick only one ) : Inception report ( First annual progress report ( Second annual progress report ( Third annual progress report ( Fourth annual progress report ( Fifth annual progress report ( Text boxes supplied in this report are meant only to be used as guides. Please feel free to add text beyond the space provided. *Unless otherwise specified, documents may be shared with GAVI partners and collaborators

# Progress Report Form:  Table of Contents

# Report on progress made during 2005

  - Immunization Services Support (ISS)

1.1.1	Management of ISS Funds

  - Use of Immunization Services Support

1.1.3	Immunization Data Quality Audit

  - GAVI/Vaccine Fund New and Under-used Vaccines

1.2.1	Receipt of new and under-used vaccines

1.2.2	Major activities

    - Use if GAVI/The Vaccine Fund financial support (US$100,000) for introduction of the new vaccine

1.3	Injection Safety

    - Receipt of injection safety support

    - Progress of transition plan for safe injections and safe management of sharps waste

    - Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

2.  Financial Sustainability

3.  Request for new and under-used vaccine for 2006

  - Up-dated immunization targets

  - Confirmed/revised request for new vaccine (to be shared with UNICEF Supply Division) for year…

  - Confirmed/revised request for injection safety support for the year…

- Please report on progress since submission of the last Progress Report based on the indicators

selected by your country in the proposal for GAVI/VF support

5.  Checklist

6.  Comments

7.  Signatures

# 1.  	Report on progress made during 2005

To be filled in by the country for each type of support received from GAVI/The Vaccine Fund.

## Immunization Services Support (ISS)

#### 1.1.1	Management of ISS Funds

Please describe the mechanism for management of ISS funds, including the role of the Inter-Agency Co-ordinating Committee (ICC).

Please report on any problems that have been encountered involving the use of those funds, such as delay in availability for programme use.

NB: The last tranche of ISS funds were disbursed to the operational levels in January 2005. The mechanism for the management of ISS funds has been standard in that a proposal is drawn up at national level for disbursement to provinces, districts and regional vaccine deports,( based on general feedback and advice from these levels) The proposal is discussed & approved with I.C.C – latest proposal tabled and approved on 17.08.2004 (but was only disbursed in January 2005) The proposal is then given the final approval for disbursement by the Accounting Officer of the Ministry of Health.

#### 1.1.2	Use of Immunization Services Support

In 2005, the following major areas of activities have been funded with the GAVI/Vaccine Fund Immunization Services Support contribution.

Funds received during 2005 – US$ I,190,680 (DQA reward)

Remaining funds (carry over) from 2004 = US $ 1,089,742

Table 1: Use of funds during 2005

| Area of Immunization Services Support | Total amount in US $ | AMOUNT OF FUNDS |
| --- | --- | --- |
|  |  | PUBLIC SECTOR | PRIVATE SECTOR & Other |
|  |  | Central | Region/State/Province | District |  |
| Vaccines | US$ 0 | 0 | 0 | 0 | US $0.0 |
| Injection supplies | US$ 0 | 0 | 0 | 0 | US $0.0 |
| Personnel | US$ 0 | 0 | 0 | 0 | US $0.0 |
| Transportation (vaccine distribution) | US$ 30,000 | 30,000 | 0 | 0 | US $0.0 |
| Maintenance and overheads | US$ 61,666 | 1,111 | 3,333 | 57,222 | US $0.0 |
| Training | US$ 83,000 | 0 | 0 | 83,000 | US $0.0 |
| IEC / social mobilization | US$ 10,833 | 0 | 0 | 10,833 | US $0.0 |
| Outreach | US$ 18,611 | 0 | 0 | 18,611 | US $0.0 |
| Supervision (personnel allowances) | US$ 271,620 | 0 | 41,335 | 230,285 | US $0.0 |
| Monitoring and evaluation | US$ 0 | 0 | 0 | 0 | US $0.0 |
| Epidemiological surveillance | US$ 0 | 0 | 0 | 0 | US $0.0 |
| Vehicles (fuel & maintenance) | US$ 112,298 | 20,833 | 16,384 | 75,081 | US $0.0 |
| Cold chain equipment (LPGas) | US$ 100,603 | 54,215 | 0 | 46,388 | US $0.0 |
| Other – incinerator construction in 31 districts | US$ 22,604 | 0 | 0 | 22,604 | US$ 0 |
| Other – secretariat | US$ 2,497 | 2,497 | 0 | 0 | US$ 0 |
| Total: | US$ 713,732 | 108,656 | 61,052 | 544,024 |  |
| Remaining funds for next year: | US$ 1,566,690 |  |  |  |  |

*If no information is available because of block grants, please indicate under ‘other’. NB: Districts do share varying amounts of their funds with local NGOs/ mission hospitals etc but exact amounts are not known.

Please attach the minutes of the ICC meeting(s) when the allocation of funds was discussed.

Please report on major activities conducted to strengthen immunization, as well as, problems encountered in relation to your multi-year plan.

#### Immunization Data Quality Audit (DQA) (If it has been implemented in your country)

Has a plan of action to improve the reporting system based on the recommendations from the DQA been prepared?

If yes, please attach the plan.

## YES                              NO            (

## If yes, please report on the degree of its implementation.

## Please attach the minutes of the ICC meeting where the plan of action for the DQA was discussed and endorsed by the ICC.

Please report on studies conducted regarding EPI issues during 2004 (for example, coverage surveys).

## GAVI/Vaccine Fund New & Under-used Vaccines Support

#### 1.2.1	Receipt of new and under-used vaccines during 2005

Start of vaccinations with the new and under-used vaccine:           MONTH… Jan-Dec          YEAR…2005

Please report on receipt of vaccines provided by GAVI/VF, including problems encountered.

(NB: New vaccines were introduced nationwide (at once) in November 2001 & no major problems were encountered.) 17th Feb 2005 – 1,006,000 doses 12th May 2005 – 1,006,000 doses 10th Aug 2005 – 409,000 doses 29th Dec 2005 – 1,000,000 doses TOTAL - 3,421,000 Doses DPT-HepB-Hib 12th April 2005 – 12,200 doses Yellow fever 8th September 2005 – 12,000 doses Yellow fever TOTAL - 24,200 Doses Yellow fever vaccine

#### 1.2.2	Major activities

Please outline major activities that have been or will be undertaken, in relation to, introduction, phasing-in, service strengthening, etc. and report on problems encountered.

No major operational activities were undertaken in 2005 for service strengthening because K.E.P.I. was tied up in preventive vaccination campaigns against the spread of polio from our neighbouring countries of Somalia, Ethiopia and Sudan, and also accelerated immunization activities to try and halt the spread of measles outbreaks all over the country. However, at the national level increased funding from the Ministry of Health were secured for the programme (350% increment), so as to ensure adequate funds for all injection equipment required, all documentation tools, all traditional vaccines. Also increased were funds to districts to procure Liquid Petroleum Gas for the vaccine refrigerators and funds for supervision and distribution of EPI supplies. All these efforts were to address the supply side of service delivery to reduce commodity stock-outs or other interruptions in service delivery. Strategies to improve the demand side of routine immunization service delivery were done indirectly during the accelerated measles outbreak control activities in the last quarter of the year and through training of over 1000 immunizing health workers on operational aspects of EPI service delivery (cost US $ 83,000)

#### 1.2.3	Use of GAVI/The Vaccine Fund financial support (US$100,000) for the introduction of the new vaccine

Please report on the proportion of 100,000 US$ used, activities undertaken, and problems encountered such as delay in availability of funds for programme use.

The US$ 100,000 given by GAVI in 2001 to facilitate the introduction of the Pentavalent vaccine was received late after the introduction activities had been concluded so these funds were added to the existing ISS funds and distributed to districts and provinces.

## Injection Safety

#### 1.3.1	Receipt of injection safety support

Please report on receipt of injection safety support provided by GAVI/VF, including problems encountered

No major problems encountered.

#### Progress of transition plan for safe injections and safe management of sharps waste.

#### Please report problems encountered during the implementation of the transitional plan for safe injection and sharp waste

No problems encountered – safe injection practices for immunization services fully operational at all service delivery points

Please report on the progress based on the indicators chosen by your country in the proposal for GAVI/VF support.

#### 1.3.3	Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

The following major areas of activities have been funded (specify the amount) with the GAVI/The Vaccine Fund injection safety support in the past year:

The injection safety support was received only once in cash (US$ 364,000 in 2003) and this was used to buy all the injection equipment required for 2004. The other two times the actual quantities of injection equipment were delivered to the programme.

# 2.  	Financial sustainability

Inception Report:	Outline timetable and process for the development of a financial sustainability plan . Describe assistance that may be needed for developing a financial sustainability plan.

First Annual Progress Report: 	Submit completed financial sustainability plan by given deadline. Describe major strategies for improving financial sustainability.

Subsequent Progress Reports:	According to current GAVI rules, support for new and under-used vaccines is covering the total quantity required to meet country targets (assumed to be equal to DTP3 targets) over a five year period (100% x 5 years = 500%).  If the requested amount of new vaccines does not target the full country in a given year (for example, a phasing in of 25%), the country is allowed to request the remaining (in that same example: 75%) in a later year.  In an attempt to help countries find sources of funding in order to attain financial sustainability by slowly phasing out GAVI/VF support, they are encouraged to begin contributing a portion of the vaccine quantity required.  Therefore, GAVI/VF support can be spread out over a maximum of ten years after the initial approval, but will not exceed the 500% limit (see figure 4 in the GAVI Handbook for further clarification).  In table 2.1, specify the annual proportion of five year GAVI/VF support for new vaccines that is planned to be spread-out over a maximum of ten years and co-funded with other sources. Please add the three rows (Proportion funded by GAVI/VF (%), Proportion funded by the Government and other sources (%), Total funding for ………….  (new vaccine)) for each new vaccine.

| Table 2.1: Sources (planned) of financing of new vaccine→ Government of Kenya budgetary allocation to the Ministry of Health (specify) |
| --- |
| Proportion of vaccines supported by * | Annual proportion of vaccines |
|  | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 |
| A: Proportion funded by GAVI/VF (%)*** | 100% | 91.1% | 91.1% | 91.1% |  |  |  |  |  |  |
| B: Proportion funded by the Government and other sources (%) | 0% | 8.9% | 8.9% | 8.9% |  |  |  |  |  |  |
| C: Total funding for ‘pentavalent’… (new vaccine) | 100% | 100% | 100% | 100% |  |  |  |  |  |  |

* Percentage of DTP3 coverage (or measles coverage in case of Yellow Fever) that is target for vaccination with a new and under-used vaccine.

** The first year should be the year of GAVI/VF new vaccine introduction

*** Row A should total 500% at the end of GAVI/VF support

In table 2.2 below, describe progress made against major financial sustainability strategies and corresponding indicators.

Table 2.2:	Progress against major financial sustainability strategies and corresponding indicators

| Financial Sustainability Strategy | Specific Actions Taken Towards Achieving Strategy | Progress Achieved | Problems Encountered | Baseline Value of Progress Indicator | Current Value of Progress Indicator | Proposed Changes To Financial Sustainability Strategy |
| --- | --- | --- | --- | --- | --- | --- |
| 1. Raising Government of Kenya allocation to the Ministry of Health | Lobbying through the cabinet and parliament by the Minister for Health for an increased allocation to the Ministry of Health in line with the Abuja Targets for governments per capita spending on health Lobbying by Health Donors Working Group and other key stakeholders for increased allocation of government budget to health as well as Ministry of Health prioritisation to activities that will impact on MDG 4 | 70% success; per capita expenditure on health has risen from 6% to 9.5% | Many competing priorities in a country which has just began its journey of economic recovery | 6% | 9.5% | Ministry of Health and its development partners current interest in moving towards a SWAp system of funding for health service delivery. |
| 2. Raising Ministry of Health’s internal allocation to routine immunization services | Lobbying by the KEPI Manager and the Director of Medical Services | 350% overall success although most of the increment was channelled to procurement of vaccines & injection equipment | Overwhelming cost of Pentavalent vaccine which would require a 1000%+ increase in allocation | US$ 900,000 | US$ 3,850,000 |  |
| 3. |  |  |  |  |  |  |
| 4. |  |  |  |  |  |  |
| 5. |  |  |  |  |  |  |

# Request for new and under-used vaccines for year 2006

Section 3 is related to the request for new and under used vaccines and injection safety for 2006.

- Up-dated immunization targets

Confirm/update basic data approved with country application: figures are expected to be consistent with those reported in the WHO/UNICEF Joint

Reporting Forms.  Any changes and/or discrepancies MUST be justified in the space provided (page 12). Targets for future years MUST be provided.

Table 3 : Update of immunization achievements and annual targets

| Number of |
| --- |
|  | Achievements and targets |
|  | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 |
| DENOMINATORS |  |  |  |  |  |  |  |  |
| Births | 1374185 | 1402126 | 1427113 | 1452346 | 1477822 | 1503537 | 1529323 | 1555421 |
| Infants’ deaths | 96265 | 108384 | 110316 | 112266 | 114236 | 116223 | 118217 | 120234 |
| Surviving infants | 1277920 | 1293742 | 1316798 | 1340080 | 1363586 | 1387314 | 1411106 | 1435187 |
| Infants vaccinated in 2005 (JRF) / to be vaccinated in 2006 and beyond with 1st dose of DTP (DTP1)* | 1104993 (86%) | 1216118 (94%) | 1250958 (95) | 1273076 (95%) | 1295407 ((95%) | 1317948 ((95%) | 1340551 (95%) | 1363428 (95%) |
| Infants vaccinated 2005 (JRF) / to be vaccinated in 2006 and beyond with 3rd dose of DTP (DTP3)* | 988866 (77%) | 1164368 (90%) | 1250958 (95%) | 1273076 (95%) | 1295407 (95%) | 1317948 (95%) | 1340551 (95%) | 1363428 (95%0 |
| NEW VACCINES ** |  |  |  |  |  |  |  |  |
| Infants vaccinated 2005 (JRF) / to be vaccinated in 2006 and beyond with 1st dose of yellow fever (new vaccine) | 12600 (39%) | 18,988 (50%) | 23,560 (60%) | 28,421 (70%) | 30,257 (80%) | 38,716 (90%) | 44,481 (100%) |  |
| Infants vaccinated 2005 (JRF) / to be vaccinated in 2006 and beyond with 3rd dose of DPT/HepB/Hip…….… | 988866 (77%) | 1164368 (90%) | 1250958 (95%) | 1273076 (95%) | 1295407 (95%) | 1317948 (95%) | 1340551 (95%) | 1363428 (95%0 |
| Wastage rate in 2005 and plan for 2006 beyond*** ………….. ( new vaccine) |  |  |  |  |  |  |  |  |
| INJECTION SAFETY**** |  |  |  |  |  |  |  |  |
| Pregnant women vaccinated in 2005 (JRF) / to be vaccinated in 2006 and beyond with TT2 | 994253 72 % | 1191807 (85%) | 1213047 85%) | 1234495(85%) | 1256149 (85%) | 1278007 (85%) | 1299925 (85%) | 1322108 (85%) |
| Infants vaccinated in 2005 (JRF) / to be vaccinated in 2006 and beyond with BCG * | 1174712 (85%) | 1332020 (95%) | 1398572 98%) | 1423300(98%) | 1448266 (98%) | 1473466 (98%) | 1498737 (98%) | 1524313 (98%) |
| Infants vaccinated in 2005 (JRF) / to be vaccinated in 2006 and beyond with Measles * | 893976 (70%) | 1086743 (84%) | 1185118 (90%) | 1206072 (90%) | 1227228 (90%) | 1248582 (90% | 1269996 (90%) | 1291668 (90%) |

* Indicate actual number of children vaccinated in 2004 and updated targets (with either DTP alone or combined)

** Use 3 rows (as indicated under the heading NEW VACCINES) for every new vaccine introduced

*** Indicate actual wastage rate obtained in past years

**** Insert any row as necessary

Please provide justification on changes to baseline, targets, wastage rate, vaccine presentation, etc. from the previously approved plan, and on reported figures which differ from those reported in the WHO/UNICEF Joint Reporting Form in the space provided below.

Coverage for yellow fever vaccine has been continuously poor in the four districts where it is given, due to the unconfirmed reason that “most mothers don’t want their children being injected twice (i.e. measles + yellow fever) in one sitting”. Therefore the projected growth in coverage for yellow fever vaccine has also been scaled down until the reasons for the discrepancy in administration of the two antigens (measles & yellow fever) are sorted out.

3.2	Availability of revised request for new vaccine (to be shared with UNICEF Supply Division) for 2006

In case you are changing the presentation of the vaccine, or increasing your request; please indicate below if UNICEF Supply Division has assured the availability of the new quantity/presentation of supply.

No changes of vaccine presentation confirmed or increases in supply in 2006

Table 4: Estimated number of doses of DPT-HepB-Hib vaccine (specify for one presentation only): Please repeat this table for any other vaccine presentation requested from

GAVI/The Vaccine Fund

*Please report the same figure as in table 3.

Table 5: Wastage rates and factors

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

Table 5: Estimated number of doses of Yellow fever vaccine (specify for one presentation only): Please repeat this table for any other vaccine presentation requested from

GAVI/The Vaccine Fund

|  |  | Formula | For 2007 |
| --- | --- | --- | --- |
| A | Infants vaccinated/to be vaccinated with 1st dose of Yellow fever (new vaccine)* |  | 23,560 |
| B | Percentage of vaccines requested from The Vaccine Fund taking into consideration the Financial Sustainability Plan | % | 100% |
| C | Number of doses per child |  | 1 |
| D | Number of doses | A x Bx C | 23,560 |
| E | Estimated wastage factor | (see list in table 3) | 1.11 |
| F | Number of doses (incl. Wastage) | A x C x E x B/100 | 26,152 |
| G | Vaccines buffer stock | F x 0.25 | 6,538 |
| H | Anticipated vaccines in stock at start of year 2006 (including balance of buffer stock) at national level |  | 160 |
| I | Total vaccine doses requested | F + G - H | 35,230 |
| J | Number of doses per vial |  | 10 |
| K | Number of AD syringes (+10% wastage) | ( D + G – H ) x 1.11 | 33,231 |
| L | Reconstitution syringes(+10% wastage) | I / J x 1.11 | 3,910 |
| M | Total safety boxes (+10% of extra need) | ( K + L ) / 100 x 1.11 | 412 |

*Please report the same figure as in table 3.

Table 5: Wastage rates and factors

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

#### 3.3	Confirmed/revised request for injection safety support for the years 2006 -2007

Table 6: Estimated supplies for safety of vaccination for the next two years with …… (Use one table for each vaccine BCG, DTP, measles and TT, and number them from 4 to 8)

#### If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference.

KENYA not eligible for injection safety support from GAVI in 2007 therefore required quantities will be procured with local resources

# 4. 	Please report on progress since submission of the last Progress Report based on the indicators selected 	by your country in the proposal for GAVI/VF support

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| Improvement in DPT-3 coverage | 90% coverage in all districts | 77% | frequent interruptions to service delivery due to ageing cold-chain equipment & staff attrition | 90% |
| Address recommendations of the National EPI Review of 2000 | Improved reporting from all levels of immunization service delivery Adequate logistics support Training of health workers on policy guidelines, practices and innovations Micro-planning for surveillance strengthened at all levels | 100% completeness and >90% timeliness of reporting approx. 90% achieved for general logistics support but only ≈40% achievement for cold-chain maintenance support 100% achievement up to district health management level but approx. 75% of facility level adequately trained Almost 100% complete up to district level & approx 75% complete at facility level | delays in approvals of funding for logistics distribution & inadequate funds for cold-chain maintenance financial support for complete cascading of training frequent staff changeovers without commensurate training of new officers | 100% timeliness 100% timeliness of general logistics support & 80% for cold-chain maintenance support 100% of immunizing health workers updated on current policies and practices by the District Health Management Teams 100% of immunizing health workers updated on current surveillance practices by the District Health Management Teams |
| Assessment of burden of disease prevented by the new/underused vaccines | Disease burden establishment studies for Hib & yellow fever | Sentinel surveillance site for Hib well established and operational (≈80% effectiveness) Entomological studies for yellow fever transmission yet to be effected although draft proposal ready | Delay in institutionalisation of recommended surveillance system and practices Competing EPI priorities delayed initialisation of this activity | 100% effectiveness of the 1st sentinel site by end 2006 and expansion to 6 other regional hospitals by end 2007 Launch of entomological survey by Jan 2007 |

# Checklist

Checklist of completed form:

| Form Requirement: | Completed | Comments |
| --- | --- | --- |
| Date of re-submission | 15th August 2006 | Addressing clarifications requested by GAVI Secretariat |
| Reporting Period (consistent with previous calendar year) | Jan-Dec 2005 |  |
| Table 1 filled-in | Yes |  |
| DQA reported on | Yes |  |
| Reported on use of 100,000 US$ | Yes |  |
| Injection Safety Reported on | Yes |  |
| FSP Reported on (progress against country FSP indicators) | Yes |  |
| Table 2 filled-in | Yes |  |
| New Vaccine Request completed | Yes |  |
| Revised request for injection safety completed (where applicable) | Yes |  |
| ICC minutes attached to the report | Yes |  |
| Government signatures | Yes |  |
| ICC endorsed | Pending |  |

6.  	Comments

ICC/RWG comments:

To be done by the ICC members

7.	Signatures

For the Government of  KENYA

Signature:	……………………………………………...……………...

Title: THE DIRECTOR OF MEDICAL SERVICES, MINISTRY OF HEALTH

Date:	………………………………………….………………….

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this report. Signature of endorsement of this document does not imply any financial (or legal) commitment on the part of the partner agency or individual.

Financial accountability forms an integral part of GAVI/The Vaccine Fund monitoring of reporting of country performance.  It is based on the regular government audit requirements as detailed in the Banking form.  The ICC Members confirm that the funds received have been audited and accounted for according to standard government or partner requirements.

| Agency/Organisation | Name/Title | Date Signature | Agency/Organisation | Name/Title | Date Signature |
| --- | --- | --- | --- | --- | --- |
| World Health Organization – KENYA | Dr. Peter Eriki Country Representative |  |  |  |  |
| UNICEF – KENYA | Mr. Heimo Laakkonen Country Representative |  |  |  |  |
| Kenya Red Cross Society | Dr. Asha Mohammed Deputy Chief Executive |  |  |  |  |
| DfID – KENYA | Mr. Tom Dahley Chief Health Advisor |  |  |  |  |

~ End ~

# Text boxes

Partnering with The Vaccine Fund

Remarks

Phasing: Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided Wastage of vaccines: Countries are expected to plan for a maximum of: 50% wastage rate for a lyophilized vaccine in 10 or 20-dose vial; 25% for a liquid vaccine in a10 or 20-dose vial; 10% for any vaccine (either liquid or lyophilized) in 1 or 2-dose vial. Buffer stock: The buffer stock is recalculated every year as 25% the current vaccine requirement Anticipated vaccines in stock at start of year 2006: It is calculated by counting the current balance of vaccines in stock, including the balance of buffer stock. Write zero if all vaccines supplied for the current year (including the buffer stock) are expected to be consumed before the start of next year. Countries with very low or no vaccines in stock must provide an explanation of the use of the vaccines. AD syringes: A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines. Reconstitution syringes: it applies only for lyophilized vaccines. Write zero for other vaccines. Safety boxes: A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes

To be determined annually

Remarks

Phasing: Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided Wastage of vaccines: Countries are expected to plan for a maximum of: 50% wastage rate for a lyophilized vaccine in 10 or 20-dose vial; 25% for a liquid vaccine in a10 or 20-dose vial; 10% for any vaccine (either liquid or lyophilized) in 1 or 2-dose vial. Buffer stock: The buffer stock is recalculated every year as 25% the current vaccine requirement Anticipated vaccines in stock at start of year 2006: It is calculated by counting the current balance of vaccines in stock, including the balance of buffer stock. Write zero if all vaccines supplied for the current year (including the buffer stock) are expected to be consumed before the start of next year. Countries with very low or no vaccines in stock must provide an explanation of the use of the vaccines. AD syringes: A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines. Reconstitution syringes: it applies only for lyophilized vaccines. Write zero for other vaccines. Safety boxes: A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes