AUGUST 2006

Progress Report

To the

Global Alliance for Vaccines and Immunization (GAVI)

and

The Vaccine Fund

by the Government of

COUNTRY: KINGDOM OF LESOTHO

Date of submission: AUGUST 2006 Reporting period: 2005( Information provided in this report MUST refer to 2005 activities ) ( Tick only one ) : Inception report ( First annual progress report ( Second annual progress report (*** Third annual progress report ( Fourth annual progress report ( Fifth annual progress report ( Text boxes supplied in this report are meant only to be used as guides. Please feel free to add text beyond the space provided. *Unless otherwise specified, documents may be shared with GAVI partners and collaborators

# Progress Report Form:  Table of Contents

# Report on progress made during 2005

  - Immunization Services Support (ISS)

1.1.1	Management of ISS Funds

  - Use of Immunization Services Support

1.1.3	Immunization Data Quality Audit

  - GAVI/Vaccine Fund New and Under-used Vaccines

1.2.1	Receipt of new and under-used vaccines

1.2.2	Major activities

    - Use if GAVI/The Vaccine Fund financial support (US$100,000) for introduction of the new vaccine

1.3	Injection Safety

    - Receipt of injection safety support

    - Progress of transition plan for safe injections and safe management of sharps waste

    - Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

2.  Financial Sustainability

3.  Request for new and under-used vaccine for 2006

  - Up-dated immunization targets

  - Confirmed/revised request for new vaccine (to be shared with UNICEF Supply Division) for year…

  - Confirmed/revised request for injection safety support for the year…

- Please report on progress since submission of the last Progress Report based on the indicators

selected by your country in the proposal for GAVI/VF support

5.  Checklist

6.  Comments

7.  Signatures

# 1.  	Report on progress made during 2005

To be filled in by the country for each type of support received from GAVI/The Vaccine Fund.

## Immunization Services Support (ISS)

#### 1.1.1	Management of ISS Funds

Please describe the mechanism for management of ISS funds, including the role of the Inter-Agency Co-ordinating Committee (ICC).

Please report on any problems that have been encountered involving the use of those funds, such as delay in availability for programme use.

Funds are used directly by the EPI programme, which submits requests to the accounting office where the money is kept under special account. For 2005, Funds were utilized by the program for collection of timely EPI Routine reports. Inter-Agency coordinating committee (ICC) is informed whenever GAVI funds are available and utilisation of such funds. Problems have been encountered as funds are received in country by ministry of Finance and Development Planning and MOHSW does not get information in time. This matter was addressed and rectified by the two ministries.

#### 1.1.2	Use of Immunization Services Support

- Funds  were  utilized for distribution of cold chain equipment to different HSAs

- Supportive monitoring and supervision

- Collection of routine immunization reports for timeliness and completeness.

USD

Funds received during 2005 _M236, 986. 00			 (34850)

Funds utilized during 2005  -M27,860.00 				(4097)

Remaining funds (carry over) to 2006_M209,126 .00 		(30753)

Table 1: Use of funds during 2005

| Area of Immunization Services Support | Total amount in US $ | AMOUNT OF FUNDS |
| --- | --- | --- |
|  |  | PUBLIC SECTOR | PRIVATE SECTOR & Other |
|  |  | Central | Region/State/Province | District |  |
| Vaccines | JICA/GAVI |  |  |  |  |
| Injection supplies | Supplied by JICA |  |  |  |  |
| Personnel | Ministry of Health |  |  |  |  |
| Transportation | Ministry of Health |  |  |  |  |
| Maintenance and overheads | Ministry of Health |  |  |  |  |
| Training | WHO |  |  |  |  |
| IEC / social mobilization | WHO/MOHSW/UNICEF |  |  |  |  |
| Outreach | Not achieved |  |  |  |  |
| Supervision | $1,000.00 |  |  |  |  |
| Monitoring and evaluation | MOHSW |  |  |  |  |
| Epidemiological surveillance | WHO |  |  |  |  |
| Vehicles | MOHSW |  |  |  |  |
| Cold chain equipment (Distribution) | $2,000.00 |  |  |  |  |
| Other ……… Collection of Timely and completeness of Routine Immunization Reports from H.S.As.…. (specify) | $1097.00 |  |  |  |  |
| Total: | USD 4097.00 |  |  |  |  |
| Remaining funds for next year: $30753.00 |  |  |  |  |  |

*If no information is available because of block grants, please indicate under ‘other’.

Please attach the minutes of the ICC meeting(s) when the allocation of funds was discussed

Please report on major activities conducted to strengthen immunization, as well as, problems encountered in relation to your multi-year plan.

Collection of routine immunization reports from the H.S.As Distribution of Cod Chain Equipment to H.S.As Distribution of Tally Sheets and vaccine order books to H.S.As Supportive supervisory visits

#### Immunization Data Quality Audit (DQA) (If it has been implemented in your country)

Has a plan of action to improve the reporting system based on the recommendations from the DQA been prepared?

If yes, please – This was reported in 2004 report.

## YES                              NO

## If yes, please report on the degree of its implementation.

The DQA report was included in the 2004 report.

DQA recommendations, the following have been implemented I).Recording Practices -Tally sheets and vaccine record books were printed and distributed to all H.S.As - During monitoring and supervision health personnel were encouraged to keep tally sheets -Drop-out Rate Chart was developed and Distributed to all Health facilities ii)Training : - health officer have been trained in cold chain and vaccine management - Public Health Nurses were trained in AFP, Measles and NNT Surveillance iii)supervision -Supportive supervisory visits were conducted except in QEII, LFDS, Maluti and Mamohau H.S.As. These will be visited in 2006 iv) DQA has been postponed to First Quarter 2007

## Please attach the minutes of the ICC meeting where the plan of action for the DQA was discussed and endorsed by the ICC.

Please report on studies conducted regarding EPI issues during 2005 (for example, coverage surveys).

N0 studies were conducted in 2005

## GAVI/Vaccine Fund New & Under-used Vaccines Support

#### 1.2.1	Receipt of new and under-used vaccines during 2005	N/A

Start of vaccinations with the new and under-used vaccine:           MONTH …           YEAR…N/A

Please report on receipt of vaccines provided by GAVI/VF, including problems encountered.

Vaccines were received on the as follows: VACCINE NO. OF VIALS BATCH NO. EXPIRY DATE HepB 1900 WVA 050002 16/03/2008 HepB 5950 HB 47905 07/2008

#### 1.2.2	Major activities

Please outline major activities that have been or will be undertaken, in relation to, introduction, phasing-in, service strengthening, etc. and report on problems encountered.

Training of health workers of different levels on new vaccine advocacy and social mobilization for increased EPI coverage printing and distribution of IEC material to promote demand for EPI services revision of child booklet to include Vitamin A review and evaluation of a cold room temperature monitor relocation of EPI management unit to new premises close to cold room with infrastructural adjustment

#### 1.2.3	Use of GAVI/The Vaccine Fund financial support (US$100,000) for the introduction of the new vaccine

Please report on the proportion of 100,000 US$ used, activities undertaken, and problems encountered such as delay in availability of funds for programme use. Reported  in 2004 report.

Fund were exhausted in 2003 and 2004 and utilization was included in 2004 GAVI report

## Injection Safety

#### 1.3.1	Receipt of injection safety support

Please report on receipt of injection safety support provided by GAVI/VF, including problems encountered

Injection safety support is provided by JICA

#### Progress of transition plan for safe injections and safe management of sharps waste.

#### Please report problems encountered during the implementation of the transitional plan for safe injection and sharp waste

There are some facilities with non functional incinerators. However, there is an ongoing project to upgrade incinerators in the country.

Please report on the progress based on the indicators chosen by your country in the proposal for GAVI/VF support.

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| -Number of Health facilities with standardized safety boxes -Availability of EPI guidelines and EPI Policy | All Health facilities All Health facilities | All Health facilities are provided with standardizes safety boxes There is an EPI Policy and EPI Guidelines distributed to all health facilities | -Transport shared with other Family Health Programs poses a problem - limited staff at central level and District level |  |

#### 1.3.3	Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

The following major areas of activities have been funded (specify the amount) with the GAVI/ The Vaccine Fund injection safety support in the past year:

No funds for Injection safety materials

# 2.  	Financial sustainability

Inception Report:	Outline timetable and process for the development of a financial sustainability plan . Describe assistance that may be needed for developing a financial sustainability plan.

First Annual Progress Report: 	Submit completed financial sustainability plan by given deadline. Describe major strategies for improving financial sustainability.

Financial sustainability plan was developed and submitted in 2004.

Subsequent Progress Reports:	According to current GAVI rules, support for new and under-used vaccines is covering the total quantity required to meet country targets (assumed to be equal to DTP3 targets) over a five year period (100% x 5 years = 500%).  If the requested amount of new vaccines does not target the full country in a given year (for example, a phasing in of 25%), the country is allowed to request the remaining (in that same example: 75%) in a later year.  In an attempt to help countries find sources of funding in order to attain financial sustainability by slowly phasing out GAVI/VF support, they are encouraged to begin contributing a portion of the vaccine quantity required.  Therefore, GAVI/VF support can be spread out over a maximum of ten years after the initial approval, but will not exceed the 500% limit (see figure 4 in the GAVI Handbook for further clarification).  In table 2.1, specify the annual proportion of five year GAVI/VF support for new vaccines that is planned to be spread-out over a maximum of ten years and co-funded with other sources. Please add the three rows (Proportion funded by GAVI/VF (%), Proportion funded by the Government and other sources (%), Total funding for ………….  (new vaccine)) for each new vaccine.

| Table 2.1: Sources (planned) of financing of new vaccine …………………… (specify) |
| --- |
| Proportion of vaccines supported by * | Annual proportion of vaccines |
|  | 2003.** | 2004. | 2005. | 2006. | 2007 | 20.. | 20.. | 20.. | 20.. | 20.. |
| A: Proportion funded by GAVI/VF (%)*** | 50% | 100% | 100% | 100% | 100% | 50% |  |  |  |  |
| B: Proportion funded by the Government and other sources (%) | 50% | 0 | 0 | 0 | 0 | 50% |  |  |  |  |
| C: Total funding for HepB…………. (new vaccine) | 100% | 100% | 100% | 100% | 100% | 100% |  |  |  |  |

* Percentage of DTP3 coverage (or measles coverage in case of Yellow Fever) that is target for vaccination with a new and under-used vaccine. N/A

** The first year should be the year of GAVI/VF new vaccine introduction

*** Row A should total 500% at the end of GAVI/VF support

In table 2.2 below, describe progress made against major financial sustainability strategies and corresponding indicators.

Table 2.2:	Progress against major financial sustainability strategies and corresponding indicators

| Financial Sustainability Strategy | Specific Actions Taken Towards Achieving Strategy | Progress Achieved | Problems Encountered | Baseline Value of Progress Indicator | Current Value of Progress Indicator | Proposed Changes To Financial Sustainability Strategy |
| --- | --- | --- | --- | --- | --- | --- |
| 1. Mobilizing additional resources | Target additional resources from GOL through MTEF process | yes |  | Proportion of programme costs in MTEF planning period funded |  |  |
| 2.Improved reliability of resources | Include programme costs and financing in MTEF | yes |  | Proportion of districts with fully costed EPI plans |  |  |
| 3.Improved programme efficiency | In service capacity aimed at improving efficiency of service delivery | yes | High staff attrition | Performance ranking of districts developed and implemented |  | Improved EPI systems support |
|  |  |  |  | Number of supervisory visits to districts using supervisory checklists |  |  |

# 3.  	Request for new and under-used vaccines for year 2006

Section 3 is related to the request for new and under used vaccines and injection safety for 2006.

- Up-dated immunization targets

Confirm/update basic data approved with country application: figures are expected to be consistent with those reported in the WHO/UNICEF Joint

Reporting  Forms.  Any changes and/or discrepancies MUST be justified in the space provided (page 12). Targets for future years MUST be provided.

| Table 3 : Update of immunization achievements and annual targets |
| --- |
| Number of | Achievements and targets |
|  | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 |
| DENOMINATORS |  |  |  |  |  |  |  |  |  |
| Births | 48886 | 49863 | 50862 | 51879 | 52917 | 53975 | 55055 | 56156 | 57279 |
| Infants’ deaths | 4449 | 4538 | 4628 | 4721 | 4815 | 5912 | 5010 | 5110 | 5212 |
| Surviving infants | 44437 | 45325 | 46234 | 47158 | 48102 | 49063 | 50045 | 51046 | 52067 |
| Infants vaccinated in 2005(JRF) / to be vaccinated in 2006 and beyond with 1st dose of DTP (DTP1)* | 42167 | 47956 | 48662 | 49950 | 51351 | 52600 | 54154 | 55332 | 57006 |
| Infants vaccinated 2005(JRF) / to be vaccinated in 2006 and beyond with 3rd dose of DTP (DTP3)* | 41553 85% | 45667 92% | 47810 94% | 49285 95% | 50271 95% | 51276 95% | 52302 95% | 53348 95% | 54415 95% |
| NEW VACCINES ** |  |  |  |  |  |  |  |  |  |
| Infants vaccinated 2005 (JRF) / to be vaccinated in 2006and beyond with 1st dose of DTP (DTP1)* …......... (new vaccine) | 37442 | 47956 | 48662 | 49950 | 48683 | 52600 | 54154 | 55332 | 57006 |
| Infants vaccinated 2005 (JRF) / to be vaccinated in 2006 and beyond with 3rd dose of…Hep B3….… ( new vaccine) | 28461 | 45667 | 48462 | 49285 | 50800 | 52355 | 53953 | 55032 | 56706 |
| Wastage rate in 2005 and plan for 2006 beyond*** Hep B 3………….. ( new vaccine) | 30% | 15% | 25% | 25% | 25% | 20% | 20% | 15% | 15% |
| INJECTION SAFETY****0 |  |  |  |  |  |  |  |  |  |
| Pregnant women vaccinated in 2005 (JRF) / to be vaccinated in 2006 and beyond with TT2 | N/D | 2952 | 36208 | 41503 | 44979 | 48578 | 52302 | 53348 | 54415 |
| Infants vaccinated in 2005(JRF) / to be vaccinated in 2006 and beyond with BCG * | 34 317 | 45667 | 48462 | 49285 | 50800 | 52355 | 53953 | 55032 | 56076 |
| Infants vaccinated in 2005(JRF) / to be vaccinated in 2006 and beyond with Measles * | 28 280 | 36075 | 40689 | 43578 | 45509 | 45558 | 47897 | 50540 | 52696 |

* Indicate actual number of children vaccinated in 2005 and updated targets (with either DTP alone or combined)

** Use 3 rows (as indicated under the heading NEW VACCINES) for every new vaccine introduced

*** Indicate actual wastage rate obtained in past years

**** Insert any row as necessary

NB: Due to the change in the new program installed data for TT2 only punctured from November 2005

Please provide justification on changes to baseline, targets, wastage rate, vaccine presentation, etc. from the previously approved plan, and on reported figures which differ from those reported in the WHO/UNICEF Joint Reporting Form in the space provided below.

These figures are from population census projections 1996 ( Bureau of statistics1996 )and Health planning and Statistics Unit in MOHSW. It is envisaged that since population projections have been a major problem, this may be resolved by the national Census of 2006. Therefore the next estimated figures for the following years would be done using the census figures and there will be major changes in the figures for the following years.

3.2	Availability of revised request for new vaccine (to be shared with UNICEF Supply Division) for 2006

In case you are changing the presentation of the vaccine, or increasing your request; please indicate below if UNICEF Supply Division has assured the availability of the new quantity/presentation of supply.

The country is not ready to change for new vaccine

Table 4: Estimated number of doses of HepB …… vaccine for 2007 (specify for one presentation only): Please repeat this table for any other vaccine presentation requested from

GAVI/The Vaccine Fund

|  |  | Formula | For 2007 |
| --- | --- | --- | --- |
| A | Infants vaccinated/to be vaccinated with 1st dose of (new vaccines) |  | 49 950 |
| B | Percentage of vaccines requested from The Vaccine Fund taking into consideration the Financial Sustainable Plan |  | 100% |
| C | Number of doses per child |  | 3 |
| D | Number of doses | AxBx C | 149 850 |
| E | Estimates wastage factor | (see list in table 3) | 1.33 |
| F | Number of doses (incl. wastage) | Ax Cx E x B/100 | 199 301 |
| G | Vaccines buffer stock | Fx 0.25 | 49 825 |
| H | Anticipated vaccines in stock at start of year 2007 (including balance of buffer stock) |  | 50,000 |
| I | Total vaccine doses requested | F + G-H | 199 126 |
| J | Number of doses per vial |  | 10 |
| K | Number of AD syringes (+10% wastage) | (D+G-H) x 1.11 | 166 139 |
| L | Reconstitution syringes (+10% wastage) | I/J x 1.11 | 22 103 |
| M | Total safety boxes (+10% of extra need) | (K+L) /100 x 1.11 | 2 089 |

*Please report the same figure as in table 3.

Table 5: Wastage rates and factors

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

#### 3.3	Confirmed/revised request for injection safety support for the years 2006 -2007

Table 6: Estimated supplies for safety of vaccination for the next two years with …… (Use one table for each vaccine BCG, DTP, measles and TT, and number them from 4 to 8)

#### If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference.

# 4. 	Please report on progress since submission of the last Progress Report based on the indicators selected 	by your country in the proposal for GAVI/VF support

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| Percentage of Drop-out rate Immunization coverage (DPT3) Reduction in Wastage Rate | Below 10% 80% below 30% | DPT- 6% BCG-14% DPT3 – 92% Wastage rate for Measles and BCG remains high. | Country experienced stock-out of BCG for 3 months Populations projections still poses a major problem The 2 antigens do not have VVM. Therefore are discarded after every Immunization Session | Not available |

# Checklist

Checklist of completed form:

| Form Requirement: | Completed | Comments |
| --- | --- | --- |
| Date of submission | August 2006 |  |
| Reporting Period (consistent with previous calendar year) | 2005 |  |
| Table 1 filled-in | Yes |  |
| DQA reported on | 2004 |  |
| Reported on use of 100,000 US$ | 2003 |  |
| Injection Safety Reported on | Yes |  |
| FSP Reported on (progress against country FSP indicators) | 2004 | FSP was developed late 2004 |
| Table 2 filled-in | Yes |  |
| New Vaccine Request completed | N/A |  |
| Revised request for injection safety completed (where applicable) | N/A |  |
| ICC minutes attached to the report | Yes |  |
| Government signatures | Yes |  |
| ICC endorsed | Yes |  |

6.  	Comments:

ICC/RWG comments:

The denominator still poses a big challenge for the country however the issue was discussed on several occasions by the ICC and consultancies .National BOS used Data from the 2001 Lesotho Demographic Health survey and utilized it to calculate population projections. However the country awaiting Census results conducted May 2006.

7.	Signatures

For the Government of ………………..…………………………………

Signature:	……………………………………………...……………...

Title:	………………………………………….………………….

Date:	………………………………………….………………….

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this report. Signature of endorsement of this document does not imply any financial (or legal) commitment on the part of the partner agency or individual.

Financial accountability forms an integral part of GAVI/The Vaccine Fund monitoring of reporting of country performance.  It is based on the regular government audit requirements as detailed in the Banking form.  The ICC Members confirm that the funds received have been audited and accounted for according to standard government or partner requirements.

| Agency/Organisation | Name/Title | Date Signature | Agency/Organisation | Name/Title | Date Signature |
| --- | --- | --- | --- | --- | --- |

~ End ~

# Text boxes

Partnering with The Vaccine Fund

X

Remarks

Phasing: Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided Wastage of vaccines: Countries are expected to plan for a maximum of: 50% wastage rate for a lyophilized vaccine in 10 or 20-dose vial; 25% for a liquid vaccine in a10 or 20-dose vial; 10% for any vaccine (either liquid or lyophilized) in 1 or 2-dose vial. Buffer stock: The buffer stock is recalculated every year as 25% the current vaccine requirement Anticipated vaccines in stock at start of year 2006: It is calculated by counting the current balance of vaccines in stock, including the balance of buffer stock. Write zero if all vaccines supplied for the current year (including the buffer stock) are expected to be consumed before the start of next year. Countries with very low or no vaccines in stock must provide an explanation of the use of the vaccines. AD syringes: A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines. Reconstitution syringes: it applies only for lyophilized vaccines. Write zero for other vaccines. Safety boxes: A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes