Updated February 2004

Progress Report

Partnering with The Vaccine Fund

to the

Global Alliance for Vaccines and Immunization (GAVI)

and

The Vaccine Fund

by the Government of

COUNTRY: MAURITANIA

Date of submission: 30.05.05…………………………… Reporting period: ………….. ( Information provided in this report MUST refer to the previous calendar year ) ( Tick only one ) : Inception report  First annual progress report  Second annual progress report X Third annual progress report  Fourth annual progress report  Fifth annual progress report  Text boxes supplied in this report are meant only to be used as guides. Please feel free to add text beyond the space provided. *Unless otherwise specified, documents may be shared with the GAVI partners and collaborators

# Progress Report Form:  Table of Contents

# Report on progress made during the previous calendar year

  - Immunization Services Support (ISS)

1.1.1	Management of ISS Funds

  - Use of Immunization Services Support

1.1.3	Immunization Data Quality Audit

  - GAVI/Vaccine Fund New and Under-used Vaccines

1.2.1	Receipt of new and under-used vaccines

1.2.2	Major activities

    - Use if GAVI/The Vaccine Fund financial support (US$100,000) for introduction of the new vaccine

1.3	Injection Safety

    - Receipt of injection safety support

    - Progress of transition plan for safe injections and safe management of sharps waste

    - Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

2.  Financial Sustainability

3.  Request for new and under-used vaccine for year… (indicate forthcoming year)

  - Up-dated immunization targets

  - Confirmed/revised request for new vaccine (to be shared with UNICEF Supply Division) for year…

  - Confirmed/revised request for injection safety support for the year…

- Please report on progress since submission of the last Progress Report based on the indicators

selected by your country in the proposal for GAVI/VF support

5.  Checklist

6.  Comments

7.  Signatures

# 1.  	Report on progress made during the previous calendar year

To be filled in by the country for each type of support received from GAVI/The Vaccine Fund.

## Immunization Services Support (ISS)

#### 1.1.1	Management of ISS Funds

Please describe the mechanism for management of ISS funds, including the role of the Inter-Agency Co-ordinating Committee (ICC).

Please report on any problems that have been encountered involving the use of those funds, such as delay in availability for programme use.

The mechanism for management of the GAVI funds involves several stages: The first stage consists in a proposal and plan for the utilization of the funds prepared by the technical committee of the ICC on the basis of the National EPI multi-year plan. The second stage is the submission of the funds utilization plan, together with an activity timetable, to the ICC for discussion and approval of the proposals made by the technical committee. Once the utilization plan has been approved by the ICC and the timetable discussed, the EPI team proceeds with implementation. For each activity, a document is drawn up, containing all the relevant information, the timetable and the estimated budget. Disbursement of the funds is effected by bank cheque in the name of the person responsible for the activity[concerned. The cheques intended for the mobile and advanced strategies are made out in the name of the General Director for Health in two instalments. The second instalment is delivered only after submission of supporting documentation for the first The account operates under the joint signature of the national coordinator and the EPI accountant.

#### 1.1.2	Use of Immunization Services Support

In the past year, the following major areas of activities have been funded with the GAVI/Vaccine Fund contribution.

Funds received during the reporting year  41200 000 ouguiyas

Remaining funds (carry over) from the previous year ________________

Table 1 : Use of funds during reported calendar year 2004_

| Area of Immunization Services Support | Total amount in US $ | Amount of funds |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | PUBLIC SECTOR |  |  | PRIVATE SECTOR & Other |
|  |  | Central | Region/State/Province | District |  |
| Vaccines |  |  |  |  |  |
| Injection supplies |  |  |  |  |  |
| Personnel |  |  |  |  |  |
| Transportation | 1872,65 | 500 000 UM |  |  |  |
| Maintenance and overheads | 7490.63 | 2 000 000 UM |  |  |  |
| Training | 9363.29 | 2 500 000 UM |  |  |  |
| IEC / social mobilization | 5617.97 | 1 500 000 UM |  |  |  |
| Outreach |  |  |  |  |  |
| Supervision |  |  |  |  |  |
| Monitoring and evaluation | 6367.04 | 1 700 000 UM |  |  |  |
| Meeting of regional and private sector EPI focal points | 5617.97 | 1 500 000 UM |  |  |  |
| Epidemiological surveillance |  |  |  |  |  |
| Vehicles |  |  |  |  |  |
| Advanced and mobile strategies | 52434.45 |  | 14 000 000 UM |  |  |
| Production of data collection tools |  |  |  |  |  |
| Acquisition of an IT unit for EPI coordination | 3370.78 | 900 000 UM |  |  |  |
| Acquisition of an office photocopier | 2247.19 | 600 000 UM |  |  |  |
| Cold chain equipment |  |  |  |  |  |
| Other … (please specify) |  |  |  |  |  |
| Total: | 94 381.97 | 25 200 000 UM | 14 000 000 UM |  |  |
| Remaining funds for next year: |  |  |  |  |  |

USD 1 = UM 267

*If no information is available because of block grants, please indicate under ‘other’.

Please attach the minutes of the ICC meeting(s) when the allocation of funds was discussed.

Please report on major activities conducted to strengthen immunization, as well as, problems encountered in relation to your multi-year plan.

All of the planned activities have been implemented and, more particularly, the advanced and mobile immunization activities carried out in the field. However, their implementation was difficult as 2004 was an unusual yea,r marked by the organization of mass immunization campaigns against measles (March – June), the assessment of immunization coverage and the related determining factors (June-July), as well as the preparation and implementation of synchronized national immunization days against poliomyelitis (August-November) . It should be recalled that, in the course of 2004, the EPI drew up the financial sustainability plan and was also the object of a data quality audit (DQA) in September.

#### Immunization Data Quality Audit (DQA) (If it has been implemented in your country)

Has a plan of action to improve the reporting system based on the recommendations from the DQA been prepared?

If yes, please attach the plan.

YES                              NO

X

## If yes, please attach the plan and report on the degree of its implementation.

On the basis of the recommendations of the DQA carried out in September 2004, a data improvement plan was drawn up and is the subject of guidelines intended for the health personnel The implementation of the plan for the reorganization of the system of establishing reports has been under way since January 2005. Training was given to this end. See attached plan

## Please attach the minutes of the ICC meeting where the plan of action for the DQA was discussed and endorsed by the ICC.

Please report on studies conducted regarding EPI issues during the last year (for example, coverage surveys).

Immunization coverage survey (see annex)

## GAVI/Vaccine Fund New & Under-used Vaccines Support

#### 1.2.1	Receipt of new and under-used vaccines during the previous calendar year

Start of vaccinations with the new and under-used vaccine:           MONTH:  MARCH          YEAR: 2005

Please report on receipt of vaccines provided by GAVI/VF, including problems encountered.

Mauritania was granted approval for the introduction of the Hepatitis B vaccine into the routine EPI in July 2004, in accordance with the letter sent to the Minister for Health and Social Affairs. Due to the delay in the acquisition of the vaccines received on 18 January 2005, the official launch of the activity for the introduction of the hep B vaccine did not take place until 1 March 2005.

#### 1.2.2	Major activities

Please outline major activities that have been or will be undertaken, in relation to, introduction, phasing-in, service strengthening, etc. and report on problems encountered.

See attached report on the introduction of the hepatitis B vaccine into the routine EPI.

#### 1.2.3	Use of GAVI/The Vaccine Fund financial support (US$100,000) for the introduction of the new vaccine

Please report on the proportion of 100,000 US$ used, activities undertaken, and problems encountered such as delay in availability of funds for programme use.

A plan for the utilization of the funds intended for the introduction of the hepatitis B vaccine into the routine EPI is attached to the present progress report.

## Injection Safety

#### 1.3.1	Receipt of injection safety support

Please report on receipt of injection safety support provided by GAVI/VF, including problems encountered

The first tranche of the GAVI funds intended for the construction of incinerators was received in 2004. At the request of the Ministry of Health, a mission of the AMP (’Agence pour la médecine préventive) consisting of Mr Philippe Jaillard, regional consultant for immunization logistics at the AMP came to Nouakchott to assist in the drafting of a waste management plan, the choice of type of incinerator and, more importantly, the criteria according to which such equipment should be built. It will be recalled that certain central departments of the Ministry of Health, particularly the Preventive Medicine Department (DMH), are responsible for the construction of incinerators in certain areas of the country. The question of incorporating such incinerators was discussed during the mission undertaken by the AMP regional coordinator. Incinerators have already been built in certain localities while others are in the course of construction.

#### Progress of transition plan for safe injections and safe management of sharps waste.

Please report on the progress based on the indicators chosen by your country in the proposal for GAVI/VF support.

It will be recalled that the country introduced the use of AD syringes and safety boxes back in 2001 with government  financing.

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |

#### 1.3.3	Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

The following major areas of activities have been funded (specify the amount) with the GAVI/The Vaccine Fund injection safety support in the past year:

The funds intended for injection safety were received in the form of a cash contribution at the request of the government of Mauritania, in view of the fact that the state budget provides for a line for the purchase of vaccines and injection supplies, particularly AD syringes for all the antigens, as well as safety boxes in sufficient quantities.

# 2.  	Financial sustainability

Inception Report :			Outline timetable and major steps taken towards improving financial sustainability and the development of a 						financial sustainability plan.

First Annual Progress Report : 	Submit completed financial sustainability plan by given deadline and describe assistance that will be needed

for financial sustainability planning.

N/A

Second Annual Progress Report :	Describe indicators selected for monitoring financial sustainability plans and include baseline and current values for each indicator. In the following table 2, specify the annual proportion of five year of GAVI/VF support for new vaccines that is planned to be spread-out to ten years and co-funded with other sources.

Sustainability plan

Mauritania submitted its financial sustainability plan for examination by the GAVI committee in January.

The indicators used for monitoring the plan are as follows :

1. Mobilization of internal resources

| Activities | Period | Responsibility | Monitoring indicators |
| --- | --- | --- | --- |
| Financing routine EPI vaccines and consumables | 2005- 2013 | MF MHSA | Availability of vaccines and consumables for the programme |
| Training additional health workers | 2005- 2013 | MFP MHSA | Number of health workers trained |
| Developing new health infrastructures | 2005- 2013 | MHSA | Number of hospitals, health centres, health posts and training colleges built |
| Ensuring that the cold chain is equipped and maintained | 2005- 2013 | MHSA PARTNERS | Health structures equipped and operational equipment |
| Strengthening transport logistics | 2005- 2013 | MHSA PARTNERS | Number of vehicles, motorbikes available |
| Decentralizing budget spending | 2005- 2013 | MF MHSA | Availability of the budget at all levels of the health pyramid |
| Contributing to the organization of supplementary immunization activities | 2005- 2013 | MHSA PARTNERS | Availability of funds allocated to supplementary activities |
| Ensuring private health sector participation in the immunization activities | 2005-2013 | MHSA | Percentage of targets covered |

2. Mobilization of external resources

| Activities | Period | Responsibility | Monitoring indicators |
| --- | --- | --- | --- |
| Advocacy with partners in favour of the mobilization of resources for the EPI | 2005 2013 |  | Volume of financing mobilised in favour of the EPI |
| GAVI financing for the introduction of new vaccines | 2005 2008 | GAVI | Availability of the new vaccines |

3. Measures and strategies to improve reliability of resources

| Activities | Period | Responsibility | Monitoring indicators |
| --- | --- | --- | --- |
| Make more flexible and improve understanding of the budgetary procedures of the government and the partners | 2005 2013 |  | Availability of funds at all times and at all levels of the health pyramid, quality supporting documentation transmitted in time and satisfactory absorption rates |

4. Measures and strategies to improve efficiency of resource utilization

| Activities | Period | Responsibility | Monitoring indicators |
| --- | --- | --- | --- |
| Reducing vaccine wastage rates | 2005 2013 | MHSA /EPI | Better use of lyophilized and non-lyophilized vaccines, with wastage rates consistent with projections |
| Reducing drop-out rates | 2005 2013 | MHSA / EPI | Knowledge of immunization timetable by the communities and association of the communities in the planning of immunization sessions |
| Monitoring EPI activities | 2005 2013 | MHSA / ICC | Number of minutes of ICC meetings |

| Table 2 : Sources (planned) of financing of new vaccine: Hepatitis B |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Proportion of vaccines supported by | Annual proportion of vaccines |  |  |  |  |  |  |  |  |  |
|  | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 |
| Proportion funded by GAVI/VF (%) | 100% | 100% | 100% | 100% | 100% |  |  |  |  |  |
| Proportion funded by the Government and other sources (%) |  |  |  |  |  | 100% | 100% | 100% | 100% | 100% |
| Total funding for hepatitis B* | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |
| * Percentage of DTP3 coverage (or measles coverage in case of Yellow Fever) that is target for vaccination with a new and under-used vaccine |  |  |  |  |  |  |  |  |  |  |

Subsequent reports:	Summarize progress made against the financing strategy, actions and indicators section of the FSP; include successes, difficulties and responses to challenges encountered in achieving outlined strategies and actions. Report current values for indicators selected to monitor progress towards financial sustainability. Include funds received to date versus those expected for last year and the current year and actions taken in response to any difficulties.

Update the estimates on program costs and financing with a focus on the last year, the current year and the next 3 years.  For the last year and current year, update the estimates of expected funding provided in the FSP tables with actual funds received since. For the next 3 years, update any changes in the costing and financing projections.  The updates should be reported using the same standardized tables and tools used for the development of the FSP (latest versions available on http://www.gaviftf.org under FSP guidelines and annexes. Highlight assistance needed from partners at local, regional and/or global level.

# 3.  	Request for new and under-used vaccines for year …………….. ( indicate forthcoming year )

Section 3 is related to the request for new and under used  vaccines and injection safety for the forthcoming year.

- Up-dated immunization targets

Confirm/update basic data  approved with country application: figures are expected to be consistent with those reported in the WHO/UNICEF Joint Reporting Forms.  Any changes and/or discrepancies MUST be justified in the space provided (page 12). Targets for future years MUST be provided.

| Table 3 : Update of immunization achievements and annual targets |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of | Achievements and targets |  |  |  |  |  |  |  |  |
|  | 2000 | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 |
| DENOMINATORS |  |  |  |  |  |  |  |  |  |
| Births | 119 138 | 121 997 | 124 925 | 127 923 | 115550 | 134 137 | 137 356 | 140 653 | 144 028 |
| Infants’ deaths | 8 816 | 9 028 | 9 244 | 9 466 | 8551 | 9 926 | 10 164 | 10 408 | 10 658 |
| Surviving infants | 110 321 | 112 969 | 115 680 | 118 457 | 115550 | 124 211 | 127 192 | 130 244 | 133 370 |
| Infants vaccinated / to be vaccinated with 1st dose of DTP (DTP1)* | 49 438 | 87 318 | 108 621 | 95 292 | 98352 | 114 274 | 120 832 | 123 732 | 126 702 |
| Infants vaccinated / to be vaccinated with 3rd dose of DTP (DTP3)* | 34 221 | 64 907 | 90 736 | 79 808 | 80973 | 105 579 | 114 473 | 117 220 | 120 033 |
| NEW VACCINES ** |  |  |  |  |  |  |  |  |  |
| Infants vaccinated / to be vaccinated with 1st dose of …......... ( new vaccine) |  |  |  |  |  | 114 274 | 120 832 | 123 732 | 126 702 |
| Infants vaccinated / to be vaccinated with 3rd dose of …….… ( new vaccine) |  |  |  |  |  | 105 579 | 114 473 | 117 220 | 120 033 |
| Wastage rate of *** ………….. ( new vaccine) |  |  |  |  |  | 1.25 | 1.18 | 1.11 | 1.11 |
| INJECTION SAFETY**** |  |  |  |  |  |  |  |  |  |
| Pregnant women vaccinated / to be vaccinated with TT | 21 799 | 37 724 | 49 487 | 45 777 | 43341 | 80 482 | 96 149 | 98 457 | 100 820 |
| Infants vaccinated / to be vaccinated with BCG | 52 708 | 74 943 | 107 636 | 94 630 | 99143 | 118 041 | 130 488 | 133 620 | 136 827 |
| Infants vaccinated / to be vaccinated with Measles | 31 116 | 62 160 | 88 717 | 74 494 | 73953 | 105 579 | 120 832 | 123 732 | 126 702 |

* Indicate actual number of children vaccinated in past years and updated targets (with either DTP alone or combined)

** Use 3 rows for every new vaccine introduced

*** Indicate actual wastage rate obtained in past years

**** Insert any row as necessary

Please provide justification on changes to baseline, targets, wastage rate, vaccine presentation, etc. from the previously approved plan, and on reported figures which differ from those reported in the WHO/UNICEF Joint Reporting Form in the space provided below.

| The initial version of the Population and Housing General Census (PHGC 2000) estimated the country’s total population at 2 548 157 inhabitants in 2000, with a growth rate of 2.6%. This figure was revised in the final version of the census, estimating the population at 2 508 159 in 2000, with a growth rate of 2.4%. As the report relied on the updated data of the PHGC 2000, the baseline data drawn from the population figures have been amended in consequence. The initial immunization targets contained in the submission plan approved in 2002 and established in accordance with the EPI strategic plan for 2002-2996 have been updated in line with the EPI achievements. The updated targets are the same as those contained in the plan for the introduction of new vaccines (hepatitis B) submitted to GAVI in April 2004 and approved in July of the same year. |  |
| --- | --- |

3.2	Confirmed/Revised request for new vaccine (to be shared with UNICEF Supply Division) for the year …… (indicate forthcoming year)

Please indicate that UNICEF Supply Division has assured the availability of the new quantity of supply according to new changes.

Table 4: Estimated number of doses of …… vaccine (specify for one presentation only) : (Please repeat this table for any other vaccine presentation requested from

GAVI/The Vaccine Fund

|  |  | Formula | For year …… | Remarks |
| --- | --- | --- | --- | --- |
| A | Infants vaccinated / to be vaccinated with 1st dose of …............... ( new vaccine) |  | * | - Phasing: Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided - Wastage of vaccines: Countries are expected to plan for a maximum of: 50% wastage rate for a lyophilized vaccine in 10 or 20-dose vial; 25% for a liquid vaccine in a 10 or 20-dose vial; 10% for any vaccine (either liquid or lyophilized) in 1 or 2-dose vial. - Buffer stock: The buffer stock for vaccines and AD syringes is set at 25%. This is added to the first stock of doses required to introduce the vaccination in any given geographic area. Write zero under other years. In case of a phased introduction with the buffer stock spread over several years, the formula should read: [ F – number of doses (incl. wastage) received in previous year ] * 0.25. - Anticipated vaccines in stock at start of year… ….: It is calculated by deducting the buffer stock received in previous years from the current balance of vaccines in stock. - AD syringes: A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines. - Reconstitution syringes: it applies only for lyophilized vaccines. Write zero for other vaccines. - Safety boxes: A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes |
| B | Percentage of vaccines requested from The Vaccine Fund taking into consideration the Financial Sustainability Plan | % |  |  |
| C | Number of doses per child |  |  |  |
| D | Number of doses | A x B/100 x C |  |  |
| E | Estimated wastage factor | (see list in table 3) |  |  |
| F | Number of doses ( incl. wastage) | A x C x E x B/100 |  |  |
| G | Vaccines buffer stock | F x 0.25 |  |  |
| H | Anticipated vaccines in stock at start of year …. |  |  |  |
| I | Total vaccine doses requested | F + G - H |  |  |
| J | Number of doses per vial |  |  |  |
| K | Number of AD syringes (+ 10% wastage) | ( D + G – H ) x 1.11 |  |  |
| L | Reconstitution syringes (+ 10% wastage) | I / J x 1.11 |  |  |
| M | Total of safety boxes (+ 10% of extra need) | ( K + L ) / 100 x 1.11 |  |  |

Table 5: Wastage rates and factors

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

*Please report the same figure as in table 3.

#### 3.3	Confirmed/revised request for injection safety support for the year …… (indicate forthcoming year)

Table 6: Estimated supplies for safety of vaccination for the next two years with …… (Use one table for each vaccine BCG, DTP, measles and TT, and number them from 4 to 8)

|  |  | Formula | For year …… | For year …… |
| --- | --- | --- | --- | --- |
| A | Target of children for …… vaccination (for TT : target of pregnant women) | # |  |  |
| B | Number of doses per child (for TT woman) | # |  |  |
| C | Number of …… doses | A x B |  |  |
| D | AD syringes (+10% wastage) | C x 1.11 |  |  |
| E | AD syringes buffer stock | D x 0.25 |  |  |
| F | Total AD syringes | D + E |  |  |
| G | Number of doses per vial | # |  |  |
| H | Vaccine wastage factor 4 | Either 2 or 1.6 |  |  |
| I | Number of reconstitution syringes (+10% wastage) | C x H x 1.11 / G |  |  |
| J | Number of safety boxes (+10% of extra need) | ( F + I ) x 1.11 / 100 |  |  |

#### If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference.

# 4. 	Please report on progress since submission of the last Progress Report based on the indicators selected 	by your country in the proposal for GAVI/VF support

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| DTP3 Immunization coverage rate | Bringing the immunization coverage rate of children aged 0 to 11 months and of pregnant women up to 70% for DTP3 and 40% for TT2 in 2003 | The results obtained in 2004 : : - BCG : 84% - DTP3 : 71% - Measles: 66% - TT2 : 36% | The constraints are connected essentially with the system for establishing the routine EPI monthly reports, with the result that the data are not reliable, leading to a major follow-up and monitoring problem. | To increase the immunization coverage of children aged 0 to 11 months and of pregnant women to 85% for DTP3 and hepatitis B and to 50% for TT2 in 2004 |

# Checklist

Checklist of completed form:

| Form Requirement: | Completed | Comments |
| --- | --- | --- |
| Date of submission | x |  |
| Reporting Period (consistent with previous calendar year) | x |  |
| Table 1 filled-in | x |  |
| DQA reported on | x |  |
| Reported on use of 100,000 US$ |  | As the introduction of the hepatitis B vaccine did not take place until March 2005, this part will be dealt with in the progress report for 2005 |
| Injection Safety Reported on | x |  |
| FSP Reported on (progress against country FSP indicators) | x |  |
| Table 2 filled-in | x |  |
| New Vaccine Request completed | x |  |
| Revised request for injection safety completed (where applicable) | x |  |
| ICC minutes attached to the report | x |  |
| Government signatures | x |  |
| ICC endorsed | x |  |

6.  	Comments

ICC/RWG comments:

7.	Signatures

For the Government of …… Mohamed Lemine Ould Selmane

Signature:	……………………………………………...……………...

Title: 	Minister of Health and Social Affairs

Date:	………………………………………….………………….

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this report. Signature of endorsement of this document does not imply any financial (or legal) commitment on the part of the partner agency or individual.

Financial accountability forms an integral part of GAVI/The Vaccine Fund monitoring of reporting of country performance.  It is based on the regular government audit requirements as detailed in the Banking form.  The ICC Members confirm that the funds received have been audited and accounted for according to standard government or partner requirements.

| Agency/Organization | Name/Title | Date Signature | Agency/Organization | Name/Title | Date Signature |
| --- | --- | --- | --- | --- | --- |
| Ministry of Health and Social Affairs | Mohamed Lemine Ould Abdi Ould Jyed: Secretary General |  |  |  |  |
| Ministry of Health and Social Affairs | Dr Mohamed Idoumou Ould Mohamed Vall : Health Protection Director, MHSA |  |  |  |  |
| Ministry of Health and Social Affairs | Dr Ishagh Ould Khalef National EPI Coordinator, MHSA |  |  |  |  |
| UNICEF | Dr Diallo Souleymane : UNICEF Representative |  |  |  |  |
| World Health Organization (WHO) | Dr Diallo Pathé : WHO representative |  |  |  |  |

~ End ~

GAVI will fund the procurement of AD syringes to deliver 2 doses of TT to pregnant women. If the immunization policy of the country includes all Women of Child Bearing Age (WCBA), GAVI/The Vaccine Fund will contribute to a maximum of 2 doses for Pregnant Women (estimated as total births).

The buffer stock for vaccines and AD syringes is set at 25%. This is added to the first stock of doses required to introduce the vaccination in any given geographic area. Write zero for other years.

Only for lyophilized vaccines. Write zero for other vaccines

4 Standard wastage factor will be used for calculation of re-constitution syringes. It will be 2 for BCG, 1.6 for measles and YF.