January 2005

Progress Report

Partnering with The Vaccine Fund

to the

Global Alliance for Vaccines and Immunization (GAVI)

and

The Vaccine Fund

by the Government of

COUNTRY: MAURITANIA

Date of submission: …May 2006 ………………………… Reporting period: 2005 ( Information provided in this report MUST refer to 2005 activities ) ( Tick only one ) : Inception report  First annual progress report  Second annual progress report  Third annual progress report x Fourth annual progress report  Fifth annual progress report  Text boxes supplied in this report are meant only to be used as guides. Please feel free to add text beyond the space provided. *Unless otherwise specified, documents may be shared with GAVI partners and collaborators

# Progress Report Form:  Table of Contents

# Report on progress made during 2004

  - Immunization Services Support (ISS)

1.1.1	Management of ISS Funds

  - Use of Immunization Services Support

1.1.3	Immunization Data Quality Audit

  - GAVI/Vaccine Fund New and Under-used Vaccines

1.2.1	Receipt of new and under-used vaccines

1.2.2	Major activities

    - Use if GAVI/The Vaccine Fund financial support (US$100,000) for introduction of the new vaccine

1.3	Injection Safety

    - Receipt of injection safety support

    - Progress of transition plan for safe injections and safe management of sharps waste

    - Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

2.  Financial Sustainability

3.  Request for new and under-used vaccine for 2006

  - Up-dated immunization targets

  - Confirmed/revised request for new vaccine (to be shared with UNICEF Supply Division) for year…

  - Confirmed/revised request for injection safety support for the year…

- Please report on progress since submission of the last Progress Report based on the indicators

selected by your country in the proposal for GAVI/VF support

5.  Checklist

6.  Comments

7.  Signatures

# 1.  	Report on progress made during 2005

To be filled in by the country for each type of support received from GAVI/The Vaccine Fund.

## Immunization Services Support (ISS)

#### 1.1.1	Management of ISS Funds

Please describe the mechanism for management of ISS funds, including the role of the Inter-Agency Co-ordinating Committee (ICC).

Please report on any problems that have been encountered involving the use of those funds, such as delay in availability for programme use.

The mechanism for the management of GAVI ISS funds comprises several stages: First stage: As soon as a tranche of ISS or injection safety funding is announced, the central EPI Unit, together with the ICC Technical Committee, is responsible for immediately drafting a proposal for use of the funds on the basis of the EPI multi-year plan and the priorities set in its annual plan of operations. Second stage: This consists of the submission of the proposal for fund use along with a chronogram of activities to the ICC, which must discuss and adopt the proposals made by the Technical Committee. Third stage: Once the fund use plan has been approved by the ICC and the chronogram has been discussed, the EPI team starts with the implementation component. For every activity, a document is prepared that contains all details, the timetable for execution and the estimated budget. Funds are disbursed by means of bank cheques made out to the officer in charge of a given activity. Cheques to cover outreach and mobile activities are made out to the Regional Health Director. Cheques must be countersigned by both the National Coordinator and the EPI Accountant.

#### 1.1.2	Use of Immunization Services Support

In 2005, the following major areas of activities have been funded with the GAVI/Vaccine Fund Immunization Services Support contribution.

Funds received during 2005:  42,103,000 (USD 157,689.13)

Remaining funds (carry over) from 2004 ________________

Table 1: Use of funds during 2005

| Area of Immunization Services Support | Total amount in US $ | AMOUNT OF FUNDS |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | PUBLIC SECTOR |  |  | PRIVATE SECTOR & Other |
|  |  | Central | Region/State/Province | District |  |
| Vaccines |  |  |  |  |  |
| Injection supplies |  |  |  |  |  |
| Personnel | 3640,44 | 972 000 UM |  |  |  |
| Transportation | 2996.25 | 800 000 UM |  |  |  |
| Maintenance and overheads | 11340.82 | 3 028 000 UM |  |  |  |
| Training | 5992.50 | 1600 000 UM |  |  |  |
| IEC / social mobilization |  |  |  |  |  |
| Outreach |  |  |  |  |  |
| Supervision | 7490.63 | 2000 000 UM |  |  |  |
| Monitoring and evaluation (meeting of regional focal pts) | 6367.04 | 1700 000 UM |  |  |  |
| Epidemiological surveillance |  |  |  |  |  |
| Vehicles |  |  |  |  |  |
| Cold chain equipment (repairs and maintenance) | 3370.78 | 900 000UM |  |  |  |
| Feedback workshop on immunization coverage survey | 2996.25 | 800 000 UM |  |  |  |
| Support for mobile and outreach immunization activities in the field | 53569.28 |  | 14 303 000 UM |  |  |
| Injection safety (construction of incinerators) | 59925.09 | 16 000 000 UM |  |  |  |
| Total: |  | 27 800 000 UM | 14 303 000 UM |  |  |
| Grand total | 157689.13 | 42 103 000 UM |  |  |  |
| Remaining funds for next year: |  |  |  |  |  |

*If no information is available because of block grants, please indicate under ‘other’.

Please attach the minutes of the ICC meeting(s) when the allocation of funds was discussed.

Please report on major activities conducted to strengthen immunization, as well as, problems encountered in relation to your multi-year plan.

All activities programmed for 2005 were executed. However, it should be noted that field activities, especially outreach and mobile strategies and supervisory missions, were executed late owing to a lack of rolling stock. The vehicle fleet of the Ministry of Health, primarily located inland, is inadequate and obsolete.

#### Immunization Data Quality Audit (DQA) (If it has been implemented in your country)

Has a plan of action to improve the reporting system based on the recommendations from the DQA been prepared?

If yes, please attach the plan.

YES                              NO

X

## If yes, please report on the degree of its implementation.

The last DQA was conducted in September 2004 and another one has been scheduled for 2006. With regard to the plan for implementing the recommendations from the 2004 DQA, please see last year’s annual status report.

## Please attach the minutes of the ICC meeting where the plan of action for the DQA was discussed and endorsed by the ICC.

Please report on studies conducted regarding EPI issues during 2004 (for example, coverage surveys).

## GAVI/Vaccine Fund New & Under-used Vaccines Support

#### 1.2.1	Receipt of new and under-used vaccines during 2004

Start of vaccinations with the new and under-used vaccine:           MONTH…MARCH..           YEAR…2005…….

Please report on receipt of vaccines provided by GAVI/VF, including problems encountered.

After Mauritania's application for the introduction of the HepB into the ordinary EPI program was approved in July 2004, we drafted a roll-out program (see annex) with a view to commencing immunization in early 2005. Accordingly, we set up a Technical Committee responsible for the preparatory phase and started to revise tools and implement a training plan covering all staff involved in immunization, at all levels of the health pyramid. Yet the vaccines were not delivered until 18 January 2005, which obliged us to postpone the official launch until March 2005, whereas the initial date was 22 January 2006.

#### 1.2.2	Major activities

Please outline major activities that have been or will be undertaken, in relation to, introduction, phasing-in, service strengthening, etc. and report on problems encountered.

Including the HepB vaccine in the immunization programme led to a need for a series of activities, all of which are described in the plan of introduction and which include the following: (1) the establishment, within the Ministry of Health, of the Technical Committee in charge of preparations for the inclusion of HepB in routine immunization; (2) revision, reproduction and distribution of management tools to the peripheral immunization sites; (3) training of all health staff involved in immunization, from the Regional Director to the Nurse Station Head, on EPI management tools based on a technical manual and guidelines drafted at the central level; (4) delivery of vaccines and consumables; (5) a broad awareness-building programme that first targeted local officials and administrative authorities, then all population groups via a media programme (radio, TV and written press). This awareness-building campaign lasted several weeks before and after the official launching by the Minister of Health and Social Affairs on 2 March 2005 in the presence of other ministers and representatives of UNICEF and WHO in Mauritania.

#### 1.2.3	Use of GAVI/The Vaccine Fund financial support (US$100,000) for the introduction of the new vaccine

Please report on the proportion of 100,000 US$ used, activities undertaken, and problems encountered such as delay in availability of funds for programme use.

See attached report on the introduction of HepB in Mauritania.

## Injection Safety

#### 1.3.1	Receipt of injection safety support

Please report on receipt of injection safety support provided by GAVI/VF, including problems encountered

The first tranche of GAVI funds earmarked for the construction of incinerators was received in 2004 while the second tranche arrived in 2005. At the request of the Ministry of Health, a mission from AMP (Agency for Preventive Medicine), composed of Mr Philippe Jaillard, AMP Regional Adviser for Immunization Logistics, came to Nouakchott to help us draft a waste management plan, choose the right type of incinerator and above all define the construction specifications. Accordingly, most health centres now have special incinerators reserved exclusively for immunization waste (Nouakchott, Trarza, Brakna, Tagant, Assaba and Gorgo). The remaining health centres are due to get incinerators in 2006.

#### Progress of transition plan for safe injections and safe management of sharp waste

#### Please report problems encountered during the implementation of the transitional plan for safe injection and sharp waste

It will be recalled that AD syringes and safety boxes were introduced nationwide 2001, with State funds.

Please report on the progress based on the indicators chosen by your country in the proposal for GAVI/VF support.

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |

#### 1.3.3	Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

The following major areas of activities have been funded (specify the amount) with the GAVI/The Vaccine Fund injection safety support in the past year:

The funds earmarked for injection safety were received in the form of contributions in kind at the request of the Mauritanian government, given that the State budget includes a line for the procurement of vaccines and injection supplies, especially AD syringes for all antigens as well as a sufficient number of safety boxes.

# 2.  	Financial sustainability

Inception Report:	Outline timetable and process for the development of a financial sustainability plan . Describe assistance that may be needed for developing a financial sustainability plan.

First Annual Progress Report: 	Submit completed financial sustainability plan by given deadline. Describe major strategies for improving financial sustainability.

The EPI financial sustainability plan for Mauritania was prepared at the end of 2004 with technical support from the ARIVA project and submitted to GAVI in early 2005.

Subsequent Progress Reports:	According to current GAVI rules, support for new and under-used vaccines is covering the total quantity required to meet country targets (assumed to be equal to DTP3 targets) over a five year period (100% x 5 years = 500%).  If the requested amount of new vaccines does not target the full country in a given year (for example, a phasing in of 25%), the country is allowed to request the remaining (in that same example: 75%) in a later year.  In an attempt to help countries find sources of funding in order to attain financial sustainability by slowly phasing out GAVI/VF support, they are encouraged to begin contributing a portion of the vaccine quantity required.  Therefore, GAVI/VF support can be spread out over a maximum of ten years after the initial approval, but will not exceed the 500% limit (see figure 4 in the GAVI Handbook for further clarification).  In table 2.1, specify the annual proportion of five year GAVI/VF support for new vaccines that is planned to be spread-out over a maximum of ten years and co-funded with other sources. Please add the three rows (Proportion funded by GAVI/VF (%), Proportion funded by the Government and other sources (%), Total funding for ………….  (new vaccine)) for each new vaccine.

| Table 2.1: Sources (planned) of financing of new vaccine …………………… (specify) |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Proportion of vaccines supported by * | Annual proportion of vaccines |  |  |  |  |  |  |  |  |  |
|  | 2005** | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 |
| A: Proportion funded by GAVI/VF (%)*** | 100% | 100% | 100% | 100% | 100% |  |  |  |  |  |
| B: Proportion funded by the Government and other sources (%) |  |  |  |  |  | 100% | 100% | 100% | 100% | 100% |
| C: Total funding for …………. (new vaccine) | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |

* Percentage of DTP3 coverage (or measles coverage in case of Yellow Fever) that is target for vaccination with a new and under-used vaccine.

** The first year should be the year of GAVI/VF new vaccine introduction

*** Row A should total 500% at the end of GAVI/VF support

In table 2.2 below, describe progress made against major financial sustainability strategies and corresponding indicators.

Table 2.2:	Progress against major financial sustainability strategies and corresponding indicators

| Financial Sustainability Strategy | Specific Actions Taken Towards Achieving Strategy | Progress Achieved | Problems Encountered | Baseline Value of Progress Indicator | Current Value of Progress Indicator | Proposed Changes To Financial Sustainability Strategy |
| --- | --- | --- | --- | --- | --- | --- |
| 1.Mobilization of internal resources | - Maintenance of funds earmarked for purchase of vaccines and consumables - Human resources development plan - Plan for extension of health structures - Technical reinforcement of health structures and immunizing units with cold chain equipment - Decentralization of State budget sequencing - Involvement of private sector in immunization activities | - Amount earmarked meets country’s requirements for traditional vaccines and consumables - HRDP adopted in 2006 with projections taking real needs into consideration - 9 private clinics and doctor’s offices benefited from support from national program for creation of fixed immunizing units | - Absence of maintenance policy and plan - HRDP not yet validated - Rolling stock not yet reinforced at operational level - Tardy implementation of State budget | - Availability of vaccines and consumables for program - Number of health agents trained - Number of hospitals, health centres and stations and training schools built and outfitted - Number of vehicles/motorcycles available - Availability of budget on all levels of health pyramid - Proportion of targets reached | - 100% of vaccines and consumables are ordered and available on time - 9 clinics and doctor’s offices are supplied regularly with vaccines and consumables | Strategies are maintained with an emphasis on advocacy for resource mobilization |
| 2.Mobilization of external resources | - Develop advocacy vis-à-vis partners for EPI resource mobilization | - 2005 funding from partners – about USD 1,294,000 - HepB introduction funded by GAVI | No major difficulties to report but some EPI activities could not be funded | - Volume of EPI funding mobilized - Availability of new vaccines | - Funding volume in line w/ forecasts - Availability of new vaccines assured | Strategies are maintained with an emphasis on advocacy for resource mobilization |
| 3.Measures and strategies to enhance resource reliability | Decentralization process under way | Funds are allocated directly to districts | Funds released late and disbursement procedures remain cumbersome | - Funds available on time at all levels of health pyramid, high-quality supporting documents forwarded in time and satisfactory absorption rates | Funds are available at district level | Strategies are maintained with an emphasis on advocacy at MHSA and Finance to ensure timely fund allocation with a view to guaranteeing implementation of planned activities |
| 4.Measures and strategies to improve efficiency of resource utilization | Vaccine management, control of wastage rates, open vial policy, communication and community involvement strategies to reduce drop-out rates were all topics covered in training courses provided for health agents in conjunction with introduction of HepB vaccine Follow-up of EPI activities | It is difficult to measure progress using wastage rates because data is fragmented. However, DTP1-DTP3 drop-out rates for 38/53 districts = >10% The ICC Technical Committee meets regularly at least once every 2 mos | - Difficult to monitor wastage rates - Insufficient funding for IEC activities | - Better utilization of lyophilized and non-lyophilized antigens with wastage rates in line w/ forecasts - Communities are familiar w/ vaccine timetables and help plan immunization sessions - Number of minutes for ICC meetings | - Wastage rates: NA - Drop-out rates: - 38 districts>10% - 5 meetings of ICC Technical Committee | Strategies are maintained with an emphasis on advocacy to secure funding for communication, training and supervisory activities |

# 3.  	Request for new and under-used vaccines for year 2007

Section 3 is related to the request for new and under used vaccines and injection safety for 2006.

- Updated immunization targets

Confirm/update basic data approved with country application: figures are expected to be consistent with those reported in the WHO/UNICEF Joint

Reporting Forms.  Any changes and/or discrepancies MUST be justified in the space provided (page 12). Targets for future years MUST be provided.

| Number of |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 |
| DENOMINATORS | 134,137 | 137,356 | 140,653 | 144,028 | 147,485 | 151,025 | 154,649 | 158,361 |
| Births | 9,926 | 10,164 | 10,408 | 10,658 | 10,914 | 11,176 | 11,444 | 11,719 |
| Infant deaths | 124,211 | 127,192 | 130,244 | 133,370 | 136,571 | 139,849 | 143,205 | 146,642 |
| Surviving infants | 101,116 | 127,192 | 130,244 | 133,370 | 136,571 | 139,849 | 143,205 | 146,642 |
| Infants vaccinated in 2005 (JRF) / to be vaccinated in 2006 and beyond with 1st dose of DTP (DTP1)* | 83,442 | 114,473 | 117,220 | 120,033 | 122,914 | 132,856 | 137,477 | 140,777 |
| Infants vaccinated 2005 (JRF) / to be vaccinated in 2006 and beyond with 3rd dose of DTP (DTP3)* |  |  |  |  |  |  |  |  |
| NEW VACCINES ** | 110,660 | 127,192 | 130,244 | 133,370 | 136,571 | 139,849 | 143,205 | 146,642 |
| Infants vaccinated 2005 (JRF) / to be vaccinated in 2006 and beyond with 1st dose of HepB | 49,900 | 114,473 | 117,220 | 120,033 | 122,914 | 132,856 | 137,477 | 140,777 |
| Infants vaccinated 2005 (JRF) / to be vaccinated in 2006 and beyond with 3rd dose of HepB | ND | 15% | 10% | 10% | 10% | 10% | 8% | 8% |
| Wastage rate in 2005 and plan for 2006 and beyond*** HepB |  |  |  |  |  |  |  |  |
| INJECTION SAFETY**** | 45,930 | 96,149 | 98,457 | 100,820 | 110,614 | 113,269 | 120,627 | 126,689 |
| Pregnant women vaccinated in 2005 (JRF) / to be vaccinated in 2006 and beyond with TT2 | 103,332 | 120,832 | 123,732 | 126,702 | 129,743 | 132,856 | 137,477 | 140,777 |
| Infants vaccinated in 2005 (JRF) / to be vaccinated in 2006 and beyond with BCG * | 72,535 | 120,832 | 123,732 | 126,702 | 129,743 | 132,856 | 137,477 | 140,777 |
| Infants vaccinated in 2005 (JRF) / to be vaccinated in 2006 and beyond with Measles * | 134,137 | 137,356 | 140,653 | 144,028 | 147,485 | 151,025 | 154,649 | 158,361 |

* Indicate actual number of children vaccinated in 2004 and updated targets (with either DTP alone or combined)

** Use 3 rows (as indicated under the heading NEW VACCINES) for every new vaccine introduced

*** Indicate actual wastage rate obtained in past years

**** Insert any row as necessary

Please provide justification on changes to baseline, targets, wastage rate, vaccine presentation, etc. from the previously approved plan, and on reported figures which differ from those reported in the WHO/UNICEF Joint Reporting Form in the space provided below.

3.2	Availability of revised request for new vaccine (to be shared with UNICEF Supply Division) for 2006

In case you are changing the presentation of the vaccine, or increasing your request; please indicate below if UNICEF Supply Division has assured the availability of the new quantity/presentation of supply.

Table 4: Estimated number of doses of HepB vaccine (specify for one presentation only): Please repeat this table for any other vaccine presentation requested from

GAVI/The Vaccine Fund

*Please report the same figure as in table 3.

Table 5: Wastage rates and factors

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

Remarks

- Phasing: Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided - Wastage of vaccines: Countries are expected to plan for a maximum of: 50% wastage rate for a lyophilized vaccine in 10 or 20-dose vial; 25% for a liquid vaccine in a10 or 20-dose vial; 10% for any vaccine (either liquid or lyophilized) in 1 or 2-dose vial. - Buffer stock: The buffer stock is recalculated every year as 25% the current vaccine requirement - Anticipated vaccines in stock at start of year 2006: It is calculated by counting the current balance of vaccines in stock, including the balance of buffer stock. Write zero if all vaccines supplied for the current year (including the buffer stock) are expected to be consumed before the start of next year. Countries with very low or no vaccines in stock must provide an explanation of the use of the vaccines. - AD syringes: A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines. - Reconstitution syringes: it applies only for lyophilized vaccines. Write zero for other vaccines. - Safety boxes: A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes

#### 3.3	Confirmed/revised request for injection safety support for the years 2006-2007

Table 6: Estimated supplies for safety of vaccination for the next two years with …… (Use one table for each vaccine BCG, DTP, measles and TT, and number them from 4 to 8)

3.4: BCG

3.5: DTP

3.6: MEAS

3.7: TT

#### If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference.

In accordance with its first application for injection safety funding, Mauritania opted for contributions in kind to further the implementation of its multi-year injection safety plan. AD syringes, dilution syringes and safety boxes were all funded out of the State budget.

# 4. 	Please report on progress since submission of the last Progress Report based on the indicators selected 	by your country in the proposal for GAVI/VF support

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| DTP3 vaccine coverage rates | Increase DTP3 and HepB3 vaccine coverage rates for children aged 0-11 mos to 85% and TT2 vaccine coverage rates for pregnant women to 60% in 2005 | Results obtained in 2005: - BCG: 87% - DTP3: 71% - MEAS: 61% - TT2: 34% - HepB: 42% | Constraints are primarily linked to the late introduction of the HepB vaccine (March 2005) and the obsolete vehicle fleet, as a result of which monitoring and supervision and field visits are irregular and infrequent. | - BCG: 95% - DTP3: 85% - MEAS: 80% - TT2: 70% - HepB3: 85% |

# Checklist

Checklist of completed form:

| Form Requirement: | Completed | Comments |
| --- | --- | --- |
| Date of submission | X |  |
| Reporting Period (consistent with previous calendar year) | X |  |
| Table 1 filled-in | X |  |
| DQA reported on |  | No DQA in 2005 |
| Reported on use of 100,000 US$ | X |  |
| Injection Safety Reported on | X |  |
| FSP Reported on (progress against country FSP indicators) | X |  |
| Table 2 filled-in | X |  |
| New Vaccine Request completed | X |  |
| Revised request for injection safety completed (where applicable) | X |  |
| ICC minutes attached to the report | X |  |
| Government signatures | X |  |
| ICC endorsed | X |  |

6.  	Comments

ICC/RWG comments:

7.	Signatures

For the Government of …MAURITANIA…Mr. SAADNA OULD BAHEIDA……..…………………………………

Signature:	……………………………………………...……………...

Title:	MINISTER OF HEALTH AND SOCIAL AFFAIRS………………………………………….………………….

Date:	………………………………………….………………….

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this report. Signature of endorsement of this document does not imply any financial (or legal) commitment on the part of the partner agency or individual.

Financial accountability forms an integral part of GAVI/The Vaccine Fund monitoring of reporting of country performance.  It is based on the regular government audit requirements as detailed in the Banking form.  The ICC Members confirm that the funds received have been audited and accounted for according to standard government or partner requirements.

| Agency/Organisation | Name/Title | Date Signature | Agency/Organisation | Name/Title | Date Signature |
| --- | --- | --- | --- | --- | --- |
| Ministry of Health and Social Affairs | Dr Mohamed Ould Ely Temoudy: Secretary General |  |  |  |  |
| Ministry of Health and Social Affairs | Dr Abderrahmne Ould Jiddou, Director, Disease Control |  |  |  |  |
| Ministry of Health and Social Affairs | Dr Ishagh Ould Khalef, National EPI Coordinator |  |  |  |  |
| UNICEF | Dr Souleymane Diallo: Representative |  |  |  |  |
| WHO | Dr Pathé Diallo: Representative |  |  |  |  |

~ End ~