Progress Report

Partnering with The Vaccine Fund

to the

Global Alliance for Vaccines and Immunization (GAVI)

and

The Vaccine Fund

by the Government of

COUNTRY:

Date of submission: 12 May 2006 Reporting period: 2005 ( Tick only one ) : Inception report  First annual progress report  Second annual progress report  Third annual progress report  Fourth annual progress report  Fifth annual progress report  Text boxes supplied in this report are meant only to be used as guides. Please feel free to add text beyond the space provided. *Unless otherwise specified, documents may be shared with the GAVI partners and collaborators

# Progress Report Form:  Table of Contents

# Report on progress made during the previous calendar year

  - Immunization Services Support (ISS)

1.1.1	Management of ISS Funds

  - Use of Immunization Services Support

1.1.3	Immunization Data Quality Audit

  - GAVI/Vaccine Fund New and Under-used Vaccines

1.2.1	Receipt of new and under-used vaccines

1.2.2	Major activities

    - Use if GAVI/The Vaccine Fund financial support (US$100,000) for introduction of the new vaccine

1.3		Injection Safety

    - Receipt of injection safety support

    - Progress of transition plan for safe injections and safe management of sharps waste

    - Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

2.  Financial Sustainability

3.  Request for new and under-used vaccine for year… (indicate forthcoming year)

  - Up-dated immunization targets

  - Confirmed/revised request for new vaccine (to be shared with UNICEF Supply Division) for year…

  - Confirmed/revised request for injection safety support for the year…

- Please report on progress since submission of the last Progress Report based on the indicators

selected by your country in the proposal for GAVI/VF support

5.  Checklist

6.  Comments

7.  Signatures

# 1.  	Report on progress made during the previous calendar year (2005)

To be filled in by the country for each type of support received from GAVI/The Vaccine Fund.

## Immunization Services Support (ISS)

#### 1.1.1	Management of ISS Funds

Please describe the mechanism for management of ISS funds, including the role of the Inter-Agency Co-ordinating Committee (ICC).

Please report on any problems that have been encountered involving the use of those funds, such as delay in availability for programme use.

The third tranche and the first reward funds (total USD 1,817,240) were received through WHO in November 2005. Funds were allocated to different activities after consultation with ICC members and budget was endorsed by the ICC.

#### 1.1.2	Use of Immunization Services Support

In the past year, the following major areas of activities have been funded with the GAVI/Vaccine Fund contribution.

Funds received during the reporting year (2005):			974,800 + 842,800= 1,817,240 USD for ISS (3rd tranche and first reward)

Remaining funds (carry over) from the previous year (2004):	273,743 USD from 2004

Table 1 : Use of funds during reported calendar year 2005

| Area of Immunization Services Support | Total amount in US $ | Amount of funds |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | PUBLIC SECTOR |  |  | PRIVATE SECTOR & Other |
|  |  | Central | Region/State/Province | District |  |
| Vaccines |  |  |  |  |  |
| Injection supplies |  |  |  |  |  |
| Personnel |  |  |  |  |  |
| Transportation | 30,000 |  | 10,000 | 20,000 |  |
| Maintenance and overheads | 221,944 | 126,944 | 70,000 | 25,000 |  |
| Training | 185,000 |  | 25,000 | 160,000 |  |
| IEC / social mobilization | 50,000 | 10,000 | 30,000 | 10,000 |  |
| Outreach | 200,000 |  |  | 200,000 |  |
| Supervision |  |  |  |  |  |
| Monitoring and evaluation |  |  |  |  |  |
| Epidemiological surveillance |  |  |  |  |  |
| Vehicles | 357,645 |  | 105,000 | 252,645 |  |
| Cold chain equipment | 59,700 |  |  | 59,700 |  |
| Cold chain operational cost | 20,000 |  | 20,000 |  |  |
| Construction of incinerator | 30,000 |  |  | 30,000 |  |
| Support outreach program | 70,000 |  |  | 70,000 |  |
| Operational cost of polio SNIDs | 31,007 |  |  | 31,007 |  |
| Other (Support to WHO) |  |  |  |  |  |
| Total: | 1,255,296 | 136,944 | 260,000 | 858,352 |  |
| Remaining funds for next year: | 835,687 |  |  |  |  |

*If no information is available because of block grants, please indicate under ‘other’.

Please attach the minutes of the ICC meeting(s) when the allocation of funds was discussed.

Please report on major activities conducted to strengthen immunization, as well as, problems encountered in relation to your multi-year plan.

The remaining funds from 2004 were reallocated for the procurement of 10 solar refrigerators, 22 small tractors to transport vaccines in the remote communities and 7 cars to support supervision and monitoring at Central and State/Division levels. Funds were allocated to mid level managers, basic health staff and cold chain engineers (USD 185,000), which was started in 2005 and will continue in 2006. Funds were also allocated as incentives to the Basic Health Staff (midwives and their supervisors) who carry out the immunization activities. The 2004 backlog incentives were disbursed only in 2005 and therefore funds allocated for 2005 will be provided to Basic Health Staff in 2006. Some funds were allocated for EPI infrastructure (USD 100,000) and will be constructed in 2006. Renovation of cold stores in Mandalay and Magwe is underway. Support for the operational cost for carrying out immunization activities were allocated to townships with hard to reach areas. Cold chain engineers were recruited in 2005 and have been providing for their running cost. Support for cold chain in the form of refurbishing the infrastructure and support for timely transportation of vaccines has been carried out. To support supervision of township and state/division level EPI managers for EPI activities carried out by midwives, 50 motorbikes and 7 cars were procured.

#### Immunization Data Quality Audit (DQA) (If it has been implemented in your country)

Has a plan of action to improve the reporting system based on the recommendations from the DQA been prepared?

If yes, please attach the plan.

YES                              NO

x

## If yes, please attach the plan and report on the degree of its implementation.

DQA was carried out in Myanmar during June/July 2004. The information that Myanmar passed the DQA was received in December 2004. The plan to improve reporting system will be addressed in cMYP EPI Multi-Year Plan (2007-2011).

## Please attach the minutes of the ICC meeting where the plan of action for the DQA was discussed and endorsed by the ICC.

Please list studies conducted regarding EPI issues during the last year (for example, coverage surveys, cold chain assessment, EPI review).

No studies/reviews were conducted during 2005.

## GAVI/Vaccine Fund New & Under-used Vaccines Support

#### 1.2.1	Receipt of new and under-used vaccines during the previous calendar year

Please report on receipt of vaccines provided by GAVI/VF, including problems encountered.

Hepatitis B vaccine was received during 2005. Vaccines; Indicative Delivery Date; Quantity in doses/pcs.; Quantity in vials/ boxes; PO Number / Delivery Order. HepB (6ds vial); 05 Jun-05; 1,720,200; 286,700; 45060197. HepB (6ds vial); 17 Oct-05; 733,260; 122,210; 45059666. HepB (6ds vial); 17 Oct-05; 755,88,; 125,980; 45050969. HepB (6ds vial); 20 Dec-05; 1,720,200; 286,700; 45059666. HepB (6ds vial); 06 Feb-06; 231,060; 38,510; 45050666. HepB (1ds vial); 19 Apr-05; 66,865; 66,865; 45056228. HepB (1ds vial); 14 Sep-05; 66,865; 66,865; 45059665. HepB (1ds vial); 15 Dec-05; 66,865; 66,865; 45059665.

#### 1.2.2	Major activities

Please outline major activities that have been or will be undertaken, in relation to, introduction, phasing-in, service strengthening, etc. and report on problems encountered.

Hepatitis B was introduced in Yangon Division (43 townships, total population under 1 : 151,980) and Mandalay Division (31 townships, total population under 1 : 183,653) in 2003. In 2004 6 more divisions introduced Hepatitis B (total population under 1 : 625,085) and in 2005 the remaining 9 States introduced Hepatitis B (total population under 1 : 368,844). No major problems were encountered.

#### 1.2.3	Use of GAVI/The Vaccine Fund financial support (US$100,000) for the introduction of the new vaccine

Please report on the proportion of 100,000 US$ used, activities undertaken, and problems encountered such as delay in availability of funds for programme use.

2004; 58,600. 2005; 41,400. Total; 100,000. Funds for the introduction of hepatitis B were used for 1) advocacy meeting at national, divisional and township level; 2) production of Hep B training manual, EPI registers and IEC materials; and 3) for training.

## Injection Safety

#### 1.3.1	Receipt of injection safety support

Please report on receipt of injection safety support provided by GAVI/VF, including problems encountered

The following injection safety items were provided : Devices; Indicative Delivery Date; Quantity in doses/pcs.; Quantity in vials/ boxes; PO Number / Delivery Order. New and Under-used Vaccines. AD Syringes; 28 Feb-05; 2,311,200; 23,112; 45055704. AD Syringes; 08 Jun-05; 2,309,400; 23,094; 45058400. Safety Boxes; 15 Jan-05; 25,650; 1,026; 50024064. Safety Boxes; 28 Jun-05; 25,650; 1,026; 45058402. Injection Safety. BCG Syringes (AD); 22 Dec-04; 1,293,800; 12,938; 50023664. AD Syringes; 10 Jan-05; 7,723,200; 77,232; 45054916. Reconstitution Syringes (BCG); 22 Dec-04; 166,700; 1,667; 50023664. Reconstitution Syringes (Measles); 22 Dec-04; 273,400; 2,734; 50023664. Safety Boxes; 03 Jan-05; 105,000; 4,200; 45054919. No problems were encountered.

#### Progress of transition plan for safe injections and safe management of sharps waste.

Please report on the progress based on the indicators chosen by your country in the proposal for GAVI/VF support.

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| No. of townships using only AD syringes for routine EPI | All states (9) in 2005 (AD syringes were introduced together with Hepatitis B) | 100% |  |  |

#### 1.3.3	Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

The following major areas of activities have been funded (specify the amount) with the GAVI/The Vaccine Fund injection safety support in the past year:

No cash contribution was received.

# 2.  	Financial sustainability

Inception Report :			Outline timetable and major steps taken towards improving financial sustainability and the development of a 							financial sustainability plan.

First Annual Report : 	Report progress on steps taken and update timetable for improving financial sustainability

Submit completed financial sustainability plan by given deadline and describe assistance that will be needed

for financial sustainability planning.

Second Annual Progress Report :	Append financial sustainability action plan and describe any progress to date.

Describe indicators selected for monitoring financial sustainability plans and include baseline and current

values for each indicator. In the following table 2, specify the annual proportion of five year of GAVI/VF support for new vaccines that is planned to be spread-out to ten years and co-funded with other sources.

| Table 2.1 : Sources (planned) of financing of new vaccine (Hep B) (specify) |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Proportion of vaccines supported by | Annual proportion of vaccines |  |  |  |  |  |  |  |  |  |
|  | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 |
| Proportion funded by GAVI/VF (%) | 18 | 61 | 100 | 100 | 100 | 82 | 39 |  |  |  |
| Proportion funded by the Government and other sources (%) | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |
| Total funding for Hepatitis B (new vaccine) * |  |  |  |  |  |  |  |  |  |  |
| * Percentage of DTP3 coverage (or measles coverage in case of Yellow Fever) that is target for vaccination with a new and under-used vaccine |  |  |  |  |  |  |  |  |  |  |

Subsequent reports:			Summarize progress made against the FSP strategic plan.  Describe successes, difficulties and how 									challenges encountered were addressed.  Include future planned action steps, their timing and persons 									responsible.

Report current values for indicators selected to monitor progress towards financial sustainability.  Describe 								the reasons for the evolution of these indicators in relation to the baseline and previous year values.

Update the estimates on program costs and financing with a focus on the last year, the current year and the 								next 3 years.  For the last year and current year, update the estimates of expected funding provided in the 								FSP tables with actual funds received since.  For the next 3 years, update any changes in the costing and 									financing projections.  The updates should be reported using the same standardized tables and tools 									used for the development of the FSP (latest versions available on http://www.gaviftf.org under FSP guidelines 								and annexes).

Highlight assistance needed from partners at local, regional and/or global level

The Financial Stability Plan was resubmitted on December 2005. No comments from the reviewers have been received yet. The following indicators were identified : - Increase health sector allocation (6.5% of government budget) - NIP expenditure as % of health budget (1.4%) - Proportion of cost of new vaccine funded by the government (0%) - NIP budget should grow at least the same rate as national health budget - Donor contribution as % of financing gap (100%) - Mean number of years of donor commitment (1 year) - Vaccine wastage decrease by 25% (Current wastage : BCG 77%, DTP 32%, TT 30%, Measles 58%, OPV 45%) Baseline figures for the year 2004 have been put between brackets. The Financial Sustainability Plan was re-submitted in December 2005. No comments from the reviewers have been received yet.

# 3.  	Request for new and under-used vaccines for year 2006 ( indicate forthcoming year )

Section 3 is related to the request for new and under used  vaccines and injection safety for the forthcoming year.

- Up-dated immunization targets

Confirm/update basic data (= surviving infants, DTP3 targets, New vaccination targets) approved with country application:  revised Table 4 of approved

application form.

DTP3 reported figures are expected to be consistent with those reported in the WHO/UNICEF Joint Reporting Forms.  Any changes and/or discrepancies MUST be justified in the space provided (page 10) .  Targets for future years MUST be provided.

| Table 3 : Baseline and annual targets |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of | Baseline and targets |  |  |  |  |  |  |  |  |  |
|  | 2000 | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 |
| DENOMINATORS |  |  |  |  |  |  |  |  |  |  |
| Births | 1352282 | 1379137 | 1407570 | 1436003 | 1465010 | 1494603 | 1525794 | 1556615 | 1588059 | 1620137 |
| Infants’ deaths | 81143 | 82748 | 84454 | 86160 | 87190 | 89676 | 91488 | 93336 | 95221 | 97145 |
| Surviving infants | 1271239 | 1296389 | 1323116 | 1349843 | 1377110 | 1404927 | 1433307 | 1462260 | 1491797 | 1521932 |
| Infants vaccinated with DTP3 * | 945566 | 951768 | 1068782 | 1075535 | 1170544 | 1264434 | 1289976 | 1316034 | 1342618 | 1369739 |
| Infants vaccinated with DTP3: administrative figure reported in the WHO/UNICEF Joint Reporting Form | 894863 | 914545 | 1023186 | 1034459 | 1,124,761 | 1,021,045 | 1289976 | 1316034 | 1342618 | 1369739 |
| NEW VACCINES |  |  |  |  |  |  |  |  |  |  |
| Infants vaccinated with Hep B * (use one row per new vaccine) |  |  |  | 168180 | 535,828 | 863,492 | 1289976 | 1316034 | 1342618 | 1369739 |
| Wastage rate of Hep B** ( new vaccine) |  |  |  | ND | 1.33 | 1.33 | 1.33 | 1.33 | 1.33 | 1.33 |
| INJECTION SAFETY |  |  |  |  |  |  |  |  |  |  |
| Pregnant women vaccinated with TT | 855811 | 904732 | 1000513 | 1049492 | 1,172, 601 | 1,072,816 | 1373215 | 1400954 | 1429253 | 1458124 |
| Infants vaccinated with BCG | 958259 | 961090 | 1063081 | 1065542 | 1,176,308 | 1,072,782 | 1289976 | 1316034 | 1342618 | 1369739 |
| Infants vaccinated with Measles | 913288 | 918088 | 996392 | 1008348 | 1,075,827 | 1,005,079 | 1289976 | 1316034 | 1342618 | 1369739 |

* Indicate actual number of children vaccinated in past years and updated targets

** Indicate actual wastage rate obtained in past years

Please provide justification on changes to baseline, targets, wastage rate, vaccine presentation, etc. from the previously approved plan, and on reported figures which differ from those reported in the WHO/UNICEF Joint Reporting Form in the space provided below.

3.2	Confirmed/Revised request for new vaccine (to be shared with UNICEF Supply Division) for the year 2007 (indicate forthcoming year)

Please indicate that UNICEF Supply Division has assured the availability of the new quantity of supply according to new changes.

Table 4: Estimated number of doses of Hepatitis B vaccine (specify for one presentation only) : (Please repeat this table for any other vaccine presentation requested from

GAVI/The Vaccine Fund

|  |  | Formula | For year 2007 | Remarks |
| --- | --- | --- | --- | --- |
| A | Infants vaccinated / to be vaccinated with 1st dose of Hepatitis B ( new vaccine) |  | 1,316,034 | - Phasing: Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided - Wastage of vaccines: Countries are expected to plan for a maximum of: 50% wastage rate for a lyophilized vaccine in 10 or 20-dose vial; 25% for a liquid vaccine in a 10 or 20-dose vial; 10% for any vaccine (either liquid or lyophilized) in 1 or 2-dose vial. - Buffer stock: The buffer stock for vaccines and AD syringes is set at 25%. This is added to the first stock of doses required to introduce the vaccination in any given geographic area. Write zero under other years. In case of a phased introduction with the buffer stock spread over several years, the formula should read: [ F – number of doses (incl. wastage) received in previous year ] * 0.25. - Anticipated vaccines in stock at start of year 2005: It is calculated by deducting the buffer stock received in previous years from the current balance of vaccines in stock. - AD syringes: A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines. - Reconstitution syringes: it applies only for lyophilized vaccines. Write zero for other vaccines. - Safety boxes: A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes |
| B | Percentage of vaccines requested from The Vaccine Fund taking into consideration the Financial Sustainability Plan | % | 82 |  |
| C | Number of doses per child |  | 3 |  |
| D | Number of doses | A x B/100 x C | 3,237,444 |  |
| E | Estimated wastage factor | (see list in table 3) | 1.33 and 1.05 |  |
| F | Number of doses ( incl. wastage) | A x C x E x B/100 | 4,260,477 |  |
| G | Vaccines buffer stock | F x 0.25 | 1,065,119 |  |
| H | Anticipated vaccines in stock at start of year 2007 |  | 0 |  |
| I | Total vaccine doses requested | F + G - H | 5,325,597 |  |
| J | Number of doses per vial | 6 dose vials for 85% for first dose and 100% of children for 2nd and 3rd dose and 1 dose vials for 15% of children for first dose | 859,272 6-dose vials 169,966 1-dose vials |  |
| K | Number of AD syringes (+ 10% wastage) | ( D + G – H ) x 1.11 | 4,732,819 |  |
| L | Reconstitution syringes (+ 10% wastage) | I / J x 1.11 | 0 |  |
| M | Total of safety boxes (+ 10% of extra need) | ( K + L ) / 100 x 1.11 | 52,061 |  |

Table 5: Wastage rates and factors

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

*Please report the same figure as in table 3.

#### 3.3	Confirmed/revised request for injection safety support for the year 2007 (indicate forthcoming year)

Table 5: Estimated supplies for safety of vaccination for the next two years with BCG (Use one table for each vaccine BCG, DTP, measles and TT, and number them from 4 to 8)

|  |  | Formula | For year 2007 | For year 2008 |
| --- | --- | --- | --- | --- |
| A | Target of children for BCG vaccination | # |  |  |
| B | Number of doses per child | # |  |  |
| C | Number of BCG doses | A x B |  |  |
| D | AD syringes (+10% wastage) | C x 1.11 |  |  |
| E | AD syringes buffer stock | D x 0.25 |  |  |
| F | Total AD syringes | D + E |  |  |
| G | Number of doses per vial | # |  |  |
| H | Vaccine wastage factor 4 | Either 2 or 1.6 |  |  |
| I | Number of reconstitution syringes (+10% wastage) | C x H x 1.11 / G |  |  |
| J | Number of safety boxes (+10% of extra need) | ( F + I ) x 1.11 / 100 |  |  |

#### If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference.

There is no GAVI support for INS in 2007

Table 6: Estimated supplies for safety of vaccination for the next two years with DTP (Use one table for each vaccine BCG, DTP, measles and TT, and number them from 4 to 8)

|  |  | Formula | For year 2007 | For year 2008 |
| --- | --- | --- | --- | --- |
| A | Target of children for DTP vaccination | # |  |  |
| B | Number of doses per child | # |  |  |
| C | Number of DTP doses | A x B |  |  |
| D | AD syringes (+10% wastage) | C x 1.11 |  |  |
| E | AD syringes buffer stock | D x 0.25 |  |  |
| F | Total AD syringes | D + E |  |  |
| G | Number of doses per vial | # |  |  |
| H | Vaccine wastage factor 4 | Either 2 or 1.6 |  |  |
| I | Number of reconstitution syringes (+10% wastage) | C x H x 1.11 / G |  |  |
| J | Number of safety boxes (+10% of extra need) | ( F + I ) x 1.11 / 100 |  |  |

#### If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference.

There is no GAVI support for INS in 2007

Table 7: Estimated supplies for safety of vaccination for the next two years with measles (Use one table for each vaccine BCG, DTP, measles and TT, and number them from 4 to 8)

|  |  | Formula | For year 2007 | For year 2008 |
| --- | --- | --- | --- | --- |
| A | Target of children for measles vaccination | # |  |  |
| B | Number of doses per child (for TT woman) | # |  |  |
| C | Number of measles doses | A x B |  |  |
| D | AD syringes (+10% wastage) | C x 1.11 |  |  |
| E | AD syringes buffer stock | D x 0.25 |  |  |
| F | Total AD syringes | D + E |  |  |
| G | Number of doses per vial | # |  |  |
| H | Vaccine wastage factor 4 | Either 2 or 1.6 |  |  |
| I | Number of reconstitution syringes (+10% wastage) | C x H x 1.11 / G |  |  |
| J | Number of safety boxes (+10% of extra need) | ( F + I ) x 1.11 / 100 |  |  |

#### If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference.

There is no GAVI support for INS in 2007

Table 8: Estimated supplies for safety of vaccination for the next two years with TT (Use one table for each vaccine BCG, DTP, measles and TT, and number them from 4 to 8)

|  |  | Formula | For year 2007 | For year 2008 |
| --- | --- | --- | --- | --- |
| A | Target of pregnant women for TT vaccination | # |  |  |
| B | Number of doses per woman | # |  |  |
| C | Number of TT doses | A x B |  |  |
| D | AD syringes (+10% wastage) | C x 1.11 |  |  |
| E | AD syringes buffer stock | D x 0.25 |  |  |
| F | Total AD syringes | D + E |  |  |
| G | Number of doses per vial | # |  |  |
| H | Vaccine wastage factor 4 | Either 2 or 1.6 |  |  |
| I | Number of reconstitution syringes (+10% wastage) | C x H x 1.11 / G |  |  |
| J | Number of safety boxes (+10% of extra need) | ( F + I ) x 1.11 / 100 |  |  |

#### If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference.

There is no GAVI support for INS in 2007

# 4. 	Please report on progress since submission of the last Progress Report based on the indicators selected 	by your country in the proposal for GAVI/VF support

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| - Number and percentage of townships having an annual micro plan for immunization services presented to central EPI and the ICC Working Group. - Monitor hepatitis B coverage on an annual basis. - Number and percentage of townships having functional cold chain. | - 324 townships - 100 % - 324 | - 100% - 61.5 % for HepB3 of total of surviving infants in all Divisions - 313/324=96% | - Hep B was introduced only in July in 9 additional States and targeted children who had not yet finished DTP3, therefore the coverage is lower than the targeted |  |

# Checklist

Checklist of completed form:

| Form Requirement: | Completed | Comments |
| --- | --- | --- |
| Date of submission | 12 May 2006 |  |
| Reporting Period (consistent with previous calendar year) | 2004 |  |
| Table 1 filled-in | Yes |  |
| DQA reported on | Yes | Submitted in 2004 |
| Reported on use of 100,000 US$ | Yes |  |
| Injection Safety Reported on | Yes |  |
| FSP Reported on (progress against country FSP indicators) | Yes | Submitted in December 2005, no feedback yet |
| Table 2 filled-in | Yes |  |
| New Vaccine Request completed | Yes |  |
| Revised request for injection safety completed (where applicable) | Yes |  |
| ICC minutes attached to the report | Yes |  |
| Government signatures | Yes |  |
| ICC endorsed | Yes |  |

6.  	Comments

ICC comments:

All ICC members endorsed on the Annual Progress Report for 2005, as presented by the National EPI Project Manager. Some ICC members raised a few points to be considered in the future. - Utilization of funds - Sustainability of injection safety and hepatitis B vaccine ICC concerned on the utilization rate of funds. As funds are channelled through WHO, its financial regulations would allow funds to be used within bi-annum budget cycle, i.e., until end of 2007. As GAVI support for the injection safety for routine immunization will continue only to mid 2006, ICC felt a need for an injection safety plan and donor commitment, which called for an urgent discussion. DoH will consider filling the gap of hepatitis B starting from 2008 from the local hepatitis B vaccine plant.

7.	Signatures

For the Government of the Union of Myanmar

Signature:	……………………………………………...……………...

Title:  Dr. Tin Win Maung, Director General, Department of Health

Date:  10 May 2006

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this report. Signature of endorsement of this document does not imply any financial (or legal) commitment on the part of the partner agency or individual.

Financial accountability forms an integral part of GAVI/The Vaccine Fund monitoring of reporting of country performance.  It is based on the regular government audit requirements as detailed in the Banking form.  The ICC Members confirm that the funds received have been audited and accounted for according to standard government or partner requirements.

| Agency/Organisation | Name/Title | Date Signature | Agency/Organisation | Name/Title | Date Signature |
| --- | --- | --- | --- | --- | --- |
| UNICEF | Ms. Elke Wisch, Deputy Representative, UNICEF-Myanmar |  |  |  |  |
| WHO | Professor Dr. Adik Wibowo, WHO Representative, Myanmar |  |  |  |  |
| JICA | Mr. Makoto Yamashita, Deputy Representative, JICA, Myanmar |  |  |  |  |

~ End ~

GAVI will fund the procurement of AD syringes to deliver 2 doses of TT to pregnant women. If the immunization policy of the country includes all Women of Child Bearing Age (WCBA), GAVI/The Vaccine Fund will contribute to a maximum of 2 doses for Pregnant Women (estimated as total births).

The buffer stock for vaccines and AD syringes is set at 25%. This is added to the first stock of doses required to introduce the vaccination in any given geographic area. Write zero for other years.

Only for lyophilized vaccines. Write zero for other vaccines

4 Standard wastage factor will be used for calculation of re-constitution syringes. It will be 2 for BCG, 1.6 for measles and YF.

GAVI will fund the procurement of AD syringes to deliver 2 doses of TT to pregnant women. If the immunization policy of the country includes all Women of Child Bearing Age (WCBA), GAVI/The Vaccine Fund will contribute to a maximum of 2 doses for Pregnant Women (estimated as total births).

The buffer stock for vaccines and AD syringes is set at 25%. This is added to the first stock of doses required to introduce the vaccination in any given geographic area. Write zero for other years.

Only for lyophilized vaccines. Write zero for other vaccines

4 Standard wastage factor will be used for calculation of re-constitution syringes. It will be 2 for BCG, 1.6 for measles and YF.

GAVI will fund the procurement of AD syringes to deliver 2 doses of TT to pregnant women. If the immunization policy of the country includes all Women of Child Bearing Age (WCBA), GAVI/The Vaccine Fund will contribute to a maximum of 2 doses for Pregnant Women (estimated as total births).

The buffer stock for vaccines and AD syringes is set at 25%. This is added to the first stock of doses required to introduce the vaccination in any given geographic area. Write zero for other years.

Only for lyophilized vaccines. Write zero for other vaccines

4 Standard wastage factor will be used for calculation of re-constitution syringes. It will be 2 for BCG, 1.6 for measles and YF.

GAVI will fund the procurement of AD syringes to deliver 2 doses of TT to pregnant women. If the immunization policy of the country includes all Women of Child Bearing Age (WCBA), GAVI/The Vaccine Fund will contribute to a maximum of 2 doses for Pregnant Women (estimated as total births).

The buffer stock for vaccines and AD syringes is set at 25%. This is added to the first stock of doses required to introduce the vaccination in any given geographic area. Write zero for other years.

Only for lyophilized vaccines. Write zero for other vaccines

4 Standard wastage factor will be used for calculation of re-constitution syringes. It will be 2 for BCG, 1.6 for measles and YF.