January 2005

Progress Report

to the

Global Alliance for Vaccines and Immunization (GAVI)

and

The Vaccine Fund

by the Government of

COUNTRY: REPUBLIC OF NIGER

Date of submission: 10 March 2005 Reporting period: 2004 ( Information provided in this report MUST refer to 2004 activities ) ( Tick only one ) : Inception report First annual progress report Second annual progress report Third annual progress report X Fourth annual progress report Fifth annual progress report Text boxes supplied in this report are meant only to be used as guides. Please feel free to add text beyond the space provided. *Unless otherwise specified, documents may be shared with GAVI partners and collaborators

# Progress Report Form:  Table of Contents

# Report on progress made during 2004

  - Immunization Services Support (ISS)

1.1.1	Management of ISS Funds

  - Use of Immunization Services Support

1.1.3	Immunization Data Quality Audit

  - GAVI/Vaccine Fund New and Under-used Vaccines

1.2.1	Receipt of new and under-used vaccines

1.2.2	Major activities

    - Use if GAVI/The Vaccine Fund financial support (US$100,000) for introduction of the new vaccine

1.3	Injection Safety

    - Receipt of injection safety support

    - Progress of transition plan for safe injections and safe management of sharp waste

    - Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

2.  Financial Sustainability

3.  Request for new and under-used vaccine for 2006

  - Up-dated immunization targets

  - Confirmed/revised request for new vaccine (to be shared with UNICEF Supply Division) for year…

  - Confirmed/revised request for injection safety support for the year…

- Report on progress since submission of the last Progress Report based on the indicators

selected by your country in the proposal for GAVI/VF support

5.  Checklist

6.  Comments

7.  Signatures

# 1.  	Report on progress made during the previous calendar year

To be filled in by the country for each type of support received from GAVI/The Vaccine Fund.

## Immunization Services Support (ISS)

#### 1.1.1	Management of ISS Funds

Please describe the mechanism for management of ISS funds, including the role of the Inter-Agency Coordinating Committee (ICC).

Please report on any problems that have been encountered involving the use of those funds, such as delay in availability for program use.

The GAVI funds are managed by the Ministry of Public Health through a bank account. A small committee of that Ministry proposes expenditures to be made to the ICC, which, after approval, orders disbursement. Thus a check is issued with two signatures: - that of the ICC Chairman or, with his authorization, of the financial controller of the Ministry of Health - and the signature of the Chief of the Immunization and Children’s Division. No delay or problem was encountered in receiving and managing these GAVI funds for the year 2004.

#### 1.1.2	Use of Immunization Services Support

During the past year, the following major areas of activities have been funded with the GAVI/Vaccine Fund contribution.

Funds received during the reporting year  _________435,100 USD ______

Remaining funds (carry over) from the previous year  ______ As of 31/12/2003: 239,839 FCFA __________

Table 1: Use of funds during the reporting calendar year  2004

Balance in December 2003	= 239,839,537 CFA

Funds received in 2004	= 227,934,760 CFA

Balance on 31/12/2004	=   76,208,506 CFA

| Area of Immunization Services Support | Total amount in US $ | AMOUNT OF FUNDS |
| --- | --- | --- |
|  |  | PUBLIC SECTOR | PRIVATE SECTOR & Other |
|  |  | Central | Region/State/Province | District |  |
| Vaccines |  |  |  |  |  |
| Injection supplies |  |  |  |  |  |
| Personnel | 35,102.74 | 2,233.39 |  | 32,869.35 |  |
| Supply | 54,769.84 |  | 15,080.96 | 39,688.88 |  |
| Vehicle maintenance | 24,129.91 | 3,722.32 | 1,191.14 | 19,216.45 |  |
| Overheads | 51,319.77 | 9.142.01 |  | 42,177.77 |  |
| Training | 30,995.19 |  |  | 30,995.19 |  |
| IEC / social mobilization | 56,535.46 |  |  | 56,535.46 |  |
| Outreach |  |  |  |  |  |
| Supervision | 130,363.84 |  | 26,494.14 | 102,869.70 |  |
| Monitoring and evaluation | 15,710.56 | 15,710.56 |  |  |  |
| Epidemiological surveillance |  |  |  |  |  |
| Equipment/transport | 171,766.93 | 1,024.32 |  | 170,742.60 |  |
| Other: Vaccinations |  |  |  |  |  |
| Banking commissions | 155.03 | 155.03 |  |  |  |
| Total: | 728,765.66 | 31,987.63 | 42,766.24 | 654,011.80 |  |
| Remaining funds for next year: | 141,836.04 | 141,836.04 | 0 | 0 |  |

* 1 USD = 537.3 CFA francs (average dollar rate in 2004)

If no information is available because overall amounts of aid were paid, please indicate so under “other”.

Please attach the minutes of the ICC meeting(s) when the allocation of funds was discussed.

Please report on major activities conducted to strengthen immunization, as well as, problems encountered in relation to your multi-year plan.

During 2004 most of the vaccination centers organized at least 3 vaccination campaigns in advanced strategy per month and one social mobilization campaign. These activities were supported by decentralized mobile strategy campaigns in certain districts, supervision, supplying of vaccination centers with inputs as well as maintenance and logistics. At the central level, 4 supervisions of the regions were carried out, i.e. one campaign per quarter. Coordinating meetings were organized by the districts, regions and the national level to evaluate activities and take corrective measures. In terms of problems encountered, we note the insufficiency of funds allocated for maintenance of the car/motorcycle fleet, which is continuing to age; the existence of areas not covered by the EPI due to the insufficiency of funds to carry out the decentralized mobile strategy; the insufficiency of human resources in that more than 60% of the health centers are run by a single trained health agent.

#### Immunization Data Quality Audit (DQA) (If it has been implemented in your country)

Has a plan of action to improve the reporting system based on the recommendations from the DQA been prepared?

If yes, please attach the plan.

## YES                              NO

## If yes, please report on the degree of its implementation.

- Training of agents in all the regions in EPI management and in particular on media for collecting EPI data - Reproduction of collection media on GAVI Fund - Effective establishment of media in the field with use scheduled for early January 2005 - Improvement of processing and filing of data at every level

## Please attach the minutes of the ICC meeting where the plan of action for the DQA was discussed and endorsed by the ICC.

Please report on studies conducted regarding EPI issues during 2004 (for example, coverage surveys).

Not applicable

## GAVI/Vaccine Fund New & Under-used Vaccines Support

#### 1.2.1	Receipt of new and under-used vaccines during 2004

Start of vaccinations with the new and under-used vaccine:           MONTH………………..           YEAR……………….

Please report on receipt of vaccines provided by GAVI/VF, including problems encountered.

Niger is still waiting for a reply to its request for support for the introduction of AAV.

#### 1.2.2	Major activities

Please outline major activities that have been or will be undertaken, in relation to, introduction, phasing-in, service strengthening, etc. and report on problems encountered.

- Revitalization of the established strategy - Granting of resources for organizing advanced strategy and mobile decentralized campaigns - Implementation of the action plan for social mobilization for systematic EPI - Training of field agents to manage the EPI

#### 1.2.3	Use of GAVI/The Vaccine Fund financial support (US$100,000) for the introduction of the new vaccine

Please report on the proportion of 100,000 US$ used, activities undertaken, and problems encountered such as delay in availability of funds for program use.

NOT APPLICABLE, No request for the introduction of new vaccines was made by Niger in 2004 and previous years. Consequently, the country has not received funds in this area.

## Injection Safety

#### 1.3.1	Receipt of injection safety support

Please report on receipt of injection safety support provided by GAVI/VF, including problems encountered

File on GAVI support for injection safety accepted. The funds for the year 2004 were paid in kind (AD syringes). We are awaiting supplies for 2005. As regards constraints, the Division is confronted with the problem of supplying the regions by batch: due to the lack of trucks to transport goods, injection supplies are only sent weeks, sometimes months, after delivery of the vaccines. In addition, the districts and health enters have always drawn from systematic EPI stocks to manage epidemics occurring in their entity, which sometimes leads to interruptions in EPI supplies.

#### Progress of transition plan for safe injections and safe management of sharp waste.

Please report on the progress based on the indicators chosen by your country in the proposal for GAVI/VF support.

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| - % of healthcare facilities with safe means of storage, treatment and elimination of wastes | 100% | Use of ADS in safety boxes in 100% of health centers |  |  |
| - Average annual number of accidental injections by healthcare personnel | 50% reduction |  | Evaluation not yet conducted |  |
| - Number of weekly curative injections at the facility level | 50% reduction | Availability of safe means of destruction at most health centers |  |  |
| - % of facilities which have experienced interruptions in single-use and auto-disable syringe stocks during the year. | 0% |  |  |  |

#### 1.3.3	Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

The following major areas of activities have been funded (specify the amount) with the GAVI/The Vaccine Fund injection safety support in the past year:

Yes, Niger did receive this contribution, in kind through the delivery of auto-disable syringes and safety boxes.

# 2.  	Financial sustainability

Initial report:	Briefly describe the timetable and measures undertaken to improve financial sustainability and to elaborate a financial sustainability plan.

First annual report:	Present the progress made in implementing measures undertaken to improve financial sustainability and attach the updated timetable.

Submit the financial sustainability plan by the deadline and describe the assistance necessary for planning of financial sustainability.

Third annual progress report:	Attach the action plan for financial sustainability and describe progress made.

Describe the indicators used to ensure follow-up to the financial sustainability plan and give the base and present values of each indicator.

Subsequent reports:	Summarize progress made under the action plan; include successes, difficulties and responses to challenges encountered.  Describe action planned and the timetable for carrying it out; give the names of the persons in charge for the year in question.

Give the present values of the indicators used to follow progress with a view to financial sustainability; explain the reasons for the evolution of those indicators with respect to the values of the base year and previous years.

Update estimates for financing and costs of the program with particular attention to the previous year, the present year and the next three years.

For the previous and present years, please provide an update of financing estimates which were provided in the tables accompanying the financial sustainability plan by including data on funds actually received to date.  For the next three years, indicate any modification expected in cost and financing forecasts.  All updates should be given using the standard tables used for developing the financial sustainability plan.  (The latest version is available at the Internet site: http://www.gaviftf.org under the heading “guidelines for financial sustainability plans”.

Describe assistance expected from partners at the local, regional and/or global levels.

As regards the financial sustainability plan, it has just been finished and transmitted to the GAVI through the WHO Secretariat.  However, the ICC is preparing a special session for its adoption on 17 March 2005 in Niamey.

As follow-up indicators for the Sustainability Plan, we have:

1.  Share of the health-care budget allocated to the EPI:	Present value = 18.25%

2.  Share of HIPC resources devoted to the EPI:	Present value = 0%

3.  Share of local authority expenditures in total EPI expenditures:	Present value unavailable

4.  Share of community expenditures in total EPI expenditures:	Present value unavailable

5.  Share of external partner expenditures in total EPI expenditures:	Present value = 52%

6.  Antigen wastage rate (2003 values: BCG =- 34.4%; DTC = 9.7%; OPV  = 20.6%; VAR = 27.4%; AVV = 15%; VAT = 32.4%)

7.  Wastage rate between DTC1 and DTC3   Present value = 18%

# 3.  	Request for new and under-used vaccines for year … (indicate next year)

Section 3 is related to the request for new and under used vaccines and injection safety for the next year.

- Up-dated immunization targets

Confirm/update basic data (= surviving infants, objectives for DTC3, new objectives in the area of vaccination) approved after consideration in the country proposal: revised Table 4 of the approved request.

The figures for DTC3 must correspond to those given in the joint WHO/UNICEF report forms.  Any change or discrepancy MUST be justified in the box provided for that purpose (page 12).  Objectives for future years MUST be indicated.

Table 2: Base data and annual objectives

| Number of | Base data and objectives |
| --- | --- |
|  | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 |
| DENOMINATORS |  |  |  |  |  |  |  |
| Births | 562,548 | 579,987 | 597,966 | 616,498 | 633,977 | 653,630 | 673,893 |
| Infant deaths | 69,237 | 71,383 | 73,596 | 75,877 | 77,979 | 80,397 | 82,889 |
| Surviving infants | 493,311 | 508,604 | 524,370 | 540,622 | 555,998 | 573,234 | 591,004 |
| Infants receiving three doses of DTC* |  |  |  |  |  |  |  |
| Infants receiving three doses of DTC: figure given in the joint WHO/UNICEF reporting form | 168,868 | 120,835 | 270,117 | 333,704 | 389,199 | - | - |
| NEW VACCINES |  |  |  |  |  |  |  |
| Infants vaccinated with DTC-HepB-Hib | - | - | - | - | - | 458,587 | 502,353 |
| Wastage rate of …………. (new vaccine) | - | - | - | - | - |  |  |
| INJECTION SAFETY |  |  |  |  |  |  |  |
| Pregnant women vaccinated with TT | 246,690 | 224,465 | 238,730 | 263,521 | 380,386 | 424,860 | 471,725 |
| Infants vaccinated with BCG | 268,330 | 293,682 | 383,776 | 442,693 | 475,483 | 522,904 | 539,114 |
| Infants vaccinated against measles | 285,948 | 266,794 | 333,695 | 397,859 | 416,999 | 458,587 | 502,354 |

* Indicate the exact number of children vaccinated during past years and updated objectives.

** Indicate the exact wastage rate recorded during the past years.

Please provide justification on changes to baseline, targets, wastage rate, vaccine presentation, etc. from the previously approved plan, and on reported figures which differ from those reported in the WHO/UNICEF Joint Reporting Form in the space provided below.

The denominators have changed starting in 2001 following the adoption by the government of the Republic of Niger of the results of the last general population census conducted in 2001. In view of the substantial results achieved in the area of vaccination coverage, the objectives of the 2001-2006 strategic plan were revised upward. As for the wastage rates, the data compiled give us the wastage by antigen and by district, but we record between 10 and 15% of erroneous data. Actors in the field attach less importance to the movement of vaccines, but even when they attach adequate importance to it, they have not completely mastered the principle.

3.2	Availability of revised request for new vaccine (to be shared with UNICEF Supply Division) for 2006

In case you are changing the presentation of the vaccine, or increasing your request; please indicate below if UNICEF Supply Division has assured the availability of the new quantity/presentation of supply.

Table 3: Estimated number of PENTAVALENT vaccine doses (DTC-HepB-Hib) (for a single packaging) (please prepare a table for each packaging requested from GAVI or Fund)

|  |  | Formula | For year 2006 | Comments Scheduling: Please adjust estimates of the number of children to receive the new vaccine if a staggered introduction is envisaged. If the objectives for hep B3 and Hib3are different from those for DTC3, indicate the reasons. Wastage of Vaccines: The country will aim at a maximum rate of 25% for the first year and will adopt a plan for gradual reduction to 15% by the third year. No maximum limit has been set for yellow fever vaccine in multi-dose vials. Buffer stock: The buffer stock for vaccines and auto-disable syringes has been set at 25%. It is added to the first stock of doses required to introduce vaccination into a given geographic area. Indicate zero for other years. In the case of staggered introduction, with the buffer stock spread out over several years, the formula is the following: [F – number of doses (including wastage) received the previous year] * 0.25. Vaccine stock anticipated for beginning of year …: Calculated by subtracting the buffer stock received in previous years from the number of vaccines in stock. Auto-disable syringes: A wastage factor of 1.11 is applied to the total number of vaccines requested from the Fund, excluding wastage of vaccines. Syringes for reconstitution: Only for freeze-dried vaccines. Indicate zero for other vaccines. Safety boxes: a multiplier of 1.11 is applied to take into account regions where a safety box will be used for less than 100 syringes. |
| --- | --- | --- | --- | --- |
| A | Number of children to receive the new vaccine | Pop 0-11 months X 80% | 458,587 |  |
| B | Percentage of vaccines requested from the Global Vaccine Fund, taking into account the Financial Sustainability Plan | % | 100 |  |
| C | Number of doses per child |  | 3 |  |
| D | Number of doses | A x B/100 x C | 1,375,761 |  |
| E | Estimated wastage factor | (See list Table 3) | 1.33 |  |
| F | Number of doses (including wastage) | A x C x B/100 | 1,829,762 |  |
| G | Vaccine buffer stock | F x 0.25 | 457,440 |  |
| H | Vaccine stock anticipated for beginning of year … |  | 0 |  |
| I | Total doses of vaccine requested | F + G – H | 2,287,202 |  |
| J | Number of doses per vial |  | 10 |  |
| K | Number of auto-disable syringes (+10% wastage) | (D + G – H) x 1.11 | 2,034,853 |  |
| L | Syringes for reconstitution (+10% wastage) | I/J x 1.11 | 0 |  |
| M | Total safety boxes (+10% of needs) | (K + L) / 100 x 1.11 | 22,586 |  |

Table 3: Wastage rates and factors

| Vaccine wastage rates | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent factors | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

* Please indicate the same figure as in Table 1.

3.3	Revised request for support under injection safety for the year 2005 and 2006 (indicate the next year)

Table 4: Estimated supplies for vaccination safety for the next two years with BCG

|  |  | Formula | For year 2005 | For year 2006 |
| --- | --- | --- | --- | --- |
| A | Number of children to be vaccinated against BCG | # | 412,085 | 522,904 |
| B | Number of doses per child | 1 | 1 | 1 |
| C | Number of doses of BCG | A x B | 412,085 | 522,904 |
| D | Auto-disable syringes (+10% wastage) | C x 1.11 | 457,414 | 580,423 |
| E | Buffer stock of auto-disable syringes | D x 0.25 | 114,354 | 0 |
| F | Total of auto-disable syringes | D + E | 571,768 | 580,423 |
| G | Number of doses per vial | 20 | 20 | 20 |
| H | Vaccine wastage factor | 2 | 2 | 2.00 |
| I | Number of syringes for reconstitution (+10% wastage) | C x H x 1.11 / G | 9,148 | 58,042 |
| J | Number of safety boxes (+10% needs) | (F + I) x 1.11 / 100 | 6,448 | 7,086 |

Table 5: Estimated supplies for vaccination safety of the next two years with DTC for 2005 and the Pentavalent for 2006.

|  |  | Formula | For year 2005 | For year 2006 (PENTAVALENT) |
| --- | --- | --- | --- | --- |
| A | Number of children to be vaccinated against DTC | # | 333,599 | 458,587 |
| B | Number of doses per child | 3 | 3 | 3 |
| C | Number of doses of DTC | A x B x H | 1,000,797 | 1,375,761 |
| D | Auto-disable syringes (+10% wastage) | C x 1.11 | 1,110,885 | 1,527,095 |
| E | Buffer stock of auto-disable syringes | D x 0.25 | 277,721 | 381,773 |
| F | Total of auto-disable syringes | D + E | 1,388,606 | 1,908,868 |
| G | Number of doses per vial | 10 | 10 | 10 |
| H | Vaccine wastage factor | 1.33 | 1.33 | 1.33 |
| I | Number of syringes for reconstitution (+10% wastage) | C x H x 1.11 / G | 0 | 0 |
| J | Number of safety boxes (+10% needs) | (F + I) x 1.11 / 100 | 15,414 | 21,188 |

Table 6: Estimated supplies for vaccination safety for the next two years with Measles

|  |  | Formula | For year 2005 | For year 2006 |
| --- | --- | --- | --- | --- |
| A | Number of children to be vaccinated against MEASLES | # | 416,998 | 458,587 |
| B | Number of doses per child | 1 | 1 | 1 |
| C | Number of doses of Measles | A x B | 416,998 | 458,587 |
| D | Auto-disable syringes (+10% wastage) | C x 1.11 | 462,868 | 509,032 |
| E | Buffer stock of auto-disable syringes | D x 0.25 | 115,717 | 0 |
| F | Total of auto-disable syringes | D + E | 578,585 | 509,032 |
| G | Number of doses per vial | 20 | 20 | 20 |
| H | Vaccine wastage factor | 1.33 | 1,33 | 1,33 |
| I | Number of syringes for reconstitution (+10% wastage) | C x H x 1.11 / G | 30,781 | 6,770 |
| J | Number of safety boxes (+10% needs) | (F + I) x 1.11 / 100 | 6,764 | 5,725 |

Table 7: Estimated supplies for vaccination safety for the next two years with TT

|  |  | Formula | For year 2005 | For year 2006 (PENTAVALENT) |
| --- | --- | --- | --- | --- |
| A | Number of children to be vaccinated against TETANUS | # | 380,386 | 424,860 |
| B | Number of doses per pregnant woman | 2 | 2 | 2 |
| C | Number of doses of TT | A x B | 760,772 | 849,720 |
| D | Auto-disable syringes (+10% wastage) | C x 1.11 | 844,457 | 943,189 |
| E | Buffer stock of auto-disable syringes | D x 0.25 | 211,114 | 0 |
| F | Total of auto-disable syringes | D + E | 1,055,571 | 943,189 |
| G | Number of doses per vial | 10 | 10 | 10 |
| H | Vaccine wastage factor | 1.33 | 1.33 | 1.33 |
| I | Number of syringes for reconstitution (+10% wastage) | C x H x 1.11 / G | 0 | 0 |
| J | Number of safety boxes (+10% needs) | (F + I) x 1.11 / 100 | 11,717 | 10,469 |

If the quantity indicated differs from the one indicated in the GAVI letter of approval, please indicate why.

Performance recorded by the routine EPI for  the national plan in 2003 led to a revision of the coverage objectives set by the EPI 2002-2006 strategic plan.  Thus, aside from TT, the targets for all the other antigens were revised upward for the years 2004, 2005 and 2006.

Table 6 [sic]: Estimated supplies for vaccination safety for the next two years with Yellow Fever

|  |  | Formula | For year 2005 | For year 2006 (PENTAVALENT) |
| --- | --- | --- | --- | --- |
| A | Number of children to be vaccinated against YELLOW FEVER | # | 416,998 | 458,587 |
| B | Number of doses per child | 1 | 1 | 1 |
| C | Number of doses of Anti-amaril | A x B | 416,998 | 458,587 |
| D | Auto-disable syringes (+10% wastage) | C x 1.11 | 462,868 | 509,032 |
| E | Buffer stock of auto-disable syringes | D x 0.25 | 115,717 | 0 |
| F | Total of auto-disable syringes | D + E | 578,585 | 509,032 |
| G | Number of doses per vial | 20 | 20 | 20 |
| H | Vaccine wastage factor | 1.33 | 1.33 | 1.33 |
| I | Number of syringes for reconstitution (+10% wastage) | C x H x 1.11 / G | 30,781 | 6,770 |
| J | Number of safety boxes (+10% needs) | (F + I) x 1.11 / 100 | 6,764 | 5,725 |

# 4. 	Please report on progress since submission of the last Progress Report based on the indicators selected 	by your country in the proposal for GAVI/VF support

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| - DTC P3 Vaccine coverage | 55% | 62% (Year 2004) | - Management of epidemics, | 70% |
|  |  |  | - Shortage of staff, |  |
| - VAT2 + (FE) Coverage | 55% | 43% (Year 2004) | - Polio, measles campaigns | 60% |
|  |  |  | - Aging car/motorcycle fleet |  |
| - Dropout rate DTC | 20% | 18% (Year 2004) | - Difficult access due to season | 15% |

# Checklist

Checklist of completed form:

| Form Requirement: | Completed | Comments |
| --- | --- | --- |
| Date of submission | 30 March 2005 |  |
| Reporting Period (consistent with previous calendar year) | 2004 |  |
| Table 1 filled-in | YES |  |
| DQA reported on | NO |  |
| Reported on use of 100,000 US$ | N/A |  |
| Injection Safety Reported on | NO |  |
| FSP Reported on (progress against country FSP indicators) | YES | The plan was prepared and transmitted |
| Table 2 filled-in | YES | Data provided starting with 2001 |
| New Vaccine Request completed | YES | Introduction of PENTAVALENT starting 2006 |
| Revised request for injection safety completed (where applicable) |  |  |
| ICC minutes attached to the report | YES |  |
| Government signatures | YES |  |
| ICC endorsed | YES |  |

6.  	Comments

ICC/RWG comments:

7.	Signatures

For the Government of the Republic of Niger,

Signature:[signature] [circular stamp reading: “Republic of Niger - Ministry of Public Health - The Minister”]

Title:		Minister of Public Health and of the Fight Against Endemics

Date:	13 / 05 / 05

We, the undersigned members of the Inter-Agency Coordinating Committee, endorse this report. Signature of endorsement of this document does not imply any financial (or legal) commitment on the part of the partner agency or individual.

Financial accountability forms an integral part of GAVI/The Vaccine Fund monitoring of reporting of country performance.  It is based on the regular government audit requirements as detailed in the Banking form.  The ICC Members confirm that the funds received have been audited and accounted for according to standard government or partner requirements.

| Agency/Organization | Name/Title | Date Signature | Agency/Organization | Name/Title | Date Signature |
| --- | --- | --- | --- | --- | --- |
| WHO | Representative | 11 APR 2005 [signature][stamp] | RED CROSS | President | 10/5/2005 [signature][stamp] |
| UNICEF | Representative | 4 MAY 2005 [signature][stamp] | ROTARY INT. | President | 10/5/2005 [signature][stamp] |
| HKI | Representative | [signature][stamp] 09/05/2005 | JICA | Representative |  |

~ End ~

Action Plan for Implementation of the Recommendations of the DQA

National and Regional Level.  Niger 2003.

| Recommendations | Activities carried out | Responsible | Deadline |
| --- | --- | --- | --- |
| 1 – Inform healthcare actors at all levels (health center to district and national level) about reporting data on secondary effects of vaccines (AEFI) | Information activities are conducted by agents on injection safety and AEFI at vaccination sessions, meetings and inspections. | DIE, DRSP and District | 2004 |
| 2 – Standardize the calculation of the value of denominators used at the district and national levels taking into account the WHO definition (number of surviving children) | Target population data come from the results of the last 2001 census and are updated, denominators are calculated based on the WHO definition (surviving children) | DIE | January 2004 |
| 3 – Harmonize the value of denominators used at the district and national levels | Strict application of denominators communicated by the national level to the district and CSI | DS, CSI | 2004 |
| 4 – At the end of each period, determine the proportion of children vaccinated by type of strategy | Action already underway | DIE | 2004 |
| 5 – Display the diagrams and other tables for follow-up of vaccination coverage, vaccine dropout rates and completeness of reports | Action already underway | DIE | 2004 |
| 6 – Establish a written procedure for processing late reports and saving computer data | Installation of software at the region and district level to process and save statistical data and written guidelines for transmission of reports | DIE | 2004 |
| 7 – Standardize formats of monthly reports at the district level | New data collection media (cards, registers) have been printed and provided to the vaccination centers | DIE | July 2004 |

Action Plan for Implementation of the Recommendations of the DQA

Integrated Health Center (CSI) Level.  Niger 2003.

| Recommendations | Activities carried out | Responsible | Deadline |
| --- | --- | --- | --- |
| 1 – Inform healthcare actors at all levels of the vaccination timetable set by the WHO (in number of weeks, not months) | Information meetings are conducted by agents on the vaccination timetable at vaccination sessions, neighborhood meetings and inspections. | ECD | 2004 |
| 2 – Individualize the objectives of the Health Centers based on the specific features of each entity and involve the agents concerned in determining those objectives | Specific annual micro-plans per health center were prepared at the beginning of the year and implemented in the course of the year | CSI | 2004 |
| 3 – Establish a collection system for new births in the community | In cooperation with secondary agents of civil status, the vaccination registers are periodically updated | CSI | 2004 |
| 4 – Prepare and display diagrams or tables of vaccination coverage for the current year | Display of control tables per antigen | ECD | 2004 |
| 5 – Prepare a map of the health area of the health center including the types of strategy | In certain health centers topographic strategy maps have been determined (advanced, mobile) | ECD, DIE | 2004 |
| 6 – Set up a mechanism for identifying and finding those “lost sight of” | The system has already been applied with the establishment of vaccination registers. Follow-up takes place during inspections. | ECD, DIE | 2004 |
| 7 – In addition to social mobilization, conduct effective information activities with the community to improve the coverage rates | Activities conducted at meetings with administrative, customary, religious authorities in the form of arguing in favor of vaccination | DIE | 2004 |
| 8 – Establish card files or a stock register of vaccines and systematically record therein all movements of stocks | Vaccine management registers have been printed and provided to the districts and health centers | DIE | First quarter 2004 |
| 9 – Establish monitoring of stocks by batch number and expiration dates | The vaccine management registers take this concern into account | DIE | First quarter 2004 |
| 10 – Establish card files or a follow-up register of auto-disable syringe stocks | The same vaccine management registers are used to monitor AD syringes and safety boxes | DIE | First quarter 2004 |
| 11 – Monitor wasted vaccine doses (broken vials, expired or discarded doses) | The vaccine management registers take this concern into account | DIE | First quarter 2004 |
| 12 – Improve timeliness of reporting | Annual on-time submission of EPI reports for 2004 is 67% | CSI, ECD | 2004 |
| 13 – Establish a system of collection and transmission to districts of data on secondary effects of vaccines | The collection medium (monthly report) has been revised to take into account monitoring of AEFI | DIE | First quarter 2004 |
| 14 – Improve document filing practices | All media for data collection have been designed in the form of a notebook or register in order to improve filing. | ECD | First quarter 2004 |
| 15 – Pay particular attention when re-transcribing data of “session sheets” | Verification at the district, regional and central level of consistency of figures (doses available, doses used, doses administered and wastage per antigen) | CSI, ECD | 2004 |
| 16 – Establish a system of reporting for “outside age group” [“hors tranche”] vaccinations | The monthly report takes into account the doses administered outside the age group | ECD, CSI | 2004 |
| 17 – Improve safety conditions of the use and destruction of used syringes | Establishment of the National Strategic Plan on injection safety and popularization of national guidelines on management of waste and IS | CSI, ECD, DIE | 2004 |
| 18 – Regularly supply Health Centers with safety boxes | Quarterly supply of regions according to the LOT system | CSI, ECD, DIE | quarterly |

Action Plan for Implementation of the Recommendations of the DQA

District Level.  Niger 2003.

| Recommendations | Activities carried out | Responsible | Deadline |
| --- | --- | --- | --- |
| 1 – Establish and systematically display all diagrams or tables of vaccination coverage for the current year | Vaccination coverage diagrams have been prepared and displayed in all districts and [word(s) missing] | ECD | 2004 |
| 2 – Set up a system to monitor the completeness and timeliness of monthly reports from the health centers (CSI) | Completeness and timeliness of monthly reports by the health centers is regularly monitored by the ECD of the districts and the regional coordinator for immunizations | DIE | 2004 |
| 3 – Include vaccine dropout rates in monitoring tables | The diagrams prepared take monitoring of dropout rates into account | ECD | 2004 |
| 4 – Establish a systematic format of regular (monthly) feedback from the district to the health centers | Feedback to agents of the health centers, after each inspection, is given to the district heads according to a list of recommendations | ECD | 2004 (during inspections) |
| 5 – Monitor wastage rates of vaccines at the health center level | Vaccine management registers existing at the level of each health center take this concern into account | CSI, ECD | 2004 |
| 6 – Improve the content and procedure of supervision visits to health centers | The EPI inspection program exists and is used during integrated supervision visits to the ECD | ECD | 2004 |
| 7 – Establish a system of follow-up and reporting of individual cases of undesirable effects of vaccines from the district level to the national level | The data collection medium (monthly report) has been revised to take into account monitoring of AEFI cases; a guide has been prepared on how to deal with any case of AEFI | DIE | 2004 |
| 8 – Computerize processing of reports at the district level by using the computer format available to capture vaccination data. | Installation of management software, training of agents to use the new statistical data base on vaccination | DIE | September 2004 |

| 9 – Write a procedure for saving computer data | This concern was taken into account when training agents to use the new data base | DIE | September 2004 |
| --- | --- | --- | --- |
| 10 – Save computer data to diskette | This concern was taken into account when training agents to use the new data base | DIE | September 2004 |
| 11 – Improve follow-up of receipt of reports from health centers and ensure that they are signed and dated at the district level | All reports coming from the health centers and DS are signed and dated, and this is checked during supervision | ECD, DIE | 2004 |
| 12 – Establish a reliable system for processing late reports | Written guidelines have been prepared for agents to ensure that reports are received by their deadlines, a reminder is sent during supervisions | ECD | 2004 |
| 13 – Display the dates of creation, printing or saving of computer files | All data bases include dates of creation and printing at every level | ECD | 2004 |
| 14 – Improve the system of filing documents | Review of the data collection media for better filing (registers and notebooks) | ECD | 2004 |
| 15 – Standardize session sheets of health centers visited | The new sheets have been printed and provided to vaccination centers | DIE | 2nd quarter 2004 |
| 16 – Systematically record all movements of vaccine stocks in the register | The registers have been printed and provided to the vaccination centers | DIE | 2nd quarter 2004 |
| 17 – Establish a system for follow-up of vaccine stocks by batch number and expiry date | The registers printed and distributed take this concern into account | DIE | 2nd quarter 2004 |
| 18 – Ensure follow-up of damaged vaccine doses (broken vials, expired, …) | The registers printed and distributed take this concern into account | DIE | 2nd quarter 2004 |
| 19 – Establish a register for follow-up of the syringe stock | The registers printed and distributed take this concern into account | DIE | 2nd quarter 2004 |

Plan to implement the Recommendations of the Data Quality Audit (DQA)

REPUBLIC OF NIGER

-----------

[coat of arms]

MINISTRY OF PUBLIC HEALTH

AND THE FIGHT AGAINST ENDEMICS

-----------

CHILD IMMUNIZATION DIVISION

***************************

Report of the Meeting of the Inter-Agency Coordinating

Committee (ICC)

of 24/06/2004

June 2004

On 24 June 2004 at 9 a.m. in the meeting room of the Ministry of Public Health and the Fight against Endemics, the meeting of the Inter-Agency Coordinating Committee was held under the chairmanship of the Minister of Public Health.  Present were:

MINISTRY OF PUBLIC HEALTH:

Mr. Zouma Salifou: SG/MSP/LCE

Dr. Barkiré Arouna: DIE/MSP/LCE

Mrs. Diana Raklatou CT/MSP/LCE

FRENCH ASSISTANCE:

Dr J.P. Louboutin Croc: French Assistant, CT/SG/MSP

UNICEF:

Mr. Abdou Karimou Adjibadé, Representative

Dr. Isselmou Ould Boukhary, Section Chief Health/Nutrition

Dr. Maoudé Hamissou, Administrator Health/EPI/NVD

Dr. Faoinet Yattara

WHO:

Dr. René Z. OODDY, Representative

Dr. José Bley, Team Leader, EPI/WHO

Dr. Ambrosio Disadidi, Monitoring Focal Point

Dr. Christophe Nsanzabaganwa, EPI Focal Point

Mr. Harou Moussa, Logistics

Dr. Ibrahima Kane, ICP/WHO, Abidjan

Mr. Imrahima Léye, Social Mobilization Focal Point, rapporteur

HKI:

Mrs. Madoul

ROTARY INTERNATIONAL:

Mr. Gaston Kaba

RED CROSS:

Dr. Moungo Yahouza

BELGIAN TECHNICAL ASSISTANCE:

Dr. Alaf I. Aly, CTB

The Minister of Public Health called the meeting to order and introduced the agenda which contained the following items:

- Stocktaking of Vaccination Days against poliomyelitis from February to March 2004 and preparations for future National Vaccination Days (NVDs).

- Measles campaign.

- Situation of monitoring.

- Other business: cooperation with the private sector under the systematic EPI.

1.  Stocktaking of Vaccination Days against poliomyelitis from February to March 2004 and preparations for future NVDs

The members of the ICC listened with interest to the presentation by Dr. Bley of the results of the NVDs from February to April 2004.  The presentation indicated that the trend was upward.  Thus, in February 3,045,197 children were vaccinated; in March 3,213,876; and in April 3,227,718.  Nevertheless, some regions had shown a decline in performance in the third passage: those regions were: Dosso, Tahoua, Tillabéri and Niamey.  This could be related to population movement during that period.  With the appearance of the first rains, certain populations returned to the countryside.  [added in handwriting: “not in April”]

There was a reduction in the number of cases of rejection by 77% in the April passage, which constitutes progress over previous passages.

In addition, the problem of the Camel Neck and Head (Agadez region) was presented with children who were missed due to insecurity, difficult access and mobility of the nomads.  In the same vein, the problems of the Northern Diffa axis and Lake Chad were also stressed.  These situations deserved that thought be given to special strategies.

2.  Measles Campaign

The plan for the measles campaign was presented by Dr. Barkiré Arouna.  In this regard, the objectives and strategies were as follows:

Objectives:

- Reduce mortality and morbidity from measles

- Vaccinate 90% of target children from 9 months to 14 years of age against measles

- Ensure injection safety and proper disposal of waste

- Inform 90% of parents of the importance and the role of systematic vaccination and the vaccination campaign against measles

Basic strategies:

- Vaccination at a fixed location within a radius of 0 – 5 km

- Advanced teams in a radius of 5 – 15 km

- Mobile teams beyond 15 km

- Special teams for vaccination at secondary fixed locations in schools and healthcare training facilities, markets, border crossing posts, etc.

Supplementary strategies:

- Communication, social mobilization

- Systematic vaccination

- Enhanced monitoring

The measles campaign in 2004 concerned all regions except Diffa and Agadez, which were scheduled for 2005.

The measles campaign in December (13 to 22 December) would be conducted in synchronization with certain countries of the sub-region.

The total budget for the measles campaigns was USD 4,999,458, of which 2,976,588 was for 2004 and 2,022,900 for 2005 (the 2005 budget took into account the strengthening of the systematic EPI with USD 145,596 for the measles campaign).

The target population was estimated at 5,128,821 for 2004 and 325,281 for 2005.

With regard to human resources, 5,400 vaccinators were planned, as well as 4,370 auxiliaries, 960 supervisors, 6 international consultants, 15 national consultants and 16 national supervisors.

Coordination would be provided at the central level by the ICC and at the regional and sub-regional levels by the epidemic management committees (COGEPI).

Steps would be taken to ensure vaccination safety through quality vaccines and injection materials, but also through the proper destruction of wastes.

3.  Epidemiological situation of AFP [acute flaccid paralysis?]

The epidemiological situation for the period from 1 January to 22 June 2004 was presented by Dr. Disadidi.

From that presentation it was apparent that:

- for the first indicator, the non-polio AFP rate, all regions achieved the objective except Niamey and Tahoua;

- for the second indicator, sampling of adequate stools within 14 days, the regions of Agadez, Maradi, Tellagéri and Niamey had not achieved the objectives.

All totaled, 19 out of 42 districts had satisfied those two indicators; sustained efforts would be needed to improve performance.

The case of savage poliovirus:

- In Niger: the number of reported cases of savage poliovirus in Niger was 18 as of 22 June 2004.  It was to be noted that we were in the period of low transmission.

- In Africa: the number of reported cases during the period was: Niger – 18; Burkina Faso – 3; Chad – 7; Côte d’Ivoire – 8; Benin – 5; Nigeria – 197; Sudan – 1 case.

4.  Discussions:

Before giving the floor to participants, the Minister of Public Health and the Fight against Endemics recalled Niger’s commitment to stop the circulation of SPV in late December 2004.  He had reiterated that commitment at the last World Health Assembly and had called upon partners to support that commitment so that together we should all achieve the objective of stopping the circulation of SPV in Niger in December 2004.

The discussions dealt mainly with the NVDs.  The following main points were mentioned:

Despite genuine commitment by the Government, authorities and partners, had it not been possible to vaccinate all children.  There was also the absence of control of the target population and the need to revise micro-planning to identify all the pockets and areas of difficult access.  The cold chain was also a matter of concern, in view of the obsolescence and insufficiency of vaccine carriers.  The training of vaccinators and supervisors also had problems in terms of quality.  In addition, there was the intense circulation of SPV in Nigeria, an adjacent country where it was highly endemic.

There were a number of shortcomings in organization the result of which was that some houses or hamlets had been skipped by vaccinators who were not familiar with the environment in which they were working.  Sometimes vaccinators were chosen on the intervention of local authorities, without objective criteria, and this affected the performance of teams and the quality of vaccination.

The constant fact was that the political will existed, but the technical aspect needed to be reviewed, i.e. recruitment and training of vaccinators, supervision, organization of NVDs, the cold chain, problems with maps, and the target population.

In addition, participation of the private sector, economic operators, was mentioned.  In this regard the experiences of some countries were cited as examples.

5.  Main decisions

NVDs:

The dates of the forthcoming NVDs had been set from 3 to 9 September 2004;

The NVD organizing committees and the other subcommittees had to begin preparatory activities immediately with a view to proper organization of the NVDs;

Micro-planning had to be reviewed to identify all the pockets and problems;

The target population had to be readjusted with regard to births (encourage registration of births in the villages);

The heads of the integrated health centers (CSI) needed support in mapping their areas;

Expansion to other partners (French Assistance, Parliament, Scouts, Army, police, teachers, students, etc.) must take place at every level, which would allow for diversifying actors and capitalizing all existing resources;

The involvement of economic actors and the private sector in general was necessary; the national organizing committee must conduct discussions to that end;

The Ministry of Health would prepare a note on local recruitment of vaccinators for the DRSP [Regional Directorates of Public Health?] and DDSP [Department Directorates of Public Health?];

The Ministry of Health would bring the matter to the Ministry of the Interior to gain its support in the selection and recruitment of vaccinators, according to set criteria;

The execution of the exploratory mission in the area of the Camel Neck and Head would take place in July 2004;

Steps would have to be taken with the partners as soon as possible to resolve the problem of the cold chain, given that the situation is already well-know.

Measles:

Instructions had already been given to the DRSP and DDSP to conduct canvassing at the regional level and contact existing industrial units able to destroy wastes.  To that end a mechanism should be set up to collect and dispose of waste.

Monitoring:

Monitoring was to be strengthened, in particular at the level of low-performing regions such as Niamey and Tillabéri; the Ministry of Public Health would make sure that there was adequate follow-up.

Cooperation with the private sector:

The areas of intervention for the private sector under the systematic EPI would have to be determined, as well as the framework for cooperation.

In closing the meeting, the Minister of Public Health and the Fight against Endemics reiterated his appeal to all that together we should put an end to the circulation of the savage poliovirus in Niger.

The meeting was adjourned at 10:57 a.m.

REPUBLIC OF NIGER

-----------

[coat of arms]

MINISTRY OF PUBLIC HEALTH

AND THE FIGHT AGAINST ENDEMICS

-----------

CHILD IMMUNIZATION DIVISION

***************************

Report of the Meeting of the Inter-Agency Coordinating

Committee (ICC)

of 14/09/2004

September 2004

On 14 September 2004 at 10 a.m. in the meeting room of the Ministry of Public Health and the Fight against Endemics, the meeting of the Inter-Agency Coordinating Committee (ICC) was held under the chairmanship of the Secretary General of the Ministry of Public Health and the Fight against Endemics.  Present at the meeting were:

MINISTRY OF PUBLIC HEALTH:

Mr. Zouma Salifou: SG/MSP/LCE

Dr. Harouna Yakouba: /MSP/LCE

Dr, Jadi Magagi, DIE/MSP/LCE

Dr J.P. Louboutin Croc: French Assistant, CT/SG/MSP

UNICEF:

Dr. Isselmou Ould Boukhary, Section Chief Health/Nutrition

Dr. Maoudé Hamissou, Administrator Health/EPI/NVD

Dr. Faoinet Yattara

Martin Morama, Unicef, Geneva

WHO:

Dr. René Z. OODDY, Representative

Dr. David Hayman, WHO/HQ Geneva

Dr. Antoine Kaoré, WHO/AFRO

Liliale Oualam, WHO/HQ Geneva

Dr. Ambrosio Disadidi, Monitoring Focal Point

Mr. Harou Moussa, Logistics

Mr. Imrahima Léye, Social Mobilization Focal Point, Rapporteur

HKI:

Mrs. Mandoul Aïssa

Mrs. Nargoungou Safia

ROTARY INTERNATIONAL:

Mr. Gaston Kaba

RED CROSS:

Dr. Moungo Yahouza

CUBAN MEDICAL ASSISTANCE:

Dr. Alphonso Pranco

JICA:

Alassane Ibrahim

Sasadate Kotchi

WORLD BANK:

Djibrilla Karamoko

Dr. Alpha Cissé, former Director for Major Endemics

The Secretary General of the Ministry of Public Health and the Fight against Endemics called the meeting to order and thanked the participants on behalf of the Minister of Health, who was attending the meeting of the Council of Ministers.  He also welcomed Doctors David Hayman and Antoine Kaboré who had come to support efforts underway.

After a tour de table to present the participants, the agenda was announced and had only on item: the status of preparations for the NVD.

The members of the ICC listened attentively to the presentation of the preparations for the polio and measles NVD by the Deputy Chief of the Immunizations Division.

That presentation indicated that several activities had been completed in various areas and other remained to be carried out.

1.  Activities completed

Monitoring:

- STOP Team mission to three regions (Maradi, Tillaberi and Zinder) from May to July

- Resumption of the active search for cases of AFP in the urban community of Niamey: July 2004: deployment of one monitoring focal point in ach of the three zones of the country: Zone 1 (Dosso, Niamey and Tillaberi); Zone 2 (Agadez and Tahoua) and Zone 3 (Diffa, Maradi and Zinder)

Polio NVDs:

- Central orientation meeting on the tools and guide: 14-16 July

- Deployment of 12 international WHO consultants in the field; 17 July

- Revision of district and region micro-plans: 19 July – 5 August

- Synthesis and finalization of budgets at the central level: 5 – 11 August

Logistics:

- Request and receipt of vaccine carriers;

- Kick polio and 496 Giostyles received

- 2504 Blow Kings expected in September

- Niamey cold room rehabilitated and that of Zinder underway

- OPV ordered:

-	1st delivery: 30 September

-	2nd delivery: 31 October

- Order by WHO of 8 additional vehicles

-	probable date of arrival: 11 October

- Assessment of resources to be mobilized:

-	Staff:

  - 15,319 vaccinators

  - 2,919 supervisors

-	Transport:

- Cars:	968

- Motorcycles:	967

- Boats:	34

- Other:	1,039

Social mobilization:

- Regular meetings of the national committee for social mobilization;

- Mobilization of 3 international communications consultants by UNICEF;

- Finalization of the communication plan and messages;

- Revision of the explanatory document [“plaidoyer”];

- Identification of various channels:

-	community relays	5,852

-	communal/private/reg. radios	121

-	Village chiefs	12,180

-	Traditional chiefs	229

Measles:

- Micro-planning of completed activities and summing up underway

- Identification and contact with entities for the destruction of waste

- Identification of a mechanism for destruction of wastes depending on the areas (incineration or burying)

- Evaluation of the cold chain (freezing capacities, ice boxes and vaccine carriers)

Other activities:

- Holding of the ICC meeting on 17/08/04

- Establishment of the budget at the level of partners

- Signing of the decree on the creation, authority and organization of the national technical organizing committee for additional vaccinations

2.	Activities to be completed:

A number of activities remain to be completed, including:

- Recruitment of 5 national consultants by the WHO

- Mobilization of other international consultants by UNICEF

- Mapping in the stage of finalization for certain regions

- Finalization of tools and establishment of logistics and other inputs (isothermal boxes, vaccines, etc.)

- Involvement of independent supervisors

- Revitalization of regional and sub-regional organizing committees

- Mobilization of internal resources (NGOs and other institutions)

- Preparation of the official launch (date, place, personages, etc.)

- Involvement of volunteers (Scouts and Peace Corps)

- Production and dissemination of communication media.

In concluding his presentation, the Deputy Division Chief referred to the challenges to be met and the opportunities:

The challenges were essentially related to the failure to reach the target population, the implementation of planned trans-boundary activities, and follow-up of the implementation of planned activities for Lake Chad, North Tillabéry, Camel Head and Neck (Agadez zone);

As for the opportunities, they could be summed up as the arrival of the WHO mission (HQ and AFRO) from 13 to 14 September, consisting of Doctors Hayman and Kaboré, informing of the population by political leaders during the forthcoming election campaigns and the use of major cultural events (salt cure)

3.  Difficulties

The main difficulties identified were:

Technical subcommittee:

- Frequent absence of members

- The work of the subcommittee was confused with that of the consultants

Social mobilization subcommittee:

- Irregularity in the presence of certain members

- Lack of communication between the national subcommittee and regional subcommittees

Logistics subcommittee:

- Lack of a cold chain in some newly built health centers

- Breakdown of the cold chain at several health centers

- Insufficiency of iceboxes and vaccine carriers

- Lack of butane gas for refrigerators

- Breakdown or obsolescence of some vehicles

4.  Budget

The budget for the first passage was 815,019,175 CFA francs, i.e. USD 1,495,448, and for the second passage 718,554,017 CFA francs, i.e. USD 1,318,448.

5.  Interventions

Following that presentation, the need to involve volunteers from the Red Cross, the Scouts and the Peace Corps in the activities was stressed.  A total of 990 young people from the Red Cross, 121 volunteers from the Peace Corps and 400 scouts would be mobilized during these vaccination days.

In addition, the implementation of the trans-boundary activities at the operational level and Niger’s participation in the meeting of traditional chiefs scheduled for 21 September 2004 at Kano, Nigeria, was mentioned.

With regard to the government’s contribution to the measles campaign and to particular measures to overcome the gap in the measles campaign, the Secretary General of the Ministry of Health informed the ICC that the Government would release 20,000,000 CFA francs and that a request had been sent to the ADB to mobilize USD 500,000.  In addition, contacts had been made with Algeria for its support, particularly in the northern border area.

The Secretary General of the Ministry of Health also stressed that for questions of residual insecurity, a letter had been sent to the Armed Forces requesting their support.  With regard to areas of difficult access, their planning had been taken into account in micro-planning at the operational level.

Doctors Hayman and Kaboré were satisfied with the state of preparations for the polio and measles NVDs and they congratulated the Ministry of Public Health, all the teams of technicians and the partners.  However, they drew attention to the importance of strengthening monitoring in view of the decline in performance in August.

To that end the Ministry of Health had already sent letters to the regions to draw their attention to the importance of monitoring and the need to use all means at their disposal to strengthen it.

Previously, a few logistical difficulties related to travel and communication during the implementation of monitoring activities and to gas supplies were mentioned.

Drawing conclusions from the meeting, Doctors Hayman and Kaboré commended the work done and in particular thanked His Excellency the President of the Republic of Niger for his commitment and his help which made it possible to dissipate rumors about vaccination, not only in Niger but also at Kano.

It was hoped that by next year the circulation of the poliovirus would be stopped, especially as the last case was reported on 13 May 2004.  But we must remain cautious, as we were in the season of high transmission.

Meeting adjourned at 11:20 a.m.

# Footnotes

The buffer stock for vaccines and auto-disable syringes has been set at 25%.  It is added to the first stock of doses required to introduce vaccination in a given geographic area.  Indicate zero for other years.

A standard wastage factor will be used to calculate the number of syringes for reconstitution.  It will be 2 for BCG and 1.6 for measles and yellow fever.

Only for freeze-dried vaccines.  Indicate zero for other vaccines.

The buffer stock for vaccines and auto-disable syringes has been set at 25%.  It is added to the first stock of doses required to introduce vaccination in a given geographic area.  Indicate zero for other years.

A standard wastage factor will be used to calculate the number of syringes for reconstitution.  It will be 2 for BCG and 1.6 for measles and yellow fever.

Only for freeze-dried vaccines.  Indicate zero for other vaccines.

The buffer stock for vaccines and auto-disable syringes has been set at 25%.  It is added to the first stock of doses required to introduce vaccination in a given geographic area.  Indicate zero for other years.

A standard wastage factor will be used to calculate the number of syringes for reconstitution.  It will be 2 for BCG and 1.6 for measles and yellow fever.

Only for freeze-dried vaccines.  Indicate zero for other vaccines.

The buffer stock for vaccines and auto-disable syringes has been set at 25%.  It is added to the first stock of doses required to introduce vaccination in a given geographic area.  Indicate zero for other years.

A standard wastage factor will be used to calculate the number of syringes for reconstitution.  It will be 2 for BCG and 1.6 for measles and yellow fever.

Only for freeze-dried vaccines.  Indicate zero for other vaccines.

The buffer stock for vaccines and auto-disable syringes has been set at 25%.  It is added to the first stock of doses required to introduce vaccination in a given geographic area.  Indicate zero for other years.

A standard wastage factor will be used to calculate the number of syringes for reconstitution.  It will be 2 for BCG and 1.6 for measles and yellow fever.

Only for freeze-dried vaccines.  Indicate zero for other vaccines.

# Text boxes

Partnering with The Vaccine Fund

X