March 2006

Progress Report

to the

Global Alliance for Vaccines and Immunization (GAVI)

and

The Vaccine Fund

by the Government of

COUNTRY: REPUBLIC OF NIGER

Date of submission: 15 May 2006 Reporting period: 2005 ( Information provided in this report MUST refer to the preceding calendar year ) ( Tick only one ) : Inception report ( First annual progress report ( Second annual progress report ( Third annual progress report ( Fourth annual progress report X Fifth annual progress report ( Text boxes supplied in this report are meant only to be used as guides. Please feel free to add text beyond the space provided. *Unless otherwise specified, documents may be shared with GAVI partners and collaborators

# Progress Report Form:  Table of Contents

# Report on progress made during the previous calendar year

  - Immunization Services Support (ISS)

1.1.1	Management of ISS Funds

  - Use of Immunization Services Support

1.1.3	Immunization Data Quality Audit

  - GAVI/Vaccine Fund New and Under-used Vaccines

1.2.1	Receipt of new and under-used vaccines

1.2.2	Major activities

    - Use if GAVI/The Vaccine Fund financial support (US$100,000) for introduction of the new vaccine

1.3	Injection Safety

    - Receipt of injection safety support

    - Progress of transition plan for safe injections and safe management of sharps waste

    - Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

2.  Financial Sustainability

3.  Request for new and under-used vaccine for … (specify coming year)

  - Up-dated immunization targets

  - Confirmed/revised request for new vaccine (to be shared with UNICEF Supply Division) for year…

  - Confirmed/revised request for injection safety support for the year…

- Please report on progress since submission of the last Progress Report based on the indicators

selected by your country in the proposal for GAVI/VF support

5.  Checklist

6.  Comments

7.  Signatures

# 1.  	Report on progress made during the previous calendar year

To be filled in by the country for each type of support received from GAVI/The Vaccine Fund.

## Immunization Services Support (ISS)

#### 1.1.1	Management of ISS Funds

Please describe the mechanism for management of ISS funds, including the role of the Inter-Agency Co-ordinating Committee (ICC).

Please report on any problems that have been encountered involving the use of those funds, such as delay in availability for programme use.

The GAVI funds are managed by the Ministry of Public Health through a bank account. A restricted committee of the same Ministry proposes the expenditure to be made to the ICC which, after approval, orders the disbursement. Thus, the cheques are signed jointly by the following : - the chairman of the ICC or, by delegation, the financial controller of the Ministry of Health - the head of the ImmunizationDdivision. Delay in the receipt of the 2005 bonus funds. No problems in the management of GAVI funds were encountered during the 2005 financial year.

#### 1.1.2	Use of Immunization Services Support

During the preceding year, the following major areas of activities have been funded with the GAVI/Vaccine Fund Immunization Services Support contribution.

Funds received during the year under review:  	FCFA 215 755 040

Remaining funds (carry over) from the preceding year:  As at 31 /12/2004 :   FCFA 2 237 699

Table 1: Use of funds during 2005

Balance of funds as at December 2004	FCFA 2 237 699

Funds received in 2005:			FCFA 215 755 040

2005 balance: 					FCFA 14 594 378

| Area of immunization services support | Total amount in US $* | AMOUNT OF FUNDS |
| --- | --- | --- |
|  |  | PUBLIC SECTOR | PRIVATE SECTOR & Other |
|  |  | Central | Region/State/Province | District |  |
| Vaccines | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| Injection supplies | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| Bonuses / Personnel | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| Procurement | 2 955.65 | 2 955.65 | 0.00 | 0.00 | 0.00 |
| Vehicle maintenance | 5 798.46 | 5 798.46 | 0.00 | 0.00 | 0.00 |
| Overheads | 9 959.28 | 9 959.28 | 0.00 | 0.00 | 0.00 |
| Training | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| IEC / social mobilization | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| Outreach | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| Supervision | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| Monitoring and evaluation | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| Epidemiological surveillance | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| Equipment /Transport | 0,.0 | 0.00 | 0.00 | 0.00 | 0.00 |
| Other: Vaccinations | 336 886.59 | 0.00 | 0.00 | 336 886.59 | 0.00 |
| Bank commissions | 141.37 | 141.37 | 0.00 | 0.00 | 0.00 |
| Total : | 355 741.36 | 18 854.77 | 0.00 | 336 886.59 | 0.00 |
| Remaining funds for next year: | 28 897.27 | 28 897.27 |  |  |  |

- USD 1  = FCFA 505.04 (average dollar rate in 2005)

*If no information is available because of block grants, please indicate under ‘other’.

Please attach the minutes of the ICC meeting(s) when the allocation of funds was discussed.

Please report on major activities conducted to strengthen immunization, as well as, problems encountered in relation to your multi-year plan.

During 2005, there was a net improvement in the EPI indicators through the strengthening of activities by accelerated campaigns across all the districts. The campaigns, which received the support of the main partners, were conducted in June, July and August and made it possible to achieve DTP3 coverage rates of more than 80% in more than 80% of the districts. In addition to such support activities, most immunization centres organised at least three advanced strategy immunization visits per month and one social mobilization visit. The immunization visits were backed by the application of the decentralised mobile strategy in certain districts, supervision, the supply of immunization centres with input materials and logistics maintenance. For its part, the central level conducted 4 supervision missions to the regions, i.e. a rate of one mission per quarter. Coordination meetings to evaluate the activities were held by the district, the regions and the central level. The problems encountered include the following : poor supervision of the immunization centres insufficient funds allocated to the maintenance of the increasingly ageing fleet of vehicles and motorbikes existence of areas not covered by the EPI due to lack of funds to implement the decentralized mobile strategy persisting shortage of human resources at the operational level.

#### Immunization Data Quality Audit (DQA) (If it has been implemented in your country)

Has a plan of action to improve the reporting system based on the recommendations from the DQA been prepared?

If yes, please attach the plan.

## YES                              NO

## If yes, please report on the degree of its implementation.

Review of data collection tools Production of data collection tools financed out of GAVI funds Effective introduction of the materials in the field Improved processing and filing of data at all levels through the review of the computer database

## Please attach the minutes of the ICC meeting where the plan of action for the DQA was discussed and endorsed by the ICC.

Please report on studies conducted regarding EPI issues during 2004 (for example, coverage surveys).

NA

## GAVI/Vaccine Fund New & Under-used Vaccines Support

#### 1.2.1	Receipt of new and under-used vaccines during the preceding year

Please report on receipt of vaccines provided by GAVI/VF, including problems encountered.

#### 1.2.2	Major activities

Please outline major activities that have been or will be undertaken, in relation to, introduction, phasing-in, service strengthening, etc. and report on problems encountered.

Renewed impetus given to the fixed strategy Granting of resources for the organization of advanced and decentralized mobile strategy activities Implementation of the action plan for social mobilization in favour of the systematic EPI Strengthening of supervision of activities

#### 1.2.3	Use of GAVI/The Vaccine Fund financial support (US$100,000) for the introduction of the new vaccine

Please report on the proportion of 100,000 US$ used, activities undertaken, and problems encountered such as delay in availability of funds for programme use.

NA. A request for the introduction of new vaccines was made by Niger in 2005. However, the country did not receive any funds in this regard.

## Injection Safety

#### 1.3.1	Receipt of injection safety support

Please report on receipt of injection safety support provided by GAVI/VF, including problems encountered

The country’s submission for GAVI injection safety support has been accepted. The funds for 2004 were paid in kind (AD syringes). The country is awaiting the supplies for 2005. With regard to the problems encountered, the Immunization Division is faced with the problem of batch procurement for the regions. Due to lack of trucks for the transport of goods, injection supplies are not delivered until several weeks and sometimes months after the vaccines have been received. Moreover, the districts and health centres have always drawn supplies from the routine EPI stock when organising response activities to epidemic diseases that break out in their catchment area. This sometimes leads to shortages of EPI consumables.

#### Progress of transition plan for safe injections and safe management of sharps waste.

Please report on the progress based on the indicators chosen by your country in the proposal for GAVI/VF support.

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| % of health units equipped with safe means of storing, processing and eliminating wastes Average annual number of sharps injuries to the health workers Number of weekly curative injections carried out by the health units % of health units having experienced shortages of disposable and AD syringes during the year. | 100 % 50 % reduction 50 % reduction 0 % | 100% of the health centres use AD syringes and safety boxes safe means of waste disposal are available in most of the health centres | Evaluation not yet carried out |  |

#### 1.3.3	Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

The following major areas of activities have been funded (specify the amount) with the GAVI/The Vaccine Fund injection safety support in the past year:

Yes, Niger received this support. The contribution was in kind, namely AD syringes and safety boxes

# 2.  	Financial sustainability

Inception Report:	Outline timetable and process for the development of a financial sustainability plan . Describe assistance that may be needed for developing a financial sustainability plan.

First Annual Progress Report: 	Submit completed financial sustainability plan by given deadline. Describe major strategies for improving financial sustainability.

Subsequent Progress Reports:	According to current GAVI rules, support for new and under-used vaccines is covering the total quantity required to meet country targets (assumed to be equal to DTP3 targets) over a five year period (100% x 5 years = 500%).  If the requested amount of new vaccines does not target the full country in a given year (for example, a phasing in of 25%), the country is allowed to request the remaining (in that same example: 75%) in a later year.  In an attempt to help countries find sources of funding in order to attain financial sustainability by slowly phasing out GAVI/VF support, they are encouraged to begin contributing a portion of the vaccine quantity required.  Therefore, GAVI/VF support can be spread out over a maximum of ten years after the initial approval, but will not exceed the 500% limit (see figure 4 in the GAVI Handbook for further clarification).  In table 2.1, specify the annual proportion of five year GAVI/VF support for new vaccines that is planned to be spread-out over a maximum of ten years and co-funded with other sources. Please add the three rows (Proportion funded by GAVI/VF (%), Proportion funded by the Government and other sources (%), Total funding for ………….  (new vaccine)) for each new vaccine.

The Financial Sustainability Plan was finalized and sent to the GAVI Secretariat through the WHO in 2005. GAVI requested clarifications and additional information on certain aspects of the FSP. The drafting committee met and answered all the queries. A corrected version of the plan was sent to the GAVI Secretariat in March 2006. The indicators for the monitoring of the sustainability plan have not changed. They remain as follows : 1. proportion of the health budget allocated to the EPI Current value = 18,25% 2. Proportion of HIPC resources allocated to the EPI Current value = 0% 3. Proportion of local authority expenditure in total EPI expenditure Current value = not available 4. Proportion of community expenditure in EPI expenditure Current value = not available 5. Proportion of expenditure by the external partners in EPI expenditure Current value = 52% 6. Wastage rate per antigen : (2003 values: BCG = 34.4% ; DTP = 9.7% ; OPV = 20.6% ; Measles = 27.4% ; AAV = 15% ; TT = 32.4%) 7. Drop out rate between DTP1 and DTP3 Current value = 18%

# 3.  	Request for new and under-used vaccines for year 2006

Section 3 is related to the request for new and under used vaccines and injection safety for 2006.

- Up-dated immunization targets

Confirm/update basic data approved with country application: figures are expected to be consistent with those reported in the WHO/UNICEF Joint

Reporting Forms.  Any changes and/or discrepancies MUST be justified in the space provided (page 12). Targets for future years MUST be provided.

| Table 2 : Basic data and annual targets |
| --- |
| Number of | Achievements and targets |
|  | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 | - | - |
| DENOMINATORS |  |  |  |  |  |  |  |  |  |
| Births | 562 548 | 579 987 | 597 966 | 616 498 | 633 977 | 653 630 | 673 893 |  |  |
| Infants’ deaths | 69 237 | 71 383 | 73 596 | 75 877 | 77 979 | 80 397 | 82 889 |  |  |
| Surviving infants | 493 311 | 508 604 | 524 370 | 540 622 | 555 998 | 573 234 | 591 004 |  |  |
| Infants vaccinated with the 3 doses of DTP* |  |  |  |  |  |  |  |  |  |
| Figures from the WHO/UNICEF joint reporting form | 168 868 | 120 835 | 270 117 | 333 704 | 389 199 | - | - |  |  |
| NEW VACCINES |  |  |  |  |  |  |  |  |  |
| Infants vaccinated with DTP-HepB-Hib | - | - | - | - | - | 458 587 | 502 353 |  |  |
| Wastage rate **……….. ( new vaccine) | - | - | - | - | - |  |  |  |  |
| INJECTION SAFETY**** |  |  |  |  |  |  |  |  |  |
| Pregnant women vaccinated with TT | 246 690 | 224 465 | 238 730 | 263 521 | 380 386 | 424 860 | 471 725 |  |  |
| Infants vaccinated with BCG * | 268 330 | 293 682 | 383 776 | 442 693 | 475 483 | 522 904 | 539 114 |  |  |
| Infants vaccinated with Measles * | 285 948 | 266 794 | 333 695 | 397 859 | 416 999 | 458 587 | 502 354 |  |  |

* Indicate actual number of children vaccinated in past years and updated targets

** Indicate actual wastage rate obtained in past years

Please provide justification on changes to baseline, targets, wastage rate, vaccine presentation, etc. from the previously approved plan, and on reported figures which differ from those reported in the WHO/UNICEF Joint Reporting Form in the space provided below.

The denominators changed in 2001, following the adoption by the government of the Republic of Niger of the results of the general population census carried out in the same year. In view of the encouraging results obtained in terms of immunization coverage, the targets of the 2002-2006 strategic plan have been revised upwards. With regard to wastage rates, the compiled data provides wastage rates per antigen and per district. However, 10 to 15% of the data is erroneous. The workers in the field do not pay due attention to the importance of the aspect concerning the movement of vaccines and even where they do, the principle is not properly understood.

3.2	Availability of revised request for new vaccine (to be shared with UNICEF Supply Division) for 2006

In case you are changing the presentation of the vaccine, or increasing your request; please indicate below if UNICEF Supply Division has assured the availability of the new quantity/presentation of supply.

Table 3: Estimated number of doses of the DTP-HepB+Hib pentavalent vaccine (specify for one presentation only): Please repeat this table for any other vaccine presentation requested from

GAVI/The Vaccine Fund

*Please report the same figure as in table 3.

Table 3: Wastage rates and factors

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

#### 3.3	Confirmed/revised request for injection safety support for the years 2006 -2007

Table 4: Estimated supplies for safety of vaccination for the next two years with BCG (Use one table for each vaccine BCG, DTP, measles and TT, and number them from 4 to 8)

Table 5: Estimated supplies for safety of vaccination for the next two years with DTP for 2005 and the pentavalent for 2006

Table 6: Estimated supplies for safety of vaccination for the next two years with Measles

Table 7: Estimated supplies for safety of vaccination for the next two years with TT

#### If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference.

The results of the routine EPI recorded at national level for the years 2003, 2004 and 2005 led to a review of the immunization coverage targets laid down in the 2002-2006 EPI strategic plan. Thus, the targets for all the antigens, with the exception of TT, were revised upwards for the years 2004, 2005 and 2006.

Table 8: Estimated supplies for safety of vaccination for the next two years with yellow fever vaccine

# 4. 	Please report on progress since submission of the last Progress Report based on the indicators selected 	by your country in the proposal for GAVI/VF support

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| DTP3 coverage rate TT2+ coverage rate (women) DTP drop out rate | 55 % 55 % 20 % | 62% (2004) 43 % (2004) 18 % (2004) | - management of epidemics, - shortage of personnel, - polio, measles campaigns - age of vehicles and motorbikes - difficulties of seasonal access | 70 % 60 % 15 % |

# Checklist

Checklist of completed form:

| Form Requirement: | Completed | Comments |
| --- | --- | --- |
| Date of submission | 15 March 2006 |  |
| Reporting Period (consistent with previous calendar year) | 2005 |  |
| Table 1 filled-in | YES |  |
| DQA reported on | NO |  |
| Reported on use of 100,000 US$ | NA |  |
| Injection Safety Reported on | NO |  |
| FSP Reported on (progress against country FSP indicators) | YES | The plan has been revised and sent |
| Table 2 filled-in | YES | Data provided with effect from 2001 |
| New Vaccine Request completed | YES | Introduction of the PENTAVALENT with effect from 2007 |
| Revised request for injection safety completed (where applicable) |  |  |
| ICC minutes attached to the report | YES |  |
| Government signatures | YES |  |
| ICC endorsed | YES |  |

6.  	Comments

ICC/RWG comments:

7.	Signatures

For the Government of  the Republic of Niger

Signature:	……………………………………………...……………...

Title:	Minister of Public Health and the Fight against Endemic Diseases

Date:	………………………………………….………………….

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this report. Signature of endorsement of this document does not imply any financial (or legal) commitment on the part of the partner agency or individual.

Financial accountability forms an integral part of GAVI/The Vaccine Fund monitoring of reporting of country performance.  It is based on the regular government audit requirements as detailed in the Banking form.  The ICC Members confirm that the funds received have been audited and accounted for according to standard government or partner requirements.

| Agency/Organization | Name/Title | Date Signature | Agency/Organization | Name/Title | Date Signature |
| --- | --- | --- | --- | --- | --- |
| WHO | Representative |  | RED CROSS | President |  |
| UNICEF | Representative |  | ROTARY INT. | President |  |
| HKI | Representative |  | JICA | Representative |  |

~ End ~

# Text boxes

Partnering with The Vaccine Fund

X

Remarks

Phasing: Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided Wastage of vaccines: Countries are expected to plan for a maximum of: 50% wastage rate for a lyophilized vaccine in 10 or 20-dose vial; 25% for a liquid vaccine in a10 or 20-dose vial; 10% for any vaccine (either liquid or lyophilized) in 1 or 2-dose vial. Buffer stock: The buffer stock is recalculated every year as 25% the current vaccine requirement Anticipated vaccines in stock at start of year 2006: It is calculated by counting the current balance of vaccines in stock, including the balance of buffer stock. Write zero if all vaccines supplied for the current year (including the buffer stock) are expected to be consumed before the start of next year. Countries with very low or no vaccines in stock must provide an explanation of the use of the vaccines. AD syringes: A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines. Reconstitution syringes: it applies only for lyophilized vaccines. Write zero for other vaccines. Safety boxes: A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes