Annual Progress Report 2006

Submitted by

The Government of

PAPUA NEW GUINEA

to the

# Date of submission: 18 may 2007

Annual progress report (this report reports on activities in 2006 and specifies requests for 2008, Jan.-Dec.)

*Unless otherwise specified, documents may be shared with GAVI partners and collaborators as well as the general public.

Signatures Page for ISS, INS and NVS

For the Government of PAPUA NEW GUINEA

| Ministry of Health: | Ministry of Finance: |
| --- | --- |
| Dr. Nicholas Mann |  |
| Title: Secretary for Health | Title: …………………………………… |
| Signature: …………………………………… | Signature: …………………………………… |
| Date: …………………………………… | Date: …………………………………… |

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this report. Signature of endorsement of this document does not imply any financial (or legal) commitment on the part of the partner agency or individual.

Financial accountability forms an integral part of GAVI Alliance monitoring of reporting of country performance.  It is based on the regular government audit requirements as detailed in the Banking form.

The ICC Members confirm that the funds received from the GAVI Funding Entity have been audited and accounted for according to standard government or partner requirements.

| Name/Title | Agency/Organisation | Signature | Date |
| --- | --- | --- | --- |
| Dr Nicholas Mann, Secretary for Health & Chairman of ICC | National Department of Health |  |  |
| Mr. Enoch Posanai, Director Health Improvement Branch & Secretary for ICC | National Department of Health |  |  |
| Dr. Eigil Sorensen, WHO Country Representative (Member ICC) | World Health Organization |  |  |
| Dr. Robyn Biti, 1st Secretary Development Corporation (ICC member) | AusAID |  |  |
| Mr Hamish Young, UNICEF Country Representative (ICC member) | UNICEF |  |  |
| Mr. Nathan Kili, Churches Medical Council Representative | Churches Medical Council |  |  |
| Mr. Joseph Klapat, Secretary for Community Development | Department of Community Development |  |  |
| Dr. Paulus Ripa, Curriculum Development officer | School of Medicine, University of PNG |  |  |
| JICA Project Formulation Officer | JICA |  |  |

Signatures Page for HSS

For the Government of ………………..…………………………………

| Ministry of Health: | Ministry of Finance: |
| --- | --- |
| Title: …………………………………… | Title: …………………………………… |
| Signature: …………………………………… | Signature: …………………………………… |
| Date: …………………………………… | Date: …………………………………… |

We, the undersigned members of the National Health Sector Coordinating Committee, ……………………………………… (insert name) endorse this report on the Health Systems Strengthening Programme. Signature of endorsement of this document does not imply any financial (or legal) commitment on the part of the partner agency or individual.

Financial accountability forms an integral part of GAVI Alliance monitoring of reporting of country performance.  It is based on the regular government audit requirements as detailed in the Banking form.

The HSCC Members confirm that the funds received from the GAVI Funding Entity have been audited and accounted for according to standard government or partner requirements.

| Name/Title | Agency/Organisation | Signature | Date |
| --- | --- | --- | --- |

# Progress Report Form:  Table of Contents

# Report on progress made during 2006

  - Immunization Services Support (ISS)

1.1.1	Management of ISS Funds

  - Use of Immunization Services Support

    - Immunization Data Quality Audit

    - ICC Meetings

  - GAVI Alliance New and Under-used Vaccines (NVS)

1.2.1	Receipt of new and under-used vaccines

1.2.2	Major activities

    - Use if GAVI Alliance financial support (US$100,000) for introduction of the new vaccine

    - Evaluation of Vaccine Management System

1.3		Injection Safety (INS)

    - Receipt of injection safety support

    - Progress of transition plan for safe injections and safe management of sharps waste

    - Statement on use of GAVI Alliance injection safety support (if received in the form of a cash contribution)

2.  Vaccine Co-financing, Immunization Financing and Financial Sustainability

3.  Request for new and under-used vaccine for 2008

  - Up-dated immunization targets

  - Confirmed/revised request for new vaccine (to be shared with UNICEF Supply Division) for year 2008 and projections for 2009 and 2010

  - Confirmed/revised request for injection safety support for the year 2008 and 2009

- Health System Strengthening (HSS)

- Checklist

- Comments

Text boxes supplied in this report are meant only to be used as guides.  Please feel free to add text beyond the space provided.

# 1.  	Report on progress made during 2006

## Immunization Services Support (ISS)

Are the funds received for ISS on-budget (reflected in Ministry of Health and Ministry of Finance budget): Yes

If yes, please explain in detail how it is reflected as MoH budget in the box below.

If not, explain why not and whether there is an intention to get them on-budget in the near future?

The funds are deposited into the Health Sector Improvement Program (HSIP) Trust Account where all the donor funds or grants are kept and are only released for activities that are planned in the annual activity plan (AAP) at the national and provincial level and budgeted for in support of the immunization activities through the MoH recurrent budget.

#### 1.1.1	Management of ISS Funds

Please describe the mechanism for management of ISS funds, including the role of the Inter-Agency Co-ordinating Committee (ICC).

Please report on any problems that have been encountered involving the use of those funds, such as delay in availability for programme use.

The ISS Funds are deposited into the Health Sector Improvement Program (HSIP) Account and are managed by the Director of the HSIP (who is the Financial delegate of the Ministry of Finance).The funds are strictly controlled and released only for activities that are being planned for, for that particular year (AAP) with an estimated budget attached to that planned activity. However, the flow of the funds is still a problem with so much delay in getting funds made available for the planned budgeted activities. ICC plays an important role in endorsing immunization plans and activities and especially how the ISS funds are being utilized and also the EPI team reports on a quarterly basis to ICC on how the funds had been used. Implementation of ISS funds is only starting now in 2007, due to arrival in late 2006, and the role of the ICC in overseeing and endorsing these plans is expected to increase as greater funds pass through this mechanism. The HSIP account at all levels is independently audited, with funds only release after a satisfactory audit report has been received. While this has dramatically improved transparency, it also means that if funds from another programme (e.g. malaria) has not been acquitted correctly, this can have an impact on the release of EPI funds, and subsequent programme implementation.

#### 1.1.2	Use of Immunization Services Support

In 2006, the following major areas of activities have been funded with the GAVI Alliance Immunization Services Support contribution.

Funds received during 2006: US$108, 500 (1st tranche, received in August 2006 and was not used)

Remaining funds (carry over) from 2005 : Nil (No GAVI ISS Funds in 2005 was received)

Balance to be carried over to 2007: US$108,500 was carried over from 2006 and had started using the funds for micro plan workshops and supporting out-reach activities to improve immunization coverage at the districts and health facilities.  The use of ISS funds received in 2006 & 2007 therefore will be reflected better in the 2007 APR.

Table 1: Use of funds during 2006*

| Area of Immunization Services Support | Total amount in US $ | AMOUNT OF FUNDS |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | PUBLIC SECTOR |  |  | PRIVATE SECTOR & Other |
|  |  | Central | Region/State/Province | District |  |
| Vaccines |  |  |  |  |  |
| Injection supplies |  |  |  |  |  |
| Personnel |  |  |  |  |  |
| Transportation |  |  |  |  |  |
| Maintenance and overheads |  |  |  |  |  |
| Training |  |  |  |  |  |
| IEC / social mobilization |  |  |  |  |  |
| Outreach |  |  |  |  |  |
| Supervision |  |  |  |  |  |
| Monitoring and evaluation |  |  |  |  |  |
| Epidemiological surveillance |  |  |  |  |  |
| Vehicles |  |  |  |  |  |
| Cold chain equipment |  |  |  |  |  |
| Other …………. (specify) |  |  |  |  |  |
| Total: |  |  |  |  |  |
| Remaining funds for next year: |  |  |  |  |  |

*If no information is available because of block grants, please indicate under ‘other’.

Please attach the minutes of the ICC meeting(s) when the allocation and utilization of funds were discussed.

Please report on major activities conducted to strengthen immunization, as well as problems encountered in relation to implementing your multi-year plan.

This will be reported in 2007 APR due to non use of ISS funds in 2006

#### Immunization Data Quality Audit (DQA)

Next* DQA scheduled for _________

*If no DQA has been passed, when will the DQA be conducted?

*If the DQA has been passed, the next DQA will be in the 5th year after the passed DQA

*If no DQA has been conducted, when will the first DQA be conducted?

What were the major recommendations of the DQA ?

Has a plan of action to improve the reporting system based on the recommendations from the DQA been prepared?

YES                              NO

## If yes, please report on the degree of its implementation and attach the plan.

## Please highlight in which  ICC meeting  the plan of action for the DQA was discussed and endorsed by the ICC.

Please report on studies conducted regarding EPI issues during 2006 (for example, coverage surveys).

1.1.4. ICC meetings

How many times did the ICC meet in 2006 ? Please attach all minutes.

Are any Civil Society Organizations members of the ICC and if yes, which ones ?

In 2006 ICC met three times but did not have the quorum for two of the scheduled meetings. A meeting on 25 July 2006, was convened and majority of the members were present (see Attachment 1). In the first meeting of 2007, the issue of including Civil Society Organization was raised and invitation will be sent to Country Women’s Organization. Regularity of ICC meetings in 2007 is expected to improve due to 1) availability of funds, 2) strong support from the Secretary of Health, and 3) coordination of ICC meeting with the PNG Child Health Advisory Committee and EPI Technical Committee that are responsible for technical aspects of the EPI programme.

1.2. GAVI Alliance New & Under-used Vaccines Support (NVS)

#### Receipt of new and under-used vaccines during 2006

When was the new and under-used vaccine introduced? Please include change in doses per vial and change in presentation, (e.g. DTP + HepB mono to DTP-HepB) and dates shipment were received in 2006.

| Vaccine | Vials size | Doses | Date of Introduction | Date shipment received (2006) |
| --- | --- | --- | --- | --- |

Please report on any problems encountered.

Hib vaccine in combination with DTP (i.e DTP-Hib liquid formulation, 10-dose vial) will be introduced into Papua New Guinea in August 2007, therefore, there is nothing to report for 2006.

#### Major activities

Please outline major activities that have been or will be undertaken, in relation to, introduction, phasing-in, service strengthening, etc. and report on problems encountered.

Funding support of US$100,000 for introduction of Hib vaccine from GAVI was received on February 2007 and will be use to support the introduction process. Plans are already underway and IEC materials have already been developed and getting them ready for distribution through all the available avenues and at every opportunity (i.e., in meetings, workshops, conferences, media, etc). See Attachment No 2- The Work-plan for Introduction of Hib Vaccine.

#### Use of GAVI funding entity support (US$100,000) for the introduction of the new vaccine

These funds were received on : February 2007

Please report on the proportion of 100,000 US$ used, activities undertaken, and problems encountered such as delay in availability of funds for programme use.

As stated in 1.2.2, this funds will be used this year in 2007 under the Hib vaccine introduction workplan, thus full report of its use will be made in next years APR.

    - Effective Vaccine Store Management/Vaccine Management Assessment

The last Effective Vaccine Store Management (EVSM)/Vaccine Management Assessment (VMA) was conducted in, Non done last year, but VMA is planned fro this year 2007.

Please summarize the major recommendations from the EVSM/VMA

Was an action plan prepared following the EVSM/VMA : Yes/No

If so, please summarize main activities under the EVSM plan and the activities to address the recommendations.

The next EVSM/VMA* will be conducted in : _____________

## *All countries will need to conduct an EVSM/VMA in the second year of new vaccine support approved under GAVI Phase 2.

## 1.3 Injection Safety

#### Receipt of injection safety support

Received in cash/kind

Please report on receipt of injection safety support provided by the GAVI Alliance during 2006 (add rows as applicable).

| Injection Safety Material | Quantity | Date received |
| --- | --- | --- |

Please report on any problems encountered.

No injection safety support received from GAVI Alliance in 2006.

#### Progress of transition plan for safe injections and safe management of sharps waste.

If support has ended, please report how injection safety supplies are funded.

The injection safety supplies are funded 100% by the government of Papua New Guinea. At present, no request is being made from NDOH PNG to GAVI for Injection Safety Support.

#### Please report how sharps waste is being disposed of.

Three methods of waste disposal are used in Papua New Guinea: - Incineration - Open burning - Burial

#### Please report problems encountered during the implementation of the transitional plan for safe injection and sharps waste.

#### Statement on use of GAVI Alliance injection safety support in 2006 (if received in the form of a cash contribution)

The following major areas of activities have been funded (specify the amount) with the GAVI Alliance injection safety support in the past year:

As stated above (1.3.1), no funds were received for injection safety support from GAVI Alliance in 2006

# 2. 	Vaccine Co-financing, Immunization Financing and Financial Sustainability

Table 2:	Financing trends for EPI in PNG 2007 to 2010 remain the same at the cMYP submitted in 2006, as does PNG Government uptake of Hib vaccine financing.  2006 expenditure figures were not available for all provinces at the time of GAVI report submittal.

Table 3:	Information on co financing remains the same as GAVI application, see table 2.1 in the 2005 APR from PNG

| Table 4: Questions on Vaccine Co-Financing Implementation |  |  |  |
| --- | --- | --- | --- |
| Q. 1: What mechanisms are currently used by the Ministry of Health in your country for procuring EPI vaccines? |  |  |  |
|  | Tick for Yes | List Relevant Vaccines | Sources of Funds |
| Government Procurement- International Competitive Bidding | Yes | All Vaccines | Recurrent Government Budget |
| Government Procurement- Other |  |  |  |
| UNICEF | Yes | Measles SIA and GAVI DTP-Hib | United Nations Foundation |
| PAHO Revolving Fund |  |  |  |
| Donations |  |  |  |
| Other (specify) |  |  |  |
| Q. 2: How have the proposed payment schedules and actual schedules differed in the reporting year? |  |  |  |
| Schedule of Co-Financing Payments | Proposed Payment Schedule | Date of Actual Payments Made in Reporting Year | Delay in Co-Financing Payments |
|  | (month/year) | (day/month) | (days) |
| 1st Awarded Vaccine (DTP-Hib) | January/2008 | Nil | Nil |
| NDOH co procurement of DTP-Hib vaccine was delayed due to uncertainty about formulation of Hib vaccine that would be available through UNICEF supply, which was only clarified early 2007, after the tender process for NDOH procurement had occurred. At the same time, the delivery date of GAVI funded DTP-Hib vaccine has been delayed from June 2007 until September 2007, and vaccine that was to be procured by GPNG in 2007 will now be procured in 2008. |  |  |  |
| Q. 3: Have the co-financing requirements been incorporated into the following national planning and budgeting systems ? |  |  |  |
|  | Tick for Yes | List Relevant Vaccines |  |
| Budget line item for vaccine purchasing | Yes | DTP-Hib |  |
| National health sector plan |  |  |  |
| National health budget | Yes | DTP-Hib, |  |
| Medium-term expenditure framework |  |  |  |
| SWAp |  |  |  |
| cMYP Cost & Financing Analysis | Yes | DTP-Hib, |  |
| Annual immunization plan | Yes | DTP-Hib, |  |
| Other |  |  |  |

| Q. 4: What factors have slowed and/or hindered mobilization of resources for vaccine co-financing ? |  |
| --- | --- |
| 1. Uncertainty about Hib vaccine formulation that would be provided by GAVI/UNICEF supply to PNG |  |
| 2. Limited supply of Hib vaccine through UNICEF, with most going to GAVI funded support. |  |
| 3. PNG does not procure routine vaccines through UNICEF, but due to tender laws in PNG, must procure on open market, making sourcing supply a problem for vaccines in high demand such as DTP-Hib |  |
| Q. 5: Do you foresee future challenges with vaccine co-financing in the future? What are these ? |  |
| 1. Availability of Hib vaccine in the preferred format for PNG |  |
| 2. Coordinating GAVI procurement with local procurement to ensure that Hib vaccine is from the same manufacturer and presentation |  |
| 3. PNG Government revenue at present is strong, and this is predicted to continue for medium term, Government co funding of Hib vaccine is not seen as a future problem, especially as PNG already funds all routine EPI vaccines |  |
| 4. |  |
| 5. |  |

3.  	Request for new and under-used vaccines for year 2008

Section 3 is related to the request for new and under-used vaccines and injection safety for 2008.

- Up-dated immunization targets

Confirm/update basic data approved with country application: figures are expected to be consistent with those reported in the WHO/UNICEF Joint Reporting Forms.  Any changes and/or discrepancies MUST be justified in the space provided. Targets for future years MUST be provided.

Please provide justification on changes to baseline, targets, wastage rate, vaccine presentation, etc. from the previously approved plan, and on reported figures which differ from those reported in the WHO/UNICEF Joint Reporting Form in the space provided below.

There are no changes to baseline, targets or wastage rates from the previously approved plan and on reported figures in WHO/UNICEF Joint Reporting Form (2006). However, the government of PNG would like to make a formal request to GAVI Alliance that PNG would like to switch to Pentavalent (DTP-HepB-Hib, liquid 1-dose formulation) as from January 2009. The reason for the switch is that PNG is the only country that has applied for DTP-Hib while all the GAVI-eligible countries had applied for pentavalent. There will be cost implications as well as production issues of DTP-Hib if only few countries are applying for this vaccine. The other reason why PNG opted for the switch in 2009 rather than 2008, is to give sufficient time for PNG to assess the volume and cold storage capacity for 1-dose liquid pentavalent vaccine at all vaccine storage points and make appropriate changes to the level of cold chain equipment.

| Table 5 : Update of immunization achievements and annual targets. Provide figures as reported in the JRF in 2006 and projections from 2007 onwards. |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of | Achievements and targets |  |  |  |  |  |  |  |  |
|  | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 |
| DENOMINATORS |  |  |  |  |  |  |  |  |  |
| Births | 190,541 | 196,639 | 202,931 | 209,425 | 216,126 | 223,042 | 230,180 | 237,546 | 245, 147 |
| Infants’ deaths | 12,195 | 12,585 | 12,988 | 13,403 | 13,832 | 14,275 | 14,732 | 15, 203 | 15,689 |
| Surviving infants | 178,347 | 184,054 | 189,943 | 196,022 | 202,294 | 208,768 | 215,448 | 222,343 | 229, 458 |
| Infants vaccinated till 2006 (JRF) / to be vaccinated in 2007 and beyond with 1st dose of DTP (DTP1)* |  | 156,402 | 170,949 | 0 | 0 | 0 | 0 | 0 | 0 |
| Infants vaccinated till 2006 (JRF) / to be vaccinated in 2007 and beyond with 3rd dose of DTP (DTP3)* |  | 141,855 | 151,955 | 0 | 0 | 0 | 0 | 0 | 0 |
| NEW VACCINES ** |  |  |  |  |  |  |  |  |  |
| Infants vaccinated till 2006 (JRF) / to be vaccinated in 2007 and beyond with 1st dose of DTP-Hib (DTP-Hib1)* |  | 0 | 75,977 | 176,419 | 192,180 | 204,592 | 211,139 | 217,896 | 224,869 |
| Infants vaccinated till 2006 (JRF) / to be vaccinated in 2007 and beyond with 3rd dose of DTP-Hib (DTP-Hib3) |  | 0 | 75,977 | 166,618 | 182,065 | 198,329 | 204,676 | 211,226 | 217,985 |
| Wastage rate till 2006 and plan for 2007 beyond*** ………….. ( new vaccine) |  | 0 | 25 | 25 | 20 | 20 | 15 | 15 | 15 |
| INJECTION SAFETY**** |  |  |  |  |  |  |  |  |  |
| Pregnant women vaccinated / to be vaccinated with TT |  | 88,906 | 208,045 | 215,064 | 222,336 | 237,132 | 244,719 |  |  |
| Infants vaccinated / to be vaccinated with BCG |  | 151,085 | 182,638 | 198,954 | 205,320 | 211,890 | 218,671 | 225,669 | 232,890 |
| Infants vaccinated / to be vaccinated with Measles (1st dose) |  | 112,775 | 132,960 | 147,016 | 161,835 | 177,453 | 193,903 | 211,226 | 217,985 |

* Indicate actual number of children vaccinated in past years and updated targets (with either DTP alone or combined)

** Use 3 rows (as indicated under the heading NEW VACCINES) for every new vaccine introduced

*** Indicate actual wastage rate obtained in past years

**** Insert any row as necessary

  - Confirmed/Revised request for new vaccine (to be shared with UNICEF Supply Division)

for 2008

In case you are changing the presentation of the vaccine, or increasing your request; please indicate below if UNICEF Supply Division has assured the availability of the new quantity/presentation of supply.

No changes requested for 2008, however to confirm that PNG would like to request supply of single dose DTP-Hib-HepB liquid vaccine in 2009

#### Please provide the XL sheet for calculating vaccine request duly completed and summarize in table 6 below. For calculations, please use same targets as in table 5.

Table 6a.  Estimated number of doses of DTP-Hib vaccine.  (Please provide additional tables for additional vaccines and number them 6a, 6b, 6c etc)

| Vaccine : | 2008 | 2009 | 2010 |
| --- | --- | --- | --- |
| Total doses required | 664, 807 | 0 | 0 |
| Doses to be funded by GAVI | 531, 846 | 0 | 0 |
| Doses to be funded by country | 132, 961 | 0 | 0 |
| Country co-pay in US$/dose* | 506, 582 | 0 | 0 |
| Total co-pay (US$) | 2, 532, 916 | 0 | 0 |

*As per GAVI co-financing policy, country grouping and order of vaccine introduction

Please note that XL table has reflects PNG co financing levels for 2008, not that of GAVI Phase II, which does not apply for PNG (but happen to be the same at 20%)

Table 6b.  Estimated number of doses of DTP-HepB-Hib vaccine.

| Vaccine : | 2008 | 2009 | 2010 |
| --- | --- | --- | --- |
| Total doses required | 0 | 682, 743 | 743, 735 |
| Doses to be funded by GAVI | 0 | 546, 194 | 557, 801 |
| Doses to be funded by country | 0 | 136, 549 | 185, 934 |
| Country co-pay in US$/dose* | 0 | 520, 252 | 708, 409 |
| Total co-pay (US$) | 0 | 2, 601, 252 | 2, 833, 630 |

Remarks

- Phasing: Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided

- Wastage of vaccines: Countries are expected to plan for a maximum of 50% wastage rate for a lyophilized vaccine in 10 or 20-dose vial; 25% for a liquid vaccine in a10 or 20-dose vial; 10% for any vaccine (either liquid or lyophilized) in a 2-dose vial, 5% for any vaccine in 1 dose vial liquid.

- Buffer stock: The buffer stock is recalculated every year as 25% the current  vaccine requirement

- Anticipated vaccines in stock at start of year 2008: It is calculated by counting the current balance of vaccines in stock, including the balance of buffer stock.  Write zero if all vaccines supplied for the current year (including the buffer stock) are expected to be consumed before the start of next year. Countries with very low or no vaccines in stock must provide an explanation of the use of the vaccines.

- AD syringes: A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines.

- Reconstitution syringes: it applies only for lyophilized vaccines. Write zero for other vaccines.

- Safety boxes: A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes

Table 7: Wastage rates and factors

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

#### 3.3   Confirmed/revised request for injection safety support for the year 2008

Table 8: Estimated supplies for safety of vaccination for the next two years with …… (Use one table for each vaccine BCG, DTP, measles and TT, and number them from 8a, 8b, 8c, etc. Please use same targets as in Table 5)

#### If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference.

PNG is eligible for Injection Safety Support, but did not apply for INS. However, PNG will consider making a formal request to GAVI in 2008 for funding support in lieu of supplies it is already purchasing.

# 4. Health Systems Strengthening (HSS)

This section only needs to be completed by those countries that have received approval for their HSS proposal. This will serve as an inception report in order to enable release of funds for 2008. Countries are therefore asked to report on any activity in 2007.

# Health Systems Support started in : _________________

Current Health Systems Support will end in : _____________

# Funds received in 2007 : 	Yes/No

If yes, date received : (dd/mm/yyyy)

If Yes, total amount : 	US$ ___________

Funds disbursed to date :  				US$ ___________

Balance of installment left: 				US$ ___________

Requested amount to be disbursed for 2008 	US$ ___________

Are funds on-budget (reflected in the Ministry of Health and Ministry of Finance budget) : Yes/No

If not, why not ? How will it be ensured that funds will be on-budget ? Please provide details.

Please provide a brief narrative on the HSS program that covers the main activities performed, whether funds were disbursed according to the  implementation plan, major accomplishments (especially impacts on health service programs, notably the immunization program), problems encountered and solutions found or proposed, and any other salient information that the country would like GAVI to know about. More detailed information on activities such as whether activities were implemented according to the implementation plan can be provided in Table 10.

Are any Civil Society Organizations involved in the implementation of the HSS proposal ? If so, describe their participation?

In case any change in the implementation plan and disbursement schedule as per the proposal is requested, please explain in the section below and justify the change in disbursement request. More detailed breakdown of expenditure can be provided in Table 9.

Please attach minutes of the Health Sector Coordinating Committee meeting(s) in which fund disbursement and request for next tranche were discussed. Kindly attach the latest Health Sector Review Report and audit report of the account HSS funds are being transferred to. This is a requirement for release of funds for 2008.

| Table 9. HSS Expenditure in 2007 (Please fill in expenditure on HSS activities and request for 2008. In case there is a change in the 2008 request, please justify in the narrative above) |  |  |  |
| --- | --- | --- | --- |
| Area for support | 2007 (Expenditure) | 2007 (Balance) | 2008 (Request) |
| Activity costs |  |  |  |
| Objective 1 |  |  |  |
| Activity 1.1 |  |  |  |
| Activity 1.2 |  |  |  |
| Activity 1.3 |  |  |  |
| Activity 1.4 |  |  |  |
| Objective 2 |  |  |  |
| Activity 2.1 |  |  |  |
| Activity 2.2 |  |  |  |
| Activity 2.3 |  |  |  |
| Activity 2.4 |  |  |  |
| Objective 3 |  |  |  |
| Activity 3.1 |  |  |  |
| Activity 3.2 |  |  |  |
| Activity 3.3 |  |  |  |
| Activity 3.4 |  |  |  |
| Support costs |  |  |  |
| Management costs |  |  |  |
| M&E support costs |  |  |  |
| Technical support |  |  |  |
| TOTAL COSTS |  |  |  |

| Table 10. HSS Activities in 2007 (Please report on activities conducted in 2007) |  |
| --- | --- |
| Major Activities | 2007 |
| Objective 1: |  |
| Activity 1.1: |  |
| Activity 1.2: |  |
| Activity 1.3: |  |
| Activity 1.4: |  |
| Objective 2: |  |
| Activity 2.1: |  |
| Activity 2.2: |  |
| Activity 2.3: |  |
| Activity 2.4: |  |
| Objective 3: |  |
| Activity 3.1: |  |
| Activity 3.2: |  |
| Activity 3.3: |  |
| Activity 3.4: |  |

| Table 11. Please update baseline indicators. Add other indicators according to the HSS proposal. |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Indicator | Data Source | Baseline Value | Source | Date of Baseline | Target | Date for Target |
| 1. National DTP3 coverage (%) |  |  |  |  |  |  |
| 2. Number / % of districts achieving ≥80% DTP3 coverage |  |  |  |  |  |  |
| 3. Under five mortality rate (per 1000) |  |  |  |  |  |  |
| 4. |  |  |  |  |  |  |
| 5. |  |  |  |  |  |  |
| 6. |  |  |  |  |  |  |

Please describe whether targets have been met, what kind of problems have occurred in measuring the indicators, how the monitoring process has been strengthened and whether any changes are proposed.

# 5.	Checklist

Checklist of completed form:

| Form Requirement: | Completed | Comments |
| --- | --- | --- |
| Date of submission |  |  |
| Reporting Period (consistent with previous calendar year) |  |  |
| Government signatures |  |  |
| ICC endorsed |  |  |
| ISS reported on |  |  |
| DQA reported on |  |  |
| Reported on use of 100,000 US$ |  |  |
| Injection Safety Reported on |  |  |
| Immunisation Financing & Sustainability Reported on (progress against country IF&S indicators) |  |  |
| New Vaccine Request including co-financing completed and XL sheet attached |  |  |
| Revised request for injection safety completed (where applicable) |  |  |
| HSS reported on |  |  |
| ICC minutes attached to the report |  |  |
| HSCC minutes, audit report of account for HSS funds and annual health sector evaluation report attached to report |  |  |

6.  	Comments

ICC/HSCC comments:

~ End ~

If baseline data is not available indicate whether baseline data collection is planned and when

Important for easy accessing and cross referencing