January 2005

Progress Report

Partnering with The Vaccine Fund

to the

Global Alliance for Vaccines and Immunization (GAVI)

and

The Vaccine Fund

by the Government of

COUNTRY: SÃO TOMÉ AND PRÍNCIPE

Date of submission: …………………………… Reporting period: 2004 ( Information provided in this report MUST refer to 2004 activities ) ( Tick only one ) : Inception report  First annual progress report  Second annual progress report  Third annual progress report x Fourth annual progress report  Fifth annual progress report  Text boxes supplied in this report are meant only to be used as guides. Please feel free to add text beyond the space provided. *Unless otherwise specified, documents may be shared with GAVI partners and collaborators

# Progress Report Form:  Table of Contents

# Report on progress made during 2004

  - Immunization Services Support (ISS)

1.1.1	Management of ISS Funds

  - Use of Immunization Services Support

1.1.3	Immunization Data Quality Audit

  - GAVI/Vaccine Fund New and Under-used Vaccines

1.2.1	Receipt of new and under-used vaccines

1.2.2	Major activities

    - Use if GAVI/The Vaccine Fund financial support (US$100,000) for introduction of the new vaccine

1.3	Injection Safety

    - Receipt of injection safety support

    - Progress of transition plan for safe injections and safe management of sharps waste

    - Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

2.  Financial Sustainability

3.  Request for new and under-used vaccine for 2006

  - Up-dated immunization targets

  - Confirmed/revised request for new vaccine (to be shared with UNICEF Supply Division) for year…

  - Confirmed/revised request for injection safety support for the year…

- Please report on progress since submission of the last Progress Report based on the indicators

selected by your country in the proposal for GAVI/VF support

5.  Checklist

6.  Comments

7.  Signatures

# 1.  	Report on progress made during 2004

To be filled in by the country for each type of support received from GAVI/The Vaccine Fund.

## Immunization Services Support (ISS)

#### 1.1.1	Management of ISS Funds

Please describe the mechanism for management of ISS funds, including the role of the Inter-Agency Co-ordinating Committee (ICC).

Please report on any problems that have been encountered involving the use of those funds, such as delay in availability for programme use.

The WHO and UNICEF funds are handled by the corresponding organisations in the Ministry of Health. GAVI funds are only used after authorisation from the ICC, which has the function of approving the plan for use of the funds. GAVI funds are not released without the signature of a WHO or UNICEF representative, and a representative of the Ministry of Health. No problem has been encountered in the use of these funds.

#### 1.1.2	Use of Immunization Services Support

In 2004, the following major areas of activities have been funded with the GAVI/Vaccine Fund Immunization Services Support contribution.

Funds received during 2004 __USD - 0__________

Remaining funds (carry over) from 2003 ___USD 35,243.67____

Table 1: Use of funds during 2004

| Area of Immunization Services Support | Total amount in US $ | AMOUNT OF FUNDS |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | PUBLIC SECTOR |  |  | PRIVATE SECTOR & Other |
|  |  | Central | Region/State/Province | District |  |
| Vaccines |  |  |  |  |  |
| Injection supplies |  |  |  |  |  |
| Personnel | 607,41 |  |  | 607,41 |  |
| Transportation |  |  |  |  |  |
| Maintenance and overheads |  |  |  |  |  |
| Training |  |  |  |  |  |
| IEC / social mobilization | 3574,00 | 1537,00 |  | 2037,00 |  |
| Outreach |  |  |  |  |  |
| Supervision | 6058,52 | 1240,00 |  | 4818,52 |  |
| Monitoring and evaluation | 2813,89 | 2813,89 |  |  |  |
| Epidemiological surveillance | 1973,47 |  |  | 1973,47 |  |
| Vehicles | 1330,98 | 1330,98 |  |  |  |
| Cold chain equipment | 2211,17 |  |  | 2211,17 |  |
| Other …………. (specify) | 5, 391,52 | 5.391,52 |  |  |  |
| Total: | 23. 960, 96 | 12. 313, 39 |  | 11. 647, 57 |  |
| Remaining funds for next year: |  |  |  |  |  |

*If no information is available because of block grants, please indicate under ‘other’.

Please attach the minutes of the ICC meeting(s) when the allocation of funds was discussed.

Please report on major activities conducted to strengthen immunization, as well as, problems encountered in relation to your multi-year plan.

- Activities to increase social awareness (dramatisation, spots in social communication media, training for community health workers and traditional midwives). - Reinforcement of supervision. - Logistical support in the field of transport for supervisors and district vaccinators. - Meetings for the evaluation of vaccination activities with those responsible and district vaccinators.

#### Immunization Data Quality Audit (DQA) (If it has been implemented in your country)

Has a plan of action to improve the reporting system based on the recommendations from the DQA been prepared?

If yes, please attach the plan.

YES                              NO

X

## If yes, please report on the degree of its implementation.

Not applicable.

## Please attach the minutes of the ICC meeting where the plan of action for the DQA was discussed and endorsed by the ICC.

Please report on studies conducted regarding EPI issues during 2004 (for example, coverage surveys).

Not applicable.

## GAVI/Vaccine Fund New & Under-used Vaccines Support

#### 1.2.1	Receipt of new and under-used vaccines during 2004

Start of vaccinations with the new and under-used vaccine:           MONTH…September..           YEAR…2003

Please report on receipt of vaccines provided by GAVI/VF, including problems encountered.

On the 22/05/04 we had received 16,800 doses of vaccines against Hepatitis B (Hepatitis B, recombinant DNA vaccine, 100 mcg. HB 30721. Expiry date: Dec. 2006) and 8,200 doses of vaccines against Yellow Fever (10 DX 6276-1-Expiry Date: 07-2006), in a good state of preservation. We are continuing to record high levels of wastage in the case of yellow fever vaccine, despite the use of 10 dose bottles. As a consequence we have been out of stock since January 2005. Given the size of the target population perhaps 5 dose bottles should be used.

#### 1.2.2	Major activities

Please outline major activities that have been or will be undertaken, in relation to, introduction, phasing-in, service strengthening, etc. and report on problems encountered.

Advocacy and social awareness Workshop for evaluating and reinforcing vaccination activities.

#### 1.2.3	Use of GAVI/The Vaccine Fund financial support (US$100,000) for the introduction of the new vaccine

Please report on the proportion of 100,000 US$ used, activities undertaken, and problems encountered such as delay in availability of funds for programme use.

Members of the ICC have expressed their concern that up to now GAVI funds have not been used for the introduction of new vaccines.

## Injection Safety

#### 1.3.1	Receipt of injection safety support

Please report on receipt of injection safety support provided by GAVI/VF, including problems encountered

As far as the receipt of support for the safety of injections is concerned, we have received: - 61,700 self-blocking syringes - 1,800 reconstitution syringes - 775 safe boxes. No problems have arisen.

#### Progress of transition plan for safe injections and safe management of sharps waste.

#### Please report problems encountered during the implementation of the transitional plan for safe injection and sharp waste

Please report on the progress based on the indicators chosen by your country in the proposal for GAVI/VF support.

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| 1. Number of districts in which self-blocking syringes have not been out of stock during the last 12 months | 100% | 100% | - | 100% |
| 2. Number of districts in which safety boxes have not been out of stock during the last 12 months | 100% | 100% | - | 100% |
| 3. Number of health services not out of stock at the time of the last monitoring visit | 100% | 100% | - | 100% |
| 4. Number of districts with a functioning incinerator | 100% | 0% | They have also shown their concern in that up to now it has not been possible to find a suitable incinerator model | 100% |
| 5. Number of health units and community units which adeauately burn and bury materials used for injection | 100% | 0% | They are of the opinion that as far as these two problems are concerned the Ministry of Health should take urgent steps to resolve these | 100% |
| 6. % of syringes and needles used in wastes in waste dumping areas or close to health units | 0% | 0% |  | 0% |
| 7. Number of collateral effects reported nationally in the course of the year | 100% | 0% | No complaints from parents | 100% |

#### 1.3.3	Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

The following major areas of activities have been funded (specify the amount) with the GAVI/The Vaccine Fund injection safety support in the past year:

Not applicable.

# 2.  	Financial sustainability

Inception Report:	Outline timetable and process for the development of a financial sustainability plan . Describe assistance that may be needed for developing a financial sustainability plan.

First Annual Progress Report: 	Submit completed financial sustainability plan by given deadline. Describe major strategies for improving financial sustainability.

A multidisciplinary team attended a training workshop on the preparation of FSP in Benin from the 28/06 to 01/07/04. There are 4 fundamental stages in the preparation of a FSP, namely: Stage 1: increasing awareness about and information on the FSP and establishment of a working party Stage 2: preparation of the first draught of the FSP Stage 3: adoption of the final FSP Stage 4: dispatch of the definitive FSP to GAVI The FSP for S. Tome and Príncipe is currently being prepared and will be forwarded to GAVI in November 2005.

Subsequent Progress Reports:	According to current GAVI rules, support for new and under-used vaccines is covering the total quantity required to meet country targets (assumed to be equal to DTP3 targets) over a five year period (100% x 5 years = 500%).  However, in an attempt to help countries find sources of funding in order to attain financial sustainability by slowly phasing out GAVI/VF support, they are encouraged to begin contributing a portion of the vaccine quantity required.  Therefore, GAVI/VF support can be spread out over a maximum of ten years after the initial approval, but will not exceed the 500% limit (see figure 4 in the GAVI Handbook for further clarification).  In table 2.1, specify the annual proportion of five year GAVI/VF support for new vaccines that is planned to be spread-out over a maximum of ten years and co-funded with other sources. Please add the three rows (Proportion funded by GAVI/VF (%), Proportion funded by the Government and other sources (%), Total funding for ………….  (new vaccine)) for each new vaccine.

| Table 2.1: Sources (planned) of financing of new Hepatitis B vaccine |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Proportion of vaccines supported by * | Annual proportion of vaccines |  |  |  |  |  |  |  |  |  |
|  | 2003.** | 2004.. | 2005.. | 2006.. | 2007.. | 2008.. | 2009.. | 2010.. | 2011.. | 2012.. |
| Proportion funded by GAVI/VF (%) | 100% | 100% | 100% | 100% | 30% | 20% | 20% | 10% | 10% | 10% |
| Proportion funded by the Government and other sources (%) | 0% | 0% | 0% | 0% | 70% | 80% | 80% | 90% | 90% | 90% |
| Total funding for Hepatitis B *** | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |

* Percentage of DTP3 coverage (or measles coverage in case of Yellow Fever) that is target for vaccination with a new and under-used vaccine

** The first year should be the year of GAVI/VF new vaccine introduction

*** Should total 500% at the end of GAVI/VF support

| Table 2.1: Sources (planned) of financing of new Yellow Fever vaccine |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Proportion of vaccines supported by * | Annual proportion of vaccines |  |  |  |  |  |  |  |  |  |
|  | 2003.** | 2004.. | 2005.. | 2006.. | 2007.. | 2008.. | 2009.. | 2010.. | 2011.. | 2012.. |
| Proportion funded by GAVI/VF (%) | 100% | 100% | 100% | 100% | 30% | 20% | 20% | 10% | 10% | 10% |
| Proportion funded by the Government and other sources (%) | 0% | 0% | 0% | 0% | 70% | 80% | 80% | 90% | 90% | 90% |
| Total funding for Yellow Fever*** | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |

In table 2.2 below, describe progress made against major financial sustainability strategies and corresponding

indicators.

Table 2.2:	Progress against major financial sustainability strategies and corresponding indicators

| Financial Sustainability Strategy | Specific Actions Taken Towards Achieving Strategy | Progress Achieved | Problems Encountered | Baseline Value of Progress Indicator | Current Value of Progress Indicator | Proposed Changes To Financial Sustainability Strategy |
| --- | --- | --- | --- | --- | --- | --- |
| 1. |  |  |  |  |  |  |
| 2. |  |  |  |  |  |  |
| 3. |  |  |  |  |  |  |
| 4. |  |  |  |  |  |  |
| 5. |  |  |  |  |  |  |

# 3.  	Request for new and under-used vaccines for year 2006

Section 3 is related to the request for new and under used vaccines and injection safety for 2006.

- Up-dated immunization targets

Confirm/update basic data approved with country application: figures are expected to be consistent with those reported in the WHO/UNICEF Joint

Reporting Forms.  Any changes and/or discrepancies MUST be justified in the space provided (page 14). Targets for future years MUST be provided.

| Table 3 : Update of immunization achievements and annual targets |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of | Achievements and targets |  |  |  |  |  |  |  |  |
|  | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 |
| DENOMINATORS |  |  |  |  |  |  |  |  |  |
| Births | 5028 | 5055 | 5072 | 5077 | 5089 | 5097 | 5098 | 5090 | 5111 |
| Infants’ deaths | 240 | 232 | 223 | 215 | 225 | 237 | 252 | 267 | 282 |
| Surviving infants | 4788 | 4823 | 4849 | 4862 | 4864 | 4860 | 4846 | 4823 | 4829 |
| Infants vaccinated in 2004 (JRF) / to be vaccinated 2005 and beyond with 1st dose of DTP (DTP1)* | 4937 | 4954 | 4970 | 4975 | 4987 | 4995 | 4996 | 4988 | 5009 |
| Infants vaccinated 2004 (JRF) / to be vaccinated 2005 and beyond with 3rd dose of DTP (DTP3)* | 4825 | 4852 | 4869 | 4874 | 4885 | 4893 | 4894 | 4886 | 4906 |
| NEW VACCINES ** |  |  |  |  |  |  |  |  |  |
| Infants vaccinated 2004 (JRF) / to be vaccinated 2005 and beyond with 1st dose of Hepatitis B | 4874 | 4954 | 4970 | 4975 | 4987 | 4995 | 4996 | 4988 | 5009 |
| Infants vaccinated 2004 (JRF) / to be vaccinated 2005 and beyond with 3rd dose of Hepatitis B | 5598 | 4852 | 4869 | 4874 | 4885 | 4893 | 4894 | 4886 | 4906 |
| Wastage rate in 2004 and plan for 2005 beyond*** ………….. ( new vaccine) | 4 % | 15% | 10% | 10% | 10% | 10% | 10% | 10% | 10% |
| INJECTION SAFETY**** | 4375 | 4802 | 4818 | 4823 | 4834 | 4842 | 4843 | 4835 | 4855 |
| Pregnant women vaccinated in 2004 (FRC) / to be vaccinated with TT 2 in 2005 and beyond | 58,6% | 40% | 30% | 30% | 25% | 25% | 25% | 25% | 25% |
| Infants vaccinated in 2004 (FRC) / to be vaccinated with BCG in 2005 and beyond |  |  |  |  |  |  |  |  |  |
| Infants vaccinated in 2004 (FRC) / to be vaccinated with Measles in 2005 and beyond | 5241 | 5721 | 5955 | 6134 | 6305 | 6478 | 6649 | 6820 | 6991 |
|  | 4980 | 5004 | 5021 | 5026 | 5038 | 5046 | 5047 | 5039 | 5060 |
|  | 4375 | 4802 | 4818 | 4823 | 4834 | 4842 | 4843 | 4835 | 4855 |

* Indicate actual number of children vaccinated in past years and updated targets (with either DTP alone or combined)

** Use 3 rows (as indicated under the heading NEW VACCINES) for every new vaccine introduced

*** Indicate actual wastage rate obtained in past years

**** Insert any row as necessary

Please provide justification on changes to baseline, targets, wastage rate, vaccine presentation, etc. from the previously approved plan, and on reported figures which differ from those reported in the WHO/UNICEF Joint Reporting Form in the space provided below.

3.2	Confirmed/Revised request for new vaccine (to be shared with UNICEF Supply Division) for 2006

Please indicate that UNICEF Supply Division has assured the availability of the new quantity of supply according to new changes.

UNICEF has not guaranteed the supply requested.

Table 4: Estimated number of doses of …… vaccine (specify for one presentation only): Please repeat this table for any other vaccine presentation requested from

GAVI/The Vaccine Fund

Remarks

- Phasing: Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided - Wastage of vaccines: Countries are expected to plan for a maximum of: 50% wastage rate for a lyophilized vaccine in 10 or 20-dose vial; 25% for a liquid vaccine in a10 or 20-dose vial; 10% for any vaccine (either liquid or lyophilized) in 1 or 2-dose vial. - Buffer stock: The buffer stock is recalculated every year as 25% the current vaccine requirement - Anticipated vaccines in stock at start of year… ….: It is calculated by counting the current balance of vaccines in stock, including the balance of buffer stock. Write zero if all vaccines supplied for the current year (including the buffer stock) are expected to be consumed before the start of next year. Countries with very low or no vaccines in stock must provide an explanation of the use of the vaccines. - AD syringes: A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines. - Reconstitution syringes: it applies only for lyophilized vaccines. Write zero for other vaccines. - Safety boxes: A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes

*Please report the same figure as in table 3.

Table 5: Wastage rates and factors

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

Table 4: Estimated number of doses of …… vaccine (specify for one presentation only): Please repeat this table for any other vaccine presentation requested from

GAVI/The Vaccine Fund

Remarks

- Phasing: Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided - Wastage of vaccines: Countries are expected to plan for a maximum of: 50% wastage rate for a lyophilized vaccine in 10 or 20-dose vial; 25% for a liquid vaccine in a10 or 20-dose vial; 10% for any vaccine (either liquid or lyophilized) in 1 or 2-dose vial. - Buffer stock: The buffer stock is recalculated every year as 25% the current vaccine requirement - Anticipated vaccines in stock at start of year… ….: It is calculated by counting the current balance of vaccines in stock, including the balance of buffer stock. Write zero if all vaccines supplied for the current year (including the buffer stock) are expected to be consumed before the start of next year. Countries with very low or no vaccines in stock must provide an explanation of the use of the vaccines. - AD syringes: A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines. - Reconstitution syringes: it applies only for lyophilized vaccines. Write zero for other vaccines. - Safety boxes: A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes

*Please report the same figure as in table 3.

Table 5: Wastage rates and factors

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

#### 3.3	Confirmed/revised request for injection safety support for the years 2006-2007

Table 6: Estimated supplies for safety of vaccination for the next two years with …… (Use one table for each vaccine BCG, DTP, measles and TT, and number them from 4 to 8)

#### If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference.

#### 3.3	Confirmed/revised request for injection safety support for the years 2006-2007

Table 6: Estimated supplies for safety of vaccination for the next two years with …… (Use one table for each vaccine BCG, DTP, measles and TT, and number them from 4 to 8)

#### If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference.

#### 3.3	Confirmed/revised request for injection safety support for the years 2006-2007

Table 6: Estimated supplies for safety of vaccination for the next two years with …… (Use one table for each vaccine BCG, DTP, measles and TT, and number them from 4 to 8)

#### If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference.

Table 6: Estimated supplies for safety of vaccination for the next two years with …… (Use one table for each vaccine BCG, DTP, measles and TT, and number them from 4 to 8)

#### If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference.

# 4. 	Please report on progress since submission of the last Progress Report based on the indicators selected 	by your country in the proposal for GAVI/VF support

| Indicators | 2004 Targets | Achievements | Constraints | Updated targets |  |
| --- | --- | --- | --- | --- | --- |
| Total population | 146.056 |  |  | 148.968 | 151.912 |
| Births | 5.028 |  |  | 5055 | 5072 |
| Infant mortality rate | 47,8 |  |  | 45,9 | 43,9 |
| Infant deaths | 240 |  |  | 232 | 223 |
| Surviving infants | 4.788 |  |  | 4.823 | 4849 |
| Children vaccinated for BCG | 4.827 | 4980 |  | 4.853 | 4971 |
| Children vaccinated for OPV3 | 4.596 | 4810 |  | 4630 | 4752 |
| Children vaccinated for DPT3 | 4.596 | 4825 |  | 4630 | 4752 |
| Children vaccinated for Measles | 4.309 | 4375 |  | 4485 | 4607 |
| Children vaccinated for monovalent Hepatitis B | 4.596 | 5598 |  | 4630 | 4752 |
| Children vaccinated for yellow fever | 4.309 | 4237 |  | 4485 | 4607 |
| Pregnant women vaccinated with TT | 5.550 | 5241 |  | 5721 | 5955 |

# Checklist

Checklist of completed form:

| Form Requirement: | Completed | Comments |
| --- | --- | --- |
| Date of submission | YES |  |
| Reporting Period (consistent with previous calendar year) | YES |  |
| Table 1 filled-in | YES |  |
| DQA reported on | ---- |  |
| Reported on use of 100,000 US$ | YES |  |
| Injection Safety Reported on | YES |  |
| FSP Reported on (progress against country FSP indicators) | YES |  |
| Table 2 filled-in | YES |  |
| New Vaccine Request completed | YES |  |
| Revised request for injection safety completed (where applicable) |  |  |
| ICC minutes attached to the report |  |  |
| Government signatures | YES |  |
| ICC endorsed | YES |  |

6.  	Comments

ICC/RWG comments:

7.	Signatures

For the Government of ………………..…………………………………

Signature:	……………………………………………...……………...

Title:	………………………………………….………………….

Date:	………………………………………….………………….

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this report. Signature of endorsement of this document does not imply any financial (or legal) commitment on the part of the partner agency or individual.

Financial accountability forms an integral part of GAVI/The Vaccine Fund monitoring of reporting of country performance.  It is based on the regular government audit requirements as detailed in the Banking form.  The ICC Members confirm that the funds received have been audited and accounted for according to standard government or partner requirements.

| Agency/Organisation | Name/Title | Date Signature | Agency/Organisation | Name/Title | Date Signature |
| --- | --- | --- | --- | --- | --- |
| WHO | Teresa Araujo Representative | 13 / 05 / 05 | Portuguese Embassy | António Machado | 13 / 05 / 05 |
| UNICEF | Batilloi Warritay, Office Manager | 13 / 05 / 05 | Portuguese Embassy | Claudia Gonçalves | 13 / 05 / 05 |
| US Embassy | Nelson Assunção | 13 / 05 / 05 | ROTARY CLUB S Tomé | Jorge Torres | 13 / 05 / 05 |
| PNUD | Graça Viegas Representative | 13 / 05 / 05 | China Taiwan Embassy | YANG-CHING YUEN | 13 / 05 / 05 |
| French Embassy | Oliver Monal | 13 / 05 / 05 |  |  |  |

~ End ~