January 2006

Progress Report

Partnering with The Vaccine Fund

to the

Global Alliance for Vaccines and Immunization (GAVI)

and

The Vaccine Fund

by the Government of

COUNTRY: TOGO

Date of submission: …13 / 05 / 06………………………… Reporting period: 2005 ( Information provided in this report MUST refer to 2005 activities ) ( Tick only one ) : Inception report  First annual progress report  Second annual progress report  Third annual progress report  X Fourth annual progress report  Fifth annual progress report  Text boxes supplied in this report are meant only to be used as guides. Please feel free to add text beyond the space provided. *Unless otherwise specified, documents may be shared with GAVI partners and collaborators

# Progress Report Form:  Table of Contents

# Report on progress made during 2005

  - Immunization Services Support (ISS)

1.1.1	Management of ISS Funds

  - Use of Immunization Services Support

1.1.3	Immunization Data Quality Audit

  - GAVI/Vaccine Fund New and Under-used Vaccines

1.2.1	Receipt of new and under-used vaccines

1.2.2	Major activities

    - Use if GAVI/The Vaccine Fund financial support (US$100,000) for introduction of the new vaccine

1.3	Injection Safety

    - Receipt of injection safety support

    - Progress of transition plan for safe injections and safe management of sharps waste

    - Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

2.  Financial Sustainability

3.  Request for new and under-used vaccine for 2007

  - Updated immunization targets

  - Confirmed/revised request for new vaccine (to be shared with UNICEF Supply Division) for year…

  - Confirmed/revised request for injection safety support for the year…

- Please report on progress since submission of the last Progress Report based on the indicators

selected by your country in the proposal for GAVI/VF support

5.  Checklist

6.  Comments

7.  Signatures

# 1.  	Report on progress made during 2005

To be filled in by the country for each type of support received from GAVI/The Vaccine Fund.

## Immunization Services Support (ISS)

#### 1.1.1	Management of ISS Funds

Please describe the mechanism for management of ISS funds, including the role of the Inter-Agency Co-ordinating Committee (ICC).

Please report on any problems that have been encountered involving the use of those funds, such as delay in availability for programme use.

The ICC Technical Committee (EPI Directorate, WHO team, UNICEF team) has endorsed the 2005 EPI Plans of Action for the districts, the regions and the central level.  The main EPI partners (WHO and UNICEF) have taken a decision on the funding of activities, taking GAVI’s ISS funds into consideration.  The Epidemiology Division has prepared funding requests that have been submitted to the Director General of Health and the Minister of Health.  These requests were subsequently forwarded to the partners concerned for funding (GAVI, WHO and UNICEF).

As far as ISS funds are concerned, the Minister of Health and the Director General of Health are joint signatories when it comes to releasing funds.  Once the financial year has ended, the EPI Directorate forwards the technical report and the accounting vouchers to the partners concerned.  The results for EPI activities in 2005 were presented to the ICC members at the meeting held on 8 March 2006.

In 2005 as well, funds were late reaching the regions.  This was because the first meeting of EPI officers, at which plans of action were drawn up, could not be held until June 2005 owing to the socio-political crisis in the country during the first half of the year.

#### 1.1.2	Use of Immunization Services Support

In 2004, the following major areas of activities have been funded with the GAVI/Vaccine Fund Immunization Services Support contribution.

Funds received during 2005		USD 801,200 (in reality we only received USD 701,200 in 2005; the remaining USD 100,000 come from funds received in 2004 in connection with the introduction of the YF vaccine but which were not reported in table 1 of 2004)

Remaining funds (carry over) from 2003 	USD 139,355

Table 1: Use of funds during 2005

| Area of Immunization Services Support | Total amount in USD | AMOUNT OF FUNDS |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | PUBLIC SECTOR |  |  | PRIVATE SECTOR & Other |
|  |  | Central | Region/State/Province | District |  |
| Vaccines | 0 | 0 | 0 | 0 | 0 |
| Injection supplies | 0 | 0 | 0 | 0 | 0 |
| Personnel | 15 288 | 1 017 | 0 | 14 272 | 0 |
| Transportation | 16 217 | 1 638 | 252 | 14 327 | 0 |
| Maintenance and overheads | 7 064 | 6 411 | 0 | 653 | 0 |
| Training | 0 | 0 | 0 | 0 | 0 |
| IEC / social mobilization | 1 515 | 0 | 0 | 0 | 1515 |
| Outreach | 0 | 0 | 0 | 0 | 0 |
| Reproduction of aids | 51 733 | 0 | 0 | 51 733 | 0 |
| Supervision | 11 450 | 0 | 0 | 11450 | 0 |
| Monitoring and evaluation | 10 166 | 0 | 380 | 9 785 | 0 |
| Epidemiological surveillance | 0 | 0 | 0 | 0 | 0 |
| Vehicles | 0 | 0 | 0 | 0 | 0 |
| Cold chain equipment | 35 723 | 9 222 | 0 | 26 501 | 0 |
| Other (bank charges) | 59 | 59 | 0 | 0 | 0 |
| Total: | 149 214 | 18 347 | 632 | 128 720 | 1515 |
| Remaining funds for next year: | 791 341 |  |  |  |  |

*If no information is available because of block grants, please indicate under ‘other’.

Please attach the minutes of the ICC meeting(s) when the allocation of funds was discussed.

Please report on major activities conducted to strengthen immunization, as well as, problems encountered in relation to your multi-year plan.

In 2005, the major activities conducted to strengthen immunization with GAVI funding were the following:

■	Implementation of the RED (Reach Every District) approach in the country’s 35 districts

The RED approach consisted first of all of micro-planning of activities to reinforce immunization in the 35 districts.  Funding was available for these activities, which covered immunization using fixed and outreach strategies, supervisory training, monitoring and social mobilization.  The outreach strategy targeted villages that were remote or situated more than five kilometres from immunization centres.  Monitoring was conducted via monthly meetings of the Station Head Nurses, which were held in each District Department to analyze vaccine coverage, vaccine wastage, drop-outs and resource utilization.  These monthly monitoring meetings enabled EPI actors in the districts to analyse the difficulties encountered in implementing the RED approach and to move towards solutions.  They also involved private and religious health groups.  Two meetings of regional and districts EPI officers and regional and prefectural health directors were held in June and October 2005 to take stock of EPI activities.

Social mobilization efforts focused on the EPI chats held before immunization sessions and the dissemination of immunization awareness-building messages via community radio.

District and regional teams conducted decentralized supervision of immunizing health groups.  In addition, the Epidemiology Division supervised under-performing regions, i.e. Lomé-commune and Maritime.

■	Cold chain reinforcement

A stock of spare parts for refrigerators and freezers was received in December 2005 with a view to ensuring the maintenance of vaccine refrigerators in the field.  Given quantities were positioned in January 2006 in each of the Regional Offices for maintenance purposes.  Moreover, the central cold chamber of the Division of Epidemiology (DEPI), which had been out of operation since 8 February 2005 owing to a fire in the meter mechanism, was repaired in September.

■	Supply of vaccines and consumables

UNICEF supplies EPI vaccines and consumables via an agreement signed with the Togolese Government.  Regions are supplied on a quarterly basis.

■	Improvement of the data management system

With a view to harmonizing the data collection system at the operational level, the document “User’s Guide to Management Aids for EPI in Togo” was prepared and distributed in June 2005.  This document contains guidelines on how to fill in all data collection tools for routine immunization and management of vaccines and consumables (tally sheets, monthly reporting sheets, registers, stock sheets, inventory sheets, order and delivery forms, temperature sheets); all regional and prefectural EPI officers were briefed on the guide.

The major problems encountered are as follows:

■	Logistics

- Difficulties in finding long-body trucks to carry vaccines to the regions;

- Insufficient cold chamber storage capacity at the Division of Epidemiology, making it necessary to rely on the cold chamber of TOGOPHARMA-MEG ;

- Frequent breakdowns of the EPDI cold chamber owing to its dilapidated state

- Cramped premises in the EPDI cold chamber, making it necessary to rely on the TOGOPHARMA-MEG stores to store injection supplies;

- Lack of a maintenance system to deal rapidly and effectively with refrigerator breakdowns in the public health centres.

■	Vaccine management and completion forms

- Supervisory visits revealed inadequate vaccine management (non-compliance with guidelines, poor refrigerator maintenance leading to breakdowns, and failure to fill in forms properly.  Accordingly, it is essential to ensure that agents receive proper training in both areas.

#### 1.1.3	Immunization Data Quality Audit (DQA) (If it has been implemented in your country)

Not applicable

Has a plan of action to improve the reporting system based on the recommendations from the DQA been prepared?

If yes, please attach the plan.

YES                              NO

## If yes, please report on the degree of its implementation.

### Not applicable

Please attach the minutes of the ICC meeting where the plan of action for the DQA was discussed and endorsed by the ICC.

Please report on studies conducted regarding EPI issues during 2004 (for example, coverage surveys).

Studies conducted regarding EPI issues during 2005 related to EPIVAC operational research reports (ORR):

- Auto-evaluation of EPI immunization data quality in the health district of Tône. Data Quality Self-assessment (DQS);

- Study on vaccine wastage rates in the health district of Wawa and their impact on efficiency;

- Study on injection safety in the Lacs health district;

- Study of the reasons behind the Management Committees’ failure to participate in immunization activities in Oti health district;

- Study of the low vaccine coverage for children aged 0-11 months in Sokodé commune;

- Situational analysis of the system for the management of sharp waste from immunization in Ogou health district in 2005.

## 1.2	GAVI/Vaccine Fund New & Under-used Vaccines Support

#### 1.2.1	Receipt of new and under-used vaccines during 2005

Start of vaccinations with the new and under-used vaccine:           MONTH…December   YEAR…2004….

Please report on receipt of vaccines provided by GAVI/VF, including problems encountered.

162,300 doses of YF vaccine were received in a single batch in October 2005.  No problems were encountered with the delivery of this vaccine.

#### 1.2.2	Major activities

Please outline major activities that have been or will be undertaken, in relation to, introduction, phasing-in, service strengthening, etc. and report on problems encountered.

With a view to ensuring that children enjoy broader protection against vaccine-preventable diseases, the Ministry of Health has decided to incorporate a new antigen, the HepB vaccine (the DTP-HepB tetravalent vaccine) into routine immunization from 2006 onwards.  To this end, a plan for introducing the HepB vaccine into routine EPI in Togo and a proposal for support were prepared and submitted to GAVI and the Vaccine Fund in October 2005.

Togo’s request for support has been conditionally approved.

## 1.3	Injection Safety

#### 1.3.1	Receipt of injection safety support

Please report on receipt of injection safety support provided by GAVI/VF, including problems encountered

In 2005, the country benefited from injection safety support for the third year:

- AD syringes 0.5ml BCG:		247,900 units

- AD syringes 0.5ml:			1,185,600 units

- Dilution syringes 5 ml:		30,800 units

- Dilution syringes 2 ml:		24,800 units

- Safety boxes 5 litres:		16,600 units

As deliveries of injection supplies are not systematically accompanied by a donor certificate, the Port authorities sometimes require that taxes be paid before releasing material.

#### 1.3.2	Progress of transition plan for safe injections and safe management of sharp waste

#### Please report problems encountered during the implementation of the transitional plan for safe injection and sharp waste.

Real progress has been made with regard to injection safety and waste management.  As far as EPI was concerned, an injection safety policy was drafted and disseminated in 2002.  Vaccine deliveries to the regions and districts are always accompanied by sufficient quantities of AD syringes, dilution syringes (DS) and safety boxes (SB).  Moreover, 100% of all health groups systematically use AD syringes for immunization and each district has at least 1 DE MONFORT incinerator for safe disposal of injection waste.  However, 36% of these incinerators require overhauling.

Please report on the progress based on the indicators chosen by your country in the proposal for GAVI/VF support.

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
|  |  | In all, 1,286,044 vaccine doses were injected according to the monthly immunization reports. With an average of 100 syringes per SB, this works out to about 12,860 SB filled. 10,784 SB were incinerated according to the monthly reports, giving an incineration rate of 84% for the country as a whole. At the district level, the results show that 46% of the districts (16/35) destroyed at least 90% of SB via incineration in 2005. | 36% of the incinerators require overhauling. | 100% of all districts destroy at least 90% of SB via incineration. |
| Percentage of safety boxes (SB) destroyed by district | 100% of all districts destroy at least 90% of SB via incineration |  |  |  |

#### 1.3.3	Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

The following major areas of activities have been funded (specify the amount) with the GAVI/The Vaccine Fund injection safety support in the past year:

The country did not receive any funds for injection safety support.

# 2.  	Financial sustainability

Inception Report:	Outline timetable and process for the development of a financial sustainability plan . Describe assistance that may be needed for developing a financial sustainability plan.

First Annual Progress Report: 	Submit completed financial sustainability plan by given deadline. Describe major strategies for improving financial sustainability.

| As Togo has not yet prepared its Financial Sustainability Plan (FSP), it began straight away to draft the Multi-year Plan (MYP) for 2006-2010. This document is being prepared. The deadline for submitting the MYP is July 2006. With technical back-up from a health economics specialist from the Agency for Preventive Medicine (APM), we have carried out a number of activities, the details of which are provided in the following chronogram: Chronogram of activities for implementation of the MYP |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | April-May 2006 |  |  |  | June 2006 |  |  |  |  |
| Activity | SI | S2 | S3 | S4 | SI | S2 | S3 | S4 |  |
| Analyze status of immunization program (EPI review) | X | X | X |  |  |  |  |  |  |
| Define EPI target, strategies and activities for 2007-2011 |  |  | X | X |  |  |  |  |  |
| Prepare chronogram of EPI activities for 2007-2011 |  |  | X | X |  |  |  |  |  |
| Finish collecting data for calculating past and future costs and financing | X | X | X | X |  |  |  |  |  |
| Enter data using Excel | X | X | X | X |  |  |  |  |  |
| Analyze past (2005) and future (2007-2011) costs and financing |  |  |  | X | X |  |  |  |  |
| Define EPI financial sustainability strategies |  |  |  |  | X | X |  |  |  |
| Have the ICC endorse the MYP |  |  |  |  |  |  | X |  |  |
| This MYP will be submitted in July 2006 once it it has been endorsed by the ICC. |  |  |  |  |  |  |  |  |  |

Subsequent Progress Reports:	According to current GAVI rules, support for new and under-used vaccines is covering the total quantity required to meet country targets (assumed to be equal to DTP3 targets) over a five year period (100% x 5 years = 500%).  If the requested amount of new vaccines does not target the full country in a given year (for example, a phasing in of 25%), the country is allowed to request the remaining (in that same example: 75%) in a later year.  In an attempt to help countries find sources of funding in order to attain financial sustainability by slowly phasing out GAVI/VF support, they are encouraged to begin contributing a portion of the vaccine quantity required.  Therefore, GAVI/VF support can be spread out over a maximum of ten years after the initial approval, but will not exceed the 500% limit (see figure 4 in the GAVI Handbook for further clarification).  In table 2.1, specify the annual proportion of five year GAVI/VF support for new vaccines that is planned to be spread-out over a maximum of ten years and co-funded with other sources. Please add the three rows (Proportion funded by GAVI/VF (%), Proportion funded by the Government and other sources (%), Total funding for ………….  (new vaccine)) for each new vaccine.

| Table 2.1: Sources (planned) of financing of new vaccine …YF |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Proportion of vaccines supported by * | Annual proportion of vaccines |  |  |  |  |  |  |  |  |  |
|  | 2005** | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 |
| A: Proportion funded by GAVI/VF (%)*** | 100 | 80 | 80 | 60 | 60 | 40 | 20 | 20 | 20 | 20 |
| B: Proportion funded by the Government and other sources (%) | 0 | 20 | 20 | 40 | 40 | 60 | 80 | 80 | 80 | 80 |
| C: Total funding for YF | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 |

* Percentage of DTP3 coverage (or measles coverage in case of Yellow Fever) that is target for vaccination with a new and under-used vaccine.

** The first year should be the year of GAVI/VF new vaccine introduction

*** Row A should total 500% at the end of GAVI/VF support

In table 2.2 below, describe progress made against major financial sustainability strategies and corresponding indicators.

Table 2.2:	Progress against major financial sustainability strategies and corresponding indicators

| Financial Sustainability Strategy | Specific Actions Taken Towards Achieving Strategy | Progress Achieved | Problems Encountered | Baseline Value of Progress Indicator | Current Value of Progress Indicator | Proposed Changes To Financial Sustainability Strategy |
| --- | --- | --- | --- | --- | --- | --- |
| 1. |  |  |  |  |  |  |
| 2. |  |  |  |  |  |  |
| 3. |  |  |  |  |  |  |
| 4. |  |  |  |  |  |  |
| 5. |  |  |  |  |  |  |

# 3.  	Request for new and under-used vaccines for year 2007

Section 3 is related to the request for new and under used vaccines and injection safety for 2007.

- Updated immunization targets

Confirm/update basic data approved with country application: figures are expected to be consistent with those reported in the WHO/UNICEF Joint

Reporting Forms.  Any changes and/or discrepancies MUST be justified in the space provided (page 12). Targets for future years MUST be provided.

Table 3 : Update of immunization achievements and annual targets

| Number of | Achievements and targets |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 |
| DENOMINATORS |  |  |  |  |  |  |  |  |  |
| Births | 234540 | 240 863 | 246 789 | 252 860 | 259 080 | 265 453 | 271 984 | 278 674 | 285 530 |
| Infant deaths | 26060 | 19 269 | 19 743 | 20 229 | 20 726 | 21 236 | 21 759 | 22 294 | 22 842 |
| Surviving infants | 208480 | 221 594 | 227 046 | 232 631 | 238 354 | 244 217 | 250 225 | 256 380 | 262 688 |

|  | Achievements and targets |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 |
| VACCINE COVERAGE TARGETS (as a %) |  |  |  |  |  |  |  |  |  |
| BCG | 96 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 |
| DTP1 | 91 | 93 | 93 | 93 | 94 | 96 | 97 | 97 | 97 |
| DTP2 | 82 | 87 | 89 | 90 | 92 | 94 | 95 | 95 | 95 |
| DTP3 | 82 | 85 | 85 | 87 | 89 | 91 | 92 | 92 | 92 |
| MEAS | 70 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 |
| YF | 56 | 75 | 80 | 80 | 80 | 80 | 80 | 80 | 80 |
| TT2+ | 70 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 |
| Infants vaccinated 2005 (JRF) / to be vaccinated in 2005 and beyond with 1st dose of DTP (DTP1)* | 188817 | 206082 | 211153 | 216347 | 224053 | 234448 | 242718 | 248689 | 254807 |
| Infants vaccinated 2005 (JRF) / to be vaccinated in 2006 and beyond with 3rd dose of DTP (DTP3)* | 171779 | 188355 | 192989 | 202389 | 212135 | 222237 | 230207 | 235870 | 241673 |
| NEW VACCINES ** |  |  |  |  |  |  |  |  |  |
| Infants vaccinated 2005 (JRF) / to be vaccinated in 2006 and beyond with 1st dose of YF | 117394 | 166196 | 181637 | 186105 | 190683 | 195374 | 200180 | 205104 | 210150 |
| Infants vaccinated 2005 (JRF) / to be vaccinated in 2006 and beyond with 3rd dose of…….… ( new vaccine) |  |  |  |  |  |  |  |  |  |
| Wastage rate in 2005 and planned for 2006 beyond*** YF…….. ( new vaccine) | 25% | 15% | 10% | 10% | 10% | 10% | 10% | 10% | 10% |
| INJECTION SAFETY**** |  |  |  |  |  |  |  |  |  |
| Pregnant women vaccinated in 2005 (JRF) / to be vaccinated in 2006 and beyond with TT2 | 163101 | 192690 | 197431 | 202288 | 207264 | 212362 | 217587 | 222939 | 228424 |
| Infants vaccinated in 2005 (JRF) / to be vaccinated in 2006 and beyond with BCG * | 199173 | 210514 | 215694 | 220999 | 226436 | 232006 | 237714 | 243561 | 249554 |
| Infants vaccinated in 2005 (JRF) / to be vaccinated in 2006 and beyond with 1st dose of DTP (DTP1) | 188817 | 206082 | 211153 | 216347 | 224053 | 234448 | 242718 | 248689 | 254807 |

Table 3 (cont.)

| Number of | Achievements and targets |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 |
| Infants vaccinated in 2005 (JRP)/to be vaccinated in 2006 and beyond with 2nd dose of DTP (DTP2) | 171900 | 192787 | 202071 | 209368 | 219286 | 229564 | 237714 | 243561 | 249554 |
| Infants vaccinated in 2005 (JRP)/to be vaccinated in 2006 and beyond with 3rd dose of DTP (DTP3) | 171779 | 188355 | 192989 | 202389 | 212135 | 222237 | 230207 | 235870 | 241673 |
| Infants vaccinated in 2005 (JRP)/to be vaccinated in 2006 and beyond with measles | 146711 | 177275 | 181637 | 186105 | 190683 | 195374 | 200180 | 205104 | 210150 |
| Infants vaccinated in 2005 (JRP)/to be vaccinated in 2006 and beyond with YF | 117394 | 166196 | 181637 | 186105 | 190183 | 195374 | 200180 | 205104 | 210150 |

* Indicate actual number of children vaccinated in 2004 and updated targets (with either DTP alone or combined)

** Use 3 rows (as indicated under the heading NEW VACCINES) for every new vaccine introduced

*** Indicate actual wastage rate obtained in past years

**** Insert any row as necessary

Please provide justification on changes to baseline, targets, wastage rate, vaccine presentation, etc. from the previously approved plan, and on reported figures which differ from those reported in the WHO/UNICEF Joint Reporting Form in the space provided below.

3.2	Availability of revised request for new vaccine (to be shared with UNICEF Supply Division) for 2007

In case you are changing the presentation of the vaccine, or increasing your request; please indicate below if UNICEF Supply Division has assured the availability of the new quantity/presentation of supply.

Not applicable

Table 4: Estimated number of doses of YF… vaccine (specify for one presentation only): Please repeat this table for any other vaccine presentation requested from GAVI/The Vaccine Fund

* Please report the same figure as in table 3.

Table 5: Wastage rates and factors

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

Remarks

- Phasing: Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided - Wastage of vaccines: Countries are expected to plan for a maximum of: 50% wastage rate for a lyophilized vaccine in 10 or 20-dose vial; 25% for a liquid vaccine in a10 or 20-dose vial; 10% for any vaccine (either liquid or lyophilized) in 1 or 2-dose vial. - Buffer stock: The buffer stock is recalculated every year as 25% the current vaccine requirement - Anticipated vaccines in stock at start of year 2007: It is calculated by counting the current balance of vaccines in stock, including the balance of buffer stock. Write zero if all vaccines supplied for the current year (including the buffer stock) are expected to be consumed before the start of next year. Countries with very low or no vaccines in stock must provide an explanation of the use of the vaccines. - AD syringes: A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines. - Reconstitution syringes: it applies only for lyophilized vaccines. Write zero for other vaccines. - Safety boxes: A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes

#### 3.3	Confirmed/revised request for injection safety support for the years 2007 -2008

Table 6.1: Estimated injection safety supplies for the next two years with YF (Use one table for each vaccine BCG, DTP, measles and TT, and number them from 4 to 8)

#### If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference.

Table 6.2: Estimated injection safety supplies for the next two years with BCG… (Use one table for each vaccine BCG, DTP, measles and TT, and number them from 4 to 8)

#### If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference.

Table 6.3: Estimated injection safety supplies for the next two years with DTP (Use one table for each vaccine BCG, DTP, measles and TT, and number them from 4 to 8)

#### If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference.

Table 6.4: Estimated injection safety supplies for the next two years with MEAS (Use one table for each vaccine BCG, DTP, measles and TT, and number them from 4 to 8)

#### If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference.

Table 6.5: Estimated injection safety supplies for the next two years with TT (Use one table for each vaccine BCG, DTP, measles and TT, and number them from 4 to 8)

#### If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference.

| 4. | Please report on progress since submission of the last Progress Report based on the indicators selected by your country in the proposal for GAVI/VF support |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Indicators | Targets | Achievements | Constraints | Updated targets targetstualisés |  |
|  | DTP3 coverage rate | 80% | 82% | - High drop-out rate for children between DTP3 and MEAS - Data from private immunizing centres not included in national reporting system | 85% |  |
|  | MEAS coverage rate | 80% | 70% |  | 80% |  |
|  | TT2+ coverage rate | 80% | 70% |  | 80% |  |
|  | DTP1/DTP3 drop-out rate | 5% | 9% | - Administrative data reported does not concern the cohorts of children | 5% |  |
|  | Rates for SB destruction via incineration | 100 % | 84% | - 36 % of incinerators require overhauling - Part of the SB used during a given year not destroyed until the following year | 100% |  |
|  | Percentage of districts destroying at least 90 % of SB via incineration | 100% | 46% |  | 100 % |  |
|  | Percentage of immunizing centres systematically using AD syringes for immunization | 100 % | 100% | - | 100 % |  |
|  | Procurement rate for refrigerators and freezers | 100% | 0% | - | 60% |  |

|  | Form Requirement: | Completed | Comments |
| --- | --- | --- | --- |
|  | Date of submission | X |  |
|  | Reporting Period (consistent with previous calendar year) | X |  |
|  | Table 1 filled-in | X |  |
|  | DQA reported on |  | NA |
|  | Reported on use of 100,000 US$ |  | NA |
|  | Injection Safety Reported on | X |  |
|  | FSP Reported on (progress against country FSP indicators) | X | EPI review just completed MYP under way |
|  | Table 2 filled-in | X | Only the part concerning YF funding has been completed. As the MYP is under preparation, the part relating to progress with regard to implementation has not been completed. |
|  | New Vaccine Request completed | X | Table 3 |
|  | Revised request for injection safety completed (where applicable) | X |  |
|  | ICC minutes attached to the report | X |  |
|  | Government signatures | X |  |
|  | ICC endorsed | X |  |

6.      Comments

ICC/RWG comments:

The year 2005 was an eventful one as far as the Expanded Program on Immunization was concerned.  Activities focused on mass immunization campaigns.  Four rounds of immunization for children aged 0-59 months were organized in February-March and November-December.  Vaccine coverage (routine EPI) was up sharply when compared with 2004. DTP3 went up from 71% in 2004 to 82% in 2005, while BCG rose from 91% in 2004 to 96% in 2005.  There was a decrease in drop-out rates between DTP1 and DTP3 (9% in 2005, 15% in 2004 and 13% in 2003).  TT2+ coverage was also up (56% in 2003, 61% in 2004 and 70% in 2005).  YF was introduced in December 2004 and extended to all districts in January 2005.  Injection safety became widespread: 100% of all immunizing centres use AD syringes for immunization, and 84% of all SB were destroyed via incineration as against 72% in 2004).

Injection safety support funds were used efficiently to support the various immunization strategies.  Plans for 2005 included the construction of a cold chamber, the purchase of a long body truck and the purchase of refrigerators to reinforce cold chain equipment at district level.  It was not possible to carry out these activities owing to certain constraints.  This explains the low utilization rate of ISS funds in 2005.  These funds will accordingly be carried over to 2006 and have already been included in the 2006 plan of action.

NB: The EPI Review has just been completed and the MYP is under way.