2006 Annual Progress Report

Submitted by

The Government of

TOGO

to

# Submission date:  14 May 2007

Annual progress report (this is a periodic report on activities carried out in 2006 and specifies needs for 2008)

*Unless otherwise stated, the documents may be made known to GAVI partners, its associates and the public.

Page of signatures for immunization services support (ISS), injection safety (IS) support and under-used vaccines

On behalf of the Government of TOGO……………………………………………..

| Health Ministry: | Finance Ministry: |
| --- | --- |
| Title: Minister of State, Minister for Health | Title: Minister for Finance, the Budget and Privatization |
| Signature: …………………………………… | Signature: …………………………………… |
| Date: …………………………………… | Date: …………………………………… |

We, the undersigned members of the Interagency Coordinating Committee [ICC], endorse this report. Signing the endorsement page of this document does not imply any financial (or legal) commitment on the part of the partner institution or the individual.

The obligation to account for financial aspects is an integral part of the GAVI Alliance's monitoring of periodic reports on countries’ performances.  This obligation is based on the need to carry out proper government audits, as specified in the bank form.

The ICC members confirm that the funds received from the GAVI Funding entity have indeed been audited and that their use has been duly evidenced in accordance with the official requirements of the government or partners.

| Name/Title | Institution/Organization | Signature | Date |
| --- | --- | --- | --- |
| Pr Kondi Charles AGBA Minister | Ministère de la Santé |  |  |
| Dr Kadri TANKARI Representative | World Health Organization |  |  |
| Mrs Una McCAULEY | United Nations Children’s Fund |  |  |
| Dr Potougnima TCHAMDJA Directeur Général | Direction Générale de la Santé |  |  |
| Mr Jean H. DJOSSOU | Ministère de l’Economie et des Finances |  |  |
| Mr Issaka LAGUEBANDE | Ministère du Développement et de l’aménagement du territoire |  |  |
| Mr Gbehomilo - Nyelolo TOMEGAH | Rotary International |  |  |
| Mr Joseph BAAH-DWOMOH | World Bank |  |  |
| Mr Olivier BOUCHER | French Cooperation Mission |  |  |
| Mrs Rosine COULIBALY | United Nations Development Program développement Développement |  |  |
| Dr Boukari OUEDRAOGO | GTZ |  |  |
| Dr Aristide APLOGAN | Agence pour la Médecine Préventive (AMP) |  |  |
| Mr Amavi AKPAMAGBO | Plan-Togo |  |  |
| Dr BARRY Alpha Oumar | UE / ADSS |  |  |
| Dr Kuami Guy BATTAH | Croix Rouge Togolaise |  |  |
| Dr Danladi NASSOURY Coordonnateur PEV | Division de l’Epidémiologie |  |  |
| Mr Kankoé ADANLETE- ADJANON Chef service | Service National Information Education Communication |  |  |
| Dr KOMLANGAN Atayi Directeur | Direction des Soins de Santé Primaires |  |  |
| Mrs Kpaba REMA GOFAGA Directrice | Direction des Affaires Communes |  |  |
| Dr Minzah PEKELE Directeur | Direction de la Planification, de la Formation et de la Recherche |  |  |
| Dr Atany NYANSA Directeur | Direction des Pharmacies, Laboratoires et Equipements Techniques |  |  |
| Dr Afefa Amivi BABA Directrice | Direction des Etablissements de Soins |  |  |
| Dr Kassouta Komlan Tchiguiri N’TAPI Chef division | Division Santé Familiale |  |  |

Page of signatures for HSS support

On behalf of the Government of……………………………………………..

| Health Ministry: | Finance Ministry: |
| --- | --- |
| Title: Minister of State, Minister for Health | Title: Minister for Finance, the Budget and Privatization |
| Signature: …………………………………… | Signature: …………………………………… |
| Date: …………………………………… | Date: …………………………………… |

We, the undersigned members of the Coordinating Committee of the …………….(insert name) national health sector endorse this report on the Health System Strengthening Program. Signing the endorsement page of this document does not imply any financial (or legal) commitment on the part of the partner institution or the individual.

The obligation to account for financial aspects is an integral part of the GAVI Alliance's monitoring of periodic reports on countries’ performances.  This obligation is based on the need to carry out proper government audits, as specified in the bank form.

The HSCC members confirm that the funds received from the GAVI funding entity have indeed been audited and that their use has been duly evidenced in accordance with the official requirements of the government or partners.

| Name/Title | Institution/ Organization | Signature | Date |
| --- | --- | --- | --- |

# Progress Report Form:  Table of contents

# Report on progress achieved in 2006

  - Immunization services support (ISS)

1.1.1	Management of ISS funds

  - Use of Immunization Services Support

    - Immunization Data Quality Audit

    - ICC meetings

  - GAVI Alliance support for new vaccines and under-used vaccines (UV)

1.2.1	Receipt of new vaccines and under-used vaccines

1.2.2	Main activities

    - Use of GAVI Alliance financial support (USD 100,000) for introduction of the new vaccine

    - Assessment of the vaccine management system

1.3		Injection Safety (IS)

    - Receipt of support for injection safety

    - Progress of the transition plan for safe injections and safe management of sharps waste

    - Statement on the use of GAVI Alliance support for injection safety (if such support has been received as a funding contribution)

2.  Co-funding of vaccines, immunization funding and financial viability

3.  Application for new vaccines and under-used vaccines for 2008

  - Updated immunization objectives

  - Confirmed/revised application for new vaccines (to be forwarded to the UNICEF Supply Division) for the year 2007 and estimates for 2009 and 2010

  - Confirmed/revised support application for injection safety for the years 2008 and 2009

- Health System Strengthening (HSS)

- Points to be checked

- Comments

The text areas in this report are supplied for guidance only.  You can of course add more text than in the space provided.

# 1.  	Report on progress achieved in 2006

## Immunization services support (ISS)

Are the funds received for ISS in accordance with the budget (do they appear in the Health Ministry and the Finance Ministry budget)?  Yes/No

If so, explain in detail in the box below how they appear in the Health Ministry budget.

If not, are there plans to put them in accordance with the budget in the near future?

The funds received for ISS are integrated in the Ministry of Health’s planning document by the financial affairs department. This funding is positioned under the Ministry of the Economy and Development so it is integrated under the external funding heading (budgetary aid).

#### 1.1.1	Management of ISS funds

Please show the mechanism for ISS funds management, including the role played by the Interagency Coordinating Committee (ICC).

Please report any problem that may be encountered when using these funds, for example delayed access to funds for carrying out the program.

The 2006 EPI action plans for districts, regions and the central level were ratified by the ICC in March 2006. The partners (WHO, UNICEF, Plan-Togo and ADSS) decided on funding the activities, considering the GAVI ISS funds. The Division of Epidemiology developed requests for funding which were submitted for approval to the Director General of Health and the Health Minister. These requests were then sent to the partners concerned for funding (GAVI, WHO, UNICEF, Plan-Togo and ADSS). After the activities were carried out, the Division of Epidemiology sent the technical report and supporting documents to the partners concerned.

#### 1.1.2	Use of Immunization Services Support

In 2006, the main activity sectors below were funded by resources from the GAVI Alliance’s Immunization Services Support.

Funds received in 2006:  355, 450 USD

Balance (carried forward) from 2005: 751,011 USD

Balance to be carried forward in 2007: 528,152 USD

Table 2: Use of funds in 2006

| Immunization Services Support Sector | Total amount in USD | AMOUNT OF FUNDS |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | PUBLIC SECTOR |  |  | PRIVATE SECTOR & Others |
|  |  | Central | Region/State/Province | District |  |
| Personnel | 59 519 | 12 419 | 0 | 47 100 | 0 |
| Transport | 37 403 | 9 507 | 0 | 27 865 | 0 |
| Maintenance and general costs | 6 915 | 6 340 | 0 | 575 | 0 |
| Training | 0 | 0 | 0 | 0 | 0 |
| IEC/ social mobilization | 1 666 | 0 | 0 | 0 | 1 666 |
| Actions aimed at groups that are difficult to reach | 0 | 0 | 0 | 0 | 0 |
| Supervision | 33 675 | 11061 | 12 786 | 9 828 | 0 |
| Monitoring and assessment* | 62 649 | 19 494 | 43 155 | 0 | 0 |
| Epidemiological surveillance | 17 340 | 0 | 0 | 17 340 | 0 |
| Vehicles (truck for transporting vaccines et vaccination equipment) | 20 826 | 20 826 | 0 | 0 | 0 |
| Motorbikes (9 motorbikes) | 25 856 | 25 856 | 0 | 0 | 0 |
| Cold chain equipment (cold room + refrigerators)*** | 164 332 | 53 120 | 0 | 111 213 | 0 |
| Building (warehouses)**** | 136 175 | 136 175 | 0 | 0 | 0 |
| Equipment and office furniture | 4 445 | 4 445 | 0 | 0 | 0 |
| Other: sundry costs + bank charges | 7 509 | 7 509 | 0 | 0 | 0 |
| Total: | 578 310 | 306 752 | 55 941 | 213 951 | 1 666 |
| Balance of funds for the following year: | 528 152 |  |  |  |  |

*If no information is available because block grants have been paid, please enter the amounts in the boxes reserved for “other” support sectors.

* The amount written on this line is 100% of the total cost of the internal EPI review carried out in 2006.

** The amount written on this line is 50% of the total cost of the truck bought in 2006. The balance will be paid in 2007.

*** The amount written on this line is 60% of the total cost of the cold rooms (positive, negative) and refrigerators and freezers ordered in 2006. The balance will be paid in 2007.

**** The amount written on this line is 50% of the total cost of warehouses for storing EPI vaccination equipment under construction at the central level in Lomé in 2006. The balance will be paid on final acceptance of the building.

Please attach the minutes of the ICC meeting(s) where allocation and use of the funds were examined.

Please give an account of the main activities carried out to increase immunization, as well as any problems that arose concerning your multi-year plan.

| In 2006, the main activities carried out as part of increasing immunization were: - Continuing implementation of the “ACD” (Atteindre Chaque District [Reach Each District]) approach in the country’s 35 districts; this began with micro-planning of activities concerning routine immunization. These activities (immunization at fixed and advanced posts, supervision, monthly monitoring meetings and involvement of community networks and local radio stations in the social mobilization) were carried out thanks to funding from the partners (GAVI, WHO, UNICEF, Plan-Togo, ADSS) and local funding. In addition to supervision by the district and regional manager teams of health training, supervision by the Division of Epidemiology of the districts of the Kara, Savanes and Plateaux regions must also be mentioned. - Two meetings were held in February and July 2006 for those in charge of EPI and the focal points of integrated regional and district disease surveillance, with participation by the central level and the Regional and Prefectoral Health Directors, in order to assess progress on EPI activities. - A review of the Expanded Program on Immunization (EPI) was conducted from February till May 2006, through a vaccine coverage survey and a study of the program’s management and logistics. - Developing the 2007-2011 comprehensive Multi-Year Plan for the Expanded Program on Immunization, which was ratified in October 2006. - Strengthening the cold chain. A stock of spare parts for refrigerators and freezers, acquired with GAVI funds, received in December 2005, was positioned operationally in 2006 in order to ensure on-site maintenance of vaccine refrigerators. Six hundred Blow King vaccine carriers funded by UNICEF and 8 refrigerators acquired with State funds were also allocated to the immunization centres. It should also be noted that two generators, funded through the State budget, were acquired for the Lomé and Kara cold rooms. - Supply of vaccines and consumables Vaccines and consumables for the country’s Expanded Program on Immunization (EPI) are supplied through UNICEF, thanks to a purchasing assistance agreement signed between this United Nations institution and the Togo State. The regions are supplied once a quarter. - Staff skills were increased, through training 168 vaccination workers from six regions in the various components of EPI management in December 2006. The main problems encountered are: - Concerning logistics - Inadequate cold room storage capacity at the Division of Epidemiology, requiring assistance to be sought from the TOGOPHARMA-MEG cold room; - Frequent breakdowns of the DEPI cold room due to its rundown state; - No maintenance system for dealing promptly and efficiently with refrigerator breakdowns in the primary care units; - Concerning management of the cold chain, vaccines and filling in data forms. The supervision showed that efforts have been made regarding vaccine management and filling in data forms in comparison with 2005 but some inadequacies remain in relation to refrigerator maintenance and vaccine management. - Inadequate financial resources for running the Division of Epidemiology. |  |
| --- | --- |

#### Immunization Data Quality Audit (DQA)

The next DQA is planned for [date] in 2009__________

*If no DQA has had a positive result, when will a DQA be done?

* If the DQA had a positive result, the following DQA will take place five years after the positive DQA.

*If no DQA has been done, when will the first DQA be done?

What were the DQA’s main recommendations?

The main recommendations of the 2004 data quality audit concern: - Introduction and routine use of tally sheets in health training. - Development of written guidelines for recording and reporting data for immunization and vaccine and syringe inventory control, for data storage, saving computerized data, feedback and AEFI management. - Retranscription of advanced strategies data in the immunization registers. - Recording and reporting of vaccinations administered to children under one year old.

Has an action plan been drawn up, based on the DQA recommendations, for improving the system of preparing reports ?

YES                           NO

x

## If so, please specify how far its implementation has progressed and attach the plan.

It must be pointed out that the action plan intended to improve the reporting system is not specific but is integrated into the 2005 and 2006 annual EPI plans and the 2007-2011 multi-year plan. Some activities aimed at strengthening the reporting system have already been carried out. These concern: - In 2005 - Development of new data forms for immunization data management (tally sheets) and inventory control for vaccines and syringes (stock records, order/delivery forms, stock inventory records); - Updating existing data forms (immunization register, monthly report card), thanks to introduction of the yellow fever vaccine in the children’s immunization schedule; - Development of guidelines on the use of all data forms used in the field; - Distribution of data forms and guidelines at the operational level; - Briefing on the EPI prefectoral and regional focal points during quarterly monitoring meetings; - In 2006 - Training of nurse post leaders and vaccination workers in data management and management of vaccines and consumables. Other activities will be carried out as part of the 2007-2011 plan, namely: - Development and distribution of a AEFI statement card. - Development and distribution of guidelines on AEFI management. - Computerized data management in the regions and districts. - Training district and regional focal point workers in immunization data quality self-assessment (DQS); - Development and distribution of an EPI supervision guide including DQS; - Immunization data quality assessment during training supervision visits;

## Please attach the minutes of the ICC meeting at which the DQA action plan was examined and adopted by the ICC.

Please report on studies carried out in 2006 concerning EPI themes (for example, coverage studies).

From March till May 2006, a review of the Expanded Program on Immunization (EPI) was conducted, as a prelude to development of the 2007-2011 EPI comprehensive multi-year plan (cMYP). The objective of this review was to assess the EPI situation in Togo, particularly as concerns immunization coverage, program and logistics management, with a view to developing recommendations for long-term improvement of its performance. According to the results of this review, the highlights concern: - Generally satisfactory immunization coverage (BCG: 92%; DTP1: 88%; DTP33: 76%; MV: 64%; TT2: 80%) with a protection rate of children at birth of 58%. - Advances in terms of program coordination, micro-planning, vaccine availability and management, staff training, monitoring, immunization safety and strengthening the cold chain in a context of increased scarcity associated with the crisis situation the country is experiencing. - Crucial support from partners (WHO, UNICEF, AMP, GAVI, Rotary International, ARIVA, Plan-Togo) financially, physically and technically, as well as the commitment of the Togo State, expressed mainly through purchase of EPI vaccines with its own resources since 2004. The weaknesses identified by the review concern: - Inadequate supervision of staff. - High proportions of invalid doses both for infant vaccinations (14% for MV, 7% for DTP3, 3% forDT1P1) and tetanus vaccinations (15% for TT3, 12% for TT4). - Losses in the immunization series which are shown in high drop-out rates (25% BCG/MV drop-out and 12% for the DTP1/DTP3 series) and a low proportion of fully immunized children (35%). - Inadequate staff training in the field of maintaining the cold chain. The review recommends: - Finalizing the process of developing the cMYP, which will be a necessary lobbying tool for mobilizing resources. - Increasing program funding through increasing the government’s contribution and that of the partners, and active consultation with the other sectors with a view to taking advantage of the funds that will come out of the “Heavily Indebted Poor Countries initiative” (HIPC). - Continuing efforts to increase personnel numbers for EPI central coordination, to implement the ACD [Reach Each District] approach, to improve data quality and in staff training and supervision, in order to improve their skills and the quality of their services. - Increasing cold chain equipment at the central and operational levels, coupled with defining, popularizing and complying with the cold chain equipment standards at all levels, as well as strengthening preventive maintenance. - The Health Ministry authorities to lobby the Government to carry out a general census of the population very soon in order to resolve the problem of unreliable demographic data. - Developing and implementing a specific communication and social mobilization plan in support of a routine Expanded Program on Immunization.

1.1.4. ICC meetings

How many times did the ICC meet in 2006? Please attach the minutes.

Are community organizations members of the ICC and if so, which ones?

The ICC met four times in 2006, namely 8 March, 17 May, 22 June and 2 November. One community organization is a member of the ICC, namely the Togo Red Cross.

1.2. GAVI Alliance support for new vaccines and under-used vaccines (UV)

#### Receipt of new vaccines and under-used vaccines in 2006

When was the new vaccine or under-used vaccine introduced? Please specify any change in doses per vial and in vaccine form (for example, from DTP + monovalent Hep B to DTP-HepB) and the receipt dates for vaccines received in 2006.

| Vaccines | Size of vials | Doses | Date of introduction | Date of receipt (2006) |
| --- | --- | --- | --- | --- |
| Yellow fever vaccine | 10 doses | 148 600 | December 2004 | 6/04/206 |

Please report any problems encountered.

No problem to report concerning receipt of this yellow fever vaccine.

#### Main activities

Please give an overview of the main activities that have been carried out or which will be carried out as regards introduction, gradual use, strengthening of services etc and describe any problems encountered.

A plan for introducing viral hepatitis B vaccine into the routine EPI, as well as a support proposal, were developed and submitted to GAVI and the Vaccine Fund in October 2005. This request for support was conditionally approved by GAVI. In 2006 a new support proposal, which takes account of the requirements as regards analysis of the program’s current and future costs as well as funding sources, was submitted to GAVI, and for the second time examination of it resulted in conditional approval. Following this result, the process of a new submission concerning the pentavalent vaccine (DTP-HepB-Hib) began based on the 2007-2011 comprehensive Multi-Year Plan ratified in October 2006, and taking account of GAVI’s new policy concerning vaccine co-funding. This process will result in a new submission during the next presentation cycle in 2007.

#### Use of financial support from the GAVI funding entity (USD 100,000) for introduction of the new vaccine

These funds were received on: In 2006 we did not introduce any new vaccines and consequently we did not receive funds for the introduction of new vaccines.

Please account for the used portion of the USD 100,000, the activities undertaken and problems encountered, such as delayed access to the funds for carrying out the program.

    - Vaccine management assessment/efficient vaccine storage management.

The last Vaccines Management Assessment (VMA)/assessment of Efficient Vaccine Storage Management (EVSM) was conducted on ____________.

Please summarize the main recommendations of the VMA/EVSM.

The Vaccine Management Assessment has not yet been done in Togo.

Was an action plan drawn up following the VMA/EVSM? Yes/No

Please summarize the main activities in the EVSM plan and the activities designed to implement the recommendations.

NOT APPLICABLE

The next VMA/EVSM will be conducted on: _____________

## * All countries will be required to conduct a VMA/EVSM during the second year of support for new vaccines in GAVI Phase 2.

## 1.3 Injection Safety (IS)

#### Receipt of support for injection safety

Received in funds/in kind

Please give an account of the support received from the GAVI Alliance in 2006 for injection safety (add lines if necessary).

| Equipment for injection safety | Quantity | Date of receipt |
| --- | --- | --- |
| 0.5 CC AD SYRINGES | 212 000 | 13/04/2006 |
| 0.05 CC AD SYRINGES | 358 400 | 4 May 2006 |
| 5 CC DILUTION SYRINGES | 53 000 | 13/04/2006 |
| 5 CC DILUTION SYRINGES | 37 000 | 4 May 2006 |
| 5 liter sharps boxes | 1750 | 13/04/2006 |

AD SYRINGE: Auto-destruct syringe; DS: Dilution syringe;

Please report any problems encountered.

There is no problem to report in relation to the receipt and use of this equipment.

#### Progress of the transition plan for safe injections and safe management of sharps waste.

If the support has ended, please specify how the injection safety equipment is funded.

Support for injection safety finished at the end of 2005. Since 2006 the injection safety equipment has been funded through State resources.

#### Please give an account of the procedures for sharps waste disposal.

Under the Expanded Program on Immunization, the injection safety policy was developed, adopted and distributed in April 2002. It provides national guidelines on the disposal of sharps waste. Generally, these guidelines are properly applied in the immunization centers. According to these guidelines: - Any injection equipment, including auto-destruct devices, must be disposed of immediately after use in a sharps box that is resistant to perforation by needles and other sharp objects. - The needle must never be re-capped or taken out of the syringe; the entire device must be put in the sharps box immediately after use. - An system of inspection and monitoring of distribution, use and destruction of injection equipment has been set up through the monthly data reporting. - Other immunization waste (caps, packaging, cotton wool) are dealt with appropriately in order not to pollute the environment. - All used injection equipment must be correctly collected and destroyed: - The method advocated for destruction of full sharps boxes is incineration, using a high-temperature incinerator (> 800° C); there is at least one available in good condition in each health district.

#### Please report any problems encountered during implementation of the transition plan for safe injections and safe management of sharps waste.

The main problem encountered concerns maintenance of the De MONFORT incinerators. The first (140 incinerators) built in 2001 had breakdowns due to cracks and chimney destruction. About 30 were restored in 2004 with new tougher materials and the cMYP provides for restoration of the rest of the broken down incinerators and construction of new ones, as well as replacement of the equipment for staff responsible for incineration.

#### Statement on the use of GAVI Alliance support in 2006 for injection safety (if such support has been received as a funding contribution).

The main activity sectors below were funded (specify the amount) during the past year thanks to the GAVI Alliance support for injection safety:

NOT APPLICABLE

# 2. 	Co-funding of vaccines, immunization funding and financial viability

Important note: As part of Phase 2 of the GAVI Alliance, all countries are supposed to co-fund the introduction of new vaccines from the start of Phase 2 (except for introduction of the second dose of vaccine against measles in routine immunization). The Annual Progress Report has been changed to try and observe what happened in countries after the GAVI Alliance’s new policies concerning vaccine co-funding were implemented. We are asking countries to fill in three new information tables and to answer questions about what happened in your country.

The objective of Table 2 is to understand the trend in overall expenses concerning immunization and the financial context.

Table 3 was designed to help GAVI Alliance grasp, at the country scale, the co-funding of vaccines allocated by GAVI, both from the point of view of the doses and the financial amounts. If GAVI Alliance allocated more than one new vaccine to your country as part of Phase 2, please fill in a separate table for each new co-funded vaccine.

The objective of the questions relating to Table 4 is to understand, at the country scale, the procedures for integrating co-funding requirements into national mechanisms for planning and budgeting.  The bulk of the information required can be extracted from the comprehensive multi-year plan, from your country’s proposal to GAVI and from the Alliance’s confirmation letter. Please report on all years until the end of your cMYP. The co-funding levels may be calculated with the Excel spreadsheet supplied for calculation of the need for vaccines.

| Table 2: Total immunization expenses and immunization funding trends. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Total immunization expenses and immunization funding trends | 2006 | 2007 | 2008 | 2009 | 2010 |
| Immunization expenses |  |  |  |  |  |
| Vaccines |  |  |  |  |  |
| Injection equipment |  |  |  |  |  |
| Personnel |  |  |  |  |  |
| Other operational expenses |  |  |  |  |  |
| Cold chain equipment |  |  |  |  |  |
| Vehicles |  |  |  |  |  |
| Other |  |  |  |  |  |
| Total immunization expenses |  |  |  |  |  |
| Total government expenses for health |  |  |  |  |  |
| Immunization funding |  |  |  |  |  |
| Government |  |  |  |  |  |
| GAVI |  |  |  |  |  |
| UNICEF |  |  |  |  |  |
| WHO |  |  |  |  |  |
| World Bank |  |  |  |  |  |
| Other (please specify) |  |  |  |  |  |
| Other (please specify) |  |  |  |  |  |
| Total funding |  |  |  |  |  |

| Table 3a: Co-funding of vaccines by your country |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| For the first vaccine allocated by GAVI, specify the vaccine concerned. DTP-Hep B-Hib |  |  |  |  |  |  |
| Actual and planned co-funding by your country | 2006 | 2007 | 2008 | 2009 |  | 2010 |
| Total quantity of doses co-funded by your country |  |  |  |  |  |  |
| Total amount of co-funding by your country |  |  |  |  |  |  |
| Including the share provided by |  |  |  |  |  |  |
| Government |  |  |  |  |  |  |
| Basket/Pooling Funding/SWAp |  |  |  |  |  |  |
| Other (please specify) |  |  |  |  |  |  |
| Other (please specify) |  |  |  |  |  |  |
| Other (please specify) |  |  |  |  |  |  |
| Total co-funding |  |  |  |  |  |  |

| Table 3b: Co-funding of vaccines by your country |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| For the second vaccine allocated by GAVI, specify the vaccine concerned. DTP-Hep B) |  |  |  |  |  |  |
| Actual and planned co-funding by your country | 2006 | 2007 | 2008 | 2009 |  | 2010 |
| Total quantity of doses co-funded by your country |  |  |  |  |  |  |
| Total amount of co-funding by your country |  |  |  |  |  |  |
| Including the share provided by |  |  |  |  |  |  |
| Government |  |  |  |  |  |  |
| Basket/Pooling Funding/SWAp |  |  |  |  |  |  |
| Other (please specify) |  |  |  |  |  |  |
| Other (please specify) |  |  |  |  |  |  |
| Other (please specify) |  |  |  |  |  |  |
| Total co-funding |  |  |  |  |  |  |

| Table 3c: Co-funding of vaccines by your country |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| For the third vaccine allocated by GAVI, specify the vaccine concerned. DTP-Hep B) |  |  |  |  |  |  |
| Actual and planned co-funding by your country | 2006 | 2007 | 2008 | 2009 |  | 2010 |
| Total quantity of doses co-funded by your country |  |  |  |  |  |  |
| Total amount of co-funding by your country |  |  |  |  |  |  |
| Including the share provided by |  |  |  |  |  |  |
| Government |  |  |  |  |  |  |
| Basket/Pooling Funding/SWAp |  |  |  |  |  |  |
| Other (please specify) |  |  |  |  |  |  |
| Other (please specify) |  |  |  |  |  |  |
| Other (please specify) |  |  |  |  |  |  |
| Total co-funding |  |  |  |  |  |  |

| Table 4: Questions relating to the introduction of vaccine co-funding. |  |  |  |
| --- | --- | --- | --- |
| Q. 1: Were there differences between the proposed payment schedules and the actual schedules in the year covered by the report? |  |  |  |
| Schedule of co-funded payments | Proposed payment schedule | Dates of actual payments in the year covered by the report | Delay in transfer of co-funded payments |
|  | (month/year) | (day/month) | (days) |
| 1st vaccine allocated (specify) |  |  |  |
| 2nd vaccine allocated (specify) |  |  |  |
| 3rd vaccine allocated (specify) |  |  |  |
| Q. 2: What mechanisms for purchasing vaccines are currently used in your country? |  |  |  |
|  | If so, tick here | List the relevant vaccines | Funding sources |
| Government purchases – International calls for tenders |  |  |  |
| Government purchases - Other |  |  |  |
| UNICEF |  |  |  |
| PAHO renewable funding |  |  |  |
| Donations |  |  |  |
| Other (specify) |  |  |  |
| Q. 3: Are the co-funding requirements integrated into the national planning and budgeting systems below? |  |  |  |
|  | If so, tick here | List the relevant vaccines |  |
| Budget item for purchase of vaccines |  |  |  |
| National health sector plan |  |  |  |
| National health budget |  |  |  |
| Framework for medium-term expenses |  |  |  |
| SWAp |  |  |  |
| Funding and cost analysis for the cMYP |  |  |  |
| Annual immunization program |  |  |  |
| Other |  |  |  |
| Q. 4: What factors slowed or hindered the raising of resources for vaccine co-funding? |  |  |  |
| 1. |  |  |  |
| 2. |  |  |  |
| 3. |  |  |  |
| 4. |  |  |  |
| 5. |  |  |  |
| Q. 5: Do you expect to run into difficulties in co-funding vaccines in future? Which difficulties? |  |  |  |
| 1. |  |  |  |
| 2. |  |  |  |
| 3. |  |  |  |
| 4. |  |  |  |
| 5. |  |  |  |

3.  	Application for new vaccines and under-used vaccines for 2008

Part 3 concerns the application for new vaccines and under-used vaccines and injection safety for 2008.

- Updated immunization objectives

Confirm/update the basic data approved in your country’s proposal.  The figures must correspond to those given in the joint WHO/UNICEF report forms.  Any change and/or discrepancy MUST be justified in the box provided for this purpose (3.2). The objectives for the coming years MUST be specified.

Please supply in the box below evidence of any changes in the reference bases, objectives, loss rates, vaccine forms etc in relation to the plan previously approved, as well as differences in the figures supplied in relation to those supplied in the joint WHO/UNICEF report forms.

| Table 7: Update of achievements concerning immunization and annual objectives. Please supply the figures indicated in the joint 2006 WHO/UNICEF report, together with the estimates for 2007 and beyond. |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Achievements and objectives |  |  |  |  |  |  |  |  |
|  | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 |
| DENOMINATORS |  |  |  |  |  |  |  |  |  |
| Births | 234 540 | 240 165 | 245 929 | 251 979 | 258 177 | 264 529 | 271 036 | 277 704 | 284 535 |
| Infant deaths | 26 060 | 19 213 | 19 674 | 12 038 | 11 459 | 10 907 | 10 382 | 9 751 | 9 080 |
| Surviving infants | 208 480 | 220 952 | 226 255 | 239 941 | 246 718 | 253 622 | 260 654 | 267 952 | 275 455 |
| IMMUNIZATION COVERAGE |  |  |  |  |  |  |  |  |  |
| BCG | 96% | 96% | 95% | 95% | 96% | 96% | 97% | 97% | 97% |
| DTP 1 (alone or in combination) | 91% | 91% | 90% | 93% | 94% | 95% | 95% | 95% | 97% |
| DTP3 (alone or in combination) | 82% | 87% | 83% | 85% | 90% | 90% | 95% | 95% | 95% |
| MV | 70% | 83% | 71% | 76% | 80% | 85% | 90% | 90% | 90% |
| YFV | 56% | 81% | 71% | 76% | 80% | 85% | 90% | 90% | 90% |
| TT2+ | 70% | 80% | 80% | 83% | 84% | 85% | 85% | 85% | 85% |
| NUMBER OF |  |  |  |  |  |  |  |  |  |
| Children immunized in 2006 (JRF)/ to be immunized in 2007 and beyond with the 1st dose of DTP (DTP1)* | 188 817 | 201 791 | 203 629 | 223 145 | 231 916 | 240 941 | 247 621 | 254 555 | 267 191 |
| Children immunized in 2006 (JRF)/ to be immunized in 2007 and beyond with the 3rd dose of DTP (DTP3)* | 171 779 | 192 042 | 187 792 | 203 950 | 222 048 | 228 260 | 247 622 | 254 555 | 261 682 |

|  | Achievements and objectives |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 |
| NEW VACCINES** YFV |  |  |  |  |  |  |  |  |  |
| Children immunized in 2006 (JRF)/ to be immunized in 2007 and beyond with YFV | 117 394 | 179 074 | 160 641 | 182 355 | 197 374 | 215 579 | 234 589 | 241 157 | 247 910 |
| Loss rates in 2006 and expected rates in 2007 and beyond*** for YFV | 12% | 17% | 25% | 25% | 20% | 20% | 20% | 20% | 20% |
| NEW VACCINES** DTP-HepB-Hib |  |  |  |  |  |  |  |  |  |
| Children immunized in 2006 (JRF)/ to be immunized in 2007 and beyond with the 1st dose |  |  |  | 223 145 | 231 916 | 240 941 | 247 621 | 254 555 | 267 191 |
| Children immunized in 2006 (JRF)/ to be immunized in 2007 and beyond with the 3rd dose |  |  |  | 203 950 | 222 048 | 228 260 | 247 622 | 254 555 | 261 682 |
| Loss rates in 2006 and expected rates in 2007 and beyond*** for the pentavalent vaccine |  |  |  | 20% | 15% | 15% | 10% | 10% | 10% |
| INJECTION SAFETY**** |  |  |  |  |  |  |  |  |  |
| Pregnant women immunized/ to be immunized with TT | 163 101 | 192 893 | 196 743 | 209 143 | 216 869 | 224 850 | 230 381 | 236 048 | 241 855 |
| Infants immunized/to be immunized with BCG | 199 173 | 213 045 | 214 942 | 227 944 | 236 849 | 243 477 | 252 834 | 259 913 | 267 191 |
| Infants immunized/to be immunized against measles | 146 711 | 182 545 | 160 641 | 182 355 | 197 374 | 215 579 | 234 589 | 241 157 | 247 910 |

* Indicate the exact number of children immunized during the past years and the updated objectives (with DTP alone or in conjugated form).

**Use three lines (as indicated in the chapter headed NEW VACCINES) for each new vaccine introduced.

***Indicate the loss rates actually recorded during the past years.

****Insert the lines needed.

  - Confirmed/revised application for new vaccines (to be forwarded to the UNICEF Supply Division) for 2007

In the event of a change in vaccine form or an increase in your need, please indicate below if the UNICEF Supply Division has assured you that the new quantity/form of supply is available.

No change has occurred in comparison with the last submission.

#### Please supply the duly completed Excel spreadsheet for calculating the need for vaccines and summarize it in Table 6 below. For the calculation, use the same objectives as in Table 5.

Table 6. Estimated quantity of DTP-Hep B-Hib vaccine doses (2-dose pentavalent vial)

| Vaccine: DTP-Hep B-Hib | 2008 | 2009 | 2010 |
| --- | --- | --- | --- |
| Total number of doses requested | 928 841 | 779 582 | 995 615 |
| Doses to be supplied by GAVI | 886 834 | 739 978 | 942 419 |
| Doses to be purchased by the country | 42 008 | 39 604 | 53 196 |
| Co-payment in USD/dose | 0,15 | 0,15 | 0,15 |
| Total co-payment (in USD) | 139 326 | 116 937 | 149 342 |

* Based on the GAVI co-funding policy, the country grouping and the order in which the vaccines are introduced.

Remarks

- Gradual introduction: Please adjust the number of targeted children who will receive the new vaccines, if gradual introduction is planned. If the target number for the HepB3 and Hib3 is different from that of DTP3, please give reasons for the difference.

- Vaccine losses: Countries are supposed to plan for a maximum loss of 50% for a freeze-dried vaccine in vials of 10 or 20 doses, 25% for a liquid vaccine in vials of 10 or 20 doses and 10% for all vaccines (liquid or freeze-dried) in vials of 1 or 2 doses.

- Buffer inventory: The buffer inventory is recalculated each year as 25% of current vaccine requirements.

- Expected vaccines in stock at the start of 2008: This number is calculated by counting the current balance of vaccines in stock, including the buffer inventory balance. Write zero if all vaccines supplied during the current year (including the buffer inventory) will probably be used up before the start of the following year. Countries that have no or very little vaccine in stock are asked to provide evidence of vaccine use.

- Auto-destruct syringe; A loss factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding vaccine losses.

- Reconstitution syringes: These are only used for freeze-dried vaccines. Write zero for the other vaccines.

- Sharps containers: A multiplication factor of 1.11 is applied to sharps containers to take account of areas where a box will be used for fewer than 100 syringes.

Table 7: Loss rates and factors

| Vaccine loss rates | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent loss factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

#### Confirmed/revised support application for support for injection safety for 2008

Table 8a: Table 8: Estimated supplies for immunization safety for the next two years with BCG

|  |  | #### Formula | #### For 2008 | #### For 2009 |
| --- | --- | --- | --- | --- |
| #### A | #### Number of children targeted for BCG immunization | #### # | 227 944 | 236 849 |
| #### B | #### Number of doses per child | #### # | 1 | 1 |
| #### C | #### Number of doses of BCG | #### A x B | 227 944 | 236 849 |
| #### D | #### Auto-destruct syringes (+10% of losses) | #### C x 1.11 | 253 018 | 262 902 |
| #### E | #### Buffer inventory of auto-destruct syringes (2) | #### C x 0.25 | 56 986 | 59 212 |
| #### F | #### Auto-destruct syringes total | #### D + E | 310 004 | 322 115 |
| #### G | #### Number of doses per vial | #### # | 20 | 20 |
| #### H | #### Vaccine loss factor (3) | #### 2 or 1.6 | 2 | 2 |
| #### I | #### Number of reconstitution syringes (+10% of losses) (4) | #### C x H x 1.11/G | 25 302 | 26 290 |
| #### J | #### Number of sharps containers (+10% more) | #### (F + I) x 1.11/100 | 3 722 | 3 867 |

Table 8b: Estimated supplies for immunization safety for the next two years with MV

|  |  | #### Formula | #### For 2008 | #### For 2009 |
| --- | --- | --- | --- | --- |
| #### A | #### Number of children targeted for DTP immunization [??MV??] | #### # | 182 355 | 197 374 |
| #### B | #### Number of doses per child | #### # | 1 | 1 |
| #### C | #### Number of doses of…. | #### A x B | 182 355 | 197 374 |
| #### D | #### Auto-destruct syringes (+10% of losses) | #### C x 1.11 | 202 414 | 219 085 |
| #### E | #### Buffer inventory of auto-destruct syringes (2) | #### C x 0.25 | 45 589 | 49 344 |
| #### F | #### Auto-destruct syringes total | #### D + E | 248 003 | 268 429 |
| #### G | #### Number of doses per vial | #### # | 10 | 10 |
| #### H | #### Vaccine loss factor (3) | #### 2 or 1.6 | 1,6 | 1,6 |
| #### I | #### Number of reconstitution syringes (+10% of losses) (4) | #### C x H x 1.11/G | 32 386 | 35 054 |
| #### J | #### Number of sharps containers (+10% more) | #### (F + I) x 1.11/100 | 3 112 | 3 369 |

Table 8c: Estimated supplies for immunization safety for the next two years with (pentavalent) DTP-Hep B-Hib

|  |  | #### Formula | #### For 2008 | #### For 2009 |
| --- | --- | --- | --- | --- |
| #### A | #### Number of children targeted for DTP-HepB-Hib immunization | #### # | 223 145 | 231 916 |
| #### B | #### Number of doses per child | #### # | 3 | 3 |
| #### C | #### Number of doses of DTP-HepB-Hib | #### A x B | 669 435 | 695 748 |
| #### D | #### Auto-destruct syringes (+10% of losses) | #### C x 1.11 | 743 073 | 772 280 |
| #### E | #### Buffer inventory of auto-destruct syringes (2) | #### C x 0.25 | 167 359 | 173 937 |
| #### F | #### Auto-destruct syringes total | #### D + E | 910 432 | 946 217 |
| #### G | #### Number of doses per vial | #### # | 2 | 2 |
| #### H | #### Vaccine loss factor |  | 1,11 | 1,11 |
| #### I | #### Number of reconstitution syringes (+10% of losses) (4) | #### C x H x 1.11/G | 0 | 0 |
| #### J | #### Number of sharps containers (+10% more) | #### (F + I) x 1.11/100 | 10 106 | 10 503 |

Table 8d: Estimated supplies for immunization safety for the next two years with YFV

|  |  | #### Formula | #### For 2008 | #### For 2009 |
| --- | --- | --- | --- | --- |
| #### A | #### Number of children targeted for YFV immunization | #### # | 182 355 | 197374 |
| #### B | #### Number of doses per child | #### # | 1 | 1 |
| #### C | #### Number of doses of YFV | #### A x B | 182 355 | 197374 |
| #### D | #### Auto-destruct syringes (+10% of losses) | #### C x 1.11 | 202414 | 219 085 |
| #### E | #### Buffer inventory of auto-destruct syringes (2) | #### C x 0.25 | 45589 | 49 344 |
| #### F | #### Auto-destruct syringes total | #### D + E | 248 003 | 268 429 |
| #### G | #### Number of doses per vial | #### # | 10 | 10 |
| #### H | #### Vaccine loss factor (3) | #### 2 or 1.6 | 1,6 | 1,6 |
| #### I | #### Number of reconstitution syringes (+10% of losses) (4) | #### C x H x 1.11/G | 32 386 | 35 054 |
| #### J | #### Number of sharps containers (+10% more) | #### (F + I) x 1.11/100 | 3 112 | 3 369 |

Table 8e: Estimated supplies for immunization safety for the next two years with TT

|  |  | #### Formula | #### For 2008 | #### For 2009 |
| --- | --- | --- | --- | --- |
| #### A | #### Number of pregnant women targeted) (1) | #### # | 209 143 | 216 869 |
| #### B | #### Number of doses per pregnant woman | #### # | 2 | 2 |
| #### C | #### Number of doses of TT | #### A x B | 418 286 | 433 738 |
| #### D | #### Auto-destruct syringes (+10% of losses) | #### C x 1.11 | 464 297 | 481449 |
| #### E | #### Buffer inventory of auto-destruct syringes (2) | #### C x 0.25 | 104 572 | 108 435 |
| #### F | #### Auto-destruct syringes total | #### D + E | 568 869 | 589 884 |
| #### G | #### Number of doses per vial | #### # | 20 | 20 |
| #### H | #### Vaccine loss factor |  | 1,12 | 1,11 |
| #### I | #### Number of reconstitution syringes (+10% of losses) (4) | #### C x H x 1.11/G | 0 | 0 |
| #### J | #### Number of sharps containers (+10% more) | #### (F + I) x 1.11/100 | 6 314 | 6 548 |

#### 1 Contribute up to 2 doses maximum for pregnant women (estimate supplied by the births total).

2 The buffer inventory of vaccines and auto-destruct syringes is set at 25%. This stock is added to the initial stock of doses required to introduce immunization to any geographic area. Write zero for the other years.

3 The standard loss factor will be used to calculate the reconstitution syringes. It will be 2 for BCG and 1.6 for measles and yellow fever.

4 Only for freeze-dried vaccines. Write zero for the other vaccines.

#### If the quantity of the current application differs from that specified in the GAVI approval letter, please explain why.

# 4. Health system strengthening (HSS)

This part must only be filled in by countries for which the proposal for HSS support has been approved. It will serve as an initial report enabling release of funds for 2008. Consequently, countries are required to account for all activities undertaken in 2007.

# Health system strengthening begun on: _________________

The Health System Strengthening under way will end on: _____________

# Funds received in 2007: 	Yes/No

If yes, total amount: 	USD

Funds disbursed to date:  				USD

Balance of the payment remaining: 				USD

Amount requested for disbursement in 2008 	USD

Are the funds in accordance with the budget (do they appear in the Health Ministry and the Finance Ministry budget)?  Yes/No

If not, please give reasons why. How will you ensure that the funds are in accordance with the budget?

Please supply a succinct summary of the HSS support program covering the main activities carried out, and mentioning if the funds were disbursed in accordance with the implementation plan, the main achievements (especially the impact on the health services programs, particularly the immunization program), the problems encountered and the solutions provided or planned, and any other important information that you wish to forward to GAVI.   You can supply more detailed information to indicate, for example, if the activities were implemented in accordance with the implementation provided for in Table 10.

Are community organizations taking part in implementing the HSS proposal? If so, explain how.

In the event that you wish to change the disbursement schedule as defined in the proposal, please give reasons why and supply evidence of the change in your disbursement application. Expenses can be broken down to show more detail in Table 9.

Please attach the minutes of the HSCC meeting(s) where the disbursement of funds and the application for the following tranche were examined.  Kindly attach the most recent health sector assessment report and the auditor’s report for the account into which the HSS funds were transferred.  This is a condition for the release of funds for 2008.

| Table 9: HSS Expenses in 2007 (Please fill in the boxes for expenses associated with HSS activities and your application for 2008. Where the application for 2008 has changed, please give reasons why in the statement above). |  |  |  |
| --- | --- | --- | --- |
| Support sector | 2007 (Expenses) | 2007 (Balance) | 2008 (Application) |
| Cost of activities |  |  |  |
| Objective 1 |  |  |  |
| Activity 1.1 |  |  |  |
| Activity 1.2 |  |  |  |
| Activity 1.3 |  |  |  |
| Activity 1.4 |  |  |  |
| Objective 2 |  |  |  |
| Activity 2.1 |  |  |  |
| Activity 2.2 |  |  |  |
| Activity 2.3 |  |  |  |
| Activity 2.4 |  |  |  |
| Objective 3 |  |  |  |
| Activity 3.1 |  |  |  |
| Activity 3.2 |  |  |  |
| Activity 3.3 |  |  |  |
| Activity 3.4 |  |  |  |
| Support costs |  |  |  |
| Management costs |  |  |  |
| Support costs for monitoring and assessment |  |  |  |
| Technical assistance |  |  |  |
| TOTAL COSTS |  |  |  |

| Table 10. HSS Activities in 2007 (Please provide an account of activities conducted in 2007) |  |
| --- | --- |
| Main activities | 2007 |
| Objective 1 |  |
| Activity 1.1 |  |
| Activity 1.2 |  |
| Activity 1.3 |  |
| Activity 1.4 |  |
| Objective 2 |  |
| Activity 2.1 |  |
| Activity 2.2 |  |
| Activity 2.3 |  |
| Activity 2.4 |  |
| Objective 3 |  |
| Activity 3.1 |  |
| Activity 3.2 |  |
| Activity 3.3 |  |
| Activity 3.4 |  |

| Table 11. Please update the indicators used as a reference basis. |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Indicator | Data source | Reference base value | Source | Reference base date | Objective | Cut-off date |
| 1. National coverage with DTP3 (%) |  |  |  |  |  |  |
| 2. Number/% of districts attaining  80% coverage with DTP3 |  |  |  |  |  |  |
| 3. Mortality rate for children under five years of age (per 1000) |  |  |  |  |  |  |
| 4. |  |  |  |  |  |  |
| 5. |  |  |  |  |  |  |
| 6. |  |  |  |  |  |  |

Please describe whether the objectives have been attained, what type of problems you encountered in measuring the indicators, how the monitoring process was strengthened and if changes have been proposed.

# 5.	Points to be checked

Checking the completed form:

| Required point in the form: | Completed | Comments |
| --- | --- | --- |
| Submission date | Yes |  |
| Period for which the report was prepared (preceding calendar year) | Yes |  |
| Government signatures |  |  |
| ICC endorsement |  |  |
| Table 1 completed |  |  |
| Report provided on DQA | Yes |  |
| Report provided on use of USD 100,000 |  |  |
| Report provided on injection safety | Yes |  |
| Report provided on the financial viability plan (FVP) (progress achieved in relation to the country’s FVP indicators) |  |  |
| Table 2 completed |  |  |
| Application for new vaccines completed | Yes |  |
| Revised support application for injection safety provided (where relevant) | Yes |  |
| Report provided on HSS support |  |  |
| ICC minutes attached to the report | Yes |  |
| HSCC minutes, auditor’s report for the account for HSS funds and annual assessment report for the health sector attached to the report. |  |  |

6.  	Comments

ICC/HSCC comments:

For the Expanded Program on Immunization, the key events in 2006 were conduct of the review and development of the 2007-2011 multi-year plan for the program. The implementation of the Reach Each District approach in the 35 health districts, funded by the GAVI fund for immunization services support, WHO, UNICEF, Plan-Togo and the EU’s ADSS project (Appui Décentralisé au Système de Santé [decentralized support for the health system]), led to improvement of the indicators in comparison with 2005. Thus immunization coverage increased for all antigens: from 2005 to 2006, it went from 82% to 87% for DTP3/OPV3, from 95% to 96% for BCG, from 70% to 83% for MV, from 56% to 81% for YFV and from 70% to 80% for TT2+. The drop-out rates for DTP1/DTP3 and BCG/MV also showed improvement, falling respectively from 9% to 5% and from 26% to 14% during the same period. These satisfactory results enabled the country to receive GAVI bonuses. Some major jobs begun in 2006 were unable to be completed during the year due to various constraints and will be completed in 2007. - Construction of new cold rooms (1 positive and 1 negative) for vaccine conservation is underway. - The submission process for the introduction of pentavalent vaccine (DTP-HepB-Hib) in routine child immunization is continuing as part of phase 2 of the GAVI Alliance in the context of new policies concerning vaccine co-funding. - The submission process for support for health system strengthening (HSS) is also continuing. The ICC is delighted with the results obtained and would like to congratulate GAVI, all the partners and the Government for the many forms of support and the fruitful and efficient collaboration which have resulted in a significant improvement in the quality of Togo’s immunization program.

~ End ~

If reference bases are not available, indicate if collection of this data is planned and when it will take place.

The source is important to facilitate access to the data and to check that they match.