Annual Progress Report

(2001-2006)

Submitted by

The Government of

turkmenistan

to the

# Date of submission: _May 2007________

Annual progress report (this report reports on activities in 2006 and specifies requests for 2008, Jan.-Dec.)

*Unless otherwise specified, documents may be shared with GAVI partners and collaborators as well as the general public.

Signatures Page for ISS, INS and NVS

For the Government of Turkmenistan

| Ministry of Health: | Ministry of Finance: |
| --- | --- |
| Title: Annamurat Orazov – Deputy Minister, Head of the State Sanitary and Epidemiological Service of the Ministry of Health and Medical Industry of Turkmenistan | Title: …………………………………… |
| Signature: ……….…………………………………… | Signature: ………………………………… |
| Date: …………………………………… | Date: …………………………………… |

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this report. Signature of endorsement of this document does not imply any financial (or legal) commitment on the part of the partner agency or individual.

| Name/Title | Agency/Organisation | Signature | Date |
| --- | --- | --- | --- |
| Annamurat Orazov – Deputy Minister, Head of the State Sanitary and Epidemiological Service – ICC Chairman | The State Sanitary and Epidemiological Service of the Ministry of Health and Medical Industry |  |  |
| Maral Aksakova – Acting as Head of Epidemiological Surveillance and Parasitology Department, SES – ICC Secretary | The State Sanitary and Epidemiological Service of the Ministry of Health and Medical Industry |  |  |
| Eziz Hellenov – Programme Manager | UNFPA Representation in Turkmenistan |  |  |
| Ayadil Saparbekov – Project Officer | UNICEF Representation in Turkmenistan |  |  |
| Elena Samarkina- Health Manager | USAID Representation in Turkmenistan |  |  |
| Bahtygul Karryeva- – Head of WHO in Turkmenistan Туркменистане | WHO Representation in Turkmenistan |  |  |
| Raisa Magerramova – Head of Department | National Institute of Statistics and Forecast Turkmenmillihasabat |  |  |

Progress Report Form:  Table of Contents

# Report on progress made during 2001-2006

    - ICC Meetings

  - GAVI Alliance New and Under-used Vaccines (NVS)

1.2.1	Receipt of new and under-used vaccines

1.2.2	Major activities

    - Evaluation of Vaccine Management System

1.3		Injection Safety (INS)

    - Receipt of injection safety support

    - Progress of transition plan for safe injections and safe management of sharps waste

- Checklist

- Comments

Text boxes supplied in this report are meant only to be used as guides.  Please feel free to add text beyond the space provided.

# 1.  	Report on progress made during 2001- 2006

1.1.4. ICC meetings

How many times did the ICC meet in 2006? Please attach all minutes.

Are any Civil Society Organizations members of the ICC and if yes, which ones?

In 2006 ICC meetings were held 4 times. The Minutes of the meetings are attached. Members of the Civil Society Organizations are not included into the ICC.

1.2. GAVI Alliance New & Under-used Vaccines Support (NVS)

#### Receipt of new and under-used vaccines during 2006

When was the new and under-used vaccine introduced? Please include change in doses per vial and change in presentation, (e.g. DTP + HepB mono to DTP-HepB) and dates shipment were received in 2006.

| Vaccine | Vials size | Doses | Date of Introduction | Date shipment received (2006) |
| --- | --- | --- | --- | --- |
| Hepatitis B vaccine | 1-dose | 207 700 | 2002 | 21.01.2006 - 69300 doses 28.05.2006 - 69200 doses 20.09.2006 – 69200 doses |
| Hepatitis B vaccine | 10-dose | 259 600 | 2002 | 06.02.2006 - 86 600 doses 28.05.2006 - 86 500 doses 20.09.2006 – 86 500 doses |

Please report on any problems encountered.

All vaccines were delivered on time and in good state.

#### Major activities

Please outline major activities that have been or will be undertaken, in relation to, introduction, phasing-in, service strengthening, etc. and report on problems encountered.

Within the period of 2001-2006: - A New National Immunoprophylaxis Programme for 2003-2020 was developed and introduced and a relevant Order was issued. In accordance with WHO recommendations a vaccination calendar was updated; - Since 2002 a new vaccine had been introduced. A 3-dose virus Hepatitis B vaccination was introduced into the National Calendar of preventive vaccination; - Since 2004 a number of vaccinations against poliomyelitis in the National Vaccination Calendar had been reduced from 7 to 5 doses (including zero one); - possibilities of new and combined vaccine introduction provided; - indications for children vaccination expended; - injection sites changed; - Open Vial Policy introduced in all places; - a policy to store and transport cold-sensitive vaccines revised; - training of health workers (epidemiologists, immunologists, neonatologists, family doctors and nurses, vaccination nurses) on safe immunization practices annually conducted; - in accordance with Agreement on Vaccine Independence between the Ministry of health and medical Industry and UNICEF vaccines for children vaccination and re-vaccination procured and delivered; - regular epidemiological surveillance of vaccine-preventable disease conducted, with monthly statistical reporting on prevalence and active surveillance of AFP within the framework of sustainability of the country’s status as a polio-free country; - epidemiological surveillance and monitoring of the immunization programme implementation improved at national and sub-national levels through local area network between the Center and velayats (provinces). From 1st January 2007a combined MMR vaccine against measles, mumps and rubella will be introduced; Due to termination of GAVI Alliance support to provide virus Hepatitis vaccine and injection equipment a plan for gradual transfer to full government financing has been developed. The Financial Plan for 2006-2009 has been approved and ensured in the Memorandum and Agreement between the Government of Turkmenistan and UNICEF. The plan also provides for introduction of a new combined vaccine against measles, mumps and rubella and full provision with injection materials (for all immunization, including re-vaccination of the elder ages.

    - Effective Vaccine Store Management/Vaccine Management Assessment

The last Effective Vaccine Store Management (EVSM)/Vaccine Management Assessment (VMA) was conducted by the WHO consultant in February 2004.

Please summarize the major recommendations from the EVSM/VMA

1.Adopt a model quality plan and introduce new provisions into the national regulatory documents; 2.Develop standard working procedures on acceptance and shipment of vaccines; 3.Include new elements specified in the new model quality plan into training materials; 4.Introduce application of Vaccine Arrival Message; 5. Develop written procedures on activities in emergency situations; 6.Revise fire safety measures; 7. Provide vaccine storage with an alarm system for cold chain equipment; 8. Conduct inventory of storage facilities and vaccine amount.

Was an action plan prepared following the EVSM/VMA: YES

If so, please summarize main activities under the EVSM plan and the activities to address the recommendations.

1.Long-term Immunization plan provides for a gradual replacement of cold chain equipment; 2.Standard working procedures on vaccine acceptance and shipment have been developed: - A Working Group (including specialists from the MH, SES, Medicine and Biological Preparations Registration Center, UNICEF) has been established. It is involved in acceptance of delivered vaccines; - notification on vaccine arrival has been introduced, both for the country of shipment and velayat shipment; - feedback on quality and quantity, vaccine delivery, etc. Has been introduced; - additional documentary requirements have been introduced with reference to vaccine receipt. 3. A written document on measures in emergency situations has been developed and approved; 4. The estimate of storage areas has been conducted on compliance with vaccine amount, both at central and velayat levels; 5. A policy of vaccine storage has been changed regarding temperature of cold packs.

The next EVSM/VMA* will be conducted in: 2007

## *All countries will need to conduct an EVSM/VMA in the second year of new vaccine support approved under GAVI Phase 2.

## 1.3 Injection Safety (INS)

#### Receipt of injection safety support

Received in cash/kind

Please report on receipt of injection safety support provided by the GAVI Alliance during 2006 (add rows as applicable).

| Injection Safety Material | Quantity | Date received |
| --- | --- | --- |
| Syringes for BCG, 0.05 gr | 120 900 | 28.07.2006 – 120 900 units |
| Syringes for Hepatitis B vaccination, 0.5 gr | 472 400 | 03.01.2006 – 236 600 units 23.06.2006 – 235 800 units |
| Syringes for other vaccinations, 0.5 gr | 484 200 | 23.03.2006 – 484 200 units |
| Reconstitution syringes, 5.0 gr | 19 700 | 28.07.2006 - 19 700 units |
| Reconstitution syringes, 2.0 gr | 12 100 | 28.07.2006 - 12 100 units |
| Safety boxes for Hepatitis B vaccination | 5 275 | 03.01.2006 – 2 650 units 28.07.2006 – 2 625 units |
| Safety boxes for other vaccinations | 7 100 | 28.07.2006 – 7 100 units |

Please report on any problems encountered.

In 2006 no problems encountered.

#### Progress of transition plan for safe injections and safe management of sharps waste.

If support has ended, please report how injection safety supplies are funded.

From 2007 injection safety supplies for immunization will be procured at the expense of the governmental budget.

#### Please report how sharps waste is being disposed of.

After being used syringes are collected in the safe disposal boxes. Filled in safe disposal boxes are disposed by the responsible appointed person through burning with further ground disposal pursuant to the instruction.

#### Please report problems encountered during the implementation of the transitional plan for safe injection and sharps waste.

No problem encountered during the implementation of the transitional plan for safe injection and sharp wastes. Since 2002 the Ministry of Health and Medical Industry has supported WHO/UNICEF policy on use of AD syringes and disposable syringes for vaccination, as well as distribution of vaccines jointly with injection equipment and safe disposal boxes. Disposal of injection materials is secured in regulatory documents.

| № | Indicators | Targets |  | Achievements |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | 2004г |  | 2005г |  |  | 2006г |  |  |
| Adequacy of supply of syringes and needles at health facility level |  |  |  |  |  |  |  |  |  |  |  |
| 1 | Proportion of vaccination points equipped with AD syringes for vaccination |  | - target 100% by 2006 |  | 100% |  |  | 100% |  | 100% |  |
| 2 | Proportion of vaccination points equipped with, AD syringes for revaccination | - target 90% by 2005; 100% by 2006 |  | Children under 7 -100% |  |  | Children under 7 -100% |  | Children under 7 -100% (from 2007 to all ages 100% ) |  |  |
| 3 | Proportion of vaccination points equipped with disposal syringes for reconstitution | - target 100% |  | 100% |  |  | 100% |  | 100% |  |  |
| 4 | Proportion of vaccination points (facilities providing vaccination more than twice in a month) having in stock AD syringes for 1 month | - target 100% by 2005 |  | 100% |  |  | 100% |  | 100% |  |  |
| Safe injection protection |  |  |  |  |  |  |  |  |  |  |  |
| 5 | Proportion of vaccination points, supplied with adequate sterile means for injection (integrity of package, expiry date) | - target 100% by 2006 |  | 100% |  | 100% |  |  | 100% |  |  |
| 6 | Proportion of health facilities provided with adequate quantity of safety boxes (one safety box in use, and at least another one on stock) – target | - target 100% by 2005 |  | 100% |  | 100% |  |  | 100% |  |  |
| 7 | Availability of an incinerator or non incineration safe facility | - target 100% by 2005 |  | 100% |  | 100% |  |  | 100% |  |  |
| 8 | Proportion of health facilities with presence of used syringes and needles in garbage, dumping areas or close to the health facility attributable to vaccination. | 0% |  | 0% |  | 0% |  |  | 0% |  |  |
| 9 | Number of abscesses following immunization injection reported |  |  | 0 |  | 0 |  |  | 0 |  |  |
| 10 | Proportion of vaccination injection given in the WHO recommended site | - target 90% by 2006; 99% by 2008 |  | 100% |  | 100% |  |  | 100% |  |  |

# Sources of financing of Hepatitis B vaccine

|  | Annual proportion of vaccines |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 |
| Proportion funded by GAVI/VF (%) | 100% | 100% | 100% | 100% | 100% | 75% |  |  |  |
| Proportion funded by the Government (%) |  |  |  |  |  | 25% | 100% | 100% | 100% |
| Total funding for Hepatitis B vaccine | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |

| Immunization achievements and targets. 2001 - 2006 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Number of | Achievements and targets |  |  |  |  |  |
|  | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 |
| Denominators |  |  |  |  |  |  |
| Births | 85 333 | 85 586 | 86 462 | 89 934 | 90 369 | 97 685 |
| Surviving infants | 87 046 | 86 970 | 87 777 | 88 758 | 87 816 | 90 406 |
| Infants vaccinated with 1st dose of DTP (DTP1) | 82 219 | 85 952 | 81 981 | 87 160 | 86 965 | 89 809 |
| Infants vaccinated with 3rd dose of DTP (DTP3) | 85 646 | 81 297 | 70 805 | 86 273 | 86 940 | 88 344 |
| NEW VACCINES |  |  |  |  |  |  |
| Infants vaccinated with 1st dose of Hepatitis В vaccine |  | 84 885 | 85 597 | 89 664 | 90 236 | 97 407 |
| Infants vaccinated with 3rd dose of Hepatitis В vaccine |  | 82 145 | 82 474 | 85 651 | 87 067 | 88 661 |
| Wastage rate |  | 15,0 | 14,8 | 19,9 | 7,5 | 9,1 |
| Injection Safety |  |  |  |  |  |  |
| Infants vaccinated / to be vaccinated with BCG | 84 008 | 84 885 | 85 424 | 89 125 | 89 454 | 96 903 |
| Infants vaccinated / to be vaccinated with Measles (1st dose) | 87 629 | 73 203 | 82 535 | 78 538 | 84 131 | 84 973 |

# 5.	Checklist

Checklist of completed form:

| Form Requirement: | Completed | Comments |
| --- | --- | --- |
| Date of submission |  |  |
| Reporting Period (consistent with previous calendar year) | 2001-2006 |  |
| Government signatures | Yes |  |
| ICC endorsed | Yes |  |
| ISS reported on |  |  |
| DQA reported on |  |  |
| Reported on use of 100,000 US$ |  |  |
| Injection Safety Reported on |  |  |
| Immunisation Financing & Sustainability Reported on (progress against country IF&S indicators) |  |  |
| New Vaccine Request including co-financing completed and XL sheet attached |  |  |
| Revised request for injection safety completed (where applicable) |  |  |
| HSS reported on |  |  |
| ICC minutes attached to the report | Yes |  |
| HSCC minutes, audit report of account for HSS funds and annual health sector evaluation report attached to report |  |  |

6.  	Comments

ICC/HSCC comments:

~ End ~