May 2002

Partnering with The Vaccine Fund

Annual Progress Report

to the

Global Alliance for Vaccines and Immunization (GAVI)

and

The Vaccine Fund

By the Government of

Republic of Yemen

Date of submission: 29 September 2002 Reporting period: 2001 (previous calendar year) ( Tick only one ) : Inception report Yes  First annual progress report  Financial sustainability plan attached  Second annual progress report  Third annual progress report  Fourth annual progress report  Fifth annual progress report 

# Progress Report

(Number of children immunized with current and new vaccines is collected from the WHO/UNICEF Joint Reporting Form (JRF))

To be filled in by the country for each type of support received from GAVI/The Vaccine Fund.

## Immunization Services

#### 1.1.1	Receipt of immunization services funding                          Date(s) of receipt of funds 30 June 2002

Please report on the progress, including any problems that have been encountered with regard to support for immunization strengthening.  Please describe the mechanism for management of these funds, including the role of the Inter-Agency Co-ordinating Committee (ICC).

The fund received and managed by Ministry of Public Health & Population jointly with ICC, it goes smoothly according to plan

#### 1.1.2	Statement on use of GAVI/The Vaccine Fund immunization services support

In the past year, the following major areas of activities have been funded with the GAVI/The Vaccine Fund contribution.

Not Applicable

| Area of immunization services support | Total amount in US $ | Proportion of funds by level |  |  |
| --- | --- | --- | --- | --- |
|  |  | Central | District | Service delivery |
| Vaccines |  |  |  |  |
| Injection supplies |  |  |  |  |
| Personnel |  |  |  |  |
| Transportation |  |  |  |  |
| Maintenance and overheads |  |  |  |  |
| Training |  |  |  |  |
| IEC / social mobilization |  |  |  |  |
| Monitoring and surveillance |  |  |  |  |
| Vehicles |  |  |  |  |
| Cold chain equipment |  |  |  |  |
| Other …………. (specify) |  |  |  |  |

Please indicate the date(s) of the ICC meeting(s) when the allocation of funds was discussed : ……………………….

#### Immunization Data Quality Audit (DQA) (If it has been implemented in your country)

A plan of action to improve the reporting system based on the recommendations from the DQA, has been prepared

X

## YES                              NO

The plan of action has been discussed and endorsed by the ICC in the meeting of ………………………(Date).

## New & Under-used Vaccines

#### 1.2.1	Receipt of new and under-used vaccines		Date(s) of receipt of vaccines …………………..

Please report on the progress, including starting date of vaccinations and any problems that have been encountered with regard to vaccines and supplies provided by GAVI/The Vaccine Fund.

Not Applicable

#### 1.2.2	Major activities

Please outline what major activities have been or will be undertaken to prepare for new vaccine introduction.

The Major Achievements:

- New vaccine introduction plan developed (Arabic Version)

- Health workers practical manual

- Supervision guidelines and new supervision checklist.

- Safety injection manual developed

- All modules for new regestration books / reporting forms and new vaccination card developed.

- Training workshop conducted from 27 – 31 August targeted all Central and Governorates supervisory teams, the total participants

- 60 supervisors, this workshop funded from the WHO regular budget for EPI Programme.

- All printing materials posted to the press for printing

- Training workshops for Districts supervisors will be commencing in each Governorate starting from 2nd October.

- Health workers training workshops will be conduct during December 2002.

- Distribution of new cold chain equipments on going, during July-August 2002, 97 health centres equipped were 47 equipped with solar refrigerators and 150 new health centres will be equipped with gas refrigerators during Nov-Dec 2002.

#### 1.2.3	Statement on use of GAVI/The Vaccine Fund financial support (US$100,000) for the introduction of the new vaccine

The following major areas of activities have been funded (specify the amount in US$) with the GAVI/The Vaccine Fund support:

The vaccine fund financial support already allocated to cover the following areas:

- Training the all EPI Districts Officers and Directors of Health Offices at districts the total participants 750, the total cost US$ 38,000.

- The total cost required for covering the two years printing needs, the total cost for printing new registers, reporting forms, cards, guidelines and manuals estimated US$ 157,000. The remaining amount US$ 62,000 will be used for covering part of the total printing cost.

## Injection safety

#### 1.3.1	Receipt of injection safety support

Please report on the progress, including any problems that have been encountered with regard to the injection safety support.

Not Applicable

#### Progress of transition plan for safe injections and safe management of sharps waste.

Should include objectives, indicators, main achievements, main constraints and targets for next year.

#### 1.3.3	Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

The following major areas of activities have been funded (specify the amount) with the GAVI/The Vaccine Fund injection safety support in the past year:

Not Applicable

# 2.  Financial sustainability

Inception Report:		Outline steps towards the development of a financial sustainability plan

First Annual Report: 	Submit completed financial sustainability plan

Subsequent Reports:	Summarize progress on financial sustainability

The Financial Sustainability Plan is a document that assesses the key financing challenges facing the national immunization program, and describes the government approach to mobilizing and effectively using financial resources to support medium- and long-term program objectives. The plan will be prepared by the Ministry of Public Heath & Population jointly with the Ministry of Finance, the Inter-Agency Coordinating Committee (ICC). The Financial Sustainability Plan will be including and focusing on self-sufficiency, mobilization of resources, reliabilty of resources and efficient use of resources.

# 3.	Request for new and under-used vaccines for year …………….. ( indicate forthcoming year )

  - Up-dated immunization targets

Confirm/update basic data (= surviving infants, DTP3 targets, New vaccination targets) of the multi-year immunization plan approved with country application: revised Table 4 of approved application form and give reasons for any changes.

| Table 1 : Baseline and annual targets |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of | Baseline and targets |  |  |  |  |  |  |  |
|  | 2000 | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 |
| Births | 640500 | 662620 | 686245 | 711480 | 737835 | 764785 | 792680 | 821063 |
| Infants’ deaths | 48038 | 49697 | 51468 | 53361 | 55338 | 57359 | 59451 | 61063 |
| Surviving infants | 592436 | 612924 | 634777 | 658119 | 682497 | 707426 | 733229 | 760000 |
| Infants vaccinated with DTP3 * | 431185 | 465063 |  |  |  |  |  |  |
| Infants vaccinated with *…(use one row for any new vaccine) |  |  |  |  |  |  |  |  |
| Wastage rate of ** ………….. ( new vaccine) |  |  |  |  |  |  |  |  |

* Indicate actual number of children vaccinated in past years

** Indicate actual wastage rate obtained in past years

If the request for supply for the coming years differs from previously approved plan:

Please indicate the reasons for those changes and, where relevant, the related modifications of targets of children to be vaccinated, wastage rate and type of vaccine. Indicate that UNICEF Supply Division has assured the availability of the new quantity of supply according to new changes. Summarise the related modifications of the activities and of the budgets of the work-plan for introduction of new vaccines and indicate the date of the ICC meeting when the changes were endorsed.

3.2	Confirmed/revised request for new vaccine (to be shared with UNICEF Supply Division) for the year 2003 (indicate forthcoming year)

Table 2: Estimated number of doses of …… vaccine (specify for one presentation only) : (Please repeat this table for any other vaccine presentation requested from

GAVI/The Vaccine Fund

|  |  | Formula | For year 2003 | Remarks |
| --- | --- | --- | --- | --- |
| A | Number of children to receive new vaccine |  | 526495 | - Phasing: Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided - Wastage of vaccines: The country would aim for a maximum wastage rate of 25% for the first year with a plan to gradually reduce it to 15% by the third year. For vaccine in single or two-dose vials the maximum wastage allowance is 5%. No maximum limits have been set for yellow fever vaccine in multi-dose vials. - Buffer stock: The buffer stock for vaccines and AD syringes is set at 25%. This is added to the first stock of doses required to introduce the vaccination in any given geographic area. Write zero under other years. In case of a phased introduction with the buffer stock spread over several years, the formula should read: [ F – number of doses (incl. wastage) received in previous year ] * 0.25. - Anticipated vaccines in stock at start of year… ….: It is calculated by deducting the buffer stock received in previous years from the current balance of vaccines in stock. - AD syringes: A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines. - Reconstitution syringes: it applies only for lyophilized vaccines. Write zero for other vaccines. - Safety boxes: A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes |
| B | Percentage of vaccines requested from The Vaccine Fund | % | 100% |  |
| C | Number of doses per child |  | 3 |  |
| D | Number of doses | A x B/100 x C | 1579485 |  |
| E | Estimated wastage factor | (see list in table 3) | 1.05 |  |
| F | Number of doses ( incl. wastage) | A x C x E x B/100 | 1658459 |  |
| G | Vaccines buffer stock | F x 0.25 | 1.25 |  |
| H | Anticipated vaccines in stock at start of year …. |  |  |  |
| I | Total vaccine doses requested | F + G - H | 2073074 |  |
| J | Number of doses per vial |  | 2 |  |
| K | Number of AD syringes (+ 10% wastage) | ( D + G – H ) x 1.11 | 2191535 |  |
| L | Reconstitution syringes (+ 10% wastage) | I / J x 1.11 | 1150556 |  |
| M | Total of safety boxes (+ 10% of extra need) | ( K + L ) / 100 x 1.11 | 37097 |  |

Table 3 : Wastage rates and factors

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

#### 3.3	Confirmed/revised request for injection safety support

(If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference).

The GAVI letter ref GAVI/102/176/jd dated 27 August 2002 stated the following:

The clarifications provided by Yemen are satisfactory. We are therefore pleased to inform you that your country has been granted support from vaccine fund for Injection Safety as outlined below.

Injection Safety

| Supplies for Injection Safety | 2002 | 2003 |
| --- | --- | --- |
| Number of AD syringes for BCG | 687,000 | 584,400 |
| Number of AD syringes for other vaccines | 4,652,300 | 2,163,895 |
| Number of re-constitution syringes for BCG | 55,000 | 58,500 |
| Number of re-constitution syringes for Measles | 88,000 | 93,500 |
| Number of safety boxes | 68,850 | 32,200 |

According to your request, in 2002 GAVI/the vaccine fund will disburse US$ 449,300 equivalent to the cost of the listed material for that year.

Table 4.1: Estimated supplies for safety of vaccination for the next two years with …… (Use one table for each vaccine BCG, DTP, measles and TT, and number them from 4.1 to 4.4)

|  |  |  |  |  | Formula |  | For year …… | For year …… |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A | Target of children for …… vaccination (for TT : target of pregnant women) |  |  |  | # |  |  |  |
| B | Number of doses per child (for TT woman) |  |  |  | # |  |  |  |
| C | Number of …… doses |  |  |  | A x B |  |  |  |
| D | AD syringes (+10% wastage) |  |  |  | C x 1.11 |  |  |  |
| E | AD syringes buffer stock |  |  |  | D x 0.25 |  |  |  |
| F | Total AD syringes |  |  |  | D + E |  |  |  |
| G | Number of doses per vial |  |  |  | # |  |  |  |
| H | Vaccine wastage factor |  |  |  | Either 2 or 1.6 |  |  |  |
| I | Number of reconstitution syringes (+10% wastage) |  |  |  | C x H x 1.11 / G |  |  |  |
| J | Number of safety boxes (+10% of extra need) |  |  |  | ( F + I ) x 1.11 / 100 |  |  |  |
| Table 5: Summary of total supplies for safety of vaccinations with BCG, DTP, TT and measles for the next two years. |  |  |  |  |  |  |  |  |
| ITEM |  |  | For the year 2002 | For the year 2003 |  | Justification of changes from originally approved supply: |  |  |
| Total AD syringes |  | for BCG | 687,000 | 584,400 |  |  |  |  |
|  |  | for other vaccines | 4,652,300 | 2163,895 |  |  |  |  |
| Total of reconstitution syringes |  |  | 143,000 | 152,000 |  |  |  |  |
| Total of safety boxes |  |  | 60,850 | 32,200 |  |  |  |  |

# Signatures

For the Government of  Yemen

Signature:	……………………………………………...……………...

Title: Minister of Public Health &  Population

Date: 29 September 2002

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this report. Signature of endorsement of this document does not imply any financial (or legal) commitment on the part of the partner agency or individual.

Financial accountability forms an integral part of GAVI/The Vaccine Fund monitoring of reporting of country performance.  It is based on the regular government audit requirements as detailed in the Banking form.  The ICC Members confirm that the funds received have been audited and accounted for according to standard government or partner requirements.

| Agency/ Organisation | Name/Title | Date Signature | Agency/Organisation | Name/Title | Date Signature |
| --- | --- | --- | --- | --- | --- |
| MOPH&P | Prof Dr Abdul Naser A. Munibari Minister of Public Health & Population |  | WHO | Dr. Hashim Al-Zain WHO Representative |  |
| MOPH&P | Prof Dr Abdul Karim A. Shiban Under Secretary for Medical and Health Services |  | UNICEF | Mr. Leonard De Vos UNICEF Representative |  |
| MOPH&P | Mohammed Ali Kolaise DG of PHC/EPI Secretary of ICC |  | JAPAN | Mr. Yoshiaki Hata Councillor, Embassy of Japan |  |
| MOPH&P | Dr Mohammed M. Hager EPI Consultant |  | WORLD BANK | Mr. Hashim Awnallah Operations Officer |  |
| MoF | Mohammed Fadel Ahmed Ministry of Finance Representative |  |  |  |  |

GAVI will fund the procurement of AD syringes to deliver 2 doses of TT to pregnant women. If the immunization policy of the country includes all Women of Child Bearing Age (WCBA), GAVI/The Vaccine Fund will contribute to a maximum of 2 doses for Pregnant Women (estimated as total births).

The buffer stock for vaccines and AD syringes is set at 25%. This is added to the first stock of doses required to introduce the vaccination in any given geographic area. Write zero for other years.

Standard wastage factor will be used for calculation of re-constitution syringes. It will be 2 for BCG, 1.6 for measles and YF.

Only for lyophilized vaccines. Write zero for other vaccines