January 2005

Progress Report

Partnering with The Vaccine Fund

to the

Global Alliance for Vaccines and Immunization (GAVI)

and

The Vaccine Fund

by the Government of

COUNTRY: ZAMBIA

Date of submission: May 2006 Reporting period: 2005 ( Information provided in this report MUST refer to 2005 activities ) ( Tick only one ) : Inception report First annual progress report Second annual progress report Third annual progress report  Fourth annual progress report Fifth annual progress report Text boxes supplied in this report are meant only to be used as guides. Please feel free to add text beyond the space provided. *Unless otherwise specified, documents may be shared with GAVI partners and collaborators

# Progress Report Form:  Table of Contents

# Report on progress made during 2005

  - Immunization Services Support (ISS)

1.1.1	Management of ISS Funds

  - Use of Immunization Services Support

1.1.3	Immunization Data Quality Audit

  - GAVI/Vaccine Fund New and Under-used Vaccines

1.2.1	Receipt of new and under-used vaccines

1.2.2	Major activities

    - Use if GAVI/The Vaccine Fund financial support (US$100,000) for introduction of the new vaccine

1.3	Injection Safety

    - Receipt of injection safety support

    - Progress of transition plan for safe injections and safe management of sharps waste

    - Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

2.  Financial Sustainability

3.  Request for new and under-used vaccine for 2007

  - Up-dated immunization targets

  - Confirmed/revised request for new vaccine (to be shared with UNICEF Supply Division) for year…

  - Confirmed/revised request for injection safety support for the year…

- Please report on progress since submission of the last Progress Report based on the indicators

selected by your country in the proposal for GAVI/VF support

5.  Checklist

6.  Comments

7.  Signatures

# 1.  	Report on progress made during 2005

To be filled in by the country for each type of support received from GAVI/The Vaccine Fund.

## Immunization Services Support (ISS)

#### 1.1.1	Management of ISS Funds

Please describe the mechanism for management of ISS funds, including the role of the Inter-Agency Co-ordinating Committee (ICC).

Please report on any problems that have been encountered involving the use of those funds, such as delay in availability for programme use.

During the year 2005, Zambia did not receive ISS funds because the 3 year support had come to an end. The funds used during this reporting period were a carry over of US$ 74,400 from 2004. However, the country received US$2,166,660 as reward money in 2004 and US$705,400 in 2005. The ISS funds were held at the Central Board of Health (now in the Ministry of Health since March 2006) and were expended as per CBoH financial regulations. There is a GAVI Core Group comprising officers from the Central Board of Health, WHO, UNICEF and USAID, which meets regularly, to ensure that GAVI activities are implemented as planned. Recommendations of the GAVI Core Group are taken to the ICC for endorsement. It is only after the ICC has approved the release of funds that CBoH can release any funds. The ISS funds have been spent on the implementation of the Reaching Every District strategy (RED) in the ten priority districts identified as low performing in the country and training on introduction of DPT+HepB-Hib vaccine including integrated child health week. The funds have also been used to provide supportive supervision by the provinces and ten DHMTs to the frontline health workers in the RED strategy implementing districts. Some of the funds have been used to facilitate central level distribution of logistics and vaccines to the provincial health offices.

1.1.2	Use of Immunization Services Support

In 2004, the following major areas of activities have been funded with the GAVI/Vaccine Fund Immunization Services Support contribution.

Funds received during 2005: US$ 2,166,660 (Award funds for 2003) + US$705,400 (Award funds for 2004)

Remaining funds (carry over) from 2004: US$74,400

Table 1: Use of funds during 2005

| Area of Immunization Services Support | Total amount in US $ | AMOUNT OF FUNDS (in ZmK) |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | PUBLIC SECTOR |  |  | PRIVATE SECTOR & Other |
|  |  | Central | Region/State/Province | District |  |
| Vaccines | - |  |  |  |  |
| Injection supplies | - |  |  |  |  |
| Personnel |  |  |  |  |  |
| Transportation (distribution) | 46,907 | 210,051,250 |  |  |  |
| Maintenance and overheads | 21,538 | 96,446,100 |  |  |  |
| Training (Integrated Child Health Week), Introduction of Pentavalent vaccine) | 219,009 | 16,760,000 | 108,000,000 | 855,960,000 |  |
| IEC / social mobilization (Launch of DPT-Hib vaccine) | 59,640 | 82,296,500 | 39,864,000 | 144,908,126 |  |
| Outreach (Implementation of RED – support to 10 priority districts) | 44,663 |  |  | 200,000,000 |  |
| Supervision | 79,705 | 110,840,000 | 214,330,000 | 31,750,000 |  |
| Monitoring and evaluation | 11,862 | 53,120,000 |  |  |  |
| Epidemiological surveillance | 2,162 | 9,680,000 |  |  |  |
| Vehicles | 36,249 | 162,324,667 |  |  |  |
| Cold chain equipment | 4,558 | 20,410,000 |  |  |  |
| Other: Bank charges | 823 | 3,684,372 |  |  |  |
| Remaining funds -balance B/F) | 74,400 |  |  |  |  |
| Total: | 527,116 | 765,612,889 | 362,194,000 | 1,232,618,126 |  |
| Remaining funds for next year: 2006 | 2,066,584 |  |  |  |  |

*If no information is available because of block grants, please indicate under ‘other’.

Please attach the minutes of the ICC meeting(s) when the allocation of funds was discussed.

Please report on major activities conducted to strengthen immunization, as well as, problems encountered in relation to your multi-year plan.

The ICC approved the use of ISS/Award funds on training of integrated child health interventions (child health week and introduction of new vaccine) for health worker, monitoring of vaccine wastage in sentinel sites, supportive supervision for RED and the implementation of the RED strategy in the ten priority districts. There were no problems encountered in accessing of funds.

#### Immunization Data Quality Audit (DQA) (If it has been implemented in your country)

Has a plan of action to improve the reporting system based on the recommendations from the DQA been prepared?

If yes, please attach the plan.

YES                              NO



## If yes, please report on the degree of its implementation.

As this has been the second year since Zambia passed the DQA, efforts have been made to implement the recommendations from the DQA. However, these recommendations were not many. Progress in the implementation so far is as follows: - The immunization tally sheet has been revised to include information on the first and second doses of DPT-HepB+Hib & OPV; other child health interventions such IMCI, ITN utilization, vitamin A supplementation for lactating mothers (<2 months of delivery) - A meeting was held with staff from CSO meant to harmonise population figures for denominators at all levels as this has been a major hindrance to calculating of coverage. - Data monitoring and usage has been emphasised during trainings and this is more visible in the ten RED strategy districts

## Please attach the minutes of the ICC meeting where the plan of action for the DQA was discussed and endorsed by the ICC.

Please report on studies conducted regarding EPI issues during 2005 (for example, coverage surveys).

- EPI comprehensive review - Monitoring of vaccine wastage in sentinel sites- ongoing

## GAVI/Vaccine Fund New & Under-used Vaccines Support

#### 1.2.1	Receipt of new and under-used vaccines during 2005

Start of vaccinations with the new and under-used vaccine: MONTH-October, YEAR-2005

Please report on receipt of vaccines provided by GAVI/VF, including problems encountered.

A total 1,707,000 doses of DPT-HepB+Hib vaccines have been received during the year in three shipments. There were no problems experienced, as the storage capacity is adequate for the received formulation. The pentavalent vaccine was launched on 17th October 2005 nationwide. There was negative publicity during the introduction of the new pentavalent vaccine. Social mobilisation was intensified through media campaign with the Minister of Health taking lead.

#### 1.2.2	Major activities

Please outline major activities that have been or will be undertaken, in relation to, introduction, phasing-in, service strengthening, etc. and report on problems encountered.

Cold Chain Equipment Ministry of Health with support from GlaxoSmithKline (GSK) trained 15 cold chain technicians from districts. The aim of the training was to enhance the capacity for maintenance of cold chain equipment at district level. The Ministry of Health submitted a proposal for JICA phase II support for replacement of 45% remaining installation of cold chain equipment. The phasing in of the new vaccine was not difficult as there was intensive training for all levels of immunization operations prior to its introduction. The messages that were publicised (message highlighted pneumonia which is a well known disease) attracted masses of caretakers especially on the day of the launch of the vaccine. UNICEF procured 68 motorcycles and USAID/HSSP procured 7 solar refrigerators. New Vaccines, Strengthening Immunisation Services and Injection Safety The following activities were undertaken: - Training of health workers ( Introduction of DPT-HepB+Hib vaccines) at all levels were conducted in June three months prior to the introduction of the new vaccine - Training was integrated with other child health interventions and were co-funded by Cooperating Partners who supported the central level training - Information on the new vaccines was very elaborate and was disseminated to communities and leaders at all levels. This made it easier for leaders to support the technical groups during the preparatory and the actual introduction of the vaccine - A field visit was made afterwards to monitor the implementation process and correct mistakes if there were any that the field team were encountering - An implementation plan of action for the Financial Sustainability Plan (FSP) has been developed and a task force/ working group has been constituted to see to it that activities are implemented

#### 1.2.3	Use of GAVI/ The Vaccine Fund financial support (US$100,000) for the introduction of the new vaccine

Please report on the proportion of 100,000 US$ used, activities undertaken, and problems encountered such as delay in availability of funds for programme use.

Not applicable for 2005. Money was spent in 2004.

## Injection Safety

#### 1.3.1	Receipt of injection safety support

Please report on receipt of injection safety support provided by GAVI/VF, including problems encountered

Following the approval of the Injection Safety proposal on 27 August 2002 by GAVI, a supply of Auto-disable (ADs) has been received at a total value of US $631,582. The materials came in about five consignments. There has been no problem with the usage of the materials as prior trainings emphasised very much on how to assemble and use the equipment. The Government of Zambia has started contributing to injection safety support following the end of the 3-year support.

#### Progress of transition plan for safe injections and safe management of sharps waste

#### Please report problems encountered during the implementation of the transitional plan for safe injection and sharp waste

Please report on the progress based on the indicators chosen by your country in the proposal for GAVI/VF support.

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| Updated inventory on incinerators and plan for collection/incineration of filled safety boxes by 2003 | Updated inventory on incinerators and plans for collection/incineration of filled safety boxes by 2003 | - Updated inventory on incinerators done – awaiting full report from dept of Medical equipment - Plans for incineration of filled safety boxes | Lack of incinerators in many health facilities | - Report to be obtained by next ICC meeting in September 2006 - Incineration of safety boxes being done |
| Installation of incinerators in three provinces by 2006 | Installation of incinerators in 3 provinces by 2006 | 22 incinerators have been procured by WHO and UNICEF. Government, through VII has procured 5 more incinerators. | Inadequate funding to procure more incinerators | Installation of incinerators in identified provincial hospitals and districts/ HCs ongoing |
| Incorporation of guidelines on collection and incineration of sharps waste in the Vaccinations Manual by 2003 | Incorporation of guidelines on collection and incineration of sharps waste in the Vaccinations Manual by 2003 | Revision of Vaccination Manual to incorporate collection and incineration of injection waste | Nil | Done |
| Introduction of safety boxes for routine immunization in all health facilities by 2003 | Introduction of safety boxes for routine immunization in all health facilities by 2003 | Training conducted and safety boxes introduced in all health facilities in 2003 | Nil | NONE |
| Development of plan for advocacy and communication on injection safety by 2003 | Development of plan for advocacy and communication on injection safety by 2003 | Draft communication plan for child health completed | Frequent postponement of planned activities | Finalisation of plan by end April 2006 - DONE |

#### 1.3.3	Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

The following major areas of activities have been funded (specify the amount) with the GAVI/The Vaccine Fund injection safety support in the past year:

# 2.  	Financial sustainability

Inception Report:	Outline timetable and process for the development of a financial sustainability plan. Describe assistance that may be needed for developing a financial sustainability plan.

First Annual Progress Report: 	Submit completed financial sustainability plan by given deadline. Describe major strategies for improving financial sustainability.

Subsequent Progress Reports:	According to current GAVI rules, support for new and under-used vaccines is covering the total quantity required to meet country targets (assumed to be equal to DTP3 targets) over a five year period (100% x 5 years = 500%).  If the requested amount of new vaccines does not target the full country in a given year (for example, a phasing in of 25%), the country is allowed to request the remaining (in that same example: 75%) in a later year.  In an attempt to help countries find sources of funding in order to attain financial sustainability by slowly phasing out GAVI/VF support, they are encouraged to begin contributing a portion of the vaccine quantity required.  Therefore, GAVI/VF support can be spread out over a maximum of ten years after the initial approval, but will not exceed the 500% limit (see figure 4 in the GAVI Handbook for further clarification).  In table 2.1, specify the annual proportion of five year GAVI/VF support for new vaccines that is planned to be spread-out over a maximum of ten years and co-funded with other sources. Please add the three rows (Proportion funded by GAVI/VF (%), Proportion funded by the Government and other sources (%), Total funding for ………….  (new vaccine)) for each new vaccine.

| Table 2.1: Sources (planned) of financing of new vaccine …DPT-HepB+Hib |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Proportion of vaccines supported by * | Annual proportion of vaccines |  |  |  |  |  |  |  |  |  |
|  | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 |
| A: Proportion funded by GAVI/VF (%)*** | 100 | 90 | 86 | 82 | 78 | 74 | 34 | 25 | 24 | 11 |
| B: Proportion funded by the Government and other sources (%) | 0 | 10 | 14 | 18 | 22 | 26 | 66 | 75 | 76 | 89 |
| C: Total funding for DPT-HepB+Hib | 8,812,000 | 7,084,006 | 5,587,030 | 5,404,171 | 5,508,431 | 5,668,175 | 5,832,552 | 6,001,696 | 6,175,745 | 6,354,842 |

* Percentage of DTP3 coverage (or measles coverage in case of Yellow Fever) that is target for vaccination with a new and under-used vaccine.

** The first year should be the year of GAVI/VF new vaccine introduction

*** Row A should total 500% at the end of GAVI/VF support

Please note that the proportion funded by government and other sources (Row B) is based on the assumption that more resources will be made available to the health sector following Zambia reaching the HIPC completion point.

In table 2.2 below, describe progress made against major financial sustainability strategies and corresponding indicators.

Table 2.2:	Progress against major financial sustainability strategies and corresponding indicators

| Financial Sustainability Strategy | Specific Actions Taken Towards Achieving Strategy | Progress Achieved | Problems Encountered |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Baseline Value of Progress Indicator | Current Value of Progress Indicator | Proposed Changes To Financial Sustainability Strategy |  |
| Mobilization of additional Govt resources | Advocacy for traditional vaccine costs covered by Government (including basket) funds by 2012 | Government contributed K 700,000 | - | 0% | 10% increase per year |  |  |
|  | Inclusion of resource needs in MTEF by 2004 | YES | - | Not included | Resource needs included in MTEF by 2004 |  |  |
|  | Inclusion of programme activities and resource requirements from the FSP in the annual Health Sector work plan by 2005 | YES | - | Not included | FSP incorporated in Health Sector plan by 2005 |  |  |
| Mobilization of additional resources from local Government | Proportion of IEC, surveillance and cold chain maintenance costs funded by local government by 2007 | 10% | Funding for printing of IEC materials | 0% | 100% by 2007 |  |  |
| Mobilization of resources from the private sector | Proportion of DTP-HepB+Hib vaccine costs covered by resources from the private sector by 2010 | 0% | Needs advocacy efforts to be made | 0% | 25% (HepB equivalent) by 2010 |  |  |
| Expansion of ICC and involvement in the Health Sector Steering Committee | Number of new ICC members recruited by 2005 Number of HSSC meetings attended by the ICC by 2005 | 2 | Needs advocacy efforts to be made | 0 None | 4 4 per year |  |  |
| Increasing reliability of public resources | Proportion of traditional vaccine costs covered by Government (including basket) funds by 2012 | 80% | Funding | 0% in 2002 | 100% by 2012 |  |  |
|  | Proportion of Government funded programme costs secured in the MTEF by 2012 | 10% | - | 0 | 100% |  |  |
| Reduction of vaccine wastage | Reduction of DTP-HepB+Hib 3 Vaccine wastage rate by 2006 | Wastage sentinel system is being introduced, MDVP introduced | High dose vials for BCG, DPT-Hib | 34% | 10% |  |  |
| Increasing vaccination through static units | Rural health facilities providing immunization services by 2005 | All HCs providing services | Staff shortages | None | 100% |  |  |
| Involvement of private providers in providing vaccination | Private providers providing immunisation services by 2005 | Most |  | None | 100% |  |  |
| Increasing numbers of infants vaccinated per outreach session | Increased immunisation coverage in all catchment areas by 2006 | Increase outreach posts | Transport and staffing | None | 90% |  |  |
| Improvement of health worker skills in EPI management and service delivery | Health workers trained in management skills by 2005 | EPI training done in all facilities, each health has one trained staff in EPI. Integrated child health week training included introduction of new vaccine. |  | 0% in 2002 | 100% by 2005 |  |  |

# 3.  	Request for new and under-used vaccines for year 2006

Section 3 is related to the request for new and under used vaccines and injection safety for 2006.

- Up-dated immunization targets

Confirm/update basic data approved with country application: figures are expected to be consistent with those reported in the WHO/UNICEF Joint

Reporting Forms.  Any changes and/or discrepancies MUST be justified in the space provided (page 12). Targets for future years MUST be provided.

| Table 3 : Update of immunization achievements and annual targets |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of | Achievements and targets |  |  |  |  |  |  |  |  |
|  | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 |
| DENOMINATORS |  |  |  |  |  |  |  |  |  |
| Births | 587,460 | 605,990 | 620,817 | 636,140 | 651,977 | 668,346 | 685,264 | 702,753 | 720,831 |
| Infants’ deaths | 55,809 | 60,599 | 62,082 | 63,614 | 65,198 | 66,835 | 68,526 | 70,275 | 72,083 |
| Surviving infants | 531,631 | 545,391 | 558,735 | 572,526 | 586,779 | 601,511 | 616,738 | 632,478 | 648,748 |
| Infants vaccinated in 2005 (JRF) / to be vaccinated in 2006 and beyond with 1st dose of DTP (DTP1)* |  |  |  |  |  |  |  |  |  |
| Infants vaccinated 2005 (JRF) / to be vaccinated in 2006 and beyond with 3rd dose of DTP (DTP3)* | 499,139 | 515,936 | 525,211 | 541,037 | 557,440 | 574,443 | 592,068 | 610,341 | 629,286 |
| NEW VACCINES ** |  |  |  |  |  |  |  |  |  |
| Infants vaccinated 2005 (JRF) / to be vaccinated in 2006 and beyond with 1st dose of DTP (DTP1)* …......... (new vaccine) |  |  |  |  |  |  |  |  |  |
| Infants vaccinated 2005 (JRF) / to be vaccinated in 2006 and beyond with 3rd dose of DPT+HepB-Hib…….… ( new vaccine) | 499,139 | 515,936 | 525,211 | 541,037 | 557,440 | 574,443 | 592,068 | 610,341 | 629,286 |
| Wastage rate in 2005 and plan for 2006 beyond*** ………….. ( new vaccine) | 45% | 10% | 10% | 10% | 5% | 5% | 5% | 5% | 5% |
| INJECTION SAFETY**** |  |  |  |  |  |  |  |  |  |
| Pregnant women vaccinated in 2005 (JRF) / to be vaccinated in 2006 and beyond with TT2 | 576,678 | 492,640 | 509,070 | 527,996 | 547,661 | 568,094 | 582,474 | 604,368 | 627,123 |
| Infants vaccinated in 2005 (JRF) / to be vaccinated in 2006 and beyond with BCG * | 552,088 | 538,409 | 558,735 | 578,887 | 599,819 | 621,562 | 644,148 | 667,615 | 691,998 |
| Infants vaccinated in 2005 (JRF) / to be vaccinated in 2005 and beyond with Measles * | 429,508 | 449,414 | 455,369 | 469,471 | 487,027 | 505,269 | 521,144 | 537,606 | 554,680 |

* Indicate actual number of children vaccinated in 2005 and updated targets (with either DTP alone or combined)

** Use 3 rows (as indicated under the heading NEW VACCINES) for every new vaccine introduced

*** Indicate actual wastage rate obtained in past years

**** Insert any row as necessary

Please provide justification on changes to baseline, targets, wastage rate, vaccine presentation, etc. from the previously approved plan, and on reported figures which differ from those reported in the WHO/UNICEF Joint Reporting Form in the space provided below.

Denominator changed during a combined review meeting between MoH/ HMIS and CSO.

3.2	Availability of revised request for new vaccine (to be shared with UNICEF Supply Division) for 2006

In case you are changing the presentation of the vaccine, or increasing your request; please indicate below if UNICEF Supply Division has assured the availability of the new quantity/presentation of supply.

Table 4: Estimated number of doses of DPT- Hep B+Hib vaccine (specify for one presentation only): Please repeat this table for any other vaccine presentation requested from

GAVI/The Vaccine Fund

*Please report the same figure as in table 3.

Table 5: Wastage rates and factors

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

Remarks

- Phasing: Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided - Wastage of vaccines: Countries are expected to plan for a maximum of: 50% wastage rate for a lyophilized vaccine in 10 or 20-dose vial; 25% for a liquid vaccine in a10 or 20-dose vial; 10% for any vaccine (either liquid or lyophilized) in 1 or 2-dose vial. - Buffer stock: The buffer stock is recalculated every year as 25% the current vaccine requirement - Anticipated vaccines in stock at start of year 2006: It is calculated by counting the current balance of vaccines in stock, including the balance of buffer stock. Write zero if all vaccines supplied for the current year (including the buffer stock) are expected to be consumed before the start of next year. Countries with very low or no vaccines in stock must provide an explanation of the use of the vaccines. - AD syringes: A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines. - Reconstitution syringes: it applies only for lyophilized vaccines. Write zero for other vaccines. - Safety boxes: A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes

#### 3.3	Confirmed/revised request for injection safety support for the years 2006 -2007

Table 6: Estimated supplies for safety of vaccination for the next two years with BCG (Use one table for each vaccine BCG, DTP, measles and TT, and number them from 4 to 8)

NB: Number of safety boxes increased by a four-fold dure to increased demand and expressed concern from the general medical/ surgical depts.  Therefore, will cater for all types of injection materials other than just EPI.

Table 7: Estimated supplies for safety of vaccination for the next two years with Measles

#### Table 6: Estimated supplies for safety of vaccination for the next two years with TT

#### If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference.

NB. Although requirements for injection safety supplies have been indicated for 2007 and 2008, Zambia is aware that GAVI support for injection safety ended in 2005. Government is sourcing funds to support injection safety.

# 4. 	Please report on progress since submission of the last Progress Report based on the indicators selected 	by your country in the proposal for GAVI/VF support

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| Introduction of the DPT-HepB+Hib | Introduction of the DPT-HepB+Hib vaccine in all health facilities by end of 2005. | DPT-HepB+Hib introduced in October 2005. | None | To achieve pentavalent ( DPT-HepB+Hib) coverage of 94% in 2006 |

# Checklist

Checklist of completed form:

| Form Requirement: | Completed | Comments |
| --- | --- | --- |
| Date of submission | Yes |  |
| Reporting Period (consistent with previous calendar year) | Yes |  |
| Table 1 filled-in | Yes |  |
| DQA reported on | Yes |  |
| Reported on use of 100,000 US$ | Yes |  |
| Injection Safety Reported on | Yes |  |
| FSP Reported on (progress against country FSP indicators) | Yes |  |
| Table 2 filled-in | Yes |  |
| New Vaccine Request completed | Yes |  |
| Revised request for injection safety completed (where applicable) | Yes |  |
| ICC minutes attached to the report | Yes |  |
| Government signatures | Yes |  |
| ICC endorsed | Yes |  |

6.  	Comments

ICC/RWG comments:

7.	Signatures

For the Government of the Republic of Zambia: Hon. Sylvia T. Masebo …………

Signature:	……………………………………………...……………....................

Title:  MINISTER OF HEALTH…………………………………………………

Date:	………………………………………….…………………………….

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this report. Signature of endorsement of this document does not imply any financial (or legal) commitment on the part of the partner agency or individual.

Financial accountability forms an integral part of GAVI/The Vaccine Fund monitoring of reporting of country performance.  It is based on the regular government audit requirements as detailed in the Banking form.  The ICC Members confirm that the funds received have been audited and accounted for according to standard government or partner requirements.

| Agency/Organisation | Name/Title | Date Signature | Agency/Organisation | Name/Title | Date Signature |
| --- | --- | --- | --- | --- | --- |
| Ministry of Health | Hon. Sylvia T. Masebo Minister of Health |  | USAID | Ms Barbara Hughes Director of Programmes |  |
| Ministry of Health | Dr. V. Mukonka Director, Public Health & Research |  | DFID | Ms Jane Miller Health & Population Advisor |  |
| WHO | Dr. S Anyangwe Resident Representative |  | HSSP | Dr. C Musumali Chief of Party |  |
| UNICEF | Ms L. Sylwander Resident Representative |  | JICA | Mr. T. Kikuchi Assistant Resident Representative |  |
| Rotary International District 9210 | Mr. D. Babbar Chairman |  | CHAZ | Dr S. Mphuka Director of Programmes |  |

~ End ~

THE FOLLOWING CLARIFICATIONS WERE RECEIVED FROM ZAMBIA