## Slide 1
COLD CHAIN EQUIPMENT OPTIMIZATION PLATFORM
Operational Deployment Guidebook for Countries
December 3, 2018

## Slide 2
This document is part of a set of resources designed to support countries (and supporting partners) in the execution and management of CCE OP deployments.
Objectives of this Guidebook
Why this guidebook?
The Gavi Cold Chain Equipment Optimisation Platform (CCEOP) requires that the manufacturer, through it’s local authorised dealer, be held responsible for delivery and commissioning of the products, including providing training of staff on maintenance and care of the products.
This requirement introduces novel processes into the procurement and installation approach, and demands solid project management and procurement planning across stakeholders.
This document is intended to provide useful information and guidance for countries engaging with this process -- with a major focus on the preparation, coordination and submission of the Operational Deployment Plan.
Who is it for?
Country MOH
In-country partners supporting MOH with CCEOP implementation

## Slide 3
The following table summarizes the major sections of this guidebook.
Contents
Table of Contents
Introduction & Overview
The Project Management Team (PMT)
Developing the Operational Deployment Plan
  Site Information & Readiness Assessment
  Deviation Management
  Spare Parts, TMDs & Voltage Regulators Management
  Customs & clearance
  Central Training of Technicians
Submission Process & Cost Overview

## Slide 4
    Country constitution of PMT
    MoH development of ODP
    WHO Pre-Review
    IRC Review and recommendation
    Gavi Board Approval of multi-year project
    Gavi issues Decision Letter to MoH to authorize annual procurements
    Gavi issues Authorization Schedule to UNICEF SD to initiate procurement
    MoH requests UNICEF SD to cost the Operational Deployment Plan
    UNICEF SD issues tender for service bundle & develops a costed operational plan
    MoH agrees to proposed costed operational plan
    Gavi approves the costed operational plan
    UNICEF SD issues final Cost Estimate (CE) to MoH
    MoH accepts CE and transfers joint-investment of funds to UNICEF SD
    Gavi transfers joint-investment funds to UNICEF SD
Activities
Status check
  Completed
  Ongoing
Status check color code :
    UNICEF SD places purchase orders for goods
    UNICEF SD issues contract to supplier for service bundle
    PMT track delivery & installation
    MoH delegate to sign commissioning checklist and certify invoices
    Supplier send to UNICEF SD for payment,
    Post installation inspection
CCEOP Application & Approval
A
Procurement Planning
B
Procurement Implementation
C
I. Introduction & Overview
Notes: Add establish PMT

## Slide 5: II . The Project Management Team (PMT)
Membership of the PMT
The key roles and responsibilities of the project management team (PMT) in the CCEOP process;
Project Management Support Package
This Section Covers

## Slide 6
The Project Management Team (PMT) – A key tool for managing the CCEOP
To manage the key processes at each stage of the CCEOP, each country should constitute of Project Management Team (PMT) that will serve as the coordination hub (A project management support package is available here)
Suggested Membership
The government has full authority to determine who sits on the PMT, but the following parties are recommended;
The chief EPI logistician or program manager to serve as Chair;
A representative from the UNICEF Country Office;
Partners and other stakeholders from the logistics working group – particularly those involved in cold chain.
A multidisciplinary team consisting of programme and supply professionals is recommended
Convening and Meeting
The PMT should be established during the application phase and should manage the project until installation is finalized. The PMT should determine how often it should meet, and develop a TOR, the necessary work plans and coordination tools.
To ensure that all key processes are covered, it is recommended that the PMT have its own meetings, separate from any existing LWG or coordination body (particularly during the first year of implementation.)
Coordination
The PMT is expected to coordinate with the following parties:
Local service providers (when the tender has been awarded)
MoH/MoF and Customs Authorities as applicable
District/Provincial Health Authorities

## Slide 7: III. Developing the Operational Deployment Plan
The rationale and requirements of the operational deployment planning (ODP) process;
A detailed breakdown of each section of the ODP, and recommendations on how to complete them.
Site installation list and readiness assessment
Spare parts
TMDs & voltage regulators for existing equipment
Training
This Section Covers

## Slide 8
Introduction to the Operational Deployment Plan
What are the contents of an operational deployment plan?
The Operational Deployment plan provides detailed information on the:
Geographical location, accessibility and readiness of all sites to receive equipment that year.
Designated equipment information per site
Contact details of staff responsible for certifying the installation of CCE at the site.
The development of an Operational Deployment Plan (ODP) is required for each year of the CCEOP, and a core responsibility of the Project Management Team.
Why is it a requirement of the CCEOP process?
The Operational Deployment Plan plays two critical roles in the CCEOP process:
Providing suppliers and UNICEF SD with the necessary information to develop the Service Bundle Cost Estimates.
To help coordinate essential processes – e.g. clearance, installation schedule, communication --- between vendors and the PMT/MoH during the arrival and deployment periods.

## Slide 9
Key steps for country in preparation of an Operational Deployment Plan
A
Document Site Information & Readiness Assessment Information
A list of installation sites (facility name, address, contact person name and contact details, GPS coordinates if available) per type of equipment
Complete a Health Facility Readiness Assessment and validate the information
Identify cadre of staff to be trained at each health facility for preventive maintenance & operation of the CCE (note per diems & travel costs are for MoH’s account
Specify cold chain equipment details
Indicate if the equipment is for extension, replacement or expansion
Indicate the manufacturer and model of the CCE designated, storage capacity range, power source and quantity per site
Use the drop down list to reduce errors
Develop Plan for Spare Parts, TMDs & Voltage Regulators (for existing platform eligible CCE no older than 5 years)
Identify which spares, TMDs & VRs must be delivered, where they will be stored and when they will be included in the CCE Inventory. Note that MoH will be the consignee (just as for CCE) and the spares will be sent to the consignee address
Identify Training Needs
Identify cadre of staff at central level for training on warranty conditions, corrective maintenance, service bundling. Note that per diems & venue costs are not covered under CCE OP.
Identify any supplemental training needs not covered under CCE OP
B
C
D
To prepare an ODP, the MoH/PMT will need to carry out the following steps – each summarized in the next sections:

## Slide 10: III-A. Site Installation List
This Section Covers
The key elements of the site installation list that are required to be populated
Rationale for data request

## Slide 11
What is the Site Installation List?
Elements of the Site Installation List
This table is the largest aspect of the operational deployment plan, and provides the majority of information required for suppliers to create and cost their service delivery offering.
The template for this data collection is in the Excel spreadsheet provided with this guidebook, under the tab labeled “Installation Sites.”
The Site Installation List has four elements, which are described on the following slides:
Location
Contact Information
Site Readiness
Staff for Training
The details in the Site Installation List are the primary determinant of costs for the supplier. Inaccuracies and incompleteness in this table can lead to delays or additional fees / penalties to the government.
!
Provision of Site Information: Collecting data to confirm site location, readiness and other factors

## Slide 12
Considerations for populating site installation list
This information helps the vendor accurately find the correct health facility and supports better coordination
The CCE information validates the specifications and quantity of equipment designated to each health facility

## Slide 13
Considerations for populating site installation list
This information helps the vendor determine the access requirements for the designated site. It is critical information required for planning and assists the vendor in correctly costing their requirements which drives down prices and reduces delays

## Slide 14
Considerations for populating site installation list
This information validates requirements for end user training
The approval year is important so that countries can develop an ODP for the entire life cycle of their CCEOP grant

## Slide 15: III-B. Deviations Management

## Slide 16
(1) In the CCEOP service bundle , the supplier quotes prices based on the information provided in the Operational Deployment Plan. When approved, cost agreement is a legal contract –– The government guarantees that the ODP is accurate, and the supplier commits to execute the service bundle at that price.
The cost of the CCEOP service delivery bundle is based off the operational deployment plan. Any deviation from this plan may incur additional costs, which may have to be paid for by the MoH. Strong forward planning will significantly reduce the risk of such events happening, and ease management if they do.
Defining Deviation
If one or more sites do not receive equipment as per agreed commitments between supplier and government, it is called a deviation.
Under some circumstances, the government will be responsible for paying any associated costs for these deviations, as the table below explains.1
Common Sources of Deviation & Responsibility For Them
The SUPPLIER is responsible for deviations arising from
The GOVERNMENT is responsible for deviations arising from
Any delays resulting from the performance of vendor equipment or staff
Any delays arising from failure to appropriately estimate for needs described in the operational deployment plan (e.g. inappropriate vehicle, non-functioning tools and/or equipment)
Any additional transportation arising from inaccuracies in the ODP (e.g. incorrect addresses provided)
Any additional installation arising from inaccurate site descriptions and not identified in ODP (e.g. roof not able to support solar panel)
Any delays in accessing designated officials
Overview of Deviation Policy & Fees

## Slide 17
Through strong planning and review processes, it is entirely possible for the country to avoid deviations and thus avoid any additional costs.
Government deviation costs can be averted by providing accurate and complete information on site location, site readiness and site accessibility, as well as ensuring staff available to train and sign-off on installation
Phase 3 (1-2 weeks before installation):
Communicate with the officer-in-charge of each site, and confirm their availability
Communicate to all officers-in-charge to confirm their availability and review the procedures on :
  equipment receipt
  Installation
  on-site training (if any)
  post-installation
Phase 2 (1-2 months before installation):
Update
Operational Deployment Plan
Convey to UNICEF SD & the vendor any changes to:
  Site readiness due to repairs that have been completed and validated
  Security status of the region.
  List of target sites due to newly installed equipment at previous facilities
  contact information of the officer in-charge
Phase 1 :(Commence upon initiation of CCE OP application initiation process)
Operational Deployment Plan (ODP) is completed accurately for all sites.
Complete Health Facility Assessment (this should be done in combination with the CCE Inventory collection)
Identify all sites to receive equipment during timeframe, including following year
Collect and provide accurate information for all sites on:
  Site location (e.g. address, distance, etc.)
  Site readiness (roof, floor level, security)
  Need for alternative installation (floor/pole mount)
  Site accessibility (e.g. distance, road quality, special access requirements, etc)
Develop a plan to repair sites not ready to receive CCE/provide details of alternate sites
Develop a deviation management plan
Conduct a random sample of visits to validate the ODP
Preventing Deviations
Emphasize the importance of deviations management

## Slide 18: III-C. - Preparing for Spare Parts - TMDs & Voltage Regulators for Existing Equipment - Passive containers
Data points required in order to deliver spare parts, TMDs ,VRs and passive containers procured through the CCEOP
This Section Covers

## Slide 19
Data Requested
Spare Parts, TMDs & Voltage Regulators
Refrigerators are bundled with voltage regulators (VR) & Temperature Monitoring Device (TMDs). This template is for ADDITIONAL VRs and TMDs, as well as spare parts
Spares must be procured as a kit. For every 10 refrigerators procured 1 spare kit can be ordered.
Spares for existing equipment is only available for platform eligible CCE not older than 5 years

## Slide 20: III-D. Customs and Clearance
This Section Covers
List of necessary documentation to be prepared as part of the ODP

## Slide 21
The process is different from country to country, it is therefore critical to map the processes and allocate sufficient resources for the planned activities
Note: Clearance of CCE will be the sole responsibility of government. As such, this is an area for significant forward planning and attention.
Why is this data being requested?
Customs Clearance: Required documents and information for customs clearance

## Slide 22: III-E. Central Training

## Slide 23
Note that this is not cold chain technicians training, but an orientation briefing on the new cold chain equipment and CCE OP modalities
  Project implementation modality (including documentation to be used);
  Outlining “what to do” in case of deviations;
  Warranty terms and conditions;
  Claims procedures in case of equipment failure or underperformance;
  Available support, response time and contacts (local / backup);
  Overview of basic handling and preventive maintenance requirements;
  Overview on the requirement of basic corrective maintenance to be handled by country;
  PMT and EPI should participate in the training. Additionally it could be advisable that cold chain technicians and other stakeholders affected by CCEOP take part
The training will last 1day per supplier.
Note that per diems, travel, accommodation should be covered by MoH.
What is included in the central training?
Data Point | Description
Location of Training Sessions | 
# of persons to be trained | 
Central Training
Data request

## Slide 24: IV. Submission Process & Cost overview

## Slide 25
Official Submission Process
The PMT supports MoH to submit the Operational Deployment Plan to UNICEF Supply Division together with the Request for Cost Estimate through UNICEF CO via the PS email (psid@unicef.org). Note: For countries submitting CCE OP applications from January 2018 onwards, the ODP must still be submitted to UNICEF SD for verification, however it needs to form part of the mandatory application documents that need to be submitted to Gavi
Defining the UNICEF Procurement Services process and subsequent steps
What Happens Next?
  Upon receipt of the Operational Deployment Plan, UNICEF will issue tenders for the service bundle & develop a costed operational plan (COP). The COP is based on the Operational Deployment plan shared in the tender for costing by the supplier, as well as the equipment required at each site.
  The COP will provide full details of the joint-investment requirement(s) to be submitted to Gavi and the MoH for approval.
  On approval from both parties, a final Cost Estimate will be issued in line with UNICEF Procurement Services procedures.
  Once the MoH has accepted the Cost Estimate through transfer of the indicated funds to UNICEF, UNICEF will request the Gavi joint-investment funds.
  Once both Gavi and MoH funds are received, UNICEF will commence procurement and place purchase orders for products and services.
  Before projects commence, the successful bidder/supplier will present the planned deployment to UNICEF and the Project Management Team to ensure that all parties are ready to support the project as per the agreed timeline.
Requesting a Cost Estimate including an Operational Deployment plan

## Slide 26
Cost Overview
Government joint investment | Gavi Joint Investment
Equipment | Equipment
International Freight & Insurance | International Freight & Insurance
Service Bundle | Service bundle
6% Buffer | 6% Buffer
TOTAL CCE OP Contribution | TOTAL CCE OP Contribution
SD Handling Fee : 8% or 8.5% (not covered by CCE OP) | Not applicable
Customs Clearance : Not covered by CCE OP | 
Central Training: DSA, accommodation & training venue not covered |