## Instructions
Instructions for adapting and using the template workplan
1) | Update the timeline ( year and month) of the workplan to best suit country schedule/context. E.g. If the activities began in May 2023, then the workplan can be modified to begin from the month of May in 2023.
2) | Adapt the suggested activities according to your specific planning needs
Note: high level activities existing in workplan template should remain, however TWG may choose to include additional activities from the "suggested sub activities tab" to build out as necessary and create a more detailed workplan
3) | Determine how much time each activity will require to complete (from start of sub activities to completion); and what firm deadlines (e.g. launch) may occur -- which should influence start dates of activities
4) | Mark time periods (green bars) and critical deadlines (red diamond) for relevant major activities (e.g. Launch date) in the workplan according to needed time and deadlines from step 2
5) | Assign a "responsible" individual within EPI and technical partner to follow up on execution of each task.
6) | If applicable, specify any deliverables (e.g. reports or products) that should be produced by the end of the activity in Column F
7) | At the beginning of each meeting, use the "Status" column (Column B) to check and note progress with the dropdown menu (e.g. "Complete", "On track", "Action required", "Critical delay" or "Not Started").
Edit Dropdown Options
Please edit the dropdown options by adding or changing only information in blue cells
Status
Complete
On track
Action required
Critical delay
Not yet started

## Template Workplan
NVI Operational Workplan Template | [5 empty] | Key
- Recommended amount of time to budget
- Firm deadlines (e.g. Launch date)
[6 empty] | Year 1 : xxxx | [11 empty] | Year 2 : XXXX
| Status | Activity | EPI responsible | Technical Partner | Comments or deliverables | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
| Action required | Planning for HPV introduction
| On track | Revitalize and develop schedule of TWG meetings for HPV
| Critical delay | Planning for timelines of sensitization for new stakeholders
| Not yet started | Update operational plan and budget (e.g. for new cohort phasing) and share with Gavi
| Not yet started | Communicate operational plan and budget to sub-national levels
| Not yet started | Manage fund disbursement up to sub-national levels (e.g. VIG funds for training)
| Not yet started | Communicate with subnational levels to ensure engagement of education sector
| Not yet started | Subnational: establish linkages with education officials and schools as relevant
| Not yet started | Subnational: Develop detailed microplan introduction activities and share with national
| Not yet started | Subnational: Microplan activities carried out in time for introduction
| Not yet started | Secure Vaccine Supply/Cold Chain
| Not yet started | Review cold chain readiness at all levels to identify gaps and develop mitigation
| Not yet started | Place vaccines order (factor in shipment time)
| Not yet started | Clear vaccine supply from customs
| Not yet started | Forecast vaccine need for subnational level and bundle supplies
| Not yet started | Distribution of materials to subnational and HF level
| Not yet started | Updating of data tools (including printing)
| Not yet started | Update distribution plan (data tools, soc mob materials, vaccine), as relevant
| Not yet started | Transport vaccine and immunisation materials to district
| Not yet started | Distribute updated immunization tools to districts
| Not yet started | Training
| Not yet started | Develop training plan, materials, and print materials
| Not yet started | Conduct national level TOT
| Not yet started | Implement training strategy (e.g. subnational trainings)
| Not yet started | Subnational: Training activities carried out in time for introduction
| Not yet started | Social Mobilization
| Not yet started | Develop social mobilization strategy with all relevant stakeholders (e.g. adolescent CSOs)
| Not yet started | Print and distribute social mobilization materials
| Not yet started | Implement communication strategy
| Not yet started | Plan for and carry out national level launch event (and subnational level)
| Not yet started | Subnational: Conduct sensitization and communication activities in time for introduction
| Not yet started | Hold HPV assessment activities
| Not yet started | Carry out district level readiness assessment (3 and 1 month prior to introduction)
| Not yet started | Hold post launch assessment (2-6 weeks post introduction)
| Not yet started | Review HPV coverage data (monthly or as relevant for campaign delivery)
| Not yet started | If proposed and budgeted, plan and implement HPV PIE (timing in line with delivery model)

## Suggested sub activities
Planning for HPV introduction
Sensitization of all stakeholders
Identify and engage all stakeholders
If applicable, link with CSOs targeted towards adolescents
Hold sensitization meetings with education leaders and stakeholders to identify new links
Update operational plan and budget
Review existing operational plan and budget by sub-committees
Draft and compile operational plan/budget for TWG review
Communicate operational plan and budget to sub-national levels
Conduct gap analysis of HPV budget and secure remaining funding
Manage fund disbursement to subnational levels
Communicate disbursement plan to subnational levels
Confirm account information for any transfers
Distribute funds for subnational activities (e.g. VIG funds for trainings)
Collaborate with MoE on HPV vaccination support in schools
Link with national MoE on HPV activities and potential areas of support for HPV activities
Plan for district education officer communication to school administrator
Development of relevant timeline for school administrator and teacher sensitization
Opportunities for school systems to support vaccination status screening and follow up
Gain commitment for activity and communication support
Subnational: link with schools for HPV support and sensitization of district and school officials
Subnational: Microplanning activities
Ensure districts/states are prepared to microplan introduction activities and aware of national timelines
Provide districts/states with key activities for HPV introduction and delivery
Give clear communication on HPV delivery model, schedule, and eligibility to districts/states
Support subnational level to microplan HPV activities within national delivery model
Support subnational level to ensure education partners are included in microplanning and messages on linking support are clear
Develop minimum checklist for HPV activities within the routine EPI program
Integrate HPV into regular supportive supervision and refresher trainings
Secure vaccine supply
Confirm vaccine supply with global partners, including estimated shipment
Place vaccine order
Vaccine shipment
Clear vaccine supply from customs
Distribute vaccines, social mobilization materials, data tools
Develop data tools
Adapt existing reporting system to integrate/add HPV (e.g. HMIS/DHIS, registers, tally sheets, etc.)
Identify if there will need to be new sets of tools (e.g. for use by school administrators)
Identify if new stakeholders will be trained on tools (e.g. school administrators)
Develop patient cards with HPV facts and clear messages for dosing schedule
Pretest tools
Print tools
Create distribution plan
Communicate distribution plan with relevant sub-national staff
Utilize RI vaccine distribution schedule for HPV vaccine and material distribution to districts
Distribute updated immunization monitoring tools to districts
See social mobilization section for additional activities on soc mob beyond distribution
Training
Develop training strategy
Identify if new stakeholders will be trained
Communicate training strategy and plan to subnational level
Develop training materials
Arrange for printing of training materials
Print training materials (frontload as this is a common bottleneck)
Distribute training materials
Hold training of trainers
Carry out trainings according to strategy (e.g. cascading)
Review pre/post test results to determine understanding of key HPV program facts
Social mobilization
Develop social mobilization strategy/plan (leveraging existing guides/resources)
Distribute draft plan and obtain feedback from new stakeholders
Develop social mobilization materials (e.g. FAQs, posters, radio spots, etc.)
Print materials as relevant
Develop plan to reduce crisis risk and necessary response plan
Develop clear communications on AEFI for training and public response
Identify community and national champions to respond to rumors
Implement communications strategy
Plan launch ceremony
Invite guest of honor
Select event location
Create and communicate agenda
Organize performances
Organize logistics (transportation, accommodation, PA system, stage, etc.)
Conduct Launch Event
HPV introduction assessments
Carry out readiness assessments
Confirm cold chain readiness for HPV introduction
National level readiness assessment at -12 and -6 months
Subnational readiness assessment at -3 and -1 month
|  | Plan and carry out Cervarix 2-dose readiness assessment (post HCW training, pre-shipment) | Note: Only for countries using Cervarix 2-dose presentations.
Post launch assessment at 2-6 weeks post launch
Identify bottlenecks and key mitigation action to early challenges
Carry out early mitigation activities to raise coverage
Post introduction evaluation planning (if in Gavi application and budget)
Develop PIE protocol
Invite stakeholders to support PIE
Conduct PIE data collection
Analyze results from PIE and develop recommendations
Share recommendations with EPI and key stakeholders
Regularly monitor coverage