Application Form B

Assistance to Strengthen the Involvement of Civil Society Organizations (CSO) in Immunization Programs and Other Related Health Issues.

PROPOSAL PREPARED AND SUBMITTED BY THE DEMOCRATIC REPUBLIC OF CONGO (DRC)

Abbreviations et acronyms

Summary (1 page)

Section 1: The Steps involved in the Elaboration of the Application for Assistance (1 to 2 pages)

This section presents the steps to be followed by CSOs to apply for assistance with the GAVI Alliance. Start by describing the Health Sector Coordination Committee (HSCC) or its equivalent:

- HSCC name (or its equivalent)

- date when the HSCC began its operations

- frequency of meetings

- The general purpose and function of the HSCC

- name of any CSO represented within the HSCC

Next, describe the process undertaken by your country in the preparation of the application, and more specifically information on the technical support group (if such a group was created/employed), along the following points:

- Who coordinated and supervised the preparation of the assistance application?

- Who was in charge of writing the application? Was a technical assistance provided?

- Describe the CSOs individual application for assistance presentation process.

- What was the mechanism used to select CSOs for assistance?

4-6/2007: GAVI publication of request for proposal for the 2 GAVI-CSO windows: Mapping Funds and 10 countries pilot Funds

4-6/2007: Spreading the information to CSOs and other partners of the Ministry of Health. Passing over responsibility from GARSS to ICC/EVP to guide over the technical aspect of the 2 funds

6-9/2007: Presentation of drafts to ICC/EVP at the Lubumbashi meeting and feedback

Sept. 17-21 2007: GAVI team visit to the DRC. Presentation of the proposal and feedback

Sept. 25 2007: Official presentation of the project draft 1 at the Technical Secretariat of the NPC and amendments

Sept. 30 2007: Official presentation of the project draft 2 at the Technical Secretariat of the NPC and approval

October, 02 2007: Signing of a memorandum of understanding and Application Form C by various partners in charge of the implementation of the project and Signing of Application Form B by the Minister of Health.

October 05, 2007: Extraordinary assembly of the NPC presided over by the Minister of Health to share out roles to the various members of the NPC. Approval by the NPC.

October 05, 2007: Official submission to GAVI

Describe the exact functions and duties of key partners associated to the process using the table below:

## Functions and Duties of Key Partners (members of the HSCC/TSG – Health Sector Coordination Committe/Technical Support Group – and others)

| Title / Position | Organization | Member of the HSCC/TSG ? | Functions in the preparation of the Application for GAVI Alliance assistance to CSOs |
| --- | --- | --- | --- |
| Coordinator | SPD/GARSS | YES | Coordination of the entire preparation process for assistance to CSOs |
| Member | EVP | YES | Technical Support |
| Member | WHO | YES | Technical Support |
| Member | UNICEF | YES | Technical Support |
| Member | EUROP. UNION | YES | Technical Support |
| Member | USAID | YES | Technical Support |
| Member | SANRU | YES | Technical Support |
| Member | ROTARY | YES | Technical Support |
| Member | BTC | YES | Technical Support |
| Member | WORLD BANK | YES | Technical Support |

Section 2: Overview of the GAVI Alliance assistance to CSOs (1 to 2 pages)

In this section, the role (current and planned) of CSOs in providing or strengthening health services, immunization particularly, infant healthcare and in strengthening the health system should be described.

Start by ascertaining the actual role of CSOs in providing or strengthening immunization or infant healthcare, and their function in the health system. Then indicate the overall goals of the application for assistance to the GAVI Alliance for the CSOs. Choose SMART objectives (Specific, Measurable, Achievable, Realistic and Time-bound).

Draw the list of the CSOs selected as potential beneficiaries of GAVI Alliance assistance for CSOs. In the table below, make a summary of the principal activities to be undertaken by each CSO when the GAVI Alliance assistance will go into operation, and the expected outcomes for each year.

## Draw the list of CSOs selected as potential beneficiaries of the GAVI Alliance assistance to CSOs.

CSOs which will be involved in the project implementation

ECC (SANRU)

ARCC

CRS

CRRDC

CNOS

## In the table below, summarize the principal activities to be undertaken by each CSO when the GAVI Alliance Assistance will go into operation, and the expected outcome in each of the years.

| CSO | Major activities | Expected outcomes |
| --- | --- | --- |
|  |  | 2008 | 2009 |
| ECC (SANRU) | Coordination of the CSOs to be involved in the project implementation | CSOs are better coordinated, with harmonization of activities and reporting | CSOs are better coordinated, with harmonization of activities and reporting |
|  | Technical, logistical and financial support to the 25 HDs of Katanga, Kasai-Oriental and Kasai-Occidental | All planned resources and inputs are provided to the HDs and ICs are improving | All planned resources and inputs are provided to the HDs and ICs are improving (at least 157,913 children aged 0 – 11 months have received three doses of DTP-HepB3/OPV3, at least 157,913 children aged 0 – 11 months have received one VAR dose, at least 170,934 pregnant women have received at least 2 ATV doses) |
|  | Technical, logistical and financial support to the EVP branches for the 25 HDs identified | The branches are strengthen to monitor the HDs | The branches are strengthen to monitor the HDs |
|  | Strengthening partnership and coordination | Effective participation at all meetings of the various bodies or committees at all the levels | Effective participation at all meetings of the various bodies or committees at all the levels |
| ARCC | Technical, logistical and financial support to the 14 HDs of Kinshasa and Kasai-Oriental | All planned resources and imputs are provided to the HDs and ICs are improving | All planned resources and inputs are provided to the HDs and ICs are improving (at least 157,913 children aged 0 – 11 months have received three doses of DTP-HepB3/OPV3, at least 157,913 children aged 0 – 11 months have received one VAR dose, at least 170,934 pregnant women have received at least 2 ATV doses) |
|  | Technical, logistical and financial support to the EVP branches for the 14 HDs identified | The units are strengthen to supervise the HDs | The branches are strengthen to monitor the HDs |
|  | Strengthening partnership and coordination | Effective participation at all meetings of the various bodies or committees at all the levels | Effective participation at all meetings of the various bodies or committees at all the levels |
| CRS | Technical, logistical and financial support to the 26 HDs of Kasai-Oriental and Sud-Kivu | All planned resources and inputs are provided to the HDs and ICs are improving | All planned resources and inputs are provided to the HDs and ICs are improving (at least 157,913 children aged 0 – 11 months have received three doses of DTP-HepB3/OPV3, at least 157,913 children aged 0 – 11 months have received one VAR dose, at least 170,934 pregnant women have received at least 2 ATV doses) |
|  | Technical, logistical and financial support to the EVP branches for the 26 HDs identified | The branches are strengthen to monitor the HDs | The branches are strengthen to monitor the HDs |
|  | Strengthening partnership and coordination | Effective participation at all meetings of the various bodies or committees at all the levels | Effective participation at all meetings of the various bodies or committees at all the levels |
| CRRDC | Support for Communication for behavioral change activities and social mobilization in all the 65 HDs selected through the Red-Cross and Community Bridging volunteers networks | The volunteers and community bridgers are trained and provided with working tools. Community involvement is palpable. The abandon rate is low. | The abandon rate drops by at least 10%, the number of children uncovered falls by at least 50% relative to the current level, the beneficiary population is satisfied with the intervention |
|  | Strengthening partnership and coordination | Effective participation at all meetings of the various bodies or committees at all the levels | Effective participation at all meetings of the various bodies or committees at all the levels |
| CNOS | Support for Advocacy activities (at the national and provincial levels) and social mobilization, through the networks of local NGOs; field visits for DQA (Data Quality Assurance) and assessment of the level of satisfaction of the beneficiary community | At least 2 Advocacy meetings are now organized at all levels, at least 1 visit is made each semester at the level of the EVP branches to the targetted HDs | The budget allocated for health has increase, the abandon rate has dropped, the number of uncovered children has fallen, the beneficiary population is satisfied with the intervention |
|  | Assistance to local NGOs working in the selected HDs | Local NGOs are chosen, supported financially and are involved in the immunization program | Local NGOs are supported financially and are involved in the immunization program |
|  | Strengthening partnership and coordination | Effective participation at all meetings of the various bodies or committees at all the levels | Effective participation at all meetings of the various bodies or committees at all the levels |

Enfin, indiquez comment vous entendez poursuivre le programme, du point de vue technique et financier, quand les ressources de GAVI seront terminées (le cas échéant), en donnant la source et le montant du financement potentiel.

Finally, indicate how you will carry on with the program, from a technical and financial viewpoint, when the GAVI resources will be exhausted (as the case might be), while providing the source and the amount of the potential financing.

Section 3: Program Implementation Plan (1-2 pages)

Prepare and present the general program implementation plan for the duration of the assistance to CSOs, on the basis of the individual programs implementation plans made in the CSOs applications. It is important to choose the best framework for the plan and ensure that the following elements are included:

- Introduction: justifications and summary of outcomes, objectives and benchmarks

- Specific activities for the project implementation and timeline

- Organization and management of the project

- Global strategy to attain the desired outcomes

- How will the project assist in achieving the CMAP and/or in the proposal for a GAVI assistance to the HSS

- How will this project be coordinated with other activities, and what role do the key participants play

Section 4: Monitoring and Evaluation (1 page))

In this section, the indicators employed to monitor the outcomes in the course of the GAVI Alliance Assistance to CSOs are to be presented. These indicators are based on the indicators presented in the CSOs Applications and should reflect the indicators used in the CMAP and/or the proposal for GAVI assistance to the HSS. Enter the required information in the table below.

## The indicators employed to monitor the outcomes

## (See table below)

| Activities | Indicators | Reference Estimation1 | Data source | Date estima-tion référence | Target | Date for target |
| --- | --- | --- | --- | --- | --- | --- |
| Micro-planning/Enumeration | No. of HAs with enumerated pop. and with an appropriate microplans |  | Reports on microplanning meetings, reports on supervision, and reports on activities |  | 100% of HAs with enumerated populations and appropriate microplans | Jan 08 Jan 09 |
| Provision of means of transport and cold chain | No. of motorcycles and bikes provided, No. Of cold chain operation days | The quick evaluation will indicate the situation in each of the HDs and HAs | Reports on activities, reports on supervision, equipment delivery slip | Jan 08 | 100% of HDs have motorcycles, 100% of HAs have bikes and cold chain equipment for advanced strategies | Dec 08 |
| Training of the staff in EVP management | No. of HDMT, IT and ITA staff trained in EVP management | The quick evaluation will provide information on the training needs of each of the HDs | Reports on training, reports on activities, reports on supervision | Jan 08 | 100% of target HDMT members, and IT and ITA members are trained/refreshed in EVP management | Dec 08 |
| Production of management tools, communication supports, conduct of sensitization activities | No. of facilities supplied with tools and communication supports, No. of Community Bridgers trained, No. of sensitization sessions held | The quick evaluation will provide information on the choice of means of communication and the community bridgers in each HD | Reports on supervision, reports on activities | Jan 08 | 100% of HDs and HAs are supplied with management tools, 100% of the community bridgers identified are trained, x sensitization sessions have been carried out | Dec 09 |
| Immunization Accelerations | IC by infectious disease, No. of immunized infants from 0 to 11 months, abandon rate | The quick evaluation will provide information on the HDs /HAs to be covered | EVP reports, SNIS reports (National Health Information System), reports on supervision and reports on d'activités | Jan 08 | At least 90% of targetted children have received vaccines | Dec 2008, Dec 2009 |
| Supervision, Monitoring and Evaluation of the activities | No. of supervisions carried out, No. of monitoring meetings held in the HDs |  | Reports on supervision, reports on monitoring meetings and reports on activities |  | More than 80% of planned supervisions are achieved, More than 40% of planned monthly meetings are held | Each quarter |

1 If reference data is not available, indicate whether the collection of reference data has been scheduled and the exact date of collection.

Finally, give detail information on the mechanisms to be adopted to monitor these indicators, including the role of beneficiaries in monitoring the progress of activities, as the case may be.

Section 5: Implementation (1 to 2 pages)

In this section, the methods of managing the GAVI Alliance assistance to CSOs should be described. Provide the following information:

- Name of the organization charged with managing the program implementation

- Name of the organization charged with the coordination, monitoring and quality control

- Role of the HSCC (or its equivalent) in the project implementation

In the table below, describe the precise functions and duties of key partners in the project implementation:

## Functions and Duties of Key Partners (HSCC/TSG and others)

| Title / Position | Organization | HSCC Member | Functions in the implementation of the GAVI Alliance assistance to CSOs |
| --- | --- | --- | --- |
| Secretary General of the Ministry of Health | Ministry of Health | YES | President of the HSSS National Pilot Committee |
| Director of the SPD | Ministry of Health | YES | Coordinator of the HSSS NPC Technical Secretariat |
| Diseases Directorate | Ministry of Health | YES | President of the Diseases Commission of the NPC Technical Secretariat |
| Director of the Primary Healthcare Directorate | Ministry of Health | YES | President of the MCH Commission |
| Director of the Pharmacy Directorate | Ministry of Health | YES | President of Inputs Management Commission |
| Director of Healthcare Facilities | Ministry of Health | YES | President of Contracts Commission |
| Director of the Human Resources Directorate | Ministry of Health | YES | President of Human Resources Commission |
| WHO Representative | WHO / DRC | YES | Technical Assistance for the implementation of HSSS |
| UNICEF Representative | UNICEF / DRC | YES | Technical and Financial Assistance for the Revitalization and Mother and Child Survival Program |
| Director of Health Programs | USAID | YES | Technical and Financial Assistance for the program implementation |
| Head of the Health Department | WORLD BANK | YES | Technical and Financial Assistance for the program implementation |
| Head of Development, Environmental and Regional Cooperation Division | European Union Delegation | YES | Technical and Financial Assistance for the program implementation |
| Medical attaché, Embassy of Belgium | DGCD | YES | Technical and Financial Assistance for the program implementation |
| Director | SANRU | YES | Leader of the consortium charged with the program implementation |
| Country Representative | CRS | YES | Member of the consortium charged with the program implementation |
| President | ARCC | YES | Member of the consortium charged with the program implementation |
| President | CRRDC | YES | Member of the consortium charged with the program implementation |
| President | CNOS | YES | Partner (non-member) of the consortium charged with the program implementation |

Describe the mechanism for the financial management of GAVI Alliance assistance to CSOs:

- Mechanism for the transfer of GAVI Alliance finances to CSOs in the country

- Mechanism (and responsibility) for the budget approval and utilization

- Planned duration of the budget approval and transfer process

- Disbursement mechanism for the GAVI Alliance finances to CSOs

- Auditing procedures (and contact information of the controllers, if known)

- Justification for management fees (if applicable)

Finally, describe the measures taken to report progress in the implementation and utilization of the GAVI Alliance finances for the CSOs, including the body in charge of preparing the annual situation reports.

Section 6: Cost and Financing of GAVI Alliance Assistance to CSOs (1 page)

In this section, the total amount of GAVI Alliance finances available for the CSOs is determined and the annual costs of all the proposed activities is calculated. That said, the costs should not surpass available finances.

The GAVI Alliance finances to be made available for the CSOs are shown in Table 2 of Chapter 4 (directives by the GAVI Alliance for assistance to CSOs). Indicate this total at the beginning of this section.

Thereafter, prepare a budget based on the costs of all the activities (of the CSOs) for the period of the GAVI Alliance assistance. Add or remove lines in the table below to produce the exact number of activities for each CSO. Ensure that the total managing costs of the assistance are included, as well as the auditing fees.

Convert all the CSOs application for assistance expenses into US$ (at current rate).

## Costs of implementing the GAVI Alliance Assistance for CSOs

| Assistance for the Activities (of each CSO) | Yearly Cost in US$ | TOTAL COST |
| --- | --- | --- |
|  | 2008 | 2009 |  |
| ARCC | 429 950 | 360 725 | 790 675 |
| CNOS | 108 500 | 57 062 | 165 562 |
| CRRDC | 357 228 | 290 669 | 647 897 |
| CRS | 809 461 | 592 988 | 1 402 449 |
| SANRU | 895 395 | 640 525 | 1 535 920 |
| Managing Expenses (all the CSOs) | 333 008 | 333 008 | 666016 |
| Managing Expenses (of HSCC/TSG) | 25 000 | 25 000 | 50 000 |
| Financial auditing costs (for all the CSOs) | 30 000 | 30 000 | 60 000 |
| TOTAL COSTS | 2 988 542 | 2 329 977 | 5 318 519 |

Section 7: Approval of the Application for Assistance

Representatives of the Health Sector Coordination Committee (HSCC), or its equivalent, will approve the application, and the HSCC president will sign the application on their behalf. All HSCC members (or its equivalent) should sign the minutes of the meeting during which the Application for Assistance to GAVI Alliance for the CSOs has been approved. The minutes should be attached to the application for assistance.

The signatures of HSCC members is regarded as a consent for the information and projects presented in this application for assistance in the implementation of these projects. It does not presuppose any financial or legal commitment of the partner institution or individual.

- Contact Person : Name, position, organization, phone number, fax number, address, email.

APPENDIXES

| Document | Organization | Available | Duration | Attachment number |
| --- | --- | --- | --- | --- |
| Timeline |  | Yes | 2008-2009 | 1 |
| HD list |  | Yes | 2008-2009 | 2 |
| Map of Targetted HDs |  | Yes | 2008-2009 | 3 |
| Consortium constitution document (collaboration and partnership agreement) |  | Yes | 2008-2009 | 4 |
| Minutes of the NPC meeting |  | Yes | oct-07 | 6 |
| Raw Bank Banking form |  | Yes | oct-07 | 8 |
| CSOs Banking form |  | Yes | oct-07 | 9 |
| ECC Registration Statement and Status | ECC (Sanru) | Yes | 1941 | 10 |
| CRS Registration Statement and Status | CRS | Yes | 1974 | 11 |
| CRRDC Registration Statement | CRRDC | Yes | 1961 | 12 |
| ARCC Registration Statement | ARCC | Yes | 2004 | 13 |
| CNOS Registration Statement | CNOS | Yes | 2004 | 14 |
| CRRDC Status | CRRDC | Yes | 2000 | 15 |
| ARCC Status | ARCC | Yes | 2001 | 16 |
| CNOS Status | CNOS | Yes | 2003 | 17 |
| ECC Annual Report | ECC (Sanru) | Yes |  | 18 |
| CRS Annual Report | CRS | Yes | 2005 | 19 |
| CRRDC Annual Report | CRRDC | Yes | 2000-2006 | 20 |
| ARCC Annual Report | ARCC | Yes |  | 21 |
| CNOS Annual and Financial Report | CNOS | Yes | 2006 | 22 |
| ECC Financial Report | ECC (Sanru) | Yes | 2006 | 23 |
| CRS Financial Report | CRS | Yes | 2006 | 24 |
| CRRDC Financial Report | CRRDC | Yes | 2006 | 25 |
| ARCC Evaluation Report | ARCC | Yes | 2001 | 26 |
| CRS Strategic Plan | CRS | Yes |  | 28 |
| ARCC Strategic Plan | ARCC | Yes | 2005-2009 | 29 |
| CNOS Strategic Plan | CNOS | Yes | 2007-2012 | 30 |
| CNOS and Global fund Cooperation Agreement | CNOS | Yes | 2005 | 31 |
| CRS-DRC Cooperation Agreement | CRS | Yes |  | 32 |
| CRRDC 2007 Action Plan | CRRDC | Yes | 2007 | 33 |
| Application form C |  | Yes | 2008-2009 | 34 |

Appendix 1. ACTIVITIES TIMELINE

| Domain | Activities / Duties | Responsables | Expected Outcomes | Means of verification | YEAR 1 | YEAR 2 |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 |
| Project Management and Reporting | Finalize the signing of the various documents of the project by the partners involved | COP | All the documents of the project are signed by the partners concerned | The signed documents of the project | X |  |  |  |  |  |  |  |
|  | Employ and install the project staff | COP and Partners | The staff of the 9 branches have been employed and installed | List of the project staff, organizational chart | X |  |  |  |  |  |  |  |
|  | Elaborate a handbook on the project procedures | COP | The project management procedure handbook is available | The procedures handbook is elaborated | X |  |  |  |  |  |  |  |
|  | Organize the project launch workshop | COP / STCNP | A project launch workshop has been organized | Report on the launched workshop, report on activities | X |  |  |  |  |  |  |  |
|  | Order all the equipment and inputs to be bought for the project | COP | The project equipment and inputs have been purchased | Reports on activities, Inputs delivery slips | X |  |  |  |  |  |  |  |
|  | Distribute all the equipment and inputs acquired for the project | COP and Partners | The equipment and inputs have been distributed in all the facilities supported by the project | Delivery slips, reports on the project activities | X | X |  |  |  |  |  |  |
|  | Organize quarterly project evaluation meetings | COP and Partners | Four quarterly reviews are held each year | Reports on the project activities | X | X | X | X | X | X | X | X |
|  | Submit the action plans and quarterly reports to the NPC Technical Secretariat | COP and Partners | The four reports and quarterly action plans are transmitted to the NPC Technical Secretariat | Reports on the project activities, NPC Technical Secretariat acknowledgement of receipt and/or feedback | X | X | X | X | X | X | X | X |
|  | Organize yearly project evaluation meetings | COP and Partners / NPC | An evaluation workship is now held every year | Reports on the project evaluation workshop |  |  |  | X |  |  |  | X |
|  | Submit action plans and annual reports to the GAVI Alliance Secretariat | NPC Technical Secretariat | Action plans and reports are now transmitted annually to the GAVI Secretariat | GAVI Acknowledgement of receipt and/or feedback |  |  |  | X |  |  |  | X |
|  | Introduce the specific project monitoring tool/software | COP and Partners | A project monitoring software is now operational | Software Product (M&E) | X |  |  |  |  |  |  |  |
| Capacities Development and Activities Planning | Conduct quick evaluations in the selected HDs | COP and Partners | A quick evaluation is done at each of the targetted HDs | Evaluation reports | X |  |  |  |  |  |  |  |
|  | Train the staff in EVP management | EVP/Partners | 100% of HDMT, IT and ITA members have been trained/recycled in EVP management | Reports on activities, reports on training, report on supervision | X |  |  |  |  |  |  |  |
|  | Train the Community Bridgers and Health committee members | EVP/Partners | 100% of the Community Bridgers and Health committee members have been chosen and trained | Reports on activities, reports on training, report on supervision | X |  |  |  |  |  |  |  |
|  | Provide bonuses to motivate the staff (Performance contracting) | Partners | The project personnel receives a monthly payment depending on the performance contract | Performance contracting, financial reports, pay slip | X | X | X | X | X | X | X | X |
|  | Promote gender equality in all activities and at all levels | COP and Partners / NPC | At least 30% of the staff involved at all the levels are now women | Reports on activities | X | X | X | X | X | X | X | X |
|  | Support enumeration activities in the HAs and HDs | ICC, COP and Partners | 100% of HAs have now enumerated their populations and have appropriate microplans | Reports on activities and report on monitoring and supervision | X |  |  |  | X |  |  |  |
|  | Support microplanning in the HAs, HDs and the consolidation of the branches | ICC, COP and Partners | 100% of the HDs and HAs now have consolidated microplans | Reports on microplanning meetings | X |  |  |  | X |  |  |  |
| HDs Activities Monitoring | Support monitoring meetings at the HAs, HDs and branches | ICC, COP and Partners | At least 80% of HAs, HDs and branches planned monitoring meetings are held | Report on monitoring meeting, report on supervision and activities | X | X | X | X | X | X | X | X |
|  | Support the holding of Board and Management Committee meetings | COP and Partners / MIP | 100% of the HDs now have operating Boards of Administration and Management Committees | Reports/minutes of the Board and Management Committee meetings | X | X | X | X | X | X | X | X |
|  | Provide the HDs and HAs with the required means of transport to undertake supervisions | COP and Partners | 100% of the HDs now have motorcybles 100% of the HAs now have bikes | Equipment delivery slips, reports on activities, reports on supervision | X | X |  |  | X | X |  |  |
|  | Provide the EVP branches with the logistical means to monitor activities in the HDs | COP and Partners | The 9 branches targetted by the project now have logistics to monitor the activities | Equipment delivery slips, reports on activities, reports on supervision | X | X |  |  | X | X |  |  |
| Strengthening of local CSOs Capacities | Train local CSOs on immunization and their role the immunization program | HDMT/Partners | 100%¨of local CSOs in the HDs are now trained in immunization and the role they have to play | Reports on training, reports on activities, reports on supervision | X | X |  |  | X | X |  |  |
|  | Provide financial support to the selected CSOs for their activities | COP/CNOS/HDMT/ Partners | 100% of targetted CSOs now have financing for their community mobilizers | Financial reports, reports on activities | X | X | X | X | X | X | X | X |
| Quality Improvement, Increase of the accessibility and utilization of immunization services | Supply vaccines and other immunization equipment | EVP | 100% of the targetted HDs/HAs now have vaccines and equipment for immunization | Equipment delivery slips, reports on activities, reports on supervision | X | X | X | X | X | X | X | X |
|  | Establish mechanisms to reduce missed opportunities, the abandon rate and losts of vaccines | HDMT, IT, Community Bridgers and local CSOs | At least 157,913 children aged 0 to 11 months have now received 3 doses of DTP-HepB3/OPV3 and 1 VAR dose, at least 170,934 pregnant women have now received at least 2 dose of ATV, the abandon rate is less than 10% in at least 90% of the HDs | Reports on activities, EVP reports, reports on supervision, SNIS reports | X | X | X | X | X | X | X | X |
|  | Organize immunization accelerations | HDMT/COP/Partners | At least 90% of the targetted children have been vaccinated | Reports on activities, EVP reports, reports on supervision, SNIS reports | X | X | X | X | X | X | X | X |
|  | Support advanced strategies in the HAs | HDMT/Partners | 100% of HAs now have cold chain and transport equipment to carry out advanced strategies | Reports on activities, EVP reports, supervision reports, SNIS | X | X | X | X | X | X | X | X |
|  | Support mobile strategies where necessary | HDMT/Partners |  | EVP report report on activities | X | X | X | X | X | X | X | X |
|  | Advocate for the opening of new facilities and the rehabilitation of existing facilities | COP/CNOS/ICC/NPC | The budget allocated for the health sector has now increased | Financial report | X | X | X | X | X | X | X | X |
|  | Provide immunization cards to the targetted children and to pregnant women | HDMT/Partners | 100% of the targetted children and of pregnant women now have immunization cards | Report on surveys, supervision and activities | X | X | X | X | X | X | X | X |
|  | Integrated immunization activities into private and parastatal structures | HDMT/Partners | At least 90% of private and parastatal health facilities now carry out immunization | Reports on activities, reports on supervision | X | X | X | X | X | X | X | X |
|  | Carry out operations research | HDMT/COP/Partners |  |  | X | X | X | X | X | X | X | X |
| Improvement of the Cold Chain, in the provision and distribution of vaccines and in injection security | Update the cold chain rehabilitation plan | HDMT/Partners | A rehabilitation plan is now in place in each target HD | Reports on activities, reports on supervisions, HDs action plan | X |  |  |  | X |  |  |  |
|  | Ensure a periodical inventory of the cold chain materials | HDMT/Partners | An inventory of all cold chain materials is now carried out each quarter in all the HDs | Transmitted inventory | X | X | X | X | X | X | X | X |
|  | Equipe the immunization facilities with cold chain and fuel | HDMT/COP/Partners | 100% of the HDCOs and HAs now have cold chain materials and fuel for their immunization activities | The inventories, reports on activities | X | X | X | X | X | X | X | X |
|  | Ensure the regular maintenance of the cold chain material | EVP/Partners | 100% of the cold chain materials now operate permanently (30days on 30) | EVP report, reports on activities, temperature slips, inventories | X | X | X | X | X | X | X | X |
|  | Advocate for the creation of a “Vaccines Purchase” budget line | COP/CNOS/ICC/NPC | The budget allocated for the health sector has now increased | Financial report | X | X | X | X | X | X | X | X |
|  | Improve on the vaccines and other EVP equipment distribution system | HDMT/EVP/Partners | 100% of vaccines and other EVP equipment are now available in all the facilities targetted for the project immunization | Delivery slip, inventory slips, EVP reports, report on activities | X | X | X | X | X | X | X | X |
|  | Provide auto-disable syringes (ADS) and receptacles | EVP | 100% of ADS and receptacles are now available in all the facilities targetted by the project | Delivery slip, inventory slips, EVP reports | X | X | X | X | X | X | X | X |
|  | Supply health facilities with incinerators | HDMT/EVP/Partners | All the targetted structures now have incinerators | Reports on activities | X | X | X | X | X |  |  |  |
| Communication, Coordination and Partnership Strengthening for EVP | Advocacy with Governments and national and provincial assemblies as well as partners | COP/CNOS/ICC/NPC |  |  | X | X | X | X | X | X | X | X |
|  | Advocate for the introduction of courses on immunization and the EVP in schools and institutions of medicine and nursery sciences | COP/CNOS/ICC/NPC | The Schools/Institutes of Medicine and Nursery Sciences now give courses on immunization and EVP | Official program of the courses, reports on school and academic activities | X | X | X | X | X | X | X | X |
|  | Train and supply the community bridgers with sensitization materials | HDMT/COP/Partners | 100% of the identified and trained Community Bridgers have been supplied with sensitization materials | Reports on training, reports on supervision, reports on activities | X |  |  |  |  |  |  |  |
|  | Supervise the community bridgers | HDMT / IT | At least 80% of the Community Bridgers planned supervisions have been carried out | Reports on supervision and reports on activities | X | X | X | X | X | X | X | X |
|  | Sensitize local CSOs to participate in the immunization program | COP/CNOS/HDMT/ Partners | At least 80% of CSOs sensitization campaigns are held, effective involvement of the CSOs in the immunization campaign | Reports on activities | X | X | X | X | X | X | X | X |
|  | Strengthen CSOs involvement in the NPC and Provincial Committees | COP/CNOS/ICC/NPC | CSOs participate regularly in all the NPC/CPP/GARSS reviews | NPC/Provincial committees meetings minutes | X | X | X | X | X | X | X | X |
|  | Strengthen CSOs involvement in the ICCs at national, intermediary and peripheral levels | COP/CNOS/ICC/NPC | The CSOs are now involved in all the ICC meeting at all levels | ICC meetings minutes | X | X | X | X | X | X | X | X |
|  | Evaluate the extent of beneciaries satisfaction in the HDs concerned | COP/CNOS/HDMT/ Partners |  | Reports on supervision, activities and surveys |  |  | X | X | X | X | X | X |

Appendix 2. LIST OF HEALTH DISTRICTS SELECTED

| No | Province | EVP branch | Partner | HD | Semester Target Population 3.49% (DTP) | DTP3 |  | VAR |  | ATV2+ |  | Tx Ab DTP1/3 | Children uncovered |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | CV | VC | CV | VC | WomenV | VC |  |  |
| 1 | Sud-Kivu | Bukavu | CRS | Bagira-Kasha | 971 | 982 | 101% | 1 109 | 114% | 1 026 | 92% | 19.2 | - 244 |
| 2 | Kinshasa | Kinshasa-Ouest | Rotary | Bandalungwa | 2 454 | 1 996 | 81% | 2 067 | 84% | 1 686 | 60% | 3.9 | 378 |
| 3 | Kinshasa | Kinshasa-Ouest | Rotary | Barumbu | 2 052 | 1 959 | 95% | 1 943 | 95% | 1 823 | 78% | 7.0 | - 55 |
| 4 | Kasai-Oriental | Lodja | CRS | Bena-Dibele | 1 212 | 1 940 | 160% | 1 315 | 108% | 1 652 | 119% | 4.3 | - 816 |
| 5 | Kasai-Oriental | Kabinda | SANRU | Bibanga | 1 730 | 1 631 | 94% | 1 391 | 80% | 1 537 | 78% | 9.8 | - 79 |
| 6 | Kinshasa | Kinshasa-Ouest | Rotary | Binza-Météo | 5 424 | 3 664 | 68% | 3 690 | 68% | 4 574 | 74% | 15.5 | 1 090 |
| 7 | Kinshasa | Kinshasa-Ouest | Rotary | Binza-Ozone | 5 055 | 3 104 | 61% | 3 742 | 74% | 3 029 | 52% | 6.9 | 1 722 |
| 8 | Katanga | Kabondo Dianda | SANRU | Bukama | 4 786 | 4 032 | 84% | 3 976 | 83% | 4 976 | 91% | 1.4 | 697 |
| 9 | Kinshasa | Kinshasa-Centre | Rotary | Bumbu | 5 598 | 3 600 | 64% | 3 339 | 60% | 5 003 | 78% | 24.4 | 834 |
| 10 | Sud-Kivu | Bukavu | CRS | Bunyakiri | 2 079 | 1 160 | 56% | 1 318 | 63% | 1 568 | 66% | 13.9 | 731 |
| 11 | Katanga | Kabondo Dianda | SANRU | Butumba | 2 670 | 1 638 | 61% | 1 750 | 66% | 1 819 | 59% | 15.6 | 729 |
| 12 | Kasai-Oriental | Mbuji Mayi | SANRU | Dibindi | 3 995 | 3 494 | 87% | 3 114 | 78% | 3 715 | 81% | 7.5 | 218 |
| 13 | Kasai-Oriental | Lodja | CRS | Dikungu | 1 994 | 1 497 | 75% | 1 021 | 51% | 1 289 | 56% | 9.2 | 346 |
| 14 | Kasai-Oriental | Mbuji Mayi | Rotary | Diulu | 5 216 | 4 187 | 80% | 3 612 | 69% | 3 920 | 66% | 6.5 | 737 |
| 15 | Kasai-Oriental | Lodja | CRS | Djalo-Ndjeka | 1 132 | 901 | 80% | 1 149 | 101% | 1 193 | 92% | 6.8 | 165 |
| 16 | Sud-Kivu | Bukavu | CRS | Ibanda | 4 278 | 954 | 22% | 951 | 22% | 1 047 | 21% | 9.7 | 3 222 |
| 17 | Katanga | Kabondo Dianda | SANRU | Kabondo-dianda | 3 605 | 2 899 | 80% | 2 818 | 78% | 3 297 | 80% | 8.2 | 446 |
| 18 | Katanga | Kamina | SANRU | Kabongo | 4 923 | 3 202 | 65% | 3 779 | 77% | 3 780 | 67% | 9.9 | 1 370 |
| 19 | Sud-Kivu | Bukavu | CRS | Kalonge | 2 134 | 1 151 | 54% | 952 | 45% | 1 374 | 56% | - 11.7 | 1 104 |
| 20 | Katanga | Kamina | SANRU | Kamina | 4 322 | 4 395 | 102% | 3 822 | 88% | 3 713 | 75% | 4.8 | - 295 |
| 21 | Sud-Kivu | Bukavu | CRS | Kamituga | 2 289 | 901 | 39% | 970 | 42% | 829 | 32% | 8.0 | 1 310 |
| 22 | Kasai-Occidental | Kananga | Rotary | Kananga | 3 787 | 3 186 | 84% | 2 105 | 56% | 2 818 | 65% | 7.4 | 348 |
| 23 | Katanga | Kamina | SANRU | Kaniama | 3 895 | 3 245 | 83% | 3 101 | 80% | 4 235 | 95% | 9.8 | 299 |
| 24 | Sud-Kivu | Bukavu | CRS | Kaniola | 2 400 | 965 | 40% | 996 | 42% | 1 127 | 41% | 17.9 | 1 225 |
| 25 | Kasai-Oriental | Lodja | CRS | Katako-Kombe | 1 899 | 1 663 | 88% | 1 474 | 78% | 1 234 | 57% | 2.8 | 188 |
| 26 | Katanga | Kamina | SANRU | Kayamba | 1 440 | 1 204 | 84% | 939 | 65% | 1 546 | 94% | 10.5 | 95 |
| 27 | Katanga | Kamina | SANRU | Kinda | 874 | 751 | 86% | 638 | 73% | 686 | 68% | 14.8 | - 7 |
| 28 | Katanga | Kabondo Dianda | SANRU | Kinkondja | 3 421 | 1 935 | 57% | 4 080 | 119% | 3 406 | 87% | 15.2 | 1 139 |
| 29 | Kinshasa | Kinshasa-Ouest | Rotary | Kintambo | 1 414 | 1 057 | 75% | 1 183 | 84% | 1 448 | 89% | 13.9 | 186 |
| 30 | Katanga | Kamina | SANRU | Kitenge | 3 811 | 2 910 | 76% | 2 717 | 71% | 2 678 | 61% | 9.1 | 609 |
| 31 | Sud-Kivu | Bukavu | CRS | Kitutu | 1 575 | 1 010 | 64% | 673 | 43% | 913 | 51% | 3.3 | 530 |
| 32 | Kasai-Oriental | Lodja | CRS | Kole | 1 240 | 1 060 | 86% | 909 | 73% | 1 422 | 100% | 5.5 | 118 |
| 33 | Kinshasa | Kinshasa-Centre | Rotary | Lemba | 4 350 | 3 132 | 72% | 3 417 | 79% | 3 584 | 72% | 10.2 | 864 |
| 34 | Sud-Kivu | Bukavu | CRS | Lemera | 2 387 | 1 366 | 57% | 1 449 | 61% | 1 343 | 49% | 16.4 | 754 |
| 35 | Kasai-Oriental | Lodja | SANRU | Lodja | 2 760 | 2 464 | 89% | 1 710 | 62% | 2 014 | 64% | 22.0 | - 397 |
| 36 | Kasai-Oriental | Lodja | CRS | Lomela | 1 591 | 1 427 | 90% | 1 368 | 86% | 1 476 | 81% | 7.0 | 56 |
| 37 | Kasai-Occidental | Kananga | SANRU | Lubondayi | 2 156 | 2 062 | 96% | 1 237 | 57% | 2 546 | 103% | 7.5 | - 74 |
| 38 | Sud-Kivu | Bukavu | CRS | Lulingu | 2 427 | 1 909 | 79% | 1 946 | 80% | 2 765 | 99% | 17.0 | 127 |
| 39 | Kasai-Oriental | Mbuji Mayi | SANRU | Lusambo | 1 286 | 948 | 74% | 784 | 61% | 1 185 | 80% | 13.4 | 191 |
| 40 | Katanga | Kabondo Dianda | SANRU | Lwamba | 1 830 | 877 | 48% | 2 127 | 116% | 2 143 | 102% | 29.7 | 582 |
| 41 | Kinshasa | Kinshasa-Centre | Rotary | Makala | 4 155 | 2 350 | 57% | 3 219 | 77% | 2 815 | 59% | 9.0 | 1 574 |
| 42 | Katanga | Kabondo Dianda | SANRU | Malemba-Nkulu | 3 572 | 1 794 | 50% | 2 642 | 74% | 2 125 | 52% | 5.3 | 1 678 |
| 43 | Kinshasa | Kinshasa-Centre | Rotary | Matete | 3 896 | 3 148 | 81% | 3 039 | 78% | 3 027 | 68% | 9.5 | 416 |
| 44 | Kasai-Oriental | Lodja | CRS | Minga | 2 256 | 2 027 | 90% | 1 329 | 59% | 2 039 | 79% | 9.0 | 29 |
| 45 | Kasai-Oriental | Mbuji Mayi | SANRU | Mpokolo | 4 353 | 3 314 | 76% | 3 441 | 79% | 3 748 | 75% | 8.4 | 734 |
| 46 | Katanga | Kabondo Dianda | SANRU | Mukanga | 2 953 | 1 053 | 36% | 2 764 | 94% | 1 769 | 52% | 23.9 | 1 569 |
| 47 | Katanga | Kabondo Dianda | SANRU | Mulongo | 3 622 | 1 394 | 38% | 1 740 | 48% | 2 143 | 52% | 7.4 | 2 116 |
| 48 | Sud-Kivu | Bukavu | CRS | Mulungu | 1 912 | 2 190 | 115% | 1 941 | 101% | 2 005 | 91% | 9.7 | - 513 |
| 49 | Sud-Kivu | Bukavu | CRS | Mwana | 2 046 | 2 090 | 102% | 2 314 | 113% | 1 502 | 64% | 1.6 | - 77 |
| 50 | Sud-Kivu | Bukavu | CRS | Mwenga | 1 684 | 1 652 | 98% | 1 651 | 98% | 1 738 | 90% | 7.0 | - 92 |
| 51 | Kinshasa | Kinshasa-Centre | Rotary | Ngiri-Ngiri | 2 192 | 1 608 | 73% | 1 619 | 74% | 1 245 | 50% | - 2.8 | 628 |
| 52 | Sud-Kivu | Bukavu | CRS | Nundu | 2 523 | 2 878 | 114% | 3 532 | 140% | 3 952 | 137% | 17.2 | - 951 |
| 53 | Kasai-Oriental | Lodja | SANRU | Omendjadi | 1 905 | 2 086 | 109% | 1 350 | 71% | 1 608 | 74% | 5.5 | - 302 |
| 54 | Kasai-Oriental | Lodja | SANRU | Vangakete | 1 824 | 1 627 | 89% | 1 634 | 90% | 1 779 | 85% | 20.6 | - 225 |
| 55 | Kasai-Oriental | Mbuji Mayi | SANRU | Pania Mutombo | 955 | 627 | 66% | 572 | 60% | 528 | 48% | 5.3 | 293 |
| 56 | Sud-Kivu | Bukavu | CRS | Ruzizi | 1 951 | 1 476 | 76% | 1 458 | 75% | 2 038 | 91% | 1.5 | 453 |
| 57 | Kinshasa | Kinshasa-Ouest | Rotary | Selembao | 4 703 | 2 421 | 51% | 2 771 | 59% | 2 149 | 40% | 13.0 | 1 920 |
| 58 | Sud-Kivu | Bukavu | CRS | Shabunda Centre | 2 158 | 2 663 | 123% | 2 595 | 120% | 2 625 | 106% | 12.7 | - 892 |
| 59 | Katanga | Kamina | SANRU | Songa | 2 198 | 2 043 | 93% | 1 819 | 83% | 2 303 | 91% | 10.9 | - 94 |
| 60 | Kasai-Occidental | Kananga | SANRU | Tshikaji | 2 004 | 1 510 | 75% | 1 528 | 76% | 1 667 | 73% | 5.9 | 399 |
| 61 | Kasai-Oriental | Mbuji Mayi | Rotary | Tshishimbi | 2 678 | 2 113 | 79% | 1 684 | 63% | 1 728 | 56% | 6.7 | 414 |
| 62 | Kasai-Oriental | Lodja | CRS | Tshudi-Loto | 1 097 | 903 | 82% | 892 | 81% | 844 | 67% | 11.1 | 81 |
| 63 | Kasai-Oriental | Lodja | CRS | Tshumbe | 1 372 | 1 143 | 83% | 1 028 | 75% | 897 | 57% | 10.3 | 98 |
| 64 | Sud-Kivu | Bukavu | CRS | Uvira | 3 797 | 1 091 | 29% | 809 | 21% | 1 175 | 27% | 4.4 | 2 656 |
| 65 | Kasai-Oriental | Lodja | CRS | Wembo-Nyama | 1 192 | 1 305 | 110% | 951 | 80% | 909 | 67% | 13.0 | - 308 |
| TOTAL FOR THE 65 SELECTED HDs FOR THE GAVI-CSO-DRC PRJECT | 175 459 | 128 964 | 74% | 129 003 | 74% | 139 777 | 70% | 10.1 | 32 046 |

Appendix 3. MAP SHOWING EACH OF THE CONSORTIUM PARTNERS SUPPORT AREA

# Text boxes

The Democratic Republic of Congo (DRC) has a population of approximately 63 million inhabitants with a land surface area of 2,345,000 km2. It is found in the Central African region and consists of 11 provinces; in which 56 Enlarged Vaccination Program (EVP) branches and 515 Health Districts (HDs) are dispersed. An EVP branch is a vertical structure that oversees the immunization performance of about ten HDs. HDs here equate to health districts in other countries and consist of about 15 health centers (HC) under a Health District Central Office (HDCO) and a Reference Hospital (RH). A HD is run by a Health District Management Team (HDMT) headed by the Health District Physician (HDP).

The DRC has one of the highest maternal and infant mortality rates in the world. Rates of access and utilization of preventive medical care are low due to over a decade warfare and the poor governance in the three preceding decades. While significant progress has been achieved in DTP3 immunization coverage (IC) rising from 49% in 2003 to 74% in 2006 and 85% by the first semester 2007, however, there are still areas where children do not receive vaccines; 54907 children did not receive vaccines in the first semester 2007. The re-emergence of the wild poliovirus after 6 years of interruption is without doubt one of the consequence.

Given the countrywide dispersion of these uncovered pockets, the ICC/EVP is bent on targeting its efforts in branches covering HDs with high population, and where a large number of children are yet to receive the vaccine. 65 HDs in 9 EVP branches: Kamina, Kananga, Kabondo-Dianda, Kinshasa Ouest, Kinshasa Centre, Lodja, Mbuji-Mayi and Uvira, which are in five of the eleven provinces of the country (Kasai-Occidental, Kasai-Oriental, Kinshasa, Katanga et Sud Kivu) will be covered by this project.

The criteria for selecting these HDs are: (i) low IC, (ii) high abandon rate, (iii) high population density, (iv) considerable number of children who have not received vaccines, (v) HDs already receiving a global support and (vi) HD with low threats to security.

The project has as major challenge to bring down significantly the number of children who have not received vaccines; 32046 of whom are in the 65 selected HDs, that is, 58.4% of children who have not received vaccines in the country. In fact, the average IC of these 65 HDs in the first Semester 2007 was 74%, which is less than the national average by 11%.

The current financing is meant to pursue the country’s commitment to progressively reduce the various uncovered pockets. To draw out the best from the GAVI CSO window, the country has opted for a consortium approach constituted of various CSOs (Civil Society Organizations) experienced in immunization, infant health and/or health system strengthening support. The CSOs will be implementing support projects in selected intervention districts. The CSOs involved are ECC (SANRU), ARCC, CRRDC and CRS. Note that SANRU refers to the ECC CSO, as the SANRU program is being carried out by ECC (Protestant Church of Congo).

CNOS (the National Council of Health NGOs) will also be involved in the implementation of the project together with the four aforementioned CSOs.

During the 2 years of the project, the goal of consortium with the support of the Ministry of Health and it’s partners, will be to increase IC from 74% to atleast 90% in the 65 selected HDs. The 15% gain in the selected HDs, everything being equal elsewhere, will increase the overall country IC by 4% to a figure of 89%, meeting the goal the country set for itself for in its CMAP!

To attain this outcome, the project will strive to: (a) strengthen the capacities of the local organizations involved in community sensitization and provide support to health facilities (health centers or health units), (b) train and guide community bridgers whose role is to find out those who are uncovered or out of sight, (c) provide technical support to the HDs (training, high level supervision, etc.) (d) ensure the logistics of the HDs (cold chain and transport), (e) provide bonuses for staff motivation (f) organize grassroot support for HDs and HCs in their various activities (enumeration, microplanning, advanced strategies, supervision, monitoring, immunization accelerations and operations research).

The amount of US$5,318,519 is the required budget for the implementation of the two years GAVI Alliance project (US$2,988,542 for the first year and US$2,329,977 for the second).

This proposal was elaborated under the coordination of the NPC which equates to a HSCC in the DRC.

The NPC was formed by a ministerial decree of September 05, 2006 and meets twice yearly. The ministerial decree defines its role as to: analyse technical aspects associated to the HSSS, define the major political and strategic orientations in the health domain, examine and approve the implementation of annual and multi-annual reports and plans of the HSSS, and monitor and evaluate reform implementation at all levels.

The NPC has created within its midst a technical body called NPC Technical Secretariat under the coordination of the Director of the Studies and Planning Directorate (SPD). It features among others, Directors of some Ministry of Health directorates, health project coordinators in the DRC, and Central Directorate technical support staff. It organizes a weekly ordinary meeting each Tuesday at the SPD.

It should be noted that within the NPC, there is the GIBS (Health Inter-donor Group) which assumes the strategic coordination of the principal donors in the health sector.

CSO members of the NPC Technical Secretariat which are effectively involved in the meetings are among others ECC (SANRU), ARCC, CRS, BTC (Belgian Technical Cooperation) and GTZ (German Technical Cooperation).

The GAVI Alliance Secretariat request for proposal was made available to the Ministry of Health in May 2007, and the SPD (which ensures the coordination of the NPC Technical Secretariat) and other partners like WHO and UNICEF were each provided with a copy. The Technical Secretariat of the SPD also issued the document to various national and international NGOs thereafter.

A technical body constituted of immunization experts at the country level, the ICC/EVP, was designated by the NPC Technical Secretariat to take charge of and supervise the CSOs bidding preparation process, with the final bid approval coming up to the NPC. All along the writing process, no foreign technical support assistance was requested by the country.

The major orientations of the intervention were defined by the ICC/EVP based on the various existing plans and documents: GPRSD, HSSS and CMAP. HDs found in EVP units with high population density, low IC and a high number of uncovered children were those chosen.

The ICC/EVP required a consortium approach for the application for assistance it was to receive, so to avoid  excessive dispersion of available finances. The consortium made up of CSOs meeting up with GAVI Alliance conditions produced “Application Form C” which enabled the country to come up with the current document, “Application Form B”.

Below is the scheme of how the process was went through.

This program operates in HDs which are effectively functional and its long term impact requires the following three elements:

- Ownership of this critical activity by the community through the involvement of local NGOs and other local institutions

- Health sector reform with the adoption of the HSSS and its financing by GAVI

- Significant involvement of the government which should progressively increase its contribution in the health sector in general and in immunization particularly.

Further, the recipient CSOs of the project will need to develop close working relations with other locally based CSOs in the intervention area to encourage their participation in the immunization program. Other initiatives, like “child for child”, directly involving the beneficiaries will be widely employed to instill immunization in the social habits.

CNOS will need to be involved along side various partners of the Ministry of Health to pursue an active Advocacy at the level of government and parliament with the aim of ensuring a significant increase of the proportion of the budget allocated for health.

INTRODUCTION

Maternal and infant mortality rates of the DRC are some of the highest in the world. Many of these children and women die from diseases that can be avoided through immunization. While IC has progressively been on the rise in the DRC since 2003, it has not attain a level required to immunize the target populations in all the HDs of the country. This situation can be accounted for by the lack of implication of the community and local structures in immunization activities, little staff motivation, insufficient technical, logistical and financial resources for the HDs, and the low security in parts of the country for a very long time now. This project will strive to immunize at least 90% of the children in the targetted HDs and will act as a complement to the support provided by other donors, to correct the coverage deficits.

STRATEGIES

The implementation of this project will be along three strategic lines: (a) the full and complete implementation of the 5 elements of the RED approach in operating health areas (good resource management and microplanning, advanced activities in health areas, on-the-job training, monitoring for action, and strengthening links with the community) (b) conducting immunization accelerations for non-operating health areas or health areas with very low vaccine coverage (c) promoting the integration of other child survival activities

SPECIFIC ACTIVITIES

The principal activities will be to support the planning and population enumeration, strengthen coordination, sensitize the population, train the EVP staff in management, provide transport and cold chain equipment, provide support to supervise and monitor the activities, provide support for immunization accelerations where necessary, and performance contracting with the management and health workers in the HDs.

The project will rely particularly on communication activities to ensure the attainment of the desired outcomes in the long term. The Communication for Behavioral Change related aspects targeting the direct beneficiaries of the project will be carried out by all the 5 organizations with IT support by the 3 monitoring partners of the HDs, community bridging and volunteers by CRRDC, and sensitization of local NGOs by CNOS. CRRDC and CNOS will be involved in social mobilization and the sensitization of various social groups as well as the financing of local NGOs working in the HDs. Advocacy to mobilize decision-makers support for the immunization program will go to CNOS.

The activities timeline in the appendix gives the details of the program implementation.

ORGANIZATION, MANAGEMENT AND COORDINATION OF THE PROJECT

For greater efficiency in the field and rational utilization of the resources made available by GAVI, four partners (ECC, CRS, Rotary and the Red Cross) now form a consortium led by ECC (SANRU) which will choose a COP (Chief of Party) to ensure the coordination of the interventions (monitoring of the action plan, indicators and financial management, and holding of periodical reviews with the various partners). The COP will also coordinate CNOS activities to ensure the harmonization of activities and reporting. A memorandum of understanding was signed by ECC (SANRU), on behalf of the consortium, with CNOS for this organization which represents all the civil society associations of the DRC to take up the role attributed to it in section 1 page 7 – “major activities of CNOS”.

The map in the appendix indicates the field of action of each of the partners with the exception of the Red Cross which will work with all the partners through its network of volunteers to supervise and monitor community activities.

The COP will be the project representative to the Ministry of Health, the NPC Technical Secretariat, other donors and partners of the DRC interested in this project and GAVI directly if necessary. The COP is also  charged with producing and transmitting to the Technical Secretariat of the NPC the action plans and other technical and financial reports of the project after receiving and centralizing those from the four partners in the consortium and CNOS.

All orientations and suggestions with regards to the project will be channeled through the COP who will be the representative of the project in all national and international meetings in which GAVI financing to CSOs in the DRC will be dealt with. The COP will strive to strengthen the coordination of immunization activities at the central, intermediary as well as peripheral levels through various recognized national policy mechanisms (ICC, NPC, etc.). Below is a scheme of how the organization will work out:

In the monitoring of indicators in this project and of performance generally a number of mechanisms are contemplated at the various levels:

- At the peripheral level (HAs and HDs):

- Activities in the HAs – monthly health committee meetings and monthly meetings of incumbent and assistant nurses in the presence of the community (principal beneficiary of the project) represented by the community bridgers – constitute the first level of performance and orientation monitoring.

- At the HD level, apart from HDMT supervision visits to the HAs, 3 key monitoring mechanisms are planned:

- Firstly, montly meetings between the HDMT and incumbent nurses to evaluate performances and share experiences which go a long way to contribute to the training of nurses.

- While, monthly meetings of management committees give room for the monitoring of indicators and formulation of relevant recommendations.

- Finally, the board of directors adopt the action plans of the HDs and endorse the annual reports of the said HDs. Here, the community, the HD management team in the presence of the provincial authority will discuss about the performance of the HD

- At the intermediary level (EVP branch/Health Districts Area/Province)

EVP branches – HDMT quarterly meetings should enable the consolidation of data as well as the analysis of the performances of each of the HDs and the formulation of recommendations.

Further, HDs are monitored by the supervision visits of EVP branches or Health Districts Areas to ensure a better performance of Health Districts.

- At the national level

Besides the monitoring done by each of the NGOs of the consortium as well as the COP team, other mechanisms include:

- CNOS monitoring by regular field trip for Advocacy with decision-makers, sensitization of other NGOs to involve themselves in the immunization program and more especially to assess the level of execution of the consortium action plan and evaluate the extent of satisfaction of the beneficiary population

- ICC/EVP meetings for the analysis of their performances each month

- Weekly GARSS meetings during which a summary of project implementation activities will be made

- Various national level experts supervision visits at the provinces, branches or targetted HDs.

It should be noted that each quarter, the COP using the CSOs reports will produce a comprehensive report to the GARSS and ICC. These reports should describe the activities undertaken within the period, the progress made in detale, the outcomes attained, the problems encountered, the solutions proposed and the lessons learned.

Evaluations will also be carried out. By the end of the first year, a mid-term evaluation will take place to evaluate success in accomplishing the project objectives. By the end of the project, a final evaluation will be made on the project impact. It will also assess the efficiency of strategies employed during the implementation of the project and make suggestions on how to apply the lessons learned in future projects.

In this project, the beneficiaries will participate directly in monitoring the indicators through the community bridgers networks, their representatives at Health Committees, Management Committees and other monitoring meetings organized at the HD or HA level.

The Technical Secretariat of the NPC gave the project execution to the consortium constituted of 4 organizations: SANRU, CRS, ARCC and CRRDC. This agreement followed the recommendations of the ICC/EVP which designated the SANRU-CRS-ARCC-CRRDC consortium as a group of trustworthy organizations satisfying the required criteria and well experienced in immunization and HDs support. Under SANRU’s leadership, the consortium has produced a document which has been approved by the NPC Technical Secretariat.

In addition to these four organizations, the CNOS is  also been included in the implementation of the project.

The choice of the NGOs to be involved in the project implementation went primarily to national NGOs as is normally expected. Of the five organizations involved in the project implementation, four are totally national (SANRU, ARCC, CRRDC and CNOS) while one is international (CRS – Catholic Relief Services). What is peculiar about CRS (the reason for including it in the consortium) is that this organization of catholic denomination works closely with the BDOMs (Medical Services of the Diocesan Office) in all the provinces and contributes to the development of the capacities of its local institutions.

The role of developing the capacities of local NGOs will also be assumed by all the organizations involved in the project implementation in these HDs. Further, SANRU, a program of the DOM-ECC, will operate in partnership with the various independent communities of this Church which have their respective legal personalities.

ARCC will work with the various rotary groups in the provinces where it will implement the project.

CRRDC and CNOS will, after the GAVI window on the mapping, continue their selection of various NGOs operating locally in the HDs, and CNOS in particular will finance these local NGOs with the credit line provided to this effect for their participation and their projects in the immunization program.

This is a DRC government project, and the NPC Technical Secretariat is its forefront. It is charged with the coordination, monitoring and quality control. Given that immunization requires some technical expertise, the NPC Technical Secretariat will operate in collaboration with the ICC/EVP in monitoring the implementation of the project. The NPC Technical Secretariat will have the final say over the annual and quarterly actions plans of the partners; will approve the budgets; analyze the different technical and financial reports which will be submitted by the COP;  initiate financial audits of the partners; and produce the annual reports and financing proposals submitted to GAVI.

The budget session will be annually from January to December. A detailed implementation plan will be elaborated. This plan will identify the activities to be accomplished in each intervention area, the indicators of the processes as well as detail information of the financial resources necessary to accomplish the activities. The plans and budgets will be prepared for approval by the NPC Technical Secretariat Coordinator latest in the month of September, and the latter will transmit this to the GAVI Alliance Secretariat for financing by October 05.

The financial resources of the approved budget will be available for use from January 1st to December 31st each year. This financial session falls in line with the government’s financial session thus acting as a complement and enabling harmonization with financial resources from the State budget allocated for Health and development assistance in the sector.

Reports on activities carried out and quarterly financial execution reports will be produced and presented for approval to the NPC Technical Secretariat Coordinator which will compile technical and financial data for an annual presentation report to GAVI. Annual reports on activities carried out and the budget execution approved by the NPC Technical Secretariat will be transmitted to GAVI before the end of the month of May of the year following the year of the budget session.

The finances will be transfered directly from the GAVI Alliance Secretariat by wire transfer to an independent bank account opened by the COP which is the body heading the project on behalf of the leader of the consortium (SANRU). The bank account will bear the title “GAVI-CSO-DRC Project”.

Then, the COP will transfer finances meant for the activities of the period concerned on the accounts of each of the four partners of the consortium and CNOS every quarter.

The finances for the upcoming quarters will be subject to quarterly technical and financial reports (including appropriate documentary evidence) submitted by the consortium members and CNOS.

The transfer of finances to EVP branches and HDs will equally be through the banks in places where banks are opened. In EVP branches and HDs where the banking system cannot be used, other means of transfer (money transfer systems) like Mister Cash, Western Union, Soficom will be employed.

The use to which the finances are employed will be audited. That is, internal audits by each partner of the consortium and CNOS to check whether the use to which the finances are put to comply with the quarterly action plan and the finances management procedures adopted.

The partners will also provide financing for external audits once a year to be undertaken by a internationally renown accounting firm.

In addition, the NPC Technical Secretariat will have the leeway to carry out audits, not to be financed by the partners of the consortium, at an interval determined together with the COP.

With regards to expenses for managing the CSOs, this will cover the items associated with CSOs operations (staff payments, rents, taxes, national and international travel where necessary, communication, Internet, health and accident insurance, etc). Documentary evidence of these expenses will be transmitted to the NPC Technical Secretariat if the latter and GAVI so require.

SANRU: Support to the HDs

“The Health Sector Coordination Committee (HSCC) which represents the government and partners is committed to provide its support to Civil Society Organizations in this application to implement the strategy. The HSCC equally certifies that the CSOs are organizations operating in good faith with the required competence and capacity to manage the job described.”

DEMOCRATIC REPUBLIC OF CONGO

Name: Dr. Hyppolite KALAMBAY NTEMBWA

Position:  Director of the Studies and Planning Directorate and GARSS Coordinator, Ministry

of Health

Phone number : (243) 81-700-5463   / (243) 81-520-3096

Email : depsante@micronet.cd  /  hkalambay@yahoo.fr

CMAP and/or HSS SUPPORT

This project will draw on the finances granted to the country through a variety of mechanisms including HSS finances provided by GAVI. In fact, with HSS finances, the country plans to support 65 HDs specifically: to build on their human resources (bonuses, training in PHC management); to support the establishment and operation of RHs and HDMT; for the elaboration of Health District Development Plans; Rehabilitation/Contruction, Equiping, and provision of pharmaceutical products to HCs and RHs; supervision of Health Centers activities; support for community activities (water resource mobilization). This project will be a complement to the HSS as it will focus on immunization activities not sufficiently developed in the HSS.

Sixteen HDs harbor both the HSS and the present project (see Table 1). To make the most out of this considering the considerable HSS resources, bonuses will only be made available for the HSS with none for the CSOs window in these sixteen HDs. Obviously, these sixteen HDs – beneficiaries of all the various forms of assistance made by GAVI –  will be the sample HDs to evaluate the impact of the organization’s assistance in the DRC.

Table 1: HDs supported both by the HSSs and the CSO window

| Provinces | Health Districts | Provinces | Health Districts |
| --- | --- | --- | --- |
| Kasai-Occidental | Lubondaie | Katanga | Mukanga |
| Kasai-Oriental | Dibindi | Sud-kivu | Kamituga |
|  | Dikungu Tshumbe |  | Kitutu |
|  | Diulu |  | Lemera |
|  | Lodja |  | Mwenga |
|  | Lusambo |  | Nundu |
|  | Tshishimbi |  | Shabunda Centre |
|  | Vangakete |  | Uvira |

The CMAP (Consolidated Multi-annual Plan) is a clear indication of the DRC immunization goal. It has a proposed budget of more than US$330,000,000. The government and some of its partners provide some of the financing but this does not cover all the needs in all the HDs. Thus, the new GAVI window for the CSOs is a complementary financing to the CMAP ensuring the rapid achievement of the desired outcomes as indicated in this document.

This project is related to the CMAP in that the planned increase in IC by 15% in the HDs supported by the project will enable the country to improve on its overall IC by 4%, that is, attaining an IC of 89% – the goal of the DRC’s CMAP.

CRS: Support to the HDs

Through the supported HDs

It has been a long time tradition in the DRC for NGOs, especially those of a confessional character, to actively involve themselves in the various development sectors. These NGOs have increasingly assumed an important role not the least because of the country’s thirty years of bad governance and ten years of warfare engendering among other consequences, the break down of state authority and the crumbling of the leadership of the Ministry of Health.

NGOs are a stong element in the upkeep of the DRC health system and are critical in the provision of PHC. NGOs are present at all the levels of the health pyramid of the country: (1) at the peripheral level, NGOs manage and/or support health facilities (the SPD 2006 annual report estimates the proportion of HDs in the DRC managed by private and particularly confessional NGOs at 70%), mobilize the population, train nurses in their medical schools and intervene during health emergencies; (2) at the intermediary level, NGO facilities work in collaboration with the intermediary level of the Ministry of Health to plan, jointly manage, and monitor the implementation of programs at the level of HDs; (3) at the national level, NGOs are members of various bodies reflecting on the HSS, they sit in various committees and participate in meetings organized by the Ministry of Health. Medical doctors and other health personnel are also trained at the universities of some of these organizations.

Unfortunately, these NGOs often lack the necessary resources for the accomplishment of their mission thus limiting the facilities they support from attaining desired outcomes.

With this in mind, many bilateral and multilateral partners like USAID, the European Union, the World Bank, CIDA and now GAVI, have resolved to grant resources to these NGOs which go a long way to help them in their mission.

With the present GAVI financing, the goal goes well beyond improving on IC, but also to acknowledge and strengthen the role played by NGOs in the DRC. The NGOs interest in the immunization campaign will be propped up by these finances thus encouraging their collaboration and integration in the various existing mechanisms (NPC, PPC – Provincial Pilot Committe, ICC, etc).

The goal of the present financing is in line with the targets set for the MDGs (Millenium Development Goals), GPRSD, CMAP and HSSS, that is :

- To contribute to the reduction by two-third of the mortality rate of children less than 5 years by the year 2015

- To contribute to the reduction by three-quarter of the maternal mortality rate by the year 2015

The general goal is to contribute in reducing the morbity and mortality rate associated with avoidable diseases through immunization.

The specific goal is to increase the immunization coverage of children less than 12 months and pregnant women in the 65 HDs, by October 2009, from:

74% to 90% for DTP-HepB3/OPV3

74% to 90% for VAR

71% to 85% for ATV2+

ARCC: Support to the HDs

CRRDC: Support to the HDs

FINANCIAL SUPPORT TO LOCAL NGOs (BDOM, COMMUNITIES, ECC, NGOs)

SUPERVISION OF LOCAL NGOs (BDOM, COMMUNITIES, ECC, NGOs)

SUPERVISION OF LOCAL NGOs (BDOM, COMMUNITIES, ECC, NGOs)

SUPERVISION OF LOCAL NGOs (BDOM, COMMUNITIES, ECC, NGOs)

SUPERVISION OF LOCAL NGOs (BDOM, COMMUNITIES, ECC, NGOs)

DRC GAVI CSOs PROJECT CONSORTIUM

The HCSS is applying to the GAVI Alliance financing partners to provide financial assistance to support the CSOs which are able to contribute to the implementation of the HSS proposal and/or the CMAP as described in this application.

- President of HCSS (or equivalent): name, position, organization, date, signature

Name: Dr. Victor MAKWENGE KAPUT

Position: DRC Minister of Health

Date: September 02, 2007

Signature and stamp:

Members of the Health Sector Coordination Committee (or its equivalent) have approved this application during a meeting held on September 02, 2007. The signed minutes are attached.

This section must also include the name and contact information of the person to be contacted by the GAVI Alliance Secretariat for any information. Please, provide the following information:

LOCATION OF THE UNITS SUPPORTED

WITH GAVI CSO FINANCES

PMURR	:	Programme Multisectoriel d’Urgence pour Relance et Reconstruction (Multisectoral 
                                       Emergency Program for Growth and Reconstruction)

PMR		:	Programme des Médecins Résidents, dépendant de DOM-ECC, il fait

la promotion de la Médecine de famille en RDC  (Resident Physician Program, under 
                                       DOM-ECC. The program promotes family medicine in DRC)

RDC		:	République Démocratique du Congo (Democratic Republic of Congo – DRC)

RECO		:	Relais Communautaires (Community Bridgers)

(S)RSS		: 	(Stratégie de) Renforcement du Système sanitaire [Health System Strengthening 
                                       (Strategy) – HSS(S)]

SANRU III	:	Programme des SSP en Milieu Rural, programme phare de DOM-ECC [SANRU Rural 
                                       PHC (Primary Healthcare) Program, the major DOM-ECC program]

SMI		:	Santé Maternelle et infantile (Maternal and Child Health – MCH)

SSP		:	Soins de Santé Primaires (Primary Health Care – PHC)

UNICEF	:	Fonds des Nations Unies pour l’Enfance (United Nations International Children’s 
                                       Emergency Fund)

USAID		:	Agence Américaine pour le Développement International (United States Agency for 
                                       International Development)

VAT		:	Vaccin Anti Tétanique (Anti-Tetanus Vaccine – ATV)

ZS		:	Zone de santé (Health District – HD)

AC		:	Animateur Communautaire (Community Mobilizer)

ACZ		:	Atteindre Chaque Zone de santé (Approche RED) [Reaching Every District (RED Approach)]

AG		:	Administrateur Gestionnaire de la Zone de Santé (Health District Administrator or Manager)

ARCC		:	Association des Rotary club du Congo (DRC Association of Rotary Clubs)

BCG		:	Bacille de Calmette et Guérin (Bacille Calmette-Guérin)

BCZS		:	Bureau Central de la Zone de Santé (Health District Central Office – HDCO)

BDOM		:	Bureau Diocésain des Œuvres Médicales, institution de l’Eglise catholique (Medical 
                                       Service of the Diocesan Office, under the Catholic Church)

CCC		:	Communication pour le Changement de Comportement (Communication for Behavioral Change - CBC)

CCIA		:	Comité de Coordination Inter Agences (Inter-agency Coordinating Committee – ICC)

CNOS		:	Conseil National des ONG Santé (National Council of Health NGOs)

CODESA	: 	Comité de Développement et de Santé (Development and Health Committee)

COGE		: 	Comité de Gestion (Management Committee)

COP		:	Chief of Party, organe régulateur du consortium (Chief of Party, consortium regulatory body)

CRRDC	:	Croix-Rouge de la RDC (DRC Red-Cross)

CRS		:	Catholic Relief Services

CNP		:	Comite National de Pilotage de la SRSS (HSSS National Pilot Committee – NPC)

CS		:	Centre de Santé (Health Center – HC)

CV		:	Couverture Vaccinale (Immunization Coverage – IC)

DGCG		:	Direction générale de Coopération pour le développement (Directorate General for

Development Cooperation)

DOM-ECC	:	Direction des Œuvres Médicales de l’ ECC, responsable  de « SANRU » (ECC Medical 
                                       Office, managing the SANRU Rural Health Program)

DSCRP		:	Document de Stratégie pour la Croissance et la Réduction de la Pauvreté (Growth and  
                                       Poverty Reduction Strategy Document – GPRSD)

DTC3		: 	Vaccin contre la Diphtérie, Tétanos, Coqueluche et l’Hépatite B (3e dose) [Diphteria,

Tetanus, Pertussis and Hepatitis B vaccine (third dose) – DTP3]

ECC 		:	Eglise du Christ au Congo (Protestant Church of Congo)

ECZS		:	Equipe Cadre de la Zone de Santé (Health District Management Team – HDMT)

GARSS		:	Groupe d’Appui a la Restructuration du Système sanitaire en RDC (Support Group for     
                                       the Restructuring of the DRC Health System)

GAVI 		: 	Global Alliance for Vaccines and Immunization

HGR		:	Hôpital Général de Référence (Reference Hospital – RH)

JNV		:	Journées Nationales de Vaccination (National Immunization Day)

MCZ		:	Médecin Chef de Zone (Health District Physician – HDP)

MICS II 	:	Multiple Indicators Cluster Survey II

OMS		:	Organisation mondiale de la Santé (World Health Organization – WHO)

ONG 		:	Organisation Non Gouvernementale (Non-Governmental Organization – NGO)

PPAC		:	Plan Pluri Annuel Consolidé (Consolidated Multi-annual Plan – CMAP)

PEV		:	Programme Elargi de Vaccination (Enlarged Vaccination Program – EVP)