# Application Form A for:

# GAVI Alliance Support to Strengthen Coordination and Representation of Civil Society Organisations

Please fill in text directly in the boxes below, which can be expanded to accommodate your text by computer

Abbreviations and Acronyms

Please ensure that all abbreviations and acronyms presented in the application and supporting documents are included at the beginning of the application form.

ACBAR	Agency Coordinating Body for Afghan Relief

ADB		Asian Development Bank

AHDS		Afghan Health and Development Services

AHS		Afghanistan Household Survey

ANCB		Afghanistan NGO Coordinating Bureau

ANDS	Afghan National Development Strategy

APHI		Afghan Public Health Institute

APR		Annual Progress Report

AWN		Afghan Women Network

BHC		Basic Health Center

BPHS		Basic Package of Health Services

BSC		Balanced Scorecard (Afghanistan Health-Sector Balanced Scorecard)

CAO		Control and Audit Office (Government of Afghanistan)

CBHC		Community Based Health Care

CGHN		Consultative Group on Health and Nutrition (HSCC equivalent in Afghanistan

CHC		Comprehensive Health Center

CHS		Community Heath Supervisor

CHW		Community Heath Worker

CIDA		Canada International Development Assistance

C-IMCI		Community Integrated Management of Childhood Illnesses

cMYP		comprehensive Multi-Year Plan

CSO		Civil Society Organisation

DFID		UK International Development Assistance

DH		District Hospital

DHO		District Health Officer

EC		European Commission

EMRO		Eastern Mediterranean Regional Office (of the World Health Organization)

EPHS		Essential Package of Hospital Services

EPI		Expanded Program on Immunization

FSP		Financial Sustainability Plan

GAVI	The GAVI Alliance (formally known as the Global Alliance for Vaccines and Immunizations)

GCMU		Grants and Contracts Management Unit

GDPP		General Director of Policy & Planning

GIVS		Global Immunization Vision and Strategy

GOA		Government of Afghanistan

HMIS		Health Management Information Systems

HSCC		Health Sector Coordination Committee

HSS		Heath System Strengthening

ICC		Interagency Immunization Coordination Committee

ICRC		International Committee of the Red Cross and Red Crescent

IEC		Information Education and Communication

IHS		Institute of Health Service

IIHMR		Indian Institute of Health Management Research

IMC		International Medical Corps

IMCI		Integrated Management of Childhood Illnesses

IRC		Independent Review Committee

ISS		Immunization Support Services

JHPIEGO	International health organization affiliated with Johns Hopkins University

JHU		Johns Hopkins University

JICA		Japan International Cooperation Agency

JRF	Joint Reporting Format (UNICEF, WHO, MOPH annual Joint Reporting for EPI Coverage)

LDC		Least Developed Country

MICS		Multi-Indicator Cluster Survey (UNICEF & Afghan Central Statistics Office)

MOF		Ministry of Finance

MOHE		Ministry of Higher Education

MOPH		Ministry of Public Health

MRDR		Ministry of Rural Development and Rehabilitation

MSH		Management Sciences for Health (nonprofit international health organization)

MYPoA	Multi Year Plan of Action (of the Expanded Program of Immunization in Afghanistan

NGO		Non-Governmental Organisation

NNGO		National Non-Governmental Organisation

NTCC		National Technical Coordination Committee

PHCC		Provincial Health Coordination Committee

PHD		Provincial Health Directorate at MoPH

PPHD		Provincial Public Health Director in each province (also called PHD)

PPHO		Provincial Public Health Office (also called PHO)

SCA		Swedish Committee for Afghanistan

SCF		Save the Children Foundation

TWG		Technical Working Group

UN		United Nations

UNFPA	UN Population Fund

UNICEF	United Nations Children’s Fund

USAID		United States Assistance for International Development

WHO		World Health Organization

Executive Summary (one page)

Please provide an executive summary of the proposal.

The MoPH is in process of re-invigorating the coordination mechanisms of the CGHN (HSCC equivalent) and the ICC for the coming implementation of the new Health and Nutrition Sector Strategy (2008-2013).  In reviewing the current TOR and membership for these organizations, it has been noted that the CSO members were selected for CGHN and ICC about 5 years ago and reflect their involvement at that time while the evolving health sector reconstruction and implementation of contracting out NGOs for BPHS means that dramatic changes have taken place since then.  Thus the CGHN and the ICC need to review and revise their membership lists and qualifications for membership.  This process is underway.

In addition to NGOs, it is recognized that academic institutions, professional organizations and other civil society organizations at central and provincial levels may play important roles in the health sector and have a contribution to the strategy to reach the public health goals such as improved immunization coverage.

Thus, a methodology is hereby proposed to recruit 2 national consultants to conduct a mapping exercise by drafting an appropriate questionnaire to identify the CSOs contributing to child health and immunization.  The questionnaire will be filled by the PHCCs, monitored and collected by the MOPH Monitoring Officers, and entered into a database in the GCMU of MOPH.

In order to improve CSO participation in the important coordination bodies of CGHN and ICC, the CSO profiles derived from the database will be ranked based on the levels of experience and degree of involvement in health and immunization services delivery or involvement in health system strengthening.  By the end of July 2008, the short list of prioritized CSOs will be presented to the Civil Society Organizations for nomination of ten candidates for each forum such as CGHN and ICC membership.  Through a selection system agreed with the CSOs, voting through their Coordination Bodies or selection by a large shura, they will nominate ten candidate CSOs and rank them from 1 to 10.

The final short list will be presented to the CGHN and the ICC to approve the selected CSO candidates as members, depending on the number of CSO members specified in the revised TOR of the CGHN and the ICC.

As Afghanistan is one of 10 pilot countries selected for the GAVI-CSO window of support, the CGHN Steering Committee for HSS is proposing to use part of this Coordination Fund for CSO information workshops and consultant time to compile the CSO proposals for the second tranche of GAVI support to CSOs for improving immunization coverage.

Section 1: Baseline Information (one page)

Please provide the following details about the current coordination and representation of CSOs:

- Current composition of the ICC and HSCC, including the names of any CSO members

- Details of any CSO involvement / inclusion in the cMYP

- Details of any CSO involvement / inclusion in the Health Sector Strategic Plan

- Current CSO coordination mechanisms  HSCC, ICC , NTCC PHCC

Current composition of the HSCC:

The Consultative Group on Health and Nutrition (CGHN, equivalent to HSCC) is chaired by the Technical Deputy Minister of Public Health, with the General Directorate of Policy and Planning serving as the secretariat. The members include a senior representative of the Ministry of Finance and key health sector international organizations and donors such as the WHO, UNICEF, the World Bank, UNFPA, USAID, European Commission, the Japan International Cooperation Agency, International Committee of the Red Cross and Red Crescent Societies, Johns Hopkins University, London School of Tropical Medicine and Hygiene, the Swedish Committee for Afghanistan, Management Sciences for Health, Joint Civil-Military Operations Task Force and the International Security Assistance Force.

Current composition of the ICC:

The ICC is a national co-ordination mechanism for all immunisation activities in Afghanistan, providing guidance to the Ministry of Public Health and its partners. Its chief purpose is to strengthen, in a sustainable and self-sufficient way, Afghanistan’s Immunisation Program, including routine EPI and global initiatives for polio eradication, measles mortality reduction, and elimination of maternal and neonatal tetanus, through close co-ordination of all partners, including the Government of Afghanistan, major partner agencies, donors, and private and NGO implementers, in program planning, funding and monitoring.

The ICC is chaired by His Excellency the Minister of Health, or his nominee. National EPI/MOPH is serving as the secretariat. The members include: Ministries (MOPH, Finance Ministry, Local Government);UN Agencies (WHO, UNICEF); World Bank; Rotary International, Health Sector Bilateral Donors (JICA, USAID, Netherlands, CIDA, DFID); and major NGOs working in the health field at the time of establishing the ICC.  AHDS, Ibn Sina, IMC, MSH, and Swedish Committee for Afghanistan (SCA) are members of the ICC.

Details of CSO involvement/ inclusion in cMPY:

Using donor funds, MOPH has “contracted out” implementation of a Basic Package of Health Services (BPHS), including immunization, throughout Afghanistan, to about 33 NGOs.  The NGOs thus are partners in the cMYP of the Immunization Program as implementers of immunization service delivery and contributing to maintaining cold chain equipment for fixed centers, providing salary to vaccinators, providing transportation cost for outreach services and distribution of vaccine, monitoring the program at facility level, and facilitating training.

The NGO members of ICC: SCA, Ibn Sina, AHDS, IMC and MSH also contributed in the review and endorsement of the revised cMYP for immunization 2006-2010, through their participation in ICC meeting.

Details of CSO involvement / inclusion in the Health Sector Strategic Plan:

The Afghanistan National Development Strategy (ANDS) was widely consulted with the provinces. The process was organized by the ANDS office and all ministries including MOPH shared their strategies and plans with peripheral levels. At the provinces, all the Gvernment sub-national offices, development councils, NGOs, elders and influential people of the provinces, were part of the process. This is the first time that the strategies for all sectors has been shared with the provinces and inputs have been obtained from several sources including civil society organizations at the provincial level.  At the national level, CSOs contributed to the strategy through the above-mentioned mechanisms of CGHN and ICC as well as NTCC mentioned below.

Current CSO coordination mechanisms:

Agency Coordination Body for Afghan Relief (ACBAR) was formed in 1988 in response to the need for NGOs to coordinate their activities and is representing ninety seven NGO members from the national and international humanitarian, reconstruction and development NGO community in Afghanistan.  The Core Functions of ACBAR currently are:

- Coordination to avoid duplication of work and to identify gaps to be filled.

- Advocacy, Policy Development and Planning NGO strategy to meet humanitarian, reconstruction and development aims.

- Collection and Dissemination of information relevant to humanitarian assistance .

- Provision of information resources and technology centers.

Afghan National NGOs Coordination Bureau (ANCB):

The Afghan NGO Coordination Bureau (ANCB) was founded in 1991 as a network of national NGOs in Afghanistan coordinating the activities among its members, with the Government, International organizations, UN and donor agencies.

ANCB strives to enhance the capacity of its member organizations through workshops, seminars, as well as building partnerships with other organizations for the enhancement of technical capacity.

ANCB has been working throughout Afghanistan through its 200 member in health, agriculture, human rights, women empowerment, education, environment, protection, capacity building and civic education sector.

Afghan Women Network (AWN):

AWN developed a formal structure in 1996, and at the present time there are 72 NGOs and 3000 individuals who have the membership of AWN. It is a non- partisan network of women and women’s NGOs to empower Afghan women and ensure their equal participation in Afghan society.  The members of the network also recognize the value and role of children as the future of Afghanistan and, as such, regard the empowerment in protection of children as fundamental of their work.

At the Ministry of Public Health central level:

The current CSO coordination mechanisms at the central level are the BPHS implementers’ coordination meetings, general and specific to each donor; NTCC (National Technical Coordination Committee) meeting; and quarterly PHDs workshop.

The BPHS implementers’ coordination meeting objectives are as follows:

- Provision of feedback on the technical reports and Health Management Information System reports (HMIS) of the BPHS implementers

- Mainstreaming on Information Education and Communication (IEC) implementation

- Improving collaboration of NGOs and Provincial Public Health Offices

- Up dating on Basic Package of Health Services (BPHS) implementation

- Addressing identified problems to improve quality of health services

Prior to the establishment of BPHS implementers’ meeting, separate meetings were held between implementers funded by the World Bank and EU under the supervision of the MOPH and with USAID-funded implementers under supervision of USAID/ Reach/ MSH program.  The first BPHS implementers’ meeting was conducted on November 2006 and still is continuing.

The MoPH has established the National Technical Coordination Committee (NTCC) to provide a venue for discussion and for information sharing to all agencies working at national level, as well as to donors, and to which all other coordination bodies should be accountable. All the Taskforces and Directorates at the MOPH are providing information on progress, plans for activities, and drafts of technical documents and guidelines to the NTCC meeting for discussion. NTCC meets on a monthly basis and the membership is open for all organizations working the health sector.

The coordination meetings of provincial health directors (PHDs) were planned to be conducted on quarterly basis but practically are conducted on an average of 3 times a year.  All the NGOs working in the provinces and implementing the BPHS are called to the meeting along with the PHDs. The objectives of the meeting are:

1) To share and orient the provincial level staff about the new policies and strategies developed and get the inputs of provincial levels to form new policies and strategies

2) To review implementation of previous workshop recommendations converted into action plans

3) To identify overall challenges and challenges under different donor approaches, up date provincial health profiles especially the health facilities’ related issues and so on.

At this forum because of the presence of MOPH managers at central and provincial levels, major donor representatives, other technical partners of the MOPH such as WHO and UNICEF, NGOs managers at central and provincial levels and some other institutions, relevant important discussions are raised and important issues are debated face to face.

At the Ministry of Public Health provincial level:

The main forum of coordination at provincial level is called the PHCC (Provincial Health Coordination Committee). The meeting is chaired by PPHD and the purpose of the PHCC is to coordinate the activities of all stakeholders in following MOPH policies, strategies and standards and achieving MoPH priorities, particularly the expanded delivery of the Basic Package of Health Services (BPHS) and Essential Package of Hospital Services (EPHS).

The PHCC members are many but voting members are:

PPHD, HMIS provincial officer, EPI provincial officer, 2 representatives from NGOs, 1 representative of UNICEF,1 representative of WHO, the Provincial Hospital Director,1 representative of Shur-I –walayati,1 representative of Private Sector.

If the province is covered by several NGOs but one NGO is the leading agency for all, PHCC will have two voting members only from the leading agency.

If the province is covered by two or more NGOs and none of them is a leading agency the two biggest NGOs (those who covered the largest population of the province) each will have one voting member at PHCC.

Section 2: Mapping Exercise (one - two pages – this could also be an attached separate document or excel spreadsheet if necessary)

Please provide all of the details about the proposed mapping exercise in this section of the form.  Please indicate which entity or organisation will conduct the mapping exercise, the expected results and the proposed timeline.  Please also describe the overall process for how the mapping exercise will be carried out and managed, and the specific methodology to be adopted. If there are plans to update the mapping exercise on a regular basis, please describe this in this section.

Please note that the aim of the mapping exercise is to develop a database or profile of in-country CSOs who could potentially be involved in GAVI-related issues. The CSOs to be targeted should therefore be those involved or contributing most to immunisation, child health and health system strengthening. A short list of those CSOs most closely related is preferable to a long list of marginal players. Consideration needs to be given to how CSOs will be encouraged to share information.

Background for Mapping Exercise:

In Afghanistan, on a large scale, the health services delivery especially the BPHS implementation has been contracted out in 31 out of 34 provinces to the NGOs under different major donor approaches. The BPHS is focused on maternal and child health services including immunization.

The MOPH in order to manage the contracts, with the support of donors especially the World Bank, established a Grants and Contracts Management Unit (GCMU). The unit is performing highly satisfactorily and has extensive contact with the NGOs throughout the country. In addition the GCMU provides support to other departments within the MOPH especially the International Relations Department which is the other source at the MOPH which has considerable number of Memoranda of Understanding with the NGOs and also registers the NGOs working in the health sector.

For its above-mentioned strategic position and capacity, the MOPH has nominated the GCMU to be the right office for carrying out the mapping exercise.

Methodology:

In order to manage the process properly, two national consultants will be recruited.

In the first stage, the existing NGO databases available in GCMU, International Relations Department of MOPH, WHO, AWN, ACBAR, and ANCB will be reviewed in order to compile a database of known NGOS active in the health sector.  Other types of Civil Society Organizations such as academic institutions and professional associations will also be searched out.

Questionnaires will then be developed to verify the existing information about CSOs, such as name, location, resources, activities, length of time and population served, and to collect more information to identify CSOs and their exact activities in the field, prioritizing those who are most heavily involved in child health, immunization and health system strengthening.

The questionnaires will be sent to the provinces to be filled through the Provincial Public Health Coordination Committees (PHCCs). The data collection process from the provinces will take 2-3 months.

The BPHS Monitoring Officers of the MoPH Monitoring and Evaluation Unit will support the data collection process in terms of advice to the PHCC, monitoring of the process in the field, and collection of the forms.

Information will be obtained from other ministries within the Government as well and will be closely coordinated with the Ministry of Economics which has the responsibility of registering the CSOs.

The GCMU team with the national consultants for this project will analyze all the collected data and make a new database which will reflect the relevant information about the Civil Society Organizations. The database will be widely shared with all CSOs, donors and other stakeholders and updated at least once a year through the PHCCs.

The whole process of developing and distributing questionnaires, retrieving the filled forms, and entering the data in a database will be started in Feb 2007 and will be completed by the end of July 2008.

Section 3: Nomination Process (one page)

Please indicate in this section the proposed process for fairly and transparently nominating CSO representatives to the national level coordination mechanisms: the HSCC (or equivalent) and ICC.

Please give details of the expected roles of the different stakeholders in the process, and how the HSCC (or equivalent) and ICC will work to ensure full participation of the CSO community in the identification of the terms and criteria for their representation, and in the election process.

Proposed process for nomination of CSO in CGHN and ICC

The MoPH is in process of re-invigorating the coordination mechanisms of the CGHN (HSCC equivalent) and the ICC for the coming implementation of the new Health and Nutrition Sector Strategy (2008-2013).  In reviewing the current TOR and membership for these organizations, it has been noted that the CSO members were selected for CGHN and ICC about 5 years ago and reflect their involvement at that time while the evolving health sector reconstruction and implementation of contracting out NGOs for BPHS means that dramatic changes have taken place since then.  Thus the CGHN and the ICC need to review and revise their membership lists and qualifications for membership.  This process is underway.

The CSO profiles derived from the database will be ranked based on the levels of experience and degree of involvement in health and immunization services delivery or involvement in health system strengthening.  By the end of July 2008, the short list of prioritized CSOs will be presented to the Civil Society Organizations for nomination of ten candidates for each forum such as CGHN and ICC membership.  Through a selection system agreed with the CSOs, voting through their Coordination Bodies or selection by a large shura, they will nominate ten candidate CSOs and rank them from 1 to 10.

The final short list will be presented to the CGHN and the ICC to approve the selected CSO candidates as members, depending on the number of CSO members specified in the revised TOR of the CGHN and the ICC.

Role of different stakeholders in the process, how CGHN /ICC will work to ensure full participation of CSO

The MOPH is committed to transparency and responsiveness and will advocate to increase the representation and participation of CSOs in the CGHN and the ICC, commensurate with their experience and involvement in the health sector.  The CGHN as mentioned above is representing the key stakeholders in the health sector including donors, UN agencies, and other partners of the MOPH as well as hosting the Steering Committee for GAVI HSS.  The CGHN will be regularly updated about the process and timely presentations will be made to the forum.

When the CSO members are chosen, their participation will be monitored so that if they are not actively participating, consideration will be made for other CSOs to be promoted to their position.

Section 4: Management of the Support (one - two pages)

The aim of this section is to show how the support will be managed in country, from both the technical and the financial perspective.  Firstly, please provide full details of who will have overall management responsibility for the support.  Then please give details of the financial aspects:

- Total funds available from the GAVI Alliance CSO support

- Budget for the two core activities (mapping exercise and nomination process)

- Proposed mechanism for channelling funds into the country

Please supply all cost information in US$, and convert at the current conversion rate. Please use the table below to provide information on the budget.

The support will be technically managed by the MOPH-Health System Strengthening coordination team under supervision of GD of Policy & Planning and Technical Deputy MOPH. Two national consultants will be recruited to properly manage the process of questionnaire and database development and CSO nomination process in close coordination with HSS coordinator/Focal point.

As Afghanistan is one of 10 pilot countries selected for the GAVI-CSO window of support, the CGHN Steering Committee for HSS is proposing to use part of this Coordination Fund for CSO information workshops and consultant time to compile the CSO proposals for the second tranche of GAVI support to CSOs for improving immunization coverage.

MOPH considering the importance and value of this new opportunity and proper management and meeting the deadlines, proposes to have the budget spent on the following activities:

- Mapping exercise.

- Nomination of the CSO to the CGHN and ICC forums.

- Development of Afghanistan’s CSO support application.

- Future follow up of implementation of the projects that will be hopefully approved by the GAVI board under CSO support scheme.

The MOPH appreciating the GAVI and WHO relationship, proposes that the funds for coordination of GAVI-CSO project be channeled through WHO as it was done for GAVI-HSS application development.

The MOPH requests the total of 100,000 US$.  Budget below.

## Cost of implementing GAVI Alliance CSO support

| Cost of core activities | Cost per year in US$ (,000) |  |  | TOTAL COSTS |
| --- | --- | --- | --- | --- |
|  | 2007 | 2008 | 2009 |  |
| Mapping exercise & Nomination process & Follow up |  |  |  |  |
| 1.1 Recruitment of two national consultants to manage the process of mapping exercise and nomination process |  | 44,000 | 4,000 | 48,000 |
| 1.2 Perdiem for Monitoring Officers to be sent to the provinces |  | 3,000 | 0 | 3,000 |
| 1.3 Communication & Transport cost |  | 2,500 | 0 | 2,500 |
| 1.4 Workshops with CSOs to assure their participation in mapping exercise and developing strategy and planning to improve immunization coverage |  | 10,000 | 0 | 10,000 |
| 1.5 Provision of equipment and stationery |  | 12,500 | 0 | 12,500 |
| Development of GAVI-CSO Application for Afghanistan |  |  |  |  |
| 2.1 Recruitment of an international consultant to compile Afghanistan application for CSO support |  | 15,000 | 0 | 15,000 |
| Management costs |  | 9,000 | 0 | 9,000 |
| TOTAL COSTS |  | 96,000 | 4,000 | 100,000 |

Section 5: Endorsement of the Application

Representatives of the Health Sector Coordinating Committee (HSCC), or equivalent, should endorse the application, and the Chair of the HSCC should sign the application on their behalf.  All HSCC members should sign the minutes of the meeting where the GAVI CSO application was endorsed. The minutes should be submitted with the application.

Please note that the signature of HSCC members represents their agreement with the information and plans provided in this application, as well as their support for the implementation of the plans. It does not imply any financial or legal commitment on the part of the partner agency or individual.

“The Consultative Group on Health and Nutrition representing the Ministry of Public Health of the Afghanistan Government and partners affirms its commitment to engaging civil society organizations to provide support towards raising immunization coverage and strengthening immunization services and health systems. The CGHN requests that GAVI Alliance funding partners provide financial assistance for strengthening the coordination and representation of CSOs as outlined in this application.

- Chair of CGHN (HSCC equivalent): Name, Post, Organisation, Date, Signature

Dr. Faizullah Kakar, Deputy MOPH for Technical Affairs.

Date: 					Signature

Members of the CGHN (HSCC equivalent) endorsed this application at a meeting on ...............................................  The signed minutes are attached.

Dr. Ahmad Rahman Swedish Committee for Afghanistan Member of the CGHN

Dr. Rana Kakar EPI WHO Member of the CGHN

Dr. Ahmad Jan General Director of Policy & Planning MOPH Member of CGHN

Dr. Abdul Wali Health System Strengthening Coordinator MOPH Member of CGHN

Dr. Sayed Health Specialist World Bank Member of CGHN

Dr. Faiz Muhamad USAID Member of CGHN

This section should also include the name and contact details of the person for the GAVI Alliance Secretariat to contact in case of any queries.  Please provide the following information:

- Contact person: Name, Post, Organisation, Tel No., Fax No., Address, Email

Dr. Abdul Wali, Health System Strengthening Coordinator and Focal Point

0093 (0) 799 353 178 – 0093(0) 775 577 096

drabwali@yahoo.com

Office of General Directorate of Policy & Planning ,Great Masoud Road, Ministry of Public Health, Kabul , Afghanistan

ANNEX Documents Submitted in Support of the GAVI CSO Support Application

Please submit the following documents with the application (in electronic copy if possible):