|  |  | [V3.10]. |  |
| --- | --- | --- | --- |
| GAVI Alliance.. Application Form for Country Proposals.. For Support to:.. Routine New Vaccines Support.. Submitted by.. The Government of.. Mozambique.. Date of submission: 16 September 2013.. Deadline for submission: 15 September 2013.. Select Start and End Year of your Comprehensive Multi-Year Plan (cMYP).. Start Year.; 2014.. End Year.; 2018.. Form revised in 2013.. (To be used with Guidelines of June 2013).. Please submit the Proposal using the online platform. https://AppsPortal.gavialliance.org/PDExtranet.. Enquiries to: proposals@gavialliance.org or representatives of a GAVI partner agency. The documents can be shared with GAVI partners, collaborators and general public. The Proposal and attachments must be submitted in English, French, Spanish, or Russian.. Note: Please ensure that the application has been received by the GAVI Secretariat on or before the day of the deadline.. The GAVI Secretariat is unable to return submitted documents and attachments to countries. Unless otherwise specified, documents will be shared with the GAVI Alliance partners and the general public.... |

GAVI ALLIANCE GRANT TERMS AND CONDITIONS. FUNDING USED SOLELY FOR APPROVED PROGRAMMES. The applicant country ("Country") confirms that all funding provided by the GAVI Alliance will be used and applied for the sole purpose of fulfilling the programme(s) described in the Country's application. Any significant change from the approved programme(s) must be reviewed and approved in advance by the GAVI Alliance. All funding decisions for the application are made at the discretion of the GAVI Alliance Board and are subject to IRC processes and the availability of funds.. AMENDMENT TO THE APPLICATION. The Country will notify the GAVI Alliance in its Annual Progress Report if it wishes to propose any change to the programme(s) description in its application.The GAVI Alliance will document any change approved by the GAVI Alliance, and the Country's application will be amended.. RETURN OF FUNDS. The Country agrees to reimburse to the GAVI Alliance all funding amounts that are not used for the programme(s) described in its application. The country's reimbursement must be in US dollars and be provided, unless otherwise decided by the GAVI Alliance, within sixty (60) days after the Country receives the GAVI Alliance's request for a reimbursement and be paid to the account or accounts as directed by the GAVI Alliance.. SUSPENSION/ TERMINATION. The GAVI Alliance may suspend all or part of its funding to the Country if it has reason to suspect that funds have been used for purpose other than for the programmes described in the Country's application, or any GAVI Alliance-approved amendment to the application.The GAVI Alliance retains the right to terminate its support to the Country for the programmes described in its application if a misuse of GAVI Alliance funds is confirmed.. ANTICORRUPTION. The Country confirms that funds provided by the GAVI Alliance shall not be offered by the Country to any third person, nor will the Country seek in connection with its application any gift, payment or benefit directly or indirectly that could be construed as an illegal or corrupt practice.. AUDITS AND RECORDS. The Country will conduct annual financial audits, and share these with the GAVI Alliance, as requested. The GAVI Alliance reserves the right, on its own or through an agent, to perform audits or other financial management assessment to ensure the accountability of funds disbursed to the Country.. The Country will maintain accurate accounting records documenting how GAVI Alliance funds are used. The Country will maintain its accounting records in accordance with its government-approved accounting standards for at least three years after the date of last disbursement of GAVI Alliance funds. If there is any claims of misuse of funds, Country will maintain such records until the audit findings are final. The Country agrees not to assert any documentary privilege against the GAVI Alliance in connection with any audit.. CONFIRMATION OF LEGAL VALIDITY. The Country and the signatories for the Country confirm that its application, and Annual Progress Report, are accurate and correct and form legally binding obligations on the Country, under the Country's law, to perform the programmes described in its application, as amended, if applicable, in the APR.. CONFIRMATION OF COMPLIANCE WITH THE GAVI ALLIANCE TRANSPARANCY AND ACCOUNTABILITY POLICY. The Country confirms that it is familiar with the GAVI Alliance Transparency and Accountability Policy (TAP) and complies with the requirements therein.. USE OF COMMERCIAL BANK ACCOUNTS. The Country is responsible for undertaking the necessary due diligence on all commercial banks used to manage GAVI cash-based support. The Country confirms that it will take all responsibility for replenishing GAVI cash support lost due to bank insolvency, fraud or any other unforeseen event.. ARBITRATION. Any dispute between the Country and the GAVI Alliance arising out of or relating to its application that is not settled amicably within a reasonable period of time, will be submitted to arbitration at the request of either the GAVI Alliance or the Country. The arbitration will be conducted in accordance with the then-current UNCITRAL Arbitration Rules. The parties agree to be bound by the arbitration award, as the final adjudication of any such dispute. The place of arbitration will be Geneva, Switzerland. . The languages of the arbitration will be English or French.. For any dispute for which the amount at issue is US$ 100,000 or less, there will be one arbitrator appointed by the GAVI Alliance. For any dispute for which the amount at issue is greater than US $100,000 there will be three arbitrators appointed as follows: The GAVI Alliance and the Country will each appoint one arbitrator, and the two arbitrators so appointed will jointly appoint a third arbitrator who shall be the chairperson.. The GAVI Alliance will not be liable to the country for any claim or loss relating to the programmes described in the application, including without limitation, any financial loss, reliance claims, any harm to property, or personal injury or death. Country is solely responsible for all aspects of managing and implementing the programmes described in its application....

1. Application Specification. Please specify for which type of GAVI support you would like to apply to... Type of Support; Vaccine; Start Year; End Year; Preferred second presentation[1]. Routine New Vaccines Support; Rotavirus, 2 -dose schedule; 2015; 2018. Routine New Vaccines Support; Measles second dose, 10 dose(s) per vial, LYOPHILISED; 2015; 2018.. [1] GAVI may not be in a position to accommodate all countries first product preferences, and in such cases, GAVI will contact the country and partners to explore alternative options. A country will not be obliged to accept its second or third preference, however GAVI will engage with the country to fully explore a variety of factors (such as implications on introduction timing, cold chain capacity, disease burden, etc.) which may have an implication for the most suitable selection of vaccine. If a country does not indicate a second or third preference, it will be assumed that the country prefers to postpone introduction until the first preference is available. It should be noted that this may delay the introduction in the country....

2. Table of Contents.. 1. Application Specification. 2. Table of Contents. 3. Executive Summary. 4. Signatures. 4.1. Signatures of the Government and National Coordinating Bodies. 4.1.1. Government and the Inter-Agency Coordinating Committee for Immunisation. 4.1.2. National Coordinating Body - Inter-Agency Coordinating Committee for Immunisation. 4.1.3. Signature Table for the Coordinating Committee for Immunisation. 4.2. National Immunization Technical Advisory Group. 4.2.1. The NITAG. 5. Immunisation Programme Data. 5.1 Background information. 5.1.1 Lessons learned. 5.1.2 Health planning and budgeting. 5.1.3 Preparatory activities. 5.1.4 Gender and equity. 5.1.5 Data quality. 5.2. Baseline and Annual Targets (NVS Routine Support). 5.3. Baseline and Annual Targets for Preventive Campaign(s). 6. New and Under-Used Vaccines (NVS Routine). 6.1. Assessment of burden of relevant diseases (if available). 6.2 Requested vaccine (Rotavirus, 2 -dose schedule). 6.2.1 Co-financing information. 6.2.2 Specifications of vaccinations with new vaccine. 6.2.3 Portion of supply to be procured by the country (and cost estimate, US$). 6.2.4 Portion of supply to be procured by the GAVI Alliance (and cost estimate, US$). 6.2.5 New and Under-Used Vaccine Introduction Grant. 6.3 Requested vaccine (Measles second dose, 10 dose(s) per vial, LYOPHILISED). 6.3.1 Co-financing information. 6.3.2 Specifications of vaccinations with new vaccine. 6.3.3 Portion of supply to be procured by the country (and cost estimate, US$). 6.3.4 Portion of supply to be procured by the GAVI Alliance (and cost estimate, US$). 6.3.5 New and Under-Used Vaccine Introduction Grant. 7. NVS Preventive Campains. 8. Procurement and Management. 8.1 Procurement and Management of New and Under-Used Vaccines Routine. 8.2 Procurement and Management for NVS Preventive Campaign(s). 8.3 Vaccine Management (EVSM/EVM/VMA). 8.4 Waste management. 9. Additional Comments and Recommendations from the National Coordinating Body (ICC/HSCC). 10. List of documents attached to this proposal. 11. Annexes. Annex 1 - NVS Routine Support. Annex 1.1 Rotavirus, 2 -dose schedule. Table Annex 1.1 A Rounded up portion of supply that is procured by the country and estimate of relative costs in US$. Table Annex 1.1 B Rounded up portion of supply that is procured by GAVI and estimate of relative costs in US$. Table Annex 1.1 C Summary table for vaccine Rotavirus, 2 -dose schedule. Table Annex 1.1 D Estimated numbers for Rotavirus, 2 -dose schedule, associated injection safety material and related co-financing budget (page 1). Annex 1.2 Measles second dose, 10 dose(s) per vial, LYOPHILISED. Table Annex 1.2 A Rounded up portion of supply that is procured by the country and estimate of relative costs in US$. Table Annex 1.2 B Rounded up portion of supply that is procured by GAVI and estimate of relative costs in US$. Table Annex 1.2 C Summary table for vaccine Measles second dose, 10 dose(s) per vial, LYOPHILISED. Table Annex 1.2 D Estimated numbers for Measles second dose, 10 dose(s) per vial, LYOPHILISED, associated injection safety material and related co-financing budget (page 1). Annex 2 - NVS Routine – Preferred Second Presentation. Annex 3 - NVS Preventive campaign(s). Annex 4. Table Annex 4A: Commodities Cost. Table Annex 4B: Freight cost as percentage of value. Table Annex 4C: Low - Minimum country's co-payment per dose of co-financed vaccine.. Table Annex 4D: Wastage rates and factors. Table Annex 4E: Vaccine maximum packed volumes. 12. Banking Form...

3. Executive Summary.. Please provide a summary of your country's proposal, including the following the information:. ; For each specific request, NVS routine support or NVS campaign :. ; The duration of support. ; The total amount of funds. ; Details of the vaccine(s), if applicable, including the reason for the choice of presentation. ; Projected month and year of introduction of the vaccine. ; Relevant baseline data, including:. ; DTP3 and Measles coverage data (as reported on the WHO/UNICEF Joint Reporting Form). ; Birth cohort, targets and immunisation coverage by vaccines. ; Country preparedness. ; Summary of EVM assessment and progress on EVM improvement plan. ; The nature of stakeholders' participation in developing this proposal. ; Inter-Agency Coordinating Committee. ; Partners. Rotavirus remains a leading cause of severe diarrhea among children in developing countries. According to WHO estimates, in 2004, 1.8 million deaths due to diarrhea occurred in children <5 years of age worldwide. Twenty nine per cent of these deaths were due to rotavirus, resulting in 527,000 rotavirus deaths annually, majority of which occurred in Africa and Asia. Available data from WHO indicated that in 2008, the annual estimated numbers of rotavirus deaths among children under age of 5 years was of 4,481 for Mozambique, ranking the country in the 5th position in the sub-region, after Ethiopia, Uganda, Tanzania and Kenya. A Global Enteric Multicentric Study (GEMS) conducted between 2007 and 2010 in Manhiça District in Mozambique with the objective to quantify the burden, sequel and microbiology etiology of moderate-to-severe diarrhea (MSD) in infants and young children, found that in Mozambican children, rotavirus were significantly associated with MSD in infants (42% in cases vs. 16% in controls; OR=6.0, 95% CI: 3.65-9.87, p<0.001) and children aged 12-23 months (22% in cases vs. 18% in controls; OR=3.30, 95%CI: 1.60-6.79, p=0.014). It was also estimated the yearly number of new MSD cases (incidence) for each pathogen. The incidence of MSD was higher among children from 0-11 months of age with 12.5 episodes of MSD each year per 100 children. The incidence of rotavirus was 3.5 episodes per 100 children year at risk, representing 28% of the total MSD in this age group suggesting nearly 30% of the MSD would be prevented by the vaccine (Kotloff et al. Lancet 2013). With regards to measles, according to WHO, the Strategies for Accelerated Measles Control and Elimination include 1) Strengthening routine immunization to achieve and sustain high coverage; 2) providing a second opportunity for measles immunization through the implementation of high quality Supplemental Immunization Activities (SIAs) or through routine (MSD); 3) conducting epidemiologic surveillance with laboratory confirmation of cases and outbreaks, and 4) ensuring that improved case management is implemented. Within the context of the above mentioned, the country has been strengthening its routine immunization through Mid‐Level Managers’ training modules and implementation of RED strategy approach for immunization. It also ensures improved measles case management integrated in the IMCI package. Meanwhile, in 2005, Mozambique conducted its first measles catch-up SIAs integrated with Vitamin A supplementation and also initiated measles case-based surveillance. In addition, the country has been providing a second opportunity for measles immunization through follow up national measles SIAs in children 9-59 months, conducted in 2008 and 2011. Concerning measles surveillance, available data indicates that since the SIAs in 2005, the number of measles cases has decreased from 23,000 in 2004 to about 300 in 2006, and then remained below 200 in each year between 2007 and 2012, except in 2009/2010 when there was a measles outbreak with a cumulative of nearly 1,570 cases, of which 670 were IGM + and the rest by epidemiological link. Meanwhile, since 2009 the country achieved and maintained non-measles febrile rash illness rate of >2/100,000 inhabitants at national and in all provinces (minimum recommended is non-measles febrile rash illness rate of 2/100,000 inhabitants), and the percentage of districts reporting at least 1 suspected measles case with blood sample tested in the lab has been above 80% every year, meaning that surveillance is quite good. This may strongly support the conclusion that the country has very few cases of measles in the past 6-7 years. According to WHO, a given country is eligible to offer second opportunity for measles through its routine immunization, if it achieves a measles first dose coverage of 80% or greater as documented by the most recent WHO UNICEF estimate or a recent high-quality coverage survey completed after the most recent WHO UNICEF estimate. In the particular case of Mozambique, the country has achieved and maintained measles coverage of above 80% in the last 3 years, according to WHO/UNICEF best estimates, which are consistent with the 81.5% measles coverage found in the last DHS conducted in 2011, making the country eligible for introduction of measles second dose into its national routine immunization program. This is the rational for country’s application for introduction of measles second dose into its routine immunization schedule. In the context of the above explained, Mozambique is applying for GAVI support through the GAVI-NVS window and measles second dose (MSD) through MSD introduction window grant in order to introduce Rotavirus vaccine, liquid 1 dose per vial, 2 dose schedule and MSD 10 doses per vial, lyophilized into its national immunization program (NIP). The country has selected rotavirus 2 dose schedule, as it requires less storage volume and less vaccine quantity as compared to 3 dose schedule, with important reflex in the cost of new vaccine introduction in terms cold chain and vaccine cost itself. It is expected that the introduction process will start in April 2015 and the support will last for the period 2015-2018 for rotavirus vaccine, in line with the cMYP life span, and for 5 years for MSD, after which the country will take over the MSD vaccine. The introduction of rotavirus vaccine, excluding the roll out process, will cost approximately $20.0 million over the 4 year period (2015-2018). The rollout process in terms of cold chain expansion (cc equipment and construction of vaccine stores), training, surveillance, monitoring and evaluation, program management, advocacy and social mobilization, and vaccine and related materials distribution (including vaccine receiving and stock management) will cost an additional $ 4.1 million, for a total cost of 24.0 million. Meanwhile, over the same period, MSD vaccine introduction will cost approximately $2.07million for vaccine and injection safety materials and an additional $1.07 million for the roll out process, for a total of $3.14 million. The Mozambican government’s investment in rotavirus vaccine will be limited to a total co-financing amount of $1.6 million, while for MSD the government will completely take over its cost after the first 5 years GAVI support. Therefore, this proposal is applying for GAVI NVS for rotavirus and GAVI MSD support in the total amount of $23,81 million ($19,97 million for rotavirus vaccine + 0,885 million for rotavirus introduction grant + $2,07 million for measles second dose and injection safety devices + 0,885 million for MSD introduction grant). The Government will raise the remaining amount through the ICC and other funding mechanisms including GAVI-HSS window grant. Overall, there is a gap of $575,296, if MSD introduction grant is excluded, representing 14% of unfunded resources, concerning advocacy and social mobilization ($76,786), program management ($28,040) and construction buildings of regional and provincial vaccine stores ($470,471). Meanwhile, if MSD is figured in, the gap will be completely covered and there will be a positive balance of $300,000 that will be used to strengthen routine immunization. According to administrative data reported in the country JRF 2012, DPT3 and measles coverage reached 92.9% and 90.6% respectively. However, in the same JFR 2012 the country official best estimates based on the last DHS conducted in 2011 were of 76% for DPT3 and 82% for measles, which is consistent with WHO/UNICEF best estimates. Based on these official estimates, the projected target coverage for vaccines provided in the national immunization program are presented in the table below: Number; Targets*. 2014; 2015; 2016; 2017; 2018. Total Population; 25.041.922; 25.727.911; 26.423.623; 27.128.530; 27.843.933. Total births; 1.076.775; 1.106.272; 1.136.186; 1.166.497; 1.197.258. Total infants' deaths; 68.914; 70.801; 72.716; 74.656; 76.625. Total surviving infants; 1.007.861; 1.035.470; 1.063.471; 1.091.841; 1.120.634. Target number for BCG; 1.033.704; 1.073.084; 1.113.463; 1.154.832; 1.197.258. BCG coverage (%); 96%; 97%; 98%; 99%; 100%. Target number for DTP1; 908.182; 935.264; 962.721; 1.011.389; 1.061.653. Target number for DTP3; 826.446; 869.795; 914.585; 960.820; 1.008.570. DPT3 Coverage (%); 82%; 84%; 86%; 88%; 90%. Target for PCV dose 3; 826.446; 869.795; 914.585; 960.820; 1.008.570. PCV dose 3 Coverage (%); 82%; 84%; 86%; 88%; 90%. Target number for Rota 1; 668.045; 962.721; 1.011.389; 1.061.653. Target number for Rota 2; 621.282; 914.585; 960.820; 1.008.570. Rota 2 Coverage (%); 60%; 86%; 88%; 90%. Target nr for Measles dose 1; 886.918; 931.923; 978.393; 1.026.330; 1.064.602. Measles 1 coverage (%); 88%; 90%; 92%; 94%; 95%. Target nr for Measles dose 2; 838.731; 900.121; 964.751; 1.011.372. Measles 2 coverage (%); 81%; 85%; 88%; 90%. * Please note that the targets here presented differ from the ones presented in the APR 2012 for the following reasons: 1) The last DHS which is attached to this application, whose definite data were released recently in June, after the APR 2012 submission in May, fixed infant mortality at 64 per 1,000 as opposed to 94/1000, used in the APR. This reduction in infant mortality rate resulted in increased nr of surviving infants, presented in the table above; 2) After reviewing the country APR2012 submitted to GAVI in May 2013, the IRC recommended the country to review its very high targets in line with the most recent WHO/UNICEF best estimates or DHS available. In line with this, new coverage targets were projected using the best estimates as baseline, as opposed to the APR report in which were used administrative coverage as baseline; 3) However, data in the table above has been harmonized with the updated EPI cMYP 2014-2018, submitted with this application. The MOH conducted its last vaccine management assessment (VMA) in May 2012. The main weaknesses were predominantly management-related criteria, vaccine arrivals (form filled only for Pentavalent DPT-HepB-Hib), temperature monitoring (non-availability of continuous temperature recording charts, non-calibration of system, lack of temperature mapping and formal review process), maintenance (no written multi–year planned preventive maintenance or a written record of the maintenance tasks that had been carried out for building and equipment), stock management system (stock balances were not updated within one working day of the transaction, the location for diluents not indicated in the stock record system, the arrival vouchers are not usually completed or signed for, there are neither records of damaged vaccines nor an internal review of the vaccine loss/ damages records, there vaccines have not been maintained within maximum and safety stock levels during the review period), vaccine management (non-use of VVM posters and stickers, non-review immunization reports), and information management system and supportive functions (lack of a list of key SOP for the vaccine stores, existing cold chain inventory not up-to-dated and seemed to be not accurate). The country has started the implementation of the EVMA recommendations on computerization of stock control tools in all provincial and regional vaccine deposits and training of users, monitoring of wastage rate and VVM. The stock management tool (SMT) is in use at national level and provincial levels, whilst the scaling up of the district data and vaccine management tool (DVDMT tool) at district level is on-going. Other measures put in place to support vaccine management, as well as cold chain management were basically the appointment and training of the EPI logisticians in all provinces, the appointment of EPI cold chain maintenance technicians for all provinces, periodic cold chain inventory, the last conducted in December 2012 and started replacement of old and depleted CC at district and health facility levels, and implementation of supportive supervision activities. The ICC was briefed on the cost implications of the introduction of the rotavirus vaccine and MSD, in terms of vaccine cost and CC equipment, as well the benefits to the public health. The ICC endorsed the proposal for rotavirus vaccine and MSD on its meeting on 10th September 2013. In support of the plan, the ICC has managed to secure $1.3 million to increase the CC capacity at central and provincial to accommodate rotavirus and MSD vaccines and replace depleted CC equipment, in line with the national cold chain update plan (CCUP). The ICC will monitor and evaluate all EPI activities including introduction of the rotavirus and MSD vaccines using indicators developed and agreed upon by the Committee. At country level, the ICC is composed of the following partners: WHO, UNICEF, USAID, FDC and Village Reach. While WHO and UNICEF have provided technical support in the development of the proposal and in the development of the Cold Chain Update Plan (CCUP) used to input some data in terms of CC needs, vaccine stores and costing figures in this application, USAID has made available financial resources for procurement and installation of necessary CC equipment to accommodate new vaccine and MSD. FDC and Village reach provided their valuable support in terms of vaccine distribution strategy at peripheral levels and strategies to reach hard to reach population, based on their own experience gained with the support they provided to provinces and districts on social mobilization, universal access to health and EPI vaccine and gas distribution. The country is presently applying for rotavirus vaccine in order to address the most common cause of severe diarrheal diseases and death due to diarrhea in children under five years. This intervention will be one of the greatest public health achievements through reduction in severe diarrheal diseases and mortality among children. Further, the country is also applying for MSD vaccine in order to provide second opportunity for measles vaccination in a more sustainably manner through the routine national immunization program (NIP) to raise population immunity to levels that will allow interruption of measles virus transmission and accelerate the achievement of the measles elimination goal....

4. Signatures.. 4.1. Signatures of the Government and National Coordinating Bodies.. 4.1.1. Government and the Inter-Agency Coordinating Committee for Immunisation.. The Government of Mozambique would like to expand the existing partnership with the GAVI Alliance for the improvement of the infants routine immunisation programme of the country, and specifically hereby requests GAVI support for:.. Rotavirus, 1 dose(s) per vial, ORAL; Measles second dose, 10 dose(s) per vial, LYOPHILISED routine introduction.. The Government of Mozambique commits itself to developing national immunisation services on a sustainable basis in accordance with the Comprehensive Multi-Year Plan presented with this document. The Government requests that the GAVI Alliance and its partners contribute financial and technical assistance to support immunisation of children as outlined in this application... Table(s) 6.2.4, 6.3.4 in the NVS Routine section of this application shows the amount of support in either supply or cash that is required from the GAVI Alliance. Table(s) 6.2.3, 6.3.3 of this application shows the Government financial commitment for the procurement of this new vaccine (NVS support only)... Following the regulations of the internal budgeting and financing cycles the Government will annually release its portion of the co-financing funds in the month of July... The payment for the first year of co-financed support will be around September 2015 for Rotavirus, 2-dose schedule.... Please note that this application will not be reviewed or recommended for approval by the Independent Review Committee (IRC) without the signatures of both the Minister of Health and Minister of Finance or their delegated authority. These signatures are attached as DOCUMENT NUMBER : 1 and 2 in Section 10. Attachments... Minister of Health (or delegated authority); Minister of Finance (or delegated authority). Name; Hon Dr Alexandre L. Jaime Manguele; Name; Hon Dr Manuel Chang. Date; Date. Signature; Signature.. This report has been compiled by (these persons may be contacted in case the GAVI Secretatiat has queries on this document):.. Full name; Position; Telephone; Email. Balbina Nhanlawia; EPI Logistician; +258 820 348 780; bkhanlawia@gmail.com. Ercílio Paulino Nhanule; Administrative assistant of EPI; +258 825 157 285; Epaulino278@gmail.com. Manuel Novela; WHO EPI Specialist; +258 828 007 610; novelama@who.int. Maria Benigna Pedro Matsinhe; EPI Manager; +258 823 024 940; bmaia69@yahoo.com.br. Onei Ouetela; UNICEF EPI Specialist; +258 843 865 242; ouetela@unicef.org. Wendy prosser; Village Reach EPI Officer; +258 825 440 660; wendy.prosser@villagereach.org.. 4.1.2. National Coordinating Body - Inter-Agency Coordinating Committee for Immunisation.. Agencies and partners (including development partners and NGOs) supporting immunisation services are co-ordinated and organised through an inter-agency coordinating mechanism (ICC, HSCC, or equivalent committee). The ICC, HSCC, or equivalent committee is responsible for coordinating and guiding the use of the GAVI NVS routine support and/or campaign support. Please provide information about the ICC, HSCC, or equivalent committee in your country in the table below... Profile of the ICC, HSCC, or equivalent committee.. Name of the committee; Comité de Coordenação Interagências. Year of constitution of the current committee; 2001. Organisational structure (e.g., sub-committee, stand-alone); Stand-alone committee. Frequency of meetings; quarterly.. The Terms of Reference or Standard Operating Principles for the ICC, including details on the ICC membership, quorum, dispute resolution process and meeting schedules is attached as DOCUMENT NUMBER : 4... Major functions and responsibilities of the ICC/HSCC:.. Coordinate all efforts to cover EPI needs in order to avoid duplication; Monitor the implementation of both EPI annual and multi annual plans; Identify program technical and financial gaps and provide guidance and support to EPI, in order to achieve the goals set in both annual and multi annual plans, and in emergency situations; Advocate enhancing interest on EPI at national level, Decide on national polices in support to EPI and follow up their implementation; Follow up the implementation of Government compromises with regard to EPI... Please describe how partners have provided support in preparation of the proposal:.. The ICC was briefed on the cost implications of the introduction of the rotavirus vaccine and MSD, in terms of vaccine cost and CC equipment, as well the benefits to the public health. The ICC endorsed the proposal for rotavirus vaccine and MSD on its meeting on 10th September 2013. In support of the plan, the ICC has managed to secure $1.3 million to increase the CC capacity at central and provincial to accommodate rotavirus and replace depleted CC equipment, in line with the national cold chain update plan (CCUP) and based on a modeling exercise in order to optimize the cold Chain. The ICC will monitor and evaluate all EPI activities including introduction of the rotavirus vaccine using indicators developed and agreed upon by the Committee. At country level, the ICC is composed of the following partners: WHO, UNICEF, USAID, FDC and Village Reach. While WHO and UNICEF have provided technical support in the development of the proposal and in the development of the Cold Chain Update Plan (CCUP) used to input some data in terms of CC needs, vaccine stores and costing figures in this application, USAID has made available financial resources for procurement and installation of necessary CC equipment to accommodate new vaccine. FDC and Village reach provided their valuable support in terms of vaccine distribution strategy at peripheral levels and strategies to reach hard to reach population, based on their own experience gained with the support they provided to provinces and districts on social mobilization, universal access to health and EPI vaccine and gas distribution... 4.1.3. Signature Table for the Coordinating Committee for Immunization.. We the members of the ICC, HSCC, or equivalent committee [1] met on the 10/09/2013 to review this proposal. At that meeting we endorsed this proposal on the basis of the supporting documentation which is attached. The minutes of the meeting endorsing this proposal are attached as Document number 5. The signatures endorsing the proposal are attached as Document number 6 (please use the list for signatures in the section below)... Please refer to Annex D of the Guidelines for more information on ICCs... Function; Title / Organisation; Name; Please sign below to indicate the attendance at the meeting where the proposal was endorsed; Please sign below to indicate the endorsement of the minutes where the proposal was discussed. Chair; National Director Public Health - MOH; Dr. Mouzinho Saíde. Secretary; National EPI manager; Dr. Maria Benigna. Members; WHO Representative; Daniel Kertesz. Acting Unicef Representative; Emmanuel Copabianco. FDC executive Director; Narciso Matos. Village Reach Coordinator; Maria Gomes.. By submitting the proposal we confirm that the quorum has been met. Yes.. The minutes from the three most recent ICC meetings are attached as DOCUMENT NUMBER : 7... 4.2. National Immunization Technical Advisory Group.. Has a NITAG been established in the country ? Yes.. We the members of the NITAG met on the to review this proposal. At that meeting we endorsed this proposal on the basis of the supporting documentation which is attached as Document number 8... 4.2.1. The NITAG.. Profile of the NITAG.. Name of the NITAG; Comité de Peritos para a Imunização (CoPI). Year of constitution of the current NITAG; 2011. Organisational structure (e.g., sub-committee, stand-alone); The Committee stands alone and is an advisory group to the Ministry of Health.. Frequency of meetings; Twice a year.. Function; Title / Organisation; Name. Chair; Prof. Dr.; Helder MARTINS – Senior Public Health Specialist. Secretary; Dr.; Mouzinho Saíde - National Director of Public Health - Ministry of Health. Members; Vice President - Prof. Doctor; Jahit SACRALAL- Epidemiologist and Researcher. Prof. Doctor; João Leopoldo da COSTA - Epidemiologist. Prof. Doctor; Moshin SIDAT - Epidemiologist. Prof. Doctor; Elena FOLGOSA - Microbiologist. Doctor; Eduardo SAMO GUDO Jr. - Immunologist. Prof. Dr.; Ana GRAÇA - Pediatrician. Dr.; Benedita SILVA - Pediatrician. Prof. Doctor; Antonio BUGALHO - Gynecologist. Prof. Dr.; Paula CAUPERS – Specialist of Internal. Dr.; Eusébio MACETE – Specialist in Clinical Trials of Vaccines / Researcher. Dr.; Betuel SIGAÚQUE – Researcher / Pediatrician. Dr.; Estrela POLÓNIA – Health Economist. Dr.; Neusa TORRES – IEC Specialist. Mrs.; Margarida MATSINHE – Logistics Specialist.. Major functions and responsibilities of the NITAG.. Major functions and responsibility of the NITAG: Conduct policy and immunization plans analysis and, on this basis, to make recommendations on its optimization, Perform analysis and, if necessary, to encourage further research on the characteristics of vaccines (including their safety, efficacy, immunogenicity, cost and Cost / benefit ratios) and on the epidemiology of vaccine-preventable diseases (including disease weight and severity, its impact on mortality, distribution by age groups, circulating strains, etc.). for from them, advise and make recommendations to national authorities and the management of the Expanded Program on Immunization (EPI) on the formulation of strategies for prevention and control of vaccine-preventable diseases through immunization, Advise and make recommendations to national authorities on monitoring and evaluation of EPI, so that the quality of the program and its impact can be measured and, if possible, quantified and on that basis, advise and make recommendations to national authorities on the continuation or modification of existing programs, Identify the data needs for the development of immunization policy and strategies and, on that basis, advise and make recommendations to national authorities on improving procedures for collecting, processing and quality assurance of these data and of other important information, Follow very closely the data from pharmacovigilance of vaccines already on the market, in order to assess their safety and efficiency and thus advise and make recommendations to national authorities on actions to be taken, ? Advise and make recommendations to national authorities and to the management of EPI on programmatic aspects, particularly with regard to cold chain, waste management, immunization schedule, calculation of the size of the target groups, mobile brigades and other forms of outreach activities, need of supplementary immunization activities, interconnection of EPI activities with other programs, etc., Keep the national authorities and EPI managers informed of the latest scientific advances in immunization and the prevention and control of vaccines preventable diseases, Advise and make recommendations to national authorities and, wherever appropriate, to government organizations and institutions and partners, in formulating policies, plans and strategies for research, development and evaluation of new vaccines and future technologies for the administration of vaccines, showing its relevance for the Health of the population. Promote intra and intersectoral links for action and for coordination with partners, on relation to the development and distribution of vaccines and of potential vaccines for priority diseases, Promote partnership between government, civil society and funding agencies for advocacy of immunization, so that immunization activities are recognized as sustainable, having scientific basis and credible, Perform analysis on the financing of vaccines and immunization programs, as well as on funding mechanisms, for from them, advise and make recommendations to national authorities and the management of the Expanded Program on Immunization (EPI) Establish partnerships and collaborative relationships with national (other countries) and International committees for immunization, Analyze, give advice and make suggestions and recommendations on all matters referred to it by the Minister of Health... The minutes from the three most recent NITAG meetings are attached as (Document Number: 9)...

5. Immunisation Programme Data.. 5.1 Background information.. Please complete the table below, using data from available sources. Please identify the source of the data, and the date. Where possible use the most recent data and attach the source document... ▪; Please refer to the Comprehensive Multi-Year Plan for Immunisation (cMYP) (or equivalent plan) and attach a complete copy (with an Executive Summary) as DOCUMENT NUMBER 10. Please attach the cMYP costing tool as DOCUMENT NUMBER 11.. ▪; Please attach relevant Vaccine Introduction Plan(s) as DOCUMENT NUMBER : 12. ▪; Please refer to the two most recent annual WHO/UNICEF Joint Reporting Forms (JRF) on Vaccine Preventable Diseases. ▪; Please refer to Health Sector Strategy documents, budgetary documents, and other reports, surveys etc, as appropriate... Please use the most recent data available and specify the source and date... Figure; Year; Source. Total population; 23,700,715; 2012; INE (National Institute of Statistic). Infant mortality rate (per 1000); 64; 2011; DHS 2011. Surviving infants[1]; 953,881; 2012; INE (National Institute of Statistic). GNI per capita (US$); 410; 2013; WHO NHA website. Total Health Expenditure (THE) as a percentage of GDP; 26; %; 2013; WHO NHA Website. General government expenditure on health (GGHE) as % of General government expenditure; 35; %; 2013; WHO NHA Website.. [1] Surviving infants = Infants surviving the first 12 months of life.. 5.1.1 Lessons learned.. Routine New Vaccines Support.. If new or under-used vaccines have already been introduced in your country, please give details of the lessons learned from previous introduction(s) specifically for: storage capacity, protection from accidental freezing, staff training, cold chain, logistics, coverage and drop-out rates, wastage rate, etc., and suggest action points or actions taken to address them. Please refer to previous Post Introduction Evaluations (PIE), if applicable... Lessons Learned; Action Points. The assumption by health care workers that most care-givers are illiterate and therefore, do not need to know the names of vaccine given to their children is grossly misplaced, as some of the care-givers already are familiar with names of vaccines like polio, measles. (PIE for penta 2011) A great opportunity was missed to increase immunization acceptance by care-givers by not providing them information about the new vaccine introduced and the diseases they prevent. (PIE Penta 2011); Actions were taken during the introduction of PCV10 in 2013. This aspect was taken into consideration, and mobilization was made to inform the community that the new vaccine was being introduced. Evaluation of the impact of this measure will be made during the PIE of PCV.. Post-introduction evaluation exercises are good opportunities to assess the program performance in general (PIE for Penta 2011); Planning for conduct PIE for PCV and other vaccines that will be introduced into the program. Perform supervision immediately after new vaccine introduction.. GAVI fund for the introduction of new vaccine was delayed, and the country di not mobilize enough internal finance resources, this compromised some activities.; It is important to mobilize local finance prior to the introduction of vaccines to avoid the constraints related to the delay of funds. Complaint of care-givers who had children under one and were not illegible for vaccination (during PCV10 Introduction); Communication messages for demand creation must be carefully designed to ensure that the people clearly understand the target group for the new vaccines.. The inclusion of NITAG in the process of vaccination in the country support for decision-making on the introduction of new vaccine; Strengthen the NITAG coordination. Limited skills and knowledge of workers at the health facility (PIE Penta 2011); Upon the introduction of the PCV10, staff at all levels received training on the new vaccine, using adapted WHO instruments. Training included knowledge of the disease protected by the vaccine and vaccine management aspects.. Wastage rate not recorded; EVMA found waste due to VMM reaching the discard point, expire date, stock out in some places and overstock in others; (PIE Penta 2011); Data collections tools have been updated to include monitoring of wastage rate. Reporting of wastage will be systematic as of 2014. Training on vaccine management commenced in 2013 and will be on going, as part of the EVM improvement plan. Appointment and training of EPI logisticians at national and provincial levels Introduction of District Vaccine Data Management tool Regular supportive supervision at all levels. Shortage of CC capacity in some provinces in northern zone of the country, leading to more shipments than normal. Depleted CC in some districts with frequent breakdown due essentially to lack of spare parts and kerosene ( Only the province of Inhambane is still using Kerosene cc equipment).; A countrywide capillary inventory of the cold chain was made in 2013, based on which a Cold Chain Upgrade Plan (CCUP) was developed, taking into consideration the CC requirements up to 2018. Immediate implementation of the CCUP by replacing obsolete cold chain equipment and gradual replacement of kerosene refrigerators by electric and solar equipment, as appropriate, and by increasing Cold Storage capacity at all levels, to accommodate the new vaccine. Enough funds have been secured for the procurement of the cold chain equipment.. Training of provincial cold chain technicians and provision of funds for cold chain maintenance activities.. Training of users at the health facility level on daily basic maintenance of refrigerators.. 5.1.2 Health planning and budgeting.. Please provide information on the planning and budgeting cycle in your country. The planning and budgeting process in the MoH of Mozambique is performed on an annual basis and is aligned with the General Health Strategic Plan (PES) of the MoH. By the end of second quarter of every year the Directorates of the MoH identify the activities for the following year taking into account the priorities set in the PES. These activities are budgeted and the final draft of the plan is presented to the Minister of Health for evaluation and approval. The MoH discusses with the cabinet and approves the plan. Subsequently the plan is presented and discussed with the partners in special forum that occurs twice a year (Health Coordination Committee – CCS) and gaps in terms of budget discussed and pledges are made from the partners to fulfill the gaps according to the areas of interest of each of the partners. Finally the plan is sent to the Ministry of Plan and Development.. Please indicate the name and date of the relevant planning document for health. he most important planning document in the health sector is the NHSSP, which will be finalized by end of October, and cover the period 2014-2018. Is the cMYP (or updated Multi-Year Plan) aligned with the proposal document (timing, content, etc.). Yes, the cMYP is aligned with this document in the sense that it captures all the needs for the introduction of new vaccines (in this case rotavirus vaccine), which is planned for introduction 2015. This document is an application for the introduction of Rotavirus vaccine in 2015. Therefore it is aligned in time and content with the cMYP.. Please indicate the national planning budgeting cycle for health. As described above, the National Planning and Budgeting cycle of the MoH is annual starting at the end of the second quarter of each year.. Please indicate the national planning cycle for immunization. In the last quarter of each year, the program prepares its annual plan for the following year. The plan is shared with the Department of Planning and Finance for review, and shared with partners for their contributions and pledges, and the added to the overall plan of the MOH. The approval of this plan is made alignment with the national plans, such as PES, PEES, CMYP, and budgeting ceiling is based on the MTEF....

5.1.3 Preparatory activities.. Please provide an outline of all preparatory activities for vaccine(s) introduction. 1. Develop an operational and technical assistance plan for the introduction of the vaccine 2. Carry out meetings with different partners and stakeholders 3. Advocate with partners and stakeholders for the mobilization of additional financial resources 4. Develop and implement a communication strategy. Activities to include mass media communication in both official and local languages, involvement of leaders of influence to engage with the communities with special focus to illiterate women and to rural areas. 5. Train health workers and APEs (Community Health Workers) for improved interpersonal communication skills in communicating about the new vaccines. 6. Adapt standard WHO instruments for training of health workers of all levels. Training to include disease being protected by the vaccine, vaccine management, surveillance, etc. 7. Update, reproduction and distribution of immunization cards to capture the new vaccines (EPI register instruments have been updated) 8. Distribution of vaccines and related supplies. 9. Supportive supervision 10. Strengthening the surveillance system to accommodate sentinel surveillance for Rotavirus. Establishment of baseline of intussusception rate 11. Launch ceremony.. 5.1.4 Gender and equity.. Please describe any barriers in access to immunisation services that are related to geographic, socio-economic and/or gender equity and actions taken to mitigate these barriers. Highlight where these issues are addressed in the vaccine introduction plan(s).. Health-for-all is the Mozambican Government policy. DHS 2011 shows that there is no difference in service utilization of immunization among male and female children (76.2 and 76.1 DTP3 coverage), but there are differences with regards to place of residence and the degree of literacy. For instance, children living in rural areas have 72.3% DPT3 coverage as compared to their mates in urban areas (86.3%). Meanwhile, DPT3 among children for mothers with secondary level education was (85.6%), primary level (76.9%) and no education (71.5%). Moreover, there are inequalities among provinces, with the province of Zambézia attaining coverage of completely vaccinated children as low as 47% in contrast to the 87% attained by the province of Maputo. (DSH2011) To mitigate the situation the country intends to use the community based structure, such as local leaders and community health workers (APE's) to intensify communication on EPI with emphasis on the benefits of immunization, vaccination schedule and importance of adherence and address misconceptions on vaccination where they may occur. As the differences in coverage are in terms of geographic areas and literacy level, both low in rural areas, systematic monitoring of performance on quarterly basis will help to identify low performing areas and design appropriate strategies to address them. A focus work to identify bottlenecks to immunization delivery and uptake will be implemented in the worst performing province of Zambézia. Lessons learned will create the basis to develop an equity improvement plan that may be scaled up to other provinces.. Discuss how equity issues (geographic, socio-economic and/or gender) are being taken into account in the design of social mobilization and other strategies to increase immunization coverage. Highlight where these issues are addressed in the vaccine introduction plan(s).. Yes. Even though no differences are found among girls and boys concerning utilization of immunization services, differences are found based on literacy level and geographic areas. However, because we are aware that gender aspects must be addressed, as a general strategy the country always tries to address gender imbalances whenever a new intervention is offered. In this context, the involvement of the Foundation for Community Development (FDC), a champion in the fight for increasing the opportunities of girls to education and health and that of the Red Cross and other community based organizations that have deep linkages with communities will be crucial. They will be the leaders in the development of the communication and community engagement components of the social mobilization plan for promoting utilization of immunization services. With support of these organizations, specific communication strategies will be developed, targeting influential people in the communities such as parents, guardians, teachers, students (of both sexes), community leaders and political leaders in order to guarantee that all layers of society are convinced that it is important and cost-effective to have both girls and boys immunized against vaccine preventable disease. The need for this communication strategy to address possible gender imbalances is highlighted in the advocacy and social mobilization chapter of the EPI cMYP 2014-2018.. Please indicate if sex disaggregated data is collected and used in immunization routine reporting systems.. Yes, it is used for children fully immunized. However, it is worth noting that according to different surveys that have been conducted in this country, there is no difference in the utilization of immunization services between girls and boys.. Is the country currently in a situation of fragility (eg. insecurity, conflict, post-conflict, refugees/and or displaced persons and recent, current or potential environmental disaster, such as flooding, earthquake or drought)? If Yes, please describe how these issues may impact your immunisation programme, planning for introduction of routine vaccines or campaigns and financing of these activities.. The country is not in any known situation of fragility... 5.1.5 Data quality.. Please attach a data quality assessment report, if one has been completed within the previous 36 months (DOCUMENT NUMBER: 13). If available, an improvement plan and progress report on the implementation of the improvement plan should also be submitted (DOCUMENT NUMBER: 14, DOCUMENT NUMBER : 15)....

5.2. Baseline and Annual Targets (NVS Routine Support)... Please refer to cMYP pages to assist in filling-in this section... Number; Base Year; Baseline and Targets; Baseline and Targets; Baseline and Targets. 2012; 2015; 2016; 2017. Total births; 1,019,104; 1,106,272; 1,136,186; 1,166,497. Total infants’ deaths; 65,223; 70,801; 72,716; 74,656. Total surviving infants; 953,881; 1,035,471; 1,063,470; 1,091,841. Total pregnant women; 1,185,036; 1,286,396; 1,321,181; 1,356,427. Target population vaccinated with BCG; 1,010,839; 1,073,084; 1,113,463; 1,154,832. BCG coverage; 99 %; 97 %; 98 %; 99 %. Target population vaccinated with OPV3. OPV3 coverage; 91 %; 84 %; 86 %; 88 %. Number of infants vaccinated (to be vaccinated) with DTP1; 950,716; 935,264; 962,721; 1,011,389. Number of infants vaccinated (to be vaccinated) with DTP3; 858,543; 869,795; 914,585; 960,820. DTP3 coverage; 90 %; 84 %; 86 %; 88 %. Wastage[1] rate in base-year and planned thereafter (%) for DTP; 16; 10; 10; 10. Wastage[1] factor in base-year and planned thereafter for DTP; 1.19; 1.11; 1.11; 1.11. Target population vaccinated with 1st dose of Measles; 837,884; 931,923; 978,393; 1,026,330. Target population vaccinated with 2nd dose of Measles; 0; 838,731; 900,121; 964,751. Measles second dose coverage; 0 %; 81 %; 85 %; 88 %. First Presentation: Measles second dose, 10 dose(s) per vial, LYOPHILISED. Wastage[1] rate in base-year and planned thereafter (%) {0}; 40; 40; 40; 40. Wastage[1] factor in base-year and planned thereafter (%); 1.67; 1.67; 1.67; 1.67. Maximum wastage rate value for Measles second dose, 10 dose(s) per vial, LYOPHILISED; 40 %; 40 %; 40 %; 40 %. Target population vaccinated with 1st dose of Rotavirus; 0; 668,045; 962,721; 1,011,389. Target population vaccinated with 2nd dose of Rotavirus; 0; 621,282; 914,585; 960,820. Rotavirus coverage; 0 %; 60 %; 86 %; 88 %. First Presentation: Rotavirus, 2-dose schedule. Wastage[1] rate in base-year and planned thereafter (%) {0}; 0; 5; 5; 5. Wastage[1] factor in base-year and planned thereafter (%); 1.00; 1.05; 1.05; 1.05. Maximum wastage rate value for Rotavirus, 2-dose schedule; 5 %; 5 %; 5 %; 5 %. Number of infants vaccinated (to be vaccinated) with 1st dose of TT+; 923,152; 951,933; 1,004,098; 1,058,013. TT+ coverage; 78 %; 74 %; 76 %; 78 %. Annual DTP Drop out rate [ ( DTP1 – DTP3 ) / DTP1 ] x 100; 10 %; 7 %; 5 %; 5 %.. [1] Number of infants vaccinated out of total births. [2] Number of infants vaccinated out of total surviving infants. [3] Indicate total number of children vaccinated with either DTP alone or combined. [4] Number of pregnant women vaccinated with TT+ out of total pregnant women. [5] The formula to calculate a vaccine wastage rate (in percentage): [ ( A - B ) / A ] x 100. Whereby: A = the number of doses distributed for use according to the supply records with correction for stock balance at the end of the supply period; B = the number of vaccinations with the same vaccine in the same period.....

Number; Baseline and Targets. 2018. Total births; 1,197,258. Total infants’ deaths; 76,625. Total surviving infants; 1,120,633. Total pregnant women; 1,392,197. Target population vaccinated with BCG; 1,197,258. BCG coverage; 100 %. Target population vaccinated with OPV3. OPV3 coverage; 90 %. Number of infants vaccinated (to be vaccinated) with DTP1; 1,061,653. Number of infants vaccinated (to be vaccinated) with DTP3; 1,008,570. DTP3 coverage; 90 %. Wastage[1] rate in base-year and planned thereafter (%) for DTP; 10. Wastage[1] factor in base-year and planned thereafter for DTP; 1.11. Target population vaccinated with 1st dose of Measles; 1,064,602. Target population vaccinated with 2nd dose of Measles; 1,011,372. Measles second dose coverage; 90 %. First Presentation: Measles second dose, 10 dose(s) per vial, LYOPHILISED. Wastage[1] rate in base-year and planned thereafter (%) {0}; 40. Wastage[1] factor in base-year and planned thereafter (%); 1.67. Maximum wastage rate value for Measles second dose, 10 dose(s) per vial, LYOPHILISED; 40 %. Target population vaccinated with 1st dose of Rotavirus; 1,061,653. Target population vaccinated with 2nd dose of Rotavirus; 1,008,570. Rotavirus coverage; 90 %. First Presentation: Rotavirus, 2-dose schedule. Wastage[1] rate in base-year and planned thereafter (%) {0}; 5. Wastage[1] factor in base-year and planned thereafter (%); 1.05. Maximum wastage rate value for Rotavirus, 2-dose schedule; 5 %. Number of infants vaccinated (to be vaccinated) with 1st dose of TT+; 1,113,757. TT+ coverage; 80 %. Annual DTP Drop out rate [ ( DTP1 – DTP3 ) / DTP1 ] x 100; 5 %.. [1] Number of infants vaccinated out of total births. [2] Number of infants vaccinated out of total surviving infants. [3] Indicate total number of children vaccinated with either DTP alone or combined. [4] Number of pregnant women vaccinated with TT+ out of total pregnant women. [5] The formula to calculate a vaccine wastage rate (in percentage): [ ( A - B ) / A ] x 100. Whereby: A = the number of doses distributed for use according to the supply records with correction for stock balance at the end of the supply period; B = the number of vaccinations with the same vaccine in the same period.....

5.3. Baseline and Annual Targets for Preventive Campaign(s).. No NVS Prevention Campaign Support this year....

6. New and Under-Used Vaccines (NVS Routine) 6.1. Assessment of burden of relevant diseases (if available).. Disease; Title of the assessment; Date; Results. Diarrheal disease; Estimated rotavirus deaths for children under 5 years of age: 2008; January 2012; Available data from WHO indicated that in 2008, the annual estimated numbers of rotavirus deaths among children under age of 5 years was of 4,481 for Mozambique, ranking the country in the 5th position in the sub-region, after Ethiopia, Uganda, Tanzania and Kenya... Disease; Title of the assessment; Date; Results. Diarrheal disease; The burden of rotavirus diarrheal among children less than 5 years of age in Manhiça district, Mozambique; 2013; A Global Enteric Multicentric Study (GEMS) conducted between 2007 and 2010 in Manhiça District in Mozambique with the objective to quantify the burden, sequel and microbiology etiology of moderate-to-severe diarrhea (MSD) in infants and young children, found that in Mozambican children, rotavirus were significantly associated with MSD in infants (42% in cases vs. 16% in controls; OR=6.0, 95% CI: 3.65-9.87, p<0.001) and children aged 12-23 months (22% in cases vs. 18% in controls; OR=3.30, 95%CI: 1.60-6.79, p=0.014). It was also estimated the yearly number of new MSD cases (incidence) for each pathogen. The incidence of MSD was higher among children from 0-11 months of age with 12.5 episodes of MSD each year per 100 children. The incidence of rotavirus was 3.5 episodes per 100 children year at risk, representing 28% of the total MSD in this age group suggesting nearly 30% of the MSD would be prevented by the vaccine (Kotloff et al. Lancet 2013)....

| 6.2. Requested vaccine (Rotavirus, 2 -dose schedule). As reported in the cMYP, the country plans to introduce Rotavirus, using Rotavirus, 2 -dose schedule.. When is the country planning to conduct this vaccine? April 2015. Please note that, due to a variety of factors, the launch date may vary compared to the date stipulated in the application. GAVI will work closely with countries and their partners to address these issues... 6.2.1. Co-financing information. If you would like to co-finance an amount higher than the minimum, please provide information in Your co-financing row... Country group; Low.. Year 1; Year 2; Year 3. 2015; 2016; 2017. Minimum co-financing; 0.20; 0.20; 0.20. Your co-financing (please change if higher); 0.20; 0.20; 0.20.. Year 1. 2018. Minimum co-financing; 0.20. Your co-financing (please change if higher); 0.20.. 6.2.2. Specifications of vaccinations with new vaccine.. Data from; Year 1; Year 2; Year 3. 2015; 2016; 2017. Number of children to be vaccinated with the first dose; Table 5.2; #; 668,045; 962,721; 1,011,389. Number of children to be vaccinated with the second dose; Table 5.2; #; 621,282; 914,585; 960,820. Immunisation coverage with the second dose; Table 5.2; #; 60.00 %; 86.00 %; 88.00 %. Country co-financing per dose; Table 6.2.1; $; 0.2; 0.2; 0.2.. Data from; Year 1. 2018. Number of children to be vaccinated with the first dose; Table 5.2; #; 1,061,653. Number of children to be vaccinated with the second dose; Table 5.2; #; 1,008,570. Immunisation coverage with the second dose; Table 5.2; #; 90.00 %. Country co-financing per dose; Table 6.2.1; $; 0.2..... |  |
| --- | --- |

6.2.3. Portion of supply to be procured by the country (and cost estimate, US$). 2015; 2016; 2017. Number of vaccine doses; #; 131,200; 162,700; 160,700. Number of AD syringes; #; 0; 0; 0. Number of re-constitution syringes; #; 0; 0; 0. Total value to be co-financed by the Country [1]; $; 351,500; 436,000; 430,500.. [1] The co-financing amount for low-income countries indicates costs for the vaccines and any freight charges. The total co-financing amount does not contain the costs and fees of the relevant Procurement Agency, such as contingency buffer and handling fees. Information on these extra costs and fees will be provided by the relevant Procurement Agency as part of the cost estimate to be requested by the Country... 2018. Number of vaccine doses; #; 168,700. Number of AD syringes; #; 0. Number of re-constitution syringes; #; 0. Total value to be co-financed by the Country [1]; $; 451,500.. [1] The co-financing amount for low-income countries indicates costs for the vaccines and any freight charges. The total co-financing amount does not contain the costs and fees of the relevant Procurement Agency, such as contingency buffer and handling fees. Information on these extra costs and fees will be provided by the relevant Procurement Agency as part of the cost estimate to be requested by the Country.... 6.2.4. Portion of supply to be procured by the GAVI Alliance (and cost estimate, US$). 2015; 2016; 2017. Number of vaccine doses; #; 1,624,100; 2,015,300; 1,990,300. Number of AD syringes; #; 0; 0; 0. Number of re-constitution syringes; #; 0; 0; 0. Total value to be co-financed by GAVI; $; 4,348,500; 5,396,000; 5,329,500.. 2018. Number of vaccine doses; #; 2,088,800. Number of AD syringes; #; 0. Number of re-constitution syringes; #; 0. Total value to be co-financed by GAVI; $; 5,593,000.......

6.2.5. New and Under-Used Vaccine Introduction Grant. Calculation of Vaccine Introduction Grant for the Rotavirus, 2 -dose schedule.. Year of New Vaccine Introduction; Births (from Table 5.2); Share per Birth in US$; Total in US$. 2015; 1,106,272; 0.80; 885,018.. The Grant will be based on a maximum award of $0.80 per infant in the birth cohort with a minimum starting grant award of $100,000.. Please describe how the GAVI Vaccine Introduction Grant will be used to facilitate the timely and effective implementation of critical activities in advance of and during the introduction of the new vaccine (refer to the cMYP and the Vaccine Introduction Plan)... Amongst the several activities for new vaccine introduction, GAVI grant will be used to finance selected items as demonstrated in the table below: Table 9: Activities, cost, funding source and gap for Rotavirus vaccine introduction.. Please summarise in the table below the full costs of preparing for and introducing the vaccine, and specify which items are expected to be covered with the one-time GAVI grant. Please note that the country will be required to submit a detailed budget for the Vaccine Introduction Grant prior to release of funds... Cost (and finance) to introduce the Rotavirus, 2 -dose schedule US$.. Cost Category. Total cost for preparation of and delivery of campaign in US$; Funded with GAVI introduction grant in US$. Training; 257,210; 247,781. Social Mobilization, IEC and advocacy; 313,054; 116,625. Cold Chain Equipment & Maintenance; 1,593,593; 166,420. Vehicles and Transportation; 0; 0. Programme Management; 114,286; 86,246. Surveillance and Monitoring; 159,286; 96,286. Human Resources; 0; 0. Waste Management; 85,714; 84,714. Technical Assistance; 10,000; 0. Other (please specify). Supportyive supervisory visits; 71,429. Post introduction evaluation; 50,000; 50,000. Vaccine clearing central and deliveryall levels; 90,069; 36,945. Construction of vaccine stores; 1,368,000. Total; 4,112,641; 885,017..... Where GAVI support is not enough to cover the full needs, please describe other sources of funding and the expected amounts to be contributed, if available, to cover your full needs... The introduction of rotavirus vaccine, excluding the roll out process, will cost approximately $20.0 million over the 4 year period (2015-2018). The rollout process in terms of cold chain expansion (cc equipment and construction of vaccine stores), training, surveillance, monitoring and evaluation, program management, advocacy and social mobilization, and vaccine and related materials distribution will cost an additional $ 4.1 million, for a total cost of 24.0 million. Overall, there is a gap of $575,296 (see tables 9 & 10), representing 14% of unfunded resources, concerning advocacy and social mobilization ($76,786), program management ($28,040) and construction buildings of regional and provincial vaccine stores ($470,471). The program will attempt the following strategies to address the gap: For advocacy and communication, the program will attempt to reduce the gap through advocacy with the media to get free radio/television spots or reduced fees. In addition, IEC for new vaccine can be integrated within those activities already being carried out by the local governments. This might include, for instance, having local authorities using its structure already in place to inform communities about the new vaccine (using leaflets), support the health sector in addressing community queries and fears about new vaccine, and mobilizing them for adherence and increased utilization of immunization services. For program management will integrate these activities in the already existing routine scheme. For instances, rotavirus vaccine management will be done using the same tools used for other vaccines, and the routine training of health workers on vaccine management and vaccine wastage monitoring will include rotavirus vaccine management. Lastly, for vaccine store buildings gap, it could be addressed through GAVI-HSS funds. In addition, if MSD is approved and simultaneous introduction of rotavirus and MSD allowed, an additional $885,017 for MSD introduction grant will be made available. This would allow the country to cover the $575,296 gap, and have extra money to strengthen routine immunization. However, it is worth mentioning that if the country fails to get final approval of the GAVI-HSS for which it has to respond satisfactorily to IRC queries, and the MSD grant is not made available, the gap will considerably increase to approximately $1.6 million, corresponding to 38% funding gap. Addressing this level of gap will require vigorous resource mobilization strategy. Taking the opportunity that introduction of new vaccines is highly regarded amongst Ministry of Health and its development partners, the MoH will advocate for more resources, or, as a last resort, reallocation of resources to cover the gap. Even though resources for other activity items have been completely secured, taking into account also the GAVI new vaccine introduction grant, the program will attempt to reduce program direct expense on these items and save some resources that can be diverted to cover other needs in the funding gap. For instances, during routine supportive supervisory visits for routine immunization, it can be taken the opportunity of checking the status and quality of preparedness for rotavirus vaccine introduction in the last 6 months prior to the introduction of rotavirus vaccine in April 2015. Meanwhile, supportive supervision for rotavirus vaccine immunization in terms of coverage, drop out etc., after introduction, will be conducted at the same time as that of other national immunization program vaccines. The same can be said about rotavirus surveillance, which can also be incorporated in already existing sentinel posts system for PBMS in the same hospitals. Vaccine distribution can also be incorporated in the already existing routine distribution system. Considering that all these are routine activities and have funds secured in the cMYP, their weight in funding gap can be easily minimized. In addition, the EPI program and ICC will advocate with other partners to get some additional resources specifically for new vaccine introduction event. Building on the experience of tetravalent DPT-HepB pentavalent DPT-HepB-Hib, PCV introductions and mass campaigns, public and private sectors at national level will also be approached to provide support. Further, the EPI program and the District Directorate of Health can advocate (based on the burden of diarrheal disease, the expected impact in child morbidity and mortality, and some examples of successful collaboration in the past) with local governments, NGO’s and private sector to mobilize resources for their constituencies to cover some selected cost items such as fuel, dissemination of messages in local languages, etc. Generally speaking, the gap for new vaccine introduction can be minimized with good communication, coordination and integration......

| 6.3. Requested vaccine (Measles second dose, 10 dose(s) per vial, LYOPHILISED). As reported in the cMYP, the country plans to introduce Measles second dose, using Measles second dose, 10 dose(s) per vial, LYOPHILISED.. When is the country planning to conduct this vaccine? April 2015. Please note that, due to a variety of factors, the launch date may vary compared to the date stipulated in the application. GAVI will work closely with countries and their partners to address these issues.. Currently the Measles 5-dose vial presentation is not available, but please indicate if the country would prefer this presentation if it becomes available. Not selected. If the country is introducting measles-rubella (MR) in the routine system, is the country planning to switch the second dose of measles to MR as well, in addition to the first MR dose? Yes. If [YES], when? January. Please note that if the country is planning to switch the routine second dose of measles to MR, the country will be required to finance the rubella component, in addition to financing the routine first dose of MR... 6.3.1. Specifications of vaccinations with new vaccine.. Data from; Year 1; Year 2; Year 3. 2015; 2016; 2017. Number of children to be vaccinated with the first dose; Table 5.2; #; 931,923; 978,393; 1,026,330. Immunisation coverage with the first dose; Table 5.2; #; 81.00 %; 84.64 %; 88.36 %.. Data from; Year 1. 2018. Number of children to be vaccinated with the first dose; Table 5.2; #; 1,064,602. Immunisation coverage with the first dose; Table 5.2; #; 90.25 %..... |  |
| --- | --- |

6.3.2. New and Under-Used Vaccine Introduction Grant. Calculation of Vaccine Introduction Grant for the Measles second dose, 10 dose(s) per vial, LYOPHILISED.. Year of New Vaccine Introduction; Births (from Table 5.2); Share per Birth in US$; Total in US$. 2015; 1,106,272; 0.80; 885,018.. The Grant will be based on a maximum award of $0.80 per infant in the birth cohort with a minimum starting grant award of $100,000.. Please describe how the GAVI Vaccine Introduction Grant will be used to facilitate the timely and effective implementation of critical activities in advance of and during the introduction of the new vaccine (refer to the cMYP and the Vaccine Introduction Plan)... Table 11: Activities, cost, funding source and gap for MSD vaccine introduction.. Please summarise in the table below the full costs of preparing for and introducing the vaccine, and specify which items are expected to be covered with the one-time GAVI grant. Please note that the country will be required to submit a detailed budget for the Vaccine Introduction Grant prior to release of funds... Cost (and finance) to introduce the Measles second dose, 10 dose(s) per vial, LYOPHILISED US$.. Cost Category. Total cost for preparation of and delivery of campaign in US$; Funded with GAVI introduction grant in US$. Training; 257,211; 247,782. Social Mobilization, IEC and advocacy; 381,791; 283,045. Cold Chain Equipment & Maintenance; 0; 0. Vehicles and Transportation; 0; 0. Programme Management; 57,143; 0. Surveillance and Monitoring; 98,458; 96,315. Human Resources; 0; 57,143. Waste Management; 75,714; 75,714. Technical Assistance; 10,000; 10,000. Other (please specify). Vaccine clearing central and distribution all levels; 42,188; 41,364. Supportive supervisory visits; 71,429; 23,655. Post introduction evaluation; 50,000; 50,000. Total; 1,043,934; 885,018..... Where GAVI support is not enough to cover the full needs, please describe other sources of funding and the expected amounts to be contributed, if available, to cover your full needs... The resources made available by GAVI will be enough to cover requirements for MSD, even if it is introduced separately of rotavirus, as demonstrated in the table 12 above. The Government and its local Partners has managed to secure the additional $185,682 necessary funds, to supplement the 885,017 GAVI MSD introduction grant. However, whenever possible, the country will still implement some measures that would allow saving some resources that could be used for strengthening of routine immunization, for instance, through integration of most of these activities into the ones already taking place in the routine, like vaccine distribution, surveillance, waste management, and so on, as describe above in section 6.2 with rotavirus vaccine introduction. The country’s preference would be the simultaneous introduction of MSD with rotavirus vaccine as explained above. This would avoid repetition of the new vaccine introduction activities (even though MSD in not a new vaccine itself, but activities to introduce it are similar as those of required for new vaccine introduction), allowing savings of resources that would be used to cover the funding gap related to rotavirus introduction, chiefly for social mobilization and community involvement ($76,786), construction of vaccine stores to install the WICR ($470,471) and program management at various levels of the system ($28,040), and yet to have some resources for strengthening of routine immunization......

7. NVS Preventive Campains. No NVS Prevention Campaign Support this year...

8. Procurement and Management. 8.1 Procurement and Management of New and Under-Used Vaccines Routine.. Note: The PCV vaccine must be procured through UNICEF to be able to access the price awarded by the Advance Market Commitment (AMC)... a) Please show how the support will operate and be managed including procurement of vaccines (GAVI expects that most countries will procure vaccine and injection supplies through UNICEF):. Mozambique has already benefited from the introduction of Hepatitis B vaccine as tetravalent (DTP-HepB) in 2001, of hemophillus influenza type B vaccine as pentavalent presentation (DTP-HepB-Hib) in 2009, and Pneumococcal vaccine as bivalent presentation (PCV10) in 2013, postponed from 2012, all with GAVI support. The procurement was through UNICEF mechanisms. With this previous experience, we propose that the same procedure be used for Rotavirus. as following: 1. Needs for the following year are presented through previous APR to GAVI; 2. Receiving GAVI’s decision letter to the country with the quantities and cost of the vaccines to be delivered and the co-financing amount 3. The country prepares and sends to UNICEF the plan, and disburses the co-financing amount to UNICEF. 4. Vaccines are shipped according to the plan.. b) If an alternative mechanism for procurement and delivery of vaccine supply (financed by the country or the GAVI Alliance) is requested, please document. ; Other vaccines or immunisation commodities procured by the country and descriptions of the mechanism used.. ; The functions of the National Regulatory Authority (as evaluated by WHO) to show they comply with WHO requirements for procurement of vaccines and supply of assured quality.. Traditional vaccines and respective injection supplies devices are bought directly by MOH through CMAM (center for medicines and medical supplies). All of them are purchased from WHO pre-qualified producers. The mechanism is the same as described above, with exception that the EPI sends the shipment plan to CMAM. For GAVI supported vaccines, as stated above ,UNICEF is the procuring agency on behalf of MOH. c) Please indicate how funds should be transferred by the GAVI Alliance (if applicable). The funds for some of the activities for new vaccine introduction (according to GAVI policy, Mozambique expects receiving $0.80per child from GAVI to support the new vaccine introduction process)should be transferred directly to MOH Bank account provided bellow. d) Please indicate how the co-financing amounts will be paid (and who is responsible for this). The co-financing will be paid by MOH through direct bank transfer of the necessary amount to UNICEF bank account. Every year, by June the Planning Department will issue an order to MOH financial directorate for transference of co-payment fund to UNICEF. It will be direct responsibility of the Finance Directorate of the MoH to pay directly the co-financing amounts to UNICEF. The ICC and EPI will monitor the process. e) Please describe the financial management procedures that will be applied for the management of the NVS cash support, including procurement.. The mechanism for channeling GAVI introduction fund into the country will work as follows: Funds from GAVI will be deposited into the Forex Account at the Central Bank of Mozambique after which the funds will be deposited into the Treasury, into so-called CUT (Conta Única do Tesouro – Single Treasury Account). The Ministry of Finance (MoF) will open a ledger with funds received through GAVI. This way, the MoF will be able to track expenses against disbursements and be able to report on performance against budget. The MoF will then transfer the funds to the MoH. Public funds from the MoF to the MoH are received and controlled through DAF accounts. Request of funds Disbursements from CUT to the implementing entity (MoH) will follow the normal procedure in the country for the planned interventions.. f) Please outline how coverage of the new vaccine will be monitored and reported (refer to cMYP). The new vaccines will be monitored by district, focusing on coverage rate, dropout rate and vaccine wastage. g) If applying for measles second dose, does the country wish to have the support in cash or in-kind? Cash.. 8.2 Procurement and Management for NVS Preventive Campaign(s).. No NVS Prevention Campaign Support this year...

8.3 Vaccine Management (EVSM/EVM/VMA).. Under the new guidelines, it is mandatory for countries to conduct an Effective Vaccine Management (EVM) assessment prior to an application for introduction of new vaccine. This EVM should have been conducted within the preceding 36 months.. Did the country have Effective Vaccine Management (EVM) in the past? Yes. When was the EVM conducted? May 2012. Please attach the most recent EVM report (DOCUMENT NUMBER: 20,21,22), the corresponding EVM improvement plan (DOCUMENT NUMBER : 21) and progress on the EVM improvement plan (DOCUMENT NUMBER : 22). The improvement plan should include a timeline, budget of committed resources for these activities and funding gaps, if any, as well as M&E indicators to monitor progress of implementation.. Does the country plan to conduct an Effective Vaccine Management (EVM) Assessment in the future? Yes. When is the next Effective Vaccine Management (EVM) Assessment planned? May 2015.. 8.4 Waste management.. Please describe the country’s waste management plan for immunisation activities (including campaigns). Include details on the safe handling, storage, transportation and disposal of immunisation waste.. Immunization program uses AD syringes and safety boxes and has standard waste management practices in all immunization sessions and in all sites were this service is provided, be it fixed or outreach. In the urban areas where there are incinerators, the safety boxes a kept in a safe place and then collected periodically for incineration, in accordance to the national policy on waste management. However, in most rural and peripheral health facilities, it is used the open burn and burry method. In outreach activities, the safety boxes are transported to the nearest health facility where they are incinerated, usually using the open burn and berry process. The program has planned to use part of new vaccine introduction grant to install incinerators in selected priority health facility, this way, gradually expanding the incinerators. Some of these resources will also be used to support waste management plan in terms of provision of fuel for collection of waste to locals with incinerators. Meanwhile, the open burn and burry method will continue to be used where collection of waste might prove very difficult....

9. Additional Comments and Recommendations from the National Coordinating Body (ICC/HSCC).. Comments and Recommendations from the National Coordinating Body (ICC/HSCC).. After several meetings, in which the introduction of rotavirus vaccine was discussed in terms public health benefits, cost implications of vaccine itself and associated cold chain expansion, the ICC agreed that: 1. The burden of diarrhea disease associated to rotavirus among children is extremely high in Mozambique. 2. The logistical aspects for the introduction of rotavirus can be met in one and a half year from now, including the increment in cold chain capacity at all levels and construction of vaccine store buildings for installation of WICR. It has also noted that after addressing the needs for rotavirus, the MSD dose needs will be automatically addressed, as big WICR have been selected in line with the cold chain update plan developed in May 2013. 3. It has already been secured $1.3 million to address primarily the CC capacity issue at all levels and vaccine distribution constraints with purchase of refrigerated trucks. The level of gap can be addressed through engagement of new stakeholders, better communication, integration and sharing of resources where feasible, at various levels of the system. The ICC has also noted that if simultaneous introduction of rotavirus vaccine and measles second dose is approved, there will be enough resources to cover the gap, as the country will receive 2 x $885,017 according to the 2015 birth cohort at $0.80 per child. However, the ICC has also noted with concern that in case the country fails to get GAVI-HSS approval, for which is now responding to IRC queries, the gap might increase considerably to $1.6 million, a level of gap that could not be easy to cover. 3. The cMYP contemplates activities that lead to an increase in the vaccine coverage among target group, with emphasis on hard to reach areas. Therefore, the ICC endorses the proposal and highly recommends that this application for simultaneous introduction of rotavirus vaccine and MSD be submitted to GAVI for consideration....

10. List of documents attached to this proposal.. 10.1. List of documents attached to this proposal.. Document Number; Document; Section; Mandatory; File. Rota signatures justification.doc. 1; MoH Signature (or delegated authority) of Proposal; File desc:. Date/time: 9/15/2013 6:07:41 PM. Size: 26624. Rota signatures justification.doc. 2; MoF Signature (or delegated authority) of Proposal; File desc:. Date/time: 9/15/2013 6:08:22 PM. Size: 26624. not applicable.doc. 3; MoE signature (or delegated authority) of HPV Proposal; 4.1.1; File desc:. Date/time: 9/15/2013 6:12:21 PM. Size: 25600. Rota signatures justification.doc. 3; Signatures of ICC or HSCC or equivalent in Proposal; File desc:. Date/time: 9/15/2013 6:09:53 PM. Size: 26624. TDR do ICC_FINAL_English.doc. 4; Terms of Reference for the ICC; 4.1.2; File desc:. Date/time: 9/15/2013 6:40:27 AM. Size: 62976. Rota signatures justification.doc. 4; Minutes of ICC/HSCC meeting endorsing Proposal; File desc:. Date/time: 9/15/2013 6:09:16 PM. Size: 26624. Mozambique- MULTI-Year Plan - 2014-2018_Final.doc. 5; comprehensive Multi Year Plan - cMYP; File desc:. Date/time: 9/16/2013 12:23:08 AM. Size: 1603072. MOZ UPDATED_cMYP_V3.3.1_Final Septemebr 2013.xlsm. 6; cMYP Costing tool for financial analysis; File desc:. Date/time: 9/16/2013 12:25:00 AM. Size: 2439096. Mozambique_Rotavirus Vaccine Introduction_Final 2013.doc. 7; Plan for NVS introduction (if not part of cMYP); 5.1; File desc:. Date/time: 9/16/2013 12:26:08 AM. Size: 1008128. Minuta ICC 7 fev 2013. (2).docx. 7; Minutes of last three ICC/HSCC meetings; File desc:. Date/time: 9/15/2013 3:27:27 PM. Size: 174706. Mozambique EVMA 2012-05 Improvement Plan Implementation (Autosaved).xls. 8; Improvement plan based on EVM; File desc:. Date/time: 9/15/2013 6:37:05 AM. Size: 42496. relatorio EVM preliminar.doc. 20; EVM report; 8.3; File desc:. Date/time: 9/15/2013 6:36:19 AM. Size: 2609152. Mozambique EVMA 2012-05 Improvement Progress.xls. 22; EVM improvement plan progress report; 8.3; File desc:. Date/time: 9/15/2013 6:39:29 AM. Size: 123392...

11. Annexes... Annex 1 - NVS Routine Support. Annex 1.1 - NVS Routine Support (Rotavirus, 2 -dose schedule). Table Annex 1.1 A: Rounded up portion of supply that is procured by the country and estimate of relative costs in US$.. 2015; 2016; 2017. Number of vaccine doses; #; 131,200; 162,700; 160,700. Number of AD syringes; #; 0; 0; 0. Number of re-constitution syringes; #; 0; 0; 0. Total value to be co-financed by the Country [1]; $; 351,500; 436,000; 430,500.. 2018. Number of vaccine doses; #; 168,700. Number of AD syringes; #; 0. Number of re-constitution syringes; #; 0. Total value to be co-financed by the Country [1]; $; 451,500... Table Annex 1.1 B: Rounded up portion of supply that is procured by GAVI and estimate of relative costs in US$.. 2015; 2016; 2017. Number of vaccine doses; #; 1,624,100; 2,015,300; 1,990,300. Number of AD syringes; #; 0; 0; 0. Number of re-constitution syringes; #; 0; 0; 0. Total value to be co-financed by GAVI; $; 4,348,500; 5,396,000; 5,329,500.. 2018. Number of vaccine doses; #; 2,088,800. Number of AD syringes; #; 0. Number of re-constitution syringes; #; 0. Total value to be co-financed by GAVI; $; 5,593,000......

Table Annex 1.1 C: Summary table for vaccine Rotavirus, 2 -dose schedule. ID. Data from; 2015; 2016; 2017. Number of surviving infants; Table 5.2; #; 1,035,471; 1,063,470; 1,091,841. Number of children to be vaccinated with the first dose; Table 5.2; #; 668,045; 962,721; 1,011,389. Number of children to be vaccinated with the second dose; Table 5.2; #; 621,282; 914,585; 960,820. Immunisation coverage with the second dose; Table 5.2; %; 60.00 %; 86.00 %; 88.00 %. Number of doses per child; Parameter; #; 2; 2; 2. Estimated vaccine wastage factor; Table 5.2; #; 1.05; 1.05; 1.05. Number of doses per vial; Parameter; #; 1; 1; 1. AD syringes required; Parameter; #; No; No; No. Reconstitution syringes required; Parameter; #; No; No; No. Safety boxes required; Parameter; #; No; No; No. g; Vaccine price per dose; Table Annexes 4A; $; 2.55; 2.55; 2.55. cc; Country co-financing per dose; Table 6.4.1; $; 0.2; 0.2; 0.2. ca; AD syringe price per unit; Table Annexes 4A; $; 0.0465; 0.0465; 0.0465. cr; Reconstitution syringe price per unit; Table Annexes 4A; $; 0; 0; 0. cs; Safety box price per unit; Table Annexes 4A; $; 0.58; 0.58; 0.58. fv; Freight cost as % of vaccines value; Table Annexes 4B; %; 5.00 %; 5.00 %; 5.00 %. fd; Freight cost as % of devices value; Parameter; %; 0; 0; 0.. ID; Data from; 2018. Number of surviving infants; Table 5.2; #; 1,120,633. Number of children to be vaccinated with the first dose; Table 5.2; #; 1,061,653. Number of children to be vaccinated with the second dose; Table 5.2; #; 1,008,570. Immunisation coverage with the second dose; Table 5.2; %; 90.00 %. Number of doses per child; Parameter; #; 2. Estimated vaccine wastage factor; Table 5.2; #; 1.05. Number of doses per vial; Parameter; #; 1. AD syringes required; Parameter; #; No. Reconstitution syringes required; Parameter; #; No. Safety boxes required; Parameter; #; No. g; Vaccine price per dose; Table Annexes 4A; $; 2.55. cc; Country co-financing per dose; Table 6.4.1; $; 0.2. ca; AD syringe price per unit; Table Annexes 4A; $; 0.0465. cr; Reconstitution syringe price per unit; Table Annexes 4A; $; 0. cs; Safety box price per unit; Table Annexes 4A; $; 0.58. fv; Freight cost as % of vaccines value; Table Annexes 4B; %; 5.00 %. fd; Freight cost as % of devices value; Parameter; %; 0......

Table Annex 1.1 D: Estimated numbers for Rotavirus, 2 -dose schedule, associated injection safety material and related co-financing budget (page 1). Formula; 2015. Total; Government; GAVI. A; Country co-finance; 7.47 %. B; Number of children to be vaccinated with the first dose; Table 1; 668,045; 49,901; 618,144. C; Number of doses per child; Vaccine parameter (schedule); 2. D; Number of doses needed; B x C; 1,336,090; 99,802; 1,236,288. E; Estimated vaccine wastage factor; Wastage factor table; 1.05. F; Number of doses needed including wastage; D x E; 1,402,895; 104,792; 1,298,103. G; Vaccines buffer stock; (F – F of previous year) * 0.25; 350,724; 26,198; 324,526. I; Total vaccine doses needed; (((F + G) / Vaccine package size) + 1) * Vaccine package size; 1,755,119; 131,102; 1,624,017. J; Number of doses per vial; Vaccine parameter; 1. K; Number of AD syringes (+ 10% wastage) needed; (D + G) x 1.11; 0; 0; 0. L; Reconstitution syringes (+ 10% wastage) needed; I / J * 1.11; 0; 0; 0. N; Cost of vaccines needed; I x g; 4,475,554; 334,309; 4,141,245. O; Cost of AD syringes needed; K x ca; 0; 0; 0. P; Cost of reconstitution syringes needed; L x cr; 0; 0; 0. Q; Cost of safety boxes needed; M x cs; 0; 0; 0. R; Freight cost for vaccines needed; N x fv; 223,778; 16,716; 207,062. S; Freight cost for devices needed; (O+P+Q) x fd; 0; 0; 0. T; Total fund needed; (N+O+P+Q+R+S); 4,699,332; 351,024; 4,348,308. U; Total country co-financing; I 3 cc; 351,024. V; Country co-financing % of GAVI supported proportion; U / T; 7.47 %... Table Annex 1.1 D: Estimated numbers for Rotavirus, 2 -dose schedule, associated injection safety material and related co-financing budget (page 2). Formula; 2016. Total; Government; GAVI. A; Country co-finance; 7.47 %. B; Number of children to be vaccinated with the first dose; Table 1; 962,721; 71,912; 890,809. C; Number of doses per child; Vaccine parameter (schedule); 2. D; Number of doses needed; B x C; 1,925,442; 143,824; 1,781,618. E; Estimated vaccine wastage factor; Wastage factor table; 1.05. F; Number of doses needed including wastage; D x E; 2,021,715; 151,016; 1,870,699. G; Vaccines buffer stock; (F – F of previous year) * 0.25; 154,705; 11,556; 143,149. I; Total vaccine doses needed; (((F + G) / Vaccine package size) + 1) * Vaccine package size; 2,177,920; 162,684; 2,015,236. J; Number of doses per vial; Vaccine parameter; 1. K; Number of AD syringes (+ 10% wastage) needed; (D + G) x 1.11; 0; 0; 0. L; Reconstitution syringes (+ 10% wastage) needed; I / J * 1.11; 0; 0; 0. N; Cost of vaccines needed; I x g; 5,553,696; 414,842; 5,138,854. O; Cost of AD syringes needed; K x ca; 0; 0; 0. P; Cost of reconstitution syringes needed; L x cr; 0; 0; 0. Q; Cost of safety boxes needed; M x cs; 0; 0; 0. R; Freight cost for vaccines needed; N x fv; 277,685; 20,743; 256,942. S; Freight cost for devices needed; (O+P+Q) x fd; 0; 0; 0. T; Total fund needed; (N+O+P+Q+R+S); 5,831,381; 435,584; 5,395,797. U; Total country co-financing; I 3 cc; 435,584. V; Country co-financing % of GAVI supported proportion; U / T; 7.47 %... Table Annex 1.1 D: Estimated numbers for Rotavirus, 2 -dose schedule, associated injection safety material and related co-financing budget (page 3). Formula; 2017. Total; Government; GAVI. A; Country co-finance; 7.47 %. B; Number of children to be vaccinated with the first dose; Table 1; 1,011,389; 75,548; 935,841. C; Number of doses per child; Vaccine parameter (schedule); 2. D; Number of doses needed; B x C; 2,022,778; 151,095; 1,871,683. E; Estimated vaccine wastage factor; Wastage factor table; 1.05. F; Number of doses needed including wastage; D x E; 2,123,917; 158,650; 1,965,267. G; Vaccines buffer stock; (F – F of previous year) * 0.25; 25,551; 1,909; 23,642. I; Total vaccine doses needed; (((F + G) / Vaccine package size) + 1) * Vaccine package size; 2,150,968; 160,670; 1,990,298. J; Number of doses per vial; Vaccine parameter; 1. K; Number of AD syringes (+ 10% wastage) needed; (D + G) x 1.11; 0; 0; 0. L; Reconstitution syringes (+ 10% wastage) needed; I / J * 1.11; 0; 0; 0. N; Cost of vaccines needed; I x g; 5,484,969; 409,709; 5,075,260. O; Cost of AD syringes needed; K x ca; 0; 0; 0. P; Cost of reconstitution syringes needed; L x cr; 0; 0; 0. Q; Cost of safety boxes needed; M x cs; 0; 0; 0. R; Freight cost for vaccines needed; N x fv; 274,249; 20,486; 253,763. S; Freight cost for devices needed; (O+P+Q) x fd; 0; 0; 0. T; Total fund needed; (N+O+P+Q+R+S); 5,759,218; 430,195; 5,329,023. U; Total country co-financing; I 3 cc; 430,194. V; Country co-financing % of GAVI supported proportion; U / T; 7.47 %... Table Annex 1.1 D: Estimated numbers for Rotavirus, 2 -dose schedule, associated injection safety material and related co-financing budget (page 4). Formula; 2018. Total; Government; GAVI. A; Country co-finance; 7.47 %. B; Number of children to be vaccinated with the first dose; Table 1; 1,061,653; 79,302; 982,351. C; Number of doses per child; Vaccine parameter (schedule); 2. D; Number of doses needed; B x C; 2,123,306; 158,604; 1,964,702. E; Estimated vaccine wastage factor; Wastage factor table; 1.05. F; Number of doses needed including wastage; D x E; 2,229,472; 166,535; 2,062,937. G; Vaccines buffer stock; (F – F of previous year) * 0.25; 26,389; 1,972; 24,417. I; Total vaccine doses needed; (((F + G) / Vaccine package size) + 1) * Vaccine package size; 2,257,361; 168,618; 2,088,743. J; Number of doses per vial; Vaccine parameter; 1. K; Number of AD syringes (+ 10% wastage) needed; (D + G) x 1.11; 0; 0; 0. L; Reconstitution syringes (+ 10% wastage) needed; I / J * 1.11; 0; 0; 0. N; Cost of vaccines needed; I x g; 5,756,271; 429,975; 5,326,296. O; Cost of AD syringes needed; K x ca; 0; 0; 0. P; Cost of reconstitution syringes needed; L x cr; 0; 0; 0. Q; Cost of safety boxes needed; M x cs; 0; 0; 0. R; Freight cost for vaccines needed; N x fv; 287,814; 21,499; 266,315. S; Freight cost for devices needed; (O+P+Q) x fd; 0; 0; 0. T; Total fund needed; (N+O+P+Q+R+S); 6,044,085; 451,473; 5,592,612. U; Total country co-financing; I 3 cc; 451,473. V; Country co-financing % of GAVI supported proportion; U / T; 7.47 %...... Annex 1.2 - NVS Routine Support (Measles second dose, 10 dose(s) per vial, LYOPHILISED). Table Annex 1.2 A: Rounded up portion of supply that is procured by the country and estimate of relative costs in US$.. 2015; 2016; 2017. Number of vaccine doses; #; 0; 0; 0. Number of AD syringes; #; 0; 0; 0. Number of re-constitution syringes; #; 0; 0; 0. Number of safety boxes; #; 0; 0; 0. Total value to be co-financed by the Country [1]; $; 0; 0; 0.. 2018. Number of vaccine doses; #; 0. Number of AD syringes; #; 0. Number of re-constitution syringes; #; 0. Number of safety boxes; #; 0. Total value to be co-financed by the Country [1]; $; 0... Table Annex 1.2 B: Rounded up portion of supply that is procured by GAVI and estimate of relative costs in US$.. 2015; 2016; 2017. Number of vaccine doses; #; 1,751,000; 1,529,000; 1,638,300. Number of AD syringes; #; 1,319,700; 1,027,600; 1,100,900. Number of re-constitution syringes; #; 194,400; 169,800; 181,900. Number of safety boxes; #; 16,825; 13,300; 14,250. Total value to be co-financed by GAVI; $; 677,000; 629,500; 674,500.. 2018. Number of vaccine doses; #; 1,708,600. Number of AD syringes; #; 1,144,300. Number of re-constitution syringes; #; 189,700. Number of safety boxes; #; 14,825. Total value to be co-financed by GAVI; $; 703,000......

Table Annex 1.2 C: Summary table for vaccine Measles second dose, 10 dose(s) per vial, LYOPHILISED. ID. Data from; 2015; 2016; 2017. Number of surviving infants; Table 5.2; #; 1,035,471; 1,063,470; 1,091,841. Number of children to be vaccinated with the first dose; Table 5.2; #; 931,923; 978,393; 1,026,330. Number of children to be vaccinated with the second dose; Table 5.2; #; 838,731; 900,121; 964,751. Immunisation coverage with the second dose; Table 5.2; %; 81.00 %; 85.00 %; 88.00 %. Number of doses per child; Parameter; #; 1; 1; 1. Estimated vaccine wastage factor; Table 5.2; #; 1.67; 1.67; 1.67. Number of doses per vial; Parameter; #; 10; 10; 10. AD syringes required; Parameter; #; Yes; Yes; Yes. Reconstitution syringes required; Parameter; #; Yes; Yes; Yes. Safety boxes required; Parameter; #; Yes; Yes; Yes. g; Vaccine price per dose; Table Annexes 4A; $; 0.296; 0.322; 0.322. cc; Country co-financing per dose; Table 6.4.1; $; 0; 0; 0. ca; AD syringe price per unit; Table Annexes 4A; $; 0.0465; 0.0465; 0.0465. cr; Reconstitution syringe price per unit; Table Annexes 4A; $; 0.037; 0.037; 0.037. cs; Safety box price per unit; Table Annexes 4A; $; 0.58; 0.58; 0.58. fv; Freight cost as % of vaccines value; Table Annexes 4B; %; 14.00 %; 14.00 %; 14.00 %. fd; Freight cost as % of devices value; Parameter; %; 10.00 %; 10.00 %; 10.00 %.. ID; Data from; 2018. Number of surviving infants; Table 5.2; #; 1,120,633. Number of children to be vaccinated with the first dose; Table 5.2; #; 1,064,602. Number of children to be vaccinated with the second dose; Table 5.2; #; 1,011,372. Immunisation coverage with the second dose; Table 5.2; %; 90.00 %. Number of doses per child; Parameter; #; 1. Estimated vaccine wastage factor; Table 5.2; #; 1.67. Number of doses per vial; Parameter; #; 10. AD syringes required; Parameter; #; Yes. Reconstitution syringes required; Parameter; #; Yes. Safety boxes required; Parameter; #; Yes. g; Vaccine price per dose; Table Annexes 4A; $; 0.322. cc; Country co-financing per dose; Table 6.4.1; $; 0. ca; AD syringe price per unit; Table Annexes 4A; $; 0.0465. cr; Reconstitution syringe price per unit; Table Annexes 4A; $; 0.037. cs; Safety box price per unit; Table Annexes 4A; $; 0.58. fv; Freight cost as % of vaccines value; Table Annexes 4B; %; 14.00 %. fd; Freight cost as % of devices value; Parameter; %; 10.00 %......

Table Annex 1.2 D: Estimated numbers for Measles second dose, 10 dose(s) per vial, LYOPHILISED, associated injection safety material and related co-financing budget (page 1). Formula; 2015. Total; Government; GAVI. A; Country co-finance; 0.00 %. B; Number of children to be vaccinated with the first dose; Table 1; 838,731; 0; 838,731. C; Number of doses per child; Vaccine parameter (schedule); 1. D; Number of doses needed; B x C; 838,731; 0; 838,731. E; Estimated vaccine wastage factor; Wastage factor table; 1.67. F; Number of doses needed including wastage; D x E; 1,400,681; 0; 1,400,681. G; Vaccines buffer stock; (F – F of previous year) * 0.25; 350,171; 0; 350,171. I; Total vaccine doses needed; (((F + G) / Vaccine package size) + 1) * Vaccine package size; 1,750,952; 0; 1,750,952. J; Number of doses per vial; Vaccine parameter; 10. K; Number of AD syringes (+ 10% wastage) needed; (D + G) x 1.11; 1,319,682; 0; 1,319,682. L; Reconstitution syringes (+ 10% wastage) needed; I / J * 1.11; 194,356; 0; 194,356. M; Total of safety boxes (+ 10% of extra need) needed; (K + L) /100 * 1.11; 16,806; 0; 16,806. N; Cost of vaccines needed; I x g; 518,282; 0; 518,282. O; Cost of AD syringes needed; K x ca; 61,366; 0; 61,366. P; Cost of reconstitution syringes needed; L x cr; 7,192; 0; 7,192. Q; Cost of safety boxes needed; M x cs; 9,748; 0; 9,748. R; Freight cost for vaccines needed; N x fv; 72,560; 0; 72,560. S; Freight cost for devices needed; (O+P+Q) x fd; 7,831; 0; 7,831. T; Total fund needed; (N+O+P+Q+R+S); 676,979; 0; 676,979. U; Total country co-financing; I 3 cc; 0. V; Country co-financing % of GAVI supported proportion; U / T; 0.00 %... Table Annex 1.2 D: Estimated numbers for Measles second dose, 10 dose(s) per vial, LYOPHILISED, associated injection safety material and related co-financing budget (page 2). Formula; 2016. Total; Government; GAVI. A; Country co-finance; 0.00 %. B; Number of children to be vaccinated with the first dose; Table 1; 900,121; 0; 900,121. C; Number of doses per child; Vaccine parameter (schedule); 1. D; Number of doses needed; B x C; 900,121; 0; 900,121. E; Estimated vaccine wastage factor; Wastage factor table; 1.67. F; Number of doses needed including wastage; D x E; 1,503,203; 0; 1,503,203. G; Vaccines buffer stock; (F – F of previous year) * 0.25; 25,631; 0; 25,631. I; Total vaccine doses needed; (((F + G) / Vaccine package size) + 1) * Vaccine package size; 1,528,934; 0; 1,528,934. J; Number of doses per vial; Vaccine parameter; 10. K; Number of AD syringes (+ 10% wastage) needed; (D + G) x 1.11; 1,027,585; 0; 1,027,585. L; Reconstitution syringes (+ 10% wastage) needed; I / J * 1.11; 169,712; 0; 169,712. M; Total of safety boxes (+ 10% of extra need) needed; (K + L) /100 * 1.11; 13,290; 0; 13,290. N; Cost of vaccines needed; I x g; 492,317; 0; 492,317. O; Cost of AD syringes needed; K x ca; 47,783; 0; 47,783. P; Cost of reconstitution syringes needed; L x cr; 6,280; 0; 6,280. Q; Cost of safety boxes needed; M x cs; 7,709; 0; 7,709. R; Freight cost for vaccines needed; N x fv; 68,925; 0; 68,925. S; Freight cost for devices needed; (O+P+Q) x fd; 6,178; 0; 6,178. T; Total fund needed; (N+O+P+Q+R+S); 629,192; 0; 629,192. U; Total country co-financing; I 3 cc; 0. V; Country co-financing % of GAVI supported proportion; U / T; 0.00 %... Table Annex 1.2 D: Estimated numbers for Measles second dose, 10 dose(s) per vial, LYOPHILISED, associated injection safety material and related co-financing budget (page 3). Formula; 2017. Total; Government; GAVI. A; Country co-finance; 0.00 %. B; Number of children to be vaccinated with the first dose; Table 1; 964,751; 0; 964,751. C; Number of doses per child; Vaccine parameter (schedule); 1. D; Number of doses needed; B x C; 964,751; 0; 964,751. E; Estimated vaccine wastage factor; Wastage factor table; 1.67. F; Number of doses needed including wastage; D x E; 1,611,135; 0; 1,611,135. G; Vaccines buffer stock; (F – F of previous year) * 0.25; 26,983; 0; 26,983. I; Total vaccine doses needed; (((F + G) / Vaccine package size) + 1) * Vaccine package size; 1,638,218; 0; 1,638,218. J; Number of doses per vial; Vaccine parameter; 10. K; Number of AD syringes (+ 10% wastage) needed; (D + G) x 1.11; 1,100,825; 0; 1,100,825. L; Reconstitution syringes (+ 10% wastage) needed; I / J * 1.11; 181,843; 0; 181,843. M; Total of safety boxes (+ 10% of extra need) needed; (K + L) /100 * 1.11; 14,238; 0; 14,238. N; Cost of vaccines needed; I x g; 527,507; 0; 527,507. O; Cost of AD syringes needed; K x ca; 51,189; 0; 51,189. P; Cost of reconstitution syringes needed; L x cr; 6,729; 0; 6,729. Q; Cost of safety boxes needed; M x cs; 8,259; 0; 8,259. R; Freight cost for vaccines needed; N x fv; 73,851; 0; 73,851. S; Freight cost for devices needed; (O+P+Q) x fd; 6,618; 0; 6,618. T; Total fund needed; (N+O+P+Q+R+S); 674,153; 0; 674,153. U; Total country co-financing; I 3 cc; 0. V; Country co-financing % of GAVI supported proportion; U / T; 0.00 %... Table Annex 1.2 D: Estimated numbers for Measles second dose, 10 dose(s) per vial, LYOPHILISED, associated injection safety material and related co-financing budget (page 4). Formula; 2018. Total; Government; GAVI. A; Country co-finance; 0.00 %. B; Number of children to be vaccinated with the first dose; Table 1; 1,011,372; 0; 1,011,372. C; Number of doses per child; Vaccine parameter (schedule); 1. D; Number of doses needed; B x C; 1,011,372; 0; 1,011,372. E; Estimated vaccine wastage factor; Wastage factor table; 1.67. F; Number of doses needed including wastage; D x E; 1,688,992; 0; 1,688,992. G; Vaccines buffer stock; (F – F of previous year) * 0.25; 19,465; 0; 19,465. I; Total vaccine doses needed; (((F + G) / Vaccine package size) + 1) * Vaccine package size; 1,708,557; 0; 1,708,557. J; Number of doses per vial; Vaccine parameter; 10. K; Number of AD syringes (+ 10% wastage) needed; (D + G) x 1.11; 1,144,230; 0; 1,144,230. L; Reconstitution syringes (+ 10% wastage) needed; I / J * 1.11; 189,650; 0; 189,650. M; Total of safety boxes (+ 10% of extra need) needed; (K + L) /100 * 1.11; 14,807; 0; 14,807. N; Cost of vaccines needed; I x g; 550,156; 0; 550,156. O; Cost of AD syringes needed; K x ca; 53,207; 0; 53,207. P; Cost of reconstitution syringes needed; L x cr; 7,018; 0; 7,018. Q; Cost of safety boxes needed; M x cs; 8,589; 0; 8,589. R; Freight cost for vaccines needed; N x fv; 77,022; 0; 77,022. S; Freight cost for devices needed; (O+P+Q) x fd; 6,882; 0; 6,882. T; Total fund needed; (N+O+P+Q+R+S); 702,874; 0; 702,874. U; Total country co-financing; I 3 cc; 0. V; Country co-financing % of GAVI supported proportion; U / T; 0.00 %........

Annex 2 - NVS Routine – Preferred Second Presentation.. No NVS Routine – Preferred Second Presentation requested this year...

Annex 3 - NVS Preventive campaign(s).. No NVS Prevention Campaign Support this year...

| Annex 4.. Table Annex 4A: Commodities Cost.. Vaccine; Presentation; 2015; 2016. DTP-HepB-Hib, 1 dose(s) per vial, LIQUID; 1; 1.986; 1.927. DTP-HepB-Hib, 10 dose(s) per vial, LIQUID; 10; 1.986; 1.927. DTP-HepB-Hib, 2 dose(s) per vial, LYOPHILISED; 2; 1.986; 1.927. HPV bivalent, 2 dose(s) per vial, LIQUID; 2; 4.600; 4.600. HPV quadrivalent, 1 dose(s) per vial, LIQUID; 1; 4.500; 4.500. Measles second dose, 10 dose(s) per vial, LYOPHILISED; 10; 0.296; 0.322. Meningococcal type A, 10 dose(s) per vial, LYOPHILISED; 10; 0.582; 0.611. MR, 10 dose(s) per vial, LYOPHILISED; 10; 0.565; 0.591. Pneumococcal (PCV10), 2 dose(s) per vial, LIQUID; 2; 3.500; 3.500. Pneumococcal (PCV13), 1 dose(s) per vial, LIQUID; 1; 3.500; 3.500. Rotavirus, 2-dose schedule; 1; 2.550; 2.550. Rotavirus, 3-dose schedule; 1; 3.500; 3.500. Yellow Fever, 10 dose(s) per vial, LYOPHILISED; 10; 0.923; 0.923. Yellow Fever, 5 dose(s) per vial, LYOPHILISED; 5; 0.923; 0.923.. Supply; Form; 2015; 2016. AD-SYRINGE; SYRINGE; 0.047; 0.047. RECONSTIT-SYRINGE-PENTAVAL; SYRINGE; 0.037; 0.037. RECONSTIT-SYRINGE-YF; SYRINGE; 0.037; 0.037. SAFETY-BOX; SAFETYBOX; 0.580; 0.580.. Note: WAP - weighted average price (to be used for any presentation: For DTP-HepB-Hib, it applies to 1 dose liquid, 2 dose lyophilised and 10 dose liquid. For Yellow Fever, it applies to 5 dose lyophilised and 10 dose lyophilised).. Table Annex 4B: Freight cost as percentage of value.. Vaccine Antigen; Vaccine Type; No Threshold; 500,000$. <=; >. DTP-HepB-Hib; HEPBHIB; 25.50 %; 6.40 %. HPV bivalent; HPV; 3.50 %. HPV quadrivalent; HPV; 3.50 %. Measles second dose; MEASLES; 14.00 %. Meningococcal type A; MENINACONJUGATE; 10.20 %. MR; MR; 13.20 %. Pneumococcal (PCV10); PNEUMO; 3.00 %. Pneumococcal (PCV13); PNEUMO; 6.00 %. Rotavirus; ROTA; 5.00 %. Yellow Fever; YF; 7.80 %.. Table Annex 4C: Low - Minimum country's co-payment per dose of co-financed vaccine... Vaccine; 2015; 2016; 2017. Rotavirus, 1 dose(s) per vial, ORAL; 0.2; 0.2; 0.2. Measles second dose, 10 dose(s) per vial, LYOPHILISED; 0; 0; 0.. Vaccine; 2018. Rotavirus, 1 dose(s) per vial, ORAL; 0.2. Measles second dose, 10 dose(s) per vial, LYOPHILISED; 0... |  |
| --- | --- |

Table Annex 4D: Wastage rates and factors.. The following table shows the wastage rates for routine and campaign vaccines, set for 2015... Vaccine; dose(s) per vial; Maximum Vaccine wastage rate*; Benchmark Wastage Rate**. DTP-HepB-Hib, 1 dose(s) per vial, LIQUID; 1; 5 %. DTP-HepB-Hib, 10 dose(s) per vial, LIQUID; 10; 25 %; 15 %. DTP-HepB-Hib, 2 dose(s) per vial, LYOPHILISED; 2; 10 %. HPV bivalent, 2 dose(s) per vial, LIQUID; 2; 10 %. HPV quadrivalent, 1 dose(s) per vial, LIQUID; 1; 5 %. Measles second dose, 10 dose(s) per vial, LYOPHILISED; 10; 40 %. Meningococcal type A, 10 dose(s) per vial, LYOPHILISED; 10; 10 %. MR, 10 dose(s) per vial, LYOPHILISED; 10; 25 %. Pneumococcal (PCV10), 2 dose(s) per vial, LIQUID; 2; 10 %. Pneumococcal (PCV13), 1 dose(s) per vial, LIQUID; 1; 5 %. Rotavirus, 2-dose schedule; 1; 5 %. Rotavirus, 3-dose schedule; 1; 5 %. Yellow Fever, 10 dose(s) per vial, LYOPHILISED; 10; 40 %. Yellow Fever, 5 dose(s) per vial, LYOPHILISED; 5; 10 %.. Comments:.. * Source - WHO indicative wastage rates.. ** Source - Country APRs and studies, approved by WHO, UNICEF, and the GAVI Secretariat.. Note: HPV demonstration project wastage rates are the same as the vaccine.. Table Annex 4E: Vaccine maximum packed volumes.. Kindly note that this table is for reference purposes only and includes GAVI- and non GAVI-supported vaccines... Vaccine product; Designation; Vaccine formulation; Admin route; No. Of doses in the schedule; Presentation (doses/vial, prefilled); Packed volume vaccine (cm3/dose); Packed volume diluents (cm3/dose). BCG; BCG; lyophilized; ID; 1; 20; 1.2; 0.7. Diphtheria-Tetanus-Pertussis; DTP; liquid; IM; 3; 20; 2.5. Diphtheria-Tetanus-Pertussis; DTP; liquid; IM; 3; 10; 3. Diphtheria-Tetanus; DT; liquid; IM; 3; 10; 3. Tetanus-Diphtheria; Td; liquid; IM; 2; 10; 3. Tetanus Toxoid; TT; liquid; IM; 2; 10; 3. Tetanus Toxoid; TT; liquid; IM; 2; 20; 2.5. Tetanus Toxoid UniJect; TT; liquid; IM; 2; Uniject; 12. Measles; Measles; lyophilized; SC; 1; 1; 26.1; 20. Measles; Measles; lyophilized; SC; 1; 2; 13.1; 13.1. Measles; Measles; lyophilized; SC; 1; 5; 5.2; 7. Measles; Measles; lyophilized; SC; 1; 10; 3.5; 4. Measles-Rubella freeze dried; MR; lyophilized; SC; 1; 1; 26.1; 26.1. Measles-Rubella freeze dried; MR; lyophilized; SC; 1; 2; 13.1; 13.1. Measles-Rubella freeze dried; MR; lyophilized; SC; 1; 5; 5.2; 7. Measles-Rubella freeze dried; MR; lyophilized; SC; 1; 10; 2.5; 4. Measles-Mumps-Rubella freeze dried; MMR; lyophilized; SC; 1; 1; 26.1; 26.1. Measles-Mumps-Rubella freeze dried; MMR; lyophilized; SC; 1; 2; 13.1; 13.1. Measles-Mumps-Rubella freeze dried; MMR; lyophilized; SC; 1; 5; 5.2; 7. Measles-Mumps-Rubella freeze dried; MMR; lyophilized; SC; 1; 10; 3; 4. Polio; OPV; liquid; Oral; 4; 10; 2. Polio; OPV; liquid; Oral; 4; 20; 1. Yellow fever; YF; lyophilized; SC; 1; 5; 6.5; 7. Yellow fever; YF; lyophilized; SC; 1; 10; 2.5; 3. Yellow fever; YF; lyophilized; SC; 1; 20; 1.5; 2. Yellow fever; YF; lyophilized; SC; 1; 50; 0.7; 1. DTP-HepB combined; DTP-HepB; liquid; IM; 3; 1; 9.7. DTP-HepB combined; DTP-HepB; liquid; IM; 3; 2; 6. DTP-HepB combined; DTP-HepB; liquid; IM; 3; 10; 3. Hepatitis B; HepB; liquid; IM; 3; 1; 18. Hepatitis B; HepB; liquid; IM; 3; 2; 13. Hepatitis B; HepB; liquid; IM; 3; 6; 4.5. Hepatitis B; HepB; liquid; IM; 3; 10; 4. Hepatitis B UniJect; HepB; liquid; IM; 3; Uniject; 12. Hib liquid; Hib_liq; liquid; IM; 3; 1; 15. Hib liquid; Hib_liq; liquid; IM; 3; 10; 2.5. Hib freeze-dried; Hib_lyo; lyophilized; IM; 3; 1; 13; 35. Hib freeze-dried; Hib_lyo; lyophilized; IM; 3; 2; 6. Hib freeze-dried; Hib_lyo; lyophilized; IM; 3; 10; 2.5; 3. DTP liquid + Hib freeze-dried; DTP+Hib; liquid+lyop.; IM; 3; 1; 45. DTP-Hib combined liquid; DTP+Hib; liquid+lyop.; IM; 3; 10; 12. DTP-Hib combined liquid; DTP-Hib; liquid; IM; 3; 1; 32.3. DTP-HepB liquid + Hib freeze-dried; DTP-Hib; liquid; IM; 3; 10; 2.5. DTP-HepB liquid + Hib freeze-dried; DTP-HepB+Hib; liquid+lyop.; IM; 3; 1; 22. DTP-HepB-Hib liquid; DTP-HepB+Hib; liquid+lyop.; IM; 3; 2; 11. DTP-HepB-Hib liquid; DTP-HepB-Hib; liquid; IM; 3; 10; 4.4. DTP-HepB-Hib liquid; DTP-HepB-Hib; liquid; IM; 3; 2; 13.1. DTP-HepB-Hib liquid; DTP-HepB-Hib; liquid; IM; 3; 1; 19.2. Meningitis A/C; MV_A/C; lyophilized; SC; 1; 10; 2.5; 4. Meningitis A/C; MV_A/C; lyophilized; SC; 1; 50; 1.5; 3. Meningococcal A/C/W/; MV_A/C/W; lyophilized; SC; 1; 50; 1.5; 3. Meningococcal A/C/W/Y; MV_A/C/W/Y; lyophilized; SC; 1; 10; 2.5; 4. Meningitis W135; MV_W135; lyophilized; SC; 1; 10; 2.5; 4. Meningitis A conjugate; Men_A; lyophilized; SC; 2; 10; 2.6; 4. Japanese Encephalitis; JE_lyo; lyophilized; SC; 3; 10; 15. Japanese Encephalitis; JE_lyo; lyophilized; SC; 3; 10; 8.1; 8.1. Japanese Encephalitis; JE_lyo; lyophilized; SC; 3; 5; 2.5; 2.9. Japanese Encephalitis; JE_lyo; lyophilized; SC; 3; 1; 12.6; 11.5. Japanese Encephalitis; JE_liq; liquid; SC; 3; 10; 3.4. Rota vaccine; Rota_lyo; lyophilized; Oral; 2; 1; 156. Rota vaccine; Rota_liq; liquid; Oral; 2; 1; 17.1. Rota vaccine; Rota_liq; liquid; Oral; 3; 1; 45.9. Pneumo. conjugate vaccine 7-valent; PCV-7; liquid; IM; 3; PFS; 55.9. Pneumo. conjugate vaccine 7-valent; PCV-7; liquid; IM; 3; 1; 21. Pneumo. conjugate vaccine 10-valent; PCV-10; liquid; IM; 3; 1; 11.5. Pneumo. conjugate vaccine 10-valent; PCV-10; liquid; IM; 3; 2; 4.8. Pneumo. conjugate vaccine 13-valent; PCV-13; liquid; IM; 3; 1; 12. Polio inactivated; IPV; liquid; IM; 3; PFS; 107.4. Polio inactivated; IPV; liquid; IM; 3; 10; 2.5. Polio inactivated; IPV; liquid; IM; 3; 1; 15.7. Human Papilomavirus vaccine; HPV; liquid; IM; 3; 1; 15. Human Papilomavirus vaccine; HPV; liquid; IM; 3; 2; 5.7. Monovalent OPV-1; mOPV1; liquid; Oral; 20; 1.5. Monovalent OPV-3; mOPV3; liquid; Oral; 20; 1.5...

12. Banking Form.. In accordance with the decision on financial support made by the GAVI Alliance, the Government of Mozambique hereby requests that a payment be made via electronic bank transfer as detailed below:. Name of Institution (Account Holder):. Address:. City Country:. Telephone no.:; Fax no.:. Currency of the bank account:. For credit to:. Bank account's title:. Bank account no.:. Bank's name:.. Is the bank account exclusively to be used by this program?.. By who is the account audited?.. Signature of Government's authorizing official.. Seal. Name:. Title:. Signature:. Date:.. FINANCIAL INSTITUTION. Bank Name:. Branch Name:. Address:. City Country:. Swift Code:. Sort Code:. ABA No.:. Telephone No.:. FAX No.:.; CORRESPONDENT BANK. (In the United States).. I certify that the account No is held by at this banking institution. The account is to be signed jointly by at least (number of signatories) of the following authorized signatories:. 1; Name:. Title:. 2; Name:. Title:. 3; Name:. Title:.. Name of bank's authorizing official. Signature:. Date:. Seal:...