UNION OF THE COMOROS

Unity-Solidarity-Development

-----------

Ministry of Health, Solidarity

Social Cohesion and

Gender Promotion

------------

[TEXT IN ARABIC]

UNION OF THE COMOROS HEALTH SYSTEM STRENGTHENING

Submission to the GAVI Global Alliance for vaccines and immunization

funding

CLARIFICATIONS REQUESTED BY THE INDEPENDENT REVIEW COMMITTEE

11 October 2012

- Provide an action plan with all the objectives and activities better organized and more logical.

The activities have been reorganized in the action plan found in appendix 5.

- Provide more details on the link between the proposed activities and other HSS activities to indicate their added value and equally to ensure the execution of these specific activities.

As announced in point 2.3 of the proposal, some activities supported by other partners are being executed for the HSS. The GAVI support shall complete these activities. Therefore:

- In the rehabilitation and equipment of health centers area, Qatar, Japan and PASCO (FDA), China and the Islamic Development Bank support a vast programme of rehabilitation and re-equipment of hospitals and health centers. Following the new reorganization of health districts into poles, a family health center per pole is designated for health care training where activities related to the prevention and promotion of health for the mother, child and family are implemented. The GAVI aid shall complete the rehabilitation and equipping of 8 DHCs and 17 health posts out of the 29 HP (A.2.1.1) in a bid to ease the implementation of activities on prevention and promotion of health for the mother, child and family including immunization. Among the 17 selected health posts, 3 are established as Family Health Centers. Moreover, GAVI shall put a roof over 8 cold rooms donated by the Japanese Cooperation and reorganize the pharmacy warehouses of 8 district health centers (A 3.1.1) for a better conservation of vaccines and medicines. Besides, GAVI shall provide 8 motorcycles to targeted DHCs in addition to the grants already given to other DHCs by the Global Fund and other partners.

- In the coordination of activities area, GAVI aid shall contribute to the execution of the work plans and the monitoring of activities in the targeted zones in addition to the assistance from WHO and UNICEF in the area (A 1.1.1 and A1.1.2). One of the weaknesses identified in the analysis of the situation is a low level of coordination of activities in the poles despite the establishment of the structures. GAVI support shall help reinforce coordination through coordination meetings and the sharing of information (A 1.2.1) for a better monitoring of interventions and a reorientation of actions where necessary. It shall help equip the coordination structures with office supplies and IT consumables. These coordination meetings shall improve the implication of all the actors in the health field particularly the private sector and the civil company in HSS activities.

- The medical information system, the PASCO (FDA) project, UNFPA, WHO, UNICEF and the Global Fund helped renew the IT facilities and establish a normative framework for the medical information system (MIS). GAVI shall contribute in establishing an internet connection in the DHC of the targeted poles to reinforce the exchange of information between the regions (already connected), the districts and the central level (A 4.2.2). As such, swiftness and completeness in the transmission of activities reports shall be improved. Aid shall also be provided in the supply of data collection media in continuation of the support from the Ministry of Health’s traditional partners. GAVI shall help realize the quality control of collected data in a bid to have reliable data for decision making (A 4.1.3).

- Population sensitization and mobilization activities poorly realized by NGOs shall be reinforced with the help of GAVI in support of communication and sensitization, especially with the donation of flat-screen TVs, DVD players and sound systems (A 2.3.2), which shall be made available to these NGOs by DHCs for sensitization activities. In addition, the central level shall be equipped with production material for sensitization media (A 2.3.4).

- Provide a better precision of some budgeted activities (as identified in the section “weak points”).

The precisions provided in the attached work plan in the appendix. For the above raised questions, we offer the following precisions:

- 20,266 USD is planned for the purchase of communication equipment for the mobilization and sensitization of the community:

It consists of furnishing 8 DHCs with communication material for community sensitization. The items designated for these 8 DHCs are:

- Flat-screen TV

- DVD player

- Complete sound system with a professional wireless microphone kit.

Moreover, costs were revised after consulting with professionals in the field. The new total amount allocated to the activity is 34,844 USD.

- 468,104 USD for the renovation of health centers in the targeted zones. What is needed?

This amount shall be used to rehabilitate and re-equip, in terms of small medical equipment, 17 out of the 29 health posts situated in the 8 targeted districts. Among the 17 HP, 3 are built as Family Health Centers. These actions add to the interventions of other partners namely PASCO (AFD), Japan and Qatar. The new total amount allocated to the activity is 538,320 USD.

- 98,601 USD is requested for advanced strategy activities. What are they?

This amount is planned for the supply of staff fuel and lunch expenses for the realization of the advanced strategy immunization activities. 8 outings are scheduled per trimester and per DHC as from the second year as soon as motorcycles are purchased.

- 407,792 USD is requested for the purchase of supervision vehicles. How many vehicles are requested and what is the unit cost?

Concerning the purchase of vehicles, 5 vehicles are programmed summing up to 28,489 USD per vehicle, a total amount of 142,443 USD instead of 407,792 USD mentioned following an error on the calculation sheet. This amount covers the purchase and supply service charges (10%) as well as transit charges.

- Clarify the budget in the questions identified in section 8.

Some clarifications are contained in the work plan and budget in the appendix.

The cost of mid-term evaluation (act 1.2.4), the final evaluation (act 1.2.5), the activity workshop 3.2.1, the cost of the activity workshop 4.1.1, the evaluation cost of quality data (act 4.1.2) and the cost of operational research (act 4.3.1) are all the same. Does it imply that the figures are all estimated and based on actual costs?

- The mid-evaluation (act 1.2.4) and the final evaluation (act 1.2.5) shall be conducted by an external team with the support of international consultants. These different evaluations were planned for a length of two weeks each. The respective costs of these activities, being 12,696 USD and 13,686 USD are different because of the rate of inflation estimated at 7.80%2. These evaluations are on all HSS activities and as such, enjoy the contribution of several partners. The GAVI aid is just part of the resources necessary for the implementation of these activities.

- Concerning the quality evaluation of data (act 4.1.2), it shall be executed by a team of national experts, the costs were revised accordingly.

- Concerning the cost of operational research, it is a fixed grant in addition to the contributions from other partners (WHO, UNICEF, UNFPA).

- Ensure compliance between the narrative and the logical framework, as explained in the section “weak points”.

Several underlined weak points were dealt with in the previous questions. Corrections were effected on minor incoherencies in the activities.

- A.3.2.2: Read: “Grant the DHCs and HPs in targeted zones essential generic medicines” in the logical framework instead of “grating the HPs of zones ...”.

- A.4.1.1: Read: “Organize a training session on the analysis and use of data for those in charge of the DHCs and HPs medical information” in the logical framework instead of “Organize two training sessions … of DHCs and HPs”.

- A.4.2.2: Read in the logical framework, “Grant the DHCs in targeted zones with an internet connection so as to facilitate the transmission of data” instead of “Grant the DHCs and EPINC… for data transmission”.

- Considering the capital expenditure on transport and equipment, indicate how these areas shall be maintained throughout the period especially the post funding program.

The Union of the Comoros shall benefit from a debt remission in December 2012, at the HIPC initiative completion point. The Ministry of Health and the Ministry of National Education shall enjoy the returns from this debt remission and have additional resources to take over the GAVI funding in a bid to maintain the assets so as to ensure the continuity of GAVI-supported activities. The resources absorption plan from the debt remission, currently being prepared, takes this question into account. Moreover, the Union of the Comoros is supported by several partners (see attached table) who can continue the GAVI-supported activities in the post funding program. It is worth noting that, beyond GAVI’s funding, the Comorian government has launched an additional resource mobilization process including PASCO2 (FDA), RSIE2 (IOC) that could contribute to the maintaining and functioning of equipment and means of transportation.

Table of partners involved in the Union of the Comoros health system strengthening.

| Sources of funding | Allocation per annum in USD |  |  |  |
| --- | --- | --- | --- | --- |
|  | Year 1 of implementation | Year 2 of implementation | Year 3 of implementation | TOTAL FUNDS |
|  | 2012 | 2013 | 2014 |  |
| GAVI | 596 605 | 601 771 | 600 889 | 1 799 265 |
| Government | 440 000 | 440 000 | 440 000 | 1 320 000 |
| WHO | 128 550 | 128 550 | 128 550 | 385 650 |
| UNICEF | 15 000 | 15 000 | 15 000 | 45 000 |
| UNFPA | 550 000 | 550 000 | 550 000 | 1 650 000 |
| PASCO | 2 080 179 | 351 000 | - | 2 431 179 |
| FM | 31536 | 37 243 | 37 898 | 106 677 |
| IDB | 447 000 | 438 000 | - | 885 000 |
| Qatar funding | 6 536 000 | 5 553 000 | 4 569 480 | 16 658 480 |
| Japanese cooperation | 873 000 | - | - | 873 000 |
| TOTAL FUNDING | 11 697 870 | 8 114 564 | 6 341 817 | 26 154 251 |

7.    Other clarifications

7.1.    Roles of the ICC and NHC

In the Union of the Comoros, the Health Sector Coordination Committee (HSCC) is called the National Health Committee (NHC). They gather when summoned by their president for an ordinary session once a year and for an extraordinary session when the need arises. Extraordinary sessions are held based on strategic questions requiring political engagements particularly the national coordination of activities related to health development, mobilization of resources, the adoption of policies and strategic plans in the health sector, etc… It should be noted that before the creation of NHC in 2007, the Inter-agency Coordination Committee (ICC) acted in the roles of the NHC concerning activities of coordination, monitoring and specific EPI evaluation.

- The main roles and missions of the National Health Committee (NHC) are:

- Define the national orientations on medical development;

- Ensure the monitoring of the implementation of the National Health Policy;

- Ensure the effective implication of all stakeholders in the process of elaboration and implementation of policies, plans and medical development programmes;

- Take all the decisions that tend to improve on the state of the population’s health.

- The main roles and missions of the Inter-agency coordination committee (ICC):

- Ease the coordination of EPI activities;

- Mobilize national authorities for a greater implication with regard to immunization;

- Ensure the mobilization of the human and financial resources necessary for the implementation of the Expanded Programme on immunization;

- Coordinate the strategic and operational planning;

- Ensure advocacy at national and international level;

- Ensure the monitoring of the implementation of EPI activities;

- Evaluate EPI activities.

7.2.    Civil society and NGO

Concerning the civil society and NGOs in immunization activities, there are two active actors in the fixed and advanced immunization activities. They are: (i) CARITAS in fixed and advanced strategy and (ii) ASCOBIE in fixed strategy.

Achievement framework

Impact indicator

| Impact indicator | Basic data |  |  | Targets |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Value | Year | Source | 2012 | Expiration of report | 2013 | Expiration of report | 2014 | Expiration of report |
| National vaccine coverage by DTP-Hep B3 | 86,7 | 2011 | EPINC annual report | 90 | 14 Feb 2013 | 91 | 14 Feb 2014 | 93 | 14 Feb 2015 |
| Number of districts reaching ≥ 80% of coverage by DTP-Hep B3 | 9 | 2011 | Annual report | 12 | 14 Feb 2013 | 14 | 14 Feb 2014 | 17 | 14 Feb 2015 |
| Child mortality rate (children less than 5 years) | 49 | 2007 | 2009 MDG report |  |  |  |  | 40 |  |
| Mortality rate of children less than 5 years (per thousand) | 69 | 2007 | 2009 MDG report |  |  |  |  | 50 |  |
| Number of districts showing an abandonment rate of DTP higher than 10% | 6 | 2011 | NCPI annual report | 5 | 14 Feb 2013 | 3 | 14 Feb 2014 | 1 | 14 Feb 2015 |
| Vaccine coverage of pregnant women in TT2+ (at least 2 doses of tetanus toxoid) (%) | 45,7 | 2011 | NCPI annual report | 55 | 14 Feb 2013 | 60 | 14 Feb 2014 | 65 | 14 Feb 2015 |
| Attendance rate of health care facilities in % | 19 | 2007 | Districts evaluation report | 23 | 14 Feb 2013 | 27 | 14 Feb 2014 | 35 | 14 Feb 2015 |

Product indicators

| Impact indicator | Basic data |  |  | Targets |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Value | Year | Source | 2012 | Expiration of report | 2013 | Expiration of report | 2014 | Expiration of report |
| Percentage of health posts and district health centers offering the complete PMA | 0 | 2007 | Districts evaluation report | 30 | 14 Feb 2013 | 65 | 14 Feb 2014 | 85 | 14 Feb 2015 |
| Availability rate of essential medicines | ND | 2011 | JRF | ND |  | 100 | 14 Feb 2014 | 100 | 14 Feb 2015 |
| Proportion of health posts and DHC with appropriate staff | 0 | 2007 | Districts evaluation report | 25 | 14 Feb 2013 | 70 | 14 Feb 2014 | 90 | 14 Feb 2015 |

Process indicators

| Policy indicator | Basic data (where relevant) |  |  |  | Year 1-3 targets (first period of engagement) |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | N | % | Year | Source | 1 July 12 |  | 1-Jan-13 |  | Jul-13 |  | 1-Jan-14 |  | 1 July 14 |  |
|  | D |  |  |  | 31-Dec-12 |  | 30-June-13 |  | 31-Dec-13 |  | 30-June-14 |  | 31-Dec-14 |  |
| Percentage of health posts and district health centers having received the initial stock of essential generic medicines (EGM) | 0 | 0 | 2012 | Report of activities | 0 | 0 | 23 | 100 | 0 | 0 | 0 | 0 | 0 | 0 |
|  | 23 |  |  |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  |
| Percentage of training supervision conducted at the Central level towards the DGS | 0 | ND | 2012 | Supervision reports | 6 | 50 | 6 | 50 | 6 | 50 | 6 | 50 | 6 | 50 |
|  | 12 |  |  |  | 12 |  | 12 |  | 12 |  | 12 |  | 12 |  |
| Percentage of members of trained core teams | 47 | 50 | 2012 | Training report | 47 | 49 | 49 | 51 | 0 | 0 | 0 | 0 | 0 | 0 |
|  | 96 |  |  |  | 96 |  | 96 |  | 96 |  | 96 |  | 96 |  |
| Percentage of training supervision conducted by the DGH for the 8 DHCs | 0 | ND | 2012 | Supervision reports | 24 | 25 | 48 | 50 | 48 | 50 | 48 | 50 | 48 | 50 |
|  | 96 |  |  |  | 96 |  | 96 |  | 96 |  | 96 |  | 96 |  |
| Percentage of returns realized (annual and mid-term) | 1 | 20 | 2012 | Reports of annual reviews | 4 | 80 | 1 | 20 | 4 | 80 | 1 | 20 | 4 | 80 |
|  | 5 |  |  |  | 5 |  | 5 |  | 5 |  | 5 |  | 5 |  |
| Percentage of the 8 DHC whose cash recovery system was revised | 0 | 0 | 2012 | Report of activities | 0 | 0 | 0 | 0 | 8 | 100 | 0 | 0 | 8 | 100 |
|  | 8 |  |  |  | 8 |  | 8 |  | 8 |  | 8 |  | 8 |  |

Appendix 5: Action plan including the budget

| Field of aid | Activities |  | Chronogram of activities |  |  |  |  |  |  |  |  |  | Cost per annum in USD |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | A1 | A1 | A2 | A2 | A2 | A2 | A3 | A3 | A3 | A3 | Year 1 | Year 2 | Year 3 | TOTAL COSTS |
|  |  |  | T3 | T4 | T1 | T2 | T3 | T4 | T1 | T2 | T3 | T4 | 2012 | 1203 | 2014 |  |
| Objective n°1: Improve on the organization and coordination of health services including the immunization program at all health system levels |  |  |  |  |  |  |  |  |  |  |  |  | 248 892 | 202 382 | 163 878 | 615 152 |
| DHP 1.1 Strengthening of management capacities of heads of health services |  | A.1.1.1 Organize 3 training sessions for core team members of health districts following the methods and techniques of planning and supervision of agents according to the health posts and district health centers (one session per Ile)Organize 3 training sessions for core team members of health districts following the methods and techniques of planning and supervision of agents according to the health posts and district health centers (one session per Ile) |  | x |  |  |  |  |  |  |  |  | 11 976 |  |  | 11 976 |
|  |  | A.1.1.2 Organize planning workshops in the DHCs and HP |  | x |  |  |  | x |  |  |  | x | 7 795 | 8 404 | 9 059 | 25 258 |
| DHP 1.2 Strengthening of coordination, monitoring and evaluation of HSS activities |  | A.1.2.1 Support the management, follow up and coordination of the implementation of GAVI HSS activities | x | x | x | x | x | x | x | x | x | x | 62 131 | 57 894 | 32 932 | 152 958 |
|  |  | A.1.2.2 Provide supervision vehicles for the central level and districts |  | x |  |  |  |  |  |  |  |  | 142 443 |  |  | 142 443 |
|  |  | A.1.2.3 Aid to supervision missions of DCH and the central level. |  | x |  | x |  | x |  | x |  | x | 24 546 | 52 922 | 57 050 | 134 518 |
|  |  | A.1.2.4. Organize a mid-evaluation during the fourth trimester 2013 |  |  |  |  |  | x |  |  |  |  |  | 12 696 |  | 12 696 |
|  |  | A.1.2.5 Organize a final evaluation of the implementation of HSS GAVI activities |  |  |  |  |  |  |  |  |  | x |  |  | 13 686 | 13 686 |
|  |  | A.1.2.6. Organize an external audit of the implementation of the proposal. |  |  |  | x |  |  |  |  |  |  |  | 23 016 |  | 23 016 |
|  |  | A.1.2.7. Encourage advanced strategies activities |  |  |  | x |  | x |  | x |  | x |  | 47 450 | 51 151 | 98 601 |

Appendix 5: Action plan including the budget (continuation)

| Field of aid | Activities | Chronogram of activities |  |  |  |  |  |  |  |  |  | Cost per annum in USD |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | A1 | A1 | A2 | A2 | A2 | A2 | A3 | A3 | A3 | A3 | Year 1 | Year 2 | Year 3 | TOTAL COSTS |
|  |  | T3 | T4 | T1 | T2 | T3 | T4 | T1 | T2 | T3 | T4 | 2012 | 2013 | 2014 |  |
| Objective 2: From now until 2014, the attendance rate for district health services will go from 19% to 30% including that of woman and children under 5 years old in target zones |  |  |  |  |  |  |  |  |  |  |  | 482 082 | 224 330 | 161 173 | 867 585 |
| DHP 2.1 Building equipment, infrastructure and maintenance and the provision of care | A.2.1.1 Rehabilitate and re-equip health posts in targeted zones |  | x | x |  |  |  | x |  |  |  | 302 456 | 130 419 | 105 444 | 538 320 |
|  | A.2.1.2 Provide 8 motorcycles for advanced strategy to the DHCs |  | x |  |  |  |  |  |  |  |  | 25 459 |  |  | 25 459 |
|  | A.2.1.3 Give incinerators to medical districts |  | x |  |  |  |  |  |  |  |  | 81 663 |  |  | 81 663 |
|  | A.2.1.4 Encourage preventive maintenance, upkeep and repairing of materials and equipment (medical, etc.) |  | x | x | x | x | x | x | x | x | x | 7 469 | 32 208 | 34 720 | 74 397 |
| DHP 2.2 Development of health human resources | A.2.2.1 Organize 3 training sessions HC agents on the implementation of essential health packages. |  | x |  |  |  |  |  |  |  |  | 12 112 |  |  | 12 112 |
|  | A.2.2.2 Train HC and HP agents in the preventive maintenance of equipment. |  |  | x |  |  |  |  |  |  |  |  | 10 114 |  | 10 114 |
| DHP 3 Strengthening of social mobilization | A.2.3.1 Organize 9 training sessions for the benefit of community health agents. |  | x | x |  |  |  | x |  |  |  | 18 078 | 19 488 | 21 009 | 58 575 |
|  | A.2.3.2 Give communication equipment on the promotion of health for the mobilization and sensitization of the community in targeted HC zones. |  | x |  |  |  |  |  |  |  |  | 34 844 |  |  | 34 844 |
|  | A.2.3.3 Organize 6 training workshops for the HC and HP management committee. |  |  | x |  |  |  |  |  |  |  |  | 20 605 |  | 20 605 |
|  | A.2.3.2 Give materials and IEC supplies to the Management of Health promotion for massive sensitization campaigns. |  |  |  | x |  |  |  |  |  |  |  | 11 496 |  | 11 496 |

Appendix 5: Action plan including the budget (continuation)

| Field of aid | Activities | Chronogram of activities |  |  |  |  |  |  |  |  |  | Cost per annum in USD |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | A1 | A1 | A2 | A2 | A2 | A2 | A3 | A3 | A3 | A3 | Year 1 | Year 2 | Year 3 | TOTAL COSTS |
|  |  | T3 | T4 | T1 | T2 | T3 | T4 | T1 | T2 | T3 | T4 | 2012 | 1203 | 2014 |  |
| Objective n°3: Between now and 2014, reduce the shortage rate of essential medicines including vaccines and inputs to 0% |  |  |  |  |  |  |  |  |  |  |  |  | 200 445 | 9104 | 209 548 |
| DHP 3.1 Improving on storage conditions of drugs and vaccines | A.3.1.1 Give autonomous pharmacies (PNAC) and its branches at the level of islands storage sheds. |  |  |  |  | X |  |  |  |  |  |  | 130 419 |  | 130 419 |
|  | A.3.1.2 Give solar refrigerators to DHPs in targeted zones. |  |  |  |  |  | X |  |  |  |  |  | 22 455 |  | 22 455 |
| DHP 3.2: Strengthening of technical capacities of the pharmaceutical storages in the targeted zones. | A.3.2.1. Organize 6 training sessions for those in charge of the management of medicines and vaccines on how to use management tools. |  |  | X |  |  |  | X |  |  |  |  | 8 445 | 9 104 | 17 549 |
|  | A.3.2.2. Give essential generic medicines to DHCs and HPs in the targeted zones. |  |  |  | X |  |  |  |  |  |  |  | 39 126 |  | 39 126 |
| Objective n°4: Strengthen the medical Information System |  |  |  |  |  |  |  |  |  |  |  | 4 734 | 64 719 | 37 526 | 106 979 |
| DHP 3.1 Improving the data quality | A.4.1.1 Organize a training session on the analysis and use of data for those in charge of medical information at the HCs and HPs. |  |  |  |  |  | X |  |  |  |  |  | 2 815 |  | 2 815 |
|  | A.4.1.2 Support the evaluation of data quality in the DHCs and HPs of the targeted zones. |  |  |  |  |  | X |  |  |  |  |  | 4 814 |  | 4 814 |
|  | A.4.1.3 Give tools for data collection to DHC and HPs. |  | X |  |  |  | X |  |  |  | X | 4 734 | 5 103 | 5 501 | 15 339 |
| DHP 3.2 Publication and divulgation of health information | A.4.2.1. Support the production and distribution of the statistical yearbook in a bid to give an account of the achievements. |  |  |  |  |  | X |  |  |  | X |  | 14 176 | 15 282 | 29 458 |
|  | A.4.2.2. Provide an internet connection to the DHCs of the targeted zones to facilitate the transmission of data. |  |  | X |  |  |  |  |  |  |  |  | 22 280 |  | 22 280 |
| DHP 3.3 Development of research into a health system | A.4.3.1. Encourage 2 operational researches on the reasons for non-immunization of children less than 11 months in the DHCs. |  |  | X |  |  |  | X |  |  |  |  | 12 696 | 13 686 | 26 382 |
|  | A.4.3.2. Publish and distribute the results of these studies. |  |  |  | X |  |  |  | X |  |  |  | 2 835 | 3 056 | 5 892 |
| GENERAL TOTAL COSTS |  |  |  |  |  |  |  |  |  |  |  | 735 708 | 691 876 | 371 680 | 1 799 265 |