Application Form for:

GAVI Alliance Health System Strengthening (HSS)

Applications of MADAGASCAR

October 2007

An electronic version of this document is available on the GAVI Alliance website (www.gavialliance.org) and provided on CD. Email submissions are highly recommended, including scanned documents containing the required signatures. Please send the completed application to:

Dr Craig Burgess

Senior Programme Officer, HSS

GAVI Alliance Secretariat

c/o UNICEF, Palais des Nations

1211 Geneva 10, Switzerland

Email: cburgess@gavialliance.org

Please ensure that the application has been received by the GAVI Secretariat on or before the day of the deadline. Proposals received after that date will not be taken into consideration for that review round. GAVI will not be responsible for delays or non-delivery of proposals by courier services.

All documents and attachments should be in English or French.  All required information should be included in this application form. No separate proposal documents will be accepted by the GAVI Secretariat. The GAVI Secretariat is unable to return submitted documents and attachments to countries. Unless otherwise specified, documents may be shared with the GAVI Alliance partners, collaborators and the general public.

Please direct all enquiries to:

Dr Craig Burgess (cburgess@gavialliance.org) or representatives of a GAVI partner agency.

Table of Contents

Page

Abbreviations and Acronyms	2

Executive Summary	2

Section 2: Country Background Information	2

Section 3: Situation Analysis / Needs Assessment	2

Section 4: Goals and Objectives of GAVI HSS Support	2

Section 5: GAVI HSS Activities and Implementation Schedule	2

Section 6: Monitoring, Evaluation and Operatenal Research	2

Section 7: Implementation Arrangements	2

Section 8: Costs and Funding for GAVI HSS	2

Section 9: Endorsement of the Application	2

ANNEX 1 Documents Submitted in Support of the GAVI HSS Application	2

ANNEX 2 Banking Form	2

ANNEX 3 Criteria for choosing the SSDs to receive HSS GAVI support	2

ANNEX 4 Detailed description of the costs	2

ANNEX 5 List of unit costs used	2

ANNEX 6 Summary of the HSCC meeting on the 12th of April 2007	2

# Abbreviations and Acronyms

ADRA		Adventist Developpment Relief Agency

AFD		Agence Française pour le Développement (French Development Agency)

AFRF		Association Française Raoul Follereau (Raoul Follereau Association)

AMIT		Association Médicale Inter-Entreprise de Tananarive (Antananarìvo Inter-Enterprise Medical Association)

BAD		Banque Africaine de Développement (ADB African development Bank – (ADF – African development Fund))

CCIA		Comité de Coordination Inter Agences (Inter Agencies Coordinating Committee)

CCSS		Comité National de Coordination du Secteur Santé (HSCC - Health Sector Coordination Committee)

CHD		Centre Hospitalier du District (District Hospital)

CHRR		Centres Hospitaliers Régionaux de Référence (Regional Preference Hospitals)

CHU		Centres Hospitaliers Universitaires (University Hospitals)

CNS		Comptes Nationaux de santé (National Health Accounts)

COGE		Comité de Gestion (Management Committee)

COSAN	Comité de Santé (Health Committee)

CRS		Catholic Relief Services

CSB		Centre de Santé de Base (Primary Health Centre)

DDDS		Direction de Développement des Districts Sanitaires (Directorate for the Development of Health Districts)

DEP		Direction des Etudes et de la Planification (Directorate for Policy and Planning)

DGS		Direction Générale de la santé (Directorate General for Health)

DHS 		Demographic Health Survey

DRSPF	Direction Régionale de la Santé et du Planning Familial (Regional Directorate for Health and Family Planning)

DSRP		Document de Stratégie pour la Réduction de la Pauvreté (Strategy Document for the Reduction of Poverty)

DSF		Direction de la Sante de la Famille (Directorate for Family Health)

DTC		Diphtérie – Tétanos – Coqueluche (vaccine)

EMAD		Equipe de Management du District (District Management Team)

EMAR		Equipe de Management de la Région (Regional Management Team)

EPM		Enquête Périodique auprès des Ménages (Periodic Household Survey)

ESM		Equipe Sanitaire Mobile (Mobile Health Team)

EU		Eurpoean Union

FANOME	Financement pour l’approvisionnement non-stop en médicaments essentiels (Funding for the non-stop provision of essential medicines)

FAR		Femmes en Age de Reproduction (Women at the age of Reproduction)

GAVI		Global Alliance for Vaccines and Immunization

GTZ		Coopératen Allemande (German Cooperaten)

Hep B		Hepatitus type b (vaccine)

Hib 		Heamophilus Influenzae type b (infection or vaccine)

IEC		Information, Education, Communication

IFP		Institut de Formation des Paramédicaux (Paramedic Training Institute)

INSPC 	Institut National de Santé Publique et Communautaire (National Institute of  Public and Cummunity Health)

INSTAT 	Institut National des Statistiques (National Institute of Statistics)

JICA 		Coopératen Japonaise (Japanese Cooperaten)

MAP 		Madagascar Action Plan

MSPF 		Ministère de la Santé, du Planning Familial et de la Protection Sociale

OMD 		Objectifs du Millénaire pour le Développement (MDG - Millennium Development Goals)

OMS 		Organisation Mondiale de la Santé (WHO – World Health Organisation)

ONG 		Organisations Non Gouvernementales (NGO – Non-Governement Organisations)

ONM		Ordre National de Médecins (National Order of Doctors)

ONN		Office Nationale de la Nutrition (National Nutrition Office)

OSF		Ordre National de Sage-femmes (National Order of Midwifery)

OSTIE		Organisation Sanitaire Tananarivienne Inter-Entreprise (Antananarìvo Inter-Enterprise Health Organisation)

PAM 		Programme Alimentaire Mondiale (WFP – World Food Programme)

PCA 		Paquet Complémentaire d'Activité (Complimentary Activities Package)

PDSS 		Plan de Développement du Secteur Santé (National Health Sector Strategy and Development Plan)

PEV 		Programme Elargi de Vaccination (Immunisation Expansion Programme)

PFA 		Paralysie Flasque Aiguë (AFP Accute Flaccid Paralysis)

###### PMA 	Paquet Minimum d'Activité (Minimum Activity Package)

PN2D		Programme National de Décentralisation et de Déconcentraten

PNUD 		Programme des Nations Unies pour le Développement (United Nations Development Programme - UNDP)

###### PPAC 	Plan Pluri Annuel Complet du PEV (Complete Multi-annual Plan of the PEV)

PPTE 		Pays Pauvres Très endettés (HIPC - Heavily Indebted Poor Countries)

PTA		Plan de Travail Annuel (Annual Works Plan)

RSS 		Soutien au renforcement des services de santé (Health System Strengthening Support - HSS)

SAF/FJKM	Département du Développement de l’Eglise Protestante FJKM (Protestant Church Development Department FJKM)

SALAMA	Centrale d’achat (buying group)

SALFA 	Sampan’Asa Loterana Fahasalamana (Département Santé de l’église Luthérienne – Lutheran Church Health Department)

SantéNet	Projet Santé de l’USAID (Health Project of USAID)

SCAC 		Service de Coopératen  et d’Actions Culturelles (Cultural Action and Cooperaten Service)

SIGS		Système d’Information pour la Gestion Sanitaire (Health Management and Information System)

SMAD		Service Militaire d’Action au Développement (Military Service for Development Action)

SSD 		Service de Santé de District (District Health Service)

SSME		Semaine de la Santé de la Mère et de l’Enfant (Mother and Child Health Week)

SSV 		Soutien aux services de immunisation (Immunisation Service Support)

TCV 		Taux de Couverture Vaccinale (Immunisation Coverage Rate)

TIC		Technologie d’Information et de Communication (Information and Communications Technology)

TMN 		Tétanos Maternel et Néonatal (Maternal and Neo-natal tetanus)

UNFPA 	United Nations Population Fund

UNICEF 	The United Nations Children's Fund

USAID	United States Agency for International Development

VAR		Vaccin Anti-Rougeoleux (Anti-measles Vaccine)

VAT		Vaccin Anti-Tétanique (Anti-Tetanus Vaccine)

VPO3 		Vaccin Polio Oral (3ème administraten) (Oral Polio Vaccine (3rd Administraten)

# Executive Summary

To the applicant

- Please provide a summary of the proposal, including the goal and objectives of the GAVI HSS application, the main strategies/activities to be undertaken, the expected results, the duration of support and total amount of funds requested and the baseline figures and targets for the priority indicators selected.

- Please identify who took overall responsibility for preparing the GAVI HSS application, the role and nature of the HSCC (or equivalent), and the stakeholders participating in developing the application.

The Madagascar proposal on the health system strengthening forms part of the implementation of the Madagascar Action Plan 2007-2012 and the National Health Sector Strategy and Development Plan (PDSS) 2007-11.

The aim of this application for support is to achieve an effective, accessible and equitable health system. The main activities envisaged target three main areas: The organisation of the health system, the increase the demands on the services provided on the part of the population and the health system environment. These activities cover five key areas:

- Organisation and management

- Finance

- Human resources

- Community mobilisation

- Improvement in health coverage and quality of service.

The main HSS activities proposed are as follows:

- Train health-care workers on the benefits and use of data for planning and decision-making.

- Asses the performance of health data transfer from the CSB to the central system

- Carry out regular follow-up and supervisory reviews of the CSBs

- Renew the CSBs

- Strengthen the application of the Equity Funds system implementation plan in the targeted health care facilities.

- Introduce different strategies for increasing the population’s financial accessibility to health-care services

- Carry out financial auditing and supervision of the priority health-care activities with PEV as top priority (focused on the continuation of child and maternal care) in the targeted areas and develop corrective strategies for improving the programme management

- Offer training on financial and programme management to the managers on the periphery of the targeted districts

- Contract health-care workers.

- Support coaching in the targeted areas (supervision, guidance, mentoring)

- Identify the factors that limit the use of the services by the population.

- Develop and institutionalise community health-care strategies.

- Equip 10 SSDs with a 4x4 vehicle, the supervisors with 2 4x4 vehicles and 120 CSBs with motor bikes.

- Set up an operational and sustainable cold chain

The proposal targets 40 SSDs and 10 regions.  The criteria selection list for the SSDs can be found in Annex 3.

The expected results are an improvement in immunisation coverage, an increase in the offer of health-care services and an increase in the use of these services in the targeted areas.

This application for support covers the final quarter of 2007 and spans 2008 to 2010.
The total amount requested of GAVI totals $US 11 215 608,4.

The development process for this proposal was overseen by the Directorate General for Health (DGS) and the Directorate for the Development of Health Districts (DDDS).

The responsibilities of the HSCC or the Comité National de Coordination du Secteur Santé (CCSS) are the drafting and ratification of this proposal, the plans for the use of the GAVI funds, the approval of the annual action plans of the activities financed by GAVI and the supervision and monitoring of the use of these GAVI funds.

The entities involved in the development of the proposal are the DGS, the DDDS, the DEP, the DSF, the Immunisation Service, the WHO, UNICEF, the World Bank, USAID (Immunization Basics, Santé Net and HS 20/20).

Section 1: Application Development Process

To the applicant

In this section, please describe the process for developing the GAVI HSS application.

- Please begin with a description of your Health Sector Coordinating Committee or equivalent (Table 1.1).

## 1.1: The HSCC (or country equivalent)

Name of HSCC (or equivalent): Comité de Coordination du Secteur Santé (CCSS)

HSCC operational since: February 2007, originally from the Comité de Coordination Senior de la Survie de l’Enfant (Senior Coordinating Committee for Child Survival), operational since 2004.

Organisational structure (e.g., sub-committee, stand-alone): The CCSS is composed of the Comité de Coordination Inter Agences (CCIA) (Inter Agencies Coordinating Committee), the Civil Society (the Order of Doctors, the Order of Pharmacists) and ONGs.

Frequency of meetings: Twice a year

Main functions and responsibilities of the CCSS: Implementation plans for GAVI funding, Approval of the annual action plans of the activities financed by GAVI Supervision and monitoring of the use of GAVI funding Three main strategies to strengthen the role and functions of the CCSS in the next 12 months Coordination and support of the help offered by GAVI and other partners for the health system strengthening plan. Mobilisation of funds for bridging the gap of the health component in the health system. Ratification of the monitoring and evaluation reports on the annual action plans of the activities financed by GAVI.

To the applicant

- Next, please describe the process your country followed to develop the GAVI HSS application (Table 1.2)

## 1.2: Overview of application development process

Who coordinated and provided oversight to the application development process? Direction Générale de la Santé (DGS) (Directorate General for Health), Direction de Développement des Districts Sanitaires (DDDS) (Directorate for the Development of Health Districts), Direction des Etudes et de la Planification (DEP) (Directorate for Policy and Planning), Service de Vaccination (the Immunisation Service), WHO, UNICEF, The World Bank, USAID (Immunization Basics, Santé Net and HS 20/20).

Who led the drafting of the application and was any technical assistance provided? The drafting process of the GAVI HSS application was led by the DGS/DDDS, the DEP, and the Immunisation Service. International and national technical assistance was provided by UNICEF and USAID respectively.

Give a brief time line of activities, meetings and reviews that led to the proposal submission. The development of the application started in October 2006 with regular meetings (with the Government and partners). The process was delayed and a decision was taken to submit in May 2007. It is for this reason that the chronology outline below only commences from March 2007. 27th of February: Constitution of the CCSS (HSCC) committee and the CCSS meeting during which it was decided to submit the GAVI HSCC document in May. Mid-March: Receipt of feedback End of March: Restitution of the Harare HSS Workshop February and March: Production of a first draft by the national consultant (financed by UNICEF) and dissemination of the draft 5th of April: Reunion of the CCSS technical committee with the USAID consultants from HS 20/20. Presentation of the final draft including feedback. 5th to the 13 of April: Group work (DDDS, DEP, Immunization Basics, HS 20/20 consultants) for redrafting draft 2 (in order to assure the HSS activities, to determine the targeted areas taking into account the PDSS and to produce a detailed budget). Strengthening of political dialogue the participating parties: Presentation of the PDSS, PPAC and contracting of the HSS activities. (to be determined together) CCSS meeting on the 19.04.07 with MinsanPF, Ministry of Finance, Ministry of education, Department of territory decentralisation and development, CCIA (partners: WHO, UNICEF, World Bank, USAID, JICA, UNFPA, AFD, GTZ, ADB, UNDP) and Civil Society (SALFA, SAF, CRS, CARE, ADRA, ONN, ONM, OSF, Red Cross, AMIT, OSTIE, Marie Stopes, AFRF, Regio Tierzo Mondo) Presentation of the different Draft stages of the Document. Finalisation and submission of the application for the 11.05.07

Who was involved in reviewing the application, and what was the process that was adopted? The ratification meeting took place on the 12th of April 2007 with the Minister for Health, The Deputy Minister and the CCSS. The process adopted was to send a draft of the application to the persons and organisations that were present at the meeting for review before the meeting was convened. During the meeting itself, they voiced their comments and suggestions, which were then incorporated in the document. The final document was then sent a final time to the members of the CCSS for their signature.

Who approved and endorsed the application before submission to the GAVI Secretariat? The CCSS, the Minister for Health and the Minister of Finances

To the applicant

- Please describe overleaf the roles and responsibilities of key partners in the development of the GAVI HSS application (Table 1.3).

Note: Please ensure that all key partners are included; the Ministry of Health; Ministry of Finance; Immunisation Program; bilateral and multilateral partners; relevant coordinating committees; NGOs and civil society; and private sector contributors. If there has been no involvement of civil society or the private sector in the development of the GAVI HSS application, please explain this below (1.4).

## 1.3: Roles and responsibilities of key partners (HSCC members and others)

| Title / Post | Organisation | HSCC member yes/no | Roles and responsibilities of this partner in the GAVI HSS application development |
| --- | --- | --- | --- |
| HAYE Mme Anne Clair | World Bank | Yes | Technical Support (participation in the drafting of the application) Technical approval |
| Dr Léonard Tapsoba WHO Representative for Madagascar and Réunion. | WHO | Yes | Technical Support (participation in the drafting of the application) Financial Support (participation in assuming the financial costs of the participants by Harare Workshop) Technical approval |
| Mr Bruno Maes Resident Representative of UNICEF | UNICEF | Yes | Technical Support (participation in the drafting of the application) Financial Support (participation in assuming the financial costs of the participants by Harare Workshop, financing the application development meetings, financing a national consultant for drafting the application) Technical approval |
| Mme Wendy Benazerga Director of the Nutrition and Population Health Bureau | USAID | Yes | Technical Support (participation in the drafting of the application) Financial Support (financing the application development meetings, financing a national consultant for drafting the application) Technical approval |
| TOGAWA Toru Resident Representative of JICA Madagascar | JICA | Yes | Technical approval |
| Mr Castaing Denis Director of AFD Madagascar | Agence Française de Développement (French Development Agency) | Yes | Technical approval |
| Dr Ralaivita Mamy Representative of SALFA | Civil Society | Yes | Technical approval |
| Dr Rakotovao Ravahatra Kalory President of l’Ordre National des Médecins (the National Order of Doctors) | Civil Society | Yes | Technical approval |
| M Detoeuf Grégoire Association Française Raoul Follereau (Raoul Follereau Association) | Civil Society | Yes | Technical approval |
| RASOARIZAKA Hantamiraho Director of Public Investment | Ministry of Finance | Yes | Technical approval |

To the applicant

- If the HSCC wishes to make any additional comments or recommendations on the GAVI HSS application to the GAVI Secretariat and Independent Review Committee, please do so below.

- Please explain if there has been no involvement of civil society or the private sector, and state if they are expected to have a service provision or advocacy role in GAVI HSS implementation.

## 1.4: Additional comments on the GAVI HSS application development process

Civil Society and the NGOs have validated the technical proposal. Civil Society will be involved in the implementation of the activities in terms of contracting health-care workers (activity 1.1). The NGOs will be involved in objective 4, which consists of developing the community health strategies. Furthermore, Civil Society and the NGOs, as part of the CCSS, will be constantly involved in monitoring the GVI HSS activities and in the dissemination of the results.

# Section 2: Country Background Information

To the applicant

- Please provide the most recent socio-economic and demographic information available for your country. Please specify dates and data sources. (Table 2.1).

## 2.1: Current socio-demographic and economic country information

| Information | Value |  | Information | Value |
| --- | --- | --- | --- | --- |
| Population Source: PPAC Report | 18 580 236 |  | GNI per capita Source: Medium Term Expenditure Framework Date: 2005 | 330 $US |
| Annual Birth Cohort Calculation method: 3.535 of the total population | 655 882 |  | Under five mortality rate Source: DHS Date: 2004 | 94 ‰ |
| Surviving Infants* Source: PPAC | 617 841 |  | Infant mortality rate Source: DHS Date: 2004 | 58 ‰ |
| Percentage of GNI allocated to Health Source: MEFB (Ministry of Finance) and FMI date and estimations produced by the World Bank | 1.4% in 2006 |  | Percentage of Government expenditure on Health Source: DEP Date: 2006 | 7,11% |

* Surviving infants = Infants surviving the first 12 months of life

To the applicant

- Please provide a brief summary of your country’s Health Sector Plan (or equivalent), including the key objectives of the plan, the key strengths and weaknesses that have been identified through health sector analyses, and the priority areas for future development (Table 2.2).

## 2.2: Overview of the National Health Sector Strategic Plan

The equivalent of the NHSP in Madagascar is called the « Plan de Développement Sectoriel Santé (PDSS), 2007-2011 » (Health Sector Development Plan) The main objectives of the PDSS are 1) to strengthen the national health system, 2) to increase the survival rates of mother and child 3) to support the fight against disease caused by the environment, 4) to boost health protection and the promotion of health consciousness. The specific goals expressed in the PDSS are: Improve the legal and institutional framework of the health system, national health policy and the health sector plan implementing the WHO and MAP priorities: Promote decentralisation of the health management and decision-making system for the regions and communities. Improve the availability of human resources qualified in at least 70% of the health care facilities; Improve health coverage and quality of service. Strengthen health funding in order to respond to the needs of the public sector and the population; Improve the organisation and management of the health system; Reduce the maternal mortality rate from 469 to 156 per 100,000 live births and neonatal mortality from 32% to 20% from now until 2012 (MAP). Reduce the infant and child mortality rate from 94 to 73 per 1,000 live births from not until 2012 (MAP). The key strengths that have been identified in the health system are: Existence of structures that lend themselves to the decentralisation policy; PDSS used as an operational instrument for implementing the National Health Policy, the Millennium Development Goals as well as those of MAP; Existence of a national health policy; Availability of regulations and standards on health infrastructure and resources for certain health-care establishments (CSBs, CHPRs) ; Existence of equity funds for taking care of the underprivileged; Collaboration between the technical and financial partners of the health sector (AFD, SCAC / FAC, USAID, JICA, IDA, ADB/ADF, UNICEF, WHO, UNFPA, UNDP, WFP, SECALINE, Global Fund, GAVI), the Ministry of National Defence (Military Service for Development Action: SMAD) and the Ministry of Health, Family Planning and Social Welfare; Existence of structures for the communication and the Information and Communications (ICT) System at all levels of the health system; Availability of the preliminary development plan of human resources and strengthening the training institutions of health practitioners; Existence of a buying group (SALAMA) for the procurement and distribution of medication, medical reagents and consumables for public health care facilities. Existence of strategic political framework (PDSS) based on a shared common vision that is directed at the logic of a sector enlargement approach (SWAp). The key weaknesses that have been identified in the health system are: Insufficiency of human resources, materials and finances in the decentralised structures; Insufficiency and unequal distribution of the human resources in the different levels of the system; Aging of technical personnel and insufficiency of stand-ins; Weak performance of the information system (lack of availability of certain data, non integrated system); Insufficient coordination among the various structures and the different priority programmes of the system; Lack of management of the community structures (COGE, COSAN etc.) and therefore non institutionalisation of these structures in the health system; Existence of areas and regions with reduced accessibility and therefore not covered by the health structures in place; Nonoperational ICT due to the absence of energy sources, hardware and software development as well as the lack of standardisation of IT equipment and materials at the various levels (central, intermediate, peripheral). Insufficiency of financial resources in terms of Equity Funds for adequate care of the poor population (68% of the population live below the poverty line but only 1% of the population is cared for by the Equity Funds). In response to these strengths and weaknesses, the priority strategies of the Madagascan Ministry of Health have been organised into the 5 following activities: 1) Pursue the strengthening of the provision of quality health services for the entire population, with the objective of assuring a quality service in the primary health centres (CSBs) and the emergency hospitals, especially in the marginalised areas. This activity also includes continuing efforts on decentralising the resources, functions and responsibilities of the districts in order to strengthen the self-efficacy of the districts in terms of the organisation, management and provision of goods and services, especially in the rural and marginalised areas. The community response in the management and financing of peripheral health services is also considered as an important element for improving the quality of services and assuring their sustainability. This will provide basic child and maternal care services in the form of immunisation, prevention and control of the main forms of disease, pre- and post-natal care etc. as they will be accessible and used by the majority of the population. Responses to HIV/AIDS must be accelerated at a community level. 2) Develop a sector enlargement strategy for contributing to the improvement of the management of human resources in the health sector. This will encompass the definition of the profiles of the professionals necessary for operating in the health sector; the revision of standards and the redeployment of personnel, based in the criteria and standards for improving the inequality between the rural and urban areas; the development of motivation strategies for the renewal of personnel who retire; the stabilisation of doctor positions who practice in the rural districts; the development of career plans for the different categories of personnel and implementing incentives for doctors practising at all levels of health care. 3) Mobilisation and allocation of financial resources. This activity is at the core of the sector strategies in Madagascar, as the country will have to increase the resources allocated to the health sector. Innovative measures in the mobilisation of resources include social and community health insurance and must be considered in the sector strategies. Furthermore, the public-private partnership could be explored as an important potential for generating new resources. The aim of this component is to bring the necessary technical assistance for developing innovative mechanisms for mobilising resources and strengthening the allocation of these in the heart of the sector with the goal of including these among the priority objectives of the government. 4) Stimulate demand and use of the health services. The goals of this component are to increase the use of the health services by the population, especially in the marginalised areas. This component will support the development and institutionalisation of the activities geared towards stimulating demand - community education and raising public awareness of the campaigns. This strategy also includes technical assistance in developing a voucher system for the use of certain services. 5) Strengthening and institutionalisation of an effective monitoring and evaluation system offering information on the inputs, structures, results and impacts. This is a priority for improving management centred on the results and for strengthening performance. The monitoring and evaluation system proposed here consists of establishing a road map of the outcome indicators relating to the health strategies laid out in the MAP, the results indicators of the project in order to measure the implementation progress and the intermediary indicators in order to align and integrate them in the operational works plan. The aim of the monitoring and evaluation plan is to align the strengthening activities of the system financed by the project with the objectives of the MAP, and to create an integrated and coherent working framework in order to monitor and evaluate the progress from in a multidimensional context. This monitoring and evaluation plan will afford the necessary information for the decision-making, planning and implementation involved in order to attain the goals and make the necessary adjustments over time.

# Section 3: Situation Analysis / Needs Assessment

To the applicant

GAVI HSS Support: GAVI HSS support cannot address all health system barriers that impact on immunisation and other child and maternal health services. GAVI HSS support should complement and not duplicate or compete with existing (or planned) efforts to strengthen the health system. GAVI HSS support should target “gaps” in current health system development efforts.

- Please provide information on the most recent assessments of the health sector that have identified health system barriers. (Table 3.1)

Note: Assessments can include a recent health sector review (conducted in the last 3 years), a recent report or study on sector constraints, a situation analysis (such as that conducted for the cMYP), or any combination of these. Please attach the reports of these assessments to the application (with executive summaries, if available). Please number them and list them in Annex 1.

Note: If there have not been any recent in-depth assessments of the health system (in the last 3 years), at the very least, a desk review identifying and analysing the key health systems bottlenecks will need to be undertaken before applying for GAVI HSS support. This assessment should identify the major strengths and weaknesses in the health system, and identify where capacity needs to be strengthened to achieve and / or sustain increased immunisation coverage.

## 3.1: Recent health system assessments

| Assessment title | Participating institutions | Sectors/themes covered | Dates |
| --- | --- | --- | --- |
| Mission report. Training and monitoring and evaluation consultation | African Development Bank (ADB) | Strengthening and development of human resources Provision of essential medical supplies Improvement of family well-being | 2007 |
| Introduction to the Quality Management Approach through cost of quality COQ in the CSBs in the intervention areas of the project | DRSPD/GTZ/KfW | Health service strengthen project in the province of Mahajanga | 16th of November 2006 |
| Final report. Support project for the implementation of the development plans of the health districts in the southern area: Antananarivo, Fianarantsoa, and Toliara. | JSI R&TI | Participation in: the production of the 2004 PTA of the CSBs and the targeted health districts observing all the stages of an ascendancy plan monitoring of the implementation of the 2004 PTA activities moving into 2005 production of the 2005 PTA for all the SSDs production of the 2005-2006 PDD with ratification by committee | November 2005 |
| Efficiency and Fairness of the Madagascan Health Care Facilities. | Department of Human Development African Region. World Bank | Characteristics of the health service offers Characteristics of the health service demands | May 2005 |
| Dubois, Carl-Ardy; Boivin, Suzanne; Albert, Lucien. Drafting of the Human Resources Development Plan for the health sector. Preliminary report. May 2006 | World Bank | Analysis of the human resources in health-care Proposal of scenarios for developing human resources. | May 2006 |
| INSTAT, Permanent Household Survey (EPM) | World Bank | Survey on health determinants | 2005 |

To the applicant

- Please provide information on the major health system barriers to improving immunisation coverage that have been identified in recent assessments listed above. (Table 3.2)

- Please provide information on those barriers that are being adequately addressed with existing resources (Table 3.3).

- Please provide information on those barriers that are not being adequately addressed and that require additional support through GAVI HSS (Table 3.4).

## 3.2: Major barriers to improving immunisation coverage identified in recent assessments

The barriers identified have been organised and classified as per the 5 priority activities of the Madagascan Ministry of Health as laid out in section 2.2. Apart from the barriers listed below, we can also identify two others that apply to the 5 activities and which constitute one of the flagship policies of the government: The decentralisation of responsibility is not yet in effect, The transfer of skills and resources within the framework of the new decentralisation policies is slow. The strengthening of the provision of quality health services to the entire population Unequal distribution and general lack of human resources, Poor use of the health services: mother-child care (except pre-natal consultations) connected to the problem of the quality of the provision of basic health services Centralisation of the consolidation of the Annual Works Plan (PTA) of the districts. Validation process of the PTA of the districts is too slow. Geographic access difficulties to certain health centres Limited financial accessibility of the users Incomplete range of essential products available through the buying group Inexistence of purchasing, maintenance and support plans for equipment and infrastructures. The result of this, for example, is an inability to source suppliers of products outside the cold chain. Management of human resources in the health sector The changing of personnel in positions of responsibility in the districts as well as the mobility of positions of trained personnel has influenced the speed of execution of the activities Shortage and aging of human resources especially paramedics Mobilisation and allocation of financial resources Lack of policy documents establishing financial strategies for the health system and therefore absence of rationalisation in the sector expenditure Administrative weight in the central government causing delays in the allocation of resources Administrative sluggishness on the part of fund donators for the disbursement of resources. Decentralisation intentions are not yet reflected in the budget: The budget is strongly centralised and the part currently allocated to primary health care is still low (allocation to the CSBs = 17%) Lack of rationalisation in the sector expenditures, Low proportion of the population benefit from equity fund (68% of the population love below the poverty line but only 1% of the population is cared for by the Equity Funds). Reduction in the percentage of the budget not included in the balance allocated to operations The MINSANPF part in the overall state budget has lowered from 8% in 2005 to 7.1% in 2006. (Source : Ministry of Finance, March 2007) Stimulation of demand and use of the health services Lack of policy documents establishing community health strategies Lack of coordination in the implementation of community strategies despite the existence multiple field experience (NGOs, civil society) Lack of institutionalisation of the community system Strengthening and institutionalisation of a monitoring and evaluation system Weaknesses in the Health Management and Information System (SIGS) in terms of epidemiological surveillance due to the non appropriation (i.e. lack of data analysis capacities by health-care workers for carry out activities and making decisions) of the SIGS tools. Weaknesses in the gathering, manipulation and use of the data produced by the SIGS on the part of the decision-makers. Insufficient auditing and monitoring of priority health activities Absence of a culture of monitoring the key strategic lines of the health sector.

## 3.3: Barriers that are being adequately addressed with existing resources

See table A on the next page for the response to this question. The first column of the table sets out the barriers identified in section 3.2 above and for each of these barriers, the activities undertaken to overcome them are in the second column and the organisations financing or participating in these activities are in the third column.

## 3.4: Barriers not being adequately addressed that require additional support from GAVI HSS

See table A on the next page for the response to this question. The first column of the table sets out the barriers identified in section 3.2 above and those that require additional funding from GAVI are marked with a cross in the fourth column.

Table A: Barriers to the Madagascan health system

|  | Barriers Identified | Activities undertaken to overcome these barriers | Organisations financing or participating in these activities | Barriers requiring additional funding from GAVI |
| --- | --- | --- | --- | --- |
| Objective 1 | Strengthen the provision of quality health services to the entire population |  |  |  |
|  | Poor use of the health services: mother-child care (except pre-natal consultations) connected to the problem of the quality of the provision of basic health services, among others | Take responsibility of childbirth and obstetric emergencies at a 1st reference level | World Bank, UNFPA, UNICEF, WHO, JICA, GTZ | x |
|  | Centralisation of the consolidation of the Annual Works Plan (PTA) of the districts. | Put macros in place for facilitating the validation of the PTAs | World Bank, UNICEF | x |
|  | Validation process of the PTA of the districts is too slow. | Offer management training to the mangers of several regions (EMAR, EMAD) | European union, UNICEF, WHO, GTZ | x |
|  | Geographic access difficulties to certain health centres | Construct 25 CSBs out of the 125 planned for the next three years (EU) and 20 CSBs by the government | European union, government, ADB | x |
|  |  | Support the mobile health teams (ESMs) | World Bank, government, UNICEF, AFD, WHO |  |
|  |  | Contract health-care workers. | EU (Santé Sud), Coopération française (French Cooperation) |  |
|  | Incomplete range of essential products available through the buying group | Revise the list of essential medicines and ensuring the initial provision of the SALAMA buying group for hospital and input products | World Bank, government, UNICEF, USAID, AFD, GTZ |  |
|  | Inexistence of purchasing, maintenance and support plans for equipment and infrastructures. The result of this, for example, is an inability to source suppliers of products outside the cold chain. | Draw up a strategy plan on the acquisition and maintenance of biomedical equipment | World Bank, AFD, WHO, UNICEF, ADB, UNFPA, USAID |  |
| Objective 2 | Improve human resources management of the health sector |  |  |  |
|  | Lack of human resources | Support initial training of paramedics and essential surgeons | World Bank, WHO, UNICEF, AFD, USAID | x |
|  | The changing of personnel in positions of responsibility in the districts as well as the mobility of positions of trained personnel has influenced the speed of execution of the activities |  |  | x |
|  | Shortage and aging of human resources especially paramedics | Contract health-care workers. | EU (Santé Sud), Coopération française (French Cooperation) |  |
|  |  | Finalise the development plan for human resources | World Bank, AFD, WHO, UNICEF, UNFPA, ADB, UNFPA, USAID, European Union |  |

|  | Barriers Identified | Activities undertaken to overcome these barriers | Organisations financing or participating in these activities | Barriers requiring additional funding from GAVI |
| --- | --- | --- | --- | --- |
| Objective 3 | Increase the mobilisation and allocation of financial resources |  |  |  |
|  | Limited financial accessibility of the users | Introduce the mutual health organisation approach | USAID, AFD, WHO, GTZ | x |
|  | Lack of policy documents establishing financial strategies for the health system and therefore absence of rationalisation in the sector expenditure | Carry out studies on the finance system of the health sector | World Bank, AFD, WHO, UNICEF, UNFPA, ADB, UNFPA, USAID, European Union |  |
|  | Lack of complete and integrated funding for the PEV | Draft a financial viability study of the PEV, PPAC | GAVI, USAID, UNICEF, WHO |  |
|  | Administrative weight in the central government causing delays in the allocation of resources | Implement a Public Finances Management and Information System (SIGFP) Deploy regional accounts managers | World Bank, AFD, WHO, UNICEF, UNFPA, ADB, UNFPA, USAID, European Union |  |
|  | Administrative sluggishness on the part of fund donators for the disbursement of resources. | Introduce the SWAP process | Government, World Bank, AFD, WHO, UNICEF, GTZ, UNFPA, ADB, USAID, European Union |  |
|  | Decentralisation intentions are not yet reflected in the budget: The budget is strongly centralised and the part currently allocated to primary health care is still low (allocation to the CSBs = 17%) | Ensure budgetary decentralisation within the framework of the implementation of the Decentralisation and Deconcentration National programme (PN2D) | Government, World Bank, AFD, WHO, UNICEF, GTZ, UNFPA, ADB, USAID, European Union | x |
|  | Low proportion of the population benefit from the equity fund for the targeted health care facilities (68% of the population love below the poverty line but only 1% of the population is cared for by the Equity Funds). | Feed the Equity Funds through a part of the FANOME. | Government, users | x |
|  | Reduction in the percentage of the health budget allocated to operations | Continue the support of the World Bank for the regions, districts and CSBs until 2008 (the government must then take the reins) | World Bank |  |
|  | The MINSANPF part in the overall state budget has lowered from 8% in 2005 to 7.1% in 2006 | Campaign for an increase in the health budget | Government |  |
|  | Investment expenditure has risen, expenditure for non-budgetary operations have fallen, the recurring costs of investment no longer be assured | Carry out a study within the SWAP framework on the prioritised investment plan | World Bank |  |
| Objective 4 | Stimulate demand and use of the health services |  |  |  |
|  | Lack of policy documents establishing community health strategies | Institutionalise the community system in the SWAP and support its implementation | Government, World Bank, AFD, WHO, UNICEF, GTZ, UNFPA, ADB, USAID, European Union | x |
|  | Lack of coordination in the implementation of community strategies despite the existence multiple field experience (NGOs, civil society) | Draft the community health national policy | Government, World Bank, AFD, WHO, UNICEF, GTZ, UNFPA, ADB, USAID, European Union |  |
|  | Under-use of the integrated basic health services | Head-up the IEC/CCC, SSME campaigns | Government, World Bank, AFD, WHO, UNICEF, GTZ, UNFPA, ADB, USAID, European Union |  |

|  | Barriers Identified | Activities undertaken to overcome these barriers | Organisations financing or participating in these activities | Barriers requiring additional funding from GAVI |
| --- | --- | --- | --- | --- |
| Objective 5 | Strengthen and institutionalise a monitoring and evaluation system |  |  |  |
|  | Weaknesses in the Health Management and Information System (SIGS) in terms of epidemiological surveillance due to the non appropriation (i.e. lack of data analysis capacities by health-care workers for carry out activities and making decisions) of the SIGS tools. | Generalise the implementation of GESIS software in the SSDs | Government, European Union, USAID (Santé Net) | x |
|  | Weaknesses in the gathering, manipulation and use of the data produced by the SIGS on the part of the decision-makers. . | Strengthen the management skills in data analysis and use for the decision-making process |  | x |
|  | Absence of a culture of monitoring the key strategic lines of the health sector | Draft monitoring guidelines | European Union, WHO | x |
|  |  | Implement and roll out an operational monitoring and evaluation system for the Coaches region | World Bank, USAID |  |
|  | The supervisory lines are too programme-fragmented and administratively-heavy for the drafting and use of an operational monitoring and evaluation | Support the integrated coaching system in the targeted areas based on operational performance management | World Bank, USAID |  |
|  | Insufficient auditing and monitoring of priority health activities | Set up an auditing directorate at the heart of the Ministry of Health supported by the partners | Government, World Bank, AFD, WHO, UNICEF, GTZ, UNFPA, ADB, USAID, European Union | x |

# Section 4: Goals and Objectives of GAVI HSS Support

To the applicant

- Please describe the goals of GAVI HSS support below (Table 4.1).

- Please describe (and number) the objectives of GAVI HSS support (Table 4.2). Please ensure that the chosen objectives are specific, measurable, achievable, realistic and time-bound.

## 4.1: Goals of GAVI HSS support

The general goals of GAVI HSS support are to contribute to the development of a sustainable and effective health system, to contribute to the improvement of routine immunisation services and to assure the equitability of the services offer through to a peripheral level. The aim is to offer a better response to the needs of the population, especially in terms of child and maternal health-care including acceptable and sustainable immunisation. These goals form part of the Madagascar Action Plan 2007-2012 whose implementation has been designed in the Health Sector Development Master plan (PDSS) 2007-2012, which has been approved by the member partners of the national health sector coordination organisation and the partners involved in the development of the country. In order to achieve these goals, GAVI HSS support is requested in order to contribute to carrying some of the PDSS activities.

## 4.2: Objectives of GAVI HSS Support

The objectives of GAVI HSS support for Madagascar relate to the priority strategies of the Madagascan Ministry of Health. The proposal targets 40 SSDs in 10 regions for certain activities. The selection criteria for the SSDs are: Immunisation (all Antigens combined) coverage rates les than 75% Proportion of the population serviced: above 75000 inhabitants in general in the District Health Service Geographical access difficulties (certain districts that have a population of less than 75000 have been included in the proposal due to their geographical isolation and difficulty of access) Poor performance and self-efficacy of the SSDs (service use, skills of the EMAD, availability of resources etc.) The list of chosen SSDs can be found in Annex 3. Objective 1 is the strengthening of the provision of quality health services to the entire population. The main activities included in this objective are: To contract health-care workers in the marginalised health care facilities in order to overcome the lack of resources in these areas. Note that this activity is also included in objective 2 below. Identify, by means of a study, the factors (geographical, financial and cultural) that limit the use of the service by the population. Following this, based on the results of this study, the next activity will be to pilot strategies aimed at increasing the use of these services in around 5 SSDs. To renovate (painting, purchase of furniture for receiving patients, roofing, ceiling etc.) 15 CSBs per year with the aim of improving their physical appearance and making them more welcoming to patients. This activity will concentrate on certain centres that are antiquated today and not used by the population for this reason. To head-up PTA ratification missions. Equip 10 SSDs with a 4x4 vehicle, the centre supervisors with 2 4x4 vehicles and 120 CSBs with motor bikes. The SSDs will be chosen based on criteria such as geographical isolation, immunisation coverage and serviced population. Introduce different strategies for increasing the population’s financial accessibility to health-care services in 5 SSDs. The strategies identified are: (1) Mutual health organisation system; (2) strengthening of the equity funds system (this system has been used to help the poor). Note that before implementing strategies on a national scale, it is essential to introduce them gradually in order to adapt and modify them and to identify their strengths and weaknesses. Objective 2 aims to improve health sector human resources management. The activity associated with this objective is to contract health-care workers in the marginalised health care facilities in order to overcome the lack of resources in these areas. Note that this activity is also included in objective 1 above. Objective 3 aims to increase mobilisation and improve the allocation of financial resources. The main activities included in this objective are: Strengthen the application of the Equity Funds and mutual health organisation system implementation plan in the targeted health care facilities. This will address several problems, notably that of a poor proportion of the population benefiting from the equity funds (in fact, 68% of the population live below the poverty line yet 1% of the population is cared for by the equity funds). Note that this activity is also included in objective 4 below. Carry out financial and management auditing including the FANOME audit in the targeted areas and develop corrective strategies for improving its management. Objective 4 aims to stimulate the demand and use of the health services through development of community health-care. The main activities are all geared towards the development of community health-care strategies and the institutionalisation of community health-care. The following activities are covered by this objective: Take inventory of the NGOs and associations working at a community level Convene 3 meetings per year with 100 local authorities in the targeted areas. The objective is to monitor the health-care and community activities with the aim of making adjustments or settling the difficulties that the community workers may be experiencing. Convene meetings for drafting policy documents establishing community health strategies (including Reference Terms and a Minimum Activity Package (PMA)) Train community health-care workers in PCA in 40 targeted SSDs. This training includes the provision of an IEC PEV kit including IEC aids, guides, supplies and management tools. Strengthen the application of the Equity Funds and mutual health organisation system implementation plan in the targeted health care facilities. Objective 5 aims to strengthen and institutionalise a monitoring and evaluation system through the following objectives: Training health-care workers on the benefits and use of data for planning and decision-making in the targeted areas. Assessment of the health data transfer performance of the CSBs on a central level in order to identify bottlenecks Carry out regular follow-up and supervisory reviews of the CSBs Carry out financial auditing and supervision of the priority health-care activities with PEV as top priority (focused on the continuation of mother-child care) in the targeted areas and develop corrective strategies for improving the programme management. Support coaching in the targeted areas in order to strengthen self-efficacy and skills at a regional and district level so that the leadership role in the mobilisation of service providers is assured, not to mention the organisation and coordination of community workers so that they can implement the priority strategies and the promotion of health-orientated attitudes as well as promoting the use of the integrated family planning services. This activity also includes the procurement of IT material for 40 SSDs.

# Section 5: GAVI HSS Activities and Implementation Schedule

To the applicant

- For each objective identified in Table 4.2, please give details of the major activities that will be undertaken in order to achieve the stated objective and the implementation schedule for each of these activities over the duration of the GAVI HSS support (Table 5.2 overleaf).

Note: GAVI recommend that GAVI HSS supports a few prioritised objectives and activities only. It should be possible to implement, monitor and evaluate the activities over the life of the GAVI HSS support.

Note: Please add (or delete) rows so that Table 5.2 contains the correct number of objectives for your GAVI HSS application, and the correct number of activities for each of your core objectives.

Note: Please add (or delete) years so that Table 5.2 reflects duration of your GAVI HSS application

To the applicant

- Please identify below how you intend to sustain, both technically and financially, the impact achieved with GAVI HSS support (5.1) when GAVI HSS resources are no longer available.

## 5.1: Sustainability of GAVI HSS support

In order to encourage the participation of partners and the government in the GAVI HSS activities and to maintain their interest, they will be regularly kept up to date on the results of these activities via joint meetings and regular correspondence (by email or post). We believe that this strategy will encourage the partners and Government to get involved financially and technically, especially if they see that good results are being accomplished, that the activities are well managed and the timelines are met. Another strategy will be to support the involvement of decentralised territorial collectives, NGOs and associations in the pursuit of the activities. These organisations will be a potential source of finance and technical support when the GAVI HSS funding is no longer available.

## 5.2: Major Activities and Implementation Schedule

See the table on the following page

|  |  | 2007 | 2008 | 2009 | 2010 |
| --- | --- | --- | --- | --- | --- |
|  |  | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 |
| Objective 1 | Strengthen the provision of quality health services to the entire population |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 1.1 | Contract health-care workers in the marginalised health care facilities | x | x | x | x | x | x | x | x | x | x | x | x | x |
| Activity 1.2 | Identify the factors (geographical, financial and cultural) that limit the use of the services through field research |  |  |  | x | x |  |  |  |  |  |  |  |  |
| Activity 1.3 | Pilot strategies in around 5 SSDs aimed at increasing the use of the services based on the results of the assessment study (see activity 1.2) |  |  |  |  |  | x | x | x | x |  |  |  |  |
| Activity 1.4 | Carry out renovations (painting, purchase of furniture for receiving patients, roofing, ceiling etc.) 15 CSBs per year with the aim of improving their physical appearance and making them more welcoming to patients. | x | x | x | x | x | x | x | x | x | x | x | x | x |
| Activity 1.5 | Head-up PTA ratification missions: the central team of the ministry and partners will be deployed in the regions and will ratify the PTA in the field, instead of having the PTA sent to them centrally. |  |  |  | x |  |  |  | x |  |  |  | x |  |
| Activity 1.6 | Equip 10 SSDs with a 4x4 vehicle, the centre supervisors with 2 vehicles and 120 CSBs with motor bikes. |  |  |  |  | x | x |  |  |  | x |  |  |  |
| Activity 1.7 | Introduce different strategies for increasing the population’s financial accessibility to health-care services in 5 SSDs: Mutual health organisation system |  |  |  | x | x |  |  |  |  | x | x | x |  |
| Objective 2 | Improve human resources management of the health sector |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 2.1 | Contracting activities (see 1.1) |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Objective 3 | Increase the mobilisation and allocation of financial resources |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 3.1 | Offer training on financial and programme management to the managers on the periphery of the targeted districts | x |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 3.2 | Strengthen the application of the Equity Funds and mutual health organisation system implementation plan in the targeted health care facilities |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 3.3 | Carry out financial auditing and supervision of the priority health-care activities with PEV as top priority (focused on the continuation of child and maternal care) in the targeted areas and develop corrective strategies for improving the programme management. |  |  |  | x |  |  |  | x |  |  |  | x | x |
| Objective 4 | Stimulate demand and use of the health services |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 4.1 | Carry out a regional mapping of the NGOs and associations working at a community level |  |  | x | x |  |  |  |  |  |  |  |  |  |
| Activity 4.2 | Convene 3 meetings per year with 160 local authorities in the targeted areas. |  | x | x | x | x | x | x | x | x | x | x | x | x |
| Activity 4.3 | Convene meetings for drafting policy documents establishing community health strategies (including Reference Terms and a Minimum Activity Package (PMA)) |  | x | x | x |  |  |  |  |  |  |  |  |  |
| Activity 4.4 | Provide training for community health-care workers in PCA in 40 targeted SSDs. This training includes the provision of an IEC PEV kit including IEC aids, guides, supplies and management tools. |  | x | x | x |  |  |  |  |  |  |  |  |  |
| Activity 4.5 | Strengthen the application of the Equity Funds and mutual health organisation system implementation plan in the targeted health care facilities (see also activity 3.2) |  | x | x | x |  |  |  |  |  |  |  |  |  |
| Objective 5 | Strengthen and institutionalise a monitoring and evaluation system |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 5.1 | Provide training for health-care workers on the benefits and use of data for planning and decision-making in the targeted areas. | x | x | x |  |  |  |  |  |  |  |  |  |  |
| Activity 5.2 | Assess the health data transfer performance of the CSBs on a central level in order to identify bottlenecks |  |  | x |  |  |  | x |  |  |  | x |  |  |
| Activity 5.3 | Carry out regular follow-up and supervisory reviews of the CSBs |  | x | x | x | x | x | x | x | x | x | x | x | x |
| Activity 5.4 | Support coaching in the targeted areas |  | x | x | x | x | x | x | x | x | x | x | x | x |

# Section 6: Monitoring, Evaluation and Operational Research

To the applicant

- All applications must include the three main GAVI HSS impact / outcome indicators:

- National DTP3 coverage (%)

- Number / % of districts achieving ≥ 80% DTP3 coverage

- Under five mortality rate (per 1000)

- Please list up to three more impact / outcome indicators that can be used to assess the impact of GAVI HSS on improving immunisation and other child and maternal health services.

Note: It is strongly suggested that the chosen indicators are linked with proposal objectives and not necessarily with activities.

- For all indicators, please give a data source, the baseline value of the indicator and date, and a target level and date. Some indicators may have more than one data source (Table 6.1).

Note: The chosen indicators should be drawn from those used for monitoring the National Health Sector Plan (or equivalent) and ideally be measured already (i.e. not an extra burden to measure). They do not have to be GAVI HSS specific. Examples of additional impact and outcome indicators are given in the tables below. It is recommended that when activities are implemented primarily at sub-national level that indicators are monitored, to the extent possible, at sub-nationally as well.

Examples of Impact Indicators

- Maternal mortality rate

Examples of Outcome Indicators

- National measles coverage

- Proportion of districts with coverage at 80% or above

- Hib coverage

- HepB coverage, BCG coverage

- DTP1-DTP3 drop-out rate

- Proportion of births attended by skilled health personnel

- Antenatal care use

- Vitamin A supplementation rate

| Intervention | Possible indicators |
| --- | --- |
| Immunisation | National measles coverage; proportion of districts with coverage at 80% or above; BCG coverage; Polio 3 coverage; Hib coverage; HepB3 coverage |
| Maternity care | Antenatal care use; skilled birth attendance; tetanus toxoid 2 or more doses; caesarean section rate; postnatal care |
| Family planning | Contraceptive use among women |
| Treatment of sick children | oral rehydration therapy and continued feeding for children with diarrhoea; Care seeking for pneumonia; Antibiotic treatment for pneumonia |
| Nutrition | Breastfeeding rate; (start on first day, exclusive at 0-3 months, supplements at 6-9 months); vitamin A supplementation rate to children 6-59 months (within last 6 months) and postpartum to mother within 8 weeks |
| Water/sanitation | Access to safe water source; adequate sanitary facilities |
| Tuberculosis | DOTS treatment coverage (treatment success rate times case detection rate) |
| Malaria | Children with fever receiving anti-malarials; children sleeping under ITN |
| AIDS | % of HIV-positive pregnant women receiving ARVs; PMTCT among pregnant women |

To the applicant

- Please list up to 6 output indicators based on the selected activities in section 5. (Table 6.2).

- For all indicators, please give a data source, the baseline value of the indicator and date, a target level and date, as well as a numerator and denominator. Some indicators may have more than one data source (Table 6.1).

Note: Examples of output indicators that could be used, with the related numerator, denominator (if applicable) and data source are shown below. Existing sources of information should be used to collect the information on the selected indicators wherever possible. In some countries there may be a need to carry out health facility surveys, household surveys, or establish demographic surveillance. If extra funds are required for these activities, they should be included.

Examples of Output Indicators

| Indicator | Numerator | Denominator | Data Source |
| --- | --- | --- | --- |
| Systematic Supervision | Number of health centres visited at least 6 times in the last year using a quantified checklist | Total number of health centres | Health facility survey |
| Knowledge of Health Workers | Mean score of health workers in public and NGO health centres on verbal knowledge test including case scenarios |  | Health facility survey |
| Drug availability index | Average number of ten selected essential drugs that are in stock in sampled health centres |  | HMIS & Health facility survey |

## 6.1: Impact and Outcome Indicators

| Indicator | Data Source | Baseline Value | Source | Date of Baseline | Target | Date for Target |
| --- | --- | --- | --- | --- | --- | --- |
| 1. National DTP3 coverage (%) | SIG/MinSan PFPS in the joint survey 2005 (WHO/UNICEF) | 92.2% | Annual report from the immunisation service | 2005 | 95% | 2010 |
| 2. Number / % of districts achieving ≥80% DTP3 coverage | SIG/MinSan PFPS in the joint questionnaire 2005 (WHO/UNICEF) | 67.6% | Annual report from the immunisation service | 2005 | 80% | 2010 |
| 3. Infant and child mortality rate (per 1000) | DHS, 2003/2004 | 94 ‰ | DHS, 2003/2004 | 2004 | 54 | 2010 |
| 4. Infant and child mortality rate (per 1000) | DHS, 2003/2004 | 58 ‰ | DHS, 2003/2004 | 2004 | 47 | 2010 |

## 6.2.1: Output Indicators

| Indicator | Numerator | Denominator | Source | Baseline value | Baseline date | Objective | Objective date |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Usage rate of the CSB external consultations in the targeted areas | Number of CSB external consultations | Population serviced by the CSB | SSSa | 49% | 2006 | 56% | 2010 |
| Number of physicians contracted to work in the targeted areas |  |  | DDDS | N/A | 2006 | 50 | 2010 |
| Number of midwives and/or nurses contracted to work in the targeted areas |  |  | DDDS | N/A | 2006 | 100 | 2010 |
| Percentage of the state budget allocated to the health sector | State Budget allocated to the health sector | State Budget | Budget act/MINSANPFPS/DEP | 8,74% | 2005 | 10,00 | 2010 |
| Percentage of births taken place in the health care facilities in the targeted areas | Number of births taken place in the health care facilities | Total number of births | SSSa | 23% | 2004 | 30% | 2010 |
| Rate of post-natal consultations as a percentage of the number of births in the CSBs in the targeted areas | Number of post-natal consultations | Number of births in the CSBs | Statistics yearbook of the Madagascan health sector 2004 | 72.5% | 2004 | 85% | 2010 |

## 6.2.2: Process Indicators

|  |  | Indicator | Numerator | Denominator | Source | Baseline value | Source | Baseline date | Objective | Objective date |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Objective 1 | Strengthen the provision of quality health services to the entire population |  |  |  |  |  |  |  |  |  |
| Activity 1.1 | Contract health-care workers in the marginalised health care facilities | Percentage of health-care workers contracted | Number of workers contracted | Planned number of workers to be contracted | Contracts signed and registered by the partner service and the DDDS | 0 | n/a | 2007 | 50 physicians and 100 midwives and or nurses | 2010 |
| Activity 1.2 | Identify the factors (geographical, financial and cultural) that limit the use of the services through field research | Existence of an assessment and protocol report on piloting strategies | n/a | n/a | Report supplied by the DDDS | n/a | n/a | n/a | n/a | 2008 |
| Activity 1.3 | Pilot strategies in around 5 SSDs aimed at increasing the use of the services based on the results of the assessment study (see activity 1.2) | Identification of strategies that have contributed to an increase in the use of the services | n/a | n/a | Report supplied by the DDDS | n/a | n/a | n/a | n/a | 2009 |
| Activity 1.4 | Carry out renovations (painting, purchase of furniture for receiving patients, roofing, ceiling etc.) 15 CSBs per year with the aim of improving their physical appearance and making them more welcoming to patients. | Percentage of CSBs renovated from the planned 45 | Number of CSBs | 45 | Written receipt of the works and the works assessment reports, obtained from the DRSPF and the DDDS | 0 | n/a | 2007 | 45 | 2010 |
| Activity 1.5 | Head-up PTA ratification missions: the central team of the ministry and partners will be deployed in the regions and will ratify the PTA in the field, instead of having the PTA sent to them centrally. | Percentage of the PTA ratified before the year end each year | Number of PTAs ratified before the year end each year | 133 (111 districts + 22 regions) per year | Ratification mission report – DGS/DDS and regions | 79% | Mission report. DGS/DDDS | 2007 | 100% | 2008, 2009, 2010 |
| Activity 1.6 | Equip 10 SSDs with a 4x4 vehicle, the centre supervisors with 2 vehicles and 120 CSBs with motor bikes | Percentage of SSDs and CSBs equipped with 4x4s and motor bikes | Number of CSBs and CSBs equipped with 4x4s and motor bikes | 132 (10 SSD + 2 centres and 120 CSB) | Acknowledgement receipts and invoices supplied by the coordination team of HSS activities | 0 | DGS/DDDS | 2007 | 100% | 2008 |
|  |  | Percentage of SSDs and CSBs with functional vehicles | Number of SSDs and CSBs with functional vehicles | 132 (10 SSD + 2 centres and 120 CSB) | Usage reports and maintenance and fuel invoices submitted by the supervising physician and the head physician of the CSB | 0 | DGS/DDDS | 2007 | 100% | 2009, 2010 |
| Activity 1.7 | Introduce different strategies for increasing the population’s financial accessibility to health-care services in 5 SSDs: Mutual health organisation system | Identification of strategies that have contributed to an increase in access to funding | n/a | n/a | Report supplied by the DGS/DDDS | n/a | n/a | n/a | n/a | 2010 |

| Objective 2 | Improve human resources management of the health sector |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Activity 2.1 | Contracting activities (see 1.1) | Percentage of workers contracted | Number of workers contracted | Planned number of workers to be contracted | Contracts signed and registered by the partner service and the DGS/DDDS | 0 | n/a | 2007 | 50 physicians and 100 midwives and or nurses | 2010 |
| Objective 3 | Increase the mobilisation and allocation of financial resources |  |  |  |  |  |  |  |  |  |
| Activity 3.1 | Offer training on financial and programme management to the managers on the periphery of the targeted districts | Percentage of managers trained | Number of managers trained | Total number of managers | Training report. Attendance sheet. DGS/DDDS | 0 | DGS/DDDS | 2007 | 100% | 2008 |
| Activity 3.2 | Strengthen the application of the Equity Funds and mutual health organisation system implementation plan in the targeted health care facilities (see also activity 4.5) | Existence of a strengthening plan for the equity funds |  |  | DGS/DDDS |  |  |  |  |  |
| Activity 3.3 | Carry out financial auditing and supervision of the priority health-care activities with the PEV as top priority (focused on the continuation of child and maternal care) in the targeted areas and develop corrective strategies for improving the programme management. | Percentage of health care facilities that have undergone an audit and monitoring | Number of health care facilities audited | Total number of health care facilities | Audit reports supplied by the EMAR (regional management team) and the DGS/DDDS | 0 | DGS/DDDS | 2002 | 100% | 2010 |
|  |  | List of corrective strategies on a national scale |  |  | Analysis and consolidation of the audit reports by the DGS/DDS |  |  |  |  | 2010 |
|  |  | Implementation guide of the corrective strategies |  |  |  |  |  |  |  | 2010 |
| Objective 4 | Stimulate demand and use of the health services |  |  |  |  |  |  |  |  |  |
| Activity 4.1 | Carry out a regional mapping of the NGOs and associations working at a community level | List of NGOs and associations working at a community level in each region |  |  | DGS/DDDS |  |  |  |  | 2008 |
| Activity 4.2 | Convene 3 meetings per year with 160 local authorities in the targeted areas. | Percentage of meetings held in each local authority per year | Number of authorities in which 3 meetings have been held | 160 | Meeting minutes supplied by SSD | 0 |  | 2007 | 100% | 2008, 2009, 2010 |
| Activity 4.3 | Convene meetings for drafting policy documents establishing community health strategies (including Reference Terms and a Minimum Activity Package (PMA)) | Existence of a community health policy |  |  | DGS/DDDS |  |  |  |  | 2008 |
| Activity 4.4 | Provide training for community health-care workers in PCA in 40 targeted SSDs. This training includes the provision of an IEC PEV kit including IEC aids, guides, supplies and management tools. | Percentage of community health-care workers trained | Number of community health-care workers trained | Total number of community health-care workers approved by the HSS = 1200 | Training report. Attendance sheet. DGS/DDDS | 0 |  | 2007 | 100% | 2008 |

| Activity 4.5 | Strengthen the application of the Equity Funds and mutual health organisation system implementation plan in the targeted health care facilities (see also activity 3.2) | Existence of a strengthening plan for the equity funds |  |  | DGS/DDDS |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Objective 5 | Strengthen and institutionalise a monitoring and evaluation system |  |  |  |  |  |  |  |  |  |
| Activity 5.1 | Provide training for health-care workers on the benefits and use of data for planning and decision-making in the targeted areas. | Percentage of health-care workers trained | Percentage of health-care workers trained | Total number of health-care workers in the targeted areas = 640 | Training report. Attendance sheet. SSD and DDDS | 0 |  | 2007 | 100% | 2008 |
| Activity 5.2 | Assess the health data transfer performance of the CSBs on a central level in order to identify bottlenecks | Assessment report identifying the bottlenecks |  |  | DGS/DDDS | 0 |  | 2007 | 100% | 2008, 2009, 2010 |
| Activity 5.3 | Carry out regular follow-up and supervisory reviews of the CSBs | Percentage of CSBs having undergone 4 reviews per year | Number of CSBs having undergone 4 reviews per year | Total number of CSBs = 600 | SSD | 0 |  | 2007 | 100% | 2008, 2009, 2010 |
| Activity 5.4 | Support coaching in the targeted areas | Percentage of regions and SSDs that have undergone coaching | Number of SSDs and regions visited 4 times per year | 50 (10 regions and 40 SSDs) | DGS/DDDS | 0 |  | 2007 | 100% | 2008, 2009, 2010 |
|  | Procurement of IT material (including ink, disks etc.) for 40 SSDs | Percentage of SSDs targeted by HSS GAVI that have received IT material | Number of SSDs that have received IT material | 40 | Invoices and acknowledgement receipts of the material, obtained from the DRSPF and the CGS/DDS | 0 |  | 2007 | 100% | 2008 |

To the applicant

- Please describe how the data will be collected, analyzed and used. Existing data collection and analysis methods should be used wherever possible. Please indicate how data will be used at local levels and ways of sharing with other stakeholders in the last column (Table 6.3).

6.3: Data collection, analysis and use

The data will be available directly by the DGS/DDDS (to be more precise, by the HSS GAVI team) where they will be collected from the CSBs, SSDs, Regions, Immunisation Service, Health Statistics Service, the Human Resources Management and the Demographic Health Survey. The table below shows which indicators are related to which organisation.

| Organisation | Indicators |
| --- | --- |
| DGS/DDDS (HSS GAVI TEAM) | Activity 1.1 Number of health-care workers contracted Activity 1.2 Existence of an assessment and protocol report on piloting the strategies (Report drafter by a consultant under the supervision of the DGS/DDDS) Activity 1.3 Identification of strategies that have contributed to an increase in the use of the service (Report drafted by a consultant under the supervision of the DGS/DDDS) Activity 1.6 Percentage of SSDs and CSBs equipped with 4x4s and motor bikes Identification of strategies that have contributed to the increase in access to funding (Report drafted by a consultant under the supervision of the DGS/DDDS) Activity 3.1 Percentage of managers who have received financial and computer training Activities 3.2 and 4.5: Existence of a strengthening plan for the equity funds (Report drafted by a consultant under the supervision of the DGS/DDDS) Activity 3.3: Percentage of health care facilities that have undergone an audit and monitoring Activity 3.3 List of corrective strategies on a national scale (Report drafted by a consultant under the supervision of the DGS/DDDS) Activity 4.1: List of NGOs and association working at a community level in each of the targeted regions (Report drafted by a consultant under the supervision of the DGS/DDDS) Activity 4.3: Existence of a community health policy (Report drafted by a consultant under the supervision of the DGS/DDDS) Activity 5.1: Percentage of health-care workers that have been trained on the benefits and use of data for planning and decision-making. Activity 5.2: Evaluation report identifying the bottlenecks in health data transfer from the CSB to central government (Report drafted by a consultant under the supervision of the DGS/DDDS) Activity 5.4: Percentage of regions and SSDs that have undergone coaching |
| CSB | Activity 1.6: Percentage of CSBs equipped with motor bikes |
| SSD | Activity 1.6: Percentage of CSBs renovated from the planned 45 Activity 1.4: Percentage of SSDs equipped with 4x4s Activity 5.1: Percentage of health-care workers that have been trained on the benefits and use of data for planning and decision-making. Activity 5.3: Percentage of CSBs having undergone 4 reviews per year Activity 5.4: Percentage of SSDs targeted by HSS GAVI that have received IT material |
| Regions | Activity 1.6: Percentage of CSBs renovated from the planned 45 Activity 3.3: Percentage of health care facilities audited |
| Immunisation Service | Impact indicator 1: National DTP3 coverage (%) Impact indicator 2: Number / % of districts achieving ≥80% DTP3 coverage |
| Health Statistics Service | Usage rate of the CSB external consultations in the targeted areas Percentage of births assisted by qualified personnel in the targeted areas Rate of post-natal consultations as a percentage of the number of births in the CSBs in the targeted areas |
| Human resources Management | Percentage of physicians affected on a decentralised level as well as physicians contracted |
| INSTAT (the Ministry of Health and the Ministry of Finances) | Health expenditure per capita ($US) |
| Demographic Health Survey | Impact indicator 3: Under five mortality rate Impact indicator 4: Infant and child mortality rate (per 1000) |

The data collected will be handled, analysed and consolidated by the GAVI HSS coordinator and assistant coordinator every 3 months in the indicator evolution reports. These reports will be submitted to the DGS/DDDS, the DEP, and the Immunisation Service for preliminary approval. Final ratification of these indicators will be carried by the HSCC.

The indicator evolution reports will be then disseminated to the regions and districts through the quarterly bulletin from the Ministry and the retro-information reports. The dissemination of this data out-side the Government will be carried out via the meetings with the HSCC, with the help of the partners, civil society and the NGOs.

To the applicant

- Please indicate if the M&E system needs to be strengthened to measure the listed indicators and if so describe which indicators specifically need strengthening. (Table 6.4).

- Please indicate if the GAVI HSS application includes elements of operational research that address some of the health systems barriers to better inform the decision making processes or health outcome. (Table 6.5).

## 6.4: Strengthening M&E system

The indicators that have been selected for each activity are the measurable indicators and therefore those that the health system can provide. In order to gather, consolidate and analyse the data for monitoring GAVI HSS, a coordinator, assistant and secretary have been appointed to work in the DGS/DDDS. However, problems relating to the monitoring and evaluating system have been identified, and whether these take the form of available skills or of an information transfer system, and activities have been planned to respond to these barriers: Activity 3.1: Offer training on financial and programme management to the managers on the periphery of the targeted districts Activity 4.2: Hold 3 meeting a year with the local authorities (45) for review of the targeted areas within the framework of the community health policy. Activity 5.1: Provide training for health-care workers on the benefits and use of data for planning and decision-making in the targeted areas. Activity 5.2 : Assessment of the health data transfer performance of the CSBs on a central level in order to identify bottlenecks Activity 5.3: Carry out regular follow-up and supervisory reviews of the CSBs Activity 5.4: Support coaching in the targeted areas

## 6.5: Operational Research

Several studies have been planned as part of this application in order to identify the bottlenecks in certain areas and also for being better equipped to target and direct the health strategies. The planned studies will be carried out as per the following activities: Activity 1.2: Identify the factors (geographical, financial and cultural) that limit the use of the services through field research Activity 1.7 : Introduce different strategies for increasing the population’s financial accessibility to health-care services in 5 SSDs per year: 1) Mutual health organisation system; Activities 3.2 and 4.5: Strengthen the application of the Equity Funds and mutual health organisation system implementation plan in the targeted health care facilities Activity 5.2: Assessment of the health data transfer performance of the CSBs on a central level in order to identify bottlenecks

# Section 7: Implementation Arrangements

To the applicant

- Please describe how the GAVI HSS support will be managed (Table 7.1).  Please also indicate the roles and responsibilities of all key partners in GAVI HSS implementation (Table 7.2).

Note: GAVI encourages aligning GAVI HSS with existing country mechanisms. Applicants are strongly discouraged from establishing a project management unit (PMU) for GAVI HSS. Support for PMUs will only be considered under exceptional circumstances, based on a strong rationale.

## 7.1: Management of GAVI HSS support

| Management mechanism | Description |
| --- | --- |
| Name of lead individual / unit responsible for managing GAVI HSS implementation / M&E etc. | Implementation of the GAVI activities will be led by the DGS/DDDS Given the large number of activities proposed and therefore the import extra work load involved in monitoring the implementation of these activities, it will be necessary to assign a coordinator, an assistant and a full time secretary. |
| Role of HSCC (or equivalent) in implementation of GAVI HSS and M&E | Implementation plans for GAVI funding Approval of the annual action plans of the activities financed by GAVI Monitoring of GAVI funding usage. |
| Mechanism for coordinating GAVI HSS with other system activities and programs | The implementation of the GAVI activities will be carried out mainly by the DDDS and in collaboration with the partners. The coordination will be carried out via regular meetings with the HSCC and through SWAp (which DGS is involved in) In its management and supervisory role, the DDDS will be up to speed on the other activities and programmes in place in the districts and will assure the coordination of activities with the DGS |

## 7.2: Roles and responsibilities of key partners (HSCC members and others)

| Title / Post | Organisation | HSCC member yes/no | Roles and responsibilities of this partner in the GAVI HSS implementation |
| --- | --- | --- | --- |
| Mr Robert BLAKE Country Manager | World Bank | Yes | Consultation and technical support Participation in the field during the supervision, coaching and monitoring activities Quarterly follow-ups of the activities and budget |
| Dr Léonard Tapsoba WHO Representative for Madagascar and Réunion. | WHO | Yes | Consultation and technical support Establishing contracts with the international consultants (to be determined) Quarterly follow-ups of the activities and budget |
| Mr Bruno Maes Resident Representative of UNICEF | UNICEF | Yes | Consultation and technical support Participation in the field during the supervision, coaching and monitoring activities Establishing contracts with the international consultants (to be determined) Quarterly follow-ups of the activities and budget |
| Mme Wendy Benazerga Director of the Nutrition and Population Health Bureau | USAID | Yes | Consultation and technical support (the activities in objective 4 in particular) Participation in the field during the supervision, coaching and monitoring activities Establishing contracts with the international consultants (to be determined) Quarterly follow-ups of the activities and budget |
| TOGAWA Toru Resident Representative of JICA Madagascar | JICA | Yes | Consultation and technical support Quarterly follow-ups of the activities and budget |
| Dr VOLKAN Cakir Director of the Santé Net programme | Santé Net | Yes | Consultation and technical support (the activities in objective 4 in particular) Participation in the field during the supervision, coaching and monitoring activities Establishing contracts with the international consultants (to be determined) Quarterly follow-ups of the activities and budget |
| Mr Castaing Denis Director of AFD Madagascar | Agence Française de Développement (French Development Agency) | Yes | Consultation and technical support Quarterly follow-ups of the activities and budget |
| Dr Ralaivita Mamy Representative of SALFA | SALFA | Yes | Consultation and technical support (the activities in objective 4 in particular) Participation in activities 1.1, 4.3, 4.4 Quarterly follow-ups of the activities and budget |
| M Grégoire Detoeuf | Raoul Follereau Foundation | Yes | Participation in the field during the supervision, coaching and monitoring activities Quarterly follow-ups of the activities and budget |
| Dr Rakotovao Ravahatra Kalory President of l’Ordre National des Médecins (the National Order of Doctors) | Civil Society | Yes | Participation in activity 1.1 Quarterly follow-ups of the activities and budget |

To the applicant

- Please give the financial management arrangements for GAVI HSS support. GAVI encourages funds to be managed ‘on-budget’. Please describe how this will be achieved (Table 7.3).

- Please describe any procurement mechanisms that will be used for GAVI HSS (Table 7.4).

## 7.3: Financial management of GAVI HSS support

| Mechanism / procedure | Description |
| --- | --- |
| Mechanism for channelling GAVI HSS funds into the country | The funds will be transferred from an HSS open account by the DGS/DDDS (with a letter of approval from UNICEF) to a National bank specifically for HSS GAVI support of Madagascar |
| Mechanism for channelling GAVI HSS funds from central level to the periphery | The funds will be transferred via bank transfer to the accounts of the Regional Health Directorate of the District after the planning stage of the health activities have been ratified by the Coordinating Committee of the health sector |
| Mechanism (and responsibility) for budget use and approval | The budget and the plans must be validated and ratified by the HSCC. The structures in receipt of the funds will produce quarterly reports of the activities and financial reports of the funds received. The health structure receiving HSS GAVI support may not receive follow-up funds without being able to account for the funds previously received. These reports will be completed via the financial assessment and monitoring of the specialised central teams. The Ministry of Health, family Planning and Social Welfare will compile these financial activity reports, via the DGS, the DEP and the Directorate for District Health Development (DDDS) in order to send them to GAVI in the established timeframes. |
| Mechanism for disbursement of GAVI HSS funds | 3 co-signers of the cheques (the Director General for Health (DGS), the Director of the PEV and the Director of the DEP) |
| Auditing procedures | The use of the funds will be verified internally by the Directorate of Administrative and Financial Affairs of the Ministry of Health, Family Planning and Social Welfare and on a peripheral level by the financial audits carried out by the specialist bureaus that have been chosen through an international call for tender. |

## 7.4: Procurement mechanisms

The procurement mechanism that will be used will respect the purchasing procedures of goods and services set out in the new code in effect on public Markets and will have recourse to UNICEF for the procurement of certain goods if this is not the case or if this approach carries significant advantages.

To the applicant

- Please describe arrangements for reporting on the progress in implementing and using GAVI HSS funds, including the responsible entity for preparing the APR. (Table 7.5)

Note: The GAVI Annual Progress Report, due annually on 15 May, should demonstrate: proof of appropriate accountability for use of GAVI HSS funds, financial audit and proper procurement (in line with national regulations or via UNICEF); efficient and effective disbursement (from national to sub-national levels; in the context of a SWAp mechanism, if applicable); and evidence on progress on whether expected annual output targets and longer term outcome targets are being achieved.

## 7.5: Reporting arrangements

The data collected will be handled, analysed and consolidated by the GAVI HSS coordinator and assistant coordinator every 3 months in the indicator evolution reports. These reports will be submitted to the DGS/DDDS, the DEP, and the Immunisation Service for preliminary approval. Final ratification of these indicators will be carried by the HSCC.

The indicator evolution reports will be then disseminated to the regions and districts through the quarterly bulletin from the Ministry and the retro-information reports. The dissemination of this data out-side the Government will be carried out via the meetings with the HSCC, with the help of the partners, civil society and the NGOs.

To the applicant

- Some countries will require technical assistance to implement GAVI HSS support. Please identify what technical assistance will be required during the life of GAVI HSS support, as well as the anticipated source of technical assistance if known (Table 7.6).

## 7.6: Technical assistance requirements

| Activities requiring technical assistance | Anticipated duration | Anticipated timing (year, quarter) | Anticipated source (local, partner etc.) |
| --- | --- | --- | --- |
| Activity 1.2: Identify the factors that limit the use of the services Assistance type: International consultation | 5 weeks | Q3 and Q4 in 2008 | Information not available |
| Activity 1.3: Pilot strategies in around 5 SSDs aimed at increasing the use of the services. Assistance type: International consultation | 6 weeks from the start of the activities | Q1 to Q4 in 2008 | Information not available |
| Activity 1.7: Introduce different strategies for increasing the population’s financial accessibility to health-care services in 5 SSDs per year. Assistance type: International consultation | 6 weeks from the start of the activities | Q3 and Q4 in 2008 | Information not available |

# Section 8: Costs and Funding for GAVI HSS

To the applicant

- Please calculate the costs of all activities for the duration of the GAVI HSS support. Please add or delete rows / columns to give the right number of objectives, activities and years. (Table 8.1)

Note: Please ensure that all support costs for management, M&E, and technical assistance are included. Please convert all costs to US$ (at the current exchange rate), and ensure that GAVI deflators are used for future costs (see guidelines on the GAVI website: www.gavialliance.org).

Note: The overall total request for GAVI HSS funds in table 8.1 should not exceed the overall total of GAVI HSS funds allocated in table 8.2. Funds may be requested in annual trenches according to estimated annual activity costs. These may vary annually from the allocation figures in table 8.2.

## 8.1: Cost of implementing GAVI HSS activities

|  |  | 2007 | 2008 | 2009 | 2010 | Total |
| --- | --- | --- | --- | --- | --- | --- |
| Cost of the activities |  |  |  |  |  |  |
| Objective 1 | Strengthen the provision of quality health services to the entire population | 0.0 | 1,988,013.3 | 2,549,787.7 | 2,505,940.1 | 7,043,741.2 |
| Activity 1.1 | Contract health-care workers in the marginalised health care facilities |  | 423,885.0 | 466,273.5 | 512,900.9 | 1,403,059.4 |
| Activity 1.2 | Identify the factors (geographical, financial and cultural) that limit the use of the services through field research |  | 162,531.6 |  |  | 162,531.6 |
| Activity 1.3 | Pilot strategies in around 5 SSDs aimed at increasing the use of the services based on the results of the assessment study (see activity 1.2) |  |  | 79,149.2 |  | 79,149.2 |
| Activity 1.4 | Carry out renovations (painting, purchase of furniture for receiving patients, roofing, ceiling etc.) 15 CSBs per year with the aim of improving their physical appearance and making them more welcoming to patients. |  | 499,702.5 | 1,099,345.5 | 1,708,982.6 | 3,308,030.6 |
| Activity 1.5 | Head-up PTA ratification missions: the central team of the ministry and partners will be deployed in the regions and will ratify the PTA in the field, instead of having the PTA sent to them centrally. |  | 69,520.0 | 76,472.0 | 84,119.2 | 230,111.2 |
| Activity 1.6 | Equip 10 SSDs with a 4x4 vehicle, the centre supervisors with 2 vehicles and 120 CSBs with motor bikes. |  | 753,225.0 | 828,547.5 | 120,788.3 | 1,702,560.8 |
| Activity 1.7 | Introduce different strategies for increasing the population’s financial accessibility to health-care services in 5 SSDs: 1) Mutual health organisation system; 2) Strengthening of the equity funds system |  | 79,149.2 |  | 79,149.2 | 158,298.5 |
| Objective 2 | Improve human resources management of the health sector |  |  |  |  |  |
| Activity 2.1 | Contracting activities (see 1.1) | see activity 1.1 | see activity 1.1 | see activity 1.1 | see activity 1.1 | see activity 1.1 |
| Objective 3 | Increase the mobilisation and allocation of financial resources | 276,514.3 | 472,335.6 | 519,569.2 | 576,577.2 | 1,844,996.3 |
| Activity 3.1 | Offer training on financial and programme management to the managers on the periphery of the targeted districts | 276,514.3 |  |  |  | 276,514.3 |
| Activity 3.2 | Strengthen the application of the Equity Funds and mutual health organisation system implementation plan in the targeted health care facilities (see also activity 4.5) |  | see activity 4.5 |  |  |  |
| Activity 3.3 | Carry out financial auditing and supervision of the priority health-care activities with the PEV as top priority (focused on the continuation of mother and child care) in the targeted areas and develop corrective strategies for improving the programme management. |  | 472,335.6 | 519,569.2 | 576,577.2 | 1,568,482.0 |
| Objective 4 | Stimulate demand and use of the health services | 241,017.5 | 263,948.4 | 120,548.7 | 132,603.5 | 758,118.1 |
| Activity 4.1 | Carry out a regional mapping of the NGOs and associations working at a community level |  | 64,892.3 |  |  | 64,892.3 |
| Activity 4.2 | Convene 3 meetings per year with 100 local authorities in the targeted areas. |  | 109,589.7 | 120,548.7 | 132,603.5 | 362,741.9 |
| Activity 4.3 | Convene meetings for drafting policy documents establishing community health strategies (including Reference Terms and a Minimum Activity Package (PMA)) |  | 66,597.4 |  |  | 66,597.4 |
| Activity 4.4 | Provide training for community health-care workers in PCA in 40 targeted SSDs. This training includes the provision of an IEC PEV kit including IEC aids, guides, supplies and management tools. | 241,017.5 |  |  |  | 241,017.5 |
| Activity 4.5 | Strengthen the application of the Equity Funds and mutual health organisation system implementation plan in the targeted health care facilities (see also activity 3.2) |  | 22,869.0 |  |  | 22,869.0 |
| Objective 5 | Strengthen and institutionalise a monitoring and evaluation system | 195,507.9 | 619,524.1 | 185,355.8 | 255,329.1 | 1,255,716.9 |
| Activity 5.1 | Provide training for health-care workers on the benefits and use of data for planning and decision-making in the targeted areas. | 195,507.9 | 456,185.0 | 0.0 | 0.0 | 651,692.9 |
| Activity 5.2 | Assess the health data transfer performance of the CSBs on a central level in order to identify bottlenecks | 0.0 | 9,223.8 | 9,223.8 | 9,223.8 | 27,671.5 |
| Activity 5.3 | Carry out regular follow-up and supervisory reviews of the CSBs | 0.0 | 87,120.0 | 95,832.0 | 105,415.2 | 288,367.2 |
| Activity 5.4 | Support coaching in the targeted areas (2 deployments per year) |  | 66,995.3 | 80,300.0 | 140,690.1 | 287,985.4 |
|  | Total cost of the activities | 713,039.7 | 3,343,821.5 | 3,375,261.4 | 3,470,450.0 | 10,902,572.5 |
| Cost of the support |  |  |  |  |  |  |
|  | Management costs | 97,475.9 | 65,123.9 | 71,636.2 | 78,799.9 | 313,035.8 |
|  | Total cost of the support | 97,475.9 | 65,123.9 | 71,636.2 | 78,799.9 | 313,035.8 |
| TOTAL |  | 810,515.5 | 3,408,945.3 | 3,446,897.6 | 3,549,249.8 | 11,215,608.4 |

A more detailed version of the budget is available in annex 4. The list of unit costs used for drafting the budget is available in annex 5.

To the applicant

- Please calculate the amount of funds available per year from GAVI for the proposed GAVI HSS activities, based on the annual number of births and GNI per capita as follows (Table 8.2):

- If GNI < $365 per capita, country is eligible to receive up to $5 per capita

- If GNI > $365 per capita, country is eligible to receive up to $2.5 per capita

Note: The following example assumes the birth cohort in the year of GAVI application is 100,000, and gives the total fund allocations if the GNI < $365 per capita and if the GNI > $365 per capita.

## 8.2: Calculation of GAVI HSS country allocation

|  | Allocation per year (US$) |
| --- | --- |
| GAVI HSS Allocation | Q4 of implementation | Year 2 of implementation | Year 3 of implementation | Year 4 of implementation | TOTAL FUNDS |
|  | 2007 | 2008 | 2009 | 2010 |  |
| Birth cohort | 655 882 | 674 247 | 693 126 | 712 533 |  |
| Allocation per newborn | $5 | $5 | $5 | $5 |  |
| Annual allocation | 819,852.5 | 3 371 235 | 3 465 630 | 3 562 665 | 11 219 382,5 |

Source and date of GNI and birth cohort information:

GNI per capita: Ministère des Finances et du Budget, 2005

Birth cohort: Plan Pluri Annuel Complet du PEV/ Madagascar (PPAC)

To the applicant:

Note: Table 8.3 is not a compulsory table.

- Please endeavour to identify the total amount of all expected health system strengthening related spending in the country during the life of the GAVI HSS application (Table 8.3).

Note: Please specify the contributions from the Government, GAVI and the main funding partners or agencies. If there are more than four main contributors, please insert more rows. Please indicate the names of the partners in the table, and group together all remaining expected contributions.  Please indicate the source of the data (Public Expenditure Review, MTEF, donor reports etc).

## 8.3: Sources of all expected funding for health systems strengthening activities

Source of information on funding sources:

MINISTRY OF HEALTH, FAMILY PLANNING AND SOCIAL WELFARE. Health Sector Development Plan 2007-2011.

Note: The financing planned from IDA has been reviewed at source following the last mission of the World Bank on April 5th 2007; it is for this reason that the figure is different to that in the PDSS.

# Section 9: Endorsement of the Application

To the applicant:

- Representatives of the Ministry of Health and Ministry of Finance, and the Chair of the Health Sector Coordinating Committee (HSCC), or equivalent, should sign the GAVI HSS application.

- All HSCC members should sign the minutes of the meeting where the GAVI HSS application was endorsed. This should be submitted with the application (numbered and listed in Annex 1).

- Please give the name and contact details of the person for GAVI to contact if there are queries.

Note: The signature of HSCC members represents their agreement with the information and plans provided in this application, as well as their support for the implementation of the plans. It does not imply any financial or legal commitment on the part of the partner agency or individual.

## 9.1: Government endorsement

The Government of Madagascar commits itself to providing immunisation and other child and maternal health services on a sustainable basis. Performance on strengthening health systems will be reviewed annually through a transparent monitoring system. The Government requests that the GAVI Alliance funding partners contribute financial assistance to support the strengthening of health systems as outlined in this application.

| Ministry of Health: | Ministry of Finance: |
| --- | --- |
| First Name: Robinson Last Name: JEAN LOUIS | First Name: Andriamparany Benjamin Last Name: RADAVIDSON |
| Title / Post: Minister of Health, Family Planning and Social Welfare | Title / Post: Ministry of Finance |
| Signature: | Signature: |
| Date: | Date: |

## 9.2: Endorsement by Health Sector Coordination Committee (HSCC) or country equivalent

Members of the Health Sector Coordination Committee or equivalent endorsed this application at a meeting on 12 April 2007 the signed minutes are attached as Annex 1.

| Chair of HSCC (or equivalent): |  |
| --- | --- |
| Name: Dr RAHANTANIRINA Marie Perline | Post / Organisation: Deputy Minister of Health, Family Planning and Social Welfare |
| Signature: | Date: |

9.3: Person to contact in case of enquiries:

Name: Dr Rasolomahefa Dieudonné Hubert

Title: Director General of Health

Tel No:

22 236 97 (office)

032 04 956 55 (mobile)

Address: Ministère  de la Santé, du Planning Familial et de la Protection Sociale

Ambohidahy BP 88

Antananarivo 101, Madagascar

Email: dgs@sante.gov.mg

# ANNEX 1 Documents Submitted in Support of the GAVI HSS Application

To the applicant:

- Please number and list in the table below all the documents submitted with this application.

Note: All supporting documentation should be available in English or French, as electronic copies wherever possible. Only documents specifically referred to in the application should be submitted.

| Document (with equivalent name used in-country) | Available (Yes/No) | Duration | Attachment Number |
| --- | --- | --- | --- |
| National Health Sector Strategic Plan Plan De Développement du Secteur Santé (PDSS) | Yes | 2007-2011 | 1 |
| cMYP Plan Pluri Annuel Complet | Yes | 2007-2011 | 2 |
| MTEF Cadre de Dépenses à Moyen Terme | Yes | 2006-2008 | 3 |
| PRSP8 Document de Stratégie de Réduction de la Pauvreté (DSRP) Madagascar Action Plan (MAP) | Yes | 2007-2011 | 4 5 |
| Recent Health Sector Assessment documents |  |  |  |
| Banque Africaine de Développement (BAD) (African Development bank ADB). Rapport de mission (Mission report). Consultante en formation et suivi évaluation (Training and monitoring and evaluation consultation). 2007 | Yes |  | 6 |
| DRSPD/GTZ/KfW. Introduction de l'Approche Quality Management par le biais du concours qualité (COQ) au niveau des CSB de la zone d'intervention du projet (Introduction to the Quality Management Approach through cost of quality COQ in the CSBs in the intervention areas of the project). 2006 | Yes |  | 7 |
| JSI and RTI. Rapport final (Final report). Projet d'appui à la mise en œuvre des plans de développement des districts sanitaires zone sud (Support project for the implementation of the development plans of the health districts in the southern area): Antananarivo, Fianarantsoa, Toliara. 2004 | Yes |  | 8 |
| Département du développement humain (Department of Human Development). Région Afrique (African Region). Banque Mondiale (World Bank). L’Efficience et l’Equité des Formations Sanitaires Malgaches (Efficiency and Fairness of the Madagascan Health Care Facilities). 2005 | Yes |  | 9 |
| Dubois, Carl-Ardy ; Boivin, Suzanne ; Albert, Lucien. Elaboraten du Plan de Développement des Ressources Humaines pour le Secteur Santé (Drafting of the Human Resources Development Plan for the health sector). Rapport préliminaire (Preliminary report). Mai 2006 (May 2006) | Yes |  | 10 |
| INSTAT, Enquête Permanente auprès des Ménages (EPM) (Permanent Household Survey) | Yes |  | 11 |
| HSCC minutes, signed by Chair of HSCC HSCC meeting report, signed by the chairman of the meeting | Yes |  | 12 |

# ANNEX 3 Criteria for choosing the SSDs to receive HSS GAVI support

The selection criteria used for choosing the 40 SSDs targeted by the HSS GAVI activities are:

- Immunisation (all Antigens combined) coverage rates les than 75%

- Proportion of the population serviced: above 75000 inhabitants in general in the District Health Service

- Geographical access difficulties (certain districts that have a population of less than 75,000 have been included in the proposal due to their geographical isolation and difficulty of access)

- Poor performance and self-efficacy of the SSDs (service use, skills of the EMAD, availability of resources etc.)

| No. | REGION | SSD | Immunisation coverage rate | Total population** | Isolation/marginalisation** | Performance (score out of 35)** |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Anosy | Taolagnaro | 28,9% | 242 793 | + | 22 |
| 2 |  | Betroka | 21,6% | 153 427 | ++ | 17 |
| 3 |  | Amboasary- Sud | 49,9% | 172 182 | ++ | 12 |
| 4 | Androy | Ambovombe | 17,6% | 209 168 | ++ | 19 |
| 5 |  | Tsihombe | 21,5% | 73 880 | ++ | 20 |
| 6 |  | Beloha | 37,2% | 72528 | ++ | 26 |
| 7 |  | Bekily | 15,3% | 142 035 | ++ | 17 |
| 8 | Atsinanana | Mahanoro | 9,8% | 233 732 | ++ | 18 |
| 9 |  | Antanambao Manampotsy | 37,5% | 50 879 | +++ | 32 |
| 10 |  | Marolambo | 4,8% | 132 284 | +++ | 11 |
| 11 | Betsiboka | Tsaratanana | 22,0% | 110 097 | +++ | 12 |
| 12 |  | Kandreho | 5,5% | 13 403 | +++ | 11 |
| 13 | SAVA | Antalaha | 23,7% | 214 331 | ++ | 13 |
| 14 |  | Vohémar | 42,6% | 189 879 | ++ | 17 |
| 15 |  | Sambava | 38,3% | 273 188 | + | 15 |
| 16 | DIANA | Ambilobe | 47,0% | 161 685 | + | 22 |
| 17 |  | Antsiranana II | 55,2% | 82152 | + | 20 |
| 18 | SOFIA | Mampikony | 20,4% | 95 096 | ++ | 16 |
| 19 |  | Port- Bergé | 41,2% | 116 841 | ++ | 20 |
| 20 |  | Antsohihy | 16,7% | 121 404 | ++ | 10 |
| 21 |  | Mandritsara | 21,3% | 230 487 | ++ | 16 |
| 22 |  | Befandriana Avaratra | 26,8% | 190 950 | ++ | 18 |
| 23 |  | Analalava | 33,3% | 101 342 | ++ | 11 |
| 24 |  | Bealanana | 37,6% | 113 552 | ++ | 15 |
| 25 | Vatovavy Fitovinany | Vohipeno | 29,2% | 107 067 | + | 14 |
| 26 |  | Manakara | 35,7% | 255746 | + | 27 |
| 27 |  | Ifanadiana | 16,1% | 148 502 | + | 16 |
| 28 |  | Mananjary | 24,8% | 253 504 | + | 21 |
| 29 |  | Ikongo | 25,3% | 116 880 | +++ | 26 |
| 30 |  | Nosy Varika | 13,4% | 192 887 | +++ | 15 |
| 31 | Atsimo Andrefana | Toliara I | 48,5% | 115 734 | + | 28 |
| 32 |  | Toliara II | 52,6% | 209 762 | + | 25 |
| 33 |  | Betioky Atsimo | 23,1% | 188 068 | ++ | 19 |
| 34 |  | Ankazoabo Atsimo | 27,4% | 54 587 | ++ | 26 |
| 35 |  | Ampanihy | 22,4% | 233699 | ++ | 14 |
| 36 |  | Morombe | 38,9% | 110160 | + | 21 |
| 37 | Vakinankaratra | Faratsiho | 67,6% | 186 103 | ++ | 24 |
| 38 |  | Betafo | 35,3% | 339581 | + | 17 |
| 39 |  | Antanifotsy | 28,7% | 313769 | + | 16 |
| 40 |  | Antsirabe II | 38,8% | 375 948 | + | 20 |

Sources :	* Immunisation service, 2007, DDDS, 2007

**Directorate for the Development of Health Districts

# ANNEX 4 Detailed description of costs

|  |  | COST PER YEAR PER CATEGORY – Calculated in USD in 2006 (costs based on the unit costs as per annex 5) |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Explanatory notes | Salaries and rates | Per diems | Transport | Lodging | Supplies | Hire of teaching equipment and room, printing expenses | Data analysis and use | Surveys | Publications/disseminations | Equipment | Vehicle purchase | Fuel and maintenance for vehicles | Renovation | Total-2007 | Total-2008 | Total-2009 | Total-2010 |
| Activity 1.1 | processes + salaries up to 2010 50 physicians and 100 midwives and or nurses | 385350 |  |  |  |  |  |  |  |  |  |  |  |  |  | 423,885 | 466,274 | 512,901 |
| Activity 1.2 | National consultant: 8 weeks; International consultant:: 5 weeks (2 trips x 2 weeks: 5000 per air ticket + per diem); Data + survey analysis and use | 29200 | 2800 | 10056 | 4200 |  |  | 1000 | 100000 | 500 |  |  |  |  |  |  | 162,532 |  |
| Activity 1.3 | National consultant: 4 weeks per SSD=15 weeks. Transport of CSD coaches to the SSBs. International consultant: 6 weeks | 47000 |  | 3000 |  | 60 | 2500 | 1000 |  | 500 |  |  |  |  |  |  |  | 79,149 |
| Activity 1.4 | 3 monitoring and supervision visits per CSB = renovation of 15 CSBs per year |  | 900 | 11250 | 675 |  |  |  |  |  |  |  |  | 60,000 per CSB |  | 1,004,108 | 1,104,518 | 1,214,970 |
| Activity 1.5 | 7 days and 6 nights per region (22), 2 people per region |  | 6160 | 50000 | 6930 | 110 |  |  |  |  |  |  |  |  |  | 69,520 | 76,472 | 84,119 |
| Activity 1.6 | The cost also includes the maintenance and fuel costs for the duration of the project |  |  |  |  |  |  |  |  |  |  | 1350000 | 82500 |  |  | 916,575 | 1,008,233 | 120,788 |
| Activity 1.7 | Same estimation as for 1.3, multiplied by 1.5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 158,298 |
| Activity 2.1 | Already budgeted in activity 1.1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 3.1 | 2 training sessions of 1 week each. 2 people per region (44 people) and 2 people per district (230) = 274 trained. 2 trainers per province and 2 training sessions per province. Drivers = 1 per region (22) and 100 per district |  | 26436 | 128800 | 32205 | 822 | 600 |  |  |  |  |  |  |  |  |  |  | 276,514 |
| Activity 3.2 | Same as activity 4.5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 3.3 | 1 week per year per CSB 40 SSDs and 15 CSBs = 400 CSBs. 2 technicians, 1 administrator and 1 chauffeur per CSB |  | 147000 | 600000 | 82687.5 | 8400 |  |  |  |  |  |  |  |  |  | 1,014,086 | 1,115,494 | 1,227,044 |
|  | National consultant for 3 weeks for drafting the corrective strategy list at a national level. | 3450 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 5,051 |
| Activity 4.1 | 1 national consultant, 1.5 weeks per region. The cost includes transport and lodging | 53130 |  |  |  |  |  |  |  | 500.00 |  |  |  |  |  | 64,892 |  |  |
| Activity 4.2 | 15 people per meeting per local authority. Duration of the meetings = 1 day. District people go down to the communities. 40 districts are targeted. |  | 17970 | 96000 | 21600 | 7200 |  |  |  |  |  |  |  |  |  | 172,752 | 190,027 | 209,030 |
| Activity 4.3 | Consultation for drafting = 1 month. 2 workshops (presentation and ratification) and 2 days with 40 people (1 person per region) Who attends the meetings? | 4600 | 1968 | 44000 | 1320 | 480 | 240 |  |  | 500.00 |  |  |  |  | 19,473 | 47,124 |  |  |
| Activity 4.4 | 40 workshops (2.5 days) at the SSDs. 30 people per SSD. |  | 22880 | 7200 | 27000 | 120000 | 4000 |  |  |  |  |  |  |  |  |  | 241,017 |  |
| Activity 4.5 | National consultant for 4 months | 18400 |  |  |  |  |  |  |  | 500.00 |  |  |  |  |  | 22,869 |  |  |
| Activity 5.1 | 400 CSBs (1 person per CSB) + 40 districts (1 person per district) = 640 trained. 2 trainers (1 regional and 1 central) per workshop, 12 workshops of 23 days each Consultant for preparing the training (curriculum) = 3 weeks Preparation meeting (team building) | 3450 | 24408 | 646000 | 30150 | 1920 | 2,160.00 |  |  |  |  |  |  |  |  |  |  | 1,036,712 |
| Activity 5.2 | Use the same data as for equity funds |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 27,671 |
| Activity 5.3 | 2 days x quarter x SSD (40) – 600 head physicians of the CSBs go to the SSds, therefore 1 head physician per CSB 6 dollars = return journey |  | 57600 | 14400 | 36000 |  |  |  |  |  |  |  |  |  |  | 130,680 | 143,748 | 158,123 |
| Activity 5.4 | Coaching visits. 10 regions. 40 districts. Each SSD is visited 4 times per year for 3 days. 2 coaches per SSD. Note: Training of the coaches covered by the World Bank |  | 15360 | 40000 | 14400 |  |  |  |  |  |  |  |  |  |  | 84,410 | 92,851 | 102,136 |
|  | Procurement of IT material (including ink, disks etc.) for 40 SSDs |  |  |  |  | 17000 |  |  |  |  | 56000 |  |  |  | 80,300 | 20,570 | 22,627 | 24,890 |
|  | Includes coordinating and supervision missions in the districts (2 per year x 40 districts) and in the regions (2 per year x 10 regions) 2 days per mission | 14700 | 3000 | 6000 | 2250 | 16930 |  |  |  |  | 25,050.00 | 50,000.00 | 10505 |  | 97235.875 | 64595.85 | 71055.435 | 78160.9785 |
|  | Twice a year 20 people |  | 200 | 40 |  | 120 | 120 |  |  |  |  |  |  |  | 240 | 528 | 580.8 | 638.88 |

| ANNEX 5 List of unit costs used The inflation rate is 10%. |
| --- |
| Activities | Sub-heading | Unit | Unit cost (in USD, 2006) |
|  |  |  | Not blocked | Blocked | National |
| Training workshop | Per diem Participant | Per day | 10.00 | 12.00 |  |
|  | Per diem trainer | Per day | 14.00 | 16.00 |  |
|  | Per diem Administrator (training secretary etc.) | Per day | 5.00 | 6.00 |  |
|  | Per diem Drivers | Per day | 5.00 | 6.00 |  |
|  | Transport costs | Pu x distance (A/R) in km x 0.15 | 4.00 |  |  |
|  | Lodging | Per day |  | 15.00 |  |
|  | Lodging of drivers | Per day |  | 7.50 |  |
|  | Supplies | Per participant | 3.00 | 3.00 |  |
|  | Hire of teaching material | Per day | 20.00 | 20.00 |  |
|  | Room hire | Per day | 40.00 | 40.00 |  |
|  | Printing costs (organisation) | Per day | 5.00 | 5.00 |  |
| Survey/research/study | Per diem | Per day |  |  | 10.00 |
|  | Transport costs | Per day |  |  | 4.00 |
|  | Data analysis and use | Fixed cost |  |  | 1,000.00 |
|  | Publications/disseminations | Per 100 copies and organisation of a meeting |  |  | 500.00 |
| Technical expertise/assistance | Per diem – international consultant (including lodging) | Per day |  |  | 800.00 |
|  | National (includes per diem and lodging | Per day |  |  | 230.00 |
| Document drafting | DTP |  |  |  | 4.00 |
|  | Production of copies |  |  |  | 5.00 |
|  | Dissemination |  |  |  | 2.00 |
| IT equipment | PC + Printer + Power supply | Unit |  |  | 1,200.00 |
|  | Laptop | Unit |  |  | 1,700.00 |
|  | Scanner | Unit |  |  | 200.00 |
|  | OHP | Unit |  |  | 1,700.00 |
|  | Screen | Unit |  |  | 200.00 |
| IT consumables | Toner cartridge | Unit |  |  | 40.00 |
|  | Masters | Unit |  |  | 100.00 |
|  | Toner | Unit |  |  | 200.00 |
|  | Flash disk | Unit |  |  | 50.00 |
|  | CD R/W | Box of 10 rewritables |  |  | 15.00 |
|  | Diskettes | Box of 10 |  |  | 5.00 |
|  | Duplicator change | Unit |  |  | 60.00 |
|  | Ink ribbon | Unit |  |  | 30.00 |
| Office equipment | Photocopier | Unit |  |  | 5,000.00 |
|  | Copier | Unit |  |  | 12,000.00 |
|  | Binder machine | Unit |  |  | 50.00 |
| Office supplies | Paper | An 80g roll of vellum paper |  |  | 4.00 |
| Office furniture | 1 table, 3 chairs, 1 cabinet, 1 computer desk |  |  |  | 1,500.00 |
| Vehicles | 4x4 | Unit |  |  | 50,000.00 |
|  | Liaison vehicle | Unit |  |  | 20,000.00 |
|  | Motor bike | Unit |  |  | 4,000.00 |
|  | Bicycle | Unit |  |  | 50.00 |
| Renovation |  | Per building |  |  | 60,000 |
| Salaries | HSS Coordinator (accountant) | Monthly |  |  | 500 |
|  | Secretary | Monthly |  |  | 250 |
|  | Assistant | Monthly |  |  | 350 |
|  | Para medic | Monthly |  |  | 166.25 |
|  | Physician (base salary plus bonuses) | Monthly |  |  | 309.75 |
|  | Driver | Monthly |  |  | 125.00 |
| Maintenance and fuel for vehicles |  | Per year per vehicle |  |  | 500 |
| IEC PEV kit |  | Per kit |  |  | 100 |

# ANNEX 6 Summary of the HSCC meeting on the 12th of April 2007

SUMMARY OF THE MEETING OF THE HEALTH SYSTEM COORDINATING COMMITTEE (HHSS) IN THE CONFERENCE ROOM OF THE MINISTRY OF HEALTH, FAMILY PLANNING AND SOCIAL WELFARE

(12 April 2007)

Chairman of the meeting: Deputy Minister of Health, Family Planning and Social Welfare

Participants : See attendance sheet attached

Meeting objectives:

- Present the Madagascar application on the health system strengthening to be submitted to GAVI

- Ratify the application for approval and signature

Meeting content:

The meeting started at 15:00.

By way of introduction the representatives of USAID, UNICEF and the WHO reiterated their commitment to support the Ministry of Health, Family Planning and Social Welfare on the technical and financial plan in order to attain the objectives of the WHO, MAP and PDSS. Furthermore they underlined the importance of health system strengthening for improving immunisation coverage and other areas of the health sector. It is an opportunity for the technical and financial partners on the one hand and the Ministry on the other to harmonise and coordinate their efforts

Following this, the Deputy Minister of Health, Family Planning and Social Welfare proceeded with the official opening of the meeting. During her address, she thanked all the partners for attending in such numbers  as this bears witness to the dynamism of the sector and the existence of a string partnership. She went over the opportunity offered by HSS GAVI to improve the health of the population. The Deputy Minister insisted on the strengthening of the partnership for the health system with immunisation as top priority.

Presentation and ratification of the HSS GAVI 2007-2010 application

2007-2010 objectives

- General objectives

The general goals of GAVI HSS support consist of contributing to the development of a sustainable and effective health system, to contribute to the improvement of immunisation services and to assure the equitability of the services offer through to a peripheral level. The aim is to offer a better response to the needs of the population, especially in terms of mother and child health-care including acceptable and sustainable vaccination.

- Specific objectives:

Objective 1 is the strengthening of the provision of quality health services to the entire population.

The main activities included in this objective are:

To contract health-care workers in the marginalised health care facilities in order to overcome the lack of resources in these areas. Note that this activity is also included in objective 2 below.

Identify, by means of a study, the factors (geographical, financial and cultural) that limit the use of the service by the population. Following this, based on the results of this study, the next activity will be to pilot strategies aimed at increasing the use of this service in around 5 SSDs.

To renovate (painting, purchase of furniture for receiving patients, roofing, ceiling etc.) 15 CSBs per year with the aim of improving their physical appearance and making them more welcoming to patients. This activity will concentrate on certain centres that are antiquated today and not used by the population for this reason.

To head-up PTA ratification missions.

To equip 10 SSDs with a 4x4 vehicle, the centre supervisors with 2 vehicles and 120 CSBs with motor bikes. The SSDs will be chosen based on criteria such as geographical isolation, vaccination coverage and serviced population.

Introduce different strategies for increasing the population’s financial accessibility to health-care services in 5 SSDs per year. The strategies identified are: 1) Mutual health organisation system; 2) Strengthening of the equity funds system Note that before implementing strategies on a national scale, it is essential to implement them gradually in order to adapt and modify them and to identify their strengths and weaknesses.

Objective 2 aims to improve health sector human resources management.  The activity associated with this objective is to contract health-care workers in the marginalised health care facilities in order to overcome the lack of resources in these areas. Note that this activity is also included in objective 1 above.

Objective 3 aims to increase mobilisation and improve the allocation of financial resources. The main activities included in this objective are:

Offer training on financial and programme management to the managers on the periphery of the targeted districts

Strengthen the application of the Equity Funds and mutual health organisation system implementation plan in the targeted health care facilities. This will address several problems, notably that of a poor proportion of the population benefiting from the equity funds in the health care facilities (in fact, 68% of the population live below the poverty line yet 1% of the population is cared for by the equity funds). Note that this activity is also included in objective 4 below.

Carry out financial and management auditing including the FANOME audit in the targeted areas and develop corrective strategies for improving its management.

Objective 4 aims to stimulate the demand and use of the health services through development of community health-care. The main activities are all geared towards the development of community health-care strategies and the institutionalisation of community health-care. The following activities are covered by this objective:

Take inventory of the NGOs and associations working at a community level

Convene 3 meetings per year with 100 local authorities in the targeted areas. The objective is to monitor the health-care and community activities with the aim of making adjustments or settling the difficulties that the community workers may be experiencing.

Convene meetings for drafting policy documents establishing community health strategies (including Reference Terms and a Minimum Activity Package (PMA))

Provide training for community health-care workers in PCA in 40 targeted SSDs. This training includes the provision of an IEC PEV kit including IEC aids, guides, supplies and management tools.

Strengthen the application of the Equity Funds and mutual health organisation system implementation plan in the targeted health care facilities.

Objective 5 aims to strengthen and institutionalise a monitoring and evaluation system through the following objectives:

Provide training for health-care workers on the benefits and use of data for planning and decision-making in the targeted areas.

Assessment of the health data transfer performance of the CSBs on a central level in order to identify bottlenecks

Carry out regular follow-up and supervisory reviews of the CSBs

Support coaching in the targeted areas in order to strengthen self-efficacy and skills at a regional and district level so that the leadership role in the mobilisation of service providers is assured, not to mention the organisation and coordination of community workers so that they can implement the priority strategies and the promotion of health-orientated attitudes as well as promoting the use of the integrated family planning services. This activity also includes the procurement of IT material for 40 SSDs.

- Total cost per objective in USD

|  |  | 2007 | 2008 | 2009 | 2010 | Total |
| --- | --- | --- | --- | --- | --- | --- |
| Objective 1 | Strengthen the provision of quality health services to the entire population | 0.0 | 1 988 013,3 | 2 549 787,7 | 2 505 940,1 | 7 043 741,2 |
| Objective 2 | Improve human resources management of the health sector | Contracting already budgeted for in activity 1.1 |  |
| Objective 3 | Increase the mobilisation and allocation of financial resources | 276 514,3 | 472 335,6 | 519 569,2 | 576 577,2 | 1,844 996,3 |
| Objective 4 | Stimulate demand and use of the health services | 241 017,5 | 263 948,4 | 120 548,7 | 132 603 5 | 758 118,1 |
| Objective 5 | Strengthen and institutionalise a monitoring and evaluation system | 195 507,9 | 619 524,1 | 185 355,8 | 255 329,1 | 1 255 716,9 |
| Cost of the support | Management costs | 97 475,9 | 65 123,9 | 71 636,2 | 78 799,9 | 313 035,8 |
|  | TOTAL | 810 515,5 | 3 408 945,3 | 3 446 897,6 | 3 549 249,8 | 11 215 608,4 |

Chairman of the meeting

# Footnotes

Minutes from HSCC meetings related to HSS should be attached as supporting documentation, together with the minutes of the HSCC meeting when the application was endorsed. The minutes should be signed by the HSCC Chair. The minutes of the meeting endorsing this GAVI HSS application should be signed by all members of the HSCC.

If the application identifies activities that are to be undertaken at a sub-national level, sub-national data will need to be provided where it is available. This will be in addition to the national data requested.

Within the last 3 years.

If number of districts is provided than the total number of districts in the country must also be provided.

If baseline data is not available indicate whether baseline data collection is planned and when

Important for easy accessing and cross referencing

This figure relates to the MAP and PDSS objectives.

This figure relates to the MAP and PDSS objectives

The costs of the coordinator, assistant and the secretary are included in the proposed budget under the heading of management costs.

If available – and if not, the National Immunisation Plan plus Financial Sustainability Plan

if available please forward the pages relevant to Health Systems Strengthening and this GAVI HSS application