REPUBLIC OF NIGER

MINISTRY OF PUBLIC HEALTH

Fraternity, Labor, Progress

PROPOSAL BY THE REPUBLIC OF NIGER FOR HEALTH SYSTEMS STRENGTHENING

SUPPORT (HSS) FROM GAVI

August 2009

Application form for:

The application to obtain Health Systems Strengthening (HSS) support from GAVI Alliance

Deadlines for sending applications for 2009: May 1 and September 4

An electronic version of this form is available on the GAVI Alliance web site (www.gavialliance.org).

Please send this electronic form with attachments (including the signature page) to the following e-mail address:: proposals@gavialliance.org

Requests for information: proposals@gavialliance.org or from the representatives of a GAVI partner agency. Proposals and attachments must be submitted in English or French.

Please make certain that the application has been received by the GAVI secretariat before or on the date of the deadline. Applications received after that date will be the first ones considered during the following reviews. GAVI will not be liable for delays or for failure to submit the applications by messaging services.

The GAVI secretariat is not able to return the documents and attachments to the country. Unless specified otherwise, the documents will be transmitted to the partners of GAVI Alliance and to the general public.

If hard copies are submitted, please send them to this address::

Novelles demands / New Proposals

GAVI Alliance Secretariat,

Chemin de Mines 2

CH 1202 Geneva

Switzerland

Table of Contents	Page

Abbreviations and acronyms	6

Executive Summary 	9

Section 1: Application process	14

There are no additional comments, given that this document is the result of an interactive process followed by all the players without reservation, and that the task force benefited from the contributions from all the healthcare partners (bilateral, multi-lateral, UN systems, NGO and civil society cooperation). These partners are represented in the different HDP monitoring and evaluation bodies at all levels of the healthcare pyramid.	20

Section 2: Information on the national context	21

21

Section 3: Situational Analysis / Evaluation of needs	25

Owing to inadequate governance, there is poor management capability at all levels of the healthcare system. The central departments suffer from compartmentalization. This prevents communication among the central departments, on the one hand, and between the MPH and the other levels of the pyramid. There is also insufficient decentralization in terms of human resources.	29

These evaluations of the sector also show major interference by political, socio-economic and cultural factors that hinder the management, availability and use of healthcare services, i.e.:	29

The poor state of the roads, reducing the accessibility of some villages to vaccine activities	29

Some socio-cultural behaviors that are harmful to health, and taboos (food, female circumcision, premature marriage, religious fundamentalism, etc.)	29

The low percentage of girls in school and the low literacy rate of the population in general 	30

The low income of most of the households (62.15 of the population lives on less than a dollar a day)	30

The more recent lack of security in some parts of the country	30

Seasonal migrations of workers to neighboring countries. 	30

The MPH is in the process of resolving the inadequacies identified in collaboration with the local authorities and the community, the partners and NGOs. 	31

Provision of services	31

However, there are still some inadequacies that the MPH aims to resolve with the support of its partners.	33

Section 4: Goals and objectives of HSS support from GAVI	37

Section 5: Program of activities and application of the GAVI HSS	42

Section 6: Monitoring, evaluation and operational research	51

Section 7: Implementation provisions 	64

Section 8: Budget projections and funding for the activities supported by the GAVI HSS	76

Section 9: Conditions of GAVI support	88

APPENDIX 1 Supporting documents submitted with the application for HSS support from GAVI and final check list	94

APPENDIX 2 Banking form	96

# Abbreviations and acronyms

To the Applicant

- Please make certain that all the abbreviations and acronyms used in this application and attachments are mentioned here.

| # AAP | # Annual Action Plan |
| --- | --- |
| # ADB | # African Development Bank |
| # ADPRS | # Accelerated Development and Poverty Reduction Strategy |
| # AFD | # French Development Agency |
| # AIDS | # Acquired Immuno-deficiency virus |
| # AMW | # All-purpose maintenance worker |
| # ARV | Anti Retro Viral |
| # AYSRH | # Adolescent and youth sexual and reproductive health |
| # CCB | # Communication for a change in behavior |
| # CDSMT | # Framework for medium-term sector expenses |
| # CEmNOC | # Comprehensive Emergency Neo Natal and Obstetrical Care |
| # CF | # Common Fund |
| # CHW | # Community health worker |
| # cMYP | # Comprehensive Multi-year Plan |
| # CNS | # National Health Committee (Board) |
| # CR | # Cost Recovery |
| # CTNS | # National Health Technical Committee |
| # DAF | # Department of Financial Affairs |
| # DDQS | # Data Quality System |
| # DEP | # Department of Research and Programming |
| # DFGP | # Department of Training and Management |
| # DGR | # General Resource Department |
| # DGSP | # General Public Health Department |
| # DH | # District Hospital |
| # DHDP | # District Health Development Plan |
| # DHP/ES | # Department of Public Hygiene and Health Education |
| # DHS | # Demographic and Health Surveys |
| # DQA | # Data Quality Audit |
| # DSSRE | # Department of Statistics on Surveillance and Response to Epidemics |
| # DTP-DTP | # Diphtheria, tetanus, pertussis (pentavalent vaccine) |
| # DTP-HepB | # Diphtheria, tetanus, hepatitis B |
| # ECD | # Lead District Team |
| # ECOWAS | # Economic Community of West African States |
| # EDF | European Development Fund |
| # EGD | # Essential Generic Drugs |
| # EMONC | # Emergency Obstetrical and Neonatal Care |
| # EONC | # Essential Obstetrical and Neonatal Care |
| # EPI | # Expanded Program on Immunization |
| # FMR | # Financial Monitoring Report |
| # FP | # Family planning |
| # FYP | # Five-year plan |
| # FYWP | # Five-year work plan |
| # GAVI | # Global Alliance for Vaccines and Immunization |
| # GDP | # Gross National Product |
| # GF | # Global Fund |
| # GIVS | # Global Immunization Vision and Strategy |
| # GMS | # Global Mobile System |
| # GPS | # Global Positioning System |
| # HC | # Health Coverage |
| # HD | # Health District |
| # HDP | # Heath Development Plan |
| # HF | # Healthcare facility |
| # HIPC | # Highly Indebted Poor Country |
| # HIV | # Human Immuno-deficiency virus |
| # HNN | Niamey National Hospital |
| # HST | # Hygiene and sanitation technician |
| # IC | # Practical nurse |
| # IDA | # International Development Agency |
| # IDE | # Registered nurse |
| # IEC | # Information Education Communication |
| # INS | # National Institute of Statistics |
| # ISU | # Institutional Support Unit |
| # ITCD | # Integrated treatment of childhood diseases |
| # IUD | # Intra-uterine device |
| # LID | # Local Immunization Days |
| # MC | # Management Committee |
| # MDG | # Millennium Development Goals |
| # MEF | # Ministry of the Economy and Finance |
| # MFPT | # Ministry of the Civil Service and Labor |
| # MND | Micro-nutriment days |
| # MNT | # Maternal neonatal tetanus |
| # MOI/AMI | Major Obstetrical Intervention for absolute maternal indication |
| # MPA | # Minimum Package of Activities |
| # MPH | # Ministry of Public Health |
| # MPH/FAE | # Ministry of Public Health/Fight against endemic diseases |
| # NA | # Not applicable |
| # ND/EPI | # National Department/Expanded Program for Immunization |
| # NGO | # Non-governmental organization |
| # NID | # National Immunization Days |
| # NTD | # Neglected Tropical Diseases |
| # OBM | # Outcome-based management |
| # ONPPC | # National Office of Pharmaceuticals and Chemicals |
| # PEA | Public establishment of an administrative nature |
| # PEIC | Public Establishment of an industrial and commercial nature |
| # PEM | # Protein energy malnutrition |
| # PMCT | # Protection from mother-to-child transmission of the AIDS virus |
| # PNC | # Prenatal Consultation |
| # POLIO | # Poliomyelitis |
| # PONC | # Postnatal Consultation |
| # PRS | # Poverty Reduction Strategy |
| # RED | # Reach every district |
| # RGP/H | # General Population and Housing Census |
| # RH | # Reproductive health |
| # RHDP | # Regional Health Development Plan |
| # RIDB | # Regional Islamic Development Bank |
| # ROASSN | # Network of Health Organizations and Associations |
| # SD | # Supporting documentation |
| # SFDE | # Registered midwife |
| # SG | # Secretary General |
| # SLT | Senior lab technician |
| # SNCT | Senior nursing care technician |
| # SNIS | # National Health Information System |
| # SOCT | Senior obstetrical care technician |
| # SPA | # Supplemental Package of Activities |
| # SPHT | Senior public health technician |
| # SPPR | # Special Program of the President of the Republic |
| # SSAT | Senior social action technician |
| # SSB | # Single side band |
| # STD | # Sexually transmitted diseases |
| # TA | # Technical assistance |
| # TETE | # Triage Emergency Treatment Evaluation |
| # TF | # Task force |
| # TFP | # Technical and Financial Partners |
| # UNDP | # United Nations Development Fund |
| # UNICEF | # United Nations Children’s Fund |
| # UNMPDA | # United Nations Master Plan for Development Assistance |
| # USD | United States Dollar |
| # VAR | # Measles vaccine |
| # VII | # Vaccine Independence Initiative |
| # WAME | # West African Economic and Monetary Union |
| # WB | # World Bank |
| # WCA | # Woman of child-bearing age |
| # WHO | # World Health Organization |

# Executive Summary

To the Applicant

- Please provide a summary of the proposal that includes the goal and objectives of the application for HSS support from GAVI, the main strategies and activities to be undertaken, the outcome planned, the duration of the support and the total amount of the funds requested, as well as the basic data and objectives to be reached for the priority indicators chosen.

EXECUTIVE SUMMARY The national healthcare policy is structured around the implementation of a 2005-2010 Health development plan (HDP) (Appendix 2). Niger’s proposal for support from GAVI for the HSS is included under the implementation of the 2005-2010 HDP and the comprehensive Multiyear Plan (cMYP) (Appendix 3) of the 2007-2010 EPI. Both documents focus entirely on reaching the Millennium Development Goals (MDG). The HDP is aimed at contributing to a reduction in maternal and child mortality by improving the efficiency and the quality of the healthcare system based on existing potential. Its eight (8) specific objectives have been translated into eight programs and outcomes expected through which all interventions in the sector are made. Under the HDP, the EPI comprehensive Multiyear Plan (2007-2010 EPI-cMYP) was developed to ensure equal access to all immunization services, increase the use of immunization services, introduce new vaccines and integrate immunization with other health interventions. The objectives of the cMYP are in keeping with the four strategic areas making up the Global Immunization Vision and Strategies (GIVS), which urge countries to institute national vaccine coverage of at least 90 percent for all antigens and at least 80 percent in all districts by the year 2010. In 2010, results will be evaluated in view of drawing up the next cMYP for the period 2011-2015. The purpose of the request to GAVI is to help to achieve the objectives of the cMYP and the HDP and to draft the 2011-2015 cMYP and the 2011-2015 HDP under preparation. This 2011-2015 HDP, which is to be implemented as part of the overall Healthcare System Strengthening strategy of the Ministry of Public Health (MPH), is consistent with the objects of the 2008-2012 Strategy for Accelerated Development and Poverty Reduction (ADPRS) approved by the Government. Drafting of the request by the Task Force (TF) was coordinated and supervised by the Chairwoman of the Comité Technique National de Santé (National Healthcare Technical Committee - CTNS), which is the technical body in charge of monitoring and evaluating the implementation of the HDP. The findings of the task force were presented and discussed at the meeting of the CTNS in February 2009. The proposals by the CTNS were presented and approved by the National Healthcare Board (CNS) during its February 2009 session With the results of the recent evaluations done in the sector , the MPH was able to identify the obstacles and inadequacies involved in implementing the current HDP, which affect the lives of the people, particularly prevention, immunization coverage and maternal and child care as well as the management of resources. The results provided input for decision-making concerning the preparation of a new 2011-2015 HDP. The preparatory document drafted (see Appendix number 1) includes two major components: A component for the “healthcare strengthening system,”, which will have to overcome the current inadequacies in the system to give it all the capabilities necessary to achieve the goals, A component for “healthcare system operations,” which will have to guarantee the availability of the human, material and financial resources necessary to achieve the objectives to be set. The GAVI application was prepared by the TF based on the inadequacies identified in the situational analysis of the healthcare system, the documentary review and consultations with the various players and partners. The MPH and its partners have a common and global view of strengthening the healthcare system, the allocation and use of financial, material and human resources to succeed in improving the system. The inadequacies noted are based on the following six primary areas: - Provision of services, - Human resources - Healthcare information, - Medicines, vaccines and technologies, - Healthcare financing, - Leadership and Governance. In each of these areas, the situational analysis also points up inadequacies that have been dealt with in the past few years (see Section 3.3) and problems that still persist. The proposal for GAVI HSS support is aimed at providing sustainable solutions to the inadequacies that have persisted over the past few years. Various forms of support (Support for Immunization Services (ISS) and Support for New Vaccines [NVS]) from GAVI have already been received to strengthen immunization activities and introduce new vaccines. The task force concentrated the proposal on the overall HSS areas recommended by the CTNS, specifically three of the six areas: Provision of services, Human Resources and Healthcare information. In addition, given the timetable of the MPH in terms of planning (End of the HDP and the CMYP in 2010), special emphasis will be placed in this proposal on the preparation of a new health development plan and a new comprehensive multi-year plan recommended by the CTNS, specifically on three of the six areas: Provision of services, governance and healthcare information. The goal of this proposal is to: Contribute to improving the state of health of the population in general and mothers and children in particular The proposal focuses specifically on the following four specific objectives. It will cover one year only in 2010 so as to be consistent with the objectives related to aligning the current planning documents, including the 2005-2010 HDP and the 2007-2010 cMYP, which all end in 2010. Objective 1: Increase the proportion of the population with access to the MPA from 44. 6% to 50 % by improving immunization coverage in children below the age of five by the end of 2010; Objective 2: Provide the central level within the deadlines comprehensive and quality data from at least 70 percent of the healthcare facilities by 2010; Objective 3: Support the preparation and adoption of a new 2011-2015 health development plan; Objective 4: Support the preparation and adoption of a new comprehensive multi-year immunization plan for 2011-2015. The outcomes expected are listed below: - Improvement in material and logistical resources to enable healthcare personnel to offer the MPA (minimum package of activities) in healthcare facilities for the most remote populations; - Improvement in the quality, availability and use of healthcare information at all levels, particularly at the district and CSI (integrated healthcare center) levels. - Improvement in the planning process so as to enlist more financial resources to implement the healthcare policy by preparing two documents (the HDP and the cMYP). To achieve these objectives, the inadequacies must be reduced, such as the poor physical accessibility (0-5Km) of the population to the MPA (vulnerable populations like nomads, i.e. transhumant populations); the poor quality of patient care and treatment; the poor management of existing personnel; inadequate initial training of the personnel in terms of epidemiology and the conditions of the poor rural population. The primary activities planned are listed below: Providing additional material, logistical and communications resources to the fourteen most isolated districts; awarding additional employee incentive bonuses in keeping with the national strategy of redeploying personnel in the most isolated areas; improving the equipment of the healthcare facilities. - Reviewing tools, the transmission process, data analysis and record keeping and improving the skills of healthcare workers, - Design and have adopted by the government a new health development plan that will be consistent with the National Compact (IHP+), - Prepare and adopt a new comprehensive multi-year immunization plan (cMYP) Concerning the viability of the intervention by GAVI, the following strategies have been selected: The HSS from GAVI will supplement the efforts by the government and its partners. The budget of the State allocated to the healthcare sector has been increasing since 2006, In addition, the prospect of developing mining and oil resources points to a possible improvement in the amount of financing for the healthcare sector. Implementing the law on decentralization will also help to increase the level of healthcare financing by the local and regional authorities. Niger has drafted a document for the overall strengthening of the healthcare system. Other TPF such as the Global Fund and Niger’s common healthcare fund are involved in the financing of this plan. The Ministry of Public Health has an official in charge of working with and coordinating the TFP. He is also in charge of managing the financing of the activities at different levels. The method for managing GAVI HSS support is based on the current mechanism for managing the funds managed in the Common Fund. The HSS activities are included in the HDP, which is translated in to the district health development plan (DHDP) and the annual action plan (AAP). Monitoring and evaluation of the interventions planned are included in the HDP monitoring and evaluation mechanism put in place by the MPH. To guarantee the lasting nature of the interventions planned, a more intense effort will be made to enlist funds from the State budget, which has included a significant increase every year since 2006 with an execution rate of nearly 85 percent. Furthermore, owing to the short duration of this proposal, Niger hopes to receive more support from GAVI eventually in a more global context (IHP+) The population of Niger in 2009 is estimated at 14,825,071 according to the projections of the National Institute of Statistic (INS). The birth cohort is estimated, according to the same projections, at 797,519. The total allocation available for the country, based on a birth cohort of one year, is US $3,987,595 for [word missing] The total cost of the support would be $3,985,799 for the year considered.

# Section 1: Application process

To the Applicant: Section 1.1

In this section, please describe the GAVI HSS application process.

- Please start with a description of your healthcare sector coordinating committee or its equivalent (table 1.1).

## 1.1: The HSCC (or its national equivalent)

Name of the HSCC (or its equivalent): In Niger, the equivalent is the Comité National de Santé (National Healthcare Committee) (CNS)

HSCC operational since: The CNS has been in operation since November 28, 2006 (created by decree N° 00229/MPH/LCE/DEP) (appendix 14a). It is chaired by the Minister of Public Health. It is a liaison and coordination body between the Government and the TFP, in charge of setting policy for the healthcare sector. In addition, it validates the proposals by the CTNS. It is made up of 30 representatives of the Ministries, the National Assembly, Regional Governments, professional organizations, educational institutions and civil and religious associations.

Organizational structure (for example, sub-committee, stand-alone committee): Organizational structure (for example, sub-committee, stand alone committee): The Comité Technique National de Santé (CTNS) has been designated by the monitoring and evaluation manual of the Health development plan (HDP) (appendix 12) to facilitate the preparation of sector policy documents (formalized by decree N° 00233/MPH/LCE/DEP of December 1, 2006 (appendix 14b). this committee, which is chaired by the Secretary General of the MPH, is made up of around one hundred members from different units of the MPH at all three levels of our healthcare pyramid, from other ministries, private healthcare representatives, NGOs and civil society organizations and TFP. Since November 16, 2006, Technical Committees have been created at the regional, district and community levels (by decree N° 003990/MPH/LCE). In connection with the preparation of the HSS applications to be submitted to the Global Fund and to GAVI, a Task Force (TF) formalized by departmental memorandum N° 00161/MPH of December 16, 2008 (appendix 13) This TF is chaired by the Director of Public Health and Education (DHP/ES) of the Ministry of Public Health.

Frequency of meetings The CNS meets twice a year in ordinary session, and in special session if need be when convened by its chairman.

Roles and general functions: The CNS is in charge of: - Validating regional plans - Monitoring and evaluating the HDP - Monitoring indicators - Holding midyear AAP meetings - Mobilizing resources - Monitoring and controlling the budget - Coordinating the actions of the TFPs The CTNS is in charge of: - Monitoring the preparation of the Sector Development Plan and the cAAP at the central level - Monitoring and evaluating the HDP - Monitoring the indicators - Holding midyear reviews of the AAPs - Monitoring and controlling the budget - Conducing audits of the healthcare sector The TF is in charge of drawing up the proposal for GAVI and for the following: - Ensuring broad participation by all the stakeholders in drawing up the proposal - Conducting a situational analysis taking into account all the components of the healthcare system - Identifying priority problems, even bottlenecks in the healthcare system related to immunization and other maternal and child healthcare services - Prepare the proposal’s action plan (objectives, activities, timetable, and budget) and the monitoring and evaluation system.

To the Applicant: section 1.2

- In this section, please describe the process followed by your country to prepare this application for HSS support from GAVI (table 1.2)

Note: Without supporting documentation (signed minutes of the HSCC meetings) and a detailed description of the process of preparing the application, the GAVI Independent Review Committee (IRC) will be unable to evaluate the involvement of the key participants (civil society, bilateral, private sector and representatives are hard-to-reach populations) in the process. The signed minutes of the HSCC meetings related to the preparation of the application for HSS support must be attached (document number…) as supporting documentation with the signed minutes of the meeting (document number …) during which the application was approved by the HSCC.

## 1.2: General description of the application process

Who coordinated and supervised the process of drawing up the proposal? The process of preparing the proposal was coordinated and supervised by the Secretary General of the MPH, who is also the Executive Secretary of the CNS and chair of the CTNS.

Who was in charge of the first draft of the application? Was technical assistance provided? The application proposal was drawn up by the ad hoc TF under the chairmanship of the Director of Public Hygiene and Health Education (DHP/ES) of the Ministry of Public Health. The TF received technical and financial assistance from the WHO Country Team, UNICEF, WHO Geneva, the UNPF, the common HDP support fund, the West African inter-country Team and an international consultant hired by Belgian Technical Cooperation.

Give a brief chronology of the activities, meetings and reviews that led to the submission. - The process started back in March 2007 after the GAVI sub-regional technical briefing workshop on strengthening the healthcare system held in Ouagadougou by the WHO. - During the same period, a task force was created to start writing the proposal. However, the resources needed to prepare the request proved to be insufficient. - In December 2008, the process was reactivated with the Ouagadougou meeting; four members of the TF participated in that workshop on strengthening capacities to write GAVI and Global Fund HSS requests. - January 21-24: workshop on harmonizing GAVI and Global Fund requests [held] by the TF sub-committees in Niamey and Tillabéry. - January 27, 2009: review by the WHO/HQ and STD team of the GAVI and Global Fund proposals for strengthening health systems. - February 17, 2009: HSS document presented to the National Healthcare Technical Committee (CTNS) and to the CNS (Report summarizing the CNS meeting: appendix 11 and attendance list of the CTNS meeting of the CTNS meeting: appendix 15). - February 16-18, 2009: workshop held by the Ministry of Health in connection with the CTNS conference at the Niamey Palais de sport to analyze the situation and identify any priority problems, with the participation of civil society and technical and financial partners. - February 25, 2009: meeting held in the office of the Minister to recap the Ouagadougou meeting on the process of preparing the HSS. - March 13-14: Meeting to flesh out the HSS strategy document with the participation of the members of the proposal writing committee, regional health directors, technical and financial partners, the central departments of the MPH and representatives from civil society. - March 17-19, 2009: participation in the peer review in Ouagadougou of the GAVI and Global Fund health systems strengthening proposals. - April 15-17, 2009: workshop held to flesh out the HSS proposal document. - April 23-26: Finalization with the support of an international consultant (CTB financing) of the HSS requests to be submitted to GAVI and the Global Fund. - April 29-30: Request submitted for signing by the Minister of Public Health, the Minister of the Economy and Finance and UNICEF. - May 1, 2009: Request submitted to GAVI in Geneva by the Government of Niger.

Who was involved in reviewing the application and what is the process that was adopted? After drafting by the TF, the proposal was submitted for review by the members of the National Healthcare Technical Committee (CTNS) during its conference held in Niamey on February 17 and 18, 2008.

Who approved and signed the application before it was submitted to the GAVI Secretariat? The application was approved by the Minister of Public Health and the Minister of Economy and Finance and by UNICEF. Was funding received from GAVI to prepare the application for HSS support? If so, how much was received and how was it or will it be used? The amount of funding received from GAVI to prepare the application for support was USD 50,000, received in May 2009. It was used to finance the workshops on drafting, correcting and finalizing the application and to reproduce working documents and the request.

To the Applicant: section 1.3

- Please describe the roles and responsibilities of the key partners in preparing the application for HSS support from GAVI (table 1.3)

Note: All the key partners must be included in the process: the Ministry of Health as well as the planning and immunization departments; the relevant coordinating committees, the NGOs and civil society and the private healthcare sector. If there is no involvement by civil society or the private healthcare sector or by other key players in the drafting of the application for the GAVI HSS, please explain below (1.4).

## 1.3: Roles and responsibilities of the key partners (members of the HSCC and others)

| Title / Position | Organization | Member of the HSCC yes/no | Please describe the specific roles and responsibilities of this partner in drafting the GAVI HSS application |
| --- | --- | --- | --- |
| Dr. Moussa Fatimata Minister of Public Health | Ministry of Public Heath | Yes | - Executive Secretary of the CNS - Coordinates and organizes the different task forces responsible for drafting the HSS application (GAVI and Global Fund). |
| Mr. Jacques Gourdin Adviser | Belgian Consulate in Niger Lead member of the TFPs | Yes | Enlisted the participation of the TFPs in drafting the application |
| Ms. Mayaki Hassana | Ministry of Finance | Yes | Participated in drafting the financial proposal of the application |
| Ide Djermakoye Coordinator of the network of NGOs and Associations in the healthcare sector | Network of NGOs and Associations in the healthcare sector (ROASSN) | Yes | Participation à la validation de la proposition |
| Dr. Abdourahamane Salamatou Regional Healthcare Director | Niamey Regional Health Department | Yes | Participated in drawing up and validating the proposal |
| Dr. Alpha Cissé Representative of the private healthcare sector | Private healthcare association | Yes | Participated in drawing up and validating the proposal |
| Mr. Danfane Weslamane Representative of the military healthcare services | Military healthcare services | Yes | Participated in validating the proposal |
| Boureima Hamidou Director of Research and Planning | Ministry of Public Health | No | Presides over the work of the Gavi HSS and Global Fund subject area groups (task forces) |
| Sadi Moussa Director of Public Hygiene and Health Education | Department of Public Hygiene and Health Education /MPH | No | Chairman of the Word Fund and GAVI HSS TF |
| Zeinab Hadari Permanent Secretary of the CCM/Global Fund | Permanent Secretariat of the CCM/Global Fund - Niger | No | Preparing meetings / Participation in preparing the proposal |
| Dr. Tiécoura Coulibaly | World Health Organization EPI Team Leader | No | Technical support in drafting the proposal |
| Dr.Gagara Magagi | WHO /MPN | No | Technical support in writing the draft proposal |
| Galadima Souley Chief of the public accounting division | Department of Financial resources and equipment of the MPH (DRFM) | No | Participated in drafting the proposal |
| Maiga Moustapha Head of the Monitoring and Evaluation Department | Immunization Division /MPH | No | Participated in drafting the proposal |
| Dr Lado Abdoulaye Division Chief | Immunization Division /MPH | No | Participated in drafting the proposal |
| Magagi Jadi Immunization Division | Immunization Division /MPH | No | Participated in writing the draft proposal – all workshops |
| Bizo Moussa Economist | WHO/Niger | No | Participated in writing the draft proposal |
| Abdoulaye Alhassane | Immunization Division /MPH | No | Participated in writing the draft proposal |
| Saadou Garekam | Civil society (ROASSN) | No | Participated in drafting the proposal |
| Ms. Dejean Mariama | Immunization Division/ MPH | No | Participated in drafting the proposal |
| Dr. Adamou Zeinab | Immunization Division/MPH | No | Participated in drafting the proposal |
| Boubacar Abdou | Immunization Division/MPH | No | Participated in drafting the proposal |
| Hinsa Ide | Immunization Division / MPH | No | Participated in drafting the proposal |
| Hamma Aissa Sambo | Global Fund subject area group (task force) | No | Participated in drafting the proposal |
| Ousmane Oumarou | DEP/MPH HSS focal point | No | Participated in drafting the proposal |

To the Applicant: section 1.4

- The partners and members of the HSCC are encouraged to provide their comments and inform the GAVI Secretariat of any concern or question anticipated on the implementation, monitoring or the financial provisions.

- If the HSCC wishes to make any additional comment or recommendation on the application for HSS support from GAVI to the GAVI Secretariat and the Independent Review Committee, please do so below.

- Please explain if there was no involvement by civil society or the private sector and indicate whether they are supposed to have a service provision or support role in applying the support for the GAVI HSS.

- If this is an application for renewal, please describe the primary changes introduced in this proposal.

- Please describe any lesson learned, or useful practice developed during the writing of the proposal for the HSS.

## 1.4: Additional comments on the process of writing the GAVI HSS application

# There are no additional comments, given that this document is the result of an interactive process followed by all the players without reservation, and that the task force benefited from the contributions from all the healthcare partners (bilateral, multi-lateral, UN systems, NGO and civil society cooperation). These partners are represented in the different HDP monitoring and evaluation bodies at all levels of the healthcare pyramid.

# Section 2: Information on the national context

To the Applicant: section 2.1

- Please provide the most recent socio-economic and demographic information available for your country. Please specify the dates and sources of the data (table 2.1). If they differ from or are inconsistent with the data used in other GAVI applications or audits, then supporting documentation must be provided.

## 2.1: Current socio-demographic and economic information on the country

| Information | Figure | Information | Figure |
| --- | --- | --- | --- |
| Population [2009] (1) | 14,825,071 | GNI per capita [2007] (4) | $284 USD |
| Annual birth cohort [2009] (1) | 797,919 | Mortality rate for children less than five years of age [2006] (4) | 198/1000 |
| Surviving infants [year] | N/A | Infant mortality rate [2006] (4) | 81/1000 |
| Percentage of GDP allocated to health [2007] (2) | 2.5% | Percentage of government expenditure on health [2007] (2) | 9.6% |
| Rate of DTP3 coverage (by gender, if available) [2008] (3) | 89% | Percentage of the population living below the poverty line [2005] (5) | 62.1 % |
| *Surviving infants = infants surviving the first 12 months of life Sources: (1) INS, RGP/H, 2001, demographic data on Niger 2008 appendix 10; (2) MPH, Review of Healthcare Sector Public Expenditures, 2007; (3) MPH, EPI administrative data, 2008 (4) Office of the Prime Minister, Accelerated Development and Poverty Reduction Strategy (ADPRS), 2008-2012 (appendix 6), Niger; (5) Office of the Prime Minister, Evaluation report on the PRS (en), 2005. |  |  |  |

- Niger is a Sahelian-Saharan country measuring 1,267,000 km² with a population of

- 14,825,071 (according to the projections of the INS), 80 percent of whom live in rural areas and 62.1 percent (Source: Accelerated Development and Poverty Reduction Strategy, Evaluation Report 2005, page 35) of whom live below the poverty level. Its population is increasing by 3.3 percent owing to one of the highest birth rates in the world (7.1 children per mother). The population is concentrated in the southern half of the country, mainly along the border of Nigeria, which is 1,200 kilometers in length. The northeastern part of the country is the vastest and the least populated. It is even unpopulated in the far north.  Although the literacy rate is only 20 %, the percentage of children in primary school is 56 percent for boys and 40 percent for girls. The national rate of access to drinking water is 62 percent (Ministry of Hydraulics 2007) and access to basic sanitation infrastructures 20 percent in 2007. With GDP of 1,850 billion FCFA, or USD 284 per capita per year, Niger’s economy is based mainly on agro-pastoral activities (40 %) and government services (43%).

- From an administrative and political standpoint, the democratic process is becoming increasingly ingrained under a presidential regime with a parliament of 113 deputies, 25 percent of whom are women. More and more is being done to increase leadership by women. Niger is subdivided into eight administrative regions run by governors appointed by the President. The representatives of local authorities (265) have been elected since 2004. Since 2001, Niger has developed a development and poverty reduction strategy based on priority interventions in the basic social sectors including health. This strategy calls in particular for interventions in favor of vulnerable groups and gender promotion.

To the Applicant: section 2.2

- Please provide a brief summary of your country’s healthcare sector plan (or its equivalent), including the key objectives of the plan, the strong points and the weak points identified through the healthcare sector analysis, and the priority areas for the development to come (table 2.2).

- Please point out any specific socio-economic barrier to access to immunization services, e.g., hard-to-reach populations or gender inequality.

## 2.2: Overview of the national strategic plan for the healthcare sector (document N °2) and how it relates to the cMYP (document N° 3.)

## The Health development plan (HDP 2005-2010) Niger’s health policy is implemented through Health development plans. The health planning process initiated in Niger starting in the 1990s led to an initial Health development plan (HDP) for the years 1994-2000. Thus a second HDP (for 2005 -2010) was prepared with the support of the technical and financial partners (TFP) responding in the healthcare sector. The HDP is consistent with the goals of the Accelerated Development and Poverty Reduction strategy (ADPRS) for 2008-2012. It is entirely focused on achieving the Millennium Development Goals, i.e. (i) reducing the prevalence of malnutrition (MDG 1), (ii) reducing the infant, child and maternal mortality rate (MDG 4 & 5), (iii) stopping the transmission of HIV/AIDS and reversing its trend, reducing the transmission of malaria and tuberculosis (MDG 6), (iv) making essential generic drugs available to all developing countries (MDG 8). To implement the 2005-2010 HDP, a Five-year Work Program (FWP) with a sliding target date and a monitoring and evaluation manual were designed. A partnership agreement was signed between the MPH and the TFP, which solidifies their commitment in a sector-based approach with the creation of an HDP Common Support Fund. A monitoring and evaluation manual was prepared with a set of indicators to be followed. The situational analysis led to the identification of 15 priority problems that can be organized into seven major categories: - The very high maternal and infant mortality rate, - The poor accessibility of the population to quality care and services, - The insufficiency in terms of quality and quantity of healthcare personnel - The lack of decentralization for better involvement of the outreach level in decision-making, programming, planning and implementing health policy, including community participation, - The institutional weakness of the MPH, - Maintenance shortages for furnishings and real property, - The shortage of essential drugs and quality medical supplies in health facilities. The general goal of the HDP is to “contribute to the reduction in maternal and child mortality by improving the efficiency and quality of the healthcare system based on existing potential.” The following eight (8) specific objectives were identified in the HDP. - Increase accessibility of the population to quality care and services; - Strengthen reproductive health activities; - Strengthen the decentralization process in the healthcare sector; - Increase community participation in local health policies; - Strengthen the management capability and the institutional skills of the MPH ; - Reduce the qualitative and quantitative insufficiency of healthcare personnel; - Increase the effectiveness and efficiency of the infrastructure management and the material resources provided to the health departments; - Increase the availability of essential drugs and quality medical supplies in healthcare facilities. These objectives were translated into eight programs and expected outcomes, through which all interventions are done in the healthcare sector (Page 109-110 of the 2005-2010 HDP).

## The Comprehensive Multiyear Plan (EPI cMYP 2007-2010) The Comprehensive Multiyear Plan (EPI cMYP 2007-2010) was prepared in order to ensure equal access by everyone to immunization services, to increase the use of immunization services, introduce new vaccines and see to it that immunization is included with other healthcare interventions. The overall purpose of this plan, which comes after the first EPI Strategic Plan for the period 1988-1992 and which was the next to the last for the period 2002-2006, is to “contribute to the reduction in morbidity and mortality related to diseases preventable through immunization.” To reach this objective, the cMYP is aimed at the following specific objectives: - Improve the current performance of routine EPI by including the pentavalent vaccine (DTP- HepB - HiB combined), by improving the use of the vaccine against yellow fever and by introducing the second dose of the measles vaccine starting in 2008. - Eradicate poliomyelitis in Niger by 2010, - Eliminate Material and Neonatal Tetanus by 2010. - Control measles. These objectives are focused on and dovetail with achieving the goal and conducting programs I and II of the HDP, which aims to reduce infant-child mortality by 25 percent by the year 2015 by improving accessibility and use of curative and preventive services. The objectives of the cMYP are in keeping with the four strategic areas making up the “Global Immunization Vision and Strategies” (GAVI), which urges countries to introduce national immunization coverage of at least 90 percent for all antigens and at least 80 percent in all districts by the year 2010. The principal strategies contained in the cMYP are the following: - Strengthen routine activities under the Expanded Immunization Program (EPI) and continue additional Immunization activities (polio, MNT, measles) combined with National Micro-nutriment Days (NMD). - Combat transmissible diseases with approaches improving prevention such as immunization. These strategies also emphasize integrating other health interventions aimed at promoting child survival, particularly vitamin A supplements and other micronutrients like iron, distribution of treated mosquito nets, deworming of children and promoting healthy childbirth. Furthermore, several other essential programs to combat childhood disease (PCIME), the IEC/healthcare program, reproductive health programs and programs to fight STD/HIV/AIDS implemented in the country help to strengthen immunization activities.

# Section 3: Situational Analysis / Evaluation of needs

To the Applicant: section 3.1

HSS support from GAVII HSS support from GAVI cannot attack all the obstacles existing in the healthcare system that have repercussions on immunization services and other maternal child healthcare services. HSS support from GAVI must not replicate but find solutions to supplement and take advantage of other funding to strengthen the healthcare system, and fill in the existing gaps in current attempts to improve the healthcare system.

- Please provide information on the most recent evaluations of the healthcare sector that have identified obstacles in the healthcare system (table 3.1)

NB: The evaluations may contain a recent assessment of the healthcare sector (conducted in the past three years), a report and a recent study of sector constraints, a situational analysis (like the one conducted for the cMYP), or any combination of those documents. Please attach the reports on those evaluations to the application (with summaries if you have any). Please number them and list them in appendix 1.

NB: If there is no recent in-depth evaluation of the healthcare system (in the past three years) then a case review must absolutely be done that identifies and analyzes the main bottlenecks in the health systems before introducing your request to obtain HSS support from GAVI. This review must identify the main strengths and weaknesses of the healthcare system and the points where it will be necessary to strengthen the capability of the system to succeed in improving immunization coverage and maintaining it at the level reached.

NB: Any questions related to the specific way in which hard to reach populations can be reached and to the increase in coverage in the evaluations or in the national healthcare plan must be stressed (like problems related to gender or to other socio-economic factors).

## 3.1: Recent Evaluations of the Healthcare or Immunization System

| Name of the evaluation | Participating agencies | Principal outcomes in terms of infant mortality, vaccine coverage or weak points in the healthcare system | Dates |  |  |
| --- | --- | --- | --- | --- | --- |
| Niger, Demographic and Health Multiple Indicator Survey (EDSN-MICSIII) (appendix 5) | National Institute of Statistics (INS) and the Ministry of Public Health (MPH), with the financial and technical assistance of UNICEF, USAID and Macro International Inc. (USA), and contributions from the WHO, World Bank, UNDP, UNPF. | The data gathered in the field produced the following indicators:: - Infant mortality rate - Mortality rate for children below the age of 5 - Maternal mortality rate - Proportion of births assisted by a qualified worker - Proportion of children one year of age vaccinated for DTP3 - Proportion of children one year of age vaccinated against measles | 81/1000 198/1000 648/100,000 21.9% 39% 47.0% | January June, 2006 |  |
| Internal interim evaluation report of the Health development plan (HDP) 2005-2010 (appendix 7) | The MPH and teams of evaluators (internal and external) with the participation of independent consultants, Technical and Financial Partners (TFP) and broad participation by civil society and the private healthcare sector. | Principal outcomes - Percentage of the MPH budget in the State budget - Proportion of HF with personnel meeting the standards (CSI, HD, RHC) - Proportion of population with access to CSI offering MPA - Proportion of children one year of age vaccinated for DTP3 | 9.54 (2007) 46% (2007) 37 % (2007) 75% (2007) | October 2008 |  |
| Memorandum on the joint review of the healthcare sector (appendix 8) | MPH and partners (see Section 1.1 of the form for the composition of the Committee). | - Proportion of the healthcare budget allocated to regions and HD - Proportion of HF with personnel meeting the standards (CSI, HD, RHC) - Proportion completed or supervised by level - Rate of PNC coverage - Proportion of population with access to CSI offering MPA | 70.6% (2008) 43.97% (2008) 62.3% (2008) 81.25% (2008) 44.57% (2008) | February 2009 |  |

To the Applicant: section 3.2

- Please provide information on the main obstacles existing in the healthcare system blocking improvement in vaccine coverage that have been identified by the recent evaluations listed above (Table 3.1). The information must also stress any socio-economic or political reason as well as the role of men and women in society, the family or the working age population, attitudes toward boys and girls as well as any perceptions that may affect the vaccine coverage of specific ethnic groups or men and women.

## 3.2: Main obstacles to improvement in vaccine coverage identified by recent evaluations

The recent evaluations done identified the obstacles and inadequacies in terms of implementing the HDP, which affect the health of the people, particularly immunization. Such inadequacies identified have given the Ministry of Public Health the information needed for decision-making to design a new HDP for 2011-2015. The preparatory document drafted specifies that the future HDP will be based on the following two principal areas: - One area devoted to “strengthening the healthcare system,” which must overcome the current inadequacies in the healthcare system and give it all the capability necessary to reach the objectives, - One area devoted to “operation of the healthcare system,” which must guarantee the availability of the human, material and financial resources to achieve the objectives to be set. The main obstacles identified by these recent evaluations relate to the following areas:: - Provision of healthcare services, - Human resources, - Health information, - Drugs, vaccines and technologies, - Health funding, - Leadership and Governance. - Provision of healthcare services Poor physical accessibility is noted (0-5Km), especially in rural areas. Integrated Health Centers (CSI) offering the minimum package of activities (MPA) including primary care. Thus 44.6 percent of the population lacks access to MPA owing in part to insufficient coverage and in part to problems reaching vulnerable populations like nomads. The poor quality of patient care and facilities that results in poor performance in terms of reproductive health, outdated healthcare facilities (HF), insufficient supervision in terms of quantity and quality, poor cold chain availability, poor availability of means of transportation, insufficient management of biomedical waste and poor coverage of healthcare facilities in terms of drinking water and basic sanitation. - Human resources - Poor distribution of human resources at all levels of the healthcare system, marked by an insufficient number of healthcare workers in the health departments. On the one hand, 52 percent of the CSI have manned by a single healthcare worker, the six regional hospitals (2nd referral) are lacking in specialists; on the other hand, there is insufficient training of healthcare workers regarding the poverty of parents of school children in terms of financing their studies, especially in the rural areas. - Lack of quality personnel Related in part to poor training and skills and in part to poor motivation of workers. Thus the evaluations reveal inadequate patient treatment and a low satisfaction rate at the community level. - Health information - The inadequacy of the health information system results in problems transmitting comprehensive quality data within the deadlines and insufficient data processing. Furthermore, the data gathered do not provide information on gender, equity and governance (transparent resource management). - Drugs, vaccines and technology - Weakness in the drug and quality medical supplies supply chain leading to frequent interruptions at all levels. - Insufficient bio-medical materials and laboratory reagents. - Health funding The evaluations show a low level of funding of the health sector. The percentage of the State budget allocated to the health sector is 9.78 percent in 2008 while the African heads of state have set an objective of 15 percent. Around US18 per capital is devoted to health expenses compared with the $34 to $40 recommended by the WHO. - Governance/Leadership # Owing to inadequate governance, there is poor management capability at all levels of the healthcare system. The central departments suffer from compartmentalization. This prevents communication among the central departments, on the one hand, and between the MPH and the other levels of the pyramid. There is also insufficient decentralization in terms of human resources. # These evaluations of the sector also show major interference by political, socio-economic and cultural factors that hinder the management, availability and use of healthcare services, i.e.: # The poor state of the roads, reducing the accessibility of some villages to vaccine activities # Some socio-cultural behaviors that are harmful to health, and taboos (food, female circumcision, premature marriage, religious fundamentalism, etc.) # The low percentage of girls in school and the low literacy rate of the population in general # The low income of most of the households (62.15 of the population lives on less than a dollar a day) # The more recent lack of security in some parts of the country # Seasonal migrations of workers to neighboring countries.

To the Applicant: section 3.3

- Please provide information on the obstacles treated adequately with existing resources (Table 3.3). These may be socio-economic, political or related to gender, in accordance with the research done in the social sciences.

## 3.3: Obstacles treated adequately with existing resources

# The MPH is in the process of resolving the inadequacies identified in collaboration with the local authorities and the community, the partners and NGOs.

# Provision of services

In terms of accessibility

The care offered in the public health system is distributed by a network of healthcare facilities that currently includes 711 CSI and 1951 healthcare huts, all operational. Still to increase this supply of quality care, 131 healthcare huts were converted to CSI (scaled down variety in 2008) and 150 will be converted every year. Furthermore, some CSI offer Sexual and Reproductive Health services to teens and youth (SSRAJ). Routine EPI activities were strengthened by holding supplemental immunization campaigns (LVD, NVD). In addition, the MPH has undertaken to build and equip six regional “Maternal-child” centers and promoted the organization of health fairs integrated mobile teams .

In terms of financing, mother and child pairs are treated free of charge for the following (prenatal consultation, free care for children up to age five, gynecological cancers, contraceptives and cesareans). However, childbirth and other obstetrical complications are not free of charge.

In terms of the quality of care

The MPH has rehabilitated several healthcare facilities with the support of the partners. This includes gas supplied to all the healthcare facilities by the State, the local authorities, the communities and some TFP, ONG and Associations. This also involved the acquisition of cold chain equipment and means of transportation for supervision.

Human Recourses

In terms of human resource management, efforts were made through the recruitment of 362 healthcare workers (all categories combined) in 2007, bring the total workforce to 7,376 at year-end 2008. In addition, 1,811 nurses or community health workers (CHW) were hired for the healthcare huts in operation. Specialists were trained in HIPC funds and other partner funds. Human resources management was decentralized with the creation of a human resources management office (BGRH) and the assigning of human resource managers to every DRSP (Regional Public Health Department). The government has also introduced financial incentives to encourage workers to work in rural areas. It also promoted the introduction of incentive bonuses (e.g., allowances for risk or hardship or duty-related bonuses).

In the area of the quality of human resources, the MPH has trained specialists in various areas, and provided on-the-job training at all levels. It also designed and adopted a National Contractualization strategy (NCS) and developed tools and procedures to implement it.

Health information

The MPH has equipped 60 percent of the CSI with BLU communications radios, including training in their use and preventive maintenance. It has equipped the central level, the Regions and the health districts with computer equipment and connections to the web. It has trained personnel to staff the epidemiological surveillance centers (ESC) as well as the regional planning and health information centers in the area of epidemiological surveillance in the field.

Drugs, vaccines and technology

The healthcare facilities are supplied every year by the State, cost recoveries and the partners. Under the Initiative for Vaccine Independence in Africa (IIV), the State pays for vaccines and medical supplies. It also buys and maintains bio-medical equipment. The TFPs also contribute to supplies of ESDs, vaccines and medical devices at all levels.

Health funding

From 2006 to 2007, the healthcare budget allocated by the State changed significantly, from 7 percent in 2006 to 9.54 percent in 2007 of the general budget of the State. In 2009, it rose to 9.81 percent of the general budget, still below the 15 percent objective set by the conference of African heads of state and government in Abuja in Nigeria in 2001. Moreover, free care was introduced for children below the age of five, women for contraception (family planning), caesarians, PNCs and the treatment of gynecological cancers. A specific line item for the purchase of vaccines was added to the State budget (841,094,000 CFAF in 2008) to guarantee vaccine independence. A law was passed on developing healthcare mutuals in Niger with the creation of a few mutuals, with initiatives for medical coverage in some companies. The MPH has designed and adopted the basic documents for the creation of a healthcare social fund.

Governance

For better management of healthcare services, the MPH has adopted several laws, regulations and strategic documents, e.g., the HDP issued under the ADPRS, Health development plans from the Districts (DHDP), the 2008-2010 MTFSE (medium term framework for sector expenses), the “Country Compact” in the process of being drafted, the hospital reform, the national strategy for community participation (decentralization of CSI and healthcare hut management) and contractualization. It is in the process of creating an intranet system connecting the MPH and decentralized departments. A liaison office has been established between the MPH and the TFPs at the national and regional levels. A law on the exercise of private healthcare was enacted as well as the decree on the structure of the MPH. Healthcare committees were created at all levels of the system to facilitate the involvement of communities in healthcare management. In addition, 60 percent of the State healthcare budget was allocated to decentralized structures and 40 percent to the central level. Bills on hospital reform now pending will make it possible to design a healthcare map, a patient charter and to implement hospital construction projects.

# However, there are still some inadequacies that the MPH aims to resolve with the support of its partners.

To the Applicant: section 3.4

- Section 3.4 must stress the most important obstacles not treated adequately, giving the reasons why they are designated as priorities compared to those not currently funded by other sources, such as those that will have a maximum impact or that will serve as catalysts for other activities for geographical or social reasons. If there is an obvious lack of a national policy emphasizing an approach based on Human Rights for access to healthcare services (including for reasons of gender) or a lack of skills at different levels of the healthcare system, it must also be mentioned here.

## 3.4: Obstacles not treated adequately (in order of priority)

In connection with the strengthening of its healthcare system, Niger designed a national strategy that was adopted by the players in the field and the TFPs in a workshop held in Niamey on March 13-14, 2009. Through this strategy, the Ministry of Public Health aims to raise funding from all the TFPs to develop the sector. Regarding the role played in strengthening the healthcare system by each technical and financial partner, funding for the HSS strategy will be broken down in accordance with priority intervention areas.

For the request to GAVI for support, it will focus on part of the six areas mentioned in the analysis of insufficiencies not treated adequately. These are listed below.

- Provision of services

- 14 districts with poor physical accessibility with vast stretches of land do not perform the integrated mobile activities due to the lack of material and financial resources.

- The poor quality of patient care and treatment results in poor performance in terms of reproductive care, outdated healthcare facilities, insufficient supervision in terms of both quality and quantity, an insufficient cold chain and a shortage of means of transportation, insufficiencies in the management of bio-medical waste and healthcare facilities lacking a drinking water supply system and basic sanitation.

II. Human resources

- Poor distribution of human resources at all levels of the healthcare system, marked by a lack of sufficient healthcare workers in the health departments. Thus as recently as 2008, 52 percent of the CSI are manned by a single healthcare worker and the six regional hospitals (2nd referral level) are lacking in specialists.

- Lack of quality personnel

Due in part to poor training and in part to a lack of worker motivation.

III. Health information

- Problems transmitting comprehensive quality data within the deadlines, insufficient data processing. In addition, the data gathered do not give information on gender, equity or governance (transparent resource management). In fact, the latest DQS dates back to 2003.

IV .Governance

The 2005-2010 HDP is nearing the end, as is the cMYP for 2007-2010, which would limit continued attempts to receive funding for immunization activities at all levels and would delay the signing of the country compact, the implementation of the HSS strategy as well as all the interventions that will have to be conducted by the players for the development of the sector.

To the Applicant: section 3.5

- Section 3.5 must present the barriers encountered by civil society and the private sector in performing immunization services and strengthening the health systems and in taking part in the national process to increase vaccine coverage.

## 3.5: Describe the specific obstacles encountered by civil society and the private sector in performing immunization services and strengthening the healthcare system and in taking part in the national process to increase vaccine coverage.

There is little participation by the private sector or civil society in implementing immunization activities.

There are several reasons for this:

- The national policy requires all children to receive vaccines free of charge.

- Most of these private entities do not have certified cold equipment, which limits their ability in this area.

- Services are rendered free, which does not suit the private entities.

- Civil society entities are lacking in capacity and they are more motivated to engage in awareness activities more in the area of HIV/AIDS.

Despite the insufficiencies listed, efforts are under way to involve more private entities in immunization activities as a medical gesture.

In terms of listing the support of citizens for immunization, civil society through NGOs and associations are our special partners in this area. This request calls for the lead teams (equipes cadre) to arrange social events with the private sector. The private health schools are also involved in implementing the activities of this request.

In addition, ROASSN (the Network of Organizations and Associations in the Health Sector) is a member of the health sector improvement task force created by the Ministry of Public Health for the purpose of preparing funding applications to be submitted to The Global Fund and to GAVI. In order to produce these applications, many meetings and discussion sessions have been held. The ROASSN representative actively participated in the preparation committee meetings. ROASSN is also a member of the Technical Health Committee and the National Health Committee. These entities reviewed, amended and approved the aforementioned applications.

In order to implement its sectoral health policy, the Ministry of Public Health (MSP) also prepared a contractualization strategy in 2009. Therefore, the MSP has a formal framework for civil society's participation in all types of health-related activities. Civil society organizations are, at all times, fully involved in all types of health-related actions through their mobilization of communities in order to access and use health services. Government entities very often rely on these organizations to carry out awareness-raising activities in order to make positive changes in public health, maintain an environment that promotes good health and fight certain emerging or vaccination-preventable illnesses.

In the context of this application, they will be used to mobilize communities around vaccination, specifically in areas that are difficult to access. They will also be a part of the vaccination committees and teams; they will play an important role in contributing to vaccination activities. They will also be directly involved in carrying out activities related to providing health services and to governance and health information. Members of civil society also participate in yearly site visits that the MSP organizes together with health sector partners.

Regarding monitoring and evaluation of the HDP, the private entities are participating in this process as member of the bodies at different levels of the system.

# Section 4: Goals and objectives of HSS support from GAVI

To the Applicant: sections 4.1 and 4.2

- Please describe below the goals of HSS support from GAVI  (table 4.1).

- Please describe (and number) the objectives for HSS support from GAVI (table 4.2). Please make certain that the objectives chosen are SMART (Specific, Measurable, Acceptable, Realistic and Time bound)

- This section must demonstrate a) why the objective proposed for HSS is supposed to maintain vaccine coverage and b) how the activities proposed will ensure that the HSS objectives will be met. Therefore it is very important to show the links between the obstacles – goal – objectives – activities and indicators. They must follow a logical sequence, and different outputs outcomes and processes must be identified. It must also appear obvious how the activities proposed will improve or maintain vaccine coverage.

- Geographical questions: If a separate subregional area was selected for an intervention, it must be clear how and why the area was selected and the reasons must be given for the specific geographical indicators and criteria.

- All supporting documentation and contextual information (like the Human Rights Policy, document number…, the procurement policy, document number…the medium term expense framework, document number…) must be cited here and references must be identified in terms of sections and page numbers referred to in the document.

## 4.1: Goals for HSS support from GAVI

Contribute to an improvement in the state of health of the population in general and maternal child health in particular.

## 4.2: SMART objectives for HSS support from GAVI

| To reach this goal and reduce existing inadequacies and bottlenecks, the TF has determined the following objectives and expected outcomes: Specific objectives Objective 1: Increase the proportion of the population with access to the MPA from 44. 6% to 50 % by improving immunization coverage in children below the age of five by the end of 2010; Objective 2: Provide the central level within the deadlines comprehensive and quality data from at least 70 percent of the healthcare facilities by 2010; Objective 3: Support the preparation and adoption of a new 2011-2015 health development plan; Objective 4: Support the preparation and adoption of a new comprehensive multi-year immunization plan for 2011-2015. The outcomes expected are listed below: - Improvement in material and logistical resources to enable healthcare personnel to offer the MPA (minimum package of activities) in healthcare facilities for the most remote populations; - Improvement in the quality, availability and use of healthcare information at all levels, particularly at the district and CSI (integrated healthcare center) levels. - Improvement in the planning process so as to enlist more financial resources to implement the healthcare policy by preparing two documents (the HDP and the cMYP). Justification Objective 1: The MPH has undertaken reforms aimed at strengthening the healthcare services of the districts in order to improve access to healthcare. However, although the network of healthcare facilities was expanded, access by the population to the MPA remains low (44.6%). In addition, the major deficit in personnel is such that healthcare activities, as well as vaccine activities are mostly conducted in limited locations within a radius of 0 – 5 kilometers. Thus health fairs and mobile teams designed for people living within a radius of more than 15 km and nomads are not properly implemented because of the immensity of the land; thus coverage remains inadequate. Because of the personnel deficit, it is not possible to offer a complete MPA. Mobile vaccine activities are done from health districts by teams of four workers (from several different healthcare facilities) on average to cover 20 to 30 villages per trip for around ten days. A pilot experiment with a mobile team offering a complete MPA is under way in three districts (Kollo, Say and Tchintabaraden). The country’s goal is to expand this promising experiment to 14 more healthcare districts (Tchiro, Guidan Roumdji, Abalak, Tahoua, Nguigmi, Maïné, Tanout, Gouré, Dakoro, Mahayi, Tessaoua, Doutchi, Filingué and Oualam) covering a broad stretch of land that is hard to reach, has poor healthcare coverage and is inhabited largely by a very poor nomadic population. The choice of these Health districts meets the concern for improving the performance of healthcare services including immunization services. To do so, the criteria defined below have been selected. - Performance of DTP3 (Coverage below 80%) - Performance in TT2+ (TT 2+ among pregnant women below 80%) - Healthcare coverage (Coverage within a radius of 0 – 5 km below 80%) - PNC coverage in 2007 (below 80%) - Promptness in transmitting monthly EPI reports in 2008 - Availability of healthcare workers in the healthcare facilities in accordance with the standards This requires mainly the following: - Equipping 14 health districts with vehicles and 156 CSI with motorcycles so they can travel to as many people as possible who do not have access to healthcare services (sparsely populated hard-to-reach areas), - Arranging integrated mobile trips and health fairs to make health services and care accessible to people not covered by activities conducted at fixed locations. To reduce the other factors that explain the poor MPA coverage: for example, the lack of motivation on the part of workers, and in particular the insufficient number of workers in rural areas, the poverty level of the population (62.1 % live below the poverty line. (Source: Accelerated Development and Poverty Reduction Strategy, 2005 report, page 35), the paucity of information for the population on the advantages of healthcare services and on some negative perceptions regarding health, the following actions are planned: - Motivating and providing performance incentives to healthcare personnel to improve the quality of care and obtain the best results; - Enlist the support of the community so that people can adopt a behavior aimed at improving their state of health and so that the healthcare system can develop. Objective 2: Effective and timely decision-making in terms of care and planning is contingent on producing, analyzing and providing quality health information. However, the availability and archiving of data at the different levels of the system are compromised by the lack of means of communication and of health workers in the required quantities with the required level of quality. Moreover, the multiplicity of the tools used to gather data related to the specific needs of the different programs also interferes with the quality of the data-gathering process and the analysis of the data. In the face of all these problems, the MPH plans to use the GAVI funds for the following purposes: - To acquire communications equipment to facilitate the transmission of data and referrals and cross referrals; - To strengthen the monitoring and evaluation of the information system activities (DQS) to improve data quality. Objective 3: Raising the financial resources needed to resolve the most pressing health problems of the population requires the existence of a general frame of reference for interventions for all the players in the healthcare sector. To that end, back in 1994, Niger prepared an initial development plan for 1994-2000, then a second plan for 2005-2010, which ends in 2010. Thus, so that all the players can continue to pursue interventions in a coordinated and efficient manner, the MPH is planning to prepare and adopt a new health development plan for 2011-2015. This means carrying out the following activities: - Recruiting national and international technical assistance to support the preparation of the 2011-2015 HDP, - Conducting missions in the field to visit all the regions to take into account the healthcare needs of the people of all the districts in the new HDP for 2011-2015, - Holding several meetings for amendments, prevalidation and validation of the new HDP in order to obtain a document based on a consensus by all the players in the sector, including the communities and Nigerien private entities, - Have the 2011-2015 HDP adopted by the government of Niger, - Distributing the new HDP document at all levels of the healthcare pyramid. Objective 4: Maintaining and expanding vaccine coverage are contingent on the existence of resources needed to fund vaccine activities. Raising these resources is definitely related to the comprehensive multiyear plan for immunization. However, in Niger this plan comes to an end in 2010. This means a new plan must be prepared and adopted by the government. The purpose of that plan is to establish a framework for the strategies and different interventions to be carried out in the next five years. The plan will be prepared and adopted through an interactive iterative process by means of the following activities: Recruiting national and international technical assistance to support the preparation of the plan, Evaluating the 2007-2010 cMYP to identify any inadequacies and introduce the necessary measures to correct them, - Organizing a data-gathering mission at all levels to take into account the immunization needs of all the health districts, - Holding several meetings at the national level to prepare and submit the draft document to the different players involved in vaccine activities. Adoption of the document by the government of Niger, Distribution of the document to all levels of the healthcare pyramid. |  |
| --- | --- |

# Section 5: Program of activities and application of the GAVI HSS

To the Applicant: section 5.1

- Please explain below plans for maintaining (both financially and technically) the impact obtained with the support from the GAVI HSS (5.1) when the resources of the GAVI HSS are no longer available.

NB: The mechanisms for technical and financial viability must be described with special attention to GAVI support concerning efforts to develop infrastructures, equipment, transportation and human resources. This must include how these investments will be maintained once support from GAVI has ended. Reference must be made to policy documents or documents stating the infrastructure, procurement or human resource development strategy (document number.(…) if any.

NB: GAVI recommends that the GAVI HSS support few priority objectives and activities  at once. It must be possible to apply, control and evaluate the activities during the time allowed for validation of HSS support from

- For every SMART objective identified, in table 4.2, list the main activities to be undertaken to meet this objective. Include the implementation plan (duration, annual steps and end point, as the case may be) for each of those activities.

- Make certain that the timetable for the activities in table 5.2 is consistent with the expense timetable for each activity mentioned in table 5.3.

## 5.1: Viability of HSS support from GAVI

GAVI support will be sustained from a financial, human, material and technical standpoint through the joint actions of the Government, local authorities, communities and partners. - In the area common to all the activities (Obj.1, 2, 3, 4): - In the analysis section, it is stated that the State budget has gradually changed starting in 2006. However, funding remains low compared with the 15 percent recommended by the meeting of the Heads of State in Abuja in Nigeria in 2001. If current trends towards an increase in GDP continue, along with an increase in funding for the sector, the State will be able to fund any recurring costs incurred by the end of the project. - In terms of decentralization, the local authorities are contributing to healthcare funding. In 2008, the contribution by the local authorities and the private sector was 2 percent (MT/FSE 2008-2010: appendix 4) of the health budget. However, there are plans in the decentralization law for at least 8 percent of the budget of local authorities to be devoted to health. The contribution by households accounts for a substantial part of the expenses (treatment costs, purchases of gas-powered cold chain, fuel support for health fairs, support for the maintenance system for infrastructures and equipment). The coordinating bodies in charge of liaison with all the players in the healthcare sector on the healthcare committees at all levels specify the funding and management terms and conditions. With the sector approach under way (with a common fund), Niger is committed to preparing a Country Compact with the partners. - Other TFPs such as the Global Fund and the partners belonging to Niger’s common healthcare fund are committed to the funding of annual plans as well as the implementation of the Healthcare Strengthening System Program (appendix 1). The support requested from GAVI will be used in this context. It will enable the healthcare sector to increase expenditures on vehicles to carry out activities designed for populations in the most isolated areas. Subsequent operating costs will be covered by Niger’s healthcare budget. - These logistical resources will be used to fund trips for health fairs and integrated mobile teams in areas where the population does not have access to the minimum package of activities (MPA). - Health fairs involve prenatal consultations, infants, immunization, nutritional monitoring, family planning and IEC by CSI health workers in some villages of their healthcare area located farther away than 5 km. - Integrated mobile outreach trips are integrated consultations conducted in outlying villages. Those activities that cover all the components of the MPA are conducted by a team of district health workers. The trips are made using 4 x 4 vehicles equipped with means of communication, immunization supplies, equipment for examinations and treatment, as well as drugs and medical supplies. - The amount requested for these activities will be used to purchase fuel and to pay per diems for the health workers on assignment. - In the area of specific activities to strengthen health information (Obj.2) - The goal of the healthcare sector is to continue results-oriented management, which started with the implementation of the 2005-2010 HDP, thus focusing primarily on the need for an effective health information system. TFPs such as the European Union applying budgetary support with variable segments pegged to indicators share this concern. Theoretically more than 65 percent of healthcare facilities send in their reports within the deadlines set by the Ministry of Health However, this figure does not take into account the quality aspect of the data transmitted. - On the national level, in terms of statistics, major reforms under way have led to (i) the creation of the National Institute of Statistics (INS), one of the primary mandates of which is to supply the grassroots sectors, (ii) the conversion of the health information division into the Department of Statistics, Surveillance and Response to Epidemics (DSSRE), and (iii) the establishment of an intranet network between the INS, the MPH and the MEN. Revision of the computer program and security provided at the national level (eliminate foreign dependence). - This future environment favorable to increased funding in the area of health information will make it possible to (i) acquire equipment, (i) train and supervise health workers in its use and (ii) establish a regular intervention maintenance and monitoring system.

To the Applicant: section 5.2

- NB: Please add or (erase) the lines so that table5.2 contains the correct number of objectives for your HSS application to GAVI and the correct number of activities for each of your objectives.

- NB: Please add (or erase) the years so that table 5.2 shows the duration of your HSS application to GAVI

- NB: The budget for the first year must show the use of the costs per unit and a breakdown of the budget. This will help to achieve consistency and realism in the proposal, especially for any activity that includes major components for training or procurement. The budgets must be based on real costs and not contingencies.

- For each of the objectives identified in table 4.2, please give details of the main activities to be undertaken to meet the objectives set and comply with the implementation program for each of those activities throughout the duration of the HSS support from GAVI.

## 5.2: Principal activities and implementation program

| Principal activities | Year 1 (20…) |  |  |  | Year 2 (20…) |  |  |  | Year 3 (20…) |  |  |  | Year 4 (20…) |  |  |  | Year 5 (20…) |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 |
| Objective 1: Increase the proportion of the population with access to the MPA from 44.57% to 50% by the end of 2010. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 1.1: Equip 14 health districts with vehicles (including GPS) to conduct integrated mobile activities | X | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity1.2 : Equip 156 CSI with motorcycles to conduct health fairs at villages located farther than 5 km | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 1.3: Organize an integrated trip 7 days a month by District in the 14 districts throughout the year to reach the villages out of range | X | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 1.4: Organize a health fair one day a week per CSI for the 52 weeks of the year x 280 CSI | X | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 1.5: Equip the CSI of the 14 health districts with cold chain equipment to better preserve antigens. | X | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 1.6: Give incentive bonuses for the performance of health services in the districts and CSIs. | X | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 1.7 Hold health information sessions for the populations of isolated villages through community radio stations | X | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 1.8 Arrange trips to enlist community support before integrated mobile activities in areas not covered | X | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 1.9 Arrange trips to enlist community support for the populations of the villages targeted by health fair activities | X | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 1.10 Conduct regular integrated supervisions at all levels of the system |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Objective 2: Provide the central level within the deadline comprehensive quality data from at least 70 percent of the healthcare facilities by 2010 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 2.1: Put in place a fleet system for 98 CSI for referrals and cross referrals to hospitals | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 2.2: Maintain the (42) existing SSB radios at the 14 health districts | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 2.3: Conduct an evaluation of the quality of the EPI data (DQS) | X | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Objective 3: Support the preparation and adoption of a new 2011-2015 health development plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1: Recruit international technical assistance in the 2nd quarter of 2010 for 9 months |  | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2: Organize missions at the health districts to support and revise the current DHDPs |  | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.3: Support mission to regions to revise the current RHDPs |  | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.4 Hold a workshop to prepare the first draft of the 2011-2015 HDP in Niamey for a period of 10 days |  |  | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.5: In each region hold a meeting to amend the new HDP |  |  | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.6 Hold a meeting to amend the draft of the 2011-2015 HDP at the central level |  |  |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.7: Hold a consensus and validation meeting for the new 2011-2015 HDP for a period of 5 days for all the players in the health sector including civil society |  |  |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.8 Have the draft 2011-2015 HDP adopted by the government in December 2010 |  |  |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.9: Reproduce and distribute the new 2011-2015 HDP document to all the levels of the healthcare pyramid and to the TFPs and members of civil society |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Objective 4: Support the preparation and adoption of a new comprehensive multi-year immunization plan for 2011-2015 by the end of 2010 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.1: Recruit international technical assistance to evaluate the 2007-2010 cMYP and prepare the 2011-2015 cMYP at the end of the 2nd quarter for 3 months |  |  | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.2: Evaluate the 2007-2010 cMYP 2007-2010 |  |  |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.3: Organize data gathering missions in the health districts to support the evaluation of the cMYP |  |  |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.4: Hold a workshop to prepare the cMYP document in Niamey for a period of 10 days |  |  |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.5: Hold a 5-day national consensus workshop for all the players focused on the cMYP document |  |  |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.6: Have the draft 2011-2015 cMYP adopted by the government in December 2010 |  |  |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.7: Reproduce and distribute the new 2011-2015 cMYP document to all levels of the healthcare pyramid and to the TFPs and members of civil society |  |  |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

## 5.3: Plan showing the figures for implementation costs for the first year

To the Applicant : section 5.3

NB: The plan for the first year of implementation must be defined in section 5.3, giving the details on the chronology, the contributions, the outputs and the processes that will be monitored with a breakdown of the costs (and the unit costs at least for the first year of implementation).

Objective I: Increase the proportion of the population with access to the MPA from 44.6 percent to 50 percent by the end of 2010:

Total amount for Objective I of the project: USD 2,870,782. Most of this budget is intended for the purchase of fourteen 4 x 4 equipped vehicles, 156 DT 125 all terrain motorcycles, refrigerators, cool boxes and other cold chain equipment These purchases will be made through a call for tenders. The other costs for operations will be decentralized and provided to the health districts that already have a bank account for that purpose.

Objective II: Provide the central level within the deadlines comprehensive and quality data from at least 70 percent of the healthcare facilities by 2010:

Total amount for Objective II of the project: USD118, 980

Objective III: Support the preparation and adoption of a new 2011-2015 health development plan

Total amount for Objective III of the project: USD 631,805

Objective IV: Support the preparation and adoption of a new comprehensive Multi-year immunization plan for 2011-2015

Total amount for Objective IV of the project: USD 214,582

Cost of project monitoring and evaluation = 2 percent of the total project amount: USD 76,723

Project management cost = 2 percent of the total project amount: USD: 76,723

Total Project Amount: USD 3,989 596

# Section 6: Monitoring, evaluation and operational research

To the Applicant : sections 6.1, 6.2 et 6.3

NB:  It is highly recommended that the indicators chosen be connected to the objectives of the proposal and not necessarily to the activities. Where possible, use and provide specific data broken down by sex and age.

- For the indicators please give a data source, the reference value of the indicator and the date and a level targeted on a given date. Some indicators may have more than one data source (table 6.1)

NB: The indicators chosen must be taken from those used for monitoring the National Health Plan (or its equivalent) or the cMYP, ideally already measured (e.g. not a new indicator selected specifically for support for the HSS from GAVI). Some examples of additional impact and outcome indicators are given in the tables below. It is recommended that when the activities are implemented on a sub-regional level, the indicators are monitored insofar as possible at the sub-regional level as well.

- All the data presented in this application form must be consistent with the other proposals and reports to GAVI and with the other official health reports and documents. Any difference between those data and the data presented in this proposal or in the annual status reports to GAVI must be duly explained and justified. This is especially important for the birth cohort, the targeted populations and the rates of coverage.

- All applications must name a point of convergence in the governmental departments supervising the monitoring and evaluations of the proposal for HSS support from GAVI.

- All applications must include GAVI’s three principal HSS impact and outcome indicators:

- Rate of national coverage for DTP3 (%)

- Number / % of  districts reaching  ≥ 80 % of DTP3 coverage

- Under five mortality rate (per 1000)

- Please indicate three other impact/outcome indicators that can be used to evaluate the impact/outcome of HSS support from GAVI in the improvement of immunization and other maternal child healthcare services in table 6.1 below.

- Please list at least six output and process indicators in tables 6.2 and 6.3 below.

- For all the indicators, please give a data source, the reference value of the indicator and the date and an objective for that level by a given date as well as a numerator and a denominator

- Some indicators can have more than one data source.

- Reference values must be noted for all the indicators and there must be a process indicator for each objective.

NB: The impact/outcome and output indicators may be found on the following web site: www.unep.org/Terminology.pdf. An HSS monitoring “toolbox” is available on the WHO web site: http://www.who.int/healthinfo/statistics/toolkit_hss/EN_PDF_Toolkit_HSS_Introduction.pdf

NB: Some examples of outcome, output and process indicators are given below. Existing information sources must be used to gather the information on the indicators chosen wherever possible. In some countries, it may be necessary to conduct surveys on healthcare equipment and households or make demographic observations. If additional funds are necessary for these activities, they must be included in this application.

Examples of outcome indicators - related to the GAVI HSS objectives (note that these are only examples)

| Objective | Possible indicators |
| --- | --- |
| Improve access to MCH services | % of coverage against measles (children under 2); % of births assisted by a registered midwife; % of contraceptive use in women between 15 and 44 % of children under 5 sleeping under mosquito nets treated with insecticide. |
| Improve the quality of healthcare services | % of the population reporting they have received good quality healthcare services; rate of decline of DTP3-DTP1. |
| Improve equality in coverage of primary healthcare services | Rate of DTP3 coverage as a % per quintile of income. |

Examples of output indicators (note that these are only examples)

| Strategy | Indicator | Numerator | Denominator | Data source |
| --- | --- | --- | --- | --- |
| Support for more expenditures on primary healthcare | General healthcare expenditures by the government in proportion to total expenditures by the government | Total government health expenditures | Total government expenditures | Government budget |
| Strengthen the national information system for health management | % of the districts that have submitted on time comprehensive, precise reports to the national level | The number of districts that have submitted on time comprehensive, precise reports to the national level | The total number of districts | Health information system |
| Strengthen supervision of community nursing personnel | Systematic supervision | Number of healthcare centers visited at least 6 times in the past year, using a quantified check list | Total number of healthcare centers | Surveys on healthcare facilities |
| Strengthen human resources capacity | Knowledge of healthcare personnel | Average score of the healthcare personnel in the public health and NGO centers on the oral test on knowledge including case studies |  | Surveys on healthcare facilities |
| Strengthen management and logistics systems | % of facilities with medical equipment tracking the date of the appointment and in the last three months | The number of facilities that have in stock specified tracking equipment (existing and not expired) to track the date of the appointment during the specified reference period (past three months) | The total number of facilities | Health information system and surveys on healthcare facilities |

Examples of process indicators (note that these are only examples)

| Activity | Possible indicators |
| --- | --- |
| Build 280 healthcare centers in rural areas | Number of healthcare centers built |
| Obtain 1,000 motorcycles for the nursing personnel of the community | Number of motorcycles received |
| Train healthcare personnel in family planning methods | Number of qualified healthcare workers |
| Obtain reliable child birthing kits | Number of reliable child birthing kits obtained and delivered |

## 6.1: Impact and outcome indicators (the data must be consistent with the other applications to GAVI and with the country’s annual status reports)

| Indicator | Data source | Reference value | Source | Reference date | Objective | Date of objective |
| --- | --- | --- | --- | --- | --- | --- |
| 1. National DTP-HepB-Hib3 coverage (%) | Annual EPI Activity Report | 89% | Annual 2008 EPI Activity Report | 2008 | 95% | 2010 |
| 2. Number / % of districts reaching ≥ 80 % DTP-HepB-Hib3 coverage | Annual EPI Activity Report | 37/42 (88%) | Annual 2008 EPI Activity Report | 2008 | 100% | 2010 |
| 3. Mortality rate of children under five (per 1,000) | EDSN/MICS3 2006 | 198/1000 | (EDS, 2006) | 2006 | 108/1000 | 2010 |
| 4. Actual national DTP-HepB-Hib3 coverage (objective N°1) | EPI, WHO or Gavi Survey Report | Baseline survey to be planned | CTNS Memorandum | Survey result date | 90% | 2010 |
| 5. Data verification factor or data consistency index (%) (Objective N°2) | Monthly reports from the HF and immunization team time sheets | DQS to be conducted in December 2010 | Audit Report (DQS) 2010 and 2013 | 2010 | 80% | 2010 |
| 6. National DTP-HepB-Hib3 coverage (%) | Annual EPI Activity Report | 89% | Annual 2008 EPI Activity Report | 2008 | 95% | 2010 |

## 6.2: Output indicators (one per objective)

| Indicator | Numerator | Denominator | Data source | Reference valueError: Reference source not found | Source | Reference date | Objective | Objective date |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. Proportion of the population with access to the MPA | Population within a radius of 0-5km from the CSI offering the MPA | Total population of Niger | SNIS reports | 44.6% of centers with access to MPA | CTNS reports 2008 | 2008 | 50% | 2010 |
| 2. % of the districts that have submitted comprehensive quality reports within the deadlines to the national level | The number of districts that have submitted comprehensive quality reports within the deadlines to the national level | Total number of districts | Health information system | An evaluation of the health information system (SNIS) is planned for June 2009 | SNIS evaluation report | 2009 | 70% | 2010 |

## 6.3: Process indicators (one per objective)

| Indicator | Numerator | Denominator | Data source | Reference valueError: Reference source not found | Source | Reference date | Objective | Objective date |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. Proportion of the districts conducting at least 10 integrated mobile trips in the year | Number of districts that have conducted at least 10 integrated mobile trips per year | Total number of HD (14) planned for integrated mobile trips | Quarterly reports from health districts, | Number of trips per year | SNIS Annual Statistics Directory | 2009 | 80% | 2010 |
| 2. Percentage (%) of healthcare facilities equipped with means of communication (GSM or SSB) | Number of HF with functional means of communication (GSM or BLU) | Total number of HF planned | Delivery report | 46.7% | Evaluation report on district operations | 2007 and 2009 | 80% | 2010 |
| 3. Availability of the 2011-2015 HDP | NA | NA | The HDP document | 2005-2010 HDP | NA | February 2006 | 100 % | 2010 |
| 4. Availability of the 2011-2015 cMYP | NA | NA | The cMYP document | 2007-2010 cMYP | NA | 2007 | 100 % | 2010 |

To the Applicant: section 6.4:

- Please describe how the data for the indicators specified were gathered and used. Existing data gathering and analysis methods must be used wherever possible. Please indicate how the data will be used at the local level and the means of communication with the other players in the last column of table 6.4 below.

- Data gathering: the level at which the data are gathered and who is responsible for gathering them

- Use of the data: the level at which the data are analyzed in broken down form and who is responsible at the local and central levels for ensuring that the data are evaluated and analyzed.

- Use of the data: how these data on indicators will be used to evaluate the performance and correct and develop plans and strategies.

6.4: Data gathering, analysis and use

| Indicator | Data gathering | Data analysis | Use of the data |
| --- | --- | --- | --- |
| Impact and outcome |  |  |  |
| - National rate of DTP-HepB-Hib3 coverage (%) | The different outreach units (CSI and CS) gather the data targeted on the SNIS forms and produce the monthly or quarterly report. These data are gathered together at the district and regional levels for the production of the quarterly reports sent to the national level. | Every level of the healthcare pyramid does a systematic analysis so as to have monitoring indicators used for decision-making. A guide to calculating the HDP monitoring indicators is available at each level of the healthcare pyramid. | The data will be used at all levels for decision-making in relation to supervision, planning, monitoring, evaluation and research |
| - Number / % of districts reaching ≥ 80 %of DTP-HepB-Hib3 coverage | As indicated above | As indicated above | As indicated above |
| - Mortality rate of children under five (per 1,000) | INS and EDSN surveys | Situational analysis | For planning, monitoring, evaluation and research |
| - Actual national DTP-HepB-Hib3 coverage (objective N°1) | Monitoring of the CSI | As indicated in indicator 1 | As indicated in indicator 1 |
| - Data verification factor or data consistency index (%)(%) (Objective N°2) | Surveys | The ECD, DRSP and SNIS do a systematic data analysis so as to have reliable indicators | The information will be used to validate the data transmitted before they are used. |
| Output |  |  |  |
| - Proportion of the population with access to the MPA | As indicated in indicator 1 | As indicated in indicator 1 | As indicated in indicator 1 |
| - % of the districts that have submitted comprehensive quality reports within the deadlines to the national level | As indicated in indicator 1 | As indicated in indicator 1 | As indicated in indicator 1 |
| Process |  |  |  |
| 1. Proportion of the districts conducting at least 10 integrated mobile trips in the year | As indicated in indicator 1 | As indicated in indicator 1 | As indicated in indicator 1 |
| 2. Percentage (%)of healthcare facilities equipped with means of communication (GSM or BLU) | Surveys | The DRSP and the MPH do a data analysis to have information on the availability of means of communication in the healthcare facilities | The data will be used to for the transmission and receipt of information among the healthcare units |

To the Applicant: section 6.5:

- Please indicate whether the monitoring and evaluation (M&E) system needs to be strengthened in order the measure the indicators cited, and if such is the case, describe which sectors of the M&E system specifically need strengthening (table 6.5)

NB:  The HSS resources from GAVI may be used to strengthen the health information system itself. If the country so decides, the investment will be harmonized with the support of other donors (like the Global Fund to Fight HIV/AIDS and tuberculosis and others). Countries may ask for HSS support from GAVI to include relevant data broken down by sex in their health information system.

## 6.5: Strengthening the M&E system

The monitoring and evaluation system was has been given a new lease on life in recent years in connection with the monitoring of HDP, cMYP and SDRP interventions. In preparing the HDP monitoring and evaluation plan, the Ministry of Public Health established a coordinating body, which is the Comité Technique National de Santé (CTNS) in charge of preparing and validating documents for the Conseil National de Santé (CNS). With this mechanism it has been possible to validate administrative and routine data, to plan and conduct periodic surveys in the field and interpret the results during periodic meetings of the CTNS. However, still needs to be strengthened for better data gathering and to be able to measure the key indicators listed.

The indicators will be measured by the system established within the National Health Information System (Système National d’Information Sanitaire) (SNIS). The GAVI implementation monitoring indicators will be included with the data to be gathered for the monitoring of interventions. Furthermore, the strengthening of the information system as called for in this application to GAVI will make it possible to better gather the data needed to produce the different reports.

Strengthening needs exist at different levels:

- Collection and transmission of quality data to the different levels of the health pyramid;

- Data analysis: support in terms of computer hardware and updating of the EPI and SNIS data gathering program;

- Training supervision;

- Communications with outreach and support structures.

The Annual Report prepared for GAVI

Activity report and financial report: This activity report will be produced by the Research and Programming Department (Direction des Etudes et de la Programmation) (DEP). The report will provide monitoring indicators and an overall view of the activities carried out in connection with the support.

Synthesis of progress reports

The annual synthesis of progress reports will give the degree to which the monitoring indicators have been reached, as well as inadequacies and suggested solutions. For specific indicators not included in the GAVI, the data will be collected from the healthcare units concerned through the SNIS.

To the Applicant : section 6.6:

- Please indicate whether the application for HSS support from GAVI includes elements of operational research dealing with certain barriers of the health systems to better information on decision-making processes. (table 6.6)

NB:  HSS support from GAVI may also be used for operational research such as an analysis of the reasons why the population is not able to access immunization services (be it for social, economic, political or gender reasons), which are aimed ultimately at equality of access to the services. This funding may also be used to test/examine specific strategies in order to see which ones work the best.

## 6.6: Operational research

Operational research is an integral part of the proposal. To that end, the MPH must identify the different bottlenecks as they appear that interfere with the proper implementation of the strategies and activities aimed at achieving the objectives. Therefore, research projects must be undertaken to identify and resolve any problems identified.

# Section 7: Implementation provisions

To the Applicant: sections 7.1 and 7.2

- Please describe how the HSS support from GAVI will be managed (table 7.1)  Please indicate also the roles and responsibilities of all the key partners in this implementation of the HSS support from GAVI. (table 7.2)

NB:  GAVI encourages countries to align the provisions for the implementation of the HSS support from GAVI with existing national mechanisms. Applicants are strongly encouraged not to establish a project management unit (PMU) for the HSS support from GAVI. The establishment of a PMU will be funded only under exceptional circumstances based on cogent reasons.

## 7.1: Managing the HSS support from GAVI

| Management mechanism | Description |
| --- | --- |
| Give the details on the costs and management mechanisms (especially if one partner will manage parts of the proposals for HSS support from GAVI | The management method proposed in this applications will be based on the current funds management mechanism, which is the common fund established for the implementation of the HDP The MPH has a TFP coordination mechanism in charge of managing the funding of activities at the central, regional and department level. |
| Name of the primary person/unit responsible for managing the implementation of the GAVI HSS support / M&E etc. | The SG of the MPH, coordinator of the common fund under fiduciary management. |
| Support coordination mechanism for the GAVI HSS with the other activities and programs to strengthen the health systems | The coordination mechanims will be the same in effect for the implementaton of the current HDP through the different monitoring and evaluation bodies and will be unitary management of all the aspects of the HSS financed by different sources. The 2011-2015 HDP will be based on two intervention approaches: “strengthening the healthcare system” and “operation of the healthcare system,” both of which are aimed at developing a single healthcare program. Every yeaar, an action plan is prepared, submitted to the CTNS and valideated by the CNS. The CNS authorizes the holding of activities and the corresponding expense commitment from all sources. The CNS and the CTNS will handle the coordination, monitoring and evaluation in connection with implementation. All the activities will be translated into the Annual Actions Plans (AAP) and discussed in the meetings of both committees. |
| Support coordination mechanism for the GAVI HSS with the other activities and programs strengthening the health systems |  |

## 7.2: Roles and responsibilities of the key partners (members of the HSCC and others)

| Title / Position | Organization | Member of the HSCC yes/no | Please list the specific roles and responsibilities of this partner in the implementation of the HSS support from GAVI |
| --- | --- | --- | --- |
| Minister in charge of Public Health | CNS | Yes | CHAIRMAN – he will give the overall guidelines |
| The Secretary General of the MPH. | CNS | Yes | EXECUTIVE SECRETARY - Prepares for CNS meetings; - Follows up on decisions by the CNS ; - Handles liaison between the CNS and the Regional Health Committees |
| The Secretary General of the MPH | CTNS | Yes | CHAIRMAN of the CTNS Will coordinated and supervise the implementation of the HSS support |
| The lead Technical and Financial Partner | TFP | Yes | As the lead TFP, it will mobilize resources from the partners, act as an intermediary between the TFP and the MPH and will facilitate communication between the MPH and the TFP. |
| ROASSN | NGOs and private sector | Yes | Players in the sector; they are involved in implementing social mobilization activities in communities, lobbying leaders and participating in health committee meetings at all levels, and in IEC and vaccination activities. |

To the Applicant : section 7.3:

Please provide information on the financial management of the HSS support from GAVI in table

NB:  Applications will not be examined or approved by the independent review committee (IRC) if the documents required on the financial provisions are not submitted with the completed application form.

NB:  The GAVI Alliance has adopted a Transparency and Accountability policy (TAP) for the financial sector, including HSS support from GAVI, which took effect on January 1, 2009.

NB: The Transparency and Accountability policy presents a series of minimum conditions required for the financial management of HSS support from GAVI.

- The funding must be used for objectives established in a proposal

- Funds must be managed in a transparent manner, and specific, verifiable financial reports must be produced regularly, as specified in the individual funding provisions

- Funds must be managed in accounts that meet the national legal conditions for audits, accounting and deposits.

NB:  In addition to the minimum financial management conditions above,

- Funds must appear in the national budget (be in the budget)

- Funds must supplement the appropriation by the government to the health sector, as well as any contributions by other partners. For example, no funding must be diverted from the health sector if HSS funds are received.

NB:  A condition required by GAVI Alliance requires all countries receiving HSS support to undergo a Financial Management Evaluation (FME) before the initial years of support are released.

## 7.3: Funding provisions

| Mechanism / procedure | Status / Description |
| --- | --- |
| Was a GAVI FME conducted? yes/no | No |
| When was the last FME conducted? month/year | NA |
| If yes, was a memorandum signed? yes /no (document number…..) | NA |
| If yes, will this memorandum govern the management of the HSS funds from GAVI? yes/no | NA |
| If not, reasons not to follow the agreements under the memorandum | NA |
| Next FME planned: month/year | The Ministry aims to conduct an evaluation before the end of the year |
| Has a joint funding mechanism been established for the health sector? yes / no | Yes. It is the Common Fund established in 2006. To date it has handled a significant part of the funding for the sector from the WORLD BANK and the AFD |
| If yes, will this joint funding mechanism be used to manage the HSS funds from GAVI ? yes /no (document number...) | YES. |
| If not, reasons not to use the joint funding mechanism | NA |
| Please provide a detailed description of the funding mechanism proposed for the management of the HSS funds from GAVI if all the agreements of the last memo are not followed or if one EGF must be followed | Management by the CF involves two kinds of accounts: A. The special account managed by the DRFM (Central level management center) Every six months the two TFP pay into the CF to cover midyear expenses attributable to the Common Fund. The amount of the midyear payments is assessed by the contributors based on the following: - Review of the Financial Monitoring Report (FMR) on supporting documentation for expenses, and internal and external audit reports, - The findings of the audit reports on the signing of contracts, - The data from progress reports and monitoring and evaluation of the HDP, - The results of entities under performance agreements, - Missions in the field - Requests by the MPH for midyear drawdowns from the funds/grants. B. Secondary accounts An account is opened in CFAF in a commercial bank for every DRSP and for every HD that are management centers. The Special Account pays into it quarterly. The amount paid in is calculated based on the following: - The amount of the AAP quarterly activities attributable to the HDP - CF, - The amount of additional midyear funds paid in by the Special Account of the HDP – CF., - Technical and financial management by the DRSP or the HD. Performance by the HD is evaluated by the DRFM. Performance by the DRSP is evaluated by the DRF/M. Performance is evaluated based on the FMR and supporting documentation for expenses incurred. The management controller is involved in this evaluation. |
| Titles of documents governing the annual budget projection process for the use of the HSS support funds from GAVI (document number appendix 16) | Manuel of administrative, financial and accounting procedures of the Common Fund prepared in June 2006 and updated on August 27, 2008 |
| Title(s) of any documents governing the financial management (accounting, record keeping and preparation of reports) on the HSS funds from (document number appendix 16) | Manuel of administrative, financial and accounting procedures of the Common Fund prepared in June 2006 and updated on August 27, 2008 |
| Title(s) any documents governing the audit of the HSS funds from GAVI (document number appendix 16) | IDA 41 NIR loan agreement and the AFD CNE 3006 01K agreement Manuel of administrative, financial and accounting procedures of the Common Fund prepared in June 2006 and updated on August 27, 2008 |
| Frequency of internal audits expected for the HSS funds from GAVI | Annual |
| Frequency of external audits expected for the HSS funds from de GAVI | Annual for the audit of the accounts and specific to the need to enter into contracts |
| Title(s) of any documents governing the procurement procedures for the HSS funds from GAVI (document number appendix 17) | Manuel of administrative, financial and accounting procedures of the Common Fund prepared in June 2006 and updated on August 27, 2008 Guidelines for entering into contracts for loans funded by loans from the IRBD and loans from the IDA on May 2004 revised (appendix 18) Guidelines selection and use of consultants by the borrowers of the World Bank |

To the Applicant: section 7.4:

- Please describe any provisions for the preparation of reports on the HSS funds from GAVI, including the member of the government responsible for preparing the annual status report (ASR)

NB:  The start of the activities supported by the GAVI HSS will be reported to GAVI Alliance through the annual status report. The report will provide information on the situation in relation to the objectives set in the application form for HSS support from GAVI. The report must also provide the financial management information on the use of the HSS funds from GAVI.

NB:  The deadline for submitting the annual status report for the previous calendar year is May 15 of every year. All countries must submit an ASR even if the HSS support from GAVI was received towards the end of the previous year.

## 7.4: Provisions for the preparation of reports

Like in the other GAVI funds used by eligible countries, the requirement to report on the financial aspects is an integral part of the monitoring by GAVI Alliance of the reports on the performance of the countries.  GAVI HSS funds will be managed by the MPH through an account. The Director of Financial Resources and Equipment (DRF/M) is in charge of financial management. The funds are planned annually through action plans. The amounts are taken into account in the synthesis of the Ministry’s plans in terms of funding. The members of the committee report not only to the CTNS but also to GAVI through audits and other control methods introduced by GAVI Meetings of the CNTS for that purpose will lead to the monitoring and physical and financial performance of the activities planned in the request.

To the Applicant : section 7.5:

- Please report what technical assistance will be required during the period of support for the HSS by GAVI as well as the source planned for technical assistance if known (table 7.5)

NB: The GAVI Alliance secretariat can provide countries with single financial support for assistance with the application process. The procedures for this support are described in the Guidelines for HSS support from GAVI in the section Technical Support.

NB:  Applications for resources for technical support to apply and supervise the HSS support from GAVI must be made using table 7.5 below.

## 7.5: Technical assistance needs

| Activities requiring technical assistance | Expected duration | Expected timetable (year, quarter) | Expected source (local partner, etc.) |
| --- | --- | --- | --- |
| - Recruiting of international technical assistance to support the preparation of the 2011-2015 HDP | 9 months | 2nd quarter 2010 | GAVI |
| - Recruiting of international technical assistance to evaluate the 2007-2010 cMYP and the preparation of the 2011-2015 cMYP | 3 months | 2nd quarter 2010 | Partner |

# Section 8: Budget projections and funding for the activities supported by the GAVI HSS

To the Applicant: section 8.1:

- Please prepare a budget for the principal activities for the duration of the HSS support from GAVI. Please add or eliminate lines/columns in order to give the correct number of objectives, activities and years (table 8.1)

NB Please make certain that all the costs for the implementation of the HSS support from GAVI, including technical assistance, are included in the budget. Please convert all the figures in the budget to US dollars (at the current exchange rate) and that GAVI deflators are used for future costs (see the guidelines on the GAVI web site): www.gavialliance.org).

NB: The amount requested in table 8.1 must not exceed the amount specified in table 8.2

NB: Management costs must be kept at a minimum. All management costs must be included in detail in the budget and also if the management is done through partners; including the costs generated by the fact of having other partners responsible for the management of part of the implementation of the activities supported by GAVI.

NB: Unit costs and calculations must be attached in a calculation sheet

For every subsequent year, provide estimated expenses (using the unit costs) for every activity. Please verify carefully that the totals in the columns (expenses per year) are consistent with the totals by line (by activity and SMART objective). Calculation errors are a frequent cause of delays, given that the IRC will ask for clarifications.

Please make certain that the total budget for the HSS proposal does not exceed the amount allocated to the country calculated in section 8.2 below.

## 8.1: Budget for the implementation of the HSS support from GAVI

|  |  |  | Funding breakdown for the GAVI HSS in US dollars for the year 2010 of the Project |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Objectives |  | Sector to be supported | Unit cost if applicable in US $ | Quantity | Year implemented 2010 | TOTAL COSTS IN $ US | TOTAL COSTS IN CFA |
|  |  | Objective 1 Increase the proportion of the population with access to the MPA from 44.,57% to 50% by the end of 2010 |  | 1.1.1 Provide 14 health districts with equipped vehicles (including GPS) to conduct integrated mobile activities | 58,787.59 | 14 | 823,026 | 823,026 | 375,300,000 |
|  |  |  |  | 1.1.2 Equip 80 CSI with motorcycles to conduct health fairs | 5,482.46 | 156 | 855,263 | 855,263 | 390,000,000 |
|  |  |  |  | 1.1.3 Organize an integrated trip 7 days a month by District in the 14 districts throughout the year to reach the village out of range | 41.73 | 1,176 | 49,074 | 49,074 | 22,377,600 |
|  |  |  |  | 1.1.4 Organize a health fair one day/week/CSI for 52 weeks in 280 CSI | 13.64 | 14,560 | 198,527 | 198,527 | 90,528,480 |
|  |  |  |  | 1.1.5 Provide the CSI of 14 Health districts with cold chain equipment to better preserve antigens | 41,555.06 | 14 | 581,771 | 581,771 | 265,287,500 |
|  |  |  |  | 1.1.6 Give incentive bonuses for the performance of health services in the districts and CSI | 438.60 | 280 | 122,807 | 122,807 | 56,000,000 |
|  |  |  |  | 1.1.7 Hold health information sessions through community media | 131.58 | 504 | 66,316 | 66,316 | 30,240,000 |
|  |  |  |  | 1.1.8 Enlist community support before integrated mobile activities in areas not covered by fixed services | 548.25 | 168 | 92,105 | 92,105 | 42,000,000 |
|  |  |  |  | 1.1.9 Arrange community support before health fair activities | 219.30 | 56 | 12,281 | 12,281 | 5,600,000 |
|  |  |  |  | 1.1.10 Conduct regular integrated supervisions at all levels of the system | 379.18 | 184 | 69,612 | 69,612 | 31,743,200 |
|  |  | Total Objective 1 |  |  |  |  | 2,870,782 | 2,870,782 | 1,309,076,780 |
|  |  | Objective 2: Have 70% of the healthcare facilities transmit comprehensive quality data within the deadlines set by 2014 : |  | 2.1 1. Put in place in 98 CSI a fleet system for referrals and cross-referrals to hospitals | 182.15 | 98 | 17,851 | 17,851 | 8,140,000 |
|  |  |  |  | 2.1.2 Maintain the existing SSB radios at the 14 Health districts | 32.89 | 168 | 5,526 | 5,526 | 2,520,000 |
|  |  |  |  | 2.1.3 Conduct an evaluation on the quality of the EPI data (DQA) | 95,603.07 | 1 | 95,603.07 | 95,603 | 43,595,000 |
|  |  | Total Objective 2 |  |  |  |  | 118,980 | 118,980 | 54,255,000 |
|  |  | Objective 3: Support the preparation and adoption of a new 2011-2015 HDP |  | 3.1.1 Recruit international technical assistance in the 2nd quarter of 2010 for 9 months | 97,697 | 1 | 97,697 | 97,697 | 44,550,000 |
|  |  |  |  | 3.1.2 : Organize missions at the health districts to support and revise the current DHDPs | 8,133 | 42 | 341,591 | $341,591 | 155,765,540 |
|  |  |  |  | 3.1.3 Support missiion to the regions to revise the current PDSR | 10,129 | 7 | 70,906 | $70,906 | 32,332,948 |
|  |  |  |  | 3.3.1 Hold a workshop to prepare the first draft of the 2011-2015 HDP in Niamey for a period of 10 days | 10,620 | 1 | 10,620 | $10,620 | 4,842,800 |
|  |  |  |  | 3.4.1 In each region, hold a meeting to amend the new HDP | 5,618 | 8 | 44,941 | $44,941 | 20,492,948 |
|  |  |  |  | 3.5. 1 Organize an amendment meeting for the Draft of the 2011-2015 HDP at the central level | 9,049 | 1 | 9,049 | $9,049 | 4,126,400 |
|  |  |  |  | 3.6.1 Hold a consensus and validation meeting for the new 2011-2015 HDP for a period of 5 days for all the players in the health sector including civil society | 46,639 | 1 | 46,639 | $46,639 | 21,267,600 |
|  |  |  |  | 3.7.1 Have the draft 2011-2015 HDP adopted by the government in December 2010 |  |  |  | $0 | 0 |
|  |  |  |  | 3.8.1 Reproduce and distribute the new 2011-2015 HDP document to all levels of the healthcare pyramid and to the TFP and members of civil society | 33 | 315 | 10,362 | 10,362 | 4,725,000 |
|  |  | Sub- Total Objective 3 |  | Sub Total Objective |  |  | 631,805 | 631,805 | 288,103,236 |
|  |  | Objective 4: Support the preparation and adoption of a comprehensive multi-year immunization plan by the end of 2010 |  | 4.1.1: Recruit international technical assistance to evaluate the 2007-2010 cMYP and prepare the 2011-2015 cMYP at the end of the 2nd quarter for 3 months | 43,816 | 1 | 43,816 | $43,816 | 19,980,000 |
|  |  |  |  | 4.2.1 : Evaluate the 2007-2010 cMYP | 66,325 | 1 | 66,325 | $66,325 | 30,244,200 |
|  |  |  |  | 4.3.1 Organize data gathering missions in the health districts to support the evaluation of the cMYP | 59,288 | 1 | 59,288 | $59,288 | 27,035,540 |
|  |  |  |  | 4.4.1 Hold a workshop to prepare the 2011-2015 cMYP document for a period of 10 days in Niamey | 4,625 | 1 | 4,625 | $4,625 | 2,108,900 |
|  |  |  |  | 4.5.1 Hold a 5-day national consensus workshop with all the players in immunization on the cMYP at the end of 2010 in Niamey | 34,081 | 1 | 34,081 | $34,081 | 15,540,800 |
|  |  |  |  | 3.6.1 Have the draft 2011-2015 cMYP adopted by the government in December 2010 |  |  |  | $0 | 0 |
|  |  |  |  | 3.7.1 Reproduce and distribute the new 2011-2015 cMYP at all levels of the healthcare pyramid and to the TFP and members of civil society | 33 | 196 | 6,447 | 6,447 | 2,940,000 |
|  |  | Sub- Total Objective 4 |  |  |  |  | 214,582 | 214,582 | 97,849,440 |
|  |  | Total for the Project |  |  |  |  | 3,836,150 | 3,836,150 | 1,749,284,456 |
|  |  | Monitoring & Evaluation 2% |  |  |  |  | 76,723 | 76,723 | 34,985,689 |
|  |  | Management cost 2% |  |  |  |  | 76,723 | 76,723 | 34,985,689 |
|  |  | Total Cost of the Project |  |  |  |  | 3,989,596 | 3,989,596 | 1,819,255,834 |

To the Applicant: section 8.2:

- Please calculate the amount of the funds available per year from GAVI for the activities proposed by the GAVI HSS, based on the annual number of births and the GDP per capita as follows (table 8.2)

- If the GDP < USD 365 per capita, the country is entitled to receive up to USD 5 per infant

- If the GDP > USD 365 per capita, the country is entitled to receive up to USD 2.5 per infant

NB: The example below assumes that the birth cohort in the year of the GAVI proposal is equal to 100,000 and gives the total allocation from the fund if the GDP < USD 365 per capita and if GDP > USD 365 per capita.

Examples of calculation of the allocation to the country for the GAVI HSS (note that these are only examples)

| Allocation for the GAVI HSS (GDP < USD 365 per capita) | Allocation per year (USD $) |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | 2007 | 2008 | 2009 | 2010 | TOTAL FUNDS |
| Birth cohort | 100,000 | 102,000 | 104,000 | 106,000 |  |
| Allocation per infant | $5 | $5 | $5 | $5 |  |
| Annual Allocation | $500,000 | $510,000 | $520,000 | $530,000 | $2,060,000 |

| Allocation for the GAVI HSS (GDP > USD 365 per capita) | Allocation per year ( USD $) |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | 2007 | 2008 | 2009 | 2010 | TOTAL FUNDS |
| Birth cohort | 100,000 | 102,000 | 104,000 | 106,000 |  |
| Allocation per infant | $2.5 | $2.5 | $2.5 | $2.5 |  |
| Annual Allocation | $250,000 | $255,000 | $260,000 | $265,000 | $1,030,000 |

## 8.2: Calculation of the allocation to the country for the GAVI HSS (these figures must be consistent with the data used in other applications to GAVI and annual situational reports)

| Allocation for the GAVI HSS |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | Year of the application to GAVI |  | Year of implementation | TOTAL FUNDS |
|  | 2009 |  | 2010 |  |
| Birth cohort (number) | 797,919 |  | 2010 |  |
| Allocation per infant ($) | $ 5 |  |  |  |
| Annual Allocation ($) | $ 3,989,519 |  |  | $3,989,595 |

Birth cohort: infants 0-11 months (797,919)

Source:	INS

To the Applicant : section 8.3:

- Please summarize the general funding available for the efforts to Strengthen the Health systems related to improving vaccine coverage and coverage of other children’s health services.

- Please provide right below the table a concise explanation to demonstrate how the proposed funding for the GAVI HSS will be used to supplement existing and/or planned efforts to strengthen the capacity of the health systems

NB:  The funds for the GAVI HSS will be in addition to the government’s health budget – and the funds must not replace the resources allocated to the health sector.

NB:  Please specify the contributions from the government, from GAVI and from the principal partners or funding agencies. If there are more than four donors, please insert more lines. Please indicate the names of the partners in the table and group together all the remaining contributions expected. Please indicate the data source (Review of public expenditures, CDMT, reports from donors, etc.)

Status of total expenses by funding source (amounts in millions of CFA francs) for the Common Fund

| Donors | Amount of the agreement | Total expenses at year-end 2008 | Amount of the funding remaining |
| --- | --- | --- | --- |
| AFD 15 million euros (1 E = 655.957 CFAF) | 9,839,355,000 | 3,417,615,661 | * |
| IDA 35 million dollars (1$ = 500 CFAF) | 17,500,000,000 | 4,818,427,722 | * |
| Total | 27,339,355,000 | 8,236,043,383 |  |

As of December 31, 2008, from  total funding of 27,339,355,000 CFAF, 8,236,043,383 CFA F were spent from the Common Fund, leaving funds available of 19,103,311,617 CFAF.

## 8.3: Sources of all the funding expected for health systems strengthening activities

| Sources of funding | Allocation per year (USD $) |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Year of application to GAVI | Year 1 of implementation |  | Year 2 of implementation | Year 3 of implementation | Year 4 of implementation | Year 5 of implementation |  | TOTAL DES FONDS |
|  | 2009 | 2010 |  | 2011 | 2012 | 2013 | 2014 |  |  |
| GAVI |  | 3, 989,596 $ |  | 0 | 0 | 0 | 0 |  | $3, 989,596 |
| Government | 154, 355,856 $ | 127, 412,886 $ |  | 132, 891, 640 $ | 138,605,038 $ | 144, 566, 038 $ | 150,782, 377 $ |  | 848,614,778 $ |
| Supports mainly operating and investment expenses of the MPH |  |  |  |  |  |  |  |  |  |
| (Common Fund) | 17, 518,629 $ | 17, 999,976 $ | 6, 084, 059 $ |  | 0 | 0 | 0 |  | 41,601,892 $ |
| Funding of activities to strengthen employee skills, and to strengthen the operating capacities of healthcare facilities in terms of equipment and repair to raise the technical level of services. |  |  |  |  |  |  |  |  |  |
| UNFPA |  | 5, 435,336 | DND |  | DND | DND | DND | 5, 435,336 |  |
| UNICEF | 15, 280, 000 $ | 15, 280, 000 $ | 15, 280, 000 $ |  | 15, 280, 000 $ | 15, 280, 000 $ | 15, 280, 000 $ | 76, 400, 000 $ |  |
| JICA |  | 3, 289,821 $ | DND |  | DND | DND | DND | 3, 289, 821 $ |  |
| Funding of activities to strengthen employee skills, and to strengthen the operating capacities of the healthcare facilities |  |  |  |  |  |  |  |  |  |
| Househods |  | 31, 797, 747 $ | 39, 429, 206 $ |  | 48, 892, 216 $ | 60, 626,348 $ | 75, 176, 671 $ | 255, 922, 188 $ |  |
| CTB |  | 2, 667,823 | 2, 393,069 |  | 2, 250,298 | 1, 852,072 |  | 9, 163,262 $ |  |
| WHO |  | 7, 155,713 | 2, 853,287 |  |  |  |  | 10, 009,001 $ |  |
| Total other |  | 19, 669, 189 $ |  |  |  |  |  | 19, 009, 001 $ |  |
| TOTAL FUNDING | 187, 154,485 $ | 234, 697,315 $ | 198, 931, 263 $ |  | 205, 028, 495 $ | 222, 324, 458 $ | 225, 959, 048 $ | 1,274, 095,064$ |  |

Source of information on funding sources:

GAVI:	Proposal Gavi Round 9

Government: 2009 Budget and Draft 2010 Budget

Donor: Common fund: 2009 Budget and Draft 2010 Budget

Donor 2: UNPF: Draft 2010 Budget of the MPH

Donor 3:	WHO: Draft 2010 Budget of the MPH

Total other:

To the Applicant : section 8.4:

- Please provide a concise explanation to demonstrate how the proposed funding for the HSS from GAVI will be used to supplement existing and/or planned efforts to strengthen the capacity of the health systems

## 8.4: Describe how the HSS funding from GAVI will supplement the other sources of HSS funding

The GAVI funds will be included in the funding of the MPH. The activities planned for the GAVI funding will be included in the AAP of the structures concerned. The funds will be managed according to the mechanism of the COMMON FUND included in the HDP. All the partners in the healthcare sector contribute to the funding of the AAP activities. The HSS funding from GAVI will therefore be added to the funding from the other partners. The management of financial resources is decentralized. The regions and districts have account where into which resources are transferred quarterly.

In the 2011-2015 HDP there are plans for the GAVI funds to be managed by officials of the CF. These funds will be an integral part of the expense plan of the Ministry of Public Health.

# Section 9: Conditions of GAVI support

To the Applicant

- This section sets forth the conditions for HSS support from GAVI. By signing this application form, you confirm that you have read and that you are in agreement with GAVI’s conditions for HSS support.

GENERAL CONDITIONS

OF GAVI ALLIANCE

FUNDING USED SOLELY FOR APPROVED PROGRAMS

The applicant country (“Country”) confirms that all the funding provided by GAVI Alliance for this application will be used and applied for the sole purpose of conducting the program(s) described in this application. Any significant change in the program(s) approved must be reviewed and approved in advance by GAVI Alliance.  All funding decisions for this proposal shall be made in accordance with the wishes of the GAVI Alliance Executive Committee and are subject to the procedures of the IRC and to the availability of funds.

AMENDING THE PROJECT

The Country shall notify GAVI Alliance in its annual situation report if it wishes to propose changes in the description of the program(s) in this proposal. GAVI Alliance shall implement  any change approved by GAVI Alliance and the proposal shall be amended.

REIMBURSEMENT OF FUNDS

The Country agrees to reimburse GAVI Alliance for any funding not used for the program described in this application. Reimbursement must be made by the country in US dollars unless GAVI Alliance decides otherwise within sixty (60) days after receipt by the said Country of the request for reimbursement from GAVI Alliance and must be paid into the account or accounts designated by GAVI Alliance.

SUSPENSION/CANCELLATION

GAVI Alliance may suspend all or part of its funding to the Country if it has reason to suspect that the funds have been used for any purpose other than for the programs described in this proposal or that there is any change in this proposal as approved by GAVI.  GAVI Alliance reserves the right to terminate its support to the Country for the programs described in this proposal if GAVI Alliance receives confirmation that the funds are misused.

FIGHT AGAINST CORRUPTION

The Country confirms that the funds provided by GAVI Alliance must not be offered by the Country to any third parties and that the Country will not seek any gift, payment or profit in connection with this proposal either directly or indirectly that could be considered an illegal act of corruption.

.

AUDITS AND RECORDS

The Country shall conduct annual financial audits and share them with GAVI Alliance as required. GAVI Alliance reserves the right, either itself or through a representative, to conduct audits or other financial management evaluations to make certain the requirement to report on the funds disbursed in the Country is met. The Country shall keep precise accounting records showing how the GAVI Alliance funds are used. The Country shall keep accounting records in keeping with its accounting standards approved by its government for at least three years after the date of the last disbursement of funds from GAVI Alliance.  In the event of a claim of misuse of funds, the country shall keep such records until the results of the audit are final. The country agrees not to claim any privilege concerning the documents with respect to GAVI Alliance as regards any audit.

CONFIRMATION OF LEGAL VALIDITY

The Country and the signatories for the government confirm that this proposal is accurate and correct and constitutes a legal commitment obliging the Country, in accordance with the laws of the Country, to conduct the programs described in this proposal.

CONFIRMATION OF COMPLIANCE WITH THE GAVI ALLIANCE POLICY OF TRANSPARENCY AND ACCOUNTABILITY

The Country confirms that it has reviewed the GAVI Alliance Policy of Transparency and Accountability (PTA) and that it will meet the conditions thereof.

ARBITRATION

Any dispute between the Country and GAVI Alliance arising from or owing to this proposal that is not settled out of court within a reasonable period of time shall be subject to arbitration at the request of GAVI Alliance or the country. The arbitration shall be conducted in accordance with the UNCITRAL arbitration rules in force at the time. The parties agree to be bound by the arbitration ruling as the final decision regarding such dispute. The place of arbitration shall be Geneva, Switzerland. The language of the arbitration shall be English.

For any dispute involving an amount of up to US$100,000 or less, there shall be an arbitrator appointed by GAVI Alliance.  For any disagreement for which the amount involved is more than US$100,000, there shall be three arbitrators appointed as follows: GAVI Alliance and the Country shall each appoint one arbitrator, and the two arbitrators thus appointed shall jointly appoint a third arbitrator, who shall preside.

GAVI Alliance shall not be liable to the country for any claim or loss in connection with the programs described in this proposal, including and without limitation any financial loss, conflict of responsibilities, any property or bodily damage or deaths. The Country shall be solely liable for all aspects of the management and implementation of the programs described in this proposal.

Section 10: Approval of the application

To the Applicant : sections 4.1, 4.2 et 4.3

- The proposal for HSS support from GAVI cannot be examined without the necessary signatures and the approval of the Ministry of Health and the Ministry of Finance the President and the member of the healthcare sector coordinating committee (HSCC)

- All the members of the HSCC must sign the minutes of the meetings during which the application for HSS support from GAVI was approved. The minutes must be submitted with the application, and any question arising during the meeting that might affect the implementation or follow-up of the proposal must be pointed out by the members of the HSCC (numbered and listed in appendix 1)

- Please give the names and coordinates of the person to be contacted by GAVI if in doubt.

NB: The signatures of the members of the ICC are considered to represent their agreement with the information and programs provided in this application, as well as their support for the implementation of the programs. This does not involve any financial or legal commitment on the part of the partner agency or person.

## 10.1: Approval by the government

The government of the Republic of Niger agrees to provide immunization and other maternal-child healthcare services on a sustainable basis. The effectiveness of the health systems will be reviewed every year through a transparent monitoring system. The government asks the funding partners of GAVI Alliance to provide financial assistance to support the strengthening of the health systems as presented in this proposal.

Please note that this application will not be examined or approved by the Independent Review Committee without the signatures of the Minister of Health and the Minister of Finances or their delegated authority.

| Minister of Public Health | Minister of the Economy and Finance |
| --- | --- |
| Name: Dr.MOUSSA FATIMATA | Name: ALI MAHAMAN LAMINE ZEÏNE |
| Signature: | Signature: |
| Date: | Date: |

## 10.2: Approval by the Health Sector Coordinating Committee (HSCC) or national equivalent

The members of the Health Sector Coordinating Committee or its equivalent approved this application at a meeting held on ……………………. The duly signed minutes of the meeting are attached in appendix 1.

| Chairman of the HSCC (or his equivalent): |  |
| --- | --- |
| Name: MR EL HADJ MAMAN ISSIAKA | Position / Organization : DEPUTY SECRETARY GENERAL/ /MPH |
| Signature: | Date: |

10.3: Member of the government to contact for any queries:

Name: Dr. MOUSSA  FATIMATA	Title: MINISTER OF PUBLIC HEALTH

Tel.: (227) 20 72 25 31		Address: MINISTRY OF PUBLIC HEALTH

BP 623 / Niamey/Niger

Fax: (227) 20 73 35 70

E-mail: moussafatim2@yahoo.fr

10.4: Member of the government who is the contact point to supervise the financial management of the HSS funds from GAVI:

Name: MR.ABDOU SAYO FARMO	Title: Manager of Financial Resources and Equipment

Tel.: (227) 20-20-36-30	             Address: MINISTRY OF PUBLIC HEALTH

BP 623/ Niamey/ Niger

Fax; (227) 20 73 35 70

E-mail: abdousan@yahoo.fr

# APPENDIX 1 Supporting documents submitted with the application for HSS support from GAVI and final check list

To the Applicant

- Please number and compile a list of all the documents submitted with this application in the table below. Please be consistent with the title and number of the context/supporting document when referring to it in this proposal.

NB:  The application for support and the appendices thereto must be presented in English or French, accompanied by any documents referred to in the proposal in electronic format.

| Document (with the equivalent name used in the country) | Available (Yes/Non) | Period | Attachment number |
| --- | --- | --- | --- |
| List of reference documents |  |  |  |
| Healthcare strengthening system for Niger April 28, 2009 | Yes | 2010-2016 | N°1 |
| Health Development Plan (HDP) (The initial duration of the 2005-2009 plan was extended by act of the Council of Ministers | YES | 2005-2010 | N°2 |
| Comprehensive Multi-year Plan (cMYP) EPI Revised | YES | 2007-2010 | N°3 |
| Framework of medium-term health sector expenses CDS/MT 2008-2010 | YES | 2008-2010 | N°4 |
| Multiple Indicator Demographic and Health Survey | YES | 2006 | N°5 |
| Accelerated Development and Poverty Reduction Strategy (ADPRS) | YES | 2008-2012 | N°6 |
| Internal mid-point evaluation of the 2005-2010 health development plan (HDP) | YES | October 2008 | N°7 |
| Memorandum on the joint review of the health sector for the year 2008 | YES | 2009 | N°8 |
| Budget for the implementation of GAVI HSS | Yes | 2009 | N°9 |
| Demographic data on Niger developed by the INS based on the 2001 General Population Census | Yes | 2008 | N°10 |
| Summary report (synthesis) of the meeting of the National Health Committee, February 20, 2009 | Yes | 2009 | N°11 |
| Monitoring & Evaluation Manual of the 2005-2010 HDP, latest version, April 2006 | Yes | 2006 | N°12 |
| List of legislative and regulatory documents |  |  |  |
| Departmental memo N° 00161 creating the GAVI HSS Task Force | Yes | 2008 | N°13 |
| Decree 0229 of November 28, 2006 creating the National Health Committee | Yes | 2006 | N° 14 a |
| Decree 0233 of December 10, 2006 creating the National Health Technical Committee (CTNS) | Yes | 2006 | N° 14 b |
| Decree 0234 of December 1, 2006 creating the M&E Committee (MEC) | Yes | 2006 | N° 14 c |
| Attendance list of the CTNS meeting of February 16, 2009 | Yes | 2009 | N°15 |
| Manuel of administrative, financial and accounting procedures of the Common Fund, review August 2008 | Yes | 2008 | N°16 |
| Guidelines selection and use of consultants by borrowers from the World Bank (Common Fund), May 2004 | Yes | 2004 | N°17 |
| Guidelines for entering into contracts funded by loans from the IBRD and IDA (Common Fund), May 2004 | Yes | 2004 | N°18 |

# APPENDIX 2 Banking form

NB: We can never emphasize too much that without a banking form that contains complete, precise coordinates (IBAN, SWIFT code, corresponding bank in the US and account information), it is impossible to transfer the funds. Failure to provide accurate and complete information in this section WILL CAUSE unnecessary delays. This must be approved by the national representative of UNICEF on letterhead.

| GLOBAL ALLIANCE FOR VACCINES AND IMMUNIZATION |  |  |  |  |  | Banking form |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SECTION 1 (To be completed by payee) |  |  |  |  |  |  |  |  |  |  |
| In accordance with the decision on financial support made by the GAVI Alliance for Vaccines and Immunization dated . . . . . . . . . ., the Government of ……………………………….. Hereby requests that a payment be made, via electronic bank transfer, as detailed below: |  |  |  |  |  |  |  |  |  |  |
| Name of Institution: (Account holder) |  |  |  |  |  |  |  |  |  |  |
| Address: |  |  |  |  |  |  |  |  |  |  |
| City-Country |  |  |  |  |  |  |  |  |  |  |
| Telephone Nº : |  |  |  | Fax Nº : |  |  |  |  |  |  |
| Amount in USD: |  | (To be filled in by GAVI secretariat) |  |  | Currency of the bank account: |  |  |  |  |  |
| For credit to Bank account title |  |  |  |  |  |  |  |  |  |  |
| Bank account No. : |  |  |  |  |  |  |  |  |  |  |
| At: Bank name |  |  |  |  |  |  |  |  |  |  |
| Is the bank account to be used exclusively for this program? |  |  |  |  |  |  | YES ( ) NO ( ) |  |  |  |
| By whom is the account audited? |  |  |  |  |  |  |  |  |  |  |
| Signature of the government’s authorizing official: |  |  |  |  |  |  |  |  |  |  |
| Name: |  |  |  |  |  |  |  |  | Seal: |  |
| Title: |  |  |  |  |  |  |  |  |  |  |
| Signature: |  |  |  |  |  |  |  |  |  |  |
| Date: |  |  |  |  |  |  |  |  |  |  |

| SECTION 2 (to be filled in by the bank) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| FINANCIAL INSTITUTION |  |  |  | CORRESPONDING BANK (in the United States) |  |
| Bank Name: |  |  |  |  |  |
| Branch Name: |  |  |  |  |  |
| Address: |  |  |  |  |  |
| City - Country |  |  |  |  |  |
| Swift code : |  |  |  |  |  |
| Sort code: |  |  |  |  |  |
| ABA No. : |  |  |  |  |  |
| Telephone No.: |  |  |  |  |  |
| Fax No.: |  |  |  |  |  |
| I certify that the account No. . . . . . . . . . …………………………….is held by (institution name) …………………………………………………………………at this banking institution. |  |  |  |  |  |
| The account is to be signed jointly by at least …….. (number of signatories) of the following authorized signatories: |  |  | Name of bank’s authorizing official: |  |  |
| 1 Name: Title: |  |  | Signature: |  |  |
|  |  |  | Date: |  |  |
| 2 Name: Title: |  |  | Seal: |  |  |
| 3 Name: Title: |  |  |  |  |  |
| 4 Name: Title: |  |  |  |  |  |

COVERING LETTER

(To be completed by UNICEF representative on letter-headed paper)

TO:

GAVI Alliance - Secretariat,

Att. Dr Julian Lob-Levyt

Executive Secretary

Chemin de Mines 2.

CH 1202 Geneva,

Switzerland

| On......................., I received the original of the BANKING DETAILS form, which is attached. I certify that the form does bear the signatures of the following officials: |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | Name |  |  | Title |
| Signature of the government’s authorizing official |  |  |  |  |  |
| Name of the bank’s authorizing official |  |  |  |  |  |
| Signature of UNICEF Representative: |  |  |  |  |  |
| Name |  |  |  |  |  |
| Signature |  |  |  |  |  |
| Date |  |  |  |  |  |

See Review of  healthcare sector public expenditures

The minutes of the HSCC meetings concerning the preparation of the application for HSS support must be attached as supporting documentation, with the minutes of the meeting in which the application was approved by the HSCC. The minutes must be signed by the chairman of the HSCC. The minutes of the meeting approving this application for HSS support from GAVI must be signed by all the members of the HSCC.

If the proposal identifies activities to be performed at the subnational level, subnational data must be provided when available. These data are to be provided in additional to national data.

Statistics UNICEF website

During the past three years.

MPA : Curative, preventive and promotional activities offered to the populaton with either health fairs or better management.

Involving a CSI nurse traveling (generally by motorcycle) to a distant village between 5 and 15 kim from his or her healthcare facility to provide the same care as in their center.

Integrated mobile teams are organized at the district level, involving 3-5 workers traveling to villages with appropriately equipped vehicles to provide the MPA to the population.

If the number of districts is provided, then the total number of districts in the country must also be provided

If the reference data are not available, indicate whether  there are plans for gathering reference data and when they will be carried out.

Important for easy access and cross-referencing

Please submit a copy of the memorandum

Please submit a copy of the agreement/memorandum of understanding governing the joint funding mechanism and a copy of the document describing how the joint funding mechanism currently operates.

Please note that the mechanism chosen must meet the minimum conditions required under the GAVI Transparency and Accountability policy

Please submit a copy of the procedures and of the legislation applicable to the annual budget projection process for the use of the HSS funds from GAVI and any documents describing how the budget projection process e processus de prévisions budgétaires pour les fonds du HSS de GAVI sera conduit.

Please submit a copy of the procedures that are applicable to the financial management (accounting, record keeping and preparation of reports) for the HSS funds from GAVI and any documents describing how the financial management of the HSS funds from GAVI will be carried out..

Please submit a copy of the procedures that are applicable to the external audits of the HSS funds from GAVI and any documents describing how the external audits of the HSS funds from GAVI will be conducted.

“External audit » means audits conducted by the government’s auditing bodies.

Please submit a copy of the procurement procedures for the HSS funds from GAVI and any documents describing how the procurement will be done.

See the guidelines for the GAVI HSS for the countries concerning funding levels in the Allocation section