Revision  4

September 2002

The Government of

Democratic People's Republic of Korea

Proposal for support submitted to the

Global Alliance for Vaccines and Immunization (GAVI)

and the Vaccine Fund

This document is accompanied by an electronic copy on diskette for your convenience. Please return a copy of the diskette with the original, signed hard-copy of the document to

GAVI Secretariat; c/o UNICEF, Palais des Nations, 1211 Geneva 10, Switzerland.

Enquiries please to: Dr Tore Godal, tgodal@unicef.org or representatives of a GAVI partner agency.  All documents and attachments must be submitted in English or French.

# Executive Summary

# Synopsis of the proposal including the specific requests for support from GAVI and the Vaccine Fund. The figures essential for the calculation of award amounts should be presented here, including: baseline data, current DTP3 coverage and targets for increased coverage, strategies for reaching all children, requested number of doses of vaccine(s) and their presentations (drawn from the tables in this form). Summarise also the nature of ICC participation in developing this proposal.

Total Population of DPRK as per record of the Central Bureau of Census for 2000 was 21,863,420. During the same year it is estimated that 451,480 children were born and 10,384 of them died before attaining the age of I year, therefore, in 2000 DPR Korea has birth cohort of 441,096 surviving infants 2000. It is estimated that 10,000 of these children die before attaining the age of 1 Year as IMR has risen to 23/1000 live births in 1996 from 9.2/1000 live births in 1991. The high increase in IMR is attributed to the effect the economic declines due to natural disasters in mid 90s. During the economic hardship period the Government could not maintain the support for health sector and therefore requested UNICEF & WHO (EHA) in 1996 for the assistance in supporting its health programmes. EPI is one of the major programmes being supported by the partner agencies since then. The estimated number and percentage of the EPI specific target groups i.e 0-11 months, 0-59month, pregnant woman and CBA for 2000 was 441,096 (2.01%) ; 2,181,099 (9.97%) , 452,354 (2.07) & 5,822,667 (26.63%) respectively.

Currently EPI is providing immunization against 6 standard antigens to the 0-11 month infants and 2 doses of TT to pregnant women. NIDS for OPV are conducted each year in October and November since 1997.Vit A is being provided to children 6-59 months in campaigns twice yearly since 1998

Hepatitis B vaccine (plasma derived) is produced in a limited quantity . It is administered to high risk groups including children  who’s mothers are known to be Hepatitis B carrier. It is planned to introduce Hep B  vaccine (mono valent) in EPI for infants in a phased manner starting 2002 .Based on the experience of including hepatitis B vaccine ( mono valent)  in EPI, the country wishes to switch to DPT –Hep B vaccine in 2005 if available in the market.

According to the most recent routine coverage reporting, the DPT3 coverage was 81%. However on analysis of the DPT3 coverage as per routine reporting and surveys during 1998-2000 a wide range of variation from 37.4% to 95.5% is noted. The causes of the difference can be attributed to multiple factors, like misunderstanding of the WHO/UNICEF joint reporting forms as they are not in the native language, error in translation of the Korean into English and vice versa and confusion at the stage of compilation of the data. Above all with the decline in the overall resources available for EPI as compared to mid 80,s the training and supervision in EPI for proper data collection could not be maintained at the desired level and a tendency for over-reporting emerged. However the coverage of campaigns (OPV, Vitamin A) has always been above 95%.

Keeping in view the above factors and observations made during the field visits, the National EPI team, and the representatives of the partner agencies have reached a consensus to consider the 62.1% DPT3 coverage based on the 2nd MICS survey as base line for future planning. This rate has also been endorsed by ICC.

To revitalize the EPI a Multi year National EPI Plan, with the active participation of ICC sub committee (Technical Working Group) and support of an international consultant has been prepared by the national EPI team

The remedial measures to improve data management and the mechanism for supervision, monitoring and evaluation of the programme have been included in the Multiyear National EPI plan (2001-2006). A system of County based 30Cluster EPI coverage surveys shall be undertaken in one-thirds of the counties each year in collaboration with the EPI partners. An Immunization Data Quality Audit will also be under taken before mid term review and also when desired by the GAVI/The Vaccine fund.

The training of the EPI staff in all the EPI components have been planed  in phased manner including refresher training every three years. Injection safety and proper disposal of the associated waste are included in the plan to be fully implemented in the initial years of implementation.

DPR Korea has a very well developed system of section doctors. Each section doctor is responsible for providing primary health care services, including immunizations to about 100-140 households. This system works very efficiently even in hard to reach areas, therefore all children residing in such areas are provided with EPI services without much difficulty. However the proposed strengthening of the EPI services, strengthening of management and supervision in the coming years (2002-2006), will further improve access to the target children.

As the EPI is an innovative and progressive programme, a number of research studies have been include to further strengthen the programme. The financial requirements for the plan period have been broadly estimated and included in the Multiyear Plan of Action.

It is planned to increase the coverage with routine immunisation from current best estimate of 62.1% to 63% in 2001, 65% in 2002, 75% in 2003, 85% in 2004, 90% in 2005 and 95% in 2006.

The Government of DPRK through this proposal requests the GAVI and The Vaccine Fund for:

- Financial support for development of the immunization services.

- New and under used vaccines (Hep B & Hep B – DPT) along with associated safe injection equipment

- Safe injection equipment for vaccines according to the standard EPI scheduled.

The doses of Hep B Vaccines, AD syringes and safety boxes requested from the GAVI/The vaccine fund  for the period of 2002-2006 are as follows.

|  | 2002 | 2003 | 2004 | 2005 | 2006 | Total |
| --- | --- | --- | --- | --- | --- | --- |
| Hep.B (Mono) doses | 477,174 | 1,592,977 | 1,422,320 | 501,440 | 485,177 | 4,479,008 |
| Hep.B – DPT (Combo) doses |  |  |  | 1,837,149 | 1,512,269 | 3,349,418 |
| AD syringes for Hep B & Hep B- DPT vaccines | 424,527 | 1,485,291 | 1,294,078 | 2,262,073 | 1,944,882 | 7,410,851 |
| AD Syringes for BCG,DPT, Measles &TT | 2,292,199 | 2,668,655 | 3,051,691 |  |  | 8,012,545 |
| Syringes for reconstitutions | 85,004 | 98,965 | 113,168 |  |  | 297,137 |
| Safety Boxes | 26,386 | 30,720 | 35,130 | 25,109 | 21,588 | 138,933 |

The country wishes to use the opportunities provided by the GAVI / the Vaccines Fund to strengthen its immunization services. As the country plans to raise its DPT3 coverage from current 62.1% to above 95% in 2006, a sum of USD 659,148 as initial investment and USD 2,706,146 as subsequent rewards is expected from the vaccines fund, to strengthen the immunization services. This fund will mainly be used to supplement the national budget and partners contribution for cold chain, transport, training, reviews and research, technical assistance and rewards for the staff. All operational cost and staff salaries shall be borne by government. Neither the ISS fund not the new vaccines fund replace existing funds / budgetary allocations for EPI.

The ICC entrusted the EPI related technical tasks including the development of this proposal to its Technical Sub committee (Technical Working Group). The technical working group mainly consisting of National EPI team and supported by an International consultant, two doctors interpreters and EPI concerned persons of WHO and UNICEF worked closely to develop this proposal.

The current  proposal was presented and approved by the ICC before submission for the vaccines fund.

# Signatures of the Government and the Inter-Agency Co-ordinating Committee

The Government of Democratic People’s Republic of Korea commits itself to developing national immunization services on a sustainable basis in accordance with the multi-year plan presented with this document. Districts’ performance on immunization will be reviewed annually through a transparent monitoring system. The Government requests that the Alliance and its partners contribute financial and technical assistance to support immunization of children as outlined in this application.

Signature:

(Prof. Dr. Choe Chang Sik)

Title:	Vice-Minister, Ministry of Public Health

Date:

The GAVI Secretariat is unable to return submitted documents and attachments to individual countries.  Unless otherwise specified, documents may be shared with the GAVI partners and collaborators.

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this proposal on the basis of the supporting documentation, which is attached. Signatures for endorsement of this proposal do not imply any financial (or legal) commitment on the part of the partner agency or individual:

| Agency/Organisation | Name/Title | Date Signature |
| --- | --- | --- |
| Ministry of Public Health, DPRK | Prof. Dr. Choe Chang Sik Vice Minister |  |
| Ministry of Public Health, DPRK | Dr. Choe Ung Jun Director, State Hygiene and Communicable Diseases Control Board |  |
| Ministry of Public Health, DPRK | Dr Pak Jong Min Director , Dept .of Foreign Affairs |  |
| State Planning Commission, DPRK | Dr.Ri In Jun Director , Dept. Foreign Fund |  |
| Ministry of Finance, DPRK | Mr O Myong II Director, Dept. International Affairs |  |
| Ministry of Education DPRK | Mr Chae Ryang II Director, Dept Foreign Affairs |  |
| Korean Democratic Women’s Union | Mrs Pak Song Ok Director, Dept. International Affairs |  |
| Academy of Medical Science, DPRK | Dr Han Hyon Chol Vice Director of Academy in charge of Science |  |
| Central Hygienic & Anti-Epidemic Institute, MoPH, DPRK | Dr Han Gyong Ho Director of Institute |  |
| Ministry of Public Health, DPRK | Dr Han Yong Sik Senior Officer, Dept. SHCDCB |  |
| Ministry of Public Health, DPRK | Dr Jong Pong Ju Vice-director, Dept Foreign Affairs |  |
| UNICEF ,DPRK | Mr Richard Bridle UNICEF Representative, DPRK |  |
| WHO , DPRK | Dr Eigil Sorensen WHO Representative, DPRK |  |

In case the GAVI Secretariat have queries on this submission, please contact :

Name: Dr. Pak Jong Min	Title/Address: Director, Dept. External Affairs, MopH, DPRK/

Sochang Dong, Central District, Pyongyang,

DPRK

Tel.No.: 850-2-381-8067

Fax No.: 850-2-381-4077

E-mail:……………………………

Alternative address:

Name: ……………………………	Title/Address: ……………………………….

Tel.No.: ………………………….   		            ………………………………..

Fax No.:………………………….. 		            ………………………………..

E-mail:……………………………                         ……………………………….

- Immunization-related fact sheet

| Table 1: Basic facts (For the year 2001 or most recent; specify dates of data provided) |
| --- |
| Population | 21,863,420 | GNP per capita | 479$US |
| Surviving Infants* | 441,096 | Infant mortality rate | 23/ 1000 |
| Percentage of GDP allocated to Health | 4.6% | Percentage of Government expenditure for Health Care | 6% |

* Surviving infants = Infants surviving the first 12 months of life

| Table 2: Trends of immunization coverage and disease burden by 12 months of age (as per annual WHO/UNICEF Joint Reporting Form on Vaccine Preventable Diseases) |
| --- |
| Trends of immunization coverage (in percentage) | Vaccine preventable disease burden |
| Vaccine | Reported | Survey | Disease | Number of reported cases |
|  | 2000 | 2001 | 2000 | Age group | 2001 | Age group |  | 2000 | 2001 |
| BCG | 81.5 | 81.5 | 69 | 0-11m | 80.0 | 0-11m | Tuberculosis | 50/100,000 | 220/100,000 |
| DTP | DTP1 | 86 | 87 | 69.1 | 0-11m | 68.1 | 0-11m | Diphtheria | - | - |
|  | DTP3 | 81 | 85 | 62.1 | 0-11m | 63.0 | 0-11m | Pertussis | 50 | 87 |
| OPV3 | 97.6 | 98.3 | 95.0 | 0-11m | 98.0 | 0-11m | Polio | - | - |
| Measles | 91.5 | 98.3 | 90.0 | 9m-2yrs | 91.5 | 9m-2yrs | Measles | - | - |
| TT2+ (Pregnant women) | 83.6 | 95.2 | 80.0 | Pregnant women | 80.0 | Pregnant women | NN Tetanus | - | - |
| Hib3 | - | - | - |  | - |  | Hib | - | - |
| Yellow Fever | - | - | - |  | - |  | Yellow fever | - | - |
| HepB3 | - | - | - |  | - |  | hepB seroprevalence (if available) | 2.1 | 2.1 |
| Vit A supplementation | Mothers ( < 6 weeks after delivery ) | - | - | - |  |  |  |  |  |  |
|  | Infants ( > 6 months) | 98 | 100 | 98 | 6-59m | 100 | 6-59m |  |  |  |

The best official estimate: Indicate the best official estimate of coverage among infants as reported in WHO/UNICEF Joint reporting form. Provide explanatory comments on why these are the best estimates: As per WHO/UNICEF joint reporting form 2001 the best official estimate of coverage among infants is as follows: BCG 81.5% , DTP1 87%, DTP3 85%, OPV3 98.3%, MV1 98.3%. However according to the ICC, the best official estimate for DTP3 coverage In 2000 is 62.1%. This is based on the finding of coverage survey (MICS) in 12-23m children with vaccination card.

- Summary of health system development status relevant to immunization:

At the time of independence from the Japanese rule in 1945 the health system in the country was in shambles.

Under the charismatic leadership of the Great Leader Comrade Kim Il Sung the Democratic Peoples Republic of Korea started development of its health system as a top priority. This included strengthening and expansion of the centuries old and time tested traditional Korean system of medicine besides establishing a very strong allopathic health system based on modern day scientific knowledge.

Expanded Programme on Immunisation

Immunisation services in the country are being provided since independence in 1945. A vaccine production unit was set up in 1946. As the need and demand for vaccination was more than the capacity of this unit, two additional vaccine production units were set up. Till recently these vaccine production units produced ten different types of vaccines, including Vaccines against, Tuberculosis, Poliomyelitis, Diphtheria, Pertusis, Tetanus, Measles, Hepatitis B and J. Encephalitis. However because of certain Geo-economic factors including natural disasters, since 1995 the production of these vaccines dropped or ceased in some cases. The immunization activities in the country were organized in a National Immunization Programme in 1984. Apart from the childhood immunizations, adult high-risk groups are also provided immunizations against J. Encephalitis and Typhoid.

To strengthen the National Immunization Programme in 1995-1996 the government requested for the support of the international health agencies (UNICEF and WHO). Since then UNICEF and WHO are providing support especially in the form of vaccines, cold chain, transport, technical assistance and local human resource capacity building. In spite of the economic difficulties the government continued its support to EPI largely in the form of trained Human Resource made available even in the remotest parts of the country to ensure that all the target population get benefit from this program.

District Health System for improvement in the quality of health services

The country has an extensive infrastructure of over 5000 health care facilities and over 70,000 trained health manpower. With such a strong resource base improving the quality of the health services will not be difficult. Therefor the programme of district health system is initiated with the objective to improve the quality and effectiveness of the health services especially for Maternal and child health at the community level. The programme focuses on the refresher trainings of the health personnel in the community and basic medical equipment for antenatal care, safe deliveries and minor surgeries.

Strengthening of Early Warning systems and control of Epidemics.

DPRK has a well-established system for the surveillance of communicable diseases. This system consists of a chain of Anti Epidemic stations at each County, province and National level. With the assistance of WHO the programme to strengthen the early warning system was launched in 1999. The objective of the programme is to strengthen the early warning system and epidemiological surveillance of communicable diseases. The strategies to achieve the objective include, strengthening of the laboratories, prompt outbreak response and safe blood transfusion services.

| Attached are the relevant section(s) of strategies for health system development | Document number 1,2,3,4 & 5 |
| --- | --- |

# Profile of the Inter Agency Co-ordinating Committee (ICC)

Various agencies and partners (including NGOs and Research Institutions) that are supporting immunization services are co-ordinated and organised through an inter-agency co-ordinating mechanism which is referred to in this document as ICC.

- Name of the ICC: Immunization Programme Coordinating Committee, DPRK

- Date of constitution of the current ICC: 25th May 2000

- Organisational structure (e.g., sub-committee, stand-alone):  Having Sub-committees

- Frequency of meetings: Quarterly

- Composition:

| Function | Title / Organization | Name |
| --- | --- | --- |
| Chair | Vice-Minister of Public health | Prof. Dr. Choe Chang Sik |
| Secretary | Director, State Hygienic & Communicable Diseases Control Board | Dr. Choe Ung Jun |
| Members | Director, Ministry of Public Health | Dr. Pak Jong Min |
|  | Director. State Planing Commission | Mr Ri In Jun |
|  | Director, Ministry of Finance | Mr O MyongII |
|  | Director, Ministry of Education | Mr Chae Ryang II |
|  | Director, Korean Democratic Women’s Union | Mrs Pak Song Ok |
|  | Director, Central HAEI | Dr Han Gyong Ho |
|  | Vice-Director, Academy of Medical Science | Dr Han Hyon Chol |
|  | Senior Officer, Ministry of Public Health | Dr Han Yong Sik |
|  | Vice-director, Ministry of Public Health | Dr Jong Pong Ju |
|  | Representative, UNICEF/DPRK | Mr Richard Bridle |
|  | Representative, WHO/DPRK | Dr Eigil Sorensen |

- Major functions and responsibilities of the ICC:

The ICC has well defined TORs, which specify the following functions and responsibilities

- Provide policy guidelines for Immunization programme in the country and if found necessary review the guidelines periodically and make necessary modifications.

- Act as an advisory board to the Government on matters related to EPI including, self sufficiency in immunization programme, adequate national resource allocations, new developments and to acquire assistance for strengthening EPI and polio eradication activities.

- Establish a forum for exchange of information and dialogue on global and national EPI status and co ordinate support at national level from the government and partner agencies for strengthening EPI and other disease eradication/elimination activities in the country.

- Ensure that partner agencies are provided necessary support for their activities to strengthen EPI and disease eradication/elimination activities in the country.

- Assists the Ministry of Public Health and partner agencies in identifying and developing support for new programme strategies when required

- Review  and give the final approval of the Multi year National  EPI plan (2001-2006)

- Assist the Government in monitoring the implementation of the Multi year National EPI  plan .

- Mobilize resources for the planned activities.

- Review the progress of EPI and advise Government on appropriate measures for achieving the targets.

- If necessary organize a   sub committees for a specific EPI related activities, for in depth review and implementation

- Assist in resource mobilization in supplementary immunization activities

- Act as a liaison with regional and global institutions in issues related to immunization

- Hold regular meetings

- Three major strategies to enhance ICC’s role and functions in the next 12 months :

- Regular ICC meetings (on an average one meeting per quarter ).

The ICC, after its constitution in May 2000, met for three times in year 2000. As many EPI issues required detailed deliberations, ICC entrusted the task to one of its sub committees i.e. The Technical Working Group headed by National EPI manager with the instruction of holding at least one meeting in a fortnight  and a field visit in a quarter(starting from July 2001) and briefing the ICC on its next meeting for the final decision. The Tech Working group had been holding frequent meetings

- Strengthening Provincial co-ordination

For the success of the EPI programme it is essential to have co-ordination with the sub national administrative units. The ICC shall nominate a sub committee (Tech Working Group) to take an immunisation site field visit and have a meeting with Provincial EPI manager at least on a bi monthly basis, so that each province is visited at least once in a two years period. The Technical working group shall brief the ICC about their visit in the quarterly meetings.

3. Circulation of minutes of meetings

The ICC decisions, which shall be based on the consensus approach, shall be pivotal for EPI functioning in the country. To keep all the key EPI personnel at all levels informed of ICC decisions, the minutes of the meetings shall be circulated to all the Provincial and county EPI managers. This will boast their morale and be an impetus for their participatory approach.

- Three main indicators (in addition to DTP3 coverage) that are chosen by the ICC to monitor implementation of this proposal:

- Increased Government Commitment for improving the EPI , as measured by:

- Timely and adequate provision of resources including the human resource

- Compliance of the recommendations of joint EPI review 1998

- Expeditious clearances of goods reaching the country port and prompt delivery to end-users.

- Percentage of achievement of planned yearly targets, as measured by comparing the yearly achievements with the targets of each component of Multi year National EPI Plan.

- Improved EPI infrastructure and performance at county level, as measured through a standardised check list and cluster coverage surveys

Attached are the supporting documents:

| Terms of reference of the ICC | Document number 5 |
| --- | --- |
| ICCs work plan of next 12 months | Document number 6 |
| Minutes of the three most recent ICC meetings or of any other meetings in which partners participated that concerned improving and expanding the national immunization program | Document number 7,8 |

# Immunization services assessment(s)

Reference is made to the most recent assessments of the immunization system that have been completed within the three years prior to the submission of this proposal.

- Assessments, reviews and studies of immunisation services for current reference:

| Title of the assessment | Main participating agencies | Dates |
| --- | --- | --- |
| WHO/UNICEF Joint EPI Review in DPR Korea | Ministry of Public Health, WHO, UNICEF | July,7-30, 1999 |
| The Multiple Indicator Cluster Survey in DPR Korea 1998 | Govt. Of DPRK Korea, UNICEF,WFP,EU | Sep-Oct 1998 |
| Draft Report on cold chain training in DPR Korea. | WHO | Nov-Dec 2000 |
| Report on the review of EPI cold chain in DPRK | WHO | May 2001 |

- The three major strengths identified in the assessments :

- Health Infrastructure and Manpower preservation despite economic hardships

- The Government of DPR Korea's political commitments towards the Global Goal of Polio eradication by year 2000, through implementation of National Immunisation days since 1997.

- The successful completion of the First Joint Review of the expanded Programme on Immunisation by Ministry of Public Health of DPR Korea with the participation of WHO and UNICEF.

- The three major problems identified in the assessments :

- Lack of Inter Agency Co-ordination Committee

- Poor Accountability, as no technical and financial reports are available for review by the partner agencies

- Deteriorating and insufficient logistic support (especially transport and cold chain)

- The three major recommendations in the assessments

- Establishment of an effective Inter Agency Co-ordination Committee.

- A Manual for EPI, providing information on different components of EPI like service delivery, vaccine storage and wastage reduction, cold chain, injection safety and disease surveillance and supervision be developed for the EPI staff.

- Need to establish a national management team for cold chain.

- Attached are  complete copies (with an executive summary) of :

| the most recent assessment reports on the status of immunization services | Document number 9,10,16,17 |
| --- | --- |
| a list of the recommendations of the assessment reports with remarks on the status of their implementation i.e. included in work-plan, implemented, not implemented, in progress…. | Document number 11. |

- Components or areas of immunization services that are yet to be reviewed (or studied).

| Component of or area | Month/Year |
| --- | --- |
| Review and the Assessment of Cold Chain | 2001 (Accomplished) |
| Review of AFP Surveillance | 2001 (Accomplished) |
| Training needs Assessment | 2001 |
| Assessment of injection practices | 2001 |
| EPI Coverage Survey (Provincial Level) | 2001 |

# Multi-Year Immunization Plan

Based upon the recommendations of the assessment of immunization services, the Government has developed (or updated) the multi-year immunization plan or adjusted the health sector plan.

| Attached is a complete copy (with an executive summary) of the Multi-Year Immunization Plan or of the relevant pages of the health sector plan. | Document number 12 |
| --- | --- |

| Technical support required for implementation of the immunization plan (expert consultants, training curricula, managerial tools…) |
| --- |
| Type of technical support | Period for the support | Desired from which agency |
| General Technical Assistance |  |  |
| To assist conduct measles and MNT review | 1 person months | WHO |
| To assist in NNT campaign | 3 person months | UNICEF |
| To assist in Measles campaign | 3 person months | UNICEF |
| To assist National Biological Institute for Serology | 2 person months | WHO |
| System Strengthening |  |  |
| To prepare a standardised system of vaccine, syringes safety box stock management and tracking | 2 person months | WHO/UNICEF |
| To prepare a guide for AFP surveillance | 2 person months | WHO/UNICEF |
| To assist in updating AFP manuals to include Measles and NNT surveillance | 2 person months | WHO/UNICEF |
| To assist in updating AEFI and preparation of the guide | 3 person months | WHO |
| To assist in reviewing and modification of current Communicable Disease Reporting system and linking with other routine reporting and surveillance systems and preparing a manual for the modified system | 8 person month | WHO/UNICEF |
| To assist in Preparation of National EPI Manual | 6 person months | WHO/UNICEF |
| To assist in preparation of cold chain supervisory system | 1 person months | WHO/UNICEF |
| Research Studies |  |  |
| To assist in undertaking KAP study | 1 person month | UNICEF |
| To undertake international Polio eradication review | 4 person months | WHO |
| To assist in cross section HepB sero prevalence studies (Multiple) | 6 person months | The Vaccine Fund |
| To assist in EPI Coverage Survey | 2 person months | WHO/UNICEF |
| To assist in EPI Coverage Survey (National) | 10 person months (2 months each year) | The Vaccine Fund |
| To assist in EPI training programme assessment | 3 person months | WHO/UNICEF |
| To assist in Cold chain assessment | 3 person months | WHO/UNICEF |
| To assist in EPI Financing Study and preparation of sustainability plan | 3 person months | WHO/UNICEF |
| To assist in undertaking safe injection practices study | 2 person months | WHO/UNICEF |
| Trainings |  |  |
| To train Viorology Lab Staff | 2 person months | WHO |
| To assist in training for Programme Management, Disease reporting, Software maintenance, Cold chain equipment repair and English language | 30 person months | WHO/UNICEF/VACCINE FUND |
| To assist in Training need assessments | 2 person months | WHO/UNICEF |
| To assist in developing Training Manuals (Programme management, Cold chain Management, Cold chain repair and maintenance, Injection Safety, Data management, District Micro planning, Software maintenance and management) | 16 person months | WHO/UNICEF |
| To assist in preparing training modules for injection safety | 2 person months | WHO/UNICEF |

| Table 3 : Schedule of vaccinations with traditional and new vaccines, and with Vit A supplementation |
| --- |
| Vaccine (do not use trade name) | Ages of administration (by routine immunization services) | Indicate by an “x” if given in : | Comments |
|  |  | Entire country | Only part of the country |  |
| BCG | At Birth | X |  |  |
| DPT | 10,14,16 week | X |  |  |
| OPV | Birth, 10,14,16 week | X |  |  |
| Measles | 9 months | X |  |  |
| Hep B | Birth (hospital), 10,14,16 week | X | X | To be introduced in phased manner from 2002 |
| Hep B-DPT | 10,14,16 week | X |  | To be substituted for Hep B at 10,14,16 week from 2005 subject to availability |
| TT | Pregnant Women | X |  |  |
| Vitamin A | 6-59 months | X |  |  |

- Summary of major action points and timeframe for improving immunization coverage:

( To Be attached from Executive summary of Plan)

| Element | Activity | Timeline |
| --- | --- | --- |
| 1. Strengthening Infrastructure | Cold chain Assessment | Q3 2001 |
|  | Procurement of cold chain and office equipment | On going WHO & UNICEF Support With VF support from Q4 2002 onwards |
|  | Strengthen National and Provincial EPI cells, Central, Provincial and County HAEI with additional personnel and office equipment | Additional personnel by Q1 2002 Additional office equipment beginning Q1 2003 |
| 2. Strengthening Management | Prepare National Multi year EPI plan. | Q3 2001 |
|  | Prepare annual Provincial EPI plan | Q4 each year beginning 2001 |
|  | Develop annual micro plans for each county/district | Q3 2001 each year beginning. |
|  | Strengthen supervision Prepare National EPI manual with list of activities and responsibilities Prepare supervisory check lists Adequate allocation of resources for operational cost | Q1 2002 Q1 2002 Q1 each year |
|  | Prepare a transport need plan Initiate procurement of transport | Q3 2001 On going with WHO & UNICEF Support With VF support from Q4 2002 onwards |
|  | Place the additional staff for AFP surveillance | Q2 2001 |
|  | Establish National Management team for cold chain. | Q3 2001 |
|  | County level coverage surveys carried out with feedback to the relevant staff | Q1 2002 onwards |
| 3. Ensure quality assurance | `Prepare and implement Injection safety and safe disposal of associated waste plan for EPI | Q1 2002 |
|  | Ensure AD syringes and safety boxes for all the immunization sessions. | On going |
|  | Institute quantified supervision during immunization sessions | Q1 2001 onwards |
|  | Undertake training need assessment and finalize training plan | Q4 2001 |
|  | Develop training materials and manuals | Q1 2002 to Q4 2003 |
|  | Provide training Overseas for senior staff English Language for Managerial staff EPI field staff Refresher training Specific training for staff concerned with logistics and data management | Q2 2002 onwards Q3 2002 On going On going Q4 2002 |
|  | Establish EPI training cells at HAEI EPI training programme assessment | Q4 2002 Q2 2005 |
|  | Strengthen the AEFI system | Q1 2002 to Q4 2002 |
| 4. Technical development | Polio eradication - National Immunization Days - Effective AFP surveillance - mop up operations , if needed - Accreditation of National Polio lab - Submission of report for issuance of Polio eradication certification | Annually, one round each in Oct &Nov at least till 2005 Q4 2001 onwards Q1 2004 onwards Q1 2002 Q1 2002 |
|  | Campaign for TT for CBA Study on impact | Q2 2003 Q3 2004 |
|  | Campaign for measles Immunization | Q2 2003 |
|  | Re- introduce hepatitis-B vaccine | Initial phase Q1 2002 Nationwide Q1 2003 |
|  | Continue vitamin A supplementation - through campaigns -through routine immunization and for post partum women | Twice yearly doses to age 6-59 months children at least up to end 2004 Develop policy by Q3 2004 |
|  | Open vial policy implemented in a phased manner | Q1 2002 onwards |
|  | Extend active surveillance to include NNT and measles | Q1 2003 onwards |
|  | Review and modify existing communicable disease reporting system. | Q1 2002 |
| 5. Commitment , Coordination and liaison with partner agencies | Conduct regular meetings of ICC | On going, to be more regular from Q3 2001 onwards-quarterly basis. |
|  | Constitute National Immunization Committee with specific TORs and meeting schedule | Q3 2001 |
|  | Create Technical working group with representation of partner agencies to meet frequently | On going |
|  | Hold annual EPI congress with Provincial EPI staff and representatives of the partner agencies. | Q3 2002 on wards |
| 6. Studies and research | Disease burden studies Hepatitis B Tetanus Measles HiB | Q1 2002 Q1 2003 Q1 2005 Q1 2003 |
|  | EPI coverage survey( provincial level) as part of annual CBS or other international agency sponsored survey | Q3 2001 |
|  | Cold chain assessment and review | Q3 2001 |
|  | EPI training need assessment | Q4 2001 |
|  | Vaccine wastage assessment and recommendations for its reduction | Q4 2001 |
|  | Assessment of injection practices and disposal of waste | Q3 2001 |
|  | County level EPI coverage survey , every three years each county | Q1 2003 onwards |
|  | EPI Financing study | Q1 2003 |
|  | National level review of EPI | Q2 2003 |
|  | How to extend benefits of EPI to other primary health care services with necessary modifications | Q2 2004 |

| Table 4 : Baseline and annual targets |
| --- |
| Number of | Baseline | Targets |
|  | 2000 | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 |
| Births | 451,480 | 455,543 | 459,643 | 463,780 | 467,954 | 472,165 | 476,415 | 480,702 |
| Infants’ deaths | 10,384 | 10,477 | 10,572 | 10,667 | 10,763 | 10,860 | 10,958 | 11,056 |
| Surviving infants | 441,096 | 445,065 | 449,071 | 453,113 | 457,191 | 461,305 | 465,457 | 469,646 |
| Infants vaccinated with BCG* | 279,918 (62.1%) | 286,992 (63%) | 298,768 (65%) | 347,835 (75%) | 397,761 (85%) | 424,949 (90%) | 452,594 (95%) | 456,667 (95%) |
| Infants vaccinated with OPV3** | 273,920 (62.1 %) | 280,391 (63%) | 291,896 (65%) | 339,835 (75%) | 388,612 (85%) | 415,175 (90%) | 442,184 (95%) | 446,164 (95%) |
| Infants vaccinated with DTP3** | 273,920 (62.1 %) | 280,391 (63%) | 291,896 (65%) | 339,835 (75%) | 388,612 (85%) | 415,175 (90%) | 442,184 (95%) | 446,164 (95%) |
| Infants vaccinated with**: Hep B (Monovalent) (use one row for any new vaccine) |  |  | 95,674 (65%) Phase I | 339,835 (75%) | 388,612 (85%) | 415,175 (90%) | 442,185 (95%) | 446,164 (95%) |
| Hep B -DPT |  |  |  |  |  | 415,175 (90%) | 442,185 (95%) | 446,164 (95%) |
| Infants vaccinated with Measles** |  | 280,391 (63%) | 291,896 (65%) | 339,835 (75%) | 388,612 (85%) | 415,175 (90%) | 442,184 (95%) | 446,164 (95%) |
| Pregnant women vaccinated with TT+ |  | 287,548 (63%) | 299,346 (65%) | 348,509 (75%) | 398,531 (85%) | 425,772 (90%) | 453,471 (95%) | 457,552 (95%) |
| CBA (Est. Annual Natural increase) |  | 280,391 (63%) | 291,896 (65%) | 339,835 (75%) | 388,612 (85%) | 415,175 (90%) | 442,184 (95%) | 446,164 (95%) |
| Vit A supplementation | Mothers (< 6 weeks from delivery) |  | 286,992 (63%) | 298,768 (65%) | 347,835 (75%) | 397,761 (85%) | 424,949 (90%) | 452,594 (95%) | 456,667 (95%) |
|  | Infants (> 6 months) | 1,940,955 | 1,958,423 (98%) | 1,976,049 (98%) | 1,993,833 (98%) | 2,011,778 (98%) | 2,029,884 (98%) | 2,048,153 (98%) | 2,066,587 (98%) |
| * Target of children out of total births | ** Target of children out of surviving infants |

- Summary of major action points and timeframe for reduction of vaccine wastage. If maximum allowance of wastage rates cannot be achieved immediately, the proposal has to provide a rationale for a higher rate. :

| Action Point | Timeline |
| --- | --- |
| Improvement in the cold chain |  |
| Assessment of the cold chain | Q 3 2001 |
| Preparation of a cold chain management Manual as a part of National EPI Manual | Q2 2002 |
| Establishment of a cold chain management team | Q3 2001 |
| Replacement/ addition of the cold chain equipment (approximately 10% of the present strength per annum | Q4 2002 on wards |
| Modifications in the frequency of immunisation sessions |  |
| The frequency of immunisation sessions will be changed from monthly to bi-monthly in Ris with small target population | Q3 2001 |
| Procurement of Appropriate size Vial |  |
| The cost-effective approach shall be considered while selecting the vial size. |  |
| Implementation of Open Vial Policy |  |
| Implementation of open vial policy of WHO in a phased manner,(as nation wide not recommended in Joint WHO UNICEF EPI review 1999) | Q3 2000 onwards |
| Emphases to be laid on the open vial policy along with VVM during the new and refresher training of the vaccinators | Q3 2001 onwards |
| Effective Supervision |  |
| Supervisors to pay special attention to the implementation of the open vial policy | Q3 2001 onwards |
| Implementation of the research findings to reduced the vaccines wastage. |  |
| A study to assess causes of vaccine wastage and measure to reduced them shall be under taken, and necessary management steps in the light of the its findings and recommendations shall be under taken. | Q1 2002 |

| Table 5 : Estimate of annual DTP wastage and drop out rates |
| --- |
|  | Actual | Targets |
|  | 2000 | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 |
| Wastage rate | 25% | 25% | 25% | 20% | 18% | 15% | 12% | 12% |
| Drop out rate [ ( DTP1 - DTP3 ) / DTP1 ] x 100 | 6 | 5 | 5 | 5 | 5 | 5 | 5 | 5 |

- Countries requesting YF vaccine have to present the same table for measles vaccine wastage rates.

- Planning and constraints for the Polio Eradication Initiative:

The Polio eradication initiative was started in 1997 with the assistance of WHO. Since then eight rounds NIDs with an average coverage of above 95% have been conducted in the country. Despite progress in the Polio eradication activities, the AFP surveillance could not be fully achieved. However with the AFP surveillance review' with the collaboration of UNICEF & WHO, planned in August 2001 it is hoped that the weak areas shall be identified and MoPH take remedial measures immediately.

The following constraints for Polio eradication initiative are identified:

- Inadequate cold chain equipment

- AFP surveillance staff not fully trained

- Data management and documentation for certification activities not of a satisfactory level

The salient features of Multiyear National EPI Plan to achieve Polio eradication activities are as follows:

- Cold chain review and strengthening

- A draft training plan prepared to be finalised in the light of the planed Training need assessment

- Reporting systems to be reviewed and strengthened especially focusing on zero reporting  and county level data.

- All activities pertaining to obtain  polio eradication certificate to be undertaken

- ICC to review the Polio eradication activities in its quarterly meetings

- Active AFP surveillance to be ensured.

# Injection safety

7.1	Summary of the injection safety strategy for immunization (for all countries):

The national EPI realises the importance of safe injections and is already using AD syringes for the immunizations. Though the injection waste is disposed mostly in a safe manner still this area needs to be strengthened in accordance with the WHO guidelines.

The national EPI has therefore prepared a draft injection safety plan for EPI. This plan shall be finalised in the light of the findings of   injection practises assessment planed to be held in 2001. The ministry of public health   plans that a national policy  and subsequent plan on injection safety and health care waste management will be developed in 2002.

The injection safety plan of EPI will then be incorporated into the national injection safety and health care waste management plan.

The national EPI plans to improve the , services delivery ,supervision , management  and operation of  injection associated activities through development of training manuals and imparting necessary trainings.

The safe injection practises shall be periodically assessed through rapid injection assessment technique of WHO. The government plans to allocate necessary resources to implement the injection safety plans  in full swing.

| Attached is a copy of the Plan to achieve Safe Injections (including plans for transition to auto-destruct syringes) and Safe Management of Sharps Waste or of the relevant pages of the health plan. | Document number 14 |
| --- | --- |

7.2	Injection safety equipment (For countries submitting a request for injection safety support). GAVI’s support is only for three years of routine immunization.

The following tables calculate the amount of supplies requested for injection safety:

| Table 6.1: Estimated supplies for safety of vaccination with BCG ( Use one table for each vaccine BCG, DTP, TT, measles and Yellow Fever, and number them from 6.1 to 6.5) |
| --- |
|  |  | Formula | 2002 | 2003 | 2004 | 2005 |
| A | Target of children for BCG vaccination (for TT : target of pregnant women) | Match with targets in table 4 | 298,768 | 347,835 | 397,761 | 424,949 |
| B | Number of doses per child (or per woman in case of TT) | # | 1 | 1 | 1 | 1 |
| C | Number of BCG doses | A x B | 298,768 | 347,835 | 397,761 | 424,949 |
| D | AD syringes (+10% wastage) | C x 1.11 | 331,632 | 386,097 | 441,515 | 471,693 |
| E | AD syringes buffer stock | D x 0.25 |  |  |  |  |
| F | Total AD syringes | D + E | 331,632 | 386,097 | 441,515 | 471,693 |
| G | Number of doses per vial | # | 20 | 20 | 20 | 20 |
| H | Vaccine wastage factor | Either 2 or 1.6 | 2 | 2 | 2 | 2 |
| I | Number of re-constitution syringes (+10% wastage) | C x H x 1.11 / G | 33,163 | 38,610 | 44,151 | 47,169 |
| J | Number of safety boxes (+10% of extra need) | ( F + I ) x 1.11 / 100 | 4,049 | 4,714 | 5,391 | 5,759 |

| Table 6.2: Estimated supplies for safety of vaccination with MV ( Use one table for each vaccine BCG, DTP, TT, measles and Yellow Fever, and number them from 6.1 to 6.5) |
| --- |
|  |  | Formula | 2002 | 2003 | 2004 | 2005 |
| A | Target of children for MV vaccination (for TT : target of pregnant women) | Match with targets in table 4 | 291,896 | 339,835 | 388,612 | 415,175 |
| B | Number of doses per child (or per woman in case of TT) | # | 1 | 1 | 1 | 1 |
| C | Number of MV doses | A x B | 291,896 | 339,835 | 388,612 | 415,175 |
| D | AD syringes (+10% wastage) | C x 1.11 | 324,005 | 377,217 | 431,359 | 460,844 |
| E | AD syringes buffer stock | D x 0.25 |  |  |  |  |
| F | Total AD syringes | D + E | 324,005 | 377,217 | 431,359 | 460,844 |
| G | Number of doses per vial | # | 10 | 10 | 10 | 10 |
| H | Vaccine wastage factor | Either 2 or 1.6 | 1.6 | 1.6 | 1.6 | 1.6 |
| I | Number of re-constitution syringes (+10% wastage) | C x H x 1.11 / G | 51,841 | 60,355 | 69,017 | 73,735 |
| J | Number of safety boxes (+10% of extra need) | ( F + I ) x 1.11 / 100 | 4,172 | 4,857 | 5,554 | 5,934 |

| Table 6.3: Estimated supplies for safety of vaccination with TT ( Use one table for each vaccine BCG, DTP, TT, measles and Yellow Fever, and number them from 6.1 to 6.5) |
| --- |
|  |  | Formula | 2002 | 2003 | 2004 | 2005 |
| A | Target of children for TT vaccination (for TT : target of pregnant women) | Match with targets in table 4 | 299,346 | 348,509 | 398,531 | 425,772 |
| B | Number of doses per child (or per woman in case of TT) | # | 2 | 2 | 2 | 2 |
| C | Number of TT doses | A x B | 598,692 | 697,018 | 797,062 | 851,544 |
| D | AD syringes (+10% wastage) | C x 1.11 | 664,548 | 773,690 | 884,739 | 945,214 |
| E | AD syringes buffer stock | D x 0.25 |  |  |  |  |
| F | Total AD syringes | D + E | 664,548 | 773,690 | 884,739 | 945,214 |
| G | Number of doses per vial | # | 10 | 10 | 10 | 10 |
| H | Vaccine wastage factor | Either 2 or 1.6 |  |  |  |  |
| I | Number of re-constitution syringes (+10% wastage) | C x H x 1.11 / G |  |  |  |  |
| J | Number of safety boxes (+10% of extra need) | ( F + I ) x 1.11 / 100 | 7,376 | 8,588 | 9,821 | 10,492 |

| Table 6.4: Estimated supplies for safety of vaccination with DPT ( Use one table for each vaccine BCG, DTP, TT, measles and Yellow Fever, and number them from 6.1 to 6.5) |
| --- |
|  |  | Formula | 2002 | 2003 | 2004 | 2005 |
| A | Target of children for DPT vaccination (for TT : target of pregnant women) | Match with targets in table 4 | 291,896 | 339,835 | 388,612 |  |
| B | Number of doses per child (or per woman in case of TT) | # | 3 | 3 | 3 |  |
| C | Number of DPT doses | A x B | 875,688 | 1,019,505 | 1,165,836 |  |
| D | AD syringes (+10% wastage) | C x 1.11 | 972,014 | 1,131,651 | 1,294,078 |  |
| E | AD syringes buffer stock | D x 0.25 |  |  |  |  |
| F | Total AD syringes | D + E | 972,014 | 1,131,651 | 1,294,078 |  |
| G | Number of doses per vial | # | 20 | 20 | 20 |  |
| H | Vaccine wastage factor | Either 2 or 1.6 |  |  |  |  |
| I | Number of re-constitution syringes (+10% wastage) | C x H x 1.11 / G |  |  |  |  |
| J | Number of safety boxes (+10% of extra need) | ( F + I ) x 1.11 / 100 | 10,789 | 12,561 | 14,364 |  |

7.3	Areas for injection safety funds (For countries requesting funds equivalent to the supplies calculated above).

List of areas of injection safety funded by different sources: (For the GAVI/The Vaccine Fund support, fill in “areas of support”. For AD syringes and waste disposal, fill in “source of funds”.)

| Source of fund | Area of support | Start of fund utilization |
| --- | --- | --- |
| GAVI/Vaccine Fund | AD syringes and waste disposal boxes |  |

(Use as many rows as necessary

# New and under-used vaccines

- Summary of those aspects of the multi-year immunization plan that refer to the introduction of new and under-used vaccines.

Locally produced monovalent Hepatitis B vaccine was introduced in 1996 in the immunisation programme for children less than five years. It was also administered to health workers at high risk from blood borne infections. As the vaccine supply could not be maintained due to economic difficulties up until 2000 it was only provided to about 30% of target population mostly in the cities, after which the vaccine production has further declined. Currently the country produces about 200,000 doses annually. This vaccine is given to those children whose mothers are proved to be Hepatitis B carriers.

The different studies have reported the sero prevalence of HbsAg among the population from 5.5 to 9.1%. .

A plan has been prepared to add Hepatitis B vaccine in EPI schedule for 0-11 month children. This will be undertaken in a phased manner from 2002, and shall be extended to the whole target population in the country in 2003. In the initial two years (2002 & 2003) 10% of the target population born in hospital will be giving birth dose of hepatitis B vaccine. Depending on outcome of a proposed study to determine prevalence of HbeAg in pregnant women in 2003 birth dose of Hepatitis B will be introduced all over the country. DPR Korea will shift to         Hep B –DPT (combo) instead of Hep B (mono) to the target population in 2005 if available in the global market.

The gradual introduction of Hep B vaccine over two years will provide experience to address managerial and logistic problem in further introduction of the vaccine in all parts of the country. A training plan encompassing different components of EPI, including service deliver, safety of injections, supervision has been conducted to all EPI staff. The strategies for vaccine wastage reduction have been given due importance in the plan

The plan also focuses on the IEC. Strengthened supervision, annual cluster coverage surveys at county level, proper routine reporting and improved AEFI system are proposed for the monitoring and evaluation of the introduction of Hep-B in the EPI.

- Assessment of burden of relevant diseases (if available) :

| Disease | Title of the assessment | Date | Results |
| --- | --- | --- | --- |
| Hepatitis B | Report of Bio-medical Institute | 2000 | 4-5% carrier rate |

- (if new or under-used vaccines have been already introduced)

Lessons learnt about storage capacity, protection from accidental freezing, staff training, cold chain, logistics, drop out rate, wastage rate etc. as per current experience with new and under-used vaccines:

- As enough quantity was not produced, the then existing cold chain capacity was sufficient.

- It was administered through the routine EPI services and the same logistic problems as for routine vaccines, like difficulty in transportation, were faced.

- The different sizes of vials having, 1,5,10 and 20 doses were produced. This some times caused confusion among the health workers.

- Wastage to the tune of 30% was noted in the 20 dose vials. The single dose vials were not found to be cost effective.

- As with the other EPI vaccines the drop out rate is low  ie 6 % , because of a strong section doctor system.

- Summary of the action points that address possible implications for storage capacity, staff training, cold chain, measures to avoid freezing of vaccines, logistics, drop out rate, wastage rate etc… in the Plan for Introduction of New and Under-used Vaccines :

- Cold chain assessment is planed for 2001 (accomplished)

- The clod chain strengthening has been planned and shall be finalised in the light of the cold chain assessment recommendation. (ongoing)

- Training areas have been identified and a draft training plan prepared. This will be finalised in early 2002 after a study on training needs is undertaken. Due importance in the training shall be given to preserve the potency of the vaccine and the safety of the injections besides other component of EPI.  (accomplished)

- Logistics strengthening has been planned in Multi year National EPI plan

- Strategies for Vaccine wastage reduction have been outlined in previous section of this document

- First preference: required number of doses and presentations of requested new and under-used vaccines. (For each one of the requested first preference of new and under-used vaccine, please use provided formulae)

Table 7.1.1: Estimated number of doses  of  Hep B monovalent vaccine for phase I (Specify one table for each presentation of any vaccine and number it 7.2, 7.3, …)

|  |  | Formula | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A | Number of children to receive new vaccine | # | 95,674 | 111,386 | 127,373 |  |  |  |
| B | Percentage of vaccines requested from The Vaccine Fund | % | 100 | 100 | 100 |  |  |  |
| C | Number of doses per child | # | 3 | 3 | 3 |  |  |  |
| D | Number of doses | A x B/100 x C | 287,022 | 334,158 | 382,119 | - | - | - |
| E | Estimated wastage factor | see list in table ( | 1.33 | 1.25 | 1.22 | 1.18 | - | - |
| F | Number of doses ( incl. wastage) | A x C x E x B/100 | 381,739 | 417,698 | 466,185 | - | - | - |
| G | Vaccines buffer stock | F x 0.25 | 95,435 |  |  | - | - | - |
| H | Total vaccine doses requested | F + G | 477,174 | 417,698 | 466,185 | - | - | - |
| I | Number of doses per vial | # | 10 | 10 | 10 | - | - | - |
| J | Number of AD syringes (+ 10% wastage) | (D + G) x 1.11 | 424,527 | 370,915 | 424,152 | - | - | - |
| K | Reconstitution syringes (+ 10% wastage) | H / I x 1.11 |  |  |  | - | - | - |
| L | Total of safety boxes (+ 10% of extra need) | (J + K) / 100 x 1.11 | 4,712 | 4,117 | 4,708 | - | - | - |

Table 7.1.2 : Estimated number of doses  of  Hep B monovalent vaccine for phase II (Specify one table for each presentation of any vaccine and number it 7.2, 7.3, …)

|  |  | Formula | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A | Number of children to receive new vaccine | # |  | 228,449 | 261,239 |  |  |  |
| B | Percentage of vaccines requested from The Vaccine Fund | % |  | 100 | 100 |  |  |  |
| C | Number of doses per child | # |  | 3 | 3 |  |  |  |
| D | Number of doses | A x B/100 x C |  | 685,347 | 783,717 | - | - | - |
| E | Estimated wastage factor | see list in table ( |  | 1.25 | 1.22 | - | - | - |
| F | Number of doses ( incl. wastage) | A x C x E x B/100 |  | 856,684 | 956,135 | - | - | - |
| G | Vaccines buffer stock | F x 0.25 |  | 214,171 |  | - | - | - |
| H | Total vaccine doses requested | F + G |  | 1,070,855 | 956,135 | - | - | - |
| I | Number of doses per vial | # |  | 10 | 10 | - | - | - |
| J | Number of AD syringes (+ 10% wastage) | (D + G) x 1.11 |  | 998,465 | 869,926 | - | - | - |
| K | Reconstitution syringes (+ 10% wastage) | H / I x 1.11 |  |  |  | - | - | - |
| L | Total of safety boxes (+ 10% of extra need) | (J + K) / 100 x 1.11 |  | 11,083 | 9,656 | - | - | - |

Table 7.1.3 : Estimated number of doses  of  Hep B monovalent vaccine for phase I & II (Specify one table for each presentation of any vaccine and number it 7.2, 7.3, …)

|  |  | Formula | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A | Number of children to receive new vaccine | # | 95,674 | 339,835 | 388,612 | 424,949 | 425,594 | 456,667 |
| B | Percentage of vaccines requested from The Vaccine Fund | % | 100 | 100 | 100 | 100 | 100 | 100 |
| C | Number of doses per child | # | 3 | 3 | 3 | 1 | 1 | 1 |
| D | Number of doses | A x B/100 x C | 287,022 | 1,019,505 | 1,165,836 | 424,949 | 425,594 | 456,667 |
| E | Estimated wastage factor | see list in table ( | 1.33 | 1.25 | 1.22 | 1.18 | 1.14 | 1.14 |
| F | Number of doses ( incl. wastage) | A x C x E x B/100 | 381,739 | 1,274,381 | 1,422,320 | 501,440 | 485,177 | 520,600 |
| G | Vaccines buffer stock | F x 0.25 | 95,435 | 318,595 |  |  |  |  |
| H | Total vaccine doses requested | F + G | 477,174 | 1,592,977 | 1,422,320 | 501,440 | 485,177 | 520,600 |
| I | Number of doses per vial | # | 10 | 10 | 10 | 10 | 10 | 10 |
| J | Number of AD syringes (+ 10% wastage) | (D + G) x 1.11 | 424,527 | 1,485,291 | 1,294,078 | 471,693 | 472,409 | 506,900 |
| K | Reconstitution syringes (+ 10% wastage) | H / I x 1.11 |  |  |  | - | - | - |
| L | Total of safety boxes (+ 10% of extra need) | (J + K) / 100 x 1.11 | 4,712 | 16,487 | 14,364 | 5,236 | 5,244 | 5,627 |

Table 7.2: Estimated number of doses  of  Hep B-DPT vaccine  (Specify one table for each presentation of any vaccine and number it 7.2, 7.3, …)

|  |  | Formula | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A | Number of children to receive new vaccine | # |  |  |  | 415,175 | 442,184 | 446,164 |
| B | Percentage of vaccines requested from The Vaccine Fund | % |  |  |  | 100 | 100 | 100 |
| C | Number of doses per child | # |  |  |  | 3 | 3 | 3 |
| D | Number of doses | A x B/100 x C |  |  |  | 1,245,525 | 1,326,552 | 1,338,492 |
| E | Estimated wastage factor | see list in table ( |  |  |  | 1.18 | 1.14 | 1.14 |
| F | Number of doses ( incl. wastage) | A x C x E x B/100 |  |  |  | 1,469,720 | 1,512,269 | 1,525,881 |
| G | Vaccines buffer stock | F x 0.25 |  |  |  | 367,430 |  |  |
| H | Total vaccine doses requested | F + G |  |  |  | 1,837,149 | 1,512,269 | 1,525,881 |
| I | Number of doses per vial | # |  |  |  | 10 | 10 | 10 |
| J | Number of AD syringes (+ 10% wastage) | (D + G) x 1.11 |  |  |  | 1,790,380 | 1,472,473 | 1,485,726 |
| K | Reconstitution syringes (+ 10% wastage) | H / I x 1.11 |  |  |  |  |  |  |
| L | Total of safety boxes (+ 10% of extra need) | (J + K) / 100 x 1.11 |  |  |  | 19,873 | 16,344 | 16,492 |

| Table ( : Wastage rates and factors |
| --- |
| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

- Second preference: Required number of doses and presentations of requested new and under-used vaccines, if first preference is not available. (Please use provided formulae as per table 7.1)

| Attached is the plan of action for vaccinations with new or under-used vaccines (if already contained within the national, multi-year plan, indicate pages) | Document number 13 |
| --- | --- |

# Strategic directions to mobilise additional resources for immunization

- Summary of strategies that the Government intends to pursue to increase the resources for immunization of children, and that will be converted in a comprehensive Financial Sustainability Plan. Highlights of the agreements made with donor agencies (i.a.: Vaccine Independence Initiative) and the use of funds freed by debt relief:

The Government of DPRK fully realises the importance of a successful immunization program, leading to healthier and prosperous nation. The Government is trying to provide maximum possible resources for the program. The partners EPI duly support the government’s efforts.

The Ministry of Health intends to secure additional funding for EPI strengthening through:

- Availing the funds been provided by GAVI.

- Making a request to Government of DPRK for corresponding increase in the resources allocated for the EPI.

- Requesting the partner agencies for greater support of EPI.

- Approaching the potential donors , through sharing with them the plans and achievements of EPI ,for bi lateral funding

- Effective utilization of the support

| Tables of expenditure for 2000 and resource needs detailing the sources of funds for 2000 and subsequent years are attached in Annex 1. | Document number Annex-1 |
| --- | --- |

- Remarks on recurrent cost reduction strategies which contribute to financial sustainability, such as vaccine wastage reduction:

- Effective use of human resource, like giving additional responsibility of ensuring safe injection practices at each health facility to an already posted doctor, rather than recruiting new persons for this post.

- A judicious system of performance based monitoring there by ensuring greater program outputs and minimizing wastage of resources.

- Implementation of vaccine wastage reduction plans leading to substantial saving by preventing the wastage of vaccine. In developing countries the cost of vaccine in EPI programme is about 30%

- With the clear procedures and job description, as planned for EPI Manual, the individuals shall be more responsible and aware of technical matters therefore resource wastage and unnecessary utilization of the resources shall be minimised.

- The well-planned refresher training courses shall not only improve the quality of service delivery but also cut the cost of programme through efficient use of resources.

- The strong system of section doctors, where the section doctors acts as vaccinators as well as social moraliser, helps in reducing dropouts and vaccine wastage.

- The vaccine schedule is flexible in area with scanty population, thus helping in reducing in vaccine wastage.

# Summary of requests to GAVI and the Vaccine Fund

With reference to all points presented above, the Government of Democratic Republic of Korea considering that its DTP3 coverage for 2001 was 65%  corresponding to 296,103 number of children vaccinated with DTP3, requests the Alliance and its partners to contribute financial and technical assistance required to increase immunization of children.

Specifically, the Government hereby applies for the following types of support from GAVI and the Vaccine Fund. (Circle “YES” or “NO” according to the requests submitted with this proposal):

- Support for Immunization Services                       		( YES  )         NO

- Support for New and Under-used vaccines                                  ( YES )         NO

- Support for Injection Safety                                                         ( YES )          NO

10.1	SUPPORT FOR IMMUNIZATION SERVICES

GAVI and the Vaccine Fund are requested to fund the strategies for strengthening immunization services in year 2002 according to the number of additional children (as compared to the baseline) that are targeted to be immunized with DTP3 as presented in table 4, namely 65,915 (number of children). Funds will also be requested for following years as estimated in table 4.

- The Government takes full responsibility to manage the in-country transfer of funds.

(In case an alternative mechanism is necessary

- Operational mechanism that is followed for safeguarding transparency, standards of accounting, long-term sustainability and empowerment of the government in using the funds:

The funds shall be held by Ministry of Public Health DPRK and utilised for activities as per Multi year National EPI Plan (2001-2006).

The local procurements shall be made according to standard Government procedures

The international procurements shall be undertaken through UNICEF

The standard government procedures of accounting and book keeping shall be followed. These are timed tested procedures for the safeguarding of transparency, accuracy and long term sustainability. The management of the funds shall further build the local capacity for the financial management. An annual government audit shall be conducted. The expenses made out of GAVI/the Vaccine funds in DPRK shall be open for the audit by GAVI/the Vaccine fund or their representative.

Countries requesting immunization services support should submit the” Banking Details” form (Annex 3) with their proposal, it will speed up the process for funds disbursement to the country, as soon as the support for Immunization Services is approved.

  - SUPPORT FOR NEW AND UNDER-USED VACCINES

GAVI and the Vaccine Fund are requested to fund the introduction of New and Under-used Vaccines by providing the following vaccines: (fill in only what is being requested from the Vaccine Fund in line with tables 7.1, 7.2…)

| Table 8: New and under-used vaccines requested from GAVI and the Vaccine Fund |
| --- |
| Vaccine presentation | Number of doses per vial | Starting month and year | Number of doses requested for first calendar year | Number of doses requested for second calendar year * |
| Hep B vaccine monovalent | 10 doses | Jan.2002 | 477,174 | 1,078,855 |
| * Vaccines will also be requested for following years as described in tables 7.1, 7.2… |

- Vaccines will be procured (tick only one) :

By UNICEF                                               By GOVERNMENT

- (If vaccines are proposed to be procured by the Government) 	Process and procedures of the National Regulatory Authority to control the purchase and delivery of vaccines into the country, including weaknesses, constraints and planned measures to improve the control system:

- (In case you are approved, you will be entitled to receive a lump-sum of US$ 100,000 to facilitate the introduction of new vaccines) Please submit the attached “Banking Form”(Annex 3) with the proposal, in case you have not yet already done so for other types of support from GAVI/The Vaccine Fund..

  - SUPPORT FOR INJECTION SAFETY

GAVI and the Vaccine Fund are requested to support the injection safety plan by providing:

(Tick one choice only):		The amount of supplies listed in table 9

The equivalent amount of funds

| Table 9: Summary of total supplies for safety of vaccinations with BCG, DTP, TT, MEASLES and YF, requested from GAVI and the Vaccine Fund for three years (fill in the total sums of rows “F”, I and J of tables 6.1,6.2, 6.3, 6.4 and 6.5). |
| --- |
|  | ITEM | 2002 | 2003 | 2004 | 2005 |
| F | Total AD syringes | for BCG | 331,632 | 386,097 | 441,515 | 471,693 |
|  |  | for other vaccines | 1,960,567 | 2,282,558 | 2,610,176 | 1,406,058 |
| I | Total of reconstitution syringes | 85,004 | 98,965 | 113,168 | 120,904 |
| J | Total of safety boxes | 26,386 | 30,720 | 35,130 | 22,185 |

- (In case you request funds equivalent to the above supplies at the prices obtained by UNICEF) Please submit the attached “Banking Form”(Annex 3) with the proposal, in case you have not yet already done so for other types of support from GAVI/The Vaccine Fund.

# Additional comments and recommendations from the ICC

The ICC under stands that the support from the GAVI/Vaccine fund for re-introducing Hep B vaccination in EPI and strengthening of immunization services is of high importance to the country.

The ICC intents to make best use of this opportunity to put back the EPI on road to success as it was prior to mid 80s economic difficulties.

The role of ICC in ensurings the implementation of  multi-year national EPI plan is critical and ICC is prepared to play its part.

The ICC in line with  the broader government policies of self reliability shall strive hard to make the EPI programme more sustainable with the country resources, through gradual annual increase in the budget allocation EPI.

ANNEX 1

#### Statement of financing and of unmet needs for immunization (USD ,000)

Table 1

| Expenditure in 2001 from different sources |
| --- |
| Ref. # | Items | government | WHO | UNICEF | TOTAL |
| 1. | Vaccine AD Syringes… |  |  |  |  |
| 1.1 | Vaccine |  | 450,000 | 3,822,191 |  |
| 1.2 | AD syringe |  |  | 102,270 |  |
| 1.3 | Reconstitution Syringe |  |  | 162,185 |  |
| 1.4 | Vaccine production | 4,878,660 |  |  |  |
| 2. | Equipment (cold chain, spare part, sterilization) |  |  |  |  |
| 2.1 | Reusable syringe | 1,793,160 |  |  |  |
| 2.2 | Cold chain equipment and repair | 328,440 |  |  |  |
| 2.3 | Cold box |  |  | 164,105 |  |
| 2.4 | Vaccine carrier and thermometer |  |  | 31,398 |  |
| 2.5 | Bicycle and motorbike |  |  | 43,890 |  |
| 2.6 | Generators and stabilizer |  |  | 69,012 |  |
| 2.7 | Refrigerator and freezer |  |  | 102,350 |  |
| 3. | Others for vaccination |  |  |  |  |
| 3.1 | Transportation | 2,056,320 | 86,500 |  |  |
| 3.2 | Management | 2,158,320 |  |  |  |
| 3.3 | Sterilization |  |  |  |  |
| 3.4 | Surveillance |  | 13,000 |  |  |
| 3.5 | Salary | 5,892,540 |  |  |  |
| 3.6 | NID’s operation |  | 37,600 |  |  |
| 3.7 | Routine immunization |  | 69,468 |  |  |
| 3.8 | EPI manual |  |  | 2,860 |  |
| 3.9 | Computer |  |  | 3,223 |  |
| 3.10 | Printing EPI posters |  |  | 9,800 |  |
| 3.11 | Printing forms for EPI surveillance |  |  | 22,900 |  |
| Total expenditure for 2001 | 17,279,820 | 594,068 | 4,536,187 |  |
| 1 If basket funding or a similar aggregated funding approach is used, please describe the total funding amounts, and/or detail partner contributions as fully as possible. 2 Please use the electronic version of the document and insert as many columns for partner contributions as are necessary for your submission. 3 Please use the electronic version of the document to insert as many line items as necessary for your submission. |

Table 2

| Budget for 2001 from different sources |
| --- |
| Ref. # | Items | Government | WHO | UNICEF | TOTAL |
| 1. | Vaccine AD syringes |  |  |  |  |
| 1.1 | Vaccine |  | 450,000 |  |  |
| 1.2 | Vaccine production | 4,878,860 |  |  |  |
| 2. | Equipment (cold chain, spare part, sterilization) |  |  |  |  |
| 2.1 | Reusable syringe | 1,793,160 |  |  |  |
| 2.2 | Cold chain equipment, repair | 328,440 | 280,000 |  |  |
| 3 | Others for immunization |  |  |  |  |
| 3.1 | Transportation | 2,056,,320 |  |  |  |
| 3.2. | Management | 2,158,320 |  |  |  |
| 3.3 | Sterilization | 172,380 | 121,000 |  |  |
| 3.4 | Surveillance | 5,892,540 |  |  |  |
| 3.5 | Salary |  | 455,260 |  |  |
| 3.6 | NID’s operation |  | 92,000 |  |  |
| 3.7 | Routine immunization | 17,279,820 | 1,398,260 | 2,003,942 |  |
| Total budget for 2001 |  |  |  |  |
| 1 If basket funding or a similar aggregated funding approach is used, please describe the total funding amounts, and/or detail partner contributions as fully as possible. 2 Please use the electronic version of the document and insert as many columns for partner contributions as are necessary for your submission. 3 Please use the electronic version of the document to insert as many line items as necessary for your submission. |

ANNEX  2

Summary of documentation

| Background information on Health System Development status |
| --- |
| National report on the implantation of the decisions of the ‘World Summit for Children” Jan 2001 | Document number 1 |
| Statement by HE Mr. Choe Su Hon | Document number 2 |
| Project plan of Action 2000, Strengthening Early Warning System, Pyongyang, Mar. 2000 EHA/DPRK WHO | Document number 3 |
| Project plan of Action 2001, District Health System, Pyongyang Sep. 2000 EHA/DPRK WHO | Document number 4 |
| Profile of the Inter Agency Co-ordinating Committee (ICC) |
| ICC’s workplan for the next 12 months | Document number 5 |
| Terms of reference of the ICC | Document number 6 |
| Minutes of the three most recent ICC meetings or any meetings concerning the introduction of new or under-used vaccines or safety of injections | Document number |
| Minute of ICC meeting 25 May 2000 | Document number 7-1 |
| Minute of ICC meeting 28 Jun 2000 | Document number 7-2 |
| Minute of ICC meeting Sep 2000 | Document number 7-3 |
| Minute of TWG meeting April 27 2001 | Document number 8-1 |
| Minute of TWG meeting May 2001 | Document number 8-2 |
| Minute of TWG meeting 12 July 2001 | Document number 8-3 |
| Minute of TWG meeting May 6, 2002 | Document number 8-4 |
| Minute of TWG meeting 12 July 2002 | Document number 8-5 |
| Minute of TWG meeting 12 Aug 2002 | Document number 8-6 |
| Immunization Services Assessment |
| Joint EPI review 1999 | Document number 9 |
| Draft report on cold chain, training in DPRK | Document number 10 |
| Summary of the recommendations of the assessment report(s) with remarks on the status of implementation of each recommendation. | Document number 11 |
| Multi-Year Immunization Plan |
| Complete copy (with executive summary) of the Multi-Year Immunization Plan or of the relevant pages of the health sector plan. | Document number 12 |
| Action plan for the introduction of Hepatitis vaccine vaccines into immunization services A copy of the Plan to achieve Safe Injections | Document number 13 Document number 14 |
| Unmet needs requiring additional resources |
| Tables of expenditure for 2001 and resource needs (Annex 1) | Document number 15 |
| Other relevant documents |
| CBS survey 2000 report | Document number 16 |
| The multi indicator Cluster Survey in DPRK 1998. | Document number 17 |
| Master Plan of Operation UNICEF | Document number 18 |
| Project plan of Actions 2001 UNICEF | Document number 19 |

# Footnotes

DPRK  WHO/UNICEF joint reporting form on vaccine preventable diseases for the period Jan-Dec 2000

Excludes DPT for 2005and 2006 as included in Hep B –DPT and also excludes syringes and safety boxes for the TT and Measles campaign.

Includes safety boxes for routine EPI vaccinations for 2002-2004 , excludes safety Boxes for campaigns.

2nd MICS in DPR Korea 2000, Central Bureau of statistics, Oct 2000

2nd MICS in DPR Korea 2000, Central Bureau of statistics, Oct 2000

The assessments reviews and studies from 2002-2006 are mentioned in the multi year national EPI plan.

Beginning and end of the activity unless specified otherwise.

The back log will be cleared in TT campaign planed for 2002.

Formula to calculate DTP vaccine wastage rate (in percentage): [ ( A – B ) / A ] x 100.   Whereby: A = The number of DTP doses distributed for use according to the supply records with correction for stock balance at start and end of the supply period; B = the number of DTP vaccinations. If you request yellow fever vaccines, include a reo for measles vaccine wastage rate.

Based on DPRK/UNICEF  Joint reporting form on Vaccine Preventable diseases 2000

WHO,UNICEF, UNFPA global policy, December 1999.

GAVI/The Vaccine Fund will fund the procurement of AD syringes to deliver 2 doses of TT to pregnant women. If the immunization policy of the country includes all Women in Child Bearing Age (WCBA), GAVI/The Vaccine Fund will contribute to a maximum of 2 doses for Pregnant Women (estimated as total births).

The buffer stock for vaccines and AD syringes is set at 25%. This is calculated with the first stock of doses required to introduce the vaccination in any given geographic area. Write zero for other years.

Standard wastage factor will be used for calculation of re-constitution syringes. It will be 2 for BCG, and 1.6 for measles and YF.

Only for lyophilized vaccines. Write zero for other vaccines

GAVI/The Vaccine Fund will fund the procurement of AD syringes to deliver 2 doses of TT to pregnant women. If the immunization policy of the country includes all Women in Child Bearing Age (WCBA), GAVI/The Vaccine Fund will contribute to a maximum of 2 doses for Pregnant Women (estimated as total births).

The buffer stock for vaccines and AD syringes is set at 25%. This is calculated with the first stock of doses required to introduce the vaccination in any given geographic area. Write zero for other years.

Standard wastage factor will be used for calculation of re-constitution syringes. It will be 2 for BCG, and 1.6 for measles and YF.

Only for lyophilized vaccines. Write zero for other vaccines

GAVI/The Vaccine Fund will fund the procurement of AD syringes to deliver 2 doses of TT to pregnant women. If the immunization policy of the country includes all Women in Child Bearing Age (WCBA), GAVI/The Vaccine Fund will contribute to a maximum of 2 doses for Pregnant Women (estimated as total births).

The buffer stock for vaccines and AD syringes is set at 25%. This is calculated with the first stock of doses required to introduce the vaccination in any given geographic area. Write zero for other years.

Standard wastage factor will be used for calculation of re-constitution syringes. It will be 2 for BCG, and 1.6 for measles and YF.

Only for lyophilized vaccines. Write zero for other vaccines

GAVI/The Vaccine Fund will fund the procurement of AD syringes to deliver 2 doses of TT to pregnant women. If the immunization policy of the country includes all Women in Child Bearing Age (WCBA), GAVI/The Vaccine Fund will contribute to a maximum of 2 doses for Pregnant Women (estimated as total births).

The buffer stock for vaccines and AD syringes is set at 25%. This is calculated with the first stock of doses required to introduce the vaccination in any given geographic area. Write zero for other years.

Standard wastage factor will be used for calculation of re-constitution syringes. It will be 2 for BCG, and 1.6 for measles and YF.

Only for lyophilized vaccines. Write zero for other vaccines

Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided

The country would aim for a maximum wastage rate of 25% for the first year with a plan to gradually reduce it to 15% by the third year. For vaccine in single or two-dose vials the maximum wastage allowance is 5%. No maximum limits have been set for yellow fever vaccine in multi-dose vials.

The buffer stock for vaccines and AD syringes is set at 25%. This is added to the first stock of doses required to introduce the vaccination in any given geographic area. Write zero under other years. In case of a phased introduction with the buffer stock spread over several years, the formula should read: [ F – number of doses (incl. wastage) received in previous year ] * 0.25.

A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines.

It applies only for lyophilized vaccines. Write zero for other vaccines.

A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes

Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided

The country would aim for a maximum wastage rate of 25% for the first year with a plan to gradually reduce it to 15% by the third year. For vaccine in single or two-dose vials the maximum wastage allowance is 5%. No maximum limits have been set for yellow fever vaccine in multi-dose vials.

The buffer stock for vaccines and AD syringes is set at 25%. This is added to the first stock of doses required to introduce the vaccination in any given geographic area. Write zero under other years. In case of a phased introduction with the buffer stock spread over several years, the formula should read: [ F – number of doses (incl. wastage) received in previous year ] * 0.25.

A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines.

It applies only for lyophilized vaccines. Write zero for other vaccines.

A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes

Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided

The country would aim for a maximum wastage rate of 25% for the first year with a plan to gradually reduce it to 15% by the third year. For vaccine in single or two-dose vials the maximum wastage allowance is 5%. No maximum limits have been set for yellow fever vaccine in multi-dose vials.

The buffer stock for vaccines and AD syringes is set at 25%. This is added to the first stock of doses required to introduce the vaccination in any given geographic area. Write zero under other years. In case of a phased introduction with the buffer stock spread over several years, the formula should read: [ F – number of doses (incl. wastage) received in previous year ] * 0.25.

A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines.

It applies only for lyophilized vaccines. Write zero for other vaccines.

A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes

Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided

The country would aim for a maximum wastage rate of 25% for the first year with a plan to gradually reduce it to 15% by the third year. For vaccine in single or two-dose vials the maximum wastage allowance is 5%. No maximum limits have been set for yellow fever vaccine in multi-dose vials.

The buffer stock for vaccines and AD syringes is set at 25%. This is added to the first stock of doses required to introduce the vaccination in any given geographic area. Write zero under other years. In case of a phased introduction with the buffer stock spread over several years, the formula should read: [ F – number of doses (incl. wastage) received in previous year ] * 0.25.

A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines.

It applies only for lyophilized vaccines. Write zero for other vaccines.

A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes

Please submit hard copy documents with an identical electronic copy whenever possible

# Text boxes

(

(