Revision 3

August 2001

The Government of

The Democratic Republic of Congo (DRC)

Proposal for support submitted to the

Global Alliance for Vaccines and Immunization (GAVI)

and the Vaccine Fund

This document is accompanied by an electronic copy on diskette for your convenience. Please return a copy of the diskette with the original, signed hard-copy of the document to

GAVI Secretariat; c/o UNICEF; Palais des Nations; 1211 Geneva 10; Switzerland.

Enquiries please to: Dr Tore Godal, tgodal@unicef.org or representatives of a GAVI partner agency.  All documents and attachments must be submitted in English or French.

# Executive Summary

As the abrupt cut-off of structural cooperation led to the withdrawal of various types of support in the development sector in 1991, this had a negative impact on the development of PHC activities, particularly in the field of immunization.

The Program lost its main sources of funding, which led to dysfunctions and a drop in the quality of support to the health zones.

This situation has been aggravated by the armed conflicts in the country since 1996, making it difficult if not impossible to conduct supervision and monitoring activities and, in general, to supervise activities by central teams in 130 health zones in the eastern part of the country.  By way of example, only 19% of the necessary funding for routine EPI was received for the year 2000, which shows just how essential GAVI is in relaunching routine EPI in the DRC.

For the time being, there is strong political will to relaunch EPI activities throughout the country by means of coordinated action by the Government and its different partners.

Accordingly, the DRC needs considerable financial backing to achieve its goals, as set out in the five-year strategic EPI plan for 2002-2006.

Financial assistance is therefore sought from GAVI for the following:

1.	Improvement of EPI infrastructures with a view to increasing vaccine coverage

2.	Introduction of Hepatitis B (HepB) vaccines and Haemophilus influenzae type b (Hib)

3.	Introduction of yellow fever vaccines.

For the year 2000, DTP3 vaccine coverage was 39%, which corresponded to 882,960 children immunized.

The program aims to achieve the following projections in coming years:

| ### Antigen | 2000 | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| DTP 3 | 39% | 45% | 55% | 70% | 75% | 80% | 85% |
| Target of children for immunization | 928,240 | 1,048,050 | 1,317,800 | 1,728,300 | 1,911,000 | 2,105,600 | 2,310,300 |

With regard to new and under-used vaccines, the following tables indicated the year of introduction, projections for vaccine coverage, the number of doses required as well as the presentation for each vaccine.

- For DTP-HepB  (combined) :

| Year | 2003 | 2004 | 2005 | 2006 | 2007 |
| --- | --- | --- | --- | --- | --- |
| Coverage targets | 70 | 75 | 80 | 85 | 90 |
| Total no. of doses of vaccines | 5,742,683 | 6,337,459 | 5,570,205 | 6,095,892 | 6,648,108 |
| No. doses per vial | 10 | 10 | 10 | 10 | 10 |

- For monovalent Hib :

| Year | 2003 | 2004 | 2005 | 2006 | 2007 |
| --- | --- | --- | --- | --- | --- |
| Coverage targets | 70 | 75 | 80 | 85 | 90 |
| Total no. of doses of vaccines | 5,742,683 | 6,337,459 | 5,570,205 | 6,095,892 | 6,648,108 |
| No. doses per vial | 10 | 10 | 10 | 10 | 10 |

- Yellow fever vaccine

| Year | 2002 | 2003 | 2004 | 2005 | 2006 |
| --- | --- | --- | --- | --- | --- |
| Coverage targets | 40 | 65 | 70 | 75 | 80 |
| Total no. of doses of vaccines | 2,123,970 | 2,559,595 | 2,413,304 | 2,4717,782 | 2,543,541 |
| No. doses per vial | 10 | 10 | 10 | 10 | 10 |

In its annual plan of activities, the Inter-Agency Coordinating Committee not only ensures that the necessary funding and other means are available to achieve the EPI goals but must also play a supervisory and follow-up role in the implementation of the annual EPI plan.  In addition, it must see to it that the funds are administered properly and transparently.

# Signatures of the Government and the Inter-Agency Co-ordinating Committee

The Government of The Democratic Republic of Congo . commits itself to develop the national immunization services on a sustainable basis in accordance with the multi-year plan presented with this document. Districts performance on immunization will be reviewed annually through a transparent monitoring system. The Government requests the Alliance and its partners to contribute financial and technical assistance to support immunization of children as outlined in this application.

Signature:	Prof. Mashako Mamba……………………...

Title:	Minister of Health…………………………………………...

Date:	…………………………………………...

The GAVI Secretariat is unable to return submitted documents and attachments to individual countries.  Unless otherwise specified, documents may be shared with the GAVI partners and collaborators.

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this proposal on the basis of the supporting documentation which is attached. Signatures for endorsement of this proposal does not imply any financial (or legal) commitment on the part of the partner agency or individual:

| Agency/Organisation | Name/Title | Date Signature |
| --- | --- | --- |
| Minister of Health | Dr. Mashako Mamba Minister of Health |  |
| WHO | Dr. Léonard Tapsoba Representative |  |
| UNICEF | Mr. Martin Mongwanja Representative |  |
| ROTARY | Mr. Ambroise Tshimbalanga President, National Polio Plus Committee |  |
| BASICS | Mr. Dan Nelson Resident Representative |  |
| USAID | Mr. Ron Harvey Director |  |

In case the GAVI Secretariat have queries on this submission, please contact :

Name : Dr. Pierre Kandolo Wenye…………………	Title/Address :Head Doctor, EPI-CCCD ……………………………….

Tel.No. : 243 40090 (Starcel)…………….   		Avenue de la Justice No. 28/32

Kinshasa GOMBE / DRC

Fax No. :……WHO Fax  1321953904097…………………….. 		            ………………………………..

E-mail :pevrdc@raga.net……………………………                         ……………………………….

Alternative address :

Name : Dr. Matthieu Kamwa…………Title/Address : Team Leader EPI/WHO-DRC 						Avenue des cliniques No. 32

Kinshasa GOMBE / DRC

Tel.No. : +243 8804119		            ………………………………..

Fax No. :13219539041097 		            ………………………………..

E-mail :kenakamwa@jobantech.cd                         ……………………………….

3.	Immunization-related fact sheet

| Table 1 : Basic facts (For the year 2000 or most recent; specify dates of data provided) |  |  |  |
| --- | --- | --- | --- |
| Population | 50,948,236 UNDP forecast 1974-2010 (revision 2000) | GNP per capita | <USD 100 |
| Surviving Infants* | 2,264,000 | Infant mortality rate | 84 / 1000 |
| Percentage of GDP allocated to Health | NA | Percentage of Government expenditure for health care | NA |

* Surviving infants = Infants surviving the first 12 months of life

| Table 2: Trends of immunization coverage and disease burden by 12 months of age as per annual WHO/UNICEF Joint Reporting Form on Vaccine Preventable Diseases |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Trends of immunization coverage ( in percentage ) |  |  |  |  |  |  |  |  | Vaccine-preventable disease burden |  |  |
| Vaccine |  |  | Reported |  | Survey |  |  |  | Disease | Number of reported cases |  |
|  |  |  | 1999 | 2000 | 1999 | Age group | 2000 | Age group |  | 1999 | 2000 |
| BCG |  |  | 45.3% | 56% | NA |  | NA |  | Tuberculosis | 59531 | 60616 |
| DTP | DTP1 |  | 37% | 43% | NA | NA |  |  | Diphtheria | NA | NA |
|  | DTP3 |  | 30.5% | 39% | NA | NA |  |  | Pertussis | 100 | 1448 |
| OPV3 |  |  | 33% | 41% | NA |  | NA |  | Polio | 2 | 28 |
| Measles |  |  | 22% | 45% | ND |  | ND |  | Measles | 26976 | 25458 |
| TT2+ (Pregnant women) |  |  | 27.7% | 25% | ND |  | ND |  | NN Tetanus | 553 | 1337 |
| Hib3 |  |  | NA | NA | NA |  | NA |  | Hib | NA | NA |
| Yellow Fever |  |  | NA | NA | NA |  | NA |  | Yellow fever | 38 | 0 |
| HepB3 |  |  | NA | NA | NA | NA | NA |  | HepB seroprevalence (if available) | NA | NA |
| Vit A supplementation |  | Mothers ( < 6 weeks after delivery ) |  |  |  |  |  |  |  |  |  |
|  |  | Infants ( > 6 months) |  |  |  |  |  |  |  |  |  |

The best official estimate: Indicate the best official estimate of coverage among infants as reported in WHO/UNICEF Joint reporting form. Provide explanatory comments on why these are the best estimates: Even though they are based on a low completeness rate (30%) and despite difficulties in obtaining data in the occupied parts of the countries, the estimates made have been extended to the entire country, in the light of previous trends observed between the EAST and the WEST. ………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………

- Summary of health system development status relevant to immunization:

In 1980, the RDC signed the African Charter for Health Development and adopted the strategy of Primary Health Care (PHC) as a basic strategy for reaching the goal of health for all by the year 2000.

Prior to this period, the country's health system was derived from the colonial model, based essentially on the establishment of medical/surgical centers in the chief towns of territories with a host of medical dispensaries.

The health system in the RDC comprises three tiers: central, intermediate (provincial) and peripheral, the latter being the operational level.

With a view to facilitating geographical access to primary health care, in 1985 the country was subdivided into 306 health zones (HZs), the equivalent of health districts in other African countries.  The health zone (peripheral level) serves an average of 100,000 inhabitants in rural areas and 150,000 inhabitants in urban areas.  Each health zone comprises a Central Health Zone Office (CHZO), a General Reference Hospital (GRH) and some 20 Health Centers (HSs).

The country is in the process of being redivided into HZs with a view to improving access to health services and facilitating effective supervision of the health centers.  The Ministry of Health launched this process, which will lead to the redrawing of the country's health map in accordance with the resolutions adopted by the Health General Assemblies held in February 2000.  On the basis of the criteria defined (observation of the limits of the territory or communes, population to be covered, area covered by the HZ and existence of a GRH), the number of Health Zones in the RDC is set to increase from 306 to around 500 by the end of this process.  Immunization activities have been integrated in the health zones since the adoption in 1981 of the strategy of primary health care in the country.

In each province, there is a Provincial Health Inspection Division headed up by the Provincial Medical Inspector.  This division comprises six offices corresponding to the central departments.

The central level may be broken down into the Cabinet of the Minister of Health, the General Secretariat and six health departments.  This level is responsible for providing strategic guidelines and drawing up health policies.  EPI comes under the 4th Health Department, which is responsible for disease control and epidemiological monitoring.

At present, the RDC has some 500 hospitals and 6,000 health groups comprising maternity wards, health centers and dispensaries.

Mention should also be made of the medical structures of private institutions, churches and NGOs which account for more than 50% of the country's health structures.  Nevertheless, hospitals and other health groups, particularly State-run structures, are very run down.

| - Attached are the relevant section(s) of strategies for health system development | Document number……1…….. |
| --- | --- |

# 4.	Profile of the Inter Agency Co-ordinating Committee (ICC)

Various agencies and partners (including NGOs and Research Institutions) that are supporting immunization services are co-ordinated and organised through an inter-agency co-ordinating mechanism which is referred to in this document as ICC.

- Name of the ICC…Inter-Agency Coordinating Committee for Action, Mobilization and Coordination of Health Resources (ICC)

- Date of constitution of the current ICC  13 July 1995…………………………………………………………

- Organisational structure (e.g., sub-committee, stand-alone) Stand-alone body with different sub-committees (EPI, AIDS, Central Bureau for Trypanosomiasis, Emergencies and Disaster Management, Epidemiological Surveillance and Health Information, Essential Drugs and Traditional Medicine, Environment, Malaria, Reproductive Health, etc.)

- Frequency of meetings  Half-yearly (monthly for the Immunization Sub-committee)

- Composition :

| Function | Title / Organization | Name |
| --- | --- | --- |
| Chair | Ministry of Health | Dr. Mashako Mamba |
| Secretary | National EPI Department | Dr. Pierre Kandolo Wenye |
| Members | - WHO - UNICEF - ROTARY - BASICS - USAID …………. | Dr. Leonard Tapsoba Mr. Martin Mongwanja Mr. Ambroise Tshimbalanga Mr. Dan Nelson Mr. Ron Harvey |

Functional relationships between the IICC and other health sector institutions:

Sub-committee BCT

Trypanosomiasis

Sub-committee on Reproductive Health

Sub-committee on Environment

Ministry of Health

ub-

Sub-committee Drugs & Trad. Medicine

Inter-Agency Coordinating Committee

Sub-committee on AIDS

Sub-committee EPI Immunization

Sub-committee

Malaria

- Major functions and responsibilities of the ICC:

- Coordination of action by partners

- Resource mobilization

- Follow-up, continuous monitoring and evaluation of all human, material and financial resources managed

- Three major strategies to enhance ICC’s role and functions in the next 12 months :

- Existence of an annual plan of action

- Opening-up to the other health partners and the other sectors of ministries (Planning, Education and Health)

- Coordinated programme support and financial assistance plan through the memorandum of understanding between the Ministry of Health and partners

- Three main indicators (in addition to DTP3 coverage) that are chosen by the ICC to monitor implementation of this proposal :

- Existence in the government budget of a line item: purchase of vaccines

- Reduction of drop-out rate and vaccine wastage rate

- Dissemination (respect) of injection safety policy

Attached are the supporting documents :

| - Terms of reference of the IICC | Document number…4…. |
| --- | --- |
| - IICCs workplan for next 12 months | Document number…5…. |
| - Minutes of the three most recent IICC meetings or of any other meetings in which partners participated that concerned improving and expanding the national immunization program | Document number…6…. |

# 5.	Immunization services assessment(s)

Reference is made to the most recent assessments of the immunization system that have been completed within the three years prior to the submission of this proposal.

- Assessments, reviews and studies of immunisation services for current reference :

| Title of the assessment | Main participating agencies | Dates |
| --- | --- | --- |
| Joint EPI/DRC Evaluation / Memorandum of Understanding between the Ministry and EPI partners | WHO, UNICEF, BASICS, USAID, ROTARY, EPI, HEALTHMIN | November 2000 |
| Joint EPI/DRC Evaluation / Memorandum of Understanding between the Ministry and EPI partners | WHO, UNICEF, BASICS, USAID, ROTARY, EPI, HEALTHMIN | April 1999 |
| Joint EPI/DRC Evaluation / Memorandum of Understanding between the Ministry and EPI partners | WHO, UNICEF, BASICS, USAID, ROTARY, EPI, HEALTHMIN | February 1998 |
| Fact-finding mission for the relaunching of EP/DRC | WHO, UNICEF, BASICS, USAID, ROTARY, EPI, HEALTHMIN | August 1997 |

- The three major strengths identified in the assessments :

- Available human resources that can be mobilized

- EPI restructuring to improve its functioning

- Positive input from polio eradication efforts

- The three major problems identified in the assessments :

- Insufficient funding for routine activities

- Weak health coverage for country as a whole

- Inadequate cold chain

- The three major recommendations in the assessments :

1.	Lobby donors and partners to secure funding for routine activities

2.	Gradually overhaul the cold chain, vaccine distribution system and other immunization equipment

3.	Push for the establishment of new health centers and the integration of immunization activities into private health structures with a view to facilitating geographical access to health services

- Attached are  complete copies (with an executive summary) of :

| - the most recent assessment reports on the status of immunization services | Document number…7.. |
| --- | --- |
| - a list of the recommendations of the assessment reports with remarks on the status of their implementation i.e. included in work-plan, implemented, not implemented, in progress…. | Document number…8.. |

- Components or areas of immunization services that are yet to be reviewed (or studied).

| ##### Component or area | Month/Year |
| --- | --- |
| Survey on injection safety | 1st half 2002 |
| MICS 2 Survey | For distribution in December 2001 |
| Global EPI Review | For late 2002 |

# 6.	Multi-Year Immunization Plan

Based upon the recommendations of the assessment of immunization services, the Government has developed (or updated) the multi-year immunization plan or adjusted the health sector plan. (Guidelines relating to country proposal No. 4.3) Five-year Plan 2002 - 2006

| - Attached is a complete copy (with an executive summary) of the Multi-Year Immunization Plan or of the relevant pages of the health sector plan. | Document number…9…. |
| --- | --- |

| - Technical support required for implementation of the immunization plan (expert consultants, training curricula, managerial tools…) |  |  |
| --- | --- | --- |
| Type of technical support | Period for the support | Desired from which agency |
| Support training of staff in EPI management | 2002 & 2003 | Dissemination of EPI modules and technical sheets |
| Support for the introduction of new vaccines | 1st half 2002 | Revision of management tools; preparation of message for new vaccines |
| Periodical evaluation of Plan | 2004 & 2006 | Results and activities evaluated; strategies adjusted during Plan to reach goals; impacts evaluated |

| Table 3 : Timetable of vaccinations with traditional and new vaccines, and with Vit A supplementation |  |  |  |  |
| --- | --- | --- | --- | --- |
| Vaccine (do not use trade name) | Ages of administration (by routine immunization services) | Indicate by an “x” if given in : |  | Comments |
|  |  | Entire country | Only part of the country |  |
| Tuberc. (BCG) | Birth | X |  |  |
| OPV | Birth, 6 wks, 10 wks, 14 wks | X |  |  |
| DTP | 6 wks, 10 wks, 14 wks | X |  | Combined with DTP |
| Measles | 9 mos | X |  |  |
| YF | 9 mos | X |  | Given at same time as measles |
| HepB | 6 wks, 10 wks, 14 wks | X |  | Combined with DTP |
| Hib | 6 wks, 10 wks, 14 wks | X |  | Monovalent |
| Vitamin A | Mothers: at birth Children: from 9 mos onwards | X |  | Children's doses renewed every 6 mos |

* Vitamin A supplementation is coordinated by the national nutrition programme (PRONANUT), as EPI represents only one opportunity for reaching a great many children.

- Summary of major action points and timeframe for improving immunization coverage:

| Table 4 : Baseline and annual targets |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of |  | Baseline | Targets |  |  |  |  |  |  |  |
|  |  | 2000 | 2001 | 2002 |  | 2003 | 2004 | 2005 | 2006 | 2007 |
| Births |  | 2441739 | 2507026 | 2576526 |  | 2653701 | 2738232 | 2827357 | 2917131 | 3003434 |
| Infants’ deaths |  | 177739 | 178026 | 160526 |  | 184701 | 190232 | 195357 | 199131 | 200434 |
| Surviving infants |  | 2264000 | 2329000 | 2396000 |  | 2469000 | 2548000 | 2632000 | 2718000 | 2803000 |
| Infants vaccinated with BCG* |  | 1267840 | 1397400 | 2061220 |  | 2255645 | 2282261 | 2544621 | 2625417 | 2853262 |
| Infants vaccinated with OPV3** |  | 928240 | 1048050 | 1317800 |  | 1728300 | 1783600 | 2105600 | 2310300 | 2522700 |
| Infants vaccinated with DTP3** |  | 928240 | 1048050 | 1317800 |  | 1728300 | 1783600 | 2105600 | 2310300 | 2522700 |
| Infants vaccinated with YF |  | NA | NA | 958400 |  | 1604850 | 1783600 | 1974000 | 2174400 | 2382550 |
| Infants vaccinated with HepB |  | NA | NA | NA |  | 1728300 | 1783600 | 2105600 | 2310300 | 2522700 |
| Infants vaccinated with Hib |  | NA | NA | NA |  | 1728300 | 1783600 | 2105600 | 2310300 | 2522700 |
| Infants vaccinated with measles** |  | 1018800 | 1164500 | 958400 |  | 1604850 | 1783600 | 1974000 | 2174400 | 2382550 |
| Pregnant women vaccinated with TT+ |  | 610435 | 752108 | 1288263 |  | 1459536 | 1642939 | 1837782 | 2041991 | 2252576 |
| Vit A supplementation | Mothers (< 6 weeks from delivery) |  |  |  |  |  |  |  |  |  |
|  | Infants (> 6 months) |  |  |  |  |  |  |  |  |  |
| * Target of children out of total births |  |  |  |  | ** Target of children out of surviving infants |  |  |  |  |  |

- Summary of major action points and timeframe for reduction of vaccine wastage. If maximum allowance of wastage rates cannot be achieved immediately, the proposal has to provide a rationale for a higher rate. :

- Improve vaccine storage capacity at all levels

- Purchase vaccine in low-volume vials (e.g. DTP in 10-dose vials)

- Introduce and publicize the policy of open vials

- Improve staff skills and capabilities with regard to vaccine management

| Table 5 : Estimate of annual DTP wastage and drop-out rates |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Actual | Targets |  |  |  |  |  |  |
|  | 2000 | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 |
| DTP wastage rate | 63% | 50% | 40% | 30% | 25% | 20% | 15% | 10% |
| Measles wastage rate | 65 % | 60 % | 50% | 40% | 30% | 20% | 15% | 10% |
| Drop-out rate [ ( DTP1 - DTP3 ) / DTP1 ] x 100 | 16.9% | 16% | 14% | 12% | 10% | 7% | 5% | 5% |

- Countries requesting YF vaccine have to present the same table for measles vaccine wastage rates.

- Planning and constraints for the Polio Eradication Initiative:

- Insecurity linked to the war in the country

- Rumours and resistance (by religious sects and special interest groups)

- Insufficient funding of routine EPI

# 7.	Injection safety

7.1	Summary of the injection safety strategy for immunization (for all countries):

- A national injection safety policy has been worked out.

- AD syringes are being introduced in the capital.

- Phased introduction of AD syringes for all routine EPI injectable vaccines is planned for the second half of 2002.

- Staff are to be trained in injection safety from February 2002 onwards.

- Continuous supervision will be provided to guarantee the proper implementation of the strategy.

| - Attached is a copy of the Plan to achieve Safe Injections (including plans for transition to auto-destruct syringes) and Safe Management of Sharps Waste or of the relevant pages of the health plan. | Document number…10…. |
| --- | --- |

7.2	Injection safety equipment (For countries submitting a request for injection safety support).

The following tables calculate the amount of supplies requested for injection safety:

| Table 6.1: Estimated supplies for safety of vaccination with …… ( Use one table for each vaccine BCG, DTP, TT and measles, and number them from 6.1 to 6.4) |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Formula | 2002 | 2003 | 2004 | 2005 |
| A | Target of children for …… vaccination (for TT target of women) | Match with targets in table 4 |  |  |  |  |
| B | Number of doses per child (for TT woman) | # |  |  |  |  |
| C | Number of …… doses | A x B |  |  |  |  |
| D | AD syringes (+10% wastage) | C x 1.11 |  |  |  |  |
| E | AD syringes buffer stock | D x 0.25 |  |  |  |  |
| F | Total AD syringes | D + E |  |  |  |  |
| G | Number of doses per vial | # |  |  |  |  |
| H | Number of re-constitution syringes (+10% wastage) | C x 1.11 / G |  |  |  |  |
| I | Number of safety boxes (+10% of extra need) | ( F + H ) x 1.11 / 100 |  |  |  |  |

BCG 6.1

|  |  | Formula | 2002 | 2003 | 2004 | 2005 | 2006 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| A | Target of children for BCG vaccination | Match with targets in table 4 | 2061221 | 2255646 | 2382262 | 2544621 | 2625418 |
| B | Number of doses per child | # | 1 | 1 | 1 | 1 | 1 |
| C | Number of BCG doses | A x B | 2061221 | 2255646 | 2382262 | 2544621 | 2625418 |
| D | BCG syringes (+10% wastage) | C x 1.11 | 2287955 | 2503767 | 2644311 | 2824529 | 2914214 |
| E | AD syringes buffer stock | D x 0.25 | 571989 | 0 | 0 | 0 | 0 |
| F | Total BCG syringes | D + E | 2859944 | 2503767 | 2644311 | 2824529 | 2914214 |
| G | Number of doses per vial | # | 20 | 20 | 20 | 20 | 20 |
| H | Number of reconstitution syringes (+10% wastage) | C x 1.11 / G | 114398 | 125188 | 132215 | 141226 | 145711 |
| I | Number of safety boxes (+10% of extra need) | ( F + H ) x 1.11 / 100 | 33015 | 29181 | 30819 | 32919 | 33965 |

6.2 DTP, Hepatitis B (liquid)

|  |  | Formula | 2003 | 2004 | 2005 | 2006 | 2007 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| A | Target of children for DPT, HepB and Hib vaccination | Match with targets in table 4 | 1728300 | 1911000 | 2105600 | 2310300 | 2522700 |
| B | Number of doses per child | # | 3 | 3 | 3 | 3 | 3 |
| C | Number of DPT doses | A x B | 5184900 | 5733000 | 6316800 | 6930900 | 7568100 |
| D | AD syringes (+10% wastage) | C x 1.11 | 5755239 | 6363630 | 7011648 | 7693299 | 8400591 |
| E | AD syringes buffer stock | D x 0.25 | 1438810 | 0 | 0 | 0 | 0 |
| F | Total AD syringes | D + E | 7194049 | 6363630 | 7011648 | 7693299 | 8400591 |
| G | Number of doses per vial | # | 10 | 10 | 10 | 10 | 10 |
| H | Number of reconstitution syringes (+10% wastage) | C x 1.11 / G | 0 | 0 | 0 | 0 | 0 |
| I | Number of safety boxes (+10% of extra need) | ( F + H ) x 1.11 / 100 | 79854 | 70636 | 77829 | 85396 | 93246 |

6.3 Measles

|  |  | Formula | 2002 | 2003 | 2004 | 2005 | 2006 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| A | Target of children for measles vaccination | Match with targets in table 4 | 1198000 | 1604850 | 1783600 | 1974000 | 2174400 |
| B | Number of doses per child | # | 1 | 1 | 1 | 1 | 1 |
| C | Number of measles doses | A x B | 1198000 | 1604850 | 1783600 | 1974000 | 2174400 |
| D | AD syringes (+10% wastage) | C x 1.11 | 1329780 | 1781384 | 1979726 | 2191140 | 2413584 |
| E | AD syringes buffer stock | D x 0.25 | 332445 | 0 | 0 | 0 | 0 |
| F | Total AD syringes | D + E | 1662225 | 1781384 | 1979726 | 2191140 | 2413584 |
| G | Number of doses per vial | # | 10 | 10 | 10 | 10 | 10 |
| H | Number of re-constitution syringes (+10% wastage) | C x 1.11 / G | 147606 | 178138 | 197979 | 219114 | 241358 |
| I | Number of safety boxes (+10% of extra need) | ( F + H ) x 1.11 / 100 | 20089 | 21751 | 24173 | 26754 | 29470 |

6.4 Tetanus

|  |  | Formula | 2002 | 2003 | 2004 | 2005 | 2006 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| A | Target of women for TT vaccination | Match with targets in table 4 | 1288263 | 1459536 | 1642939 | 1837782 | 2041991 |
| B | Number of TT doses per woman | # | 2 | 2 | 2 | 2 | 2 |
| C | Number of TT doses | A x B | 2576526 | 2919072 | 3285878 | 3675564 | 4083982 |
| D | AD syringes (+10% wastage) | C x 1.11 | 2859914 | 3240170 | 3647325 | 4079876 | 4533220 |
| E | AD syringes buffer stock | D x 0.25 | 714986 | 0 | 0 | 0 | 0 |
| F | Total AD syringes | D + E | 3574930 | 3240170 | 3647325 | 4079876 | 4533220 |
| G | Number of doses per vial | # | 20 | 20 | 20 | 20 | 20 |
| H | Number of reconstitution syringes (+10% wastage) | C x 1.11 / G | 0 | 0 | 0 | 0 | 0 |
| I | Number of safety boxes (+10% of extra need) | ( F + H ) x 1.11 / 100 | 39682 | 35966 | 40485 | 45287 | 50319 |

6.5 Hib liquid monovalent 10 doses

|  |  | Formula | 2003 | 2004 | 2005 | 2006 | 2007 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| A | Target of children for Hib vaccination | Match with targets in table 4 | 17283000 | 1911000 | 2105600 | 2310300 | 2522700 |
| B | Number of doses per child | # | 3 | 3 | 3 | 3 | 3 |
| C | Number of Hib doses | A x B | 5184900 | 5733000 | 6316800 | 6930900 | 7568100 |
| D | AD syringes (+10% wastage) | C x 1.11 | 5755239 | 6363630 | 7011648 | 7693299 | 8400591 |
| E | AD syringes buffer stock | D x 0.25 | 1438809 | 0 | 0 | 0 | 0 |
| F | Total AD syringes | D + E | 7194049 | 6363630 | 7011648 | 7693299 | 8400591 |
| G | Number of doses per vial | # | 10 | 10 | 10 | 10 | 10 |
| H | Number of reconstitution syringes (+10% wastage) | C x 1.11 / G | 0 | 0 | 0 | 0 | 0 |
| I | Number of safety boxes (+10% of extra need) | ( F + H ) x 1.11 / 100 | 79854 | 70636 | 77829 | 85396 | 93247 |

6.6 Yellow fever

|  |  | Formula | 2002 | 2003 | 2004 | 2005 | 2006 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| A | Target of children for YF vaccination | Match with targets in table 4 | 1198000 | 1604850 | 1783600 | 1974000 | 2174400 |
| B | Number of doses per child | # | 1 | 1 | 1 | 1 | 1 |
| C | Number of YF doses | A x B | 1198000 | 1604850 | 1783600 | 1974000 | 2174400 |
| D | AD syringes (+10% wastage) | C x 1.11 | 1329780 | 1781384 | 1879796 | 2191140 | 2413584 |
| E | AD syringes buffer stock | D x 0.25 | 332445 | 0 | 0 | 0 | 0 |
| F | Total AD syringes | D + E | 1662225 | 1781384 | 1879796 | 2191140 | 2413584 |
| G | Number of doses per vial | # | 10 | 10 | 10 | 10 | 10 |
| H | Number of reconstitution syringes (+10% wastage) | C x 1.11 / G | 132978 | 197734 | 197980 | 219114 | 241358 |
| I | Number of safety boxes (+10% of extra need) | ( F + H ) x 1.11 / 100 | 19927 | 21968 | 23063 | 26754 | 29470 |

7.3	Areas for injection safety funds (For countries requesting funds equivalent to the supplies calculated above).

List of areas of injection safety funded by different sources: (For the GAVI/Vaccine Fund support, fill in “areas of support”. For AD syringes and waste disposal, fill in “source of funds”.)

| Source of fund | ###### Area of support | Start of fund utilization |
| --- | --- | --- |
| Government | Workshop for elaboration of national injection safety policy | September 2001 |
| GAVI/Vaccine Fund | Purchase of AD syringes and waste disposal boxes | July 2002 |
| GAVI- Government and traditional partners | Purchase /construction of incinerators for destruction of syringes and needles | First quarter of 2002 |
| GAVI- Government and traditional partners | Injection safety training | First quarter of 2002 |
| GAVI- Government and traditional partners | Social mobilization in favour of injection safety | First quarter of 2002 |

(Use as many rows as necessary

# 8.	New and under-used vaccines

- Summary of those aspects of the multi-year immunization plan that refer to the introduction of new and under-used vaccines.

1.	The YF vaccine will be introduced countrywide in 2002.

2.	The HepB vaccine will be introduced in a form combined with DTP (tetravalent) in January 2003.

3.	The Hib vaccine will be introduced in routine EPI in a monovalent form in January 2003.

4.	A detailed plan embracing all activities related to vaccine introduction will be submitted once the country has met the eligibility criteria for the new vaccines.

- Assessment of burden of relevant diseases (if available) :

| Disease | Title of the assessment | Date | Results |
| --- | --- | --- | --- |
| HepB | Study on prevalence of HepB virus among blood donors in Kinshasa | 2000 | 7 to 12% surface antibodies (Australian antigen) |
|  | Study on prevalence of HepA and HepB viruses in the northern part of the RDC | 1985 | 20.7% surface antibodies |
| Hib | NA | NA | NA |

- (if new or under-used vaccines have been already introduced)

Lessons learnt about storage capacity, protection from accidental freezing, staff training, cold chain, logistics, drop-out rate, wastage rate etc. as per current experience with new and under-used vaccines: NA

NA (no new vaccines already introduced)

- Summary of the action points that address possible implications for storage capacity, staff training, cold chain, measures to avoid freezing of vaccines, logistics, drop out rate, wastage rate etc… in the Plan for Introduction of New and Under-used Vaccines :

Storage capacity, cold chain and logistics

-	A cold chain inventory was conducted in 2000

-	Annual updating of inventories planned for the last quarter of 2001

-	Plan for overhaul of cold chain prepared but execution slow due to lack of funds.  Funding is required for the completion of the overhaul in order to accommodate both old and new vaccines prior to the introduction of new vaccines, with a view to ensuring adequate storage capacity.

-	New inventory scheduled for July 2002 in order to evaluate capacity for accommodating the new vaccines requested.

Mesures to prevent vaccines from freezing and reduce vaccine wastage rates and drop-out rates

-	Train staff at all levels in vaccine management.  Training modules have already been prepared and training has been mapped out.

-	Ensure consistent use of temperature sheets

-	Immunize on a daily basis

-	Apply the open vial policy

-	An EPI communication plan (social mobilization) has already been prepared and will be disseminated with a view to promoting communication

-	Ensure regular (training-related) supervision

-	Apply the policy of open vials and ordering low-volume vials if possible (10 doses)

- First preference: required number of doses and presentations of requested new and under-used vaccines. (For each one of the requested first preference of  new and under-used vaccine, please use provided formulas)

DTP-Hep B, (tetravalent, 10-doses vials)

| Year | 2003 | 2004 | 2005 | 2006 | 2007 |
| --- | --- | --- | --- | --- | --- |
| No. doses | 9268009 | 7624890 | 7896000 | 8178462 | 8400591 |

Hib ( monovalent liquid, 10-dose vials)

| Year | 2003 | 2004 | 2005 | 2006 | 2007 |
| --- | --- | --- | --- | --- | --- |
| No. doses | 9268009 | 7624890 | 7896000 | 8178462 | 8400591 |

YF vaccine (monovalent, lyophilized, 10-dose vials)

| Year | 2002 | 2003 | 2004 | 2005 | 2006 |
| --- | --- | --- | --- | --- | --- |
| No. doses | 2995000 | 2680100 | 2532712 | 2467500 | 2565792 |

- Second preference: Required number of doses and presentations of requested new and under-used vaccines, if first preference is not available. (Please use provided formulas as per table 7.1)

Not applicable (NA)

7.1 DTP-HepB (tetravalent, 10-dose vials):

|  |  | Formula | 2003 | 2004 | 2005 | 2006 | 2007 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| A | Number of children to receive new vaccine | match with targets in table 4 | 1329780 | 1781384 | 1879796 | 2191140 | 2413584 |
| B | Number of doses per child | # | 332445 | 0 | 0 | 0 | 0 |
| C | Estimated wastage rate as a % | % | 1662225 | 1781384 | 1879796 | 2191140 | 2413584 |
| D | Equivalent wastage factor | See list in table  | 10 | 10 | 10 | 10 | 10 |
| E | Number of doses | A x B x D | 132978 | 197734 | 197980 | 219114 | 241358 |
| F | Number of vaccines buffer stock | E x 0.25 | 19927 | 21968 | 23063 | 26754 | 29470 |
| G | Total of vaccine doses needed | E + F | 1329780 | 1781384 | 1879796 | 2191140 | 2413584 |
| H | Percentage of vaccines requested from the Vaccine Fund | % | 332445 | 0 | 0 | 0 | 0 |
| I | Number of doses requested from the Vaccine Fund | G x H / 100 | 1662225 | 1781384 | 1879796 | 2191140 | 2413584 |
| J | Number of doses per vial | # | 10 | 10 | 10 | 10 | 10 |
| K | Number of AD syringes (+10% wastage) | [( A x B) + F] x x 1.11 x H / 100 | 7812737 | 6363600 | 7011600 | 7693299 | 8400591 |
| L | Number of AD syringes buffer stock | K x 0.25 | 1953184 | 0 | 0 | 0 | 0 |
| M | Total of AD syringes | K + L | 9765921 | 6363600 | 7011600 | 7693299 | 8400591 |
| N | Number of reconstitution syringes (+10% wastage) | I x 1.11 / J | 0 | 0 | 0 | 0 | 0 |
| ##### O | Number of safety boxes (+10% of extra need) | (M + N) x 1.11 / 100 | 108402 | 70636 | 77829 | 85396 | 93247 |

7.2 Hib

|  |  | Formula | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A | Number of children to receive new vaccine | match with targets in table 4 | 1728300 | 1911000 | 2105600 | 2310300 | 2522700 | 1728300 |
| B | Number of doses per child | # | 3 | 3 | 3 | 3 | 3 | 3 |
| C | Estimated wastage rate as a % | % | 30 | 25 | 20 | 15 | 10 | 30 |
| D | Equivalent wastage factor | See list in table  | 1,43 | 1,33 | 1,25 | 1,18 | 1,11 | 1,43 |
| E | Number of doses | A x B x D | 7414407 | 7624890 | 7896000 | 8178462 | 8400591 | 7414407 |
| F | Number of vaccine buffer stocks | E x 0.25 | 1853602 | 0 | 0 | 0 | 0 | 1853602 |
| G | Total of vaccine doses needed | E + F | 9268009 | 7624890 | 7896000 | 8178462 | 8400591 | 9268009 |
| H | Percentage of vaccines requested from the Vaccine Fund | % | 100 | 100 | 100 | 100 | 100 | 100 |
| I | Number of doses requested from the Vaccine Fund | G x H / 100 | 9268009 | 7624890 | 7896000 | 8178462 | 8400591 | 9268009 |
| J | Number of doses per vial | # | 10 | 10 | 10 | 10 | 10 | 10 |
| K | Number of AD syringes (+10% wastage) | [( A x B) + F] x x 1.11 x H / 100 | 7812737 | 6363600 | 7011600 | 7693299 | 8400591 | 7812737 |
| L | Number of AD syringes buffer stock | K x 0.25 | 1953184 | 0 | 0 | 0 | 0 | 1953184 |
| M | Total of AD syringes | K + L | 9765921 | 6363600 | 7011600 | 7693299 | 8400591 | 9765921 |
| N | Number of reconstitution syringes (+10% wastage) | I x 1.11 / J | 0 | 0 | 0 | 0 | 0 | 0 |
| ##### O | Number of safety boxes (+10% of extra need) | (M + N) x 1.11 / 100 | 108402 | 70636 | 77829 | 85396 | 93247 | 108402 |

7.3 Yellow fever

|  |  | Formula | 2002 | 2003 | 2004 | 2005 | 2006 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| A | Number of children to receive new vaccine | match with targets in table 4 | 1198000 | 1604850 | 1783600 | 1974000 | 2174400 |
| B | Number of doses per child | # | 1 | 1 | 1 | 1 | 1 |
| C | Estimated wastage rate as a % | % | 50 | 40 | 30 | 20 | 15 |
| D | Equivalent wastage factor | See list in table  | 2.0 | 1.67 | 1.42 | 1.25 | 1.18 |
| E | Number of doses | A x B x D | 2396000 | 2680100 | 2532712 | 2467500 | 2565792 |
| F | Number of vaccine buffer stocks | E x 0.25 | 599000 | 0 | 0 | 0 | 0 |
| G | Total of vaccine doses needed | E + F | 2995000 | 2680100 | 2532712 | 2467500 | 2565792 |
| H | Percentage of vaccines requested from the Vaccine Fund | % | 100 | 100 | 100 | 100 | 100 |
| I | Number of doses requested from the Vaccine Fund | G x H / 100 | 2995000 | 2680100 | 2532712 | 2467500 | 2565792 |
| J | Number of doses per vial | # | 10 | 10 | 10 | 10 | 10 |
| K | Number of AD syringes (+10% wastage) | [( A x B) + F] x x 1.11 x H / 100 | 1994670 | 1781384 | 1979776 | 2191140 | 2413584 |
| L | Number of AD syringes buffer stock | K x 0.25 | 498668 | 445346 | 494949 | 547785 | 603396 |
| M | Total of AD syringes | K + L | 2493338 | 2226730 | 2474745 | 2738925 | 3016980 |
| N | Number of reconstitution syringes (+10% wastage) | I x 1.11 / J | 55352 | 49433 | 54939 | 60804 | 66977 |
| ##### O | Number of safety boxes (+10% of extra need) | (M + N) x 1.11 / 100 | 28290 | 25265 | 28079 | 31077 | 34232 |

| - Attached is the plan of action for vaccinations with new or under-used vaccines (if already contained within the national, multi-year plan, indicate pages) | Document number…… |
| --- | --- |

# 9.	Strategic directions to mobilise additional resources for immunization

- Summary of strategies that the Government intends to pursue to increase the resources for immunization of children, and that will be converted in a comprehensive Financial Sustainability Plan by the time of the mid-term review. Highlights of the agreements made with donor agencies (i.a.: Vaccine Independence Initiative) and the use of funds freed by debt relief :

For the time being, the RDC is not among those countries which has benefited from debt relief measures taken by the World Bank and the International Monetary Fund.  The fact that all forms of cooperation were broken off a decade ago, combined with the local war situation, are major obstacles when it comes to developing initiatives for vaccine independence.

However, now that structural cooperation has got back on track on a very modest scale, a major project for the revitalization of the heath sectors in some 60 Health Zones is being run.  This project is vital for the relaunching of immunization activities throughout the country and could be extended to other health zones.

| - Tables of expenditure for 2000 and resource needs detailing the sources of funds for 2000 and subsequent years are attached in Annex 1. | Document number .…. |
| --- | --- |

- Remarks on recurrent cost reduction strategies which contribute to financial sustainability, such as vaccine wastage reduction:

- The programme aims to focus on the training and retraining of immunization staff with a view to improving the management of vaccines and other materials over the next five years.

- The open vial policy will be applied to reduce vaccine wastage.

- Follow-up and regular training supervision of health centers will make it possible to maintain performances and the new practices acquired during training.

# 10.	Summary of requests to GAVI and the Vaccine Fund

With reference to all points presented above, the Government of The Democratic Republic of Congo (RDC),

considering that its DTP3 coverage for 2000 was …39%……%  corresponding to …928,240…… children vaccinated with DTP3, requests the Alliance and its partners to contribute financial and technical assistance required to increase immunization of children.

Specifically, the Government hereby applies for the following types of support from GAVI and the Vaccine Fund. (Circle “YES” or “NO” according to the requests submitted with this proposal):

- Support for Immunization Services                       		  YES

- Support for New and Under-used vaccines                                  YES

- Support for Injection Safety                                                          YES

10.1	SUPPORT FOR IMMUNIZATION SERVICES

GAVI and the Vaccine Fund are requested to fund the strategies for strengthening immunization services in year 2002 according to the number of additional children (as compared to the baseline) that are targeted to be immunized with DTP3 as presented in table 4, namely 389,560………… (number of children). Funds will also be requested for following years as estimated in table 4.

- The Government takes full responsibility to manage the in-country transfer of funds.

(In case an alternative mechanism is necessary please describe it and the reasons for it)  YES

- Operational mechanism that is followed for safeguarding transparency, standards of accounting, long-term sustainability and empowerment of the government in using the funds:

See Annex 11 of the accompanying documents

- Countries requesting immunization services support should submit the “Banking Details” form (Annex 3) with their proposal

10.2	SUPPORT FOR NEW AND UNDER-USED VACCINES

GAVI and the Vaccine Fund are requested to fund the introduction of New and Under-used Vaccines by providing the following vaccines: (fill in only what is being requested from the Vaccine Fund in line with tables 7.1, 7.2…)

| Table 9 : New and under-used vaccines requested from GAVI and the Vaccine Fund |  |  |  |  |
| --- | --- | --- | --- | --- |
| Vaccine presentation | Number of doses per vial | Starting month and year | Number of doses requested for first calendar year | Number of doses requested for second calendar year * |
| ### DTP-HepB | 10 | January 2003 | 9268009 | 7624890 |
| Hib | 10 | January 2003 | 9268009 | 7624890 |
| Yellow fever | 10 | July 2002 | 2995000 | 2680100 |
| * Vaccines will also be requested for following years as described in tables 7.1, 7.2… |  |  |  |  |

- Vaccines will be procured (tick only one) :

By UNICEF       x  x                                     By GOVERNMENT

- (If vaccines are proposed to be procured by the Government) 	Process and procedures of the National Regulatory Authority to control the purchase and delivery of vaccines into the country, including weaknesses, constraints and planned measures to improve the control system:

- (In case you are entitled to receive US$ 100,000 to facilitate the introduction of new vaccines) Please submit the attached “Banking Details” form (Annex 3) with the proposal.

10.3	SUPPORT FOR INJECTION SAFETY

GAVI and the Vaccine Fund are requested to support the injection safety plan by providing:

(Tick one choice only):		The amount of supplies listed in table 8

The equivalent amount of funds

| Table 8: Summary of total supplies for safety of vaccinations with BCG, DTP, TT and MEASLES requested from GAVI and the Vaccine Fund (fill in the total sums of rows “F”, “H” and “I” of tables 6.1,6.2, 6.3, 6.4. |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | ITEM |  | 2002 | 2003 | 2004 | 2005 |
| F | Total AD syringes | for BCG | 2859944 | 2503767 | 2644311 | 2824529 |
|  |  | for other vaccines | 6899380 | 21191036 | 20234107 | 22485452 |
| H | Total of reconstitution syringes |  | 380351 | 169124 | 178341 | 194734 |
| I | Total of safety boxes |  | 272421 | 243138 | 274307 | 302506 |

- (In case you request funds equivalent to the above supplies at the prices obtained by UNICEF) Please submit the attached “Banking Details” form (Annex 3) with the proposal.

# 11.	Additional comments and recommendations from the IICC

The ICC welcomed the finalization of this proposal and hastened to sign it.  The body feels that GAVI's resources are considerable, specifically in the present context of the country, in helping to evitalize EPI activities.

The ICC feels that the cold chain absolutely must be overhauled prior to the introduction of new vaccines in order to guarantee storage capacity.  Mobilizing the community and building awareness will therefore be crucial in this connection.

ANNEX 1

#### STATEMENT OF FUNDING AND OF UNMET IMMUNIZATION NEEDS

#### (USD 000s)

Table 1: EXPENDITURE IN 2000 FROM DIFFERENT SOURCES

# I.1. ROUTINE EPI

| Ref. | Category / line item | Central Govern- ment | Private sector | Donor ## UNICEF | Donor WHO | Donor BASICS | Donor | Donor n..² | Total expend- iture in 2000 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | Vaccines, AD syringes |  |  |  |  |  |  |  |  |
| 1.1. | Vaccines |  |  | 509,420 |  |  |  |  | 509,420 |
| 2. | Equipment (cold chain, spare parts, sterilization…) |  |  |  |  |  |  |  |  |
| 2.1. | Cold chain equipment |  |  | 215,410 |  |  |  |  | 215,410 |
| 3. | Other immuniz. items |  |  |  |  |  |  |  |  |
| 3.1. | Prog. development (EPI Consensus-building and Policy Adoption Workshop) |  |  |  |  | X |  |  | 16,049 |
| 3.2. | Microplan. & training |  |  | 132,805 |  |  |  |  | 132,805 |
| 3.3. | Distribution vaccines & equipment |  |  | 97,808 |  |  |  |  | 97,808 |
| 3.4. | Acquisition motos Transport & fuel/gas Computers |  |  | 100,514 |  |  |  |  | 100,514 |
| 3.5. | Purchase rolling stock |  |  | 244,913 |  |  |  |  | 244,913 |
| 3.6. | Communication Maintenance C.C. Acquisition vehicles |  |  | 81,704 |  |  |  |  | 81,704 |
| 3.7. | Supervision |  |  | 41,877 |  |  |  |  | 41,877 |
| 3.8. | Preparation EPI modules |  |  |  |  | X |  |  | 2,245 |
| 3.9. | Incentives Contribution to EPI functioning/diesel fuel and gas |  |  | 9,720 |  |  |  |  | 9720 |
| 3.10 | Nat'l coordination |  |  |  |  |  |  |  |  |
| 3.11 | Customs clearance |  |  | 36,360 |  |  |  |  | 36,360 |
| 3.12 | Annual EPI review and in provinces |  |  | 19,995 |  | X |  |  | 25,560 |
| 3.13 | Social mobilization |  |  | 93 |  |  |  |  | 93 |
| 3.14 | Reinforcement of structures and capabilities of EPI staff |  |  |  |  | X |  |  | 22,936 |
| 3.15 | Reproduction of PHC sheets |  |  | 1,227 |  |  |  |  | 1,227 |
| 3.16 | Communication & office supplies |  |  |  |  |  |  |  |  |
| 3.17 | Staff meals |  |  |  |  |  |  |  |  |
| 3.18 | Follow-up & evaluation |  |  |  |  |  |  |  |  |
| 3.19 | Additional costs |  |  |  |  |  |  |  |  |
|  | ## TOTAL |  |  | 1,491846 |  | 146,795 |  |  | 1,638,641 |

# I.2. NIDs

| Ref. | Category / line item | Central Govern-ment | Priv-ate sec-tor | Donor ## UNICEF | Donor WHO | Donor BASICS | Donor ## ROTARY | Donor n..² | Total expenditure in 2000 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | Vaccines, AD syringes |  |  |  |  |  |  |  |  |
| 1.1. | Vaccines |  |  | 4,526,586 |  |  |  |  | 4,526,586 |
| 1.2. | Vitamin A / West & East |  |  |  | 100,000 |  |  |  | 100,000 |
| 1.3. | Needles BCG/Vitamin A |  |  | 15,240 |  |  |  |  | 15,240 |
| 2. | Equipment (cold chain, spare parts, sterilization…) |  |  |  |  |  |  |  |  |
| 2.1. | Purchase vaccine racks |  |  | 208,200 |  |  |  |  | 208,200 |
| 2.2. | Purchase innoculation equipment |  |  | 482,090 |  |  |  |  | 482,090 |
| 2.3. | Cold chain equipment |  |  |  | 596,000 |  |  |  | 596,000 |
| 3. | Other immuniz. items |  |  |  |  |  |  |  |  |
| 3.1. | Staff meals | 129,954 |  | 2,111,587 | 2,816,100 |  |  |  | 5,057,641 |
| 3.2. | Microplan. & training |  |  | 475,155 |  |  |  |  | 475,155 |
| 3.3. | Distribution vaccines & equipment |  |  | 1,287,889 | 251,212 |  |  |  | 1,539,101 |
| 3.4. | Follow-up & evaluation |  |  | 83,948 | 100,000 |  |  |  | 183,948 |
| 3.5. | Social mobilization | 29,615 |  | 878,536 | 195,4603 |  | 11.932 |  | 1,115,543 |
| 3.6. | Supervision | 26,391 |  | 335,544 | 76,346 |  |  |  | 438,281 |
| 3.7. | Additional costs |  |  | 60,773 |  |  |  |  | 60,773 |
| 3.8. | National coordination |  |  |  | 16,948 |  |  |  | 16,948 |
| 3.9. | Incentives |  |  |  | 9,880 |  |  |  | 9,880 |
| 3.10 | Transport & fuel | 832,336 |  |  | 865,400 |  | 27,660 |  | 1,725,396 |
| 3.11 | Computers |  |  |  | 17,436 |  |  |  | 17,436 |
| 3.12 | Communication |  |  |  | 21,500 |  |  |  | 21,500 |
| 3.13 | Acquisition vehicles |  |  |  |  |  |  |  |  |
| 3.14 | Acquisition motos |  |  |  |  |  |  |  |  |
| 3.15 | Technical assistance |  |  |  | 400,000 |  |  |  | 400,000 |
| 3.16 | Office supplies & equipment | 13,619 |  |  | 22 ;177 |  |  |  | 35,796 |
|  | Local contribution | 64,675 |  |  |  |  |  |  | 64,675 |
|  | ## TOTAL | 1.096,590 |  | 10,465,548 | 5,488,459 |  | 39,592 |  | 17,090,189 |

# I.3. AFP

| Ref. | Category / line item | Central govern-ment | Priv-ate sec-tor | Donor ## UNICEF | Donor WHO | Donor BASICS | Donor ## ROTARY | Donor n..² | Total expenditure in 2000 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | Vaccines, AD syringes |  |  |  |  |  |  |  |  |
| 1.1. | Vaccines |  |  |  |  |  |  |  |  |
| 1.2. | Vitamin A / West & East |  |  |  |  |  |  |  |  |
| 1.3. | Needles BCG/Vitamin A |  |  |  |  |  |  |  |  |
| 2. | Equipment (cold chain, spare parts, sterilization…) |  |  |  |  |  |  |  |  |
| 2.1. | Purchase vaccine racks |  |  |  |  |  |  |  |  |
| 2.2. | Purchase inoculation equipment |  |  |  |  |  |  |  |  |
| 2.3. | Cold chain equipment |  |  |  |  |  |  |  |  |
| 3. | Other immuniz. items |  |  |  |  |  |  |  |  |
| 3.1. | Functioning of Logistics Team (central & provincial) |  |  |  | 303,319 |  |  |  | 303,319 |
| 3.2. | Acquisition vehicles |  |  |  | 281,258 |  |  |  | 281,258 |
| 3.3. | Acquisition motos |  |  |  | 186,650 |  |  |  | 186,650 |
| 3.4. | Purchase of Codan |  |  |  |  |  |  |  |  |
| 3.5. | Laboratory |  |  |  | 69,001 |  |  |  | 69,001 |
| 3.6. | RFH contract |  |  |  | 487,906 |  |  |  | 487,906 |
|  | ## TOTAL |  |  |  | 1,328,134 |  |  |  | 1,328,134 |

# TABLE 2 : BUDGET FOR 2000

#### 2.1.- NIDs

| ### Budget for 2000 |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. | Category / line item | Central govern-ment | Private sector | Donor ## UNICEF | Donor WHO | Donor BASICS | Donor ## ROTARY | Donor n..² | Total budget 2000 |
| 1. | Vaccines, AD syringes |  |  |  |  |  |  |  |  |
| 1.1. | Vaccines |  |  | 3,821,097 |  |  |  |  | 3,821,097 |
| 1.2. | Vitamin A / West & East |  |  | 290,957 |  |  |  |  | 290,957 |
| 1.3. | Needles BCG/Vitamin A |  |  |  |  |  |  |  |  |
| 1.4. | AD syringes |  |  | 569,034 |  |  |  |  | 569,034 |
| 1.5. | Hypo syringes |  |  | 8,430 |  |  |  |  | 8,430 |
| 2. | Equipment (cold chain, spare parts, sterilization…) |  |  |  |  |  |  |  |  |
| 2.1. | Purchase vaccine racks |  |  |  |  |  |  |  |  |
| 2.2. | Purchase inoculation equipment |  |  |  |  |  |  |  |  |
| 2.3. | Cold chain equipment |  |  |  | 596,000 |  |  |  | 596,000 |
| 3. | Other immuniz. items |  |  |  |  |  |  |  |  |
| 3.1. | Boxes & miscellaneous |  |  | 54,329 |  |  |  |  | 54,329 |
| 3.2. | Staff meals | 750,000 |  | 1,127,000 | 2,816,100 |  | 82,000 |  | 4,775,100 |
| 3.3. | Microplan. & training |  |  | 500,000 |  |  |  |  | 500,000 |
| 3.4. | Distribution vaccines & equipment |  |  | 482,500 | 251,219 |  |  |  | 733,719 |
| 3.5. | Follow-up & evaluation | 50,000 |  | 295,600 | 100,000 |  |  |  | 445,600 |
| 3.6. | Social mobilization | 48,400 |  | 754,400 | 195,460 |  | 46,000 |  | 1,044,260 |
| 3.7. | Supervision |  |  |  |  |  |  |  |  |
| 3.8. | Additional costs |  |  | 200,000 | 199,104 |  | 532,000 |  | 931,104 |
| 3.9. | National coordination |  |  |  | 54,540 |  |  |  | 54,540 |
| 3.10. | Incentives |  |  |  |  |  |  |  |  |
| 3.11 | Transport & fuel | 3,332,356 |  |  | 865,400 |  | 46,000 |  | 4,243,756 |
| 3.12 | Computers |  |  |  |  |  |  |  |  |
| 3.13 | Communication |  |  |  |  |  |  |  |  |
| 3.14 | Acquisition vehicles |  |  |  |  |  |  |  |  |
| 3.15 | Acquisition motos |  |  |  |  |  |  |  |  |
| 3.16 | Office equipment & supplies |  |  |  |  |  |  |  |  |
| 3.17 | Local contribution |  |  |  |  |  |  |  |  |
|  | ## TOTAL | 4,180,756 |  | 8,103,347 | 5,077,823 |  | 706,000 |  | 18,067,926 |

# 2.2.  ROUTINE EPI

| ### Budget for 2000 |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. | Category / line item | Central government | Secteur Privé | Donor ## UNICEF | Donor OMS | Donor BASICS | Donor ## ROTARY | Donor n..² | Total budget 2000 |
| 1. | Vaccines, AD syringes |  |  |  |  |  |  |  |  |
| 1.1. | Vaccines |  |  | 1,086,263 |  |  |  |  | 1,086,263 |
| 1.2. | Vitamin A |  |  | 82,318 |  |  |  |  | 82,318 |
| 1.3. | Needles BCG/Vitamin A |  |  |  |  |  |  |  |  |
| 1.4. | AD syringes |  |  | 2,518,354 |  |  |  |  | 2,518,354 |
| 1.5. | Measles dilution syringes |  |  |  |  |  |  |  |  |
| 2. | Equipment (cold chain, spare parts, sterilization…) |  |  |  |  |  |  |  |  |
| 2.1. | Purchase vaccine racks |  |  |  |  |  |  |  |  |
| 2.2. | Purchase inoculation equipment |  |  |  |  |  |  |  |  |
| 2.3. | Cold chain equipment |  |  | 745,843 |  |  |  |  | 745,843 |
| 3. | Other immuniz. items |  |  |  |  |  |  |  |  |
| 3.1. | Boxes and miscellaneous |  |  |  |  |  |  |  |  |
|  | Support staff |  |  |  |  |  |  |  |  |
| 3.2. | Immunization site staff |  |  |  |  |  |  |  |  |
| 3.3. | Microplan. & training |  |  | 434,900 |  |  |  |  | 434,900 |
| 3.4. | Distribution vaccines & equipment |  |  | - |  |  |  |  | - |
| 3.5. | Follow-up & evaluation |  |  | 356,500 |  |  |  |  | 356,500 |
| 3.6. | Social mobilization |  |  | 367,040 |  |  |  |  | 367,040 |
| 3.7. | Supervision |  |  |  |  |  |  |  |  |
| 3.8. | Reproduction of PHC sheets |  |  |  |  |  |  |  |  |
| 3.9. | National coordination |  |  | - |  |  |  |  | - |
| 3.10. | Operational research |  |  | 27,000 |  |  |  |  | 27,000 |
| 3.11. | Printed material and miscellaneous |  |  | 24,796 |  |  |  |  | 24,796 |
| 3.12. | Staff motivation |  |  | 350,040 |  |  |  |  | 350,040 |
| 3.13. | Transport & fuel/gas |  |  | 250,000 |  |  |  |  | 250,000 |
| 3.14. | EPI annual review in provinces |  |  |  |  |  |  |  |  |
| 3.15. | Operational costs (customs clearance) |  |  |  |  |  |  |  |  |
| 3.16. | Purchase rolling stock |  |  | 568,000 |  |  |  |  | 568,000 |
|  | Maintenance rolling stock |  |  | 281,150 |  |  |  |  | 281,150 |
| 3.17. | Maintenance cold chain |  |  | 142,688 |  |  |  |  | 142,688 |
| 3.18. | Follow-up mission on social mobilization activities |  |  |  |  |  |  |  |  |
| 3.19. | Strengthening of structures and capabilities of EPI-CCCD staff |  |  |  |  |  |  |  |  |
| 3.20. | Production of advertising spots |  |  |  |  |  |  |  |  |
| 3.21. | Functioning of rolling stock |  |  | 789,568 |  |  |  |  | 789,568 |
| 3.22. | Prog. development/EPI Consensus-building and Policy Adoption Workshop |  |  |  |  | 73,500 |  |  | 73,500 |
| 3.23. | Preparation and production of EPI modules |  |  |  |  |  |  |  |  |
| 3.24 | Contribution to EPI functioning Diesel fuel and gas |  |  |  |  |  |  |  |  |
|  | ## TOTAL |  |  |  |  |  |  |  | 8,097,960 |

# 2.3. AFP

| ### Budget for 2000 |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. | Category / line item | Central govern-ment | Private sector | Donor ## UNICEF | Donor OMS | Donor BASICS | Donor ## ROTARY | Donor n..² | Total budget 2000 |
| 1. | Vaccines, AD syringes |  |  |  |  |  |  |  |  |
| 2. | Equipment (cold chain, spare parts, sterilization…) |  |  |  |  |  |  |  |  |
| 3. | Other immuniz. items |  |  |  |  |  |  |  |  |
| 3.1. | Social mobilization |  |  |  | 62,720 |  |  |  | 62,720 |
| 3.2. | Staff motivation |  |  |  | 618,300 |  |  |  | 618,300 |
| 3.3. | Supervision of activities |  |  |  | 230,400 |  |  |  | 230,400 |
| 3.4. | Strengthening of structures and capabilities of EPI-CCCD |  |  |  | 524,140 |  |  |  | 524,140 |
| 3.5. | Awareness-building among clinicians |  |  |  | 314,440 |  |  |  | 314,440 |
| 3.6. | Other support activities Surveillance |  |  |  | 42,400 |  |  |  | 42,400 |
|  | ## TOTAL |  |  |  |  |  |  |  | 1,792,400 |

ANNEX  2

Summary of documentation

| Background information on Health System Development status |  |
| --- | --- |
| - Attached are the relevant section(s) of strategies for health system development | Document number…1…. |
| Profile of the Inter Agency Co-ordinating Committee (ICC) |  |
| - ICC’s workplan of next 12 months | Document number…4. |
| - Terms of reference of the ICC | Document number…5 |
| - Minutes of the three most recent ICC meetings or any meetings concerning the introduction of new or under-used vaccines or safety of injections | Document number 6 |
| Immunization Services Assessment |  |
| - Most recent, national assessment report(s) on the status of immunization services | Document number…7 |
| - Summary of the recommendations of the assessment report(s) with remarks on the status of implementation of each recommendation. | Document number…8 |
| Multi-Year Immunization Plan |  |
| - Complete copy (with executive summary) of the Multi-Year Immunization Plan or of the relevant pages of the health sector plan. | Document number…9 |
| - Action plan for the introduction of new or under-used vaccines into immunization services (if already contained within the national, multi-year plan, please indicate page and paragraphs) - A copy of the Plan to achieve safe injections (including plans for transition to auto-destruct syringes) and safe management of Sharp Wastes or of the relevant pages of the health plan. | Document number…… p. 30 of Five-year Plan Document number…10 |
| Unmet needs requiring additional resources |  |
| - Tables of expenditure for 2000 and resource needs (Annex 1) | Document number Annex I, GAVI Form… |

ANNEX  3

| GLOBAL ALLIANCE FOR VACCINES AND IMMUNIZATION |  |  |  |  |  | ##### Banking Details |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SECTION 1 (To be completed by payee) |  |  |  |  |  |  |  |  |  |  |
| In accordance with the decision on support to immunization services made by the Global Alliance for Vaccines and Immunization and the Vaccine Fund dated . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . , the Government of The Democratic Republic of Congo, hereby requests that a payment be made, via electronic bank transfer, as detailed below : |  |  |  |  |  |  |  |  |  |  |
| #### Name of Institution : (Account Holder) |  | Expanded Programme of Immunization and Control of Communicable Childhood Diseases (EPI-CCCD) |  |  |  |  |  |  |  |  |
| #### Address : |  |  |  |  |  |  |  |  |  |  |
|  |  | 2, Avenue de la Justice |  |  |  |  |  |  |  |  |
| #### City – Country : |  | Kinshasa-Gombe (Democratic Republic of Congo) |  |  |  |  |  |  |  |  |
| Telephone No. : |  |  |  | Fax No. : |  |  |  |  |  |  |
| #### Amount in USD : |  | ( To be filled in by GAVI Secretariat ) |  |  | Currency of the bank account : |  |  |  |  |  |
| For credit to : Bank account’s title |  | EPI-CCCD (Expanded Programme of Immunization and Control of Transmissible Childhood Diseases) |  |  |  |  |  |  |  |  |
| Bank account No. : |  | RME N° 201-0013093-02-43 |  |  |  |  |  |  |  |  |
| At : Bank’s name |  | UNION DES BANQUES CONGOLAISES |  |  |  |  |  |  |  |  |
| #### Is the bank account exclusively to be used by this programme? |  |  |  |  |  |  | YES ( X ) NO ( ) |  |  |  |
| #### By whom is the account audited ? |  |  |  |  |  |  | Medical Director for EPI-CCCD |  |  |  |
| # Signature of Government’s authorizing official : |  |  |  |  |  |  |  |  |  |  |
| #### Name : | Dr. MASHAKO MAMBA N.L. |  |  |  |  |  |  |  | Seal : |  |
| #### Title : | Minister of Health |  |  |  |  |  |  |  |  |  |
| #### Signature : |  |  |  |  |  |  |  |  |  |  |
| Date : |  |  |  |  |  |  |  |  |  |  |

| SECTION 2 ( To be completed by the Bank ) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| # FINANCIAL INSTITUTION |  |  |  | CORRESPONDENT BANK (In the United States) |  |
| Bank Name : |  | UNION DES BANQUES CONGOLAISES |  | BANQUE BRUXELLES LAMBERT (BBL) |  |
| Branch Name : |  | NATIONS-UNIES |  |  |  |
| Address : |  | BUILDING ROYAL |  |  |  |
| City – Country : |  | KINSHASA – RDC |  |  |  |
| Swift code : |  |  |  |  |  |
| Sort code : |  | ubc(afrinet.cd |  |  |  |
| ABA No. : |  |  |  |  |  |
| Telephone No : |  | 44301 or 41333 |  |  |  |
| Fax No : |  | 243 88 466 28 |  |  |  |
| I certify that the account No. 201-00-13093-02-43 . is held by EPI-CCCD at this banking institution. |  |  |  |  |  |
| The account is to be signed jointly by at least …3 (number of signatories) of the following authorized signatories : |  |  | Name of bank’s authorizing official : Mr. KISSY MUBIKWA |  |  |
| 1 Name : Title : | KANDOLO WENYE |  | Signature : |  |  |
|  | MEDICAL DIRECTOR |  | Date: |  | 28/09/2001 |
| 2 Name : Title : | Mrs. KAWENDE FATUMA |  | Seal: |  |  |
|  | HEAD, ADMINISTRATIVE AND FINANCIAL DEPT. |  |  |  |  |
| 3 Name : Title : | Mr. MPUNDU GERMAIN |  |  |  |  |
|  | FINANCIAL ADVISOR TO THE MINISTER OF HEALTH |  |  |  |  |
| 4 Name : Title : | LEONARD TAPSOBA |  |  |  |  |
|  | WHO REPRESENTATIVE |  |  |  |  |

COVERING LETTER

(To be completed by UNICEF representative on letter-headed paper)

### TO:    GAVI – Secretariat

### Att. Dr Tore Godal

### Executive Secretary

C/o UNICEF

Palais des Nations

CH 1211 Geneva 10

Switzerland

| On the ……………………………… I received the original of the BANKING DETAILS form, which is attached. I certify that the form does bear the signatures of the following officials : |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | Name |  |  | Title |
| Government’s authorizing official |  | Dr. MASHAKO MAMBA |  |  | Minister of Health |
| Bank’s authorizing official |  | Mr. KISSY MUBIKWA |  |  | Account Officer |
| Signature of UNICEF Representative : |  |  |  |  |  |
| Name | Martin MONGWANJA |  |  |  |  |
| Signature |  |  |  |  |  |
| Date |  |  |  |  |  |

Formula to calculate DTP vaccine wastage rate (in percentage): [ ( A – B ) / A ] x 100.   Whereby : A = The number of DTP doses distributed for use according to the supply  records with correction for stock balance at start and end of the supply period; B =  the number of DTP vaccinations.

Formula to calculate DTP vaccine wastage rate (in percentage): [ ( A – B ) / A ] x 100.   Whereby : A = The number of DTP doses distributed for use according to the supply  records with correction for stock balance at start and end of the supply period; B =  the number of DTP vaccinations.

The buffer stock for vaccines and AD syringes is set at 25%. This is calculated with the first stock of doses required to introduce the vaccination in any given geographic area. Write zero for other years.

Only for lyophilized vaccines. Write zero for other vaccines

The buffer stock for vaccines and AD syringes is set at 25%. This is calculated with the first stock of doses required to introduce the vaccination in any given geographic area. Write zero for other years.

Only for lyophilized vaccines. Write zero for other vaccines

The buffer stock for vaccines and AD syringes is set at 25%. This is calculated with the first stock of doses required to introduce the vaccination in any given geographic area. Write zero for other years.

Only for lyophilized vaccines. Write zero for other vaccines

The buffer stock for vaccines and AD syringes is set at 25%. This is calculated with the first stock of doses required to introduce the vaccination in any given geographic area. Write zero for other years.

Only for lyophilized vaccines. Write zero for other vaccines

The buffer stock for vaccines and AD syringes is set at 25%. This is calculated with the first stock of doses required to introduce the vaccination in any given geographic area. Write zero for other years.

Only for lyophilized vaccines. Write zero for other vaccines

The buffer stock for vaccines and AD syringes is set at 25%. This is calculated with the first stock of doses required to introduce the vaccination in any given geographic area. Write zero for other years.

Only for lyophilized vaccines. Write zero for other vaccines

The buffer stock for vaccines and AD syringes is set at 25%. This is calculated with the first stock of doses required to introduce the vaccination in any given geographic area. Write zero for other years.

Only for lyophilized vaccines. Write zero for other vaccines

Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3 an explanation of the difference should be provided.

The country should aim for a maximum wastage rate of 25% for the first year with a plan to gradually reduce it to 15% by the third year. For vaccine in single or two-dose vials the maximum wastage allowance is 5%. No maximum limits have been set for yellow fever vaccine in multi-dose vials.

The buffer stock for vaccines and AD syringes is set at 25%. This is calculated with the first stock of doses required to introduce the vaccination in any given geographic area. Write zero for other years.

A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Vaccine Fund, excluding the wastage of vaccines.

Only for lyophilized. Write zero for other vaccines.

A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes

Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3 an explanation of the difference should be provided.

The country should aim for a maximum wastage rate of 25% for the first year with a plan to gradually reduce it to 15% by the third year. For vaccine in single or two-dose vials the maximum wastage allowance is 5%. No maximum limits have been set for yellow fever vaccine in multi-dose vials.

The buffer stock for vaccines and AD syringes is set at 25%. This is calculated with the first stock of doses required to introduce the vaccination in any given geographic area. Write zero for other years.

A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Vaccine Fund, excluding the wastage of vaccines.

Only for lyophilized. Write zero for other vaccines.

A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes

Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3 an explanation of the difference should be provided.

The country should aim for a maximum wastage rate of 25% for the first year with a plan to gradually reduce it to 15% by the third year. For vaccine in single or two-dose vials the maximum wastage allowance is 5%. No maximum limits have been set for yellow fever vaccine in multi-dose vials.

The buffer stock for vaccines and AD syringes is set at 25%. This is calculated with the first stock of doses required to introduce the vaccination in any given geographic area. Write zero for other years.

A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Vaccine Fund, excluding the wastage of vaccines.

Only for lyophilized. Write zero for other vaccines.

A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes

Please submit hard copy documents with an identical electronic copy whenever possible