Global Alliance for Vaccines and Immunization (GAVI)

APPLICATION FORM FOR COUNTRY PROPOSALS

For Support to:

Immunization Services,

Health System Strengthening

and Injection Safety

18 May 2006

This document is accompanied by an electronic copy on CD for your convenience. Please return a copy of the CD with the original, signed hard-copy of the document to:

GAVI Secretariat; c/o UNICEF, Palais des Nations, 1211 Geneva 10, Switzerland.

Enquiries to: Dr Julian Lob-Levyt, jloblevyt@unicef.org or representatives of a GAVI partner agency.  All documents and attachments must be in English or French.

## CONTENTS

| SECTION |  | SUPPORT | PAGE |
| --- | --- | --- | --- |
| 1. | Executive Summary | ALL | 2 |
| 2. | Signatures of the Government and National Coordinating Bodies |  |  |
|  | - Government and the Health Sector Strategy Committee | HSS | 3 |
|  | - Government and the Inter-Agency Coordinating Committee for Immunization (ICC) | ALL | 4 |
|  | - The Inter-Agency Coordinating Committee for Immunization (ICC) | ALL | 5 |
| 3. | Immunization Programme Data | ALL | 6 |
|  | - Immunization Fact Sheet |  | 6 |
|  | - Comprehensive Multi-Year Immunization Plan |  | 7 |
| 4. | Immunization Services Support (ISS) | ISS | 11 |
| 5. | Health Systems Strengthening Support (HSS) | HSS | 12 |
|  | - Proposed GAVI Health Systems Strengthening Support |  | 14 |
|  | - HSS Financial Analysis and Planning |  | 16 |
|  | - Management and Accountability of GAVI HSS Funds |  | 17 |
|  | - Involvement of Partners in GAVI HSS Implementation |  | 18 |
| 6. | Injection Safety Support (INS) | INS | 19 |
| 7. | Additional comments and recommendations from the National Coordinating Body (Health Sector Strategic Committee / ICC) | ALL | 20 |
| 8. | Documents required for each type of support | ALL | 21 |
| Annex 1 – Banking Form |  | ISS | 22 |

## Executive Summary

Executive summary of the application for ISS

Niger submitted an application for Immunization Services Support to GAVI as part of the implementation of its multi-year EPI plan for 2002-2006. That application was accepted in 2002, and Niger was granted US$ 1,740,000, plus US$ 4,561,080 for additional children vaccinated with DTP3, US$ 1,442,010 of which has already been received. In 2003 Niger also applied for, and was granted, Injection Safety Support for three years (2004 to 2006), in the form of AD syringes, reconstitution syringes and safety boxes. Thanks to these different forms of support, and that of its other partners, Niger has been able significantly to improve its immunization coverage for systematic EPI. For example, DTP3 coverage rose from 22% in 2002 to 89% in 2005.

This application is based on the main activities identified in the 2007-2010 comprehensive multi-year plan (cMYP) to further increase immunization coverage nationwide to 90% per antigen under the Global Immunization and Vision Strategy (GIVS). The aim is to help lower the morbidity and mortality rates for vaccine-preventable diseases.

In addition, this support will help strengthen the coordination of EPI activities at all levels of the health system. EPI logistics will be given a facelift, and vaccines will be better managed than ever.

Under this application, GAVI is called on to mobilize US$ 251,500 in 2007, US$ 102,820 in 2008, US$ 593,800 in 2009, and US$ 376,300 in 2010.

## Signatures of the Government and National Coordinating Bodies

## Government and the Health Sector Strategy Committee (for HSS only)

The Government of the Republic of Niger commits itself to developing national immunization services on a sustainable basis in accordance with the multi-year plan presented with this document.

Districts’ performance on immunization will be reviewed annually through a transparent monitoring system. The Government requests that the Alliance and its partners contribute financial and technical assistance to support immunization of children as outlined in this application.

| Ministry of Health: | Ministry of Finance: |
| --- | --- |
| MAMANE KABAOU | ALI LAMINE ZENE |
| Signature: …………………………………… | Signature: …………………………………… |
| Title: Minister of Health and Endemic Disease | Title: Minister of the Economy and Finance |
| Date: …………………………………… | Date: …………………………………… |

National Coordinating Body: Health Sector Strategy Committee:

We, the members of the National Co-ordinating Body:………..……………………… (insert name) met on the ………………(insert date) to review this proposal.  At that meeting we endorsed this proposal on the basis of the supporting documentation which is attached.

  - The endorsed minutes of this meeting are attached as DOCUMENT NUMBER: ………

| Agency/Organisation | Name/Title |
| --- | --- |

In case the GAVI Secretariat has queries on this submission, please contact:

| Name: …………………………………… | Title: …………………………………… |
| --- | --- |
| Tel No.: …………………………………… | Address: …………………………………… |
| Fax No.: …………………………………… | …………………………………… |
| Email: …………………………………… | …………………………………… |

The GAVI Secretariat is unable to return submitted documents and attachments to individual countries.  Unless otherwise specified, documents may be shared with the GAVI partners and collaborators.

## Government and the Inter-Agency Coordinating Committee for Immunization

The Government of the Republic of Niger commits itself to developing national immunization services on a sustainable basis in accordance with the multi-year plan presented with this document.

Districts’ performance on immunization will be reviewed annually through a transparent monitoring system. The Government requests that the Alliance and its partners contribute financial and technical assistance to support immunization of children as outlined in this application.

| Ministry of Health: | Ministry of Finance: |
| --- | --- |
| MAMANE KABAOU | ALI LAMINE ZENE |
| Signature: …………………………………… | Signature: …………………………………… |
| Title: Minister of Health and Endemic Disease | Title: Minister of the Economy and Finance |
| Date: …………………………………… | Date: …………………………………… |

National Coordinating Body: Inter-Agency Coordinating Committee for Immunization:

We, the members of the CIC/AV, met on 25 October 2006 to review this proposal.  At that meeting we endorsed this proposal on the basis of the supporting documentation which is attached.

  - The endorsed minutes of this meeting are attached as DOCUMENT NUMBER: ………

| Agency/Organisation | Name/Title |
| --- | --- |
| Ministry of Health and Endemic Disease | MAMANE KABAOU, Minister |
| Ministry of the Economy and Finance | ALI LAMINE ZENE, Minister |
| WHO | Dr. CODDY RENE, representative |
| UNICEF | ABOUDOU KARIMOU ADJIBADE, representative |
| Helen Keller International (HKI) | PIERRE ADOU, representative |
| RED CROSS | ALI BONDIERE, President |
| JICA | SASDTE KAICHI, head of mission |
| ROTARY INTERNATIONAL | GASTON KABA, representative |
| WORLD BANK | OUSMANE DIAGANA |
| CARITAS | YORO YOUNOUSSI, Director |
| Private sector health ASSOCIATION | Dr. ALFA CISSE, Secretary General |
| EUROPEAN UNION | Delegate |
| Belgian Technical Cooperation | VINCENT VERCRUYSS |
| UNDP | MICHEL FALAVIGNA |
| CIDA | GUY VILLENEUVE |

In case the GAVI Secretariat has queries on this submission, please contact:

| Name: Dr. HAROUNA A. YACOUBA | Title: HEAD, IMMUNIZATION DIVISION |
| --- | --- |
| Tel No.: (227) 96 99 63 92 | Address: MINISTRY OF HEALTH AND ENDEMIC DISEASE BP 205 Niamey (NIGER) |
| Fax No.: (227) 20 73 35 71 | …………………………………… |
| Email: markyacouba@yahoo.fr | …………………………………… |

The GAVI Secretariat is unable to return submitted documents and attachments to individual countries.  Unless otherwise specified, documents may be shared with the GAVI partners and collaborators.

## The Inter-Agency Coordinating Committee for Immunization

Agencies and partners (including development partners, NGOs and Research Institutions) that are supporting immunization services are co-ordinated and organised through an inter-agency coordinating mechanism (ICC).  The ICC are responsible for coordinating and guiding the use of the GAVI ISS support.  Please provide information about the ICC in your country in the spaces below.

Profile of the ICC

| Name of the ICC: CIC/AV |  |  |
| --- | --- | --- |
| Date of constitution of the current ICC: Decree No. 10 of 30 January 2002 |  |  |
| Organisational structure (e.g., sub-committee, stand-alone): Inter-Agency Coordinating Committee for Immunization Activities (CIC/AV) |  |  |
| Frequency of meetings: every three months |  |  |
| Composition: |  |  |
| Function | Title / Organization | Name |
| Chair | Minister of Health and Endemic Disease | MAMANE KABAOU |
| Secretary | Head, Immunization Division | HAROUNA A. YACOUBA |
| Members | - WHO - UNICEF - Rotary International - HKI - JICA - Red Cross - World Bank - CARITAS - Private sector association - CIDA - UNFPA - Belgian Technical Cooperation - UNDP | - Dr. CODDY RENE - Mr. ABOUDOU MARIMOU ADJIBADE - GASTON KABA - PIERRE ADOU - SASDTE KAICHI - ALI BONDIERE - OUSMANE DIAGANA - YORO YOUNOUSSI - Dr. ALFA CISSE - GUY VILLENEUVE - Mrs. MARLENE FRANCOIS LAYS - VINCENT VERCRUYSS - MICHEL FALAVIGNA |

Major functions and responsibilities of the ICC:

The CIC/AV’s mission is to help the Ministry of Health and Endemic Disease (MSP/LCE) formulate, implement, monitor and evaluate national immunization policy. To that end, its tasks are:

- to lend support for the design and implementation of immunization strategies;

- to coordinate the planning of all immunization activities;

- to help examine and approve the action plans drawn up by the Division for Immunization and Children at all levels;

- to help the Division for Immunization and Children manage the Programme transparently and efficiently;

- to support and encourage the exchange of information and feedback at all levels of the national health system and with the partners;

- to ensure coordination of the partners’ immunization activities.

Three major strategies to enhance the CIC/AV’s role and functions in the next 12 months:

1. Plan and hold regular meetings of the CIC/AV

2. Coordinate activities at all levels

3. Advocate greater mobilisation of resources

## Immunization Programme Data

Please complete the immunization fact sheet below, using data from available sources.

## Immunization Fact Sheet

Table 1: Basic facts for the year 2005 (most recent; specify dates of data provided)

| Population | 12,223,261 | GNI per capita | US$ 223 |
| --- | --- | --- | --- |
| Surviving Infants* | 557,396 | Infant mortality rate | 123 / 1000 |
| Percentage of GDP allocated to Health | 2.2% | Percentage of Government expenditure on Health | 5.96% |

* Surviving infants = Infants surviving the first 12 months of life

Table 2: Trends of immunization coverage and disease burden

(as per last two annual WHO/UNICEF Joint Reporting Form on Vaccine Preventable Diseases)

| Trends of immunization coverage (in percentage) |  |  |  |  |  | Vaccine preventable disease burden |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Vaccine |  | Reported |  | Survey |  | Disease | Number of reported cases |  |
|  |  | 2004 | 2005 | 200… | 200… |  | 2004 | 2005 |
| BCG |  | 72% | 93% |  |  | Tuberculosis* | ND | ND |
| DTP | DTP1 | 75% | 97% |  |  | Diphtheria | 0 | 0 |
|  | DTP3 | 62% | 89% |  |  | Pertussis | 2,159 | 1,206 |
| Polio 3 |  | 62% | 89% |  |  | Polio | 25 | 10 |
| Measles (first dose) |  | 74% | 83% |  |  | Measles | 62,926 | 710 |
| TT2+ (Pregnant women) |  | 43% | 54% |  |  | NN Tetanus | 43 | 3 |
| Hib3 |  | NA | NA |  |  | Hib ** | 47 | ND |
| Yellow Fever |  | 18% | 65% |  |  | Yellow fever | 0 | 0 |
| HepB3 |  | NA | NA |  |  | hepB sero-prevalence* | ND | ND |
| Vit A supplement | Mothers (<6 weeks post-delivery) | NA | NA |  |  |  |  |  |
|  | Infants (>6 months) | 16% | 63% |  |  |  |  |  |

* If available ** Note: JRF asks for Hin meningitis

If survey data is included in the table above, please indicate the years the surveys were conducted, the full title and if available, the age groups the data refers to:

No immunization coverage surveys were carried out between 2003 and 2005.

## Comprehensive Multi-Year Immunization Plan

  - A complete copy (with an executive summary) of the Comprehensive Multi-Year Plan for Immunization is attached, as DOCUMENT NUMBER…………..

The following tables record the relevant data contained in the cMYP, indicating the relevant pages.

Table 3: Current Vaccination Schedule: Traditional, New Vaccines and Vitamin A Supplement

(cMYP page 10)

| Vaccine (do not use trade name) | Ages of administration (by routine immunization services) | Indicate by an “x” if given in: |  | Comments |
| --- | --- | --- | --- | --- |
|  |  | Entire country | Only part of the country |  |
| BCG | At birth | X |  |  |
| DTP | 0-11 months (3 doses, at 6, 10 and 14 weeks) | X |  |  |
| MEAS | 9-11 months (1 dose as of the 9th month) | X |  |  |
| OPV | 0-11 months (3 doses, at 6, 10 and 14 weeks) | X |  |  |
| AAV | 9-11 months (1 dose as of the 9th month) | X |  |  |
| TT | Pregnant women (2 doses before term) | X |  |  |
| Vitamin A | 6-11 months (2 doses as of the 6th month) | X |  |  |

Summary of major action points and timeframe for improving immunization coverage identified in the cMYP

| Major Action Points (cMYP pages 53 - 56) | Timeframe |
| --- | --- |
| 1. Implement immunization activities using out-reach and mobile strategies | January-December (2007-2010) |
| 2. Monitor and supervise immunization activities | January-December (2007-2010) |
| 3. Implement the strategic communication plan | January-December (2007-2010) |
| 4. Organize awareness-raising sessions for health personnel | January-December (2007-2010) |
| 5. Present the cMYP to regional directorates, health departments and local elected officials | March 2006 |
| 6. Ensure regions, districts receive regular supplies of vaccines and inputs | January-December (2007-2010) |
| 7. Acquire equipment (cold chain, logistics, computers) | January-December (2007-2010) |
| 8. Adopt the national safe injection policy | February 2006 |
| 9. Provide supervision | January-December (2007-2010) |
| 10. Provide feedback | January-December (2007-2010) |
| 11. Organize CIC/AV, regional committee meetings | February-May-August-November (2007-2010) |
| 12. Draw up a national immunization policy document | February 2006 |
| 13. Maintain equipment | January-December (2007-2010) |

Table 4: Baseline and annual targets (cMYP pages 8, 26 and 27)

| ###### Number |  | ###### Baseline and targets |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Base-year | Year of GAVI application | Year 1 of Program | Year 2 of Program | Year 3 of Program | Year 4 of Program | Year 5 of Program | Year 6 of Program |
|  |  | 2005***** | 2006 | 2007 | 2008 | 2009 | 2010 | 20… | 20… |
| Births |  | 633,225 | 619,229 | 633,632 | 653,274 | 673,526 | 695,079 |  |  |
| Infants’ deaths |  | 75,823 | 50,158 | 51,324 | 52,915 | 54,556 | 56,301 |  |  |
| Surviving infants |  | 557,396 | 569,071 | 582,308 | 600,359 | 618,970 | 638,777 |  |  |
| Pregnant women |  | 633,225 | 619,229 | 633,632 | 653,274 | 673,526 | 695,079 |  |  |
| Infants vaccinated with BCG |  | 589,893 | 588,268 | 601,950 | 620,610 | 639,852 | 660,325 |  |  |
| BCG coverage* |  | 93% | 95% | 95% | 95% | 95% | 95% |  |  |
| Infants vaccinated with OPV3 |  | 498,072 | 540,618 | 553,192 | 570,341 | 588,024 | 606,839 |  |  |
| OPV3 coverage** |  | 89% | 95% | 95% | 95% | 95% | 95% |  |  |
| Infants vaccinated with DTP3*** |  | 498,730 | 540,618 | 553,192 |  |  |  |  |  |
| DTP3 coverage** |  | 89% | 95% | 95% |  |  |  |  |  |
| Infants vaccinated with DTP1*** |  | 540,172 |  |  |  |  |  |  |  |
| Wastage rate in base-year and planned thereafter |  | 6% | 5% | 5% | 5% | 5% | 5% |  |  |
| Infants vaccinated with 3rd dose of pentavalent (DTP-HepB-Hib) |  |  |  | 232,923 | 558,334 | 588,024 | 606,839 |  |  |
| Pentavalent coverage** |  |  |  | 40% | 93% | 95% | 95% |  |  |
| Infants vaccinated with 1st dose of …………….. |  |  |  |  |  |  |  |  |  |
| Wastage1 rate in base-year and planned thereafter for the pentavalent |  |  |  | 5% | 5% | 5% | 5% |  |  |
| Infants vaccinated with Measles |  | 462,283 | 512,164 | 524,077 | 540,232 | 588,024 | 606,839 |  |  |
| Measles coverage** |  | 83% | 90% | 90% | 90% | 95% | 95% |  |  |
| Pregnant women vaccinated with TT+ |  | 344,376 | 495,383 | 506,906 | 555,283 | 606,175 | 660,325 |  |  |
| TT+ coverage**** |  | 54% | 80% | 80% | 85% | 90% | 95% |  |  |
| Vit A supplement | Mothers (<6 weeks from delivery) |  |  |  |  |  |  |  |  |
|  | Infants (>6 months) | 352,200 | 455,257 | 465,846 | 510,305 | 557,075 | 606,839 |  |  |

* Number of infants vaccinated out of total births

** Number of infants vaccinated out of surviving infants

*** Indicate total number of children vaccinated with either DTP alone or combined

**** Number of pregnant women vaccinated with TT+ out of total pregnant women

***** In 2005, a birth rate of 5.2% was applied before final validation of the 2001 general census (RGP/H) results. The census ultimately indicated a birth rate of 4.77% from 2006 to 2009 and 4.69% from 2010 to 2014.

Please indicate the method used for calculating TT and coverage:

The TT target group consists of pregnant women, who represent 4.77% of the total population according to the 2001 general census figures. All TT1, TT2 and subsequent injections are reported during contacts and prenatal consultations. Women who have already been immunized and benefit from protection thanks to contacts during previous pregnancies are also reported and added to the numerator when calculating TT2+ immunization coverage.

Table 5: Estimate of annual DTP drop out rates

| Number | Actual rates and targets |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 20… | 20… |
| Drop out rate [ ( DTP1 - DTP3 ) / DTP1 ] x 100 | 8% | 5% | 5% | 5% | 5% | 5% |  |  |

Table 6: Summary of current and future immunization programme budget (cMYP pages 42-49)

|  | Estimated costs per annum in US$ (,000) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Budget chapter | Current Year 2005 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 |
| Title 1 Traditional vaccines | 926,115 | 832,022 | 588,236 | 618,386 | 642,903 |  |
| Title 2 Injection inputs | 378,803 | 553,360 | 523,276 | 558,338 | 586,661 |  |
| Title 3 New and under-used vaccines | 417,342 | 4,302,86 | 7,440,581 | 7,859,389 | 8,110,89 |  |
| Title 4 Personnel | 1,220,295 | 1,936,86 | 1,982,131 | 2,021,774 | 2,062,209 |  |
| Title 5 Transportation | 193,483 | 263,058 | 315,089 | 347,888 | 187,938 |  |
| Title 6 Maintenance | 2,071,741 | 2,192,683 | 2,312,682 | 2,439,454 | 2,074,274 |  |
| Title 7 Cold chain | 245,693 | 301,667 | 357,075 | 419,089 | 223,811 |  |
| Title 8 Other equipment (data processing) | 221,471 | 254,347 | 286,205 | 317,576 | 113,617 |  |
| Title 9 Buildings | 1,604,577 | 1,636,669 | 1,669,402 | 1,702,79 | 1,736,846 |  |
| Title 10 Short-term training |  | 91,174 | 122,059 | 45,453 | 16,126 |  |
| Title 11 Social mobilisation | 929,235 | 947,820 | 966,776 | 986,112 | 1,005,834 |  |
| Title 12 Disease control and surveillance | 435,388 | 444,249 | 453,29 | 462,515 | 471,927 |  |
| Title 13 Programme management | 49,796 | 254,792 | 51,808 | 52,844 | 53,901 |  |
| Title 14 Logistical upkeep |  | 643,470 | 656,339 | 669,466 | 682,856 |  |
| Title 15 Capital costs | 662,953 | 1,825,562 | 1,356,995 | 972,583 | 987,621 |  |
| Title 16 Immunization campaigns | 11,236,574 | 13,497,892 | 11,815,177 | 12,264,702 | 12,980,133 |  |
| Title 17 Shared costs | 1,095,431 | 2,710,042 | 2,527,031 | 2,577,572 | 2,629,123 |  |
| GRAND TOTAL | 19,727,156 | 30,495,843 | 31,111,469 | 31,876,475 | 32,492,396 |  |

Table 7: Summary of current and future financing and sources of funds (cMYP pages 42/49)

|  |  | Estimated financing per annum in US$ (,000) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Budget chapter | Funding source | Current Year | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 |
| Title 1 Traditional vaccines | STATE | 2,492,956 | 832,022 | 588,236 | 618,386 | 642,903 |  |
| Title 2 Injection inputs | STATE |  | 553,360 | 523,276 | 558,338 | 586,661 |  |
| Title 3 New and under-used vaccines | GAVI, STATE |  | 4,302,86 | 7,440,581 | 7,859,389 | 8,110,89 |  |
| Title 4 Personnel | STATE, WHO, GAVI, UNICEF, PLAN, WORLD VISION | 308,257 | 1,936,86 | 1,982,131 | 2,021,774 | 2,062,209 |  |
| Title 5 Transportation | GAVI, WHO |  | 263,058 | 315,089 | 347,888 | 187,938 |  |
| Title 6 Maintenance | GAVI, WHO |  | 2,192,683 | 2,312,682 | 2,439,454 | 2,074,274 |  |
| Title 7 Cold chain | JICA | 1,156,872 | 301,667 | 357,075 | 419,089 | 223,811 |  |
| Title 8 Other equipment (data processing) | UNICEF, GAVI |  | 254,347 | 286,205 | 317,576 | 113,617 |  |
| Title 9 Buildings | STATE |  | 1,636,669 | 1,669,402 | 1,702,79 | 1,736,846 |  |
| Title 10 Short-term training | GAVI, WHO |  | 91,174 | 122,059 | 45,453 | 16,126 |  |
| Title 11 Social mobilisation | WHO, STATE | 349,358 | 947,820 | 966,776 | 986,112 | 1,005,834 |  |
| Title 12 Disease control and surveillance | WHO |  | 444,249 | 453,29 | 462,515 | 471,927 |  |
| Title 13 Programme management |  | 390,423 | 254,792 | 51,808 | 52,844 | 53,901 |  |
| Title 14 Logistical upkeep | GAVI, WHO | 77,238 | 643,470 | 656,339 | 669,466 | 682,856 |  |
| Title 15 Capital costs | GAVI |  | 1,825,562 | 1,356,995 | 972,583 | 987,621 |  |
| Title 16 Immunization campaigns | WHO, UNICEF, HKI, ROTARY | 9,352,429 | 13,497,892 | 11,815,177 | 12,264,702 | 12,980,133 |  |
| Title 17 Shared costs | STATE |  | 2,710,042 | 2,527,031 | 2,577,572 | 2,629,123 |  |
| GRAND TOTAL |  | 14,127,533 | 30,495,843 | 31,111,469 | 31,876,475 | 32,492,396 |  |

## Immunization Services Support (ISS)

Please indicate below the total amount of funds you expect to receive through ISS:

Table 8: Estimate of fund expected from ISS

|  | Baseline Year | Current Year * | Year 1** | Year 2** | Year 3** | Year 4** | Year 5** |
| --- | --- | --- | --- | --- | --- | --- | --- |
| DTP3 Coverage rate | 89% | 95% | 95% | 93% | 95% | 95% |  |
| Number of infants reported / planned to be vaccinated with DTP3 (as per table 4) | 498,730 | 540,618 | 553,192 | 558,334 | 588,024 | 606,839 |  |
| Number of additional infants that annually are reported / planned to be vaccinated with DTP3 |  |  | 12,575 | 5,141 | 20,690 | 18,815 |  |
| Funds expected ($20 per additional infant) |  |  | 251,500 | 102,820 | 593,800 | 376,300 |  |

* Projected figures

** As per duration of the cMYP

If you have received ISS support from GAVI in the past, please describe below any major lessons learned, and how these will affect the use of ISS funds in future.

Please state what the funds were used for, at what level, and if this was the best use of the flexible funds; mention the management and monitoring arrangements; who had responsibility for authorising payments and approving plans for expenditure; and if you will continue this in future.

| Major Lessons Learned from Phase 1 | Implications for Phase 2 |
| --- | --- |
| 1. Renewed impetus for out-reach and mobile strategies | Pursue support to maintain and improve the out-reach and mobile strategies |
| 2. Implementation of the social mobilisation action plan for systematic EPI |  |
| 3. Stepped up supervision and monitoring of EPI activities |  |
| 4. Training of agents in EPI management and immunization techniques |  |
| 5. Strengthened rolling stock |  |
| 6. Establishment of a system of performance-based financial incentives | Need to pursue the experience with a view to maintaining performance |
| 7. Delay in the transfer of funds to the country | Need to transfer funds early in the year to avoid delays in the implementation of action plans |

The formula to calculate a vaccine wastage rate (in percentage): [ ( A – B ) / A ] x 100.   Whereby : A = The number of doses distributed for use according to the supply  records with correction for stock balance at the end of the supply period; B =  the number of  vaccinations with the same vaccine in the same period. For new vaccines check table   after Table 7.1.