Global Alliance for Vaccines and Immunization (GAVI)

APPLICATION FORM FOR SUDAN PROPOSAL

For Support to:

Immunization Services

April  2007

This document is accompanied by an electronic copy on CD for your convenience. Please return a copy of the CD with the original, signed hard-copy of the document to:

GAVI Secretariat; c/o UNICEF, Palais des Nations, 1211 Geneva 10, Switzerland.

Enquiries to: Dr Julian Lob-Levyt, jloblevyt@unicef.org or representatives of a GAVI partner agency.  All documents and attachments must be in English or French.

## CONTENTS

| SECTION |  | SUPPORT | PAGE |
| --- | --- | --- | --- |
| 1. | Executive Summary | ALL | 2 |
| 2. | Signatures of the Government and National Coordinating Bodies |  |  |
|  | - Government and the Health Sector Strategy Committee | HSS | 3 |
|  | - Government and the Inter-Agency Coordinating Committee for Immunization (ICC) | ALL | 4 |
|  | - The Inter-Agency Coordinating Committee for Immunization (ICC) | ALL | 5 |
| 3. | Immunization Programme Data | ALL | 6 |
|  | - Immunization Fact Sheet |  | 6 |
|  | - Comprehensive Multi-Year Immunization Plan |  | 7 |
| 4. | Immunization Services Support (ISS) | ISS | 10 |
| 5. | Health Systems Strengthening Support (HSS) | HSS | 12 |
|  | - Proposed GAVI Health Systems Strengthening Support |  | 14 |
|  | - HSS Financial Analysis and Planning |  | 16 |
|  | - Management and Accountability of GAVI HSS Funds |  | 17 |
|  | - Involvement of Partners in GAVI HSS Implementation |  | 18 |
| 6. | Injection Safety Support (INS) | INS | 19 |
| 7. | Additional comments and recommendations from the National Coordinating Body (Health Sector Strategic Committee / ICC) | ALL | 20 |
| 8. | Documents required for each type of support | ALL | 21 |
| Annex 1 – Banking Form |  | ISS | 22 |

## Executive Summary

Synopsis of the proposal including the specific requests for support from GAVI and the Vaccine Fund. The figures essential for the calculation of award amounts are presented here, including: baseline data, current DTP3 coverage and targets for increased coverage.

Sudan is the largest country in Africa, with a very wide geographic dispersion of the population. Difficult access to some areas, rural-urban migration, natural disasters, transitional period in north and south Sudan after peace agreement (IDPs, refugees and returnees) and limited resources have a significant impact on the provision of health services including immunization services. As a consequence there are wide variations within the country in delivery of services, vaccination coverage and disease incidence.

Sudan had received GAVI phase (1) support for Immunization Service support, injection safety support and introduction of Hepatitis (B) new vaccine during the period 2002-2006 for all Government controlled areas before the comprehensive peace agreement.

During the period of the previous support EPI had made a great achievement and reached more children that the DTP3 coverage raised from 64% in 2002 to 83% in 2005. During this period DQA was conducted as a test in 2003 where the result was not satisfactory, based on the recommendations of this test, major changes in the information system was implemented and the results of the official DQA conducted in 2004 was excellent.

Maintaining this coverage level is still a challenge for Sudan. The National coverage does not reflect the low coverage in some districts which oftenly reports coverage less than 80%. Sudan is seeking support from GAVI to strengthen EPI all over the country even in those conflict (Darfour zone) areas . Reaching those areas will be through coordination with partners and NGOs. In those areas, routine EPI has collapsed and need to be reinitialised and sustained.

After the peace agreement Sudan established Government of Southern Sudan, which will be responsible of all affairs in Southern Sudan, therefore it is agreed that the government of South Sudan will apply for GAVI phase (2) separately due to different situation and different implementing programms in each part. Accordingly this application will cover only Northern  Sudan.

The 5 year plan: Based on the situation analysis for Northern Sudan conducted at the end of 2005 for all programme aspects, a strategic comprehensive 5 year-plan (2006-2010) has been drawn up aiming to improve the routine immunization coverage, polio eradication, measles and MNT elimination, introduction of new vaccines, improve the quality of the immunization services and strengthening all EPI related activities. All the targets to be achieved are projected from the base line data of the year 2006.

## Government and the Inter-Agency Coordinating Committee for Immunization

The Government of SUDAN commits itself to developing national immunization services on a sustainable basis in accordance with the multi-year plan presented with this document.

Districts’ performance on immunization will be reviewed annually through a transparent monitoring system. The Government requests that the Alliance and its partners contribute financial and technical assistance to support immunization of children as outlined in this application.

| Ministry of Health: | Ministry of Finance: |
| --- | --- |
| Signature: | Signature: …………………………………… |
| Title: Federal Minister of Health | Title: Federal Minister of Finance |
| Date: 6/1/2007 | Date: 10/1/2007 |

National Coordinating Body: Inter-Agency Coordinating Committee for Immunization:

We, the members of the ICC met on the 28th /Dec/ 2006 to review this proposal.  At that meeting we endorsed this proposal on the basis of the supporting documentation which is attached.

  - The endorsed minutes of this meeting are attached as DOCUMENT NUMBER: (2)

| Name/Title | Agency/Organisation | Signature |
| --- | --- | --- |
| Dr. Yahiya Mohamed Ali PHC National Director | PHC /FMOH |  |
| Dr. Eltayeb Ahmed Elsayed EPI National Director | EPI / FMOH |  |
| Mrs. Mohamed Abdelrahman MOF rep. | Ministry of Finance |  |
| Dr. Babiker Mubasher MOI rep. | Ministry of Interior |  |
| Dr. Elamin Osman MOD rep. | Ministry of Defence |  |
| Mrs. Sawsan Omer MO Int. co rep. | Ministry of International Cooperation |  |
| Dr. Mohammed Abdur Rab / Representitive | WHO |  |
| Mr. Ted Chaiban / Representitive | UNICEF |  |
| Dr. Mohamed Hussain Dafalla/ Representative | Humanitarian Aid Commission (HAC) |  |
| Dr. Abdelrahman Hamid / Representative | International Federation of Red Cross |  |

In case the GAVI Secretariat has queries on this submission, please contact:

| Name: Dr. Eltayeb Ahmed Elsayed | Title: National EPI Manager |
| --- | --- |
| Tel No.: +249912302883 | Address: Expanded Programme on Immunization |
| +249183-793332 | Federal Ministry of Health |
| Fax No.: +249183-793331 | Nile street |
| +249183-793321 | Khartoum |
| Email: episud@sudanmail.net | Sudan |

The GAVI Secretariat is unable to return submitted documents and attachments to individual countries.  Unless otherwise specified, documents may be shared with the GAVI partners and collaborators.

## The Inter-Agency Coordinating Committee for Immunization

Agencies and partners (including development partners, NGOs and Research Institutions) that are supporting immunization services are co-ordinated and organised through an inter-agency coordinating mechanism (ICC).  The ICC are responsible for coordinating and guiding the use of the GAVI ISS support.  Please provide information about the ICC in your country in the spaces below.

Profile of the ICC

| ## Name of the ICC: Inter-Agency Coordinating Committee for Immunization |  |  |  |  |
| --- | --- | --- | --- | --- |
| Date of constitution of the current ICC: April 2001 |  |  |  |  |
| Organisational structure (e.g., sub-committee, stand-alone): stand alone |  |  |  |  |
| Frequency of meetings: Every three months (4 meetings / year) |  |  |  |  |
| Composition: |  |  |  |  |
|  | Function | Title / Organization | Name |  |
|  | Chair | Federal Minister of Health / FMOH | Dr. Tabita Botross Shokai |  |
|  | Secretary | Under-Secretary/ FMOH | Dr. Abdalla Sid Ahmed |  |
|  | Members | - PHC Director General / FMOH - EPI Director General / FMOH - Ministry of Finance - Ministry of Interior - Ministry of Defence - Ministry of International Cooperation - Representative / WHO - Representative / UNICEF - Representative / Rotary International - Representative / International Federation of Red Cross - Representative / Humanitarian Aid Commission (HAC) | - Dr. Yahiya Mohamed Ali - Dr. Eltayeb Ahmed Elsayed - Mr. Mohammed Abdelrahman - Dr. Babiker Mubasher - Dr. Elamin Osman - Mrs. Sawsan Omer - Dr. Mohammed Abdur Rab - Mr. Ted Chaiban - Mr. Sohaib Elbadawi - Dr. Abdelrahman Hamid - Dr. Mohamed Hussain Dafalla |  |

Major functions and responsibilities of the ICC:

- Advocacy and commitment of different partners.

- Resource mobilization and fund raising.

- Coordination between the EPI and regional, global partners and stake-holder to achieve      the  set goals.

- Technical support for all EPI activities.

-  Revise approve and monitor the implementation of the EPI plans

-  Monitoring and follow up of the end use of supplies and support.

Three major strategies to enhance the ICC’s role and functions in the next 12 months:

1. Formation of Technical Committee (WHO/UNICEF) with monthly meetings.

2. Improve sharing of information and communications (News letter, reports) to insure coordination of the activities

3. Addition of new members to include NGOs, university staff, etc

## Immunization Programme Data

Please complete the immunization fact sheet below, using data from available sources.

## Immunization Fact Sheet

Table 1: Basic facts for the year 2006 (most recent; specify dates of data provided)

| Population | 30,741,234** | GNI per capita | 640 $US |
| --- | --- | --- | --- |
| Surviving Infants* | 1,044,415 | Infant mortality rate | 110/ 1000 |
| Percentage of GDP allocated to Health | 4% | Percentage of Government expenditure on Health | 1.5% |

* Surviving infants = Infants surviving the first 12 months of life

** Population estimates are for Northern Sudan only

Table 2: Trends of immunization coverage and disease burden

(as per last two annual WHO/UNICEF Joint Reporting Form on Vaccine Preventable Diseases)

| Trends of immunization coverage (in percentage) |  |  |  |  |  | Vaccine preventable disease burden |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Vaccine |  | Reported |  | Survey |  | Disease | Number of reported cases |  |
|  |  | 2005 | 2006 | 200… | 200… |  | 2005 | 2006 |
| BCG |  | 80% | 77.7% | NA | NA | Tuberculosis* | 264 | 123 |
| DTP | DTP1 | 97% | 95.1% | NA | NA | Diphtheria | 13 | 15 |
|  | DTP3 | 85.8% | 84.7% | NA | NA | Pertussis | 70 | 39 |
| Polio 3 |  | 85.8% | 84.7% | NA | NA | Polio | 23 | 0 |
| Measles (first dose) |  | 74.6% | 75.5% | NA | NA | Measles | 995 | 228 |
| TT2+ (Pregnant women) |  | 42% | 42.6% | NA | NA | NN Tetanus | 90 | 115 |
| Hib3 |  | NR | NR |  |  | Hib ** | NA | NA |
| Yellow Fever |  | NR | NR |  |  | Yellow fever | NA | NA |
| HepB3 |  | 52% | 68.2% | NA | NA | hepB sero-prevalence* | NA | NA |
| Vit A supplement | Mothers (<6 weeks post-delivery) | NR | NR |  |  |  |  |  |
|  | Infants (>6 months) | NR | NR |  |  |  |  |  |

* If available ** Note: JRF asks for Hin meningitis

If survey data is included in the table above, please indicate the years the surveys were conducted, the full title and if available, the age groups the data refers to:

No coverage survey has been conducted in 2005, 2006

## Please Note That: The above mentioned data is for Northern Sudan only while the (2005) annual WHO/UNICEF Joint Reporting INCLUDED the data for whole Sudan

## Comprehensive Multi-Year Immunization Plan

  - A complete copy (with an executive summary) of the Comprehensive Multi-Year Plan for Immunization is attached, as DOCUMENT NUMBER (3)

The following tables record the relevant data contained in the cMYP, indicating the relevant pages.

Table 3: Current Vaccination Schedule: Traditional, New Vaccines and Vitamin A Supplement

(cMYP page (10)

| Vaccine (do not use trade name) | Ages of administration (by routine immunization services) | Indicate by an “x” if given in: |  | Comments |
| --- | --- | --- | --- | --- |
|  |  | Entire country | Only part of the country |  |
| BCG | Birth Dose | X |  |  |
| DTP | 6, 10,14 Weeks | X |  |  |
| POLIO | Birth, 6, 10,14 Weeks | X |  |  |
| Hepat B | 6, 10,14 Weeks |  | X | New vaccine introduced in 2005, in phased manner. |
| MCV | 9 Months | X |  |  |
| TT | Pregnant Women | X |  |  |
| Vitamin A |  |  |  | Supplemented during NIDs |

Summary of major action points and timeframe for improving immunization coverage identified in the cMYP

| Major Action Points (cMYP pages 29, 42) | Timeframe |
| --- | --- |
| 1. Re-establish immunization services for hard-to-reach and war affected areas. | 2007 -2009 |
| 2. Implement RED strategy in localities with < 80% DPT3 coverage | 2006 -2010 |
| 3. Conduct 3 to 4 pulse immunization campaigns per year in hard to reach and newly accessible areas | 2006 -2010 |
| 4. Implement supportive supervision using DQS tool and transfer skills and competencies to lower levels by conducting on job training | 2006 -2010 |
| 5. Recruitment of permanent staff and ensure proper use of information at all levels | 2006 -2010 |

Table 4: Baseline and annual targets (cMYP pages.)

| ###### Number |  | ###### Baseline and targets |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Base-year | Year of GAVI application | Year 1 of Program | Year 2 of Program | Year 3 of Program | Year 4 of Program | Year 5 of Program | Year 6 of Program |
|  |  | 2006 | 2007 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 |
| Births |  | 1,167,795 | 1,199,389 | 1,199,389 | 1,231,913 | 1,265,396 | 1,299,868 | 1,335,360 | 1,371,903 |
| Infants’ deaths |  | 123,380 | 126,677 | 126,677 | 130,070 | 133,563 | 137,159 | 140,859 | 144,669 |
| Surviving infants |  | 1,044,415 | 1,072,712 | 1,072,712 | 1,101,842 | 1,131,832 | 1,162,709 | 1,194,501 | 1,227,234 |
| Pregnant women |  | 1,167,795 | 1,199,389 | 1,199,389 | 1,231,913 | 1,265,396 | 1,299,868 | 1,335,360 | 1,371,903 |
| Infants vaccinated with BCG |  | 907,204 | 983,499 | 983,499 | 1,034,806 | 1,100,894 | 1,169,881 | 1,228,531 | 1,303,307 |
| BCG coverage* |  | 77.7% | 82% | 82% | 84% | 87% | 90% | 92% | 95% |
| Infants vaccinated with OPV3 |  | 884489 | 933,260 | 933,260 | 969,620 | 1,007,330 | 1,046,438 | 1,086,995 | 1,129,055 |
| OPV3 coverage** |  | 84.7% | 87% | 87% | 88% | 89% | 90% | 91% | 92% |
| Infants vaccinated with DTP3*** |  | 884187 | 933,260 | 933,260 | 969,620 | 1,007,330 | 1,046,438 | 1,086,995 | 1,129,055 |
| DTP3 coverage** |  | 84.7% | 87% | 87% | 88% | 89% | 90% | 91% | 92% |
| Infants vaccinated with DTP1*** |  | 992958 | 1,040,530 | 1,040,530 | 1,079,805 | 1,109,195 | 1,139,454 | 1,170,610 | 1,202,689 |
| Wastage rate in base-year and planned thereafter |  | 20% | 19% | 19% | 18% | 17% | 16% | 15% | 15% |
| Infants vaccinated with 3rd dose of Hepatitis B |  | 711938 | 933,260 | 933,260 | 969,620 | 1,007,330 | 1,046,438 | 1,086,995 | 1,129,055 |
| Hepatitis B Coverage** |  | 68.2% | 87% | 87% | 88% | 89% | 90% | 91% | 92% |
| Infants vaccinated with 1st dose of Hepatitis B |  | 980,878 | 1,040,530 | 1,040,530 | 1,079,805 | 1,109,195 | 1,139,454 | 1,170,610 | 1,202,689 |
| Wastage1 rate in base-year and planned thereafter |  | 20% | 19% | 19% | 18% | 17% | 16% | 15% | 15% |
| Infants vaccinated with Measles |  | 788643 | 847,442 | 847,442 | 892,492 | 939,420 | 988,302 | 1,039,215 | 1,092,238 |
| Measles coverage** |  | 75.5% | 79% | 79% | 81% | 83% | 85% | 87% | 89% |
| Pregnant women vaccinated with TT+ |  | 497742 | 575,706 | 575,706 | 640,594 | 708,621 | 779,920 | 827,923 | 891,737 |
| TT+ coverage**** |  | 42.6% | 48% | 48% | 52% | 56% | 60% | 62% | 65% |
| Vit A supplement | Mothers (<6 weeks from delivery) | NA | NA | NA | 30% | 40% | 50% | 60% | 65% |
|  | Infants (>6 months) | NA | NA | NA | 50% | 60% | 70% | 80% | 85% |

*  Number of infants vaccinated out  of total births

**  Number of infants vaccinated out of surviving infants

***  Indicate total number of children vaccinated with either DTP alone or combined

**** Number of pregnant women vaccinated with TT+ out of total pregnant women

Please indicate the method used for calculating TT and coverage:

Total number of pregnant women vaccinated with TT2+ out of the total pregnant women

Table 5: Estimate of annual DTP drop out rates

| Number | Actual rates and targets |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2006 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 |
| Drop out rate [ ( DTP1 - DTP3 ) / DTP1 ] x 100 | 11% | 11% | 10% | 10% | 9% | 8% | 7% | 6% |

Table 6: Summary of current and future immunization programme budget (cMYP pages 42-50)

|  | Estimated costs per annum in US$ (,000) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Budget chapter | Base line year | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 |
| 1. Capital cost | 176.5 | 119.3 | 1687.4 | 1701.3 | 1765.9 | 1791.1 |
| Recurrent Costs |  |  |  |  |  |  |
| 2. Routine vaccines | 2090.6 | 3244.9 | 3115.8 | 22008.5 | 18628.6 | 19229.8 |
| 3. Injection supplies | 559.3 | 896.7 | 938.6 | 730.6 | 771.3 | 821.8 |
| 4. Personnel | 6470 | 6620 | 7198.1 | 7796.8 | 8407.5 | 9030.3 |
| 5. Transportation | 647.8 | 702.7 | 971.6 | 1242.7 | 880.3 | 1143.7 |
| 6. Maintenance and over head | 1814 | 1860 | 1978.1 | 2097.8 | 2221.5 | 2337.2 |
| 7) Training | 12.3 | 18.1 | - | 101.5 | - | - |
| 8) Social mobilization | 112.9 | 102.4 | 114.9 | 128.9 | 144.7 | 162.3 |
| 9) Disease surveillance | 271.7 | 245.8 | 286.6 | 303.8 | 353.5 | 376.6 |
| 10) Programme management | 57.7 | 67 | 75.2 | 84.2 | 94.5 | 106.1 |
| 11) Campaigns | 23911 | 10112.3 | 15556.6 | 7686.3 | 4477.6 | 7034.7 |
| 12) Other costs | 2197 | 1817 | 2544.3 | 1890.5 | 1928.3 | 1966.9 |
| GRAND TOTAL | 38320.8 | 25806.2 | 34467.2 | 45772.9 | 39673.7 | 44000.5 |

Table 7: Summary of current and future financing and sources of funds (cMYP pages 42-50.)

|  |  | Estimated financing per annum in US$ (,000) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Budget chapter | Funding source | Current Year | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 |
| 1. Capital cost | -WHO -UNICEF | 176.5 | - | - | - | - | - |
| 2. Routine vaccines | -UNICEF -GAVI | 2090.6 | 3244.9 | 2914.8 | 1099.6 | 976.2 | 838.7 |
| 3. Injection supplies | GOVERNMENT UNICEF | 559.3 | 896.7 | 938.6 | - | - | - |
| 4. Personnel | GOVERNMENT -Sub-National Government - GAVI -WHO | 6470 | 6620 | 7198.1 | 5006.7 | 5388.1 | 5775.9 |
| 5.Transportation | GAVI GOVERNMENT | 647.8 | 702.7 | 971.6 | - | - | - |
| 6. Maintenance and over head | Sub-National Government | 1814 | 733 | 828.3 | - | - | - |
| 7.Training | WHO | 12.3 | - | - | - | - | - |
| 8. Social mobilization | -UNICEF -GAVI | 112.9 | 102.4 | - | - | - | - |
| 9. Disease surveillance | WHO | 271.7 | 245.8 | 286.6 | 303.9 | 353.5 | 376.6 |
| 10. Programme management | GAVI | 57.7 | 67 | 75.2 | - | - | - |
| 11) Campaigns | -UNICEF -WHO - UN Foundation | 23911 | 9966.8 | 2650.6 | - | - | - |
| 12) Other costs | Sub-National Government | 2197 | 1817 | 1853.4 | 1890.5 | 1928.3 | 1966.9 |
| GRAND TOTAL |  | 38320.8 | 24396.3 | 16778.6 | 8300.6 | 8646.1 | 8958 |

## Immunization Services Support (ISS)

Please indicate below the total amount of funds you expect to receive through ISS:

Table 8: Estimate of fund expected from ISS

|  | Baseline Year 2006 | Current 2006 | Year 1** | Year 2** | Year 3** | Year 4** | Year 5** |
| --- | --- | --- | --- | --- | --- | --- | --- |
| DTP3 Coverage rate | 84.7% | 84.7% | 87% | 88% | 89% | 90% | 91% |
| Number of infants reported / planned to be vaccinated with DTP3 (as per table 4) | 884187 | 884187 | 933,260 | 969,620 | 1,007,330 | 1,046,438 | 1,086,995 |
| Number of additional infants that annually are reported / planned to be vaccinated with DTP3 |  |  | 49,073 | 36,360 | 37,710 | 39,108 | 40,557 |
| Funds expected ($20 per additional infant) |  |  | 981,460 | 727,200 | 754,200 | 782,160 | 811,140 |

*  Projected figures

**  As per duration of the cMYP

If you have received ISS support from GAVI in the past, please describe below any major lessons learned, and how these will affect the use of ISS funds in future.

Please state what the funds were used for, at what level, and if this was the best use of the flexible funds; mention the management and monitoring arrangements; who had responsibility for authorising payments and approving plans for expenditure; and if you will continue this in future.

| Major Lessons Learned from Phase 1 | Implications for Phase 2 |
| --- | --- |
| 1. RED Strategy Implementation of RED approach has the major role in increasing the routine immunization coverage, RED evaluation assessment is on process | Use of the results and the recommendations of the assessment to improve the implementation of RED approach in all the districts |
| 2. Micro planning The experience of developing districts micro plans, and monitoring its implementation had improved the managerial capacity of the district personnel. | Involvement of the district persons in the annual evaluation meetings to monitor the overall progress of the implementation of the micro plans and share experiences |
| 3. DQA & DQS Based on the results and recommendations, of the DQA the immunization information system has been improved The use of the DQS tool for supervision, reflects the weak area of the Programme, which will be concentrated on during the supervision visits and trainings | Conduction of DQA at local level to verify and improve the information system To expand the use of the tool to all districts and strengthen the supportive supervision at all levels |
| 4. Introduction of Hepatitis B new vaccine Pre-introduction assessment at district and health facility levels showed the need for special training for vaccine management at all levels, which was implemented in all states that had introduced the new vaccine. - The introduction of the new vaccine had raised the community awareness towards immunization | - Pre introduction training, and cold chain capacity building is crucial. - Conduction of strong social mobilization campaign before the introduction of new combined vaccines. |

If you have not received ISS support before, please indicate:

a) when you would like the support to begin:

ISS support has been received before (GAVI phase 1 )

b) when you would like the first DQA to occur:

DQA has already being done with the first phase

c) how you propose to channel the funds from GAVI into the country:

The same channel of the previous support will be used.

Supporting funds for the immunization services to be channelled into the country through the same  process of transferring the immunization service support ( ISS ) being used for the past five years into the same existing system and banking account of the ISS fund of phase (1) GAVI support

Note: ( all the details of banking form was already submitted to GAVI for the ISS support)

d) How you propose to manage the funds in-country:

- The support will be managed through the same regulation of the ISS funds of the first phase support that is through the Federal Ministry of Health which will take complete responsibility of managing the in country transfer of funds through its existing health sector account.

e) who will be responsible for authorising and approving expenditures:

The Federal Ministry of health will be responsible for authorising and approving the expenditure has its strong system and well trained staff for managing this process

-  Federal Ministry of Health will be responsible for managing and reporting to GAVI the required reports on the use of funds.

- The ICC Monitor and follow up the end use of supplies and support.

  - Please complete the banking form (annex 1) if required

## Banking form not required

## Additional comments and recommendations from the National Coordinating Body (ICC)

- ICC members expressed their appreciation for all the achievements made by GAVI support to increase the immunization coverage. And all the efforts made to reduce child mortality including the new vaccines introduction and other PHC package of services integration.

- ICC members confirmed their commitment to support all EPI activities.

- All members commented, that the proposal is satisfactory for them and they were very pleased to have second opportunity with GAVI support for the immunization service support in order to increase and sustain the achievements of the routine immunization coverage made during phase one of the support.

- WHO commented on the importance of updating the targets annually

## DOCUMENTS REQUIRED FOR EACH TYPE OF SUPPORT

| Type of Support | Document | DOCUMENT NUMBER | Duration * |
| --- | --- | --- | --- |
| ALL | WHO / UNICEF Joint Reporting Form | 4 | 2005 2006 |
| ALL | Comprehensive Multi-Year Plan (cMYP) | 3 | 2006-2010 |
| ALL | Endorsed minutes of the National Coordinating Body meeting where the GAVI proposal was endorsed |  |  |
| If relevant | Endorsed minutes of the ICC meeting discussing the requested GAVI support | 2 |  |
| HSS | National Health Sector Strategic Plan | NA | NA |
| HSS | Medium Term Expenditure Framework ** | NA | NA |
| HSS | Recent Health Sector Assessment documents | NA | NA |
| HSS | Outline of HSS Programme with budget and Justification for support or HSS Relevant parts of National Planning Document | NA | NA |
| HSS | Other Health Systems Strengthening Plans / estimates | NA | NA |
| Injection Safety | National Policy on Injection Safety including safe medical waste disposal (if separate from cMYP) | NA | NA |
| Injection Safety | Action plans for improving injection safety and safe management of sharps waste (if separate from cMYP) | NA | NA |
| Injection Safety | Evidence that alternative supplier complies with WHO requirements (if not procuring supplies from UNICEF) | NA | NA |

* Please indicate the duration of the plan / assessment / document where appropriate

** Where available

ANNEX 1

| GLOBAL ALLIANCE FOR VACCINES AND IMMUNIZATION |  |  |  |  |  | ##### Banking Form |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SECTION 1 (To be completed by payee) |  |  |  |  |  |  |  |  |  |  |
| In accordance with the decision on financial support made by the Global Alliance for Vaccines and Immunization dated . . . . . . . . . . . , the Government of SUDAN. hereby requests that a payment be made, via electronic bank transfer, as detailed below: |  |  |  |  |  |  |  |  |  |  |
| #### Name of Institution: (Account Holder) |  | Expanded Programme on Immunization, Federal Ministry of Health |  |  |  |  |  |  |  |  |
| #### Address: |  | Expanded Programme on Immunization, Federal Ministry of Health |  |  |  |  |  |  |  |  |
|  |  | Nile street, Khartoum, SUDAN |  |  |  |  |  |  |  |  |
|  |  | P.O.Box 3068 Khartoum, Sudan |  |  |  |  |  |  |  |  |
| #### City – Country: |  | Khartoum - SUDAN |  |  |  |  |  |  |  |  |
| Telephone No.: |  | 00249183793333 00249183793334 |  | Fax No.: |  |  |  | 00249183793331 00249183793332 |  |  |
| #### Amount in USD: |  | (To be filled in by GAVI Secretariat) |  |  | Currency of the bank account: |  |  |  |  | US$ |
| For credit to: Bank account’s title |  |  |  |  |  |  |  |  |  |  |
| Bank account No.: |  | 321032 |  |  |  |  |  |  |  |  |
| At: Bank’s name |  | ELNILEN INDUSTRIAL DEV. BANK |  |  |  |  |  |  |  |  |
| #### Is the bank account exclusively to be used by this programme? |  |  |  |  |  |  | YES ( ) NO ( ) |  |  |  |
| #### By whom is the account audited? |  |  |  |  |  |  |  |  |  |  |
| # Signature of Government’s authorizing official: |  |  |  |  |  |  |  |  |  |  |
| #### Name: | d |  |  |  |  |  |  |  | Seal: |  |
| #### Title: |  |  |  |  |  |  |  |  |  |  |
| #### Signature: |  |  |  |  |  |  |  |  |  |  |
| Date: |  |  |  |  |  |  |  |  |  |  |

| SECTION 2 (To be completed by the Bank) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| # FINANCIAL INSTITUTION |  |  |  | CORRESPONDENT BANK (In the United States) |  |
| Bank Name: |  |  |  |  |  |
| Branch Name: |  |  |  |  |  |
| Address: |  |  |  |  |  |
| City – Country: |  |  |  |  |  |
| Swift code: |  |  |  |  |  |
| Sort code: |  |  |  |  |  |
| ABA No.: |  |  |  |  |  |
| Telephone No.: |  |  |  |  |  |
| Fax No.: |  |  |  |  |  |
| I certify that the account No. . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . is held by (Institution name) . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . .at this banking institution. |  |  |  |  |  |
| The account is to be signed jointly by at least …… (number of signatories) of the following authorized signatories: |  |  | Name of bank’s authorizing official: |  |  |
| 1 Name: Title: |  |  | Signature: |  |  |
|  |  |  | Date: |  |  |
| 2 Name: Title: |  |  | Seal: |  |  |
| 3 Name: Title: |  |  |  |  |  |
| 4 Name: Title: |  |  |  |  |  |

COVERING LETTER

(To be completed by UNICEF representative on letter-headed paper)

### TO:    GAVI – Secretariat

### Att. Dr Julian Lob-Levyt

### Executive Secretary

C/o UNICEF

Palais des Nations

CH 1211 Geneva 10

Switzerland

| On the ……………………………… I received the original of the BANKING DETAILS form, which is attached. I certify that the form does bear the signatures of the following officials: |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | Name |  |  | Title |
| Government’s authorizing official |  |  |  |  |  |
| Bank’s authorizing official |  |  |  |  |  |
| Signature of UNICEF Representative: |  |  |  |  |  |
| Name |  |  |  |  |  |
| Signature |  |  |  |  |  |
| Date |  |  |  |  |  |

The formula to calculate a vaccine wastage rate (in percentage): [ ( A – B ) / A ] x 100.   Whereby : A = The number of doses distributed for use according to the supply  records with correction for stock balance at the end of the supply period; B =  the number of  vaccinations with the same vaccine in the same period. For new vaccines check table   after Table 7.1.