APPLICATION FORM FOR COUNTRY PROPOSALS

to obtain support for:

Conjugated meningococcal A vaccine

Submitted by the

Government of

BENIN

Reviewed in February 2011

For the 2011 application submission session

Please send this electronic application along with its attachments (including the signature page) to the following address: proposals@gavialliance.org

Information from: proposals@gavialliance.org or from the representatives of a GAVI partner agency.  The proposal and annexes must be presented in English or French.

Please be sure the GAVI Secretariat receives the application before or at the latest on the deadline date.

The GAVI Secretariat is unable to return documents and items which may have been sent to it to individual countries. Unless otherwise specified, documents may be shared with the GAVI partners or the public.

## Acronyms

ADIP		Accelerated Development and Introduction Plans

NRA		Autorité Nationale de Réglementation [National Regulatory Authority]

BCG		Calmette-Guérin Bacillus

ICC		Interagency Coordination Committee

HSCC		Health Sector Coordination Committee

IEC		Independent Exam Committee

DQA		Data Quality Audit for Vaccination Data

3rd		Diphtheria-Tetanus-Pertussis, Third Dose

JRF	WHO/UNICEF Joint Report Form on Disease Prevention on vaccination-preventable diseases

ICG		International Coordination Group

Hep B		Hepatitis B vaccine

Hib		Haemophilus influenzae type b

MF		Ministry of Finance

MH		Ministry of Health

MDG		Millennium Development Goals

WHO		World Health Organization

UN		United Nations

CSO		Civil Society Organization

EPI		Expanded Program on Immunization

Phase 1	Phase 1 of GAVI Alliance support (2000-2005)

Phase 2	Phase 2 of GAVI Alliance support (2006-2010)

GDP		Gross Domestic Product

LDC		UN list of Least Developed Countries

cMYP		Complete Multiyear Plan for Vaccination

GNR		Gross National Revenue

APR		Annual Progress Report

ALS		Auto-disable (AD) syringes

SAGE		Strategic Advisory Group of Experts from WHO

NVS		New and Underused Vaccine Support

ISS		Injection Safety Support

VSS		Vaccination Services Support

SWAp		Sector Wide Approach Strategy

TT		Tetanus toxoid

UNFPA	United Nations Population Fund

UNICEF	United Nations Children's Fund

## Table of Contents

Acronyms	1

Table of Contents	2

1.	Executive Summary	3

2. Signatures of the Government and National Coordinating Bodies	6

Government and the Inter-Agency Coordinating Committee for Immunisation	6

Inter-Agency Coordinating Committee for Vaccination	7

3. Data Regarding the Vaccination Program	9

4.  Request for Meningococcal A conjugate vaccine	16

5. Procurement and Management of New and Under-Used Vaccines	27

6. Grants for the Operational Cost for Vaccination Campaigns	27

7. Additional comments and recommendations from the National Coordinating Body (ICC/HSCC)	31

8. Documents required for each type of support	31

Signature of the authorised government representative:	33

FINANCIAL ESTABLISHMENT	34

# Executive Summary

Benin is part of the African meningitis belt.  Therefore, it is often subject to meningitis epidemics, in particular in the northern part of the country.  Serogroup A meningitis is the most common strain found in these epidemic flare-ups.

As stated in the revised cMYP for 2009-2013, the government of Benin plans to organize a mass vaccination campaign to prevent these devastating meningococcal meningitis A epidemics. This will occur during the fourth quarter of 2012 in the five departments in Benin that are part of the meningitis belt (Atacora, Donga, Borgou, Alibori, Collines).  To this end, Benin is submitting this request to the GAVI Secretariat. The Ministry of Health coordinated its preparation by a national Technical committee with support from various partners (WHO and UNICEF). It was approved by the Inter-Agency Coordinating Committee on April 28, 2011.

This vaccination campaign is aimed at eliminating serogroup A meningitis epidemics in Benin.  It is part of the WHO's recommended strategies in the African region, specifically case-based surveillance, the inclusion of the vaccine in the routine EPI, catch-up vaccination campaigns and tracking and management of cases caused by other germs.

Benin has benefited from the GAVI fund’s support to improve injection safety since 2002, and to include new vaccines into the routine EPI:  The Viral Hepatitis B vaccine in 2002, Hib infection vaccination in 2005 in pentavalent form (DTP HepB Hib) and improvement of vaccination services since 2009.

In the context of vaccine management at the central level, Benin has four (4) cold rooms including three positive cold rooms with a net total capacity of 15,000 liters and one negative cold room with a net capacity of 5,000 liters.  Each of these rooms has two refrigerant groups and four freezers and refrigerators (3 TCW 1152 and 1 TFW 800) with a net total capacity of 752 liters.  These are used particularly for freezing the ice packs.

Two emergency electric generators, with automatic starting systems, will ensure the operation of the cold chain in the case of a power outage.  The cold rooms have continuous temperature loggers and a reliable alarm system in the event of a power outage.    This capacity is sufficient for storage of routine vaccines and those that will be purchased in the context of the meningitis prevention campaign.

In the context of waste management, the safety boxes filled with used syringes will be collected and supervisors will take them to the closest health facilities that have incinerators.   There are two types of incinerators available :  De Monfort incinerators and incinerators manufactured by the DHAB (Direction de l’Hygiène et de l’Assainissement de Base).   All sharps boxes will be destroyed by incineration at health centers that have incinerators.

Benin has acquired extensive experience through prior vaccination campaigns, and has learned a great deal about the introduction of new vaccines.  Benin plans to implement many strategies in order to achieve success. Specifically:

- Improved coordination at all levels (National, departmental, municipal and local);

- An improved micro-planning process at the decentralized level in order to better define roles and responsibilities and to provide improved assessment of resources;

- Improved communication/social mobilization, especially in terms of locally-based communications with the involvement of local leaders;

- Improved employee skills at all levels, through training related to the various components of the vaccination campaigns;

- Effective tracking of vaccines and input items during the entire campaign;

- Reliable management of vaccine stocks and monitoring of their use

- Strict application of injection safety and waste management

- Improved pharmaco-vigilance, specifically in terms of post-vaccination adverse events (PVAEs) and how to properly manage them;

- Improved supervision, tracking and evaluation;

- Improved case-by-case monitoring, taking experiences with measles, yellow fever and polio into account and using knowledge gained from the first countries to introduce MenAfriVac. In order to achieve this, guides and tools for case-by-case monitoring will be revised.  Health and laboratory agents will benefit from trickle-down training.  Reagents and laboratory equipment will be purchased.  A state-of-the art system for transporting samples from health centers to laboratories will be implemented.

The projected target population is 2,640,459 people between 1 and 29 years of age. The total required quantity of vaccines is 3,115,741 doses. The campaign will consist of one phase in November, 2012.

The plan’s overall total cost is US $4,047,779, or US $1.30 per person vaccinated and the operational cost (including investment) is US $2,004,201, or US $0.64 per person vaccinated (the unit cost of the vaccine plus injection materials is estimated at US $0.67).

# 2. Signatures of the Government and National Coordinating Bodies

## Government and the Inter-Agency Coordinating Committee for Immunisation

The Government of Benin would like to expand the existing partnership with the GAVI Alliance for the improvement of the infants’ routine immunisation programme of the country, and specifically hereby requests for GAVI support for the conjugate meningococcus A vaccine.

The government of Benin is committed to developing national vaccination services on a sustainable basis, in accordance with the cMYP submitted together with the introduction plan for the meningitis A vaccine. The government requests that GAVI Alliance and its partners provide financial and technical assistance to support the vaccination program as described in this proposal.

Table N° xx of page xx of this application shows the amount of support in either supply or cash that is requested from the GAVI Alliance. Table no. ….. on page ….. of this proposal presents the government's financial commitment to operational costs for vaccination campaigns.

Please note that this application will not be examined or approved by the Independent Review Committee without the signatures of the Minister of Health and the Minister of Finances or their delegated authority.

National Coordinating Body: Inter-Agency Coordinating Committee for Vaccination

We undersigned, members of the ICC/HSCC, met April 28, 2011 to examine this proposal. At that meeting we endorsed this proposal on the basis of the supporting documentation which is attached.

  - The endorsed minutes of this meeting are attached as Document Number:  3

In case the GAVI Secretariat has queries on this submission, please contact:

| Name: Laurent Assogba | Title: National Director of Public health (NDPH) |
| --- | --- |
| Tel No.: (00229) 21336679/95454966 | Address: 01 BP 882 Cotonou |
| Fax no.: (00229) 21330464 |  |
| E-mail: laurassog@yahoo.fr |  |

## Inter-Agency Coordinating Committee for Vaccination

Agencies and partners (including development partners and CSOs) supporting immunization services are coordinated and organized through an inter-agency coordinating mechanism (ICC/HSCC). The ICC/HSCC are responsible for coordinating and guiding the use of the GAVI ISS and NVS support. Please provide information about the ICC/HSCC in your country in the spaces below.

Profile of the ICC/HSCC

| Name of the ICC/HSCC: ................................................................................................. Inter-Agency Coordinating Committee for the EPI (ICC-EPI) |  |  |  |
| --- | --- | --- | --- |
| Date of constitution of the current ICC/HSCC:....................................................................... 2005 |  |  |  |
| Structure (for example subcommittee, autonomous body): Stand-alone body |  |  |  |
| Frequency of meetings: Quarterly |  |  |  |
| Composition: |  |  |  |
| Post | Title / Organization | Name |  |
| Chair | Minister of Health | Issifou Takpara |  |
| Secretary | NDEPI/PHC | Marie Rose Nago |  |
| Members | - President, Polio Plus Commission, Rotary International - USAID Representative - European Union Representative - Representative, Belgian Development Agency - Representative, Swiss Development Agency - APM Representative - President, Benin EPI Foundation - EPI Focal Point for the Ministry of Finance and Economy - EPI Focal Point for the Ministry of Planning - Director for Planning and Outlook of the Ministry of Health - Director of Financial Resources and Supplies of the Ministry of Health - Representative of the WHO - Representative of UNICEF | - Ashock Mirchandani - Simplice Takoubo - Thierry Soyez - Aristide Aplogan - Joséphine Aballo - Isaïe Zekpa - Françoise Allodjogbe - Pascal Kora Bata - Béatrice Radji - Raphaël Akpa Gbary - Souleymane Diallo |  |

Major functions and responsibilities of the ICC/HSCC:

The ICC-EPI is responsible for:

-Helping to set the policy direction of the EPI;

- Supporting the preparation of EPI strategic and annual plans

-Mobilising the national and international resources required to implement the programmes developed

-Monitoring programme implementation;

-Making periodic inspections of programme activity

-Ensuring that maximum use is made of the resources mobilised

-Supporting the NDEPI/PHC in organizing periodic programme reviews

Three major strategies to enhance the ICC/HSCC's role and functions in the next 12 months:

1. Drafting a work plan for all the structures of the ICC-EPI (meeting timeline).

2. More assertive support and involvement from partners in managing the EPI (in accordance with the recommendations from the most recent internal review of the 2008 EPI and the conclusions of the IACC meetings).

3. Advocating for donor (including GAVI) resources to be allocated to the EPI.

# 3. Data Regarding the Vaccination Program

Please complete the tables below, using data from available sources. Please identify the source of the data, and the date. Where possible use the most recent data, and attach the source document.

  - Please refer to the cMYP and the meningitis A vaccine introduction plan. Please attach a complete copy (with an executive summary) as document number…………

  - Please refer to Health Sector Strategy documents, budgetary documents, and other reports, surveys etc, as appropriate.

Table 3.1: Basic facts for the year 2009... (the most recent; specify dates of data provided)

|  | Number | Date | Source |
| --- | --- | --- | --- |
| Total population | 8 778 648 | 2010 | Projections based on the 2002 General Population and Housing Census (GPHC) and 3.2% annual growth rate |
| Infant mortality rate (per 1000 live births) | 67 | 2006 | INSAE, DHS III 2006 |
| Surviving Infants* | 351 192 | 2010 | INSAE, DHS III 2006 |
| GNI per capita (US$) | 350 | 2004 | INSAE, DHS III 2006 |
| Percentage of GDP allocated to Health | 4,6 | 2005 | Health statistics 2006, DPP 2006 |
| Percentage of Government expenditure on Health | 10,13 | 2009 | Health statistics 2009, DPP 2009 |

* Surviving infants = Infants surviving the first 12 months of life

Please provide some additional information on the planning and budgeting context in your country:

Please indicate the name and date of the relevant planning document for health

This document is the National Health Plan for 2009-2018. It was prepared using the "Ministry of Health integrated planning procedure" which was completed in December 2006.

Is the cMYP consistent with this document (schedule, content, etc.)? If not, please attach a MenAfrivac introduction plan for the next upcoming mass campaigns.

YES

Please indicate the national planning budgeting cycle for health

the national planning cycle is 10 years

The budget cycle is three years long with an annual action plan

Please indicate the national planning cycle for vaccination

The national planning cycle for immunisation is 3 years then annual National planning for vaccination is completed in a “bottom to top” manner, beginning with the health zones and ending with the central level.

- Regardless of the level involved, situational analysis is the first step in this process.

- The multi-year vaccination plan is prepared in accordance with the WHO’s tools and strategies (GIVS (Global Immunization Vision and Strategy), cMYP)

- The annual action plan is drawn from the multi-year plan.

- Quarterly activity planning is completed using the annual action plan.

- The plan specifies tracking and evaluation activities (monthly monitoring, quarterly session for evaluating activities related to the EPI and surveillance, coverage studies, EPI performance review).

Vaccination stakeholders are involved in the planning and implementation processes at all levels of the health pyramid.

The ICC members approve the EPI plan documents and the results of their implementation.

Please indicate whether data broken down by sex are reported in conjunction with routine vaccination reporting.  No

Please indicate whether gender related aspects have been incorporated in this vaccine's introduction plan:

No. All subjects from 1-29 years of age will receive vaccinations regardless of their gender.

Table 3.2 	Current vaccination schedule : Traditional, New Vaccines and Vitamin A Supplement (pages ……. of the cMYP)

| Vaccine (do not use trade name) | Ages of administration (by routine immunisation services) | Indicate by an "x" if given in: |  | Comment |
| --- | --- | --- | --- | --- |
|  |  | entire country | Only part of the country |  |
| BCG | Birth | X |  |  |
| Oral Polio Vaccine | At birth, and at 6 weeks, 10 weeks and 14 weeks of life | X |  |  |
| DTPHepB+Hib | At birth, and at 6 weeks, 10 weeks and 14 weeks of life | X |  | Pneumo 13 will be introduced in the EPI starting July 1er, 2001 and will follow the same schedule as DTP-Hep P + HIB. |
| Measles vaccine | 9 months | X |  |  |
| Yellow fever vaccine | 9 months | X |  |  |
| Tetanus vaccine | 1st contact, 4 weeks, 6 months, 1 year, 1 year [sic] | X |  | For the EPI: Pregnant women (women of childbearing age {15-49 years} during immunisation campaigns) |

Table 3.3: Trends of vaccination coverage and disease burden

(as described in the last two annual WHO/UNICEF Joint Reporting Forms on Vaccine Preventable Diseases)

| Trends of vaccination coverage (in percentage) |  |  |  |  |  |  | Vaccine preventable disease burden |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Vaccine |  |  | Reported |  | Survey |  | Disease | Number of reported cases |  |
|  |  |  | 2008 | 2009 | 2001 | 2008 |  | 2008 | 2009 |
| BCG |  |  | 114% | 110% | 93% | 97% | Tuberculosis | Not available | 3987 |
| DTP | 3rd |  | 105% | 106% | 91% | 94% | Diphtheria | Not available | Not available |
|  | 3rd |  | 93% | 98% | 78% | 82% | Whooping cough | Not available | 48 |
| Polio 3 |  |  | 94% | 98% | 78% | 82% | Polio | 6 | 20 |
| Measles (first dose) |  |  | 89% | 95% | 70% | 70% | Measles | 928 | 718 |
| TT2+ (Pregnant women) |  |  | 64% | 68% | 84% | 86% | Neonatal tetanus (NT) | 7 | 3 |
| 3rd |  |  | 93% | 98% |  |  | Hib ** | Not available | 6 |
| Yellow Fever |  |  | 89% | 95% |  | 70% | Yellow Fever | 0 | 0 |
| HepB3 |  |  | 93% | 98% |  | 82% | hepB sero-prevalence* | Not available | Not available |
| Vit A supplement |  | Mothers (<6 weeks from delivery) |  |  |  |  |  |  |  |
|  |  | Infants (>6 months) |  |  |  |  |  |  |  |

.

Table 3.4: Vaccination Coverage Trends during Recent Broad Vaccination Campaigns (pages…. of the cMYP)

| ###### Number |  | ###### Baseline and targets |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Baseline year: 2009 | Year 1 2010 | Year 2 2011 | Year 3 2012 | Year 4 2013 | Year 5 2014 |
| Polio | Targets | 2 807 512 | 3 006 224 |  |  |  |  |
|  | Children immunized | 2 915 670 (104%) | 2 958 151 (98%) |  |  |  |  |
| Measles | Targets |  |  |  |  |  |  |
|  | Children immunized |  |  |  |  |  |  |
| TT2+ (pregnant women) | Targets |  |  |  |  |  |  |
|  | Children immunized |  |  |  |  |  |  |
| Yellow Fever | Targets | 6. 331. 572 |  |  |  |  |  |
|  | Children immunized | 6.316.808 (99%) |  |  |  |  |  |

If survey data is included in the table above, please indicate the years the surveys were conducted, the full title and if available, the age groups the data refers to:

Survey data is not included in the table above.  However, in 2009 a yellow fever campaign was organized and six polio vaccination campaigns were completed (National Vaccination Days in February, March, June and July 2009); National Vaccination Day in October (35 municipalities out of 77) and in December (6 municipalities out of 77). In 2010, Benin organized four National Polio Vaccination Days in March, April, November and December.

A measles vaccination campaign is planned for 2011.

Table 3.5: Estimate of Fund and Annual Objectives (pages… of the cMYP)

Please refer to the cMYP and the meningitis A vaccine introduction plan which contain a summary of the estimates of funds and annual objectives in order to complete the mandatory calculation sheet (Annex 1).

Table 3.6 Summary of the Current and Future Vaccination Budget

|  | Estimated costs per annum in US$ (thousands) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Budget Line Item | Baseline year 2008 | Year 1 2009 | Year 2 2010 | Year 3 2011 | Year 4 2012 | Year 5 2013 |
| Recurring Cost for routine vaccination |  |  |  |  |  |  |
| Vaccines (routine vaccines only) | 4 280,242 | 4 955, 763 | 5 385, 975 | 10 251,063 | 17 483,244 | 16 595,535 |
| - Traditional vaccines | 637,242 | 541,515 | 611,172 | 625,548 | 690,249 | 738,405 |
| - New vaccines or | 3 643,000 | 4 414,248 | 4 774,803 | 4 305,099 | 3 805,763 | 3 489,628 |
| - Under-used vaccines |  |  |  | 5 320,415 | 12 987,232 | 12 367,502 |
| Injection supplies | 292,307 | 234,839 | 266,025 | 371,126 | 374,628 | 406,203 |
| Personnel | 511,593 | 537,653 | 564,535 | 592,762 | 673,243 | 706,905 |
| - Salaries of full-time NIP health workers (vaccination specific) | 76,846 | 80,688 | 84,722 | 88,959 | 120,078 | 126,082 |
| - Per-diems for outreach vaccinators / mobile teams | 293,856 | 308,549 | 323,976 | 340,175 | 357,184 | 375,043 |
| Transportation | 108,970 | 159,656 | 191,487 | 215,648 | 244,846 | 149,487 |
| Maintenance and overhead | 392,238 | 502,570 | 614,138 | 791,851 | 855,268 | 867,523 |
| Training | 268,849 | 164,404 | 176,077 | 188,578 | 201,839 | 215,967 |
| Social mobilization and IEC | 75,255 | 67,974 | 73,735 | 160,011 | 79,563 | 83,848 |
| Epidemiological monitoring | 446,289 | 304,256 | 345,189 | 346,834 | 157,205 | 167,531 |
| Program management | 309,768 | 203,983 | 194,231 | 263,498 | 183,512 | 413,802 |
| other | 19,178 | 25,525 | 29,185 | 19,924 | 16,600 | 17,759 |
| Subtotal Recurring Costs | 6 704,689 | 7 156,623 | 7 840,577 | 13 201,295 | 20 269,948 | 19 624,559 |
| Routine Vaccination Equipment Costs |  |  |  |  |  |  |
| Vehicles | 64,380 | 518,006 | 356,855 | 349,880 | 588,975 | 266,553 |
| Cold chain equipment | 222,150 | 979,933 | 301,726 | 751,890 | 108,982 | 72,684 |
| Miscellaneous equipment |  |  | 198,825 | 169,165 | 138,568 | 145,496 |
| Subtotal Equipment Costs | 286,530 | 1 497,939 | 857,406 | 1 270,935 | 836,525 | 484,733 |
| Campaigns |  |  |  |  |  |  |
| Polio | 2 566,001 | 2 724,620 | 5 736,690 | 3 345,930 | 5 175,491 | 5 599,616 |
| Measles | 1 575,524 |  |  | 1 514,378 |  |  |
| Yellow Fever |  | 8 004,120 |  |  |  |  |
| MNT campaigns |  |  |  |  |  |  |
| Other campaigns |  |  |  |  |  |  |
| Subtotal Campaign Costs | 4 141,525 | 10 728,741 | 5 736,690 | 4 860,309 | 12 907,808 | 5 599,616 |
| GRAND TOTAL | 12 493,338 | 20 775,562 | 15 891,744 | 20 857,567 | 35 660,129 | 27 431,954 |

Please list in the tables below the funding sources for each type of cost category (if known). Please try and indicate which vaccination program costs are covered by the Government budget, and which costs are covered by development partners (or the GAVI Alliance), and name the partners.

Table 3.6: Summary of current and future financing and sources of funds (pages…. of the cMYP)

|  |  | Estimated financing per annum in US$ (,000) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Budget Line Item | Funding source | Baseline year 2008 | Year 1 2009 | Year 2 2010 | Year 3 2011 | Year 4 2012 | Year 5 2013 |
| Recurring costs |  |  |  |  |  |  |  |
| 1. | 1. Government | 995,141 | 1037,242 | 1214,004 | 1078,547 | 1243,094 | 1325,123 |
| 2. | 2. GAVI | 3788,150 | 4569,233 | 4792,200 | 9236,898 | 16202,678 | 15283,088 |
| 3. | 3. WHO | 517,564 | 375,099 | 464,589 | 348,380 | 243,831 | 295,058 |
| 4. | 4. UNICEF | 73,462 | 30,851 | 83,080 | 57,624 | 82,011 | 191,415 |
| 5. | 5. European Union | 18,000 |  |  |  |  |  |
| 6. | 6. Swiss Development Agency | 25,000 |  |  |  |  |  |
| 7. | 7. Community Funding | 367,808 | 393,973 | 426,904 | 1094,557 | 843,139 | 711,225 |
| 8. | 8. Highly indebted poor countries fund | 784,399 | 750,225 | 859,800 | 1385,291 | 1665,194 | 1718,650 |
| 9. | 9. Belgian Development Agency | 50,000 |  |  |  |  |  |
| 10. | 10. UNIDEA | 10,000 |  |  |  |  |  |
| 11. | 11. World Bank | 20,000 |  |  |  |  |  |
| 12. | 12. USAID | 55,165 |  |  |  |  |  |
| 13. | 13. Rotary International | 0 |  |  |  |  |  |
| 14. | 14. |  |  |  |  |  |  |
| Equipment Costs |  |  |  |  |  |  |  |
| 1. | 1. Government |  | 642,166 | 272,213 | 284,058 |  | 88,851 |
| 2. | 2. GAVI |  | 38,558 | 22,501 |  |  |  |
| 3. | 3. WHO |  |  | 38,572 |  |  |  |
| 4. | 4. UNICEF |  | 817,415 | 325,295 | 485,438 | 108,982 | 165,917 |
| 5. | 5. Japanese Development Agency |  |  | 198,825 | 501,439 | 727,543 | 189,487 |
|  | 6. UNIDEA |  |  |  |  |  | 145,496 |
| Campaigns |  |  |  |  |  |  |  |
| 1. | 1. Government | 1201,710 | 1161,010 | 89,376 | 579,526 | 676,212 | 88,444 |
| 2. | 2. WHO | 1067,900 | 2814,397 | 3664,416 | 2703,736 | 3571,192 | 3626,196 |
| 3. | 3. UNICEF | 1871,915 | 1239,420 | 1982,898 | 1577,047 | 1912,597 | 1884,976 |
| 4. | 4. GAVI |  | 5513,913 |  |  | 6747,807 |  |
| 5. | 5. |  |  |  |  |  |  |
| GRAND TOTAL |  | 12493,338 | 20775,562 | 15891,744 | 20857,567 | 35660,129 | 27431,954 |

# 4.  Request for Meningococcal A conjugate vaccine

Please summarize the cMYP and/or the Meningitis A vaccine introduction plan. Emphasize important points that have information on the decision-making process (data taken into consideration). Meningitis is responsible for approximately 170,000 deaths each year. Approximately 10-20% of people who contract the disease become disabled. This situation results in a heavy socio-economic burden on families. The disease's mortality rate is often very high; without proper treatment, it can reach 50%. Despite the measures that health care facilities take for their patients, the mortality rate exceeds 10%. There are 12 meningitis serotypes. The most common are A, B, C W 135 and X. These are the most frequent causes of epidemics. Serogroup A accounts for 80-85% of all cases in the meningitis belt, and it causes the epidemics that occur every 7-14 years. During the 2009 epidemic season, there were serogroup A epidemics in 14 African countries including Benin. This resulted in 88,199 cases including 5,352 deaths, a number unprecedented since 1996. In Benin and other countries in the meningitis belt, meningitis cases are recorded each year. These cause not only deaths, but harmful after-effects. The table below shows the progression of cases, deaths and mortality in Benin from 2006 to 2010. Table 1: Progression of cases, deaths and mortality caused by meningitis in Benin from 2006 to 2010. Year; Cases; Incidence per 100,000 residents; Deaths; Mortality. 2001; 9561; Not available; 436; 5%. 2002; 762; Not available; 91; 11,9%. 2003; 488; Not available; 91; 19%. 2004; 413; Not available; 101; 24,5%. 2005; 305; Not available; 75; 24,6%. 2006; 385; 4,91; 97; 25%. 2007; 504; 6,21; 107; 21%. 2008; 461; 5,61; 63; 14%. 2009; 416; 4,9; 64; 15%. 2010; 318; 3,62; 52; 16%. 2011 (W13); 113; 1,28; 25; 22,1%. The most recent epidemic in Benin was in 2001, resulting in 9,561 cases and 436 deaths. An analysis of case-by-case data on meningitis in Benin from 2006 to 2009 (for a total of 1,203 meningitis cases) shows that the most severe epidemic conditions are in the northern half of the country. (See figure below) Figure 1: Geographic breakdown of cases: - Breakdown by age and sex The breakdown by sex shows 538 women and 665 men, and the breakdown by age shows that the under-30 age group represents 90% of cases, for a total of 1,086 cases. The additional 10% of the population represents 117 cases. Children under 5 represent 35% of cases, for a total of 416 cases out of 1,203. - Breakdown by epidemiologic week and by month The chart below clearly shows that the majority of cases occur between the 1st and 22nd epidemiologic weeks with a spike in the 14th or 15th week. Figure 2 : Monthly change in meningitis cases in 2006 in Benin - Primary causative germs: In 2004, a study in the Tanguiéta health zone showed that out of 102 cases, three primary germs were the cause: N. Meningitidis (50%) ; S. pneumoniae (37, 2%) and H. influenzae (6,9%). The African meningitis belt runs through Benin's northern departments and through a portion of the country's center (the Collines department). Because the country's central and southern regions have almost never experienced meningococcus A epidemics, the ICC decided at its April 28, 2011 meeting to conduct the MenAfriVac campaign in the high-risk departments in the north (Alibori, Atacora, Borgou and Donga) and in the Collines department. This decision was also made because of the vaccine’s characteristics: it gives herd immunity and it will be included in the routine EPI after 2013. Despite steps that have been taken to ensure that medications are available in health facilities, the fact that treatment is given free of charge and there have been periodic vaccinations with polio vaccine, there is still a high mortality rate. This exceeds the expected rate of 10% and can be up to 25%. This situation affects not only the country's socio-economic and health sectors, but it also impedes the government of Benin's efforts to reach its internal goals for improving the health of the general population and that of children in particular. This affects its ability to reach the MDGs and primarily MDG No. 4. In addition Benin, like most countries, has implemented the GIVS and is committed to implementing the strategies suggested by it. Within this framework, the country has committed since the year 2000 to introduce new vaccines and new immunisation technologies and the cMYP strategies have been aligned with those of the GIVS. Hepatitis B (Hep B) vaccine and yellow fever vaccine (YFV) were introduced in an effective manner into the routine EPI starting in August 2002 with the assistance of the Global Alliance for Vaccines and Immunisation (GAVI). Based on this experience, after an evaluation of the morbidity burden related to infections with Haemophilus influenza, the country decided to introduce Hib vaccine. This was successfully done in June 2005 throughout the entire country of the Republic of Benin. At present, vaccination coverage paints a favorable picture of the country's efforts to improve vaccination coverage for this antigen. In less than two years, it has reached the same level of coverage that the DTP3 has. In addition, Benin has decided to submit an application to GAVI for the introduction of the pneumococcus vaccine which will occur this year. There are many vaccines to prevent meningitis. However, some of them have limited effectiveness. Specifically, the existing polio vaccines that are currently used against meningitis A cannot be given to children under two years of age. These vaccines are effective for only 2-3 years, they do not decrease carrying of the bacteria and they do not give herd immunity. The development and market availability of the new MenAfriVac conjugate vaccine have sparked renewed interest in the countries that are affected by this disease. The vaccine has been successfully introduced into some countries in the sub-region: Burkina Faso, Mali and Niger. Consequently, the government of Benin hopes to obtain GAVI's support for the introduction of the new conjugate meningitis A vaccine, MenAfriVac. The government of Benin considers this application to be of the utmost importance. As stated in the revised cMYP for 2009-2013, the government of Benin plans to organize a mass vaccination campaign to prevent these devastating meningococcal meningitis A epidemics. This will occur during the fourth quarter of 2012 in the five departments in Benin that are part of the meningitis belt (Atacora, Donga, Borgou, Alibori, Collines). From the programmatic point of view, the introduction of this vaccine is appealing because the country has the ability to effectively store and distribute it, and to ensure vaccination that meets the required safety standards. Benin has gained a great deal of experience in (i) implementing integrated surveillance of diseases and response (since 1998), as well as in specific aspects of case-based surveillance (AFP, measles, yellow fever), (ii) implementing additional polio vaccination campaigns, (iii) implementing measles vaccination campaigns (catch-up and booster) in the context of the accelerated measles control program, (iv) organizing response campaigns against numerous meningitis epidemics with polysaccharide vaccines, with administration coverage of more than 95% in the vaccinated areas. In the context this application, an initial MenAfriVac catch-up campaign plan has been prepared. This plan deals with Benin’s specific context, goals to be reached, primary strategies and activities including evaluation, and some critical implementation steps as well as the required budget. In accordance with the Yaoundé declaration of September, 2008, Benin has committed to transforming this document into a national strategic plan for reducing meningitis-related morbidity and mortality. Other strategic initiatives will be developed in an integrated manner along with the response activities that the country normally conducts. Based on the experience of previous campaigns conducted in Benin and the lessons that have been learned about the introduction of new vaccines, the following primary strategies have been selected. These will support the success of this inaugural introduction campaign for the conjugate meningitis A vaccine: - Improved coordination at all levels (National, departmental, municipal and local); - An improved micro-planning process at the decentralized level in order to better define roles and responsibilities and to provide improved assessment of resources; - Improved communication/social mobilization, especially in terms of locally-based communications with the involvement of local leaders; - Improved employee skills at all levels, through training related to the various components of the vaccination campaigns; - Effective tracking of vaccines and input items during the entire campaign; - Reliable management of vaccine stocks and monitoring of their use - Strict application of injection safety and waste management - Improved pharmaco-vigilance, specifically in terms of post-vaccination adverse events (PVAEs) and how to properly manage them; - Improved supervision, tracking and evaluation; - Improved case-by-case monitoring, taking experiences with measles, yellow fever and polio into account and using knowledge gained from the first countries to introduce MenAfriVac. In order to achieve this, guides and tools for case-by-case monitoring will be revised. Health and laboratory agents will benefit from trickle-down training. Reagents and laboratory equipment will be purchased. A state-of-the art system for transporting samples from health centers to laboratories will be implemented. The projected target population is 2,640,459 people between 1 and 29 years of age. The total quantity of vaccines required is 3,115,741 doses (with a 15% wastage rate, for a wastage factor of 1.18). The campaign will consist of one phase in November 2012. In light of the workloads facing the NDEPI and the NDPH, the introduction of this new vaccine and the efficient implementation of this campaign will require considerable technical support, consisting of the hiring of an international consultant to support coordination at the national level. The plan’s overall total cost (with investment included) is US $2,004,201, or US $0.64 per person vaccinated (the unit cost of the vaccine plus injection materials is estimated at US $0.67). The country’s financial contribution is 150 million CFA francs. This campaign requires substantial funding and will require advocacy with respect to international partners working in Benin (WHO, UNICEF, the European Union, The French Development Agency, the Belgian Development Agency, the Danish Development Agency, the Swiss Development Agency, the Japanese Development Agency, USAID, Rotary, the Red Cross, etc.) and economic players (mobile phone providers), para-governmental and private enterprises. The government of Benin has committed to contribution to operational costs in the amount of 150 million CFA francs from its own funds. In the context of the integrated epidemiologic surveillance program, the country has had standard operational procedure documents and revised and approved directives on meningitis since 2008. In addition, the laboratory network has been improved with trainings in 2009 and 2010, additional equipment and additional supervision tools. A case-by-case monitoring system will be implemented in order to measure this campaign’s impact. Using data from the first countries that have already introduced MenAfriVac, the guide and the case-by-case surveillance tools will be revised. The health and laboratory agents will undergo trickle-down training, equipment and reagents will be purchased and deployed to laboratories, and the method for sending samples to laboratories will be improved. We will use information technology (Internet and SMS) to transmit data.

Briefly describe (1) the vaccine wastage management plan, and (2) the cold chain capacity and indicate whether it is sufficient to store the new vaccines. Please indicate whether the acquisition of vaccines for this campaign will have consequences on the delivery and storage capacity for traditional vaccines and indicate how this situation will be managed. 1) Waste management: The safety boxes filled with used syringes will be collected and supervisors will take them to the closest health facilities that have incinerators. There are two types of incinerators available : De Monfort incinerators and incinerators manufactured by the DHAB (Direction de l’Hygiène et de l’Assainissement de Base). All sharps boxes and other waste (boxes, empty vials and packaging) will be destroyed by incineration at health centers that have incinerators. 2. Cold Chain The vaccine storage capacity available centrally and regionally makes it possible to accommodate routine vaccines and vaccines for the meningitis A campaign. Therefore in 2012 there will be no storage capacity gap, for the following reasons: - The routine EPI vaccines (including the pneumococcus vaccine) are delivered 4 times per year from the central level to the departments; - In addition, there will be three National Vaccination Days for polio vaccine and one day for the MenAfriVac vaccination (with a corresponding target of 28% of the total population): Population from 1-29 years of age in the departments of Atacora/Donga, Borgou/Alibori and Collines. Nevertheless, there are two constraints still to be managed: - The EPI uses a refrigerated truck to distribute vaccines; it was purchased in 2003 and it now breaks down frequently. A new refrigerated truck is very much needed in order to avoid delays in distributing vaccines to intermediate storage areas. - A new warehouse needs to be constructed in order to eliminate the 1,485 m3 deficit in ambient storage area for consumables and equipment. During the campaign, the vaccine will be distributed to the various departments using the refrigerated truck. Coolers will be used to transport the vaccines from the departmental locations to the municipalities. The regions will make use of these boxes and coolers available locally for transporting the vaccine to the health centers. Considering the availability in the field, it can be said that all the teams will each have a vaccine carrier for implementing the campaign. However, the mobile teams will need an additional vaccine carrier to store the vaccines and ice packs.

Table 4.1: Capacity and Cost (for Positive Storage)

|  |  | Formula | Year 1 2009 | Year 2 2010 | Year 3 2011 | Year 4 2012 | Year 5 2013 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| A | Yearly positive volume needs, including the new vaccine(s) (specify: __________) (liters or m3) | Product of total vaccine doses times unit packed volume of the vaccine | 23,554 liters | 23,703 liters | 40,432 liters | 48,869 liters | 51,007 liters |
| B | Annual positive capacity, including new vaccine (specify:________________) (liters or m3) | # | 15,000 liters | 15,000 liters | 15,000 liters | 15,000 liters | 15,000 liters |
| C | Estimate of minimum number of annual shipments required for actual cold chain capacity | A / B | 1.57 | 1.58 | 2.70 | 3.26 | 3.40 |
| D | Number of consignments/shipments per year | Based on national vaccine shipment plan | 4 | 4 | 4 | 4 | 4 |
| E | Difference (where applicable) | ((A / D) - B) | - 9,111 liters | - 9,074 liters | - 4,892 liters | - 2,783 liters | - 2,248 liters |
| O | Estimated cost for expansion | US$ | $0 | $0 | $0 | $0 | $0 |

MenAfriVac studies are ongoing, and an indication for use in children under one year of age is expected to be issued in January, 2014. Briefly describe when your country plans to introduce the conjugate Meningococcus A vaccine into the systematic vaccination schedule, how your country plans to fulfil its co-financing options for systematically introducing the Meningococcus A vaccine and other issues related to the systematic introduction that you are considering (refer to the cMYP).

The country plans to include the vaccine in the routine EPI as soon as it is available, using the same co-financing principles as the other new vaccines (pneumococcus in 2011).

Table 4.2: Evaluation of the Meningococcus Disease Burden (if available):

| Disease | Title of the assessment | Date | Outcomes |
| --- | --- | --- | --- |
| Meningitis | Epidemiology of bacterial meningitis in the Tanguieta health zone in Benin, 2004, Public Health Brief, D. Toboe | 2004 | - 102 cases of meningitis were reported - The three primary causative germs were: N. Meningitidis (50%) ; S. pneumoniae (37.2%) and H. influenzae (6.9%). |
| Meningitis | Meningitis surveillance data | 2009 | Cases: 416 Deaths: 64 Mortality: 15,4% Bacterio : N Meningitidis W135, H. influenzae and S. Pneumonia |
| Meningitis | Meningitis surveillance data | 2010 | Cases: 318 Deaths: 52 Mortality: 16% Bacterio : S. Pneumonia |
| Meningitis | Meningitis surveillance data | 2011 (weeks 1 to 13) | Cases: 113 Deaths: 25 Mortality: 22,1% Bacterio :H. influenzae and S. Pneumonia |

If new or under-used vaccines have already been introduced in your country or if you have already conducted vaccination campaigns, please give details of the lessons learned from the experience related to storage capacity, protection from accidental freezing, staff training, cold chain logistics, drop out rate, wastage rate, etc. and suggest improvements on these points:

| Lessons Learned | Solutions / Action Points |
| --- | --- |
| Micro-planning is an essential component of the success of vaccination campaigns | Particular emphasis should be placed on fundamental micro-planning with community involvement and with support from central and departmental teams. |
| Involvement of politicians at the highest level makes it possible to mobilize the resources that are required in the context of co-financing, and it also enables community mobilization. | Improved advocacy and social mobilization for effective involvement of higher authorities and other sectors, and the country's health development. |
| The need to join mass communication with increased continuous nearby communication and improved communication in order to manage risks and rumors. | Provide local communication in order for the populations to have more accurate knowledge of the new vaccines. Prepare for managing risks/rumors. |
| Selection and training of campaign stakeholders. | There will be particular emphasis placed on training of local staff (vaccinators, health and safety technicians, supervisors) |
| The need for local tracking of providers after training | Provide close monitoring of the providers' skills after training |
| A dynamic organizational committee (national, department and local) is crucial to the success and quality of a campaign to introduce a new vaccine. | Prepare a work plan including regular meetings to ensure the involvement of all EPI partners. Reports from these meetings will be sent to the ICC members and they will follow up on them. |
| The importance of implementing a PVAE management system | Timely implementation of PVAE management committees at all levels (central, departmental and remote). These committees must be trained and must have substantial tools. |
| The need to have a detailed logistics and waste management plan (as far as the municipal level) | - Improve stakeholder logistics capacity; - Inspect incinerators and carry out any necessary repairs |
| The need for monitoring during the campaign | Independent monitoring needs to be done early (beginning with the second day) |

# 5. Procurement and Management of New and Under-Used Vaccines

a) Please show how the support will be implemented and managed, including the purchase of vaccines (GAVI expects that the countries will buy their vaccines and injection supplies through UNICEF):

This arrangement is part of the current procurement mechanism for traditional vaccines and supplies through UNICEF in compliance with the terms of the memorandum of agreement for the provision of procurement services reached between UNICEF and Benin's Ministry of Health. Payment of Benin's share will be made during the second half of each year by bank wire transfer to UNICEF.

b) Please indicate when you intend to plan the conduct of the campaign (month and date) and how the campaign will be deployed,  e.g. different phases or one single time)

Fourth quarter of 2012, one phase, in the five departments in the meningitis belt. These are:  Collines, Borgou, Alibori, Atacora and Donga.

f) Please describe how the new vaccine's coverage will be monitored and declared (refer to the cMYP and the Meningitis A vaccine introduction plan)

Monitoring will be ensured through daily compilation and tracking of vaccination coverage data; daily meetings will be held between vaccinators and team supervisors in health units, and between supervisors at the municipal and departmental level. Quick studies will be conducted in the high-risk areas beginning with the third day after the campaign is implemented, and based on a protocol prepared at the central level.  In addition, a vaccination coverage study will be conducted at the end of the campaign.

# 6. Grants for the Operational Cost for Vaccination Campaigns

Table 6.5: calculation of lump-sum

| Year of New Vaccine introduction | Objective 1-29 years-old (see table 3.4) | Amount per dose in US $ | Total in US$ |
| --- | --- | --- | --- |
| 2012 | 2 640 459 | $ 0,30 | 934 722 |

In the following tables, please indicate how this amount will be used for financing the vaccination campaign introduction cost and also other essential activities. GAVI support will not be sufficient to cover all the needs, consequently please indicate in the following table how the remaining needs will be met and by whom (refer to the cMYP and/or to the Meningitis A conjugate vaccine introduction plan).

Table 6.6: Campaign Cost (and Financing; US$. Rate: ) 1US$= 475 F CFA)

| No. | Budget Line Item | Total needs |  | GAVI Support US$ | Other source: US$ |
| --- | --- | --- | --- | --- | --- |
|  |  | CFA | US$ |  |  |
| 1 | Functioning of the national organization and coordination committee (management of members and various activities) and ICC members | 5 000 000 | 10 526 |  | 10 526 |
| 2 | Functioning of the organizational committee, decentralized level (department and municipality) | 4 550 000 | 9 579 |  | 9 579 |
| 3 | Preparation meeting for the mass vaccination plan, and tailoring of the case-by-case monitoring guide | 10 000 000 | 21 053 | 21 053 |  |
| 4 | Preparation meetings for the communication plan, including communication tools | 10 000 000 | 21 053 | 21 053 |  |
| 5 | Municipal micro-planning meetings | 5 000 000 | 10 526 | 10 526 |  |
| 6 | Departmental micro-plan summary meeting | 11 000 000 | 23 158 | 23 158 |  |
| 7 | National micro-plan summary | 5 000 000 | 10 526 | 10 526 |  |
| 8 | Department planning meeting | 11 000 000 | 23 158 |  | 23 158 |
| 9 | National planning meeting | 5 000 000 | 10 526 |  | 10 526 |
| 10 | Copying of the case by monitoring plan and guide | 2 000 000 | 4 211 | 4 211 |  |
| 11 | Data collection | 1 000 000 | 2 105 | 2 105 |  |
| 12 | Copying of documents and other central office supplies | 5 000 000 | 10 526 |  | 10 526 |
| 13 | Technical input | PM | 0 | 0 | 0 |
|  | Sub-total 1: Coordination-planning and tracking | 74 550 000 | 156 947 | 50 526 | 106 421 |
| 14 | Training of departmental trainers | 11 000 000 | 23 158 |  | 23 158 |
| 15 | Trickle-down training sessions for health agents, volunteers and team supervisors | 46 519 600 | 97 936 |  | 97 936 |
|  | Sub-total 2: Training | 57 519 600 | 121 094 |  | 121 094 |
| 16 | Transportation of vaccination teams | 39 690 000 | 83 558 |  | 83 558 |
| 17 | Transportation of team supervisors | 6 240 000 | 13 137 |  | 13 137 |
| 18 | Transportation of municipal supervisors | 6 600 000 | 13 895 |  | 13 895 |
| 19 | Transportation of departmental supervisors | 4 500 000 | 9 474 |  | 9 474 |
| 20 | Transportation of national consultants | 1 500 000 | 3 158 |  | 3 158 |
| 21 | Transportation for resupplying municipalities with vaccines | 2 009 478 | 4 230 |  | 4 230 |
| 22 | C/SRFM transportation of DDS | 800 000 | 1 684 |  | 1 684 |
| 23 | Fuel for supervision and training for the campaign at the central level | 8 000 000 | 16 842 |  | 16 842 |
| 24 | Fuel for trips to collect supporting documents (financial, central level) | 800 000 | 1 684 |  | 1 684 |
| 25 | Rental of 2 vehicles | 7 200 000 | 15 158 | 15 158 |  |
| 26 | Rental of motorcycles and car/motorcyle maintenance | 6 050 000 | 12 737 | 12 737 |  |
| 27 | Vaccine supply (central and departmental levels) | 2 000 000 | 4 211 |  | 4 211 |
|  | Sub-total 3: Transportation | 85 389 478 | 179 767 | 27 895 | 151 872 |

| 28 | Implementation of communication activities at the central level using media. Copying of media materials and official launch | 20 000 000 | 42 105 |  | 42 105 |
| --- | --- | --- | --- | --- | --- |
| 29 | Social mobilization, town criers (local communications) | 12 445 000 | 26 200 |  | 26 200 |
| 30 | Municipal social mobilization | 3 300 000 | 6 947 |  | 6 947 |
| 31 | Departmental social mobilization | 1 000 000 | 2 105 |  | 2 105 |
|  | Sub-total 4: Communication and social mobilisation | 36 745 000 | 77 358 |  | 77 358 |
| 32 | Volunteer management | 123 680 000 | 260 379 | 260 379 |  |
| 33 | Health agent (vaccinators) management | 262 820 000 | 553 305 | 553 305 |  |
| 34 | Management of team supervisors | 26 520 000 | 55 832 |  | 55 832 |
| 35 | Management of municipal supervisors | 6 600 000 | 13 895 |  | 13 895 |
| 36 | Management of municipal drivers | 3 300 000 | 6 947 |  | 6 947 |
| 37 | Management of departmental supervisors | 13 500 000 | 28 421 |  | 28 421 |
| 38 | Management of departmental drivers | 4 500 000 | 9 474 |  | 9 474 |
| 39 | Management of national consultants | 3 000 000 | 6 316 |  | 6 316 |
| 40 | Management of national consultant drivers | 2 000 000 | 4 211 |  | 4 211 |
| 41 | Management C/SRFM and collaborator | 900 000 | 1 895 |  | 1 895 |
| 42 | Management of C/SRFM drivers | 300 000 | 632 |  | 632 |
| 43 | Management of municipal accountant | 1 402 500 | 2 953 |  | 2 953 |
| 44 | Management of data managers | 1 200 000 | 2 526 |  | 2 526 |
| 45 | Managements of national supervisors | 12 000 000 | 25 263 |  | 25 263 |
| 46 | Management of national supervisors’ drivers | 12 000 000 | 25 263 |  | 25 263 |
| 47 | Management of members of the finance subcommittee | 600 000 | 1 263 |  | 1 263 |
| 48 | Management of drivers for the members of the finance subcommittee | 300 000 | 632 |  | 632 |
|  | Sub-total 5: Personnel management | 474 622 500 | 999 205 | 813 684 | 185 521 |
| 49 | Waste management (management of operators, supervision or tracking, incineration oversight) in the 5 departments | 6 000 000 | 12 632 |  | 12 632 |
| 50 | Implementation of case by case monitoring activities and support for laboratories | 17 000 000 | 35 789 |  | 35 789 |
| 51 | Monitoring/investigation and management of PVAEs | 50 000 000 | 105 263 |  | 105 263 |
| 52 | Purchase of cotton rolls | 2 640 459 | 5 559 |  | 5 559 |
|  | Sub-total 6: Epidemiologic and injection safety monitoring | 75 640 459 | 159 243 |  | 159 243 |
| 53 | Purchase of a refrigerated truck | 40 000 000 | 84 211 |  | 84 211 |
| 54 | Construction of a dry warehouse at the central level | 40 000 000 | 84 211 |  | 84 211 |
|  | Sub-total 7: Investment | 80 000 000 | 168 421 |  | 168 421 |
| 55 | Vaccination card order | 47 528 262 | 100 059 |  | 100 059 |
| 56 | Conducting monitoring and evaluation for the campaign | 20 000 000 | 42 105 | 42 105 |  |
|  | Sub-total 8: Monitoring and evaluation | 67 528 262 | 142 165 | 42 105 | 100 060 |
|  | Total operational costs | 871 995 299 | 1 835 780 | 934 210 | 901 570 |
|  | Total investment costs | 80 000 000 | 168 421 |  | 168 421 |
|  | GRAND TOTAL | 951 995 299 | 2 004 201 | 934 210 | 1 069 991 |

  - Please complete the banking form (annex 1) if necessary

Please briefly describe who will finance the operational costs not financed by GAVI. If the government is the source of financing, please confirm that this is in fact entered in the health budget. If you are looking for other sources of financing, please indicate and confirm their commitments.

This campaign requires substantial funding and will require advocacy with respect to international partners working in Benin (WHO, UNICEF, the European Union, the French Development Agency, the Belgian Development Agency, the Danish Development Agency, the Swiss Development Agency, the Japanese Development Agency, USAID, Rotary, the Red Cross, etc.)  and economic players (mobile phone providers), para-governmental and private enterprises.

The government of Benin has committed to contribution to operational costs in the amount of 150 million CFA francs from its own funds.

# 7. Additional comments and recommendations from the National Coordinating Body (ICC/HSCC)

Recommendations

- Conduct a meningococcal meningitis A vaccination campaign (MenAfriVac) in 5 of the country’s departments located in the meningitis belt (Atacora, Donga, Collines, Borgou, Alibori);

- Set up a national MenAfriVac organization committee;

- Prepare a ministerial decree creating the National PVAE Monitoring Committee;

- Immediately begin the process of registering the vaccine in Benin by the ANR;

- Advocate with other economic partners and operators in order to support the State's contribution (MenAfriVac Organization Committee)

- Ensure that the Minister of Health and the Minister of Finance sign during the week of May 3-6.

- Emphasis on micro-planning and the efficient implementation of activities;

# 8. Documents required for each type of support

| Document | DOCUMENT NUMBER | Duration * |
| --- | --- | --- |
| Complete Multiyear Plan (CMYP) MenAfriVac introduction plan (if not already included in the cMYP) | 1 2 | 2009-2013 2012 |
| endorsed minutes of the National Coordinating Body meeting where the GAVI proposal was endorsed | Not available |  |
| endorsed minutes of the ICC/HSCC meeting where the GAVI proposal was discussed | 3 | 28 April 2011 |
| Minutes of the three most recent ICC/HSCC meetings | 4 5 6 |  |
| ICC/HSCC workplan for the next 12 months | Not available |  |
| The calculation sheet required for the vaccine | 7 |  |

* Please indicate the duration of the plan / assessment / document where appropriate

Annex 1 - Banking Form

| Banking form |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| SECTION 1 (To be completed by payee) |  |  |  |  |  |  |  |
| Again we indicate that without the complete and accurate bank information (IBAN, SWIFT code, bank contact information and the corresponding bank in the USA, the bank transfer will prove to be impossible and that can cost needless delays. |  |  |  |  |  |  |  |

Annex 2: GAVI Alliance general terms

FINANCING USED SOLELY FOR APPROVED PROGRAMMES

The candidate country ("Country") confirms that any financing granted by the GAVI Alliance in conjunction with this application will be used and allocated solely for the purpose of conducting the program(s) described in this application. Any significant change to the approved program(s) must be examined and approved by the GAVI Alliance in advance.  Any financing decision on this proposal is made at the discretion of the GAVI Alliance council and depends on the IEC process and funds availability.

AMENDMENT OF THIS PROPOSAL

The Country shall inform the GAVI Alliance through its Annual Status Report of its desire to propose a modification of any kind to the description of the program(s) in this proposal. The Country shall produce documents supporting any modification approved by the GAVI Alliance and this proposal will be amended as a consequence.

RESTITUTION OF THE FUNDS

The Country agrees to return to the GAVI Alliance any financing amount which is not used on behalf of the program(s) described in this proposal. Unless the GAVI Alliance decides otherwise, reimbursement must be made by the Country in US dollars within sixty (60) days following receipt by the Country of the request from the GAVI Alliance and will be deposited in the account(s) indicated by the GAVI Alliance.

SUSPENSION/TERMINATION

GAVI Alliance may suspend all or part of its financing to a Country if it has reason to suspect that the funds have been used for any purpose other than for the programs described in this proposal or an amendment to this proposal approved by GAVI. GAVI Alliance reserves the right to terminate its support to the Country for the programs described in this proposal if GAVI Alliance receives confirmation of abusive use of the funds granted by GAVI Alliance.

ANTICORRUPTION

The Country confirms that the funds provided by the GAVI Alliance will not be offered to a third party by the Country and the country will not seek on the basis this proposal a gift, payment or other direct or indirect advantage which could be interpreted as an illegal practice or an act of corruption.

AUDITS AND RECORDS

The Country will conduct a financial audit annually and share the results with the GAVI Alliance on the first request. The GAVI Alliance reserves the right for itself or through an agent to conduct audits or any other form of evaluation of the financial management in order to assure itself of the financial accountability for the funds deposited on behalf of the Country.

The Country shall retain precise accounting records which documents the manner in which the GAVI Alliance funds were used. The Country will keep up to date accounting records in accordance with its government-approved accounting standards for at least three years after the date of last disbursement of GAVI Alliance funds. In case of recourse for abusive use of the funds, the Country will retain these records until the final conclusion of the audit. The Country agrees not to raise privilege with the GAVI Alliance over the documents in conjunction with any audit.

CONFIRMATION OF LEGAL VALIDITY

The Country and the signatories for the government confirm that this proposal is accurate and correct and constitutes an irrevocable legal obligation on the Country, under the terms of the Country's laws, to conduct the programs described in this proposal.

CONFIRMATION OF COMPLIANCE WITH THE GAVI ALLIANCE ACCOUNTING TRANSPARENCY AND RESPONSIBILITY POLICY

The Country confirms that it is been informed of the GAVI Alliance accounting transparency and responsibility (ATR) policy and will comply with its requirements.

ARBITRATION

Any dispute between the Country and the GAVI I Alliance which arises from this proposal or refers to this proposal and cannot be amicably resolved in a reasonable interval will upon the request of either the GAVI Alliance or the country be subject to arbitration. The arbitration will be conducted according to the UNCITRAL Arbitration Rules in force at that time. The parties agree that they shall be bound by the arbitration sentence as a definitive settlement of the dispute. The forum shall be Geneva, Switzerland. The language of the arbitration shall be English.

For any dispute involving a contested amount which is less than or equal to US$100,000, the single arbitrator shall be designated by the GAVI Alliance. For any dispute whose contested amount is over US$100,000, three arbitrators shall be designated as follows: The GAVI Alliance and the Country shall each designate one arbitrator and these two arbitrators shall by mutual agreement designate a third arbitrator who will preside over the panel.

The GAVI I Alliance shall not be responsible to the Country for any recourse or loss relative to the programs described in this proposal, including (list not exhaustive) financial losses, appeal on suspicion, property damage, physical lesions to people or death.  The Country is solely responsible for all aspects of managing and implementing the programs described in this proposal.