Revision  4

August  2002

The Government of

The Republic of BENIN

Proposal for support submitted to the

Global Alliance for Vaccines and Immunization (GAVI)

and the Vaccine Fund

This document is accompanied by an electronic copy on diskette for your convenience. Please return a copy of the diskette with the original, signed hard-copy of the document to

GAVI Secretariat; c/o UNICEF, Palais des Nations, 1211 Geneva 10, Switzerland.

Enquiries please to: Dr Tore Godal, tgodal@unicef.org or representatives of a GAVI partner agency.  All documents and attachments must be submitted in English or French.

# Executive Summary

# Synopsis of the proposal including the specific requests for support from GAVI and the Vaccine Fund. The figures essential for the calculation of award amounts should be presented here, including: baseline data, current DTP3 coverage and targets for increased coverage, strategies for reaching all children, requested number of doses of vaccine(s) and their presentations (drawn from the tables in this form). Summarise also the nature of ICC participation in developing this proposal.

The Republic of Benin requests the support of the Global Alliance for Vaccines and Immunization for the introduction of the pentavalent vaccine (DTP-HepB+Hib) into EPI and for injection safety.

Coverage rates per antigen for 2003, based on routine data, were as follows:

DTP		88%

HepB3		81%

YF		83%

OPV3		88%

MEAS		83%

Coverage goals are as follows:

| Year | Coverage goals per antigen |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Vit A Infants (>6mos) |  | Vit A Mothers (<6 wks after delivery) |  | DTP3 |  | HepB3 |  | Penta |  | MEAS |  | YF |  | BCG |  |
| 2001 | NA |  | NA |  | 84% |  | 83% |  | NA |  | 81% |  | NA |  | NA |  |  |
| 2002 | NA |  | NA |  | 93% |  | 83% |  | NA |  | 88% |  | 27% |  | NA |  |  |
| 2003 | NA |  | NA |  | 88% |  | 81% |  | NA |  | 83% |  | 83% |  | NA |  |  |
| 2004 | 50% |  | 30% |  | 93% |  | 92% |  | SO |  | 86% |  | 86% |  | 100% |  |  |
| 2005 | 60% |  | 50% |  | NA |  | NA |  | 85% |  | 90% |  | 90% |  | 100% |  |  |
| 2006 | 80% |  | 70% |  | NA |  | NA |  | 85% |  | 91% |  | 91% |  | 100% |  |  |
| 2007 | 85% |  | 75% |  | NA |  | NA |  | 90% |  | 92% |  | 92% |  | 100% |  |  |
| 2008 | 85% |  | 80% |  | NA |  | NA |  | 90% |  | 93% |  | 93% |  | 100% |  |  |
| 2009 | 90% |  | 85% |  | NA |  | NA |  | 93% |  | 94% |  | 94% |  | 100% |  |  |
| 2010 | 95% |  | 90% |  | NA |  | NA |  | 95% |  | 95% |  | 95% |  | 100% |  |  |

The coverage rates for this table have been projected on the basis of current EPI performance.  As the pentavalent vaccine is to be introduced in January 2005, we aim to achieve a coverage rate of 85% during the first two years.

The quantities of vaccines requested for meet these goals are as follows:

| Year | Antigènes |  |  |
| --- | --- | --- | --- |
|  | HepB (10 doses) | VF (10 doses) | DTP-HepB + Hib (2 doses) |
| 2004 | 774,000* | 152,000* | NA |
| 2005 | NA | 529,808 | 1,240,021 |
| 2006 | NA | 497,794 | 1,269,217 |
| 2007 | NA | 461,885 | 1,320,474** |
| 2008 | NA | 482,080 | 1,363,560 |
| 2009 | NA | 471,656 | 1,408,161 |
| 2010 | NA | 492,165 | 1,451,068 |

* Overview of new vaccine supplies (2004) Bénin, cf. lettre GAVI /03/169/jj of 09/02/04

* From 2007 onwards, with a view to ensuring the continuity of services, Benin plans to gradually cover the costs of the pentavalent vaccine as per a proposal that will be defined in the financial viability scheme.

The coverage rates in this table were set taking two factors into consideration: current EPI performance levels, and the target populations to be reached calculated on the basis of the results of the 2002 census.

As far as the introduction of the DTP-HepB+Hib (pentavalent) vaccine is concerned, a WHO support mission was in Benin from 22 March to 2 April 2004 to assist with the preparation of the following documents:

- The plan of introduction for the pentavalent vaccine DTP-HepB-Hib) into EPI in 2005:

- The national plan of action for injection safety;

- The national policy statement on injection safety and the management of used injection materials.

A small team tasked by the ICC drafted the present proposal for support submitted to GAVI and the Vaccine Fund, based on information taken from the three (3) documents mentioned above.

The Inter-Agency Coordinating Committee is thus entirely committed to the process of requesting GAVI support and is hence involved in the management and follow-up process.

# Signatures of the Government and the Inter-Agency Co-ordinating Committee

The Government of the Republic of Benin commits itself to developing national immunization services on a sustainable basis in accordance with the multi-year plan presented with this document. Districts’ performance on immunization will be reviewed annually through a transparent monitoring system. The Government requests that the Alliance and its partners contribute financial and technical assistance to support immunization of children as outlined in this application.

Signature:	…………………………………………...

Title:	Minister of Public Health…………………………………………...

Date:	15 April 2004…………………………………………...

The GAVI Secretariat is unable to return submitted documents and attachments to individual countries.  Unless otherwise specified, documents may be shared with the GAVI partners and collaborators.

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this proposal on the basis of the supporting documentation that is attached. Signatures for endorsement of this proposal do not imply any financial (or legal) commitment on the part of the partner agency or individual:

| Agency/Organisation | Name/Title | Date Signature |
| --- | --- | --- |
| WHO | Lazare LOCO WHO ResRep |  |
| UNICEF | Philippe DUHAMEL UNICEF ResRep |  |
| USAID | Modupé BRODERICK USAID Directcor |  |
| AMP | Aristide APLOGAN AMP Rep. in Benin |  |
| Ministry of Finance and the Economy | Isaïe ZEKPA Representative/MFE |  |
| Ministry for Planning and Development | Françoise ALODJOGBE Rep/MPD |  |
| National Polio Plus Commission of Rotary International | Ashock MIRCHANDANI Vice-President of the NPPCB |  |
| EPI Foundation | Joséphine ABALLO President, EPI Foundation Benin |  |

In case the GAVI Secretariat have queries on this submission, please contact :

Name: Jacques P. TOSSOU………………	Title/Address: EPI-SSP Director……….

Tel.No.: (229) 95-61-08………….   		            ………………………………..

Fax No.(229) 31-61-54………….. 		            ………………………………..

E-mail: jptossou@internet.bj…………                         ……………………………….

Alternative address:

Name: Abdou Moudjibi CHITOU…………	Title/Address: Head Immunization Department.

Tel.No.: (229) 31-61-54/31-23-29

(229) 90-33-05        ………………………………..

Fax No.(229) 31-61-54………….. 		            ………………………………..

E-mail: mchitou@internet.bj                         ……………………………….

Other address: pevben@leland.bj

- Immunization-related fact sheet

| Table 1: Basic facts (For the year 2003 or most recent; specify dates of data provided) |  |  |  |
| --- | --- | --- | --- |
| Population | 7,182,2902 | GNP per capita | $US 3503 |
| Surviving Infants* | 262,065 | Infant mortality rate | 89.1 / 10004 |
| Percentage of GDP allocated to Health | 7.14%5 | Percentage of Government expenditure for Health Care | 7.68%6 |

* Surviving infants = Infants surviving the first 12 months of life

| Table 2: Trends of immunization coverage and disease burden by 12 months of age (as per annual WHO/UNICEF Joint Reporting Form on Vaccine Preventable Diseases) |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Trends of immunization coverage (in percentage) |  |  |  |  |  |  |  |  | Vaccine preventable disease burden |  |  |
| Vaccine |  |  | Reported |  | Survey |  |  |  | Disease | Number of reported cases |  |
|  |  |  | 2000 | 2001 | 2000 | Age group | 2001 | Age group |  | 2000 | 2001 |
| BCG |  |  | 106 | 105 |  |  |  |  | Tuberculosis | 51* |  |
| DTP | DTP1 |  | 110 | 104 |  |  |  |  | Diphtheria | 0 | NA |
|  | DTP3 |  | 93 | 88 |  |  |  |  | Pertussis | 47 | NA |
| OPV3 |  |  | 93 | 88 |  |  |  |  | Polio | 0 | 2* |
| Measles |  |  | 88 | 83 |  |  |  |  | Measles | 610** | 73* |
| TT2+ (Pregnant women) |  |  | 75 | 72 |  |  |  |  | NN Tetanus | 89* | NA |
| Hib3 |  |  | NA | NA |  |  |  |  | Hib | NA | 13* |
| Yellow Fever |  |  | 27 | 83 |  |  |  |  | Yellow fever | 66** | 57** |
| HepB3 |  |  | 15 | 81 |  |  |  |  | hepB seroprevalence (if available) | NA | NA |
| Vit A supplementation |  | Mothers ( < 6 weeks after delivery ) | NA | NA |  |  |  |  |  |  |  |
|  |  | Infants ( > 6 months) | NA | NA |  |  |  |  |  |  |  |

* Confirmed cases

** Suspected cases

The best official estimate: Indicate the best official estimate of coverage among infants as reported in WHO/UNICEF Joint reporting form. Provide explanatory comments on why these are the best estimates: ………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………

2Projected population based on 2002 census – INSAE, March 2004

3INSAE social indicators

4EDSB-II document, 2001

5Finance Act 1999

6Finance Act 2003

- Summary of health system development status relevant to immunization:

For the period from 2002 to 2006, the national policy and strategies for the development of the health sector comprise the following five strategic thrusts:

- Restructuring the base of the health pyramid and strengthening health coverage;

- Ensuring funding for the health sector and improving resource management;

- Preventing and controlling the main diseases with a view to improving the quality of care;

- Preventing and controlling high-priority diseases;

- Promoting family health.

The development of immunization activities comes under point No. 3.  With regard to implementation, several measures and reforms have been introduced and are being pursued, including:

  - The establishment of the National Department for the Expanded Program on Immunization and Primary Health Care

  - The strengthening of community participation and funding via the Bamako Initiative (e.g. revitalizing monitoring activities and charging for services);

  - The Vaccine Independence Initiative (VII), whereby the State is to gradually take over EPI vaccine procurement, a policy that reflects the desire at the highest level to protect vulnerable segments of the population;

  - Promotion of the partnership between public and private sectors that facilitates the development of immunization activities via private health groups;

  - Introduction of a national cell for integrated disease surveillance and counterattack;

  - Organization of mass immunization campaigns within the framework of initiatives to eradicate/eliminate diseases (polio, measles and tetanus).

The main results obtained are as follows:

-	A political commitment, as reflected by the Vaccine Independence Initiative;

-	The smooth functioning of routine EPI (maintenance of immunization coverage at around 80% since 1994);

-	Proper functioning of the cold chain; some 80% of which was replaced in 1999;

-	Immunization coverage for DTP3, which was very low in the 80s (around 12%), has improved considerably and is now at around 80%, a factor that has certainly helped to improve the health status of children;

-	An 86% drop in the number of cases of measles in 2003;

-	A 93% drop in the number of measles-related deaths;

-	A drop to 0 cases of polio for two straight years (2001 and 2002).

| - Attached are the relevant section(s) of strategies for health system development | Document number………….. |
| --- | --- |

- Policies and strategies for the development of the health sector 2002 – 2006	Doc. 1

(Excerpt)

- Structure of government health services and linked with immunization

- services (attach organizational chart)						Doc. 2

- Joint WHO/UNICEF reporting form for vaccine-preventable

diseases for Jan-Dec 2003							Doc 3

# Profile of the Inter Agency Co-ordinating Committee (ICC)

Various agencies and partners (including NGOs and Research Institutions) that are supporting immunization services are co-ordinated and organised through an inter-agency co-ordinating mechanism that is referred to in this document as ICC.

- Name of the ICC: Inter-Agency Coordinating Committee for the Expanded Program on Immunization (ICC-EPI)

- Date of constitution of the current ICC: 23 July 2003…………………………………………………

- Organisational structure (e.g., sub-committee, stand-alone):multisectoral…………………………….

One Technical Committee

Three Commissions (Immunization and Surveillance, Social Mobilization, Logistics)

- Frequency of meetings: one meeting per quarter and special meetings on request

Monthly meetings for the Technical Committee and each commission……………………

- Composition:

| Function | Title / Organization | Name |
| --- | --- | --- |
| Chair | Minister of Public Health | Yvette Céline SEIGNON KANDISSOUNON |
| Secretary | National Director – EPI/PHC | Jacques Philippe TOSSOU |
| Rapporteur | Head, Immunization Dept/MPH | Abdou Moudjibi CHITOU |
| Members | - WHO ResRep - UNICEF ResRep - World Bank ResRep - Director, USAID - Vice-President, National Polio Plus Commission of Rotary International - EU Representative - Rep of the Dept for Cooperation and Cultural Action - Rep of Belgian technical cooperation - Rep of the Swiss Technical Cooperation Department - Rep of German technical cooperation - Rep of the Association for the Promotion of Preventive Medicine (AMP) - President of the EPI Foundation - Ministry of Finance and the Economy - Demographics/Ministry for Planning - Director of Programming and Planning/MP - Director of Financial and Material Resources/MP …………. | Lazare LOCO Philippe DUHAMEL Dariétou GAYE Modupé BRODERICK Ashock MIRCHANDANI Stéphanie BAUD Benoît DECAMPS Jeanine SIMBIZI Ursula FUNK Régina ECKER Aristide APLOGAN Joséphine ABALLO Isaïe ZEKPA Françoise ALODJOGBE Latifou SOUMANOU Théodore HOUSSOU-FREJUS |

- Major functions and responsibilities of the ICC:

The Inter-Agency Committee for EPI provides a framework for partnership between the Government and the cooperation agencies in charge of the scheduling, implementation and follow-up of immunization activities.  As such, it is responsible for:

-	Helping to define EPI policy guidelines;

-	Helping to prepare EPI strategic plans and annual plans;

-	Providing the necessary resources both inside and outside the country for the implementation of the programs designed;

-	Following up the implementation of these programs;

-	Periodically examining program execution reports;

-	Ensuring optimum use of the resources mobilized;

-	Helping the National EPI-PHC Department organized periodic program reviews.

The ICC-EPI is the body that supervises the management of the national and international resources earmarked for immunization, including those of the Vaccine Fund within the framework of the Global Alliance for Vaccines and Immunization (GAVI).

- Three major strategies to enhance the ICC’s role and functions in the next 12 months:

-	Preparation of a work plan for all ICC-EPI structures;

-	Advocacy efforts with a view to the mobilization of EPI resources and aimed at donors, including GAVI;

-	Stronger support for the management of routine EPI (in accordance with the recommendations of the last internal EPI review)

- Three main indicators (in addition to DTP3 coverage) that are chosen by the ICC to monitor implementation of this proposal:

-	Proportion of zero doses;

-	Wastage rates between DTP1 and DTP3;

-	Coverage rates for new antigens (YF and HepB)

Attached are the supporting documents:

| - Terms of reference of the ICC | Document number 4. |
| --- | --- |
| - ICC’s workplan for the next 12 months | Document number 5. |
| - Minutes of the three most recent ICC meetings or of any other meetings in which partners participated that concerned improving and expanding the national immunization program | Document number 6. |

# Immunization services assessment(s)

Reference is made to the most recent assessments of the immunization system that have been completed within the three years prior to the submission of this proposal.

- Assessments, reviews and studies of immunisation services for current reference:

| Title of the assessment | Main participating agencies | Dates |
| --- | --- | --- |
| External EPI review | AMP/CVP, WHO, UNICEF, USAID, PATH, PBA/PHC | Apr 2001 |
| Evaluation of mass measles immunization campaign in the departments of l’Atacora/Donga and Zou/Collines (pilot phase) | WHO, UNICEF | Jan 2002 |
| Evaluation of management of biomedical wastes | WHO, UNICEF, USAID | Apr 2003 |
| Evaluation of mass measles immunization campaign in the departments of l’Atlantique/Littoral, Ouémé/Plateau, Borgou/Alibori and Mono/Couffo | WHO, UNICEF | Feb 2003 |
| Evaluation of the impact of introduction of new HepB and YF vaccines into routine EPI | WHO | May 2003 |
| Estimate of additional costs for introduction of new vaccines into routine EPI | WHO | June 2003 |
| Evaluation of immunization coverage of the 2002 Polio NIDs | WHO, UNICEF | Nov 2002 |
| Evaluation of immunization coverage of the 2003 Polio NIDs | WHO, UNICEF | Nov 2003 |
| Evaluation of immunization coverage of the 2004 Polio NIDs | WHO, UNICEF | Mar 2004 |

- The three major strengths identified in the assessments:

-	It was unanimously agreed that there had been no opposition of any kind to the introduction of new vaccines and that the introduction had gone without any major hitches;

-	The agents surveyed were familiar with the different types of APIEs and of the relevant rules to be followed;

-	The external EPI review conducted in 2001 showed a health pyramid management structure that is favourable to EPI execution; institutionally speaking, it also noted that the management of peripheral health groups was also favourable to EPI execution.

- The three major problems identified in the assessments:

-	32% of the districts have DTP3 rates below 80%;

-	Wastage rates between DTP1 and DTP3 exceed 10% in 76.62 of the districts;

-	The external review conducted in 2001 showed that agents in one-third of the centers were not reaching the target populations.

- The three major recommendations in the assessments:

-	Prepare microplans in each department, district by district, for the collection of sharp wastes (safety boxes) and for the routine care activities performed by the different health groups in order to ensure their proper destruction by means of DeMonfort incinerators;

-	Reduce vaccine wastage by relying on an open vial policy and by persuading suppliers to provide vaccines in packs of 10 doses maximum;

-	Devote the bulk of the funds freed up from debt relief to achieving vaccine independence.

- Attached are  complete copies (with an executive summary) of:

| - the most recent assessment reports on the status of immunization services (external EPI review) | Document number 7.. |
| --- | --- |
| - a list of the recommendations of the assessment reports with remarks on the status of their implementation i.e. included in work-plan, implemented, not implemented, in progress…. | Document number 8.. |

| Recommendations | Implementation | Not applied | Under way |
| --- | --- | --- | --- |
| - Draft an EPI strategic policy document - Include EPI results as performance indicators for health zones - Increase the human, material and logistic resources of the immunization services - Make permanent the process for drafting three-yearly plans and yearly internal reviews - Transmit the results of internal EPI reviews to partners in support of advocacy efforts - Strengthen the role and activities of the ICC with regard to routine immunization - Ensure that all partners are represented on the ICC - Examine the possibility of turning the SVAC into a national cell attached to the Minister - Step up the process of EPI decentralization - Reduce vaccine wastage by relying on an open vial policy and by persuading suppliers to send vials of 10 doses maximum. - Ensure earliest possible ordering of vaccines nationwide. - Ensure that the CAME is involved in the choice of supply sources. - Cut supervision costs and shift training to actual immunization players (starting with nurse’s aides) - Cut NID staffing costs - Entrust cold chain maintenance to the private sector and motorcycle maintenance to health agents (review and harmonize motorcycle contracts nationwide) - Set up integrated workshops in zones with no technical facilities. - Have the COGEC/COGES provide funding for maintenance - Have the COGEC/COGES provide funding for depreciation - For the two previous points, establish a solidarity mechanism for contributions between “rich” centers and “poor” centers - Set up depreciation savings accounts to avoid hoarding of funds set aside for this purpose - Transfer the wage bill borne by the health groups to the MPH (bearing in mind the constraints linked to the Structural Adjustment Program) - Use the first funds freed up via debt relief to achieve vaccine independence - Improve the skills of immunizers by training/retraining all of them (including nurse’s aides) - Increase the number of immunizers by adding qualified healthcare workers - Lower drop-out rates by strengthening the advance strategy, reducing missed opportunities, actively looking for those who drop out, and relying on daily immunization - Reduce the gap between doses administered and valid doses by informing, training and supervising immunizers in the importance of respecting the vaccine timetable - Reduce information loss by making parents aware of the need to keep immunization records and immunizers of the need to enter all doses administered in these records - Reconstruct the TT vaccine history of women during prenatal consultations - Explore in greater depth the causes of poor EPI performance in the departments of l’Alibori, l’Atacora, l’Atlantique, le Borgou and le Couffo - Administer TT vaccines to women of childbearing age, relying on the advanced strategy - Train/retrain all immunizing staff (including nurse’s aides and recently recruited healthcare workers) in various EPI aspects, in particular the open vial policy, disease surveillance and APIEs - Revitalize the supervision process within the health groups by training staff in supervision techniques, by introducing post-supervisory feedback and by monitoring all immunization-related areas - Relaunch advanced strategy activities in health groups that do not use them - Prepare and distribute technical sheets on various EPI management aspects - Get all categories of healthcare workers involved in preparing and implementing the plan of action at the local level - Improve the transmission of reports on surveillance of EPI target diseases by simplifying the circuit (sources, addressees) and by promoting the use of modern communication media (fax, e-mail, RAC) - Make available and distribute widely standardized and layman’s definitions of cases for EPI target diseases - Make available at the operational level kits for taking samples and iceboxes for transporting samples of biological products (stools, blood, LCR) - Continue efforts to equip all health groups with rolling stock for the implementation of activities - Update and circulate widely the policy document on injection safety and the related guidelines and technical sheets (including the recording and reporting of APIEs and the destruction of use injection materials) - Ensure the systematic use of injection safety material in routine EPI (AD syringes and safety boxes) - Improve the quality of vaccine handling and cold chains by: - Getting NGOs, women’s associations, leaders, religious figures and healers involved in social mobilization - Strengthening cooperation between health centers and social promotion centers and NGOs with regard to immunization and social mobilization - Further increasing awareness via community radio and the use of traditional media - Ensuring regular awareness-building via the media (particularly community radio) and interpersonal communication so as to strengthen routine EPI - Promoting awareness-building among specific groups (especially reluctant groups) via mothers already convinced of the benefits of immunization - Drafting targeted messages that take people’s prior knowledge into consideration - Keeping behavioral determinants in mind when preparing messages and conducting pretests at every site - Ensuring injection safety by training all staff involved in immunization - Organizing and improving follow-up of side effects linked to immunization - Giving the public sufficient advance warning before immunization sessions - Taking due account of the availability of the public when programming immunization sessions using advanced strategies - Pencilling in appointments on the flyleaf of the immunization record, in capital letters (to be updated at each session) - Keeping immunization-related expenses down to a bearable level - Encouraging women who ensure that their children are properly immunized - Sufficiently informing the public as to the new vaccines to be included in EPI (vaccine type and cost). | X X X X X X X X X X X X X | X X X X X X X X X | X X X X X X X X X X X X X X X X X X X X X X X X X X X X X X X X X X |

- Components or areas of immunization services that are yet to be reviewed (or studied).

| ##### Component or area | Month/Year |
| --- | --- |

# Multi-Year Immunization Plan

Based upon the recommendations of the assessment of immunization services, the Government has developed (or updated) the multi-year immunization plan or adjusted the health sector plan.

| - Attached is a complete copy (with an executive summary) of the Multi-Year Immunization Plan or of the relevant pages of the health sector plan. | Document number 9. |
| --- | --- |

| Technical support required for implementation of the immunization plan (expert consultants, training curricula, managerial tools…) |  |  |
| --- | --- | --- |
| Type of technical support | Period for the support | Desired from which agency |
| Support for the drafting of a communication program for introducing the pentavalent vaccine into EPI | Nov – Dec 2004 | Sept 2004 |

| Table 3: Schedule of vaccinations with traditional and new vaccines, and with Vit A supplementation |  |  |  |  |
| --- | --- | --- | --- | --- |
| Vaccine (do not use trade name) | Ages of administration (by routine immunization services) | Indicate by an “x” if given in: |  | Comments |
|  |  | Entire country | Only part of the country |  |
| BCG | Birth | X |  |  |
| OPV | Birth, W6, W10, W14 | X |  |  |
| DTP | W6, W10, W14 | X |  |  |
| HepB | W6, W10, W14 | X |  |  |
| MEAS | M9 | X |  |  |
| YF | M9 | X |  |  |
| TT | 1st contact, +4W, +6M, +1Y | X |  | Women of child-bearing age (15-49) |
| Vitamin A |  | X |  | 2 passages per yr for children aged 6-59 months |

- Summary of major action points and timeframe for improving immunization coverage:

Implementation of the approach to reach each district

- Identification of priority districts (done in Jan 2004);

- Organization of rapid reviews in priority districts (Apr 2004);

- Drafting of plans for relaunching advanced strategies (Jun 2004);

- Strengthening of ties with community (ongoing).

Monthly monitoring of immunization coverage

- Validation of immunization coverage data (quarterly)

| Table 4: Baseline and annual targets |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ###### Number of |  | ###### Baseline and targets |  |  |  |  |  |  |  |  |
|  |  | 2003 | 2004 | 2005 |  | 2006 | 2007 | 2008 | 2009 | 2010 |
| Births |  | 287667 | 288557 | 297903 |  | 304917 | 317231 | 327582 | 338297 | 348605 |
| Infants’ deaths |  | 25602 | 25682 | 26513 |  | 27138 | 28234 | 29155 | 30108 | 31026 |
| Surviving infants |  | 262065 | 262875 | 271390 |  | 277779 | 288997 | 298427 | 308189 | 317579 |
| Pregnant women |  | 330817 | 331841 | 342588 |  | 350655 | 364816 | 376719 | 389042 | 400896 |
| Infants vaccinated with BCG* |  | 303506 | 288557 | 297903 |  | 304917 | 317231 | 327582 | 338297 | 348605 |
| Infants vaccinated with OPV3** |  | 254623 | 249732 | 257820 |  | 263890 | 274548 | 283506 | 292779 | 301700 |
| Infants vaccinated with DTP3** |  | 254623 | 244474 | 162834 |  | NA | NA | NA | NA | NA |
| Infants vaccinated with 1 HepB3**: |  | 232029 | 241845 | 162834 |  | NA | NA | NA | NA | NA |
| Infants vaccinated with pentavalent 3** |  | NA | NA | 230681 |  | 236112 | 260098 | 268584 | 286615 | 301700 |
| Infants vaccinated with YF** |  | 238329 | 226073 | 244251 |  | 252779 | 265878 | 277537 | 289697 | 301700 |
| Infants vaccinated with Measles** |  | 238372 | 285383 | 244251 |  | 252779 | 265878 | 277537 | 289697 | 301700 |
| Pregnant women vaccinated with TT+ |  | 283305 | 265472 | 265472 |  | 280524 | 291853 | 301375 | 311233 | 320717 |
| Vit A supplementation | Mothers (< 6 weeks from delivery) | NA | 47785 | 79642 |  | 117820 | 131334 | 144660 | 158729 | 173187 |
|  | Infants (> 6 months) | NA | 721139 | 89371 |  | 121967 | 134823 | 139222 | 152234 | 165587 |
| * Target of children out of total births |  |  |  |  | ** Target of children out of surviving infants |  |  |  |  |  |

Summary of major action points and timeframe for reduction of vaccine wastage. If maximum allowance of wastage rates cannot be achieved immediately, the proposal has to provide a rationale for a higher rate:

The use of two-dose vials has helped keep wastage rates down to 10%.

| Table 5: Estimate of annual DTP wastage and drop out rates |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Actual rates and targets |  |  |  |  |  |  |  |
|  | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 |
| Wastage rate |  | 22% | 27% | 25% | 25% | 10% | 10% | 10% |
| Drop out rate [ ( DTP1 - DTP3 ) / DTP1 ] x 100 | 16% | 16% | 15% | 13% | 12% | 10% | 10% | 10% |

- Countries requesting YF vaccine have to present the same table for measles vaccine wastage rates.

- Planning and constraints for the Polio Eradication Initiative:

# Injection safety

7.1	Summary of the injection safety strategy for immunization (for all countries):

(a)	Publicize the national injection safety policy;

(b)	Provide staff involved in immunization activities with injection safety training;

(c)	Set up a sustainable mechanism for ensuring the supply of AD syringes and safety boxes;

(d)	Introduce an efficient system for the management of used immunization materials in all immunization centers;

(e)	Strengthen follow-up and regular supervision of immunization activities, including injection safety, on all levels;

(f)	Increase the community’s awareness of and participation in injection safety.

| - Attached is a copy of the Plan to achieve Safe Injections (including plans for transition to auto-destruct syringes) and Safe Management of Sharp Waste or of the relevant pages of the health plan. | Document number 10. |
| --- | --- |

7.2	Injection safety equipment (For countries submitting a request for injection safety support). GAVI’s support is only for three years of routine immunization.

The following tables calculate the amount of supplies requested for injection safety:

Table 6.1: Estimated supplies for injection safety with BCG

|  |  | Formula | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A | Number of children to receive new vaccine [1] | # | 297903 | 304917 | 317231 | 327582 | 338297 | 348605 |
| B | Percentage of vaccines requested from The Vaccine Fund | % | 100 | 100 | 100 | 100 | 100 | 100 |
| C | Number of doses per child | # | 1 | 1 | 1 | 1 | 1 | 1 |
| D | Number of doses | A x B/100 x C | 297903 | 304917 | 317231 | 327582 | 338297 | 348605 |
| E | Estimated wastage factor | see list in table  | 2 | 1.8 | 1.6 | 1.6 | 1.5 | 1.5 |
| F | Number of doses (incl. wastage) | A x C x E x B/100 | 595806 | 548851 | 507570 | 524131 | 507446 | 522908 |
| G | Vaccine buffer stock [3] | F x 0.25 | 0 | 0 | 0 | 0 | 0 | 0 |
| H | Total vaccines doses requested | F + G | 595806 | 548851 | 507570 | 524131 | 507446 | 522908 |
| I | Number of doses per vial | # | 20 | 20 | 20 | 20 | 20 | 20 |
| J | Number of AD syringes (+10% wastage) [4] | (D + G) x 1.11 | 330672 | 338458 | 352126 | 363616 | 375510 | 386952 |
| K | Reconstitution syringes (+10% wastage) [5] | H / I x 1.11 | 33067 | 30461 | 28170 | 29089 | 28163 | 29021 |
| L | Total of safety boxes (+10% of extra need) | (J + K) / 100 x 1.11 | 4038 | 4095 | 4221 | 4359 | 4481 | 4617 |

Table 6.2: Estimated supplies for injection safety with MEAS

|  |  | Formula | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A | Number of children to receive vaccine [1] | # | 297903 | 304917 | 317231 | 327582 | 338297 | 348605 |
| B | Percentage of vaccines requested from The Vaccine Fund | % | 100 | 100 | 100 | 100 | 100 | 100 |
| C | Number of doses per child | # | 1 | 1 | 1 | 1 | 1 | 1 |
| D | Number of doses | A x B/100 x C | 297903 | 304917 | 317231 | 327582 | 338297 | 348605 |
| E | Estimated wastage factor [2] | see list in table  | 2 | 1.8 | 1.6 | 1.6 | 1.5 | 1.5 |
| F | Number of doses (incl. wastage) | A x C x E x B/100 | 595806 | 548851 | 507570 | 524131 | 507446 | 522908 |
| G | Vaccines buffer stock [3] | F x 0.25 | 0 | 0 | 0 | 0 | 0 | 0 |
| H | Total vaccine doses requested | F + G | 595806 | 548851 | 507570 | 524131 | 507446 | 522908 |
| I | Number of doses per vial | # | 10 | 10 | 10 | 10 | 10 | 10 |
| J | Number of AD syringes (+10% wastage) [4] | (D + G) x 1.11 | 330672 | 338458 | 352126 | 363616 | 375510 | 386952 |
| K | Reconstitution syringes (+10% wastage) [5] | H / I x 1.11 | 66134 | 60922 | 56340 | 58179 | 56326 | 58043 |
| L | Total of safety boxes (+10% of extra need) [6] | (J + K) / 100 x 1.11 | 4405 | 4433 | 4534 | 4682 | 4793 | 4939 |

Table 6.3: Estimated supplies for injection safety with YF

|  |  | Formula | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A | Number of children to receive new vaccine [1] | # | 297903 | 304917 | 317231 | 327582 | 338297 | 348605 |
| B | Percentage of vaccines requested from The Vaccine Fund | % | 100 | 100 | 100 | 100 | 100 | 100 |
| C | Number of doses per child | # | 1 | 1 | 1 | 1 | 1 | 1 |
| D | Number of doses | A x B/100 x C | 297903 | 304917 | 317231 | 327582 | 338297 | 348605 |
| E | Estimated wastage factor [2] | see list in table  | 2 | 1.8 | 1.6 | 1.6 | 1.5 | 1.5 |
| F | Number of doses (including wastage) | A x C x E x B/100 | 595806 | 548851 | 507570 | 524131 | 507446 | 522908 |
| G | Number of vaccines in the buffer stock [3] | F x 0.25 | 0 | 0 | 0 | 0 | 0 | 0 |
| H | Total vaccine doses required | F + G | 595806 | 548851 | 507570 | 524131 | 507446 | 522908 |
| I | Number of doses per vial | # | 10 | 10 | 10 | 10 | 10 | 10 |
| J | Number of AD syringes (+10% wastage) [4] | (D + G) x 1.11 | 330672 | 338458 | 352126 | 363616 | 375510 | 386952 |
| K | Number of reconstitution syringes (+10% wastage) [5] | H / I x 1.11 | 66134 | 60922 | 56340 | 58179 | 56326 | 58043 |
| L | Number of safety boxes (+10% extra need) [6] | (J + K) / 100 x 1.11 | 4405 | 4433 | 4534 | 4682 | 4793 | 4939 |

Table 6.4: Estimated supplies for injection safety with TT

|  |  | Formule | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A | Target of pregnant women for immunization [1] | # | 342588 | 350655 | 364816 | 376719 | 389042 | 400896 |
| B | % of vaccines requested from the World Vaccine Fund | % | 100 | 100 | 100 | 100 | 100 | 100 |
| C | Number of doses per women | # | 3 | 3 | 3 | 3 | 3 | 3 |
| D | Number of doses | A x B/100 x C | 1027765 | 1051964 | 1094447 | 1130158 | 1167125 | 1202687 |
| E | Vaccine wastage factor [2] | see list in table  | 1.4 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 |
| F | Number of doses (including wastage) | A x C x E x B/100 | 1438871 | 1367553 | 1422781 | 1469205 | 1517262 | 1563493 |
| G | Number of vaccines in the buffer stock [3] | F x 0.25 | 0 | 0 | 0 | 0 | 0 | 0 |
| H | Total vaccine doses requested | F + G | 1438871 | 1367553 | 1422781 | 1469205 | 1517262 | 1563493 |
| I | Nombre de doses par flacon | # | 20 | 20 | 20 | 20 | 20 | 20 |
| J | Number of AD syringes (+10% wastage) [4] | (D + G) x 1.11 | 1140820 | 1167680 | 1214836 | 1254475 | 1295508 | 1334983 |
| K | Reconstitution syringes (+10% wastage) [5] | H / I x 1.11 | 79857 | 75899 | 78964 | 81541 | 84208 | 86774 |
| L | Total of safety boxes (+10% of extra need) [6] | (J + K) / 100 x 1.11 | 13550 | 13804 | 14361 | 14830 | 15315 | 15781 |

Table 6.5: Estimated supplies for injection safety with the pentavalent vaccine

First scenario

|  | Formula | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Number of children to receive vaccine [1] | # | 297903 | 304917 | 317231 | 327582 | 338297 | 348605 |
| Percentage of vaccines requested from The Vaccine Fund | % | 100 | 100 | 100 | 100 | 100 | 100 |
| Number of doses per child | # | 3 | 3 | 3 | 3 | 3 | 3 |
| Number of doses | A x B/100 x C | 893709 | 914751 | 951693 | 982746 | 1014891 | 1045815 |
| Estimated wastage factor [2] | see list in table  | 1.11 | 1.11 | 1.11 | 1.11 | 1.11 | 1.11 |
| Number of doses (including wastage) | A x C x E x B/100 | 992017 | 1015374 | 1056379 | 1090848 | 1126529 | 1160855 |
| Vaccines buffer stock [3] | F x 0.25 | 248004 | 253843 | 264095 | 272712 | 281632 | 290214 |
| Total vaccine doses requested | F + G | 1240021 | 1269217 | 1320474 | 1363560 | 1408161 | 1451068 |
| Number of doses per vial | # | 2 | 2 | 2 | 2 | 2 | 2 |
| Number of AD syringes (+10% wastage) [4] | (D + G) x 1.11 | 1267302 | 1297140 | 1349524 | 1393558 | 1439141 | 1482992 |
| Reconstitution syringes (+10% wastage) [5] | H / I x 1.11 | 688212 | 704415 | 732863 | 756776 | 781530 | 805343 |
| Total of safety boxes (+10% extra need) [6] | (J + K) / 100 x 1.11 | 21706 | 22217 | 23115 | 23869 | 24649 | 25401 |

Second scenario

|  | Introduction from January 2005 onwards |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Formula | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 |
| A | Number of children to receive new vaccine [1] | # | 297903 | 304917 | 317231 | 327582 | 338297 | 348605 |
| B | Percentage of vaccines requested from The Vaccine Fund | % | 100 | 80 | 81 | 82 | 83 | 84 |
| C | Number of doses per child | # | 3 | 3 | 3 | 3 | 3 | 3 |
| D | Number of doses | A x B/100 x C | 893709 | 731800.8 | 770871.3 | 805851.7 | 842359.5 | 878484.6 |
| E | Estimated wastage factor [2] | see list in table  | 1,11 | 1,11 | 1,11 | 1,11 | 1,11 | 1,11 |
| F | Number of doses (including wastage) | A x C x E x B/100 | 992017 | 812299 | 855667 | 894495 | 935019 | 975118 |
| G | Vaccines buffer stock [3] | F x 0.25 | 248004 | 203075 | 213917 | 223624 | 233755 | 243779 |
| H | Total vaccine doses requested | F + G | 1240021 | 1015374 | 1069584 | 1118119 | 1168774 | 1218897 |
| I | Number of doses per vial | # | 2 | 2 | 2 | 2 | 2 | 2 |
| J | Number of AD syringes (+10% wastage) [4] | (D + G) x 1.11 | 1267302 | 1037712 | 1093115 | 1142718 | 1194487 | 1245713 |
| K | Reconstitution syringes (+10% wastage) [5] | H / I x 1.11 | 688212 | 563532 | 593619 | 620556 | 648669 | 676488 |
| L | Total of safety boxes (+10% of extra need) [6] | (J + K) / 100 x 1.11 | 21706 | 17774 | 18723 | 19572 | 20459 | 21336 |

  - Areas for injection safety funds (For countries requesting funds equivalent to the supplies calculated above).

List of areas of injection safety funded by different sources: (For the GAVI/The Vaccine Fund support, fill in “areas of support”. For AD syringes and waste disposal, fill in “source of funds”.)

| Source of fund | ###### Area of support | Start of fund utilization |
| --- | --- | --- |
| GAVI/Vaccine Fund | AD syringes and waste disposal boxes | year 2005 |

(Use as many rows as necessary

# New and under-used vaccines

- Summary of those aspects of the multi-year immunization plan that refer to the introduction of new and under-used vaccines.

-	Carefully plan orders of DTP vaccines for 2004 in order to avoid “overstocking” when the pentavalent vaccine is introduced in 2005;

-	Improve the vaccine distribution system;

-	Continue to stringently apply the open vial policy for multidose vials;

-	Ensure rigorous cold chain maintenance;

-	Reduce missed immunization opportunities;

-	Improve access to immunization services by revitalizing the advanced strategy (ACD approach).

- Assessment of burden of relevant diseases (if available) :

| Disease | Title of the assessment | Date | Results |
| --- | --- | --- | --- |

- (if new or under-used vaccines have been already introduced)

Lessons learnt about storage capacity, protection from accidental freezing, staff training, cold chain, logistics, drop out rate, wastage rate etc. as per current experience with new and under-used vaccines:

- Summary of the action points that address possible implications for storage capacity, staff training, cold chain, measures to avoid freezing of vaccines, logistics, drop out rate, wastage rate etc… in the Plan for Introduction of New and Under-used Vaccines:

-	Ensure preventive and curative maintenance of cold chain equipment at all levels of the health pyramid;

-	Take daily temperature readings to ensure proper vaccine conservation;

-	Supply spare parts for cold chain equipment;

-	Train/retrain staff in preventive maintenance techniques;

-	Manage vaccine stock life by level;

-	Systematically use inventory management tools;

-	Computerize stock life tools.

- First preference: required number of doses and presentations of requested new and under-used vaccines. (For each one of the requested first preference of  new and under-used vaccine, please use provided formulae)

| Table 7.1: Estimated number of doses of pentavalent vaccine (Specify one table for each presentation of any vaccine and number it 7.2, 7.3, …) |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | First scenario: Introduction starting in January 2005, with 100% of vaccines requested yearly from the Vaccine Fund |  |  |  |  |  |  |  |
|  |  | Formule | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 |
| A | Number of children to receive new vaccine [1] | # | 297903 | 304917 | 317231 | 327582 | 338297 | 348605 |
| B | Percentage of vaccines requested from The Vaccine Fund | % | 100 | 100 | 100 | 100 | 100 | 100 |
| C | Number of doses per child | # | 3 | 3 | 3 | 3 | 3 | 3 |
| D | Number of doses | A x B/100 x C | 893709 | 914751 | 951693 | 982746 | 1014891 | 1045815 |
| E | Estimated wastage factor [2] | see list in table  | 1.11 | 1.11 | 1.11 | 1.11 | 1.11 | 1.11 |
| F | Number of doses (incl. wastage) | A x C x E x B/100 | 992017 | 1015374 | 1056379 | 1090848 | 1126529 | 1160855 |
| G | Vaccines buffer stock [3] | F x 0.25 | 248004 | 253843 | 264095 | 272712 | 281632 | 290214 |
| H | Total vaccine doses requested | F + G | 1240021 | 1269217 | 1320474 | 1363560 | 1408161 | 1451068 |
| I | Number of doses per vial | # | 2 | 2 | 2 | 2 | 2 | 2 |
| J | Number of AD syringes (+10% wastage) [4] | (D + G) x 1.11 | 1267302 | 1297140 | 1349524 | 1393558 | 1439141 | 1482992 |
| K | Reconstitution syringes (+10% wastage) [5] | H / I x 1.11 | 688212 | 704415 | 732863 | 756776 | 781530 | 805343 |
| L | Total of safety boxes (+ 10% of extra need) [6] | (J + K) / 100 x 1.11 | 21706 | 22217 | 23115 | 23869 | 24649 | 25401 |

| Table  : Wastage rates and factors |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

- Second preference: Required number of doses and presentations of requested new and under-used vaccines, if first preference is not available. (Please use provided formulae as per table 7.1)

| Table 7.1b : Estimated number of doses of pentavalent vaccine |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Introduction starting in Jan 2005 with % of the vaccines requested spread out over time |  |  |  |  |  |  |  |
|  |  | Formula | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 |
| A | Number of children to receive new vaccine [1] | # | 297903 | 304917 | 317231 | 327582 | 338297 | 348605 |
| B | Percentage of vaccines requested from The Vaccine Fund | % | 100 | 80 | 81 | 82 | 83 | 84 |
| C | Number of doses per child | # | 3 | 3 | 3 | 3 | 3 | 3 |
| D | Number of doses | A x B/100 x C | 893709 | 731800,8 | 770871,3 | 805851,7 | 842359,5 | 878484,6 |
| E | Estimated wastage factor [2] | see list in table  | 1.11 | 1.11 | 1.11 | 1.11 | 1.11 | 1.11 |
| F | Number of doses (incl. wastage) | A x C x E x B/100 | 992017 | 812299 | 855667 | 894495 | 935019 | 975118 |
| G | Vaccines buffer stock [3] | F x 0.25 | 248004 | 203075 | 213917 | 223624 | 233755 | 243779 |
| H | Total vaccine doses requested | F + G | 1240021 | 1015374 | 1069584 | 1118119 | 1168774 | 1218897 |
| I | Number of doses per vial | # | 2 | 2 | 2 | 2 | 2 | 2 |
| J | Number of AD syringes (+10% wastage) [4] | (D + G) x 1.11 | 1267302 | 1037712 | 1093115 | 1142718 | 1194487 | 1245713 |
| K | Reconstitution syringes (+10% wastage) [5] | H / I x 1.1 | 688212 | 563532 | 593619 | 620556 | 648669 | 676488 |
| L | Total of safety boxes (+ 10% of extra need) [6] | (J + K) / 100 x 1.11 | 21706 | 17774 | 18723 | 19572 | 20459 | 21336 |

| - Attached is the plan of action for vaccinations with new or under-used vaccines (if already contained within the national, multi-year plan, indicate pages) | Document number 11 |
| --- | --- |

# Strategic directions to mobilise additional resources for immunization

- Summary of strategies that the Government intends to pursue to increase the resources for immunization of children, and that will be converted in a comprehensive Financial Sustainability Plan. Highlights of the agreements made with donor agencies (i.a.: Vaccine Independence Initiative) and the use of funds freed by debt relief:

Benin must submit a financial sustainability scheme by 30 November at the latest.  Accordingly, it plans to take an active part in the training workshops that will be organized in June 2004 with a view to helping countries draft these plans.

| - Tables of expenditure for 2001 and resource needs detailing the sources of funds for 2001 and subsequent years are attached in Annex 1. | Document number .NA |
| --- | --- |

- Remarks on recurrent cost reduction strategies which contribute to financial sustainability, such as vaccine wastage reduction:

# Summary of requests to GAVI and the Vaccine Fund

With reference to all points presented above, the Government of …………………………………………..,

considering that its DTP3 coverage for 2001 was ………%  corresponding to ……… number of children receiving 3 doses of DTP, requests the Alliance and its partners to contribute financial and technical assistance required to increase immunization of children.

Specifically, the Government hereby applies for the following types of support from GAVI and the Vaccine Fund. (Circle “YES” or “NO” according to the requests submitted with this proposal):

- Support for Immunization Services                       		                    NO

- Support for New and Under-used vaccines                                  YES

- Support for Injection Safety                                                          YES

10.1	SUPPORT FOR IMMUNIZATION SERVICES

GAVI and the Vaccine Fund are requested to fund the strategies for strengthening immunization services in year 2003 according to the number of additional children (as compared to the baseline) that are targeted to be immunized with DTP3 as presented in table 4, namely ………… (number of children). Funds will also be requested for following years as estimated in table 4.

- The Government takes full responsibility to manage the in-country transfer of funds.

(In case an alternative mechanism is necessary please describe it and the reasons for it:)

- Operational mechanism that is followed for safeguarding transparency, standards of accounting, long-term sustainability and empowerment of the government in using the funds:

- Countries requesting immunization services support should submit the “Banking Details” form (Annex 3) with their proposal.

  - SUPPORT FOR NEW AND UNDER-USED VACCINES

GAVI and the Vaccine Fund are requested to fund the introduction of New and Under-used Vaccines by providing the following vaccines: (fill in only what is being requested from the Vaccine Fund in line with tables 7.1, 7.2…)

| Table 8: New and under-used vaccines requested from GAVI and the Vaccine Fund |  |  |  |  |
| --- | --- | --- | --- | --- |
| Vaccine presentation | Number of doses per vial | Starting month and year | Number of doses requested for first calendar year | Number of doses requested for second calendar year * |
| DTP-Hep+Hib | 2 | Sept 2005 | 220,750 | 619,964 |
| * Vaccines will also be requested for following years as described in tables 7.1, 7.2… |  |  |  |  |

- Vaccines will be procured (tick only one) :

By UNICEF  X                            By GOVERNMENT

- (If vaccines are proposed to be procured by the Government) 	Process and procedures of the National Regulatory Authority to control the purchase and delivery of vaccines into the country, including weaknesses, constraints and planned measures to improve the control system:

- (In case you are approved, you will be entitled to receive a lump-sum of US$ 100,000 to facilitate the introduction of new vaccines) Please submit the attached “Banking Form”(Annex 3) with the proposal, in case you have not yet done for other types of support from GAVI/The Vaccine Fund..

  - SUPPORT FOR INJECTION SAFETY

GAVI and the Vaccine Fund are requested to support the injection safety plan by providing:

(Tick one choice only):		The amount of supplies listed in table 9

The equivalent amount of funds

| Table 9: Summary of total supplies for safety of vaccinations with BCG, DTP, TT, MEASLES and YF, requested from GAVI and the Vaccine Fund for three years (fill in the total sums of rows “F”, I and J of tables 6.1,6.2, 6.3, 6.4 and 6.5). |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | ITEM |  | 2005 | 2006 | 2007 | 2008 |
| F | Total AD syringes | for BCG | 413340 | 338458 | 352126 | 363616 |
|  |  | for other vaccines | 4 133 404 | 3 384 579 | 3 521 264 | 3 636 160 |
| I | Total of reconstitution syringes |  | 138 882 | 142 152 | 147 893 | 152 719 |
| J | Total of safety boxes |  | 50 729 | 42 531 | 44 249 | 45 693 |

- (In case you request funds equivalent to the above supplies at the prices obtained by UNICEF) Please submit the attached “Banking Form”(Annex 3) with the proposal, in case you have not yet done for other types of support from GAVI/The Vaccine Fund.

# Additional comments and recommendations from the ICC

With regard to such challenges as:

- Reinforcing the cold chain

- Reducing wastage rates

- Reducing zero doses and the number of children who drop out of sight

1 - The ICC-EPI appreciates the opportunity provided by GAVI to enlarge immunization activities in Benin.

2 – The ICC-EPI supports the Government of Benin and commends it on its commitment to the Vaccine Independence Initiative (VII) despite its limited resources.

3 – The ICC-EPI hopes that negotiations with GAVI will be flexible enough to allow coverage to be broadened to include other vaccine-preventable diseases in coming years.

4 – The ICC-EPI strongly hopes that this file will be approved so that Benin will receive the resources needed to improve its vaccine coverage.

5 – The ICC-EPI hereby undertakes to ensure the proper administration of the resources provided by GAVI.

ANNEX 1

#### Statement of financing and of unmet needs for immunization (USD ,000)

Table 1

| Expenditure in 2003 from different sources |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. # | Category / Line item | Central Govern-ment | Local Govern-ment | Private sector | Donor 11 | Donor 2 | Donor 3 | Donor 4 | Donor n.. 2 | Total Expendi-ture |
| 1. | Vaccines, AD syringes… | 1,651,276.15 |  |  |  | 1,901,736.33 |  |  |  |  |
| 1.1 | - Line item … |  |  |  |  |  |  |  |  |  |
| 1.2 | - Line item …3 |  |  |  |  |  |  |  |  |  |
| 2. | Equipment (cold chain, spare parts, sterilisation…) |  |  |  |  | 437,696.25 |  |  |  |  |
| 2.1 | - Line item … |  |  |  |  |  |  |  |  |  |
| 2.2 | - Line item …3 |  |  |  |  |  |  |  |  |  |
| 3. | Other item immunization specific |  |  |  |  | 234,825.69 |  |  |  |  |
| 3.1 | - Line item … |  |  |  |  |  |  |  |  |  |
| 3.2 | - Line item …3 |  |  |  |  |  |  |  |  |  |
| Total expenditure |  | 1,651,276.15 |  |  |  |  |  |  |  |  |
| 1 If basket funding or a similar aggregated funding approach is used, please describe the total funding amounts, and/or detail partner contributions as fully as possible. 2 Please use the electronic version of the document and insert as many columns for partner contributions as are necessary for your submission. 3 Please use the electronic version of the document to insert as many line items as necessary for your submission. |  |  |  |  |  |  |  |  |  |  |

Table 2

| Budget for 2004 (Fill in a similar table for subsequent years) |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. # | Category / Line item | Contributions committed by partners |  |  |  |  |  |  | Total projected needs | Unmet needs |
|  |  | Central Govern-ment | Local Govern-ment | Private sector | Donor 11 | Donor 2 | Donor 3 | Donor n.. 2 |  |  |
| 1. | Vaccines, AD syringes… | 1,651,276.15 |  |  | 409,500 |  |  |  |  |  |
| 1.1 | - Line item … |  |  |  |  |  |  |  |  |  |
| 1.2 | - Line item …3 |  |  |  |  |  |  |  |  |  |
| 2. | Equipment (cold chain, spare parts, sterilisation…) |  |  |  |  |  |  |  |  |  |
| 2.1 | - Line item … |  |  |  |  |  |  |  |  |  |
| 2.2 | - Line item …3 |  |  |  |  |  |  |  |  |  |
| 3. | Other item immunization specific |  |  |  |  |  |  |  |  |  |
| 3.1 | - Line item … |  |  |  |  |  |  |  |  |  |
| 3.2 | - Line item …3 |  |  |  |  |  |  |  |  |  |
| Total commitment |  | 1,651,276.15 |  |  |  |  |  |  |  |  |
| 1 If basket funding or a similar aggregated funding approach is used, please describe the total funding amounts, and/or detail partner contributions as fully as possible. 2 Please use the electronic version of the document and insert as many columns for partner contributions as are necessary for your submission. 3 Please use the electronic version of the document to insert as many line items as necessary for your submission. |  |  |  |  |  |  |  |  |  |  |

ANNEX  2

Summary of documentation

| Background information on Health System Development status |  |
| --- | --- |
| - Attached are the relevant section(s) of strategies for health system development | Document number 1. |
| Profile of the Inter Agency Co-ordinating Committee (ICC) |  |
| - ICC’s workplan for the next 12 months | Document number 5. |
| - Terms of reference of the ICC | Document number 4 |
| - Minutes of the three most recent ICC meetings or any meetings concerning the introduction of new or under-used vaccines or safety of injections | Document number 6 |
| Immunization Services Assessment |  |
| - Most recent, national assessment report(s) on the status of immunization services | Document number 7… |
| - Summary of the recommendations of the assessment report(s) with remarks on the status of implementation of each recommendation. | Document number 8… |
| Multi-Year Immunization Plan |  |
| - Complete copy (with executive summary) of the Multi-Year Immunization Plan or of the relevant pages of the health sector plan. | Document number 9 |
| - Action plan for the introduction of new or under-used vaccines into immunization services (if already contained within the national, multi-year plan, please indicate page and paragraphs) - A copy of the Plan to achieve Safe Injections (including plans for transition to auto-destruct syringes) and Safe Management of Sharps Waste or of the relevant pages of the health plan. | Document number 11 Document number 12 |
| Unmet needs requiring additional resources |  |
| - Tables of expenditure for 2001 and resource needs (Annex 1) | Document number NA… |

ANNEX  3

| GLOBAL ALLIANCE FOR VACCINES AND IMMUNIZATION |  |  |  |  |  | ##### Banking Form |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SECTION 1 (To be completed by payee) |  |  |  |  |  |  |  |  |  |  |
| In accordance with the decision on financial support made by the Global Alliance for Vaccines and Immunization and the Vaccine Fund dated . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . , the Government of . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . , hereby requests that a payment be made, via electronic bank transfer, as detailed below: |  |  |  |  |  |  |  |  |  |  |
| #### Name of Institution: (Account Holder) |  |  |  |  |  |  |  |  |  |  |
| #### Address: |  |  |  |  |  |  |  |  |  |  |
| #### City – Country: |  |  |  |  |  |  |  |  |  |  |
| Telephone No.: |  |  |  | Fax No.: |  |  |  |  |  |  |
| #### Amount in USD: |  | (To be filled in by GAVI Secretariat) |  |  | Currency of the bank account: |  |  |  |  |  |
| For credit to: Bank account’s title |  |  |  |  |  |  |  |  |  |  |
| Bank account No.: |  |  |  |  |  |  |  |  |  |  |
| At: Bank’s name |  |  |  |  |  |  |  |  |  |  |
| #### Is the bank account exclusively to be used by this programme? |  |  |  |  |  |  | YES ( ) NO ( ) |  |  |  |
| #### By whom is the account audited? |  |  |  |  |  |  |  |  |  |  |
| # Signature of Government’s authorizing official: |  |  |  |  |  |  |  |  |  |  |
| #### Name: |  |  |  |  |  |  |  |  | Seal: |  |
| #### Title: |  |  |  |  |  |  |  |  |  |  |
| #### Signature: |  |  |  |  |  |  |  |  |  |  |
| Date: |  |  |  |  |  |  |  |  |  |  |

| SECTION 2 (To be completed by the Bank) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| # FINANCIAL INSTITUTION |  |  |  | CORRESPONDENT BANK (In the United States) |  |
| Bank Name: |  |  |  |  |  |
| Branch Name: |  |  |  |  |  |
| Address: |  |  |  |  |  |
| City – Country: |  |  |  |  |  |
| Swift code: |  |  |  |  |  |
| Sort code: |  |  |  |  |  |
| ABA No.: |  |  |  |  |  |
| Telephone No.: |  |  |  |  |  |
| Fax No.: |  |  |  |  |  |
| I certify that the account No. . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . is held by (Institution name) . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . .at this banking institution. |  |  |  |  |  |
| The account is to be signed jointly by at least …… (number of signatories) of the following authorized signatories: |  |  | Name of bank’s authorizing official: |  |  |
| 1 Name: Title: |  |  | Signature: |  |  |
|  |  |  | Date: |  |  |
| 2 Name: Title: |  |  | Seal: |  |  |
| 3 Name: Title: |  |  |  |  |  |
| 4 Name: Title: |  |  |  |  |  |

COVERING LETTER

(To be completed by UNICEF representative on letter-headed paper)

### TO:    GAVI – Secretariat

### Att. Dr Tore Godal

### Executive Secretary

C/o UNICEF

Palais des Nations

CH 1211 Geneva 10

Switzerland

| On the ……………………………… I received the original of the BANKING DETAILS form, which is attached. I certify that the form does bear the signatures of the following officials: |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | Name |  |  | Title |
| Government’s authorizing official |  |  |  |  |  |
| Bank’s authorizing official |  |  |  |  |  |
| Signature of UNICEF Representative: |  |  |  |  |  |
| Name |  |  |  |  |  |
| Signature |  |  |  |  |  |
| Date |  |  |  |  |  |

YF: Yellow Fever

Formula to calculate DTP vaccine wastage rate (in percentage): [ ( A – B ) / A ] x 100.   Whereby : A = The number of DTP doses distributed for use according to the supply  records with correction for stock balance at start and end of the supply period; B =  the number of DTP vaccinations.

Please submit hard copy documents with an identical electronic copy whenever possible