FORM TO BE COMPLETED BY COUNTRIES: PHASE 2

Application for support for:

new vaccines and under-used vaccines

15 November 2006

Côte d’Ivoire

Ivory Coast

For convenience, this document is accompanied by a copy on CD.

Please return a copy of the CD as well as a signed copy of the original document on paper to the Secretariat of GAVI:

C/o UNICEF, Palais des Nations, 1211 Geneva 10, Switzerland.

Any documents and any exhibits enclosed must be transmitted in English or in French.

For any questions, please contact directly

Dr Ivone Rizzo irizzo@gavialliance.org or representatives of a partner institution of the GAVI Alliance.

## CONTENTS

|  |  | PAGE |
| --- | --- | --- |
| 1. | Analytical summary | 2 |
| 2. | Signatures of the Government and the national coordination organisation | 3 |
|  | The Inter-agency Coordination Committee for vaccination (CCI) | 5 |
| 3. | Data on the vaccination programme | 6 |
| 4. | Support for new vaccines and under-used vaccines (SVN) | 11 |
|  | First priority vaccine | 13 |
|  | Second priority vaccine | 14 |
|  | Purchase and management of new vaccines and under-used vaccines | 15 |
| 5. | Observations and recommendations of the Inter-agency Coordination Committee for vaccination (CCI) and other partners for development aid in the health sector | 17 |
| 6. | Documents to be furnished | 18 |
| APPENDIX 1: Calculation of the support applied for and of the co-financing budget relating thereto |  | ** |
| APPENDIX 2: Bank form |  | 19 |

** Appendix 1 consists of an Excel calculation sheet enclosed with this document – Please update and complete the tables.

1.	Analytical summary

The Government of the Ivory Coast considers it a priority for the period 2007-2011 to introduce the pentavalent vaccine into the routine EPI in view of the heavy burden of Hib infections.

Moreover, the vaccine against yellow fever has been in the vaccination programme since 1983. The current vaccinal schedule envisages its simultaneous administration with that of measles at the age of 9 months. In spite of substantial progress noted these two last years in the evolution of the EPI performances, there still persists a gap between the vaccinal coverage of the VCAr and of the VAA. This difference is primarily related to the out-of-stock conditions noted for the VAA.

With the aim of introducing the pentavalent vaccine and guaranteeing an adequate and regular supply of the vaccine against yellow fever, the support of GAVI is requested for the next 4 years 2008 – 2011.

The country has also introduced to GAVI a proposal for support for the safety of vaccinal injections over the period 2008-2010.

The Inter-agencies Coordinating Committee (CCIA), at its meeting of Wednesday 18 April 2007, examined and ratified this proposal to GAVI for support for the introduction of the pentavalent vaccine and the supply of the vaccine against yellow fever for the period 2008-2011. The support requested from GAVI is support in kind.

The country will bear part of the costs of the pentavalent vaccine to a total value of 0.10 $ US per dose and of 0.15 $ US per dose for the vaccine against yellow fever. The Ministry of Health will sign a draft-agreement with the UNICEF office at country level and will pay its share in July each year. A bank transfer will be made out in favour of UNICEF by the Ministry for the Economy and Finances on the request of the Directorate of Financial Services of the Ministry of Health, on a mutually agreed bank account.

The total quantities of pentavalent vaccines and vaccines against yellow fever needed as well as the costs and the shares of the State are summarized in the 2 tables below:

Table 1: number of doses needed and cost of first vaccine: DTC-HepB-Hib vaccination with liquid pentavalent

| Table 2.1a : Objectives and budgets for the introduction of the first vaccine: DTC-HepB-Hib (antigen) vaccination with liquid pentavalent (1dose/vial) |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total supplies |  |  | Year of reference 2006 | Year 1 2008 | Year 2 2009 | Year 3 2010 | Year 4 2011 | Year 5 2012 |
| National objective of number of children to vaccinate |  | # | 441 135 | 498 420 | 526 309 | 561 406 | 579 933 |  |
| Total number of doses of vaccine needed |  | # |  | 1 962 529 | 1 657 873 | 1 768 429 | 1 826 789 |  |
| Total number of self-blocking syringes needed |  | # |  | 2 095 420 | 1 752 609 | 1 869 482 | 1 931 177 |  |
| Total number of reconstitution syringes needed |  | # |  | - | - | - | - |  |
| Total number of safety receptacles needed |  | # |  | 23 259 | 19 454 | 20 751 | 21 436 |  |
| Total budget | Price per dose of vaccine * | $ |  | 3,200 | 2,900 | 2,650 | 2,300 |  |
|  | Total funds needed | $ |  | 6 516 765 | 5 001 338 | 4 896 550 | 4 412 372 |  |
| Co-financing at the charge of country | Co-financing per dose | $ |  | 0,10 | 0,10 | 0,10 | 0,10 |  |
|  | Total payments made by country | $ |  | 196253 | 165 787 | 176 843 | 182 679 |  |
| Support applied for from GAVI | Payment made by GAVI per dose | $ |  | 3,100 | 2,800 | 2,550 | 2,200 |  |
|  | Total payments made by GAVI | $ |  | 6 320 513 | 4 835 551 | 4 719 708 | 4 229 693 |  |

Table 2: number of doses needed and cost of second vaccine: Yellow fever vaccination with lyophilised form, vial 10 doses

| Table 2.1b : Objectives and budgets for the introduction of the second vaccine: Yellow fever (antigen) vaccination with lyophilised form, vial 10 doses (presentation of vaccine) |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total supplies |  |  | Year of reference 2006 | Year 1 2008 | Year 2 2009 | Year 3 2010 | Year 4 2011 | Year 5 20… |
| National objective of number of children to vaccinate |  | # | 470 213* | 459 654 | 486 264 | 514 130 | 549 410 |  |
| Total number of doses of vaccine needed |  | # |  | 718 209 | 607 830 | 606 673 | 648 304 |  |
| Total number of self-blocking syringes needed |  | # |  | 668 658 | 539 753 | 570 684 | 609 845 |  |
| Total number of reconstitution syringes needed |  | # |  | 79 721 | 67 469 | 67 341 | 71 962 |  |
| Total number of safety receptacles needed |  | # |  | 8 318 | 6 740 | 7 082 | 7 568 |  |
| Total budget | Price per dose of vaccine * | $ |  | 0,800 | 0,820 | 0,780 | 0,820 |  |
|  | Total funds needed | $ |  | 657 803 | 569 485 | 545 364 | 582 787 |  |
| Co-financing at the charge of country | Co-financing per dose | $ |  | 0,15 | 0,15 | 0,15 | 0,15 |  |
|  | Total payments made by country | $ |  | 107 731 | 91 175 | 91 001 | 97 246 |  |
| Support applied for from GAVI | Payment made by GAVI per dose | $ |  | 0,650 | 0,670 | 0,630 | 0,670 |  |
|  | Total payments made by GAVI | $ |  | 550 072 | 478 310 | 454 363 | 485 541 |  |

The Government of the Ivory Coast requests support from GAVI for the introduction of the pentavalent vaccine and the procurement of the vaccine against yellow fever for the period 2008-2011.

## Signature of the Government and the national coordination organisation

The government of the Ivory Coast undertakes to develop the national vaccination services in a sustainable manner, in conformity with the global multi-annual vaccination plan (PPgV) or the updated multi-annual plan, set forth in this document.

The table below summarises the objectives pursued in the matter of vaccination as presented in the PPgV or the updated multi-annual plan, the commitment made by the government for the development of a partnership and a participation with GAVI in the financing of the plan for the introduction of new vaccines as well as the amount of the funds applied for from GAVI.

| Table 2.1a : Objectives and budgets for the introduction of the first vaccine: DTC-HepB-Hib (antigen) vaccination with liquid pentavalent (1dose/vial) |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total supplies |  |  | Year of reference 2006 | Year 1 2008 | Year 2 2009 | Year 3 2010 | Year 4 2011 | Year 5 2012 |
| National objective of number of children to vaccinate |  | # | 441 135 | 498 420 | 526 309 | 561 406 | 579 933 |  |
| Total number of doses of vaccine needed |  | # |  | 1 962 529 | 1 657 873 | 1 768 429 | 1 826 789 |  |
| Total number of self-blocking syringes needed |  | # |  | 2 095 420 | 1 752 609 | 1 869 482 | 1 931 177 |  |
| Total number of reconstitution syringes needed |  | # |  | - | - | - | - |  |
| Total number of safety receptacles needed |  | # |  | 23 259 | 19 454 | 20 751 | 21 436 |  |
| Total budget | Price per dose of vaccine * | $ |  | 3,200 | 2,900 | 2,650 | 2,300 |  |
|  | Total funds needed | $ |  | 6 516 765 | 5 001 338 | 4 896 550 | 4 412 372 |  |
| Co-financing at the charge of country | Co-financing per dose | $ |  | 0,10 | 0,10 | 0,10 | 0,10 |  |
|  | Total payments made by country | $ |  | 196253 | 165 787 | 176 843 | 182 679 |  |
| Support applied for from GAVI | Payment made by GAVI per dose | $ |  | 3,100 | 2,800 | 2,550 | 2,200 |  |
|  | Total payments made by GAVI | $ |  | 6 320 513 | 4 835 551 | 4 719 708 | 4 229 693 |  |

| Table 2.1b : Objectives and budgets for the introduction of the second vaccine: Yellow fever (antigen) vaccination with lyophilised form, vial 10 doses (presentation of vaccine) |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total supplies |  |  | Year of reference 2006 | Year 1 2008 | Year 2 2009 | Year 3 2010 | Year 4 2011 | Year 5 20… |
| National objective of number of children to vaccinate |  | # | 470 213* | 459 654 | 486 264 | 514 130 | 549 410 |  |
| Total number of doses of vaccine needed |  | # |  | 718 209 | 607 830 | 606 673 | 648 304 |  |
| Total number of self-blocking syringes needed |  | # |  | 668 658 | 539 753 | 570 684 | 609 845 |  |
| Total number of reconstitution syringes needed |  | # |  | 79 721 | 67 469 | 67 341 | 71 962 |  |
| Total number of safety receptacles needed |  | # |  | 8 318 | 6 740 | 7 082 | 7 568 |  |
| Total budget | Price per dose of vaccine * | $ |  | 0,800 | 0,820 | 0,780 | 0,820 |  |
|  | Total funds needed | $ |  | 657 803 | 569 485 | 545 364 | 582 787 |  |
| Co-financing at the charge of country | Co-financing per dose | $ |  | 0,15 | 0,15 | 0,15 | 0,15 |  |
|  | Total payments made by country | $ |  | 107 731 | 91 175 | 91 001 | 97 246 |  |
| Support applied for from GAVI | Payment made by GAVI per dose | $ |  | 0,650 | 0,670 | 0,630 | 0,670 |  |
|  | Total payments made by GAVI | $ |  | 550 072 | 478 310 | 454 363 | 485 541 |  |

*: in 2006, the country used live births to estimate the vaccination target

According to the settlement of the internal cycles of inclusion in the budget and financing, the Government will normally pay for its share of the financing in July. Payment for purchases made in the course of the first year of co-financed support will be made around July 2008 (give the month and year).

The Government agrees to make its purchases from the Procurement Services Division of UNICEF (Copenhagen) which it chooses as the official supplier for the purchase of all the supplies detailed in the application for support. If this is not possible, the Government agree to conform to the conditions fixed by GAVI and must state clearly at point 5 of the application form what mechanism it proposes. It must moreover explain in detail what the procedures of the national regulatory authority are.

The results obtained by the districts in the matter of vaccination will have to be examined every year by means of a transparent monitoring system. The Government asks GAVI and its partners to provide it with financial and technical assistance in order to promote the vaccination of children, in the manner described in this application for support.

| The Minister of Health (or the senior civil servant): | The Minister of Finances (or the senior civil servant: |
| --- | --- |
| Dr BLEDI Trouin Félix | Mrs ESSOH Lattroh Marie |
| Signature: …………………………………… | Signature: …………………………………… |
| Title : Deputy Director of the cabinet of the Ministry of Health | Title : Technical counsellor to the Ministry of the Economy and Finances |
| Date : 19 April 2007 | Date : 19 April 2007 |

National coordination organisation: Inter-agencies coordination committee for vaccination:

We the undersigned, members of the CCI, are meeting on the 18 April 2007 to examine the present proposal of support. At this meeting, we have approved the proposal on the basis of the supporting documents appended to the proposal.

  - After approval, we have appended the minutes of this meeting under NUMBER 1: ………

| Name/Title | Institution/Organisation | Signature |
| --- | --- | --- |
| Dr BLEDI Trouin Félix | Ministry of Health |  |
| Mrs Lattroh Marie ESSOH | Ministry of the Economy and Finances |  |
| Mrs Soumahoro Assata | Ministry of the Economy and Finances |  |
| Pr. N’DRI Yoman Thérèse | Ministry of Health |  |
| M. KONAN Yao Simplice | Ministry of Health |  |
| Pr YAVO Jean Claude | Ministry of Health |  |
| Pr DAGNAN N’CHO Simplice | Ministry of Health |  |
| Dr OUATTARA SIGUIFOTA Coulibaly Germaine | Ministry of Health |  |
| Dr LOROUGNON Arnaud | Ministry of Health |  |
| M. TRA BI Irié Dénis | Ministry of Health |  |
| Dr NIANGUE Joseph | Ministry of Health |  |
| Dr DRAME Kandjoura | WHO |  |
| Dr EPA Kouacou | UNICEF |  |
| Dr KROMAN SAVANÉ Sita | AMP |  |
| Mrs RICHMOND Marie-Irène | ROTARY |  |

For any questions relating to this application, the Secretariat of GAVI can contact:

| Name: Dr OUATTARA SIGUIFOTA Coulibaly Germaine | Title: Director coordinator of the EPI |
| --- | --- |
| Tel. N°.: 00 (225) 21 24 25 29 | Address: 18 BP 976 Abidjan 18 |
| Fax N°.: 00 (225) 21 24 25 25 |  |
| Email: ouattarasiguifota@yahoo.fr; dc_pev@afnet.net |  |

The Secretariat of GAVI is not able to return the documents and enclosures submitted to each country. Unless there are contrary instructions, the documents could be transmitted to the partners and the collaborators of GAVI.

The Inter-agencies Coordinating Committee for vaccination

## The institutions and partners (particularly partners in development aid, NGOs and research institutes) which support the vaccination services are coordinated and organised by means of an inter-agency organisation (CCI).

The CCI has the responsibility of coordinating and directing the use of the funds allocated by the GAVI Alliance for support for new or under-used vaccines, as well as any other vaccination related activities in the country. Kindly provide the information on the CCI of your country by completing the fields below.

Profile of the CCI

Name of the CCI: Inter-Agencies Coordination Committee

Date of constitution of the current CCI: 22 Mars 2001

Structure (for example, sub-committee, independent organisation): Independent committee

Frequency of meetings: Four (4) ordinary or statutory meetings per year and extraordinary meetings if necessary

Composition :

President : Minister of Health

Secretary : Director coordinator of the EPI

Members :

National Institute of Public Hygiene

Public Health Pharmacy

National Institute of Public Health

Directorate of Infrastructures, Equipment and Maintenance

Directorate of Financial Affairs

WHO

UNICEF

AMP

Principal functions and responsibilities of the CCI:

The CCIA has the role of defining the main strategic trends and general objectives of the vaccination programme in the country. For this reason, the CCIA is particularly responsible for:

- Developing and implementing the national policy of the Expanded Programme of Immunisation;

- Coordinating, harmonizing and assuring the coherence of all the interventions by the various partners;

- Adopting the annual and multi-annual action plans of the Expanded Programme of Immunisation and the budgets related thereto;

- Mobilizing the resources needed for the activities of the Expanded Programme of Immunisation;

- Coordinating and monitoring the implementation of the activities of the various sections of the Expanded Programme of Immunisation;

- Monitoring the realization of the action plans;

- Assessing the implementation of the Expanded Programme of Immunisation.

The three principal strategies aiming at strengthening the role and functions of the CCI during the next 12 months:

1. Strengthening advocacy and the mobilisation of resources;

2. Widening the CCIA to other programmes and partners of the Ministry of Health so as to aim at the integration of the activities concerned with child survival;

3. Strengthening coordination at the regional and district levels within the framework of the strengthening of the health system.

## Data on the vaccination programme

Please complete the information sheet below, using data from available sources. Do not forget to give the name and date of the source used. If possible, use the most recent data and append the source document.

  - Please refer to the global multi-annual plan for vaccination (or equivalent plan) and enclose a complete copy (accompanied by an analytical summary) under the NUMBER: Document n°2

  - Please refer to the last two forms of the joint WHO/UNICEF declaration on diseases preventable by vaccination and append them under NUMBER:

Documents n°3 et n°4

  - Please refer to the documents relating to the policy of the health sector, the budgetary documents and other appropriate reports, surveys, etc.

Table 3.1: Basic information for 2006 (the most recent; specify the dates of the data furnished as well as the source of the data notified)

|  | Figure | Date | Source |
| --- | --- | --- | --- |
| Total population | 19 924 269 | 1998 | National Statistics Institute |
| Rate of infant mortality (per 1000) | 117 | 1998 | National Statistics Institute |
| Surviving infants * | 587 766 | 1998 | National Statistics Institute |
| GNI per inhabitant (US$) | 876 USD | 2006 | Bulletin of the UEMOA |
| Percentage of GDP allocated to health | 1,8% | 2006 | Bulletin of the UEMOA |
| Percentage of government expenditure allocated to health | 5,44% | 2006 | Ministry of the Economy and Finances |

* Surviving children = infants who survive beyond 12 months after birth

** In 2006, the country used live births to estimatee the vaccinal coverage

Please provide additional information with regard to planning and budgeting in your country:

Please give the name and the date of the health planning document used:

National Health Development Plan (PNDS) 1996-2005 has expired and the five-year plan 2007-2011 is in course of development

Is the PPgV (or updated multi-annual plan) in accordance with this document (deadlines, contents, etc.):

The complete multi-annual plan of the Expanded Programme of Vaccination (EPI) 2007-2011 comes within the overall framework of the National Health Development Plan 1996-2005 and within the framework of the strategy document for the reduction of poverty. The major lines of the five year health plan 2007-2011 in course of development were taken into account in the drafting of the PPAC 2007-2011, particularly the introduction of new vaccines and new technologies in the routine EPI and the strengthening of the safety of vaccinal injections.

The PPAC EPI and the five year health plan cover the same period 2007-2011.

Please give the national planning and budgeting cycle for health: January to December

Please give the national planning cycle for vaccination: January to December

Table 3.2: Current vaccinal schedule: traditional vaccines, new vaccines and supplementing with vitamin A (refer to the pages of the PPgV or of the updated multi-annual plan)

| Vaccine (do not use brand name) | Ages of administration of the vaccine (by the routine vaccination services) | Mark with an "x" if the vaccine is administered in: |  | Comments |
| --- | --- | --- | --- | --- |
|  |  | All the country | Only part of the country |  |
| BCG/Polio 0 | From birth | X |  |  |
| DTC-HepB1/ Polio 1 | 6 weeks | X |  |  |
| DTC-HepB2/ polio 2 | 10 weeks | X |  |  |
| DTC-HepB3/ Polio 3 | 14 weeks | X |  | The Hib which will be introduced in the EPI in 2008, will follow the same schedule as DTC-Hep B. |
| Measles | 9 months | X |  |  |
| Yellow fever | 9 months | X |  |  |
| VAT 1 | 1st contact with pregnant women | X |  |  |
| VAT 2 | 4 weeks after 1st contact with pregnant women | X |  |  |

Table 3.3: Trends in routine vaccinal coverage and the rate of morbidity

(according to the last two forms of the joint WHO/UNICEF declaration on diseases preventable by vaccination)

| Trends in vaccinal coverage (percentage)) |  |  |  |  |  | Rate of morbidity of diseases preventable by vaccination |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Vaccine |  | Reported |  | Survey |  | Disease | Number of declared cases |  |
|  |  | 2005 | 2006 | 2005 | 2006 |  | 2005 | 2006 |
| BCG |  | 51% | 77% | NR | 74,4% | Tuberculosis* | ND | ND |
| DTC | DTC1 | 71% | 95% | NR | 80,2% | Diphtheria | ND | ND |
|  | DTC3 | 56% | 77% | 63,3% |  | Pertussis | ND | ND |
| Polio 3 |  | 56% | 77% | 46,4% |  | Polio | 0 | 0 |
| Measles (first dose) |  | 51% | 73% | 60,9% |  | Measles | 4 731 | 226 |
| VAT2+ (pregnant women) |  | 34% | 26% | 66% |  | Neonatal tetanus ** | 31 | 32 |
| Hib3 |  | NR | NR | NR |  | Hib ** | 620 | 571 |
| Yellow fever |  | 52% | 67% | 56,5% |  | Yellow fever | 2 | 2 |
| HepB3 |  | 56% | 77% | 63,3% |  | Seroprevalence Hepatitis B * | ND | ND |
| Supp. with vitamin A | Mothers (<6 weeks after delivery) | ND | ND |  |  |  |  |  |
|  | Infants (>6 months) : | ND | ND |  |  |  |  |  |

* If available ** Note: the FDC mentions meningitis Hib

If the data resulting from the survey is also reproduced in the table below, please give the year when the study was carried out, the complete title and, if need be, the age groups to which the data refers:

External review of the Expanded Programme of Immunisation:  Survey carried out in August 2006 covering the year 2005 and concerning infants from 12 to 23 months and the mothers of infants of less than one year old.

Table 3.4: Basic data and annual objectives (refer to the pages of the PPgV or of the updated multi-annual plan)

| ###### Number of |  | ###### Basic data and objectives |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2006 | Year 1 2007 | Year 2 2008 | Year 3 2009 | Year 4 2010 | Year 5 2011 |
| Births |  | 587 766 | 607 144 | 627 180 | 647 877 | 669 257 | 691 343 |
| Deaths in infancy |  | 2 234 | 71 036 | 73 380 | 75 802 | 78 303 | 80 887 |
| Surviving infants |  | 585 533 | 536 109 | 553 800 | 572 076 | 590 954 | 610 455 |
| Femmes enceintes |  | 996 213 | 1 029 058 | 1 063 018 | 1 098 097 | 1 134 334 | 1 171 567 |
| Target population vaccinated with BCG |  | 451 216 | 516 073 | 564 462 | 596 047 | 635 794 | 656 775 |
| Coverage by BCG * |  | 77% | 85% | 90% | 92% | 95% | 95% |
| Target population vaccinated with VPO3 |  | 449 460 | 455 692 | 498 420 | 526 309 | 561 406 | 579 933 |
| Coverage by VPO3** |  | 77% | 85% | 90% | 92% | 95% | 95% |
| Target population vaccinated with DTC3*** |  | 453 101 | 455 692 | 498 420 | 526 309 | 561 406 | 579 933 |
| Coverage by DTC3** |  | 77% | 85% | 90% | 92% | 95% | 95% |
| Target population vaccinated with DTC1*** |  | 558 144 | 455 692 | 498 420 | 526 309 | 561 406 | 579 933 |
| Rate of loss in year of reference and rate subsequently provided for |  | 25% | 15% | 5% | 5% | 5% | 5% |
| Target population vaccinated with a 3rd dose of ………….. |  |  |  |  |  |  |  |
| …………. Coverage ** |  |  |  |  |  |  |  |
| Target population vaccinated with a 1st dose of VAA |  | 430 981 | 418 165 | 459 654 | 486 264 | 514 130 | 549 410 |
| Rate of loss in year of reference and rate subsequently provided for |  |  | 25% | 20% | 20% | 15% | 15% |
| Target population vaccinated with a 1st dose of vaccine against measles |  | 430 981 | 418 165 | 459 654 | 486 264 | 514 130 | 549 410 |
| Target population vaccinated with a 2nd dose of vaccine against measles |  |  |  |  |  |  |  |
| Coverage of vaccine against measles** |  | 73,33% | 78% | 83% | 85% | 87% | 90% |
| Pregnant women vaccinated with AT + |  | 262 655 | 617 435 | 744 113 | 856 516 | 964 184 | 1 054 410 |
| Coverage by AT+**** |  | 26,37% | 60% | 70% | 78% | 85% | 90% |
| Supplementation Vitamin A | Mothers (<6 weeks after delivery | 87 945 |  |  |  |  |  |
|  | Infants (>6 months) | 141 133 |  |  |  |  |  |
| Annual rate of abandonment of DTC [ ( DTC1 - DTC3 ) / DTC1 ] x 100 |  | 19% | <10% | <10% | <10% | <10% | <10% |
| Annual rate of abandonment of vaccine against measles (for countries which make a application for vaccine against yellow fever) |  | 20% | <10% | <10% | <10% | <10% | <10% |

* Number of infants vaccinated in relation to total births

** Number of infants vaccinated in relation to the number of infants surviving

*** Give the total number of infants vaccinated either with DTC alone or with the combined vaccine

**** Number of pregnant women vaccinated with AT+ in relation to the total number of pregnant women.

Table 3.5: Summary of the current and future budget for vaccination programmes (refer to the pages of the PPgV or of the updated multi-annual plan)

|  | Expenditure | Requirements in Future Resources |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Cost Heading | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | Total 2007 - 2011 |
| Recurring cost | US$ | US$ | US$ | US$ | US$ | US$ | US$ |
| Vaccines | $3 188 394 | $3 913 463 | $7 497 680 | $6 131 813 | $6 042 494 | $6 271 696 | $29 857 145 |
| - Traditional vaccines | $539 139 | $619 144 | $639 919 | $677 702 | $714 097 | $746 390 | $3 397 252 |
| - New and under-used vaccines | $2 649 254 | $3 294 319 | $6 857 761 | $5 454 110 | $5 328 397 | $5 525 306 | $26 459 893 |
| Injection equipment | $301 155 | $411 641 | $493 594 | $525 632 | $560 616 | $587 593 | $2 579 076 |
| Personnel | $1 079 174 | $1 134 953 | $1 182 847 | $1 222 379 | $1 254 620 | $1 287 662 | $6 082 462 |
| - Wages of full-time personnel | $497 543 | $522 163 | $541 788 | $557 543 | $568 694 | $580 068 | $2 770 256 |
| - Daily allowances SAV/ mobile teams | $233 568 | $245 583 | $257 986 | $270 786 | $283 996 | $297 625 | $1 355 976 |
| - Daily allowances for supervision | $348 062 | $367 207 | $383 072 | $394 050 | $401 931 | $409 969 | $1 956 230 |
| Transport | $286 001 | $347 990 | $438 736 | $500 713 | $586 825 | $395 476 | $2 269 740 |
| - Fixed strategy and delivery of vaccines | $241 211 | $292 592 | $367 762 | $419 030 | $490 030 | $332 334 | $1 901 748 |
| - Advanced and mobile strategy | $44 790 | $55 398 | $70 975 | $81 683 | $96 795 | $63 142 | $367 992 |
| Maintenance and overheads | $1 932 586 | $2 002 316 | $2 069 696 | $2 137 272 | $2 272 356 | $2 086 873 | $10 568 513 |
| Cold Chains | $319 305 | $338 919 | $347 775 | $369 159 | $445 014 | $257 310 | $1 758 178 |
| Other Equipment | $43 890 | $62 618 | $89 126 | $102 661 | $128 582 | $96 828 | $479 815 |
| Buildings | $1 569 392 | $1 600 780 | $1 632 795 | $1 665 451 | $1 698 760 | $1 732 735 | $8 330 521 |
| Short-term training | $102 423 | $200 068 | $181 287 | $216 560 | $196 231 | $234 411 | $1 028 557 |
| Social mobilization and IEC | $3 676 | $332 363 | $345 790 | $359 760 | $374 295 | $389 416 | $1 801 624 |
| Control and monitoring of diseases | $88 459 | $729 411 | $630 924 | $676 336 | $674 036 | $732 088 | $3 442 795 |
| Management of the programme | $192 269 | $225 445 | $234 553 | $244 028 | $253 887 | $264 144 | $1 222 057 |
| Other recurring costs | $410 231 | $485 989 | $399 502 | $431 346 | $434 419 | $451 970 | $2 203 225 |
| Sub-total of Recurring Costs | $7 584 368 | $9 783 638 | $13 474 609 | $12 445 839 | $12 649 779 | $12 701 329 | $61 055 195 |
| Capital Cost |  |  |  |  |  |  |  |
| Vehicles | $0 | $832 320 | $969 653 | $848 966 | $954 705 | $998 089 | $4 603 733 |
| Equipment for cold chain | $60 800 | $279 855 | $7 928 | $255 713 | $650 628 | $411 103 | $1 605 228 |
| Other capital costs | $1 000 | $112 200 | $105 601 | $56 775 | $139 634 | $70 661 | $484 870 |
| Sub-total of Capital Costs | $61 800 | $1 224 375 | $1 083 181 | $1 161 454 | $1 744 967 | $1 479 854 | $6 693 831 |
| Vaccination campaigns |  |  |  |  |  |  |  |
| Polio | $2 231 444 | $0 | $0 | $0 | $0 | $0 | $0 |
| Vaccines | $938 497 | $0 | $0 | $0 | $0 | $0 | $0 |
| Operational costs | $1 292 947 | $0 | $0 | $0 | $0 | $0 | $0 |
| Measles | $0 | $0 | $3 194 345 | $0 | $0 | $0 | $3 194 345 |
| Vaccines and injection equipment | $0 | $0 | $974 905 | $0 | $0 | $0 | $974 905 |
| Operational costs | $0 | $0 | $2 219 440 | $0 | $0 | $0 | $2 219 440 |
| Yellow fever | $0 | $0 | $9 815 703 | $0 | $0 | $0 | $9 815 703 |
| Vaccines and injection equipment | $0 | $0 | $6 093 192 | $0 | $0 | $0 | $6 093 192 |
| Operational costs | $0 | $0 | $3 722 510 | $0 | $0 | $0 | $3 722 510 |
| Neonatal tetanus | $0 | $2 795 848 | $4 709 160 | $5 524 578 | $0 | $0 | $13 029 586 |
| Vaccines and injection equipment | $0 | $507 861 | $841 635 | $971 413 | $0 | $0 | $2 320 909 |
| Operational costs | $0 | $2 287 988 | $3 867 525 | $4 553 165 | $0 | $0 | $10 708 677 |
| Sub-total of Campaign Costs | $2 231 444 | $2 795 848 | $17 719 208 | $5 524 578 | $0 | $0 | $26 039 634 |
| Shared costs |  |  |  |  |  |  |  |
| Shared costs of personnel | $5 207 944 | $5 503 416 | $5 800 646 | $6 092 971 | $6 388 802 | $6 694 029 | $30 479 865 |
| Shared costs of transport | $159 025 | $162 206 | $165 450 | $168 759 | $172 134 | $175 577 | $844 125 |
| Buildings | $1 297 200 | $12 750 | $31 212 | $0 | $32 473 | $0 | $76 435 |
| Sub-total of Shared Costs | $6 664 169 | $5 678 372 | $5 997 308 | $6 261 730 | $6 593 409 | $6 869 606 | $31 400 425 |
| GENERAL TOTAL | $16 541 781 | $19 482 233 | $38 274 306 | $25 393 601 | $20 988 156 | $21 050 789 | $125 189 085 |
| Routine Vaccination (Fixed Strategy) | $12 750 282 | $14 726 641 | $17 929 078 | $17 400 555 | $18 454 321 | $18 518 369 | $87 028 964 |
| Routine Vaccination (SAV and Mobile) | $1 560 054 | $1 959 743 | $2 626 020 | $2 468 469 | $2 533 835 | $2 532 420 | $12 120 487 |
| Vaccination Campaigns | $2 231 444 | $2 795 848 | $17 719 208 | $5 524 578 | $0 | $0 | $26 039 634 |

Please list on the tables below the sources of financing for each category of cost (if known). Please also indicate which vaccination programmes have their costs covered by the Government budget and which are covered by the partners in development aid (or by the GAVI Alliance) giving the names of these partners.

Table 3.6: Summary of financing and current and future sources of financing (or refer to the pages of the PPgV or of the updated multi-annual plan)

|  |  | Estimated financing per annum in US$ (thousands) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Budget item | Source of financing | Year of reference 2005 | Year 1 2008 | Year 2 2009 | Year 3 2010 | Year 4 2011 | Year 5 2012 |
| Recurring cost (routine vaccination) |  | 7 584 368 | 9 783 638 | 13 474 610 | 12 445 839 | 12 649 779 | 12 701 329 |
| Vaccines | Sub-total 1 | 3 188 394 | 3 913 463 | 7 497 680 | 6 131 813 | 6 042 494 | 6 271 696 |
|  | Government | 768 084 | 1 278 008 | 2 011 471 | 1 768 525 | 1 779 776 | 1 851 451 |
|  | UNICEF | 300 906 | - | - | - | - | - |
|  | GAVI | 2 119 403 | 2 635 455 | 5 486 209 | 4 363 288 | 4 262 718 | 4 420 244 |
| - Traditional vaccines | Sub-total 1.1 | 539 139 | 619 144 | 639 919 | 677 702 | 714 097 | 746 390 |
|  | Government | 238 233 | 619 144 | 639 919 | 677 702 | 714 097 | 746 390 |
|  | UNICEF | 300 906 | - | - | - | - | - |
| - New and under-used vaccines | Sub-total 1.2 | 2 649 254 | 3 294 319 | 6 857 761 | 5 454 110 | 4 847 779 | 5 525 306 |
|  | Government | 529 851 | 658 864 | 1 371 552 | 1 090 822 | 1 065 679 | 1 105 061 |
|  | GAVI | 2 119 403 | 2 635 455 | 5 486 209 | 4 363 288 | 4 262 718 | 4 420 244 |
| Injection equipment | Sub-total 2 | 301 155 | 411 641 | 493 594 | 525 632 | 560 616 | 587 593 |
|  | Government | 195 393 | 312 191 | 350 653 | 374 693 | 399 612 | 421 276 |
|  | UNICEF | 13 400 | - | - | - | - | - |
|  | GAVI | 92 362 | 99 450 | 142 941 | 150 939 | 161 004 | 166 317 |
| Personnel | Sub-total 3 | 1 079 174 | 1 134 953 | 1 182 847 | 1 222 379 | 1 254 620 | 1 287 662 |
| - Wages of full-time personnel | Government | 497 543 | 522 163 | 541 788 | 557 543 | 568 694 | 580 068 |
| - Daily allowances SAV/ mobile teams | Government | 233 568 | 245 583 | 257 986 | 270 786 | 283 996 | 297 625 |
| - Daily allowances for supervision | Government | 348 062 | 367 207 | 383 072 | 394 050 | 401 931 | 409 969 |
| Transport | Sub-total 4 | 286 001 | 347 990 | 438 736 | 500 713 | 586 825 | 395 476 |
| - Fixed strategy and delivery of vaccines | Sub-total 4.1 | 241 211 | 292 592 | 367 762 | 419 030 | 490 030 | 332 334 |
|  | GAVI | - | - | - | 419 030 | 490 030 | 332 334 |
|  | Government | 241 211 | 292 592 | 367 762 | - | - | - |
| - Advanced and mobile strategy | Sub-total 4.2 | 44 790 | 55 398 | 70 975 | 81 683 | 96 795 | 63 142 |
|  | Government | 44 790 | - | - | - | - | - |
|  | GAVI |  | 55 398 | 70 975 | 81 683 | 96 795 | 63 142 |
|  |  | Estimated financing per annum in US$ (thousands) |  |  |  |  |  |
| Budget item | Source of financing | Year of reference 2005 | Year 1 2008 | Year 2 2009 | Year 3 2010 | Year 4 2011 | Year 5 2012 |
| Maintenance overheads | Sub-total 5 | 1 932 586 | 2 002 316 | 2 069 697 | 2 137 272 | 2 272 356 | 2 086 873 |
| Cold Chains | Sub-total 5.1 | 319 305 | 338 919 | 347 776 | 369 159 | 445 014 | 257 310 |
|  | UNICEF | 319 305 | 84 730 | 168 160 | 184 580 | 222 507 | 128 655 |
|  | Government | - | 169 459 | 173 888 | 184 580 | 222 507 | 128 655 |
|  | GAVI |  | 84 730 | 5 728 | - | - | - |
| Other Equipment | Sub-total 5.2 | 43 890 | 62 618 | 89 126 | 102 661 | 128 582 | 96 828 |
|  | Government | 43 890 | 62 618 | 89 126 | 102 661 | - | 96 828 |
|  | GAVI |  |  |  |  | 128 582 |  |
| Buildings | Government | 1 569 392 | 1 600 780 | 1 632 795 | 1 665 451 | 1 698 760 | 1 732 735 |
| Short-term training | Sub-total 6 | 102 423 | 200 068 | 181 287 | 216 560 | 196 231 | 234 411 |
|  | Government | 13 520 | - | - | - | - | - |
|  | UNICEF | 34 568 | - | - | - | - | - |
|  | GAVI | 26 241 | 200 068 | - | - | - | - |
|  | HKI | 1 250 |  |  |  |  |  |
|  | AMP | 13 591 |  |  |  |  |  |
|  | WHO | 13 253 | - | 181 287 | 216 560 | 196 231 | 234 411 |
| Social mobilisation and IEC | Sub-total 7 | 3 676 | 332 363 | 345 790 | 359 760 | 374 295 | 389 416 |
|  | GAVI | 3 676 | - | - | - | - | - |
|  | UNICEF |  | 332 363 | 345 790 | 359 760 | 374 295 | 389 416 |
| Control and monitoring of diseases | Sub-total 8 | 88 459 | 729 411 | 630 924 | 676 336 | 674 036 | 732 088 |
|  | WHO | 88 459 | 729 411 | 630 924 | 676 336 | 674 036 | 732 088 |
| Management of the programme | WHO | 192 269 | 225 445 | 234 553 | 244 028 | 253 887 | 264 144 |
| Other recurring costs | Sub-total 9 | 410 231 | 485 989 | 399 502 | 431 346 | 434 419 | 451 970 |
|  | Government | 285 231 | 485 989 | 399 502 | 431 346 | 434 419 | 451 970 |
|  | WHO | 50 000 | - | - | - | - | - |
|  | UNICEF | 75 000 | - | - | - | - | - |
| Costs of investment (routine vaccination) |  | 61 800 | 1 224 375 | 1 083 181 | 1 161 454 | 1 744 967 | 1 479 854 |
| Vehicles | Sub-total 10 | - | 832 320 | 969 653 | 848 966 | 954 705 | 998 089 |
|  | WHO |  |  |  | 250 000 | - | - |
|  | UNICEF |  |  |  | 248 966 | - | - |
|  | Government | - | 832 320 | 969 653 | 350 000 | 954 705 | 998 089 |
| Equipment for cold chain | Sub-total 11 | 60 800 | 279 855 | 7 928 | 255 713 | 650 628 | 411 103 |
|  | Government | 8 640 | - | 7 928 | - | - | - |
|  | UNICEF | 39 064 | 229 500 | - | - | - | - |
|  | Japanese Cooperation | - | - | - | 255 713 | 650 628 | 411 103 |
|  |  | Estimated financing per annum in US$ (thousands) |  |  |  |  |  |
| Budget item | Source of financing | Year of reference 2005 | Year 1 2008 | Year 2 2009 | Year 3 2010 | Year 4 2011 | Year 5 2012 |
|  | GAVI | 13 096 | 50 355 | - | - | - | - |
| Other capital costs | Sub-total 12 | 1 000 | 112 200 | 105 601 | 56 775 | 139 634 | 70 661 |
|  | Government | 1 000 | 112 200 | 105 601 | - | 139 634 | - |
|  | WHO | - | - | - | - | - | 70 661 |
|  | GAVI | - | - | - | 56 775 | - | - |
| Vaccination campaigns |  | 2 231 444 | 2 795 848 | 17 719 208 | 5 524 578 | - | - |
| Polio | Sub-total 13 | 2 231 444 | - | - | - | - | - |
| Vaccines | Sub-total 13.1 | 938 497 | - | - | - | - | - |
|  | UNICEF | 938 497 | - | - | - | - | - |
| Operational costs | Sub-total 13.2 | 1 292 947 | - | - | - | - | - |
|  | Government | 25 859 | - | - | - | - | - |
|  | UNICEF | 400 814 | - | - | - | - | - |
|  | WHO | 788 698 | - | - | - | - | - |
|  | ROTARY | 77 577 | - | - | - | - | - |
| Measles | Sub-total 14 | - | - | 3 194 345 | - | - | - |
| Vaccines and injection equipment | Sub-total 14. 1 | - | - | 974 905 | - | - |  |
|  | UNICEF | - | - | 974 905 | - | - |  |
| Operational costs | Sub-total 14.2 | - | - | 2 219 440 | - | - | - |
|  | Government | - | - | 1 109 720 | - | - | - |
|  | WHO | - |  | 1 109 720 |  |  |  |
| Yellow fever | Sub-total 15 | - | - | 9 815 703 | - | - | - |
| Vaccines and injection equipment | Sub-total 15.1 |  | - | 6 093 192 | - | - | - |
|  | GAVI |  | - | 6 093 192 | - | - | - |
| Operational costs | Sub-total 15.2 | - | - | 3 722 510 | - | - | - |
|  | Government | - | - | 1 861 255 | - | - | - |
|  | GAVI | - | - | 1 861 255 | - | - | - |
| Neonatal tetanus | Sub-total 16 | - | 2 795 848 | 4 709 160 | 5 524 578 | - | - |
| Vaccines and injection equipment | Sub-total 16.1 | - | 507 861 | 841 635 | 971 413 | - | - |
|  | UNICEF | - | 507 861 | 841 635 | 971 413 | - | - |
| Operational costs | Sub-total 16.2 | - | 2 287 988 | 3 867 525 | 4 553 165 | - | - |
|  | Government |  |  | 309 402 | 455 316 | - | - |
|  | WHO |  |  | 464 103 | - | - | - |
|  | UNICEF | - | 2 287 988 | 3 094 020 | 4 097 848 | - | - |
| TOTAL |  | 9 877 612 | 13 803 861 | 32 276 999 | 19 131 870 | 14 394 747 | 14 181 183 |

## New Vaccines and under-used vaccines (SVN)

Please summarize the aspects of the global multi-annual vaccination plan relating to the introduction of new vaccines and under-used vaccines (refer to PPgV or updated multi-annual plan). Please list the key points relating to the decision-making process (data taken into account, etc.):

With the aim of contributing to reaching the millennium development objectives (particularly objective N°4), the Government of the Ivory Coast has put in place a certain number of strategies to bring about an improvement in child survival. This is how one of the major priorities of the PPAC 2007-2011 is the introduction of the pentavalent vaccine in the routine EPI in view of the high rate of Hib infections.

Please describe (or indicate the point of the PPgV or the updated multi-annual plan relating thereto) the way in which your country intends to arrive at financial viability for the new vaccines selected, the way in which the co-financing shares will be paid as well as all the other points relating to financial viability which have been taken into account:

The strategies for the financial viability of the EPI for the period 2007-2011 are concentrated around the following three points:

-	Strengthening the Government's contribution in the EPI

-	Securing "probable financing" for the programme

-	Mobilisation of additional resources for the programme,

-	Improvement in the programme's management

The Ministry of Health will sign a protocol of agreement with the UNICEF office at the country level and will pay its shares each year in July. A detailed report on the co-financing will be included in the annual GAVI progress report.

Please list the vaccines to be introduced with the support of the GAVI Alliance (also give the presentation):

- Pentavalent DTC-HepB-Hib vaccine in January 2008 in liquid form in vial of one dose

- Vaccine against yellow fever in January 2008 in lyophilised form in vial of 10 doses

Evaluation of the rate of morbidity in the diseases concerned (if available):

| Disease | Title of evaluation | Date | Results |
| --- | --- | --- | --- |
|  | ND |  |  |

If the new or under-used vaccines have already been introduced, please explain in detail what lessons have been drawn at the level of storage capacity, the prevention of the risks of accidental freezing, training personnel, the cold chain, logistics, the rate of abandonment, the rate of loss, etc., and the measures taken with a view to their implementation in the new plan:

| Lessons drawn | Actions |
| --- | --- |
| 1. the gradual introduction of the tetravalent vaccine between 2001 and 2003, entailed major difficulties in the management of vaccine stocks, for reporting and data management. | Decision to introduce the pentavalent vaccine immediately throughout all the districts in the country from January 2008. |
| 2. the training of vaccinating personnel in vaccinal techniques including the conservation of vaccines, was too far removed from the introduction. This training was not therefore capitalised on at the introduction. | Training of vaccinators planned for the last quarter 2007. |
| 3. the management tools were revised after the introduction. This resulted in difficulties of reporting on the former tool. | Revision of management supports planned for the last quarter 2007. |
| 4. the absence of strengthening of the system for monitoring the loss rate entailed a wastage of the new vaccine which cost dearly. | Training personnel in stock management planned for the last quarter and installation of a tool for monitoring losses at all levels. |

First priority vaccine

  - Please complete table A.1 in the Appendix (a calculation sheet in Excel) for the first vaccine applied for.

In order to complete table A.1, you must update the figures in table β and table µ of the Appendix 1 by referring to the last prices and tariffs of the UNICEF Procurement Services Division published on the UNICEF website.

The most recent guide by GAVI to the selection of vaccination products is available at www.unicef.org/supply. In order to know the category of country to which you belong and the minimum co-financing share for each vaccine in each group, refer to the directives of the GAVI Alliance intended for countries that wish to present a application for SVN support.

Please indicate the requirements in the table below: number of doses of vaccine, presentation of the vaccine, associated injection equipment and safety receptacles for the first vaccine applied for, in conformity with the calculations made in Appendix 1.

| Table 4.1a: Equipment required for the introduction of DTCHepB Hib (specify the antigen) vaccination with liquid pentavalent, vial of one dose (specify the presentation of the vaccine) |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Year of reference | Year 1 2008 | Year 2 2009 | Year 3 2010 | Year 4 2011 | Year 5 20… |  |
| National objective of number of children to vaccinate | # | 441 135 | 498 420 | 526 309 | 561 406 | 579 933 |  |  |
| Total number of doses of vaccine needed | # |  | 1 962 529 | 1 657 873 | 1 768 429 | 1 826 789 |  |  |
| Total number of self-blocking syringes needed | # |  | 2095420 | 1752609 | 1869482 | 1931177 |  |  |
|  |  | Year of reference | Year 1 2008 | Year 2 2009 | Year 3 2010 | Year 4 2011 | Year 5 20… |  |
| Total number of reconstitution syringes needed | # |  | - | - | - | - |  |  |
| Total number of safety receptacles needed | # |  | 23 259 | 19 454 | 20 751 | 21 436 |  |  |

Please indicate in the table below the price per dose, the total amount of funds needed to respond to the demand, the co-financing share at the charge of the country and the funds applied for from GAVI, according to the calculations made on the calculation sheet in Appendix 1.

|  | Table 4.2a : Financial requirements for the introduction of DTCHepBHib vaccination (specify the antigen) with liquid pentavalent, vial of one dose (specify the presentation of the vaccine) |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Year of reference 2006 | Year 1 2008 | Year 2 2009 | Year 3 2010 | Year 4 2011 | Year 5 2012 |  |
| Total budget |  | Price per dose * | $ |  | 3,200 | 2,900 | 2,650 | 2,300 |  |  |
|  |  | Total funds needed | $ |  | 6516765 | 5001338 | 4896550 | 4412372 |  |  |
| Co-financing at the charge of country |  | Co-financing per dose | $ |  | 0,10 | 0,10 | 0,10 | 0,10 |  |  |
|  |  | Total payments made by country | $ |  | 196253 | 165787 | 176843 | 182679 |  |  |
| GAVI co-financing |  | Payment made by GAVI per dose | $ |  | 3,100 | 2,800 | 2,550 | 2,200 |  |  |
|  |  | Total payments made by GAVI | $ |  | 6320513 | 4835551 | 4719708 | 4229693 |  |  |

* The total price per dose includes the costs of the vaccine plus costs of transport, supplies, insurance, visa, etc.

Second priority vaccine

  - Please complete table A.2 in Appendix 1 for the second vaccine applied for after having updated the data in table β and table µ of the Appendix 1 by referring to the last prices and tariffs of the UNICEF Procurement Services Division.

The most recent guide by GAVI to the selection of vaccination products is available at www.unicef.org/supply. In order to know the category of country to which you belong and the minimum co-financing share for each vaccine in each group, refer to the directives of the GAVI Alliance intended for countries that wish to present an application for SVN support.

Please indicate the requirements in table 4.1b below: number of doses of vaccine, presentation of the vaccine, associated injection equipment and safety receptacles, in conformity with the calculations made in Appendix 1.

| Table 4.1b: Equipment required for the introduction of the vaccine against yellow fever (specify the antigen) vaccination with lyophilised form, vial of 10 doses (specify the presentation of the vaccine) |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Year of reference 2006 | Year 1 2008 | Year 2 2009 | Year 3 2010 | Year 4 2011 | Year 5 20… |
| National objective of number of children to vaccinate | # |  | 459 654 | 486 264 | 514 130 | 549 410 |  |
| Total number of doses of vaccine needed | # |  | 718 209 | 607 830 | 606 673 | 648 304 |  |
| Total number of self-blocking syringes needed | # |  | 668 658 | 539 753 | 570 684 | 609 845 |  |
| Total number of reconstitution syringes needed | # |  | 79 721 | 67 469 | 67 341 | 71 962 |  |
| Total number of safety receptacles needed | # |  | 8 318 | 6 740 | 7 082 | 7 568 |  |

Please indicate in the table 4.2b below the price per dose, the total amount of funds needed to respond to the demand, the co-financing share at the charge of the country and the funds applied for from GAVI, according to the calculations made on the calculation sheet in Appendix 1.

| Table 4.2b: Financial requirements for the introduction of the vaccine against yellow fever (specify the antigen) vaccination with lyophilised form, vial of 10 doses (specify the presentation of the vaccine) |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Year of reference 2006 | Year 1 2008 | Year 2 2009 | Year 3 2010 | Year 4 2011 | Year 5 20… |
| Total budget | Price per dose * | $ |  | 0,800 | 0,820 | 0,780 | 0,820 |  |
|  | Total funds needed | $ |  | 657 803 | 569 485 | 545 364 | 582 787 |  |
| Co-financing at the charge of country | Co-financing per dose | $ |  | 0,15 | 0,15 | 0,15 | 0,15 |  |
|  | Total payments made by country | $ |  | 107 731 | 91 175 | 91 001 | 97 246 |  |
| GAVI co-financing | Payment made by GAVI per dose | $ |  | 0,650 | 0,670 | 0,630 | 0,670 |  |
|  | Total payments made by GAVI | $ |  | 550 072 | 478 310 | 454 363 | 485 541 |  |

* The total price per dose includes the costs of the vaccine plus costs of transport, supplies, insurance, visa, etc.

  - Please complete new tables A.3 and A.4 for each new vaccine applied for.

  - Please complete new tables 4.1 and 4.2 for each new vaccine applied for.

Purchases and management of new vaccines and under-used vaccines

a) Please indicate the way in which the funds will be used and managed, including purchases of vaccines (GAVI expects the majority of countries to purchase their vaccines and injection equipment through UNICEF):

The country will be supplied with pentavalent vaccine through the UNICEF Procurement Services Division. The government share of the purchase of new vaccines and under-used vaccines will be paid to the UNICEF country account in accordance with the draft-agreement signed for this purpose.

The 100,000 $ US which accompanies approval of the introduction of the new vaccine will mainly be used for the preparatory activities of this introduction, the improvement of the cold chain and the renewal of management supports.

The CCIA will ensure the monitoring of the preparatory activities of the introduction of the new vaccine and the use of the funds. A detailed report of the activities will be included in the annual progress report.

b) If another mechanism should be used for the purchase and delivery of supplies (whether they are financed by the country or by the GAVI Alliance), kindly enclose the following documents: following documents in proof:

- Documents proving that the functions of the national regulatory authority conform to the WHO requirements for the purchase of quality vaccines and equipment.

- Delivery to the country of the supplies purchased conforms to the co-financing plan.

- The national purchasing principles and processes.

Not relevant

c) Describe the introduction of the vaccines (refer to the PPgV or the updated multi-annual plan).

The introduction of the pentavalent will be made at the start in the country's 79 health districts from January 2008 to replace the tetravalent vaccine currently used. The vaccine schedule will be identical to that of the tetravalent.

The following strategies will support the introductory process of the pentavalent vaccine:

- Strengthening the capacities of personnel

- Improvement in the supply of vaccines, logistics and the safety of injections

- Improvement of access to vaccination services

- Strengthening of supervision and the monitoring system

- Strengthening advocacy and communication in favour of vaccination.

d) Please indicate the way in which the funds allocated by GAVI should be transferred to the country (if need be)

The funds allocated by GAVI will be routed the country by bank transfer according to the same procedures used during phase 1.

e) Please indicate the way in which the co-financing shares will be paid (as well as the person responsible for this).

The Ministry of Health will sign a draft agreement with the UNICEF country office and will pay its shares in July each year. A bank transfer will be made out in favour of UNICEF by the Ministry for the Economy and Finances on the request of the Directorate of Financial Services of the Ministry of Health, on a mutually agreed bank account.

The Director of Financial Services of the Ministry of Health, a member of the CCIA, will be responsible for this operation..

f) Please describe the way in which the coverage for the new vaccine will be controlled and reported (refer to the PPgV or the updated multi-annual plan).

The tools for the management of vaccines and vaccinations will be revised to incorporate the new pentavalent vaccine.

Vaccinations carried out will be manually compiled on the basis of tally cards and will be reported on the monthly report sheet at the level of each health unit. A summary of all the reports will be drawn up monthly at the level of the health district followed by an analysis of the data and feedback to each health unit.

The data compiled on an Excel spreadsheet at district level will be transmitted to the central level through the monthly report.

The reports from all the districts will be compiled and analyzed. Feedback will be given to all districts through the quarterly monitoring meetings.

Regular supervision visits will be made at each level to monitor performances and to take the appropriate corrective measures where necessary.

The results of the programme will be periodically shared with all the actors involved in vaccination at the national and international level.

If your application for support for new vaccines has been approved, you have the right to a fixed sum of US$ 100,000 intended to promote the introduction of each new vaccine. If you wish to receive this sum, please return the "bank form" enclosed (Appendix 2) with this application, if this has not already been done for other types of support granted by the GAVI Alliance.

## Observations and recommendations of the Inter-agencies Coordination Committee for Vaccination (CCI) and other partners in development aid in the health sector.

The collaboration between the Global Alliance for Vaccines and Immunisation and the Republic of the Ivory Coast, which began in 2001, has so far been profitable. The EPI indeed received support for the strengthening of vaccination services and successfully introduced the tetravalent vaccine in the routine vaccination programme thanks to the support of GAVI. This introduction has made it possible to strengthen vaccination activities by particularly awaking the community's interest in vaccination while adding new antigens to the traditional vaccinal schedule.

The CCIA notes with satisfaction the progress made in these past two years by the improvement of performances of the districts in spite of the difficult socio-political situation that the country has experienced since 2002.

Indeed, the coverage of the DTC-HepB 3 vaccine went from 56% to 77% between 2005 and 2006; the performances of disease monitoring were satisfactory and the recurring measles epidemics could be controlled.

However, the CCIA notes a difference between the vaccinal coverage of VCAr (73%) and VAA (67%), two antigens which are administered at the same period in the vaccinal schedule. This difference is primarily related to out-of-stock conditions noted for the VAA.

With the aim of consolidating these advantages, extending the benefits of vaccination to more children and contributing to reaching the millennium development objectives (particularly objective N°4), considering the heavy burden of Hib disease at the regional level and in the country, and noting the out-of-stock conditions of the VAA, the CCIA, meeting on the 18 April 2007, examined and approved this proposal to GAVI and strongly recommends the request for support for delivery of the vaccine against yellow fever and the introduction of the pentavalent vaccine into the routine vaccination programme of the Ivory Coast.

## Documents to be enclosed

| Document | NUMBER OF DOCUMENT | Duration * |
| --- | --- | --- |
| Global multi-annual plan (PPgV) or updated multi-annual plan | 2 |  |
| Form of joint WHO/UNICEF declaration (the two last) | 3 et 4 |  |
| Plan of introduction of the new vaccine (if it is not already included in the PPgV or the updated multi-annual plan) | 5 |  |
| Endorsed minutes of the meeting of the CCI where the application to GAVI for support for the new vaccines and under-used vaccines was examined (SVN) | 1 |  |
| Endorsed minutes of the meeting of the national body of coordination where the GAVI proposal was approved | NR |  |
| Minutes of the last three meetings of the CCI. | 7 |  |
| Working plan of the CCI for the 12 months to come. | 6 |  |
| Analysis tool of costs and financing | 8 |  |
| Appendix 1: Calculation of the supplies needed and the co-financing budget | 9 |  |

*If needed, give the duration of the plan / of the evaluation / of the document.

|  | MINISTRY FOR HEALTH AND PUBLIC HYGIENE --------------- DIRECTORATE GENERAL OF HEALTH --------------- DIRECTORATE OF COMMUNITY HEALTH --------------- |  | RÉPUBLIC OF THE IVORY COAST Unity – Discipline - Labour |
| --- | --- | --- | --- |
|  | COORDINATION DIRECTORATE OF THE EXPANDED PROGRAMME OF IMMUNIZATION |  |  |

Reponses to GAVI conditions to introduce new vaccines

(DTP-HepB-Hib pentavalent and yellow fever vaccines)

12th September 2007

Introduction

In April 2007, the Ivory Coast submitted a request for new vaccine support from the Global Alliance for Vaccination Immunization (GAVI) to introduce immunization against Hib using the DTP-HepB-Hib pentavalent vaccine and to strengthen routine immunization against yellow fever.

In reply to this request, GAVI notified its conditional approval to the Minister of Health and Public Hygiene, in a letter GAVI/07/161/ir/sk of 29th June 2007, expressed as follows:

« To be eligible for definitive approval, the country must fulfil the following conditions: New Vaccine Support (Penta + yellow fever) :

- Carry out a thorough analysis of the cold chain, showing the space which is currently available and the volumetric capacity required once the pentavalent vaccine has been added”

Also, the following is also specified in this letter:

- “As yellow fever immunization is already included in the routine immunization programme, GAVI will complement the existing government obligations regarding yellow fever vaccines with additional assistance. The country will also be required to finance jointly the additional share of assistance in accordance with joint financing rules”

- “The Ministry of Health must work on results already obtained in collaboration with the Ministry of Finance and fix the joint financing of the pentavalent vaccine as being its objective up to a sum which is at least equal to the financial contribution of previous years for the purchase of new and under-used vaccines”

- “In addition to meeting the above conditions, in order to obtain the grant to introduce the vaccine, the country must draw up a budgetary table itemising overall non-vaccine requirements for the introduction and how the allocated funds will be used to bridge deficits”

The aim of this document, which has been shared with ICC members, is to provide responses to the conditions and advice given by GAVI.

1. Carry out a thorough analysis of the cold chain, showing the space which is currently available and the volumetric capacity required once the pentavalent vaccine has been added

The country has a central national vaccine depot at the National Institute of Public Hygiene (INHP) in Abidjan and 10 regional depots located in the regional INHP outposts in Bouaké, Korhogo, Daloa, Yamoussoukro, Abengourou, Bondoukou, Odienné, Man, Gagnoa and San Pedro.

Table 1 : Existing volumetric capacity of the cold chain at central and regional levels in 2007

| Vaccine depot | Existing gross storage volume (litre) |  | Net storage volume (litre) |  |
| --- | --- | --- | --- | --- |
|  | Positive | Negative | Positive | Negative |
| Central depot at INHP Abidjan | 85 000 | 40 000 | 24 286 | 11 429 |
| INHP Bouaké | 8 000 | 20 000 | 2 286 | 5 714 |
| INHP Korhogo | 8 000 | 20 000 | 2 286 | 5 714 |
| INHP Daloa | 12 000 | 20 000 | 3 429 | 5 714 |
| INHP Yamoussoukro | 40 000 | 20 000 | 11 429 | 5 714 |
| INHP Abengourou | 8 000 | 20 000 | 2 286 | 5 714 |
| INHP Bondoukou | 8 000 | - | 2 286 | - |
| INHP Odienné | 8 000 | - | 2 286 | - |
| INHP Man | 8 000 | 20 000 | 2 286 | 5 714 |
| INHP Gagnoa | 8 000 | - | 2 286 | - |
| INHP San Pedro | 12 000 | 20 000 | 3 429 | 5 714 |

Estimates of requirements and existing capacities are analysed in the following tables which show the situation at central and regional level and which are based on objectives for vaccine cover, loss rates, the vaccine schedule and vaccine presentation contained in the PPAC (full multi-annual plan)

Table 2 : Capacity and cost of positive storage at central level from 2008 to 2011

|  |  | Formula | Year 1 2008 | Year 2 2009 | Year 3 2010 | Year 4 2011 |
| --- | --- | --- | --- | --- | --- | --- |
| A | Annual positive volume requirements including new vaccine(s) (litres) | Sum of all vaccines except Polio and VAR Volume of a vaccine = total number of doses of the vaccine multiplied by the volume occupied by the packaging of each dose | 28 163 | 29 905 | 31 806 | 33 177 |
| B | Annual positive capacity (litres) | Net available volume = gross volume divided by 3,5 (volume factor) | 24 286 | 24 286 | 24 286 | 24 286 |
| C | Minimum estimated number of annual dispatches required for the actual cold chain capacity | A / B | 1,16 | 1,23 | 1,31 | 1,37 |
| D | Annual number of dispatches | National directives : 2 supplies per year | 2 | 2 | 2 | 2 |
| E | Difference (if the case arises) | ((A / D) - B) | -10 205 | - 9 334 | - 8 383 | - 7 698 |
| F | Estimate of cost of expansion | $US | 0 | 0 | 0 | 0 |

Line E in table 2 shows that given a supply frequency of twice a year, storage capacities are sufficient at central level for the pentavalent to be introduced in the Ivory Coast in 2008 to 2001. It is not therefore necessary to reinforce the cold chain at central level.

At an intermediary level, storage capacities are analysed for each of the 10 regional vaccine depots in the country. Table 3 shows a summary of this analysis in terms of volume required, available capacity and the gap.

Given the quarterly supply frequency used by the country, table 3 shows that all the regional depots have a surplus positive storage capacity. Storage capacities at regional levels are therefore sufficient for the pentavalent to be introduced between 2008 and 2011. There is no need to reinforce the cold chain at a regional level.

Detailed estimates regarding this analysis can be found in the appendix for each of the depots.

Table 3 : Summary of positive storage capacities at the level of the 10 regional depots to 2008 to 2011.

| Regional vaccine depot | Year 2008 |  |  |  | Year 2009 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Required (annual positive volume requirements, including new vaccines) A | Available (positive annual capacity) B | Annual number of dispatches C | Gap (difference if the case arises) ((A / C) - B) | Required annual positive volume requirements, including new vaccines)) A | Available (positive annual capacity) B | Annual number of dispatches C | Gap (difference if the case arises) ((A / C) - B) |
| Bouaké | 1 955 | 2 286 | 4 | -1 797 | 2 074 | 2 286 | 4 | -1 767 |
| Korhogo | 1 497 | 2 286 | 4 | -1 911 | 1 588 | 2 286 | 4 | -1 889 |
| Daloa | 2 705 | 3 429 | 4 | -2 752 | 2 869 | 3 429 | 4 | -2 711 |
| Yamoussoukro | 2414 | 11 429 | 4 | -10 825 | 2561 | 11 429 | 4 | -10 788 |
| Abengourou | 659 | 2 286 | 4 | -2 121 | 699 | 2 286 | 4 | -2 111 |
| Bondoukou | 1 536 | 2 286 | 4 | -1 902 | 1 628 | 2 286 | 4 | -1 879 |
| Odienné | 465 | 2 286 | 4 | -2 169 | 493 | 2 286 | 4 | -2 162 |
| Man | 2 983 | 2 286 | 4 | -1 540 | 3 165 | 2 286 | 4 | -1 494 |
| Gagnoa | 1 501 | 2 286 | 4 | -1 910 | 1 591 | 2 286 | 4 | -1 888 |
| San Pedro | 3 573 | 3 429 | 4 | -2 535 | 3 790 | 3 429 | 4 | -2 481 |

| Regional vaccine depot | Year 2010 |  |  |  | Year 2011 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Required (annual positive volume requirements, including new vaccines) A | Available (positive annual capacity) B | Annual number of dispatches C | Gap (difference if the case arises) ((A / C) - B) | Required annual positive volume requirements, including new vaccines)) A | Available (positive annual capacity) B | Annual number of dispatches C | Gap (difference if the case arises) ((A / C) - B) |
| Bouaké | 2 205 | 2 286 | 4 | -1 734 | 2 301 | 2 286 | 4 | -1 710 |
| Korhogo | 1 689 | 2 286 | 4 | -1 863 | 1 761 | 2 286 | 4 | -1 845 |
| Daloa | 3 052 | 3 429 | 4 | -2 666 | 3 183 | 3 429 | 4 | -2 633 |
| Yamoussoukro | 2 724 | 11 429 | 4 | -10 748 | 2 841 | 11 429 | 4 | -10 718 |
| Abengourou | 744 | 2 286 | 4 | -2 100 | 776 | 2 286 | 4 | -2 092 |
| Bondoukou | 1 726 | 2 286 | 4 | -1 854 | 1 801 | 2 286 | 4 | -1 835 |
| Odienné | 523 | 2 286 | 4 | -2 155 | 545 | 2 286 | 4 | -2 149 |
| Man | 3 366 | 2 286 | 4 | -1 444 | 3 511 | 2 286 | 4 | -1 408 |
| Gagnoa | 1 686 | 2 286 | 4 | -1 864 | 1 759 | 2 286 | 4 | -1 846 |
| San Pedro | 4 031 | 3 429 | 4 | -2 421 | 4 205 | 3 429 | 4 | -2 377 |

2. Joint financing

The Ministry of Health and Public Hygiene takes note of GAVI’s proposal to complement the existing obligations regarding yellow fever vaccines with additional assistance whilst requiring the country to finance jointly the additional share of assistance in accordance with joint financing rules.

Having examined the costs which this additional assistance might represent, the country states its undertaking, as in the past, to support all the yellow fever vaccine costs.

Regarding the introduction of the DTP-HepB+Hib vaccine, the government would like to reaffirm its undertaking to finance jointly the said vaccine up to the financial contribution provided in previous years to purchase the tetravalent DTP-HepB vaccine, as stated in the minutes from the ICC meeting dated 18th April 2007.

- Budgetary table itemising overall non-vaccine requirements for the introduction, and how the allocated funds will be used to bridge deficits

Table 4 : Cost and financing to introduce the initial preferred vaccine ($US)

| N° | Budget item | Total requirements to introduce the new vaccine | Requirements financed with the GAVI grant to introduce new and under-used vaccines |
| --- | --- | --- | --- |
|  |  | US$ | US$ |
|  | Training | 287 766,90 | 89 309,45 |
|  | Social mobilisation, IEC and submissions | 66 723,51 | 33 231,42 |
|  | Equipping and maintaining the cold chain | - | - |
|  | Vehicles and transport | 79 058,60 | 42 889,31 |
|  | Programme management | - | - |
|  | Monitoring and supervision | 111 335,65 | 16 713,02 |
|  | Human resources | - | - |
|  | Waste management | - | - |
|  | Technical assistance | - | - |
|  | Total | 544 884,66 | 182 143,20 |

1 USD =  481,472 F CFA (UNS rate, September 2007)

The total budget to introduce the pentavalent amounts to 544 884,66 USD. The expected grant from GAVI is 182 143,20 USD. This grant is obtained by multiplying the number of forecast births in 2007 (607 144) by 0.30 USD. In addition to the GAVI grant, the State will contribute 202 741,46 USD, the WHO 35 000 USD and l’UNICEF 125 000 USD. All costs linked to introducing the new vaccine are covered as detailed in table 5.

Table 5 : Sources for financing of costs and financing the introduction of the first preferred vaccine ($US)

| N° | Budget item | Total requirements to introduce the new vaccine | Sum per financing source |  |  |  | GAP |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | GAVI | STATE | WHO | UNICEF |  |
|  |  | US$ | US$ | US$ | US$ | US$ | US$ |
|  | Training | 287 766,90 | 89 309,45 | 168 457,45 |  | 30 000,00 | 0,00 |
|  | Social mobilisation, IEC and submissions | 66 723,51 | 33 231,42 | 13 492,08 |  | 20 000,00 | 0,00 |
|  | Equipping and maintaining the cold chain | - | - |  |  |  | - |
|  | Vehicles and transport | 79 058,60 | 42 889,31 | 11 169,29 |  | 25 000,00 | 0,00 |
|  | Programme management | - | - |  |  |  | - |
|  | Monitoring and supervision | 111 335,65 | 16 713,02 | 9 622,64 | 35 000,00 | 50 000,00 | 0,00 |
|  | Human resources |  |  |  |  |  |  |
|  | Waste management |  |  |  |  |  |  |
|  | Technical assistance |  |  |  |  |  |  |
|  | Total | 544 884,66 | 182 143,20 | 202 741,46 | 35 000,00 | 125 000,00 | 0,00 |

1 USD =  481,472 F CFA (UNS rate, September 2007)

APPENDICES ON THE ANALYSIS OF COLD CHAIN CAPACITIES

Appendix 1. PRIMARY DATA FROM PPAC AND INTRODUCTION PLAN

  - Total population of the Ivory Coast in 2007 : 20 581 167 inhabitants

  - Objectives of the routine immunization programme for 2008 - 2011

|  |  | Year |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Routine Vaccines | Items | 2008 | 2009 | 2010 | 2011 |
| BCG | Schedule | 1 | 1 | 1 | 1 |
|  | Cover | 90% | 92% | 95% | 95% |
|  | Presentation | 20 | 20 | 20 | 20 |
|  | Losses | 40% | 40% | 40% | 40% |
|  | Packaged volume /dose (ml) | 1,2 |  |  |  |
| Oral Polio | Schedule | 4 | 4 | 4 | 4 |
|  | Cover | 85% | 87% | 90% | 90% |
|  | Presentation | 10 | 10 | 10 | 10 |
|  | Losses | 10% | 10% | 10% | 10% |
|  | Packaged volume /dose (ml) | 2 |  |  |  |
| VAR | Schedule | 1 | 1 | 1 | 1 |
|  | Cover | 83% | 85% | 87% | 90% |
|  | Presentation | 10 | 10 | 10 | 10 |
|  | Losses | 15% | 15% | 15% | 15% |
|  | Packaged volume /dose (ml) | 3,5 |  |  |  |
| Tetanus | Schedule | 2 | 2 | 2 | 2 |
|  | Cover | 70% | 78% | 85% | 90% |
|  | Presentation | 10 | 10 | 10 | 10 |
|  | Losses | 15% | 10% | 10% | 10% |
|  | Packaged volume /dose (ml) | 2 |  |  |  |
| AAV | Schedule | 1 | 1 | 1 | 1 |
|  | Cover | 83% | 85% | 87% | 90% |
|  | Presentation | 10 | 10 | 10 | 10 |
|  | Losses | 15% | 15% | 15% | 15% |
|  | Packaged volume /dose (ml) | 2,5 |  |  |  |
| DTP-HepB-Hib | Schedule | 3 | 3 | 3 | 3 |
|  | Cover | 85% | 87% | 90% | 90% |
|  | Presentation | 1 | 1 | 1 | 1 |
|  | Losses | 5% | 5% | 5% | 5% |
|  | Packaged volume /dose (ml) | 1,9 |  |  |  |

Objectives of the programme for additional immunization activities for 2008-2011

| Type of immunization campaign | Items | 2008 | 2009 | 2010 | 2011 |
| --- | --- | --- | --- | --- | --- |
| Measles campaign | Number of doses (rounds) | 1 |  |  |  |
|  | % total population | 15% |  |  |  |
|  | Presentation | 10 |  |  |  |
|  | Losses | 10% |  |  |  |
| Yellow fever campaign | Number of doses (rounds) | 1 |  |  |  |
|  | % total population | 26% |  |  |  |
|  | Presentation | 10 |  |  |  |
|  | Losses | 10% |  |  |  |
| Tetanus campaign | Number of doses (rounds) | 3 | 3 |  |  |
|  | % total population | 9% | 10% |  |  |
|  | Presentation | 10 | 10 |  |  |
|  | Losses | 10% | 10% |  |  |

Appendix 2. DESCRIPTION OF THE EXISTING COLD CHAIN VOLUME

A large space will be required for the introduction of the new vaccines (DTC-HepB+Hib) because of the presentation of the vaccines. In fact, the presentation chosen by the Ivory Coast is a single dose in liquid form with a larger number of vials to be stored. A thorough analysis of the cold chain is required to show existing capacities, the capacities required and to determine the gap to bridge if necessary.

This analysis takes available storage capacities at central and regional levels into account.

The country has a central national vaccine depot in Abidjan and 10 regional vaccine depots in Bouaké, Korhogo, Daloa, Yamoussoukro, Abengourou, Bondoukou, Odienné, Man, Gagnoa and San Pedro.

Table A 1. Existing volumetric cold chain capacity at central and regional level in 2007

| Vaccine depots | Gross storage volume (litre) |  | Net storage volume (litre) |  |
| --- | --- | --- | --- | --- |
|  | Positive | Negative | Positive | Negative |
| Central depot in INHP Abidjan | 85 000 | 40 000 | 24 286 | 11 429 |
| INHP Bouaké | 8 000 | 20 000 | 2 286 | 5 714 |
| INHP Korhogo | 8 000 | 20 000 | 2 286 | 5 714 |
| INHP Daloa | 12 000 | 20 000 | 3 429 | 5 714 |
| INHP Yamoussoukro | 40 000 | 20 000 | 11 429 | 5 714 |
| INHP Abengourou | 8 000 | 20 000 | 2 286 | 5 714 |
| INHP Bondoukou | 8 000 | - | 2 286 | - |
| INHP Odienné | 8 000 | - | 2 286 | - |
| INHP Man | 8 000 | 20 000 | 2 286 | 5 714 |
| INHP Gagnoa | 8 000 | - | 2 286 | - |
| INHP San Pedro | 12 000 | 20 000 | 3 429 | 5 714 |

To date, the various storage capacities mentioned above have been sufficient to store vaccines in the required preservation conditions both for routine immunizations and additional immunization activities.

Appendix 3. DESCRIPTION OF THE REQUIRED VOLUME GIVEN THE INTRODUCTION OF THE PENTAVALENT VACCINE DTP-HepB+Hib FROM 2008 TO 2011

The volume required for each antigen per annum has been calculated based on the target population, the number of contacts in the vaccine schedule, the loss factor, coverage objectives and the packaged volume per dose. For each year, the sum of the required volumes per antigen has been calculated to determine the total volume required for the year.

Volume required for routine immunization

We envisage two scenarios to understand better the storage capacity requirements for the introduction of the pentavalent:

(i) All vaccines are stored cold at a positive temperature, (ii) VAR and oral polio vaccines are stored at a negative temperature and the others are stored at a positive temperature. In the specific case of the Ivory Coast, scenario (ii) is in force centrally and regionally. However, all vaccines are stored at a positive temperature at some regional outposts which do not have negative cold chambers.

- Scenario n°1 : Required storage volume if all vaccines are stored cold at a positive temperature

Table A 2. Required volumetric capacity to store all vaccines cold at positive temperatures centrally and in the regions from 2008 to 2011 for routine immunization activities.

| Depot | Required storage volume (litre) |  |  |  |
| --- | --- | --- | --- | --- |
|  | 2008 | 2009 | 2010 | 2011 |
| Central Depot in INHP Abidjan | 35 209 | 37 325 | 39 558 | 41 270 |
| INHP Bouaké | 2 441 | 2 588 | 2 743 | 2 862 |
| INHP Korhogo | 1 869 | 1 982 | 2 100 | 2 191 |
| INHP Daloa | 3 378 | 3 581 | 3 795 | 3 959 |
| INHP Yamoussoukro | 3 015 | 3 196 | 3 388 | 3 534 |
| INHP Abengourou | 823 | 873 | 925 | 965 |
| INHP Bondoukou | 1 536 | 1 628 | 1 726 | 1 801 |
| INHP Odienné | 465 | 493 | 523 | 545 |
| INHP Man | 3 726 | 3 950 | 4 186 | 4 367 |
| INHP Gagnoa | 1 501 | 1 591 | 1 686 | 1 759 |
| INHP San Pedro | 4 462 | 4 730 | 5 013 | 5 230 |

- Scenario n°2 : Required storage volume if the VAR and oral polio vaccines are stored, centrally and regionally, cold at negative temperatures and the other vaccines are stored cold at positive temperatures

Table A 3. Required volumetric capacity to store  the VAR and oral polio vaccine, centrally and regionally, at negative temperatures and other vaccines cold at positive temperatures from 2008 to 2012 for routine immunization activities.

| Depot | Required cold storage volume at positive temperatures (litre) |  |  |  | Required cold storage volume at negative temperatures (litre) |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2008 | 2009 | 2010 | 2011 | 2008 | 2009 | 2010 | 2011 |
| Central Depot in INHP Abidjan | 28 193 | 29 905 | 31 806 | 33 177 | 7 016 | 7 420 | 7 752 | 8 093 |
| INHP Bouaké | 1 955 | 2 074 | 2 205 | 2 301 | 486 | 514 | 537 | 561 |
| INHP Korhogo | 1 497 | 1 588 | 1 689 | 1 761 | 372 | 394 | 412 | 430 |
| INHP Daloa | 2 705 | 2 869 | 3 052 | 3 183 | 673 | 712 | 744 | 776 |
| INHP Yamoussoukro | 2 414 | 2 561 | 2 724 | 2 841 | 601 | 635 | 664 | 693 |
| INHP Abengourou | 659 | 699 | 744 | 776 | 164 | 173 | 181 | 189 |
| INHP Bondoukou | 1 230 | 1 305 | 1 388 | 1 448 | 306 | 324 | 338 | 353 |
| INHP Odienné | 372 | 395 | 420 | 438 | 93 | 98 | 102 | 107 |
| INHP Man | 2 983 | 3 165 | 3 366 | 3 511 | 742 | 785 | 820 | 856 |
| INHP Gagnoa | 1 202 | 1 275 | 1 356 | 1 414 | 299 | 316 | 330 | 345 |
| INHP San Pedro | 3 573 | 3 790 | 4 031 | 4 205 | 889 | 940 | 982 | 1 026 |

Appendix 4. ANALYSIS OF ADEQUACY BETWEEN REQUIRED STORAGE CAPACITY AND EXISTING STORAGE CAPACITY

4.1. Analysis of adequacy of capacities for routine EPI without additional immunization activities

National directives in force for vaccine supplies have determined the following:

- For central level: two annual supplies (every 6 months) ;

- For the regional level 4 annual supplies (every 3 months). Every three months, the regional level supplies the health districts in the territory it services.

The adequacy analysis is carried out depending on this supply rate which is determined per level.

Table A 4.Adequacy between the existing storage capacity and the required storage capacity at the central depot level from 2008 to 2012.

|  |  |  | Values in |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2008 | 2009 | 2010 | 2011 |
|  | Storage at a positive temperature |  |  |  |  |  |
| A | Annual storage volume required (litres) | Volume of all vaccines except oral polio and VAR | 28 163 | 29 905 | 31 806 | 33 177 |
| B | Existing storage capacity (litres) | Net available volume | 24 286 | 24 286 | 24 286 | 24 286 |
| C | Minimum estimated supply number | A/B | 1,16 | 1,23 | 1,31 | 1,37 |
| D | Supply number at country’s central level | National directive for central level 2 times a year | 2 | 2 | 2 | 2 |
| E | Gap | (A/D)-B | -10 205 | - 9 334 | - 8 383 | - 7 698 |
| F | Storage at a negative temperature |  |  |  |  |  |
| G | Annual storage volume required (litres) | Volume of oral polio +VAR | 7 016 | 7 420 | 7 752 | 8 093 |
| H | Existing storage capacity (litres) | Net available volume | 11 429 | 11 429 | 11 429 | 11 429 |
| I | Minimum possible number of supplies | G/H | 0,61 | 0,65 | 0,68 | 0,71 |
| J | Number of supplies at central level | National directive for central level 2 times a year | 2 | 2 | 2 | 2 |
| K | Gap | (G/J)-H | - 7 920 | - 7 719 | - 7 553 | - 7 382 |

Table A 5. Adequacy between the existing storage capacity and the required storage capacity at the regional depot level for vaccines from 2008 to 2012.

|  |  |  | Values in |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2008 | 2009 | 2010 | 2011 |
|  | Storage at a positive temperature |  |  |  |  |  |
| A | Annual storage volume required (litres) | Volume of all vaccines except oral polio and VAR | 18 591 | 19 720 | 20 974 | 21 878 |
| B | Existing storage capacity (litres) | Net available volume | 34 286 | 34 286 | 34 286 | 34 286 |
| C | Minimum estimated supply number | A/B | 0,54 | 0,58 | 0,61 | 0,64 |
| D | Supply number at a regional level | National directive for the regional level | 4 | 4 | 4 | 4 |
| E | Gap | (A/D)-B | - 29 638 | - 29 356 | - 29 042 | - 28 816 |
| F | Storage at negative temperature |  |  |  |  |  |
| G | Annual storage volume required (litres) | Volume of oral polio +VAR | 4 627 | 4 893 | 5 112 | 5 337 |
| H | Existing storage capacity (litres) | Net available volume | 40 000 | 40 000 | 40 000 | 40 000 |
| I | Minimum possible number of supplies | G/H | 0,12 | 0,12 | 0,13 | 0,13 |
| J | Number of supplies at central level | National directive for regional level | 4 | 4 | 4 | 4 |
| K | Gap | (G/J)-H | - 38 843 | - 38 777 | - 38 722 | - 38 666 |

At a quarterly supply rate (4 supplies per year) there is surplus cold chain availability in the regions both for positive storage and for negative storage. It would not be necessary to strengthen the current storage capacity if the pentavalent is introduced into the programme.

4.2 Analysis of adequacy of capacities for routine EPI and for additional immunization activities

The following immunization campaigns are planned in the full multi-annual plan:

- Campaign against tetanus in 2007, 2008 and 2009,

- Campaign against yellow fever in 2008,

- Campaign against measles in 2008.

During these immunization campaigns, the country will mainly focus on surplus storage capacities which are available sat central and regional levels for both positive and negative storage.

Table A 6. Availability of storage capacity at central and regional levels for additional immunization activities

|  |  | 2008 | 2009 | 2010 | 2011 |
| --- | --- | --- | --- | --- | --- |
| A | Surplus positive volume | 39 843 | 38 690 | 37 425 | 36 514 |
| B | Surplus negative volume | 46 763 | 46 496 | 46 275 | 46 048 |
| C | Volume (+) required for tetanus vaccine campaign | 12 756 | 15 945 | 0 | 0 |
| D | Volume (+) required for yellow fever vaccine campaign | 15 355 | 0 | 0 | 0 |
| E | Volume (-) required for measles vaccine campaign | 12 402 | 0 | 0 | 0 |
| F | GAP - positive storage (litres) (C+D-A) | -11 732 | -22 745 | -37 425 | -36 514 |
| G | GAP - negative storage (litres) (E-B) | -34 361 | -46 496 | -46 275 | -46 048 |

In all cases, the surplus volume at both central and regional levels is sufficient to store the vaccines in the immunization campaigns planned for 2008 and 2009. Moreover, there is a lot of flexibility in the cold chain. In fact, the Public Health Pharmacy and the international airport have cold chambers which can be used for emergency storage at a central level.

In total, given the national directives in terms of supply (2 times a year at central level and 4 times a year at regional level), storage capacities at central and regional levels are sufficient to house the addition of the pentavalent vaccine from 2008 to 2011 in the Ivory Coast. There is surplus positive and negative storage at both central and regional levels. These surpluses could be used during the mass campaigns in 2008 and 2009.

# Appendix 5. DETAILS OF STORAGE CAPACITIES AT VARIOUS LEVELS

5.1. Central Depot : INHP Abidjan

Availability of the cold chain at the central depot in Abidjan

| Number of units | Total capacity (litres) |  | Volume factor |
| --- | --- | --- | --- |
|  | Gross | Net |  |
| 3 positive cold chambers | 85 000 | 24 286 | 3,5 |
| 2 negative cold chambers | 40 000 | 11 429 | 3,5 |

## Adequacy of storage capacity for requirements

|  |  |  | Values in |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2008 | 2009 |  | 2010 | 2011 |
|  | Positive storage temperature |  |  |  |  |  |  |
| A | Annual storage volume required (litres) | Volume of all vaccines except oral polio and VAR | 28 163 | 29 905 |  | 31 806 | 33 177 |
| B | Existing storage capacity (litres) | Net available volume | 24 286 | 24 286 |  | 24 286 | 24 286 |
| C | Minimum possible supply number | A/B | 1,16 | 1,23 |  | 1,31 | 1,37 |
| D | Supply number at central level | National directive for the central level | 2 | 2 |  | 2 | 2 |
| E | Gap | (A/D)-B | -10 205 | - 9 334 |  | - 8 383 | - 7 698 |
| F | Storage at a negative temperature |  |  |  |  |  |  |
| G | Annual storage volume required (litres) | Volume of oral polio +VAR | 7 016 |  | 7 420 | 7 752 | 8 093 |
| H | Existing storage capacity (litres) | Net available volume | 11 429 |  | 11 429 | 11 429 | 11 429 |
| I | Minimum possible number of supplies | G/H | 0,61 |  | 0,65 | 0,68 | 0,71 |
| J | Number of supplies at central level | National directive for central level | 2 |  | 2 | 2 | 2 |
| K | Gap | (G/J)-H | - 7 920 |  | - 7 719 | - 7 553 | - 7 382 |

5.2. Regional depots

5. 2.1. Bouaké Region : INHP BOUAKE depot

Availability of the cold chain at the Bouaké depot

| Number of units | Total positive capacity (litres) |  | Volume factor |
| --- | --- | --- | --- |
| 1 positive cold chain | Gross | Net |  |
|  | 8 000 | 2 286 | 3,5 |
|  | Total negative capacity (litres) |  |  |
| 1 negative cold chain | Gross | Net |  |
|  | 20 000 | 5 714 | 3,5 |

## Adequacy of storage capacity for requirements

|  |  |  | Values in |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2008 | 2009 | 2010 | 2011 |
|  | Positive storage temperature |  |  |  |  |  |
| A | Annual storage volume required (litres) | Volume of all vaccines except oral polio and VAR | 1 955 | 2 074 | 2 205 | 2 301 |
| B | Existing storage capacity (litres) | Net available volume | 2 286 | 2 286 | 2 286 | 2 286 |
| C | Minimum possible supply number | A/B | 0,86 | 0,91 | 0,96 | 1,01 |
| D | Supply number at regional level | National directive for the regional level | 4 | 4 | 4 | 4 |
| E | Gap | (A/D)-B | - 1 797 | - 1 767 | - 1 734 | - 1 710 |
| F | Storage at a negative temperature |  |  |  |  |  |
| G | Annual storage volume required (litres) | Volume of oral polio +VAR | 486 | 514 | 537 | 561 |
| H | Existing storage capacity (litres) | Net available volume | 5 714 | 5 714 | 5 714 | 5 714 |
| I | Minimum possible number of supplies | G/H | 0,09 | 0,09 | 0,09 | 0,10 |
| J | Number of supplies at regional level | National directive for regional level | 4 | 4 | 4 | 4 |
| K | Gap | (G/J)-H | - 5 593 | - 5 586 | - 5 580 | - 5 574 |

At the quarterly supply rate (4 supplies per year), the cold chain availability at the Bouake regional depot, both for negative and positive storage, shows a surplus which indicates that it would not be necessary to reinforce the current storage capacity if the pentavalent is introduced into the programme. The storage capacity surpluses can be used in the framework of immunization campaigns.

5.2.2. Korhogo region: INHP KORHOGO Depot

Availability of the cold chain at the KORHOGO regional depot

| Number of units | Total positive capacity (litres) |  | Volume factor |
| --- | --- | --- | --- |
| 1 positive cold chain | Gross | Net |  |
|  | 8 000 | 2 286 | 3,5 |
|  | Total negative capacity (litres) |  |  |
| 1 negative cold chain | Gross | net |  |
|  | 20 000 | 5 714 | 3,5 |

## Adequacy of the storage capacity for requirements

|  |  |  | Values in |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2008 | 2009 | 2010 | 2011 |
|  | Positive storage temperature |  |  |  |  |  |
| A | Annual storage volume required (litres) | Volume of all vaccines except oral polio and VAR | 1 497 | 1 588 | 1 689 | 1 761 |
| B | Existing storage capacity (litres) | Net available volume | 2 286 | 2 286 | 2 286 | 2 286 |
| C | Minimum possible supply number | A/B | 0,65 | 0,69 | 0,74 | 0,77 |
| D | Supply number at regional level | National directive for the regional level | 4 | 4 | 4 | 4 |
| E | Gap | Gap | - 1 912 | - 1 889 | - 1 864 | - 1 845 |
| F | Storage at a negative temperature |  |  |  |  |  |
| G | Annual storage volume required (litres) | Volume of oral polio +VAR | 372 | 394 | 412 | 430 |
| H | Existing storage capacity (litres) | Net available volume | 5 714 | 5 714 | 5 714 | 5 714 |
| I | Minimum possible number of supplies | G/H | 0,07 | 0,07 | 0,07 | 0,08 |
| J | Number of supplies at regional level | National directive for regional level | 4 | 4 | 4 | 4 |
| K | Gap | (G/J)-H | - 5 621 | - 5 616 | - 5 611 | - 5 607 |

At the quarterly supply rate (4 supplies per year), the cold chain availability at the Korhogo regional depot, both for negative and positive storage, shows a surplus which indicates that it would not be necessary to reinforce the current storage capacity if the pentavalent is introduced into the programme

5.2.3  Daloa Region: INHP DALOA Depot

Availability of the cold chain at the Daloa depot

| Number of units | Total positive capacity (litres) |  | Volume factor |
| --- | --- | --- | --- |
| 1 positive cold chain | Gross | Net |  |
|  | 12 000 | 3 429 | 3,5 |
|  | Total Negative capacity (litres) |  |  |
| 1 negative cold chain | Gross | net |  |
|  | 20 000 | 5 714 | 3,5 |

### Adequacy of the storage capacity for requirements

|  |  |  | Values in |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2008 | 2009 | 2010 | 2011 |
|  | Positive storage temperature |  |  |  |  |  |
| A | Annual storage volume required (litres) | Volume of all vaccines except oral polio and VAR | 2 705 | 2 869 | 3 052 | 3 183 |
| B | Existing storage capacity (litres) | Net available volume | 3 429 | 3 429 | 3 429 | 3 429 |
| C | Minimum possible supply number | A/B | 0,79 | 0,84 | 0,89 | 0,93 |
| D | Supply number at regional level | National directive for the regional level | 4 | 4 | 4 | 4 |
| E | Gap | (A/D)-B | - 2 752 | - 2 711 | - 2 666 | - 2 633 |
| F | Storage at a negative temperature |  |  |  |  |  |
| G | Annual storage volume required (litres) | Volume of oral polio +VAR | 673 | 712 | 744 | 776 |
| H | Existing storage capacity (litres) | Net available volume | 5 714 | 5 714 | 5 714 | 5 714 |
| I | Minimum possible number of supplies | G/H | 0,12 | 0,12 | 0,13 | 0,14 |
| J | Number of supplies at regional level | National directive for regional level | 4 | 4 | 4 | 4 |
| K | Gap | (G/J)-H | - 5 546 | - 5 536 | - 5 528 | - 5 520 |

At the quarterly supply rate (4 supplies per year), the cold chain availability at the Daloa regional depot, both for negative and positive storage, shows a surplus which indicates that it would not be necessary to reinforce the current storage capacity if the pentavalent is introduced into the programme. The storage capacity surpluses can be used in the framework of the various immunization campaigns.

5.2.4 Yamoussoukro region: INHP YAMOUSSOKRO depot

Availability of the cold chain at the Yamoussoukro depot

| Number of units | Total positive capacity (litres) |  | Volume factor |
| --- | --- | --- | --- |
| 1 positive cold chain | Gross | Net |  |
|  | 40 000 | 11 429 | 3,5 |
|  | Total negative capacity (litres) |  |  |
| 1 negative cold chain | Gross | Net |  |
|  | 20 000 | 5 714 | 3,5 |

## Adequacy of the storage capacity for the requirements of the Yamoussoukro depot

|  |  |  | Years |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2008 | 2009 | 2010 | 2011 |
|  | Positive storage temperature |  |  |  |  |  |
| A | Annual storage volume required (litres) | Volume of all vaccines except oral polio and VAR | 2 414 | 2 561 | 2 724 | 2 841 |
| B | Existing storage capacity (litres) | Net available volume | 11 429 | 11 429 | 11 429 | 11 429 |
| C | Minimum possible supply number | A/B | 0,21 | 0,22 | 0,24 | 0,25 |
| D | Supply number at regional level | National directive for the regional level | 4 | 4 | 4 | 4 |
| E | Gap | (A/D)-B | -10 825 | -10 788 | -10 748 | -10 718 |
| F | Storage at a negative temperature |  |  |  |  |  |
| G | Annual storage volume required (litres) | Volume of oral polio +VAR | 601 | 635 | 664 | 693 |
| H | Existing storage capacity (litres) | Net available volume | 5 714 | 5 714 | 5 714 | 5 714 |
| I | Minimum possible number of supplies | G/H | 0,11 | 0,11 | 0,12 | 0,12 |
| J | Number of supplies at regional level | National directive for regional level | 4 | 4 | 4 | 4 |
| K | Gap | (G/J)-H | - 5 564 | - 5 555 | - 5 548 | - 5 541 |

At the quarterly supply rate (4 supplies per year), the cold chain availability at the Yamoussoukro regional depot, both for negative and positive storage shows a surplus. It would not be necessary to reinforce the current storage capacity if the pentavalent is introduced into the programme.

5.2.5 Abengourou region : INHP D’ABENGOUROU Depot

Availability of the cold chain at the Abengourou regional depot

| Number of units | Total positive capacity litres) |  | Volume factor |
| --- | --- | --- | --- |
| 1 positive cold chain | Gross | Net |  |
|  | 8 000 | 2 286 | 3,5 |
|  | Total negative capacity (litres) |  |  |
| 1 negative cold chain | Gross | Net |  |
|  | 20 000 | 5 714 | 3,5 |

Adequacy of the storage capacity for requirements

|  |  |  | Values en |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2008 | 2009 | 2010 | 2011 |
|  | Positive storage temperature |  |  |  |  |  |
| A | Annual storage volume required (litres) | Volume of all vaccines except oral polio and VAR | 659 | 699 | 744 | 776 |
| B | Existing storage capacity (litres) | Net available volume | 2 286 | 2 286 | 2 286 | 2 286 |
| C | Minimum possible supply number | A/B | 0,29 | 0,31 | 0,33 | 0,34 |
| D | Supply number at regional level | National directive for the regional level | 4 | 4 | 4 | 4 |
| E | Gap | (A/D)-B | - 2 121 | - 2 111 | - 2 100 | - 2 092 |
| F | Storage at a negative temperature |  |  |  |  |  |
| G | Annual storage volume required (litres) | Volume of oral polio +VAR | 164 | 173 | 181 | 189 |
| H | Existing storage capacity (litres) | Net available volume | 5 714 | 5 714 | 5 714 | 5 714 |
| I | Minimum possible number of supplies | G/H | 0,03 | 0,03 | 0,03 | 0,03 |
| J | Number of supplies at country’s central level | National directive for regional level | 4 | 4 | 4 | 4 |
| K | Gap | (G/J)-H | - 5 673 | - 5 671 | - 5 669 | - 5 667 |

At the quarterly supply rate (4 per year), the cold chain availability at the Abengourou regional depot, for positive storage, shows a surplus which indicates that it would not be necessary to reinforce the current storage capacity if the pentavalent is introduced into the programme.

5.2.6 Bondoukou Region : INHP BONDOUKOU Depot

Availability of the cold chain at the Bondoukou regional depot

| Number of units | Total positive capacity (litres) |  | Volume factor |
| --- | --- | --- | --- |
| 1 positive cold chain | Gross | Net |  |
|  | 8 000 | 2286 | 3,5 |
| 1 negative cold chain | Total negative capacity (litres) |  |  |
|  | Gross | net |  |
|  | 20 000 | 5714 | 3,5 |

Adequacy of the storage capacity for requirements

|  |  |  | Values in |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2008 | 2009 | 2010 | 2011 |
|  | Positive storage temperature |  |  |  |  |  |
| A | Annual storage volume required (litres) | Volume of all vaccines except oral polio and VAR | 1 536 | 1 628 | 1 726 | 1 801 |
| B | Existing storage capacity (litres) | Net available volume | 2 286 | 2 286 | 2 286 | 2 286 |
| C | Minimum possible supply number | A/B | 0,67 | 0,71 | 0,76 | 0,79 |
| D | Supply number at regional level | National directive for the regional level | 4 | 4 | 4 | 4 |
| E | Gap | (A/D)-B | - 1 902 | - 1 879 | - 1 854 | - 1 836 |

At the quarterly supply rate (4 per year), the cold chain availability at the Bondoukou regional depot, for positive storage, shows a surplus which indicates that it would not be necessary to reinforce the current storage capacity if the pentavalent is introduced into the programme.

5.2.7. Odienné Region : INHP ODIENNE Depot

Availability of the cold chain at the Odienné depot

| Number of units | Total Positive Capacity (litres) |  | Volume factor |
| --- | --- | --- | --- |
| 1 positive cold chain | Gross | Net |  |
|  | 8 000 | 2 286 | 3,5 |
|  | Total Negative Capacity (litres) |  |  |
| 1 negative cold chain | Gross | net |  |
|  | 0 | 0 | 3,5 |

Adequacy of the storage capacity for requirements

|  |  |  | Year |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2008 | 2009 | 2010 | 2011 |
|  | Positive storage temperature |  |  |  |  |  |
| A | Annual storage volume required (litres) | Volume of all vaccines except oral polio and VAR | 465 | 493 | 523 | 545 |
| B | Existing storage capacity (litres) | Net available volume | 2 286 | 2 286 | 2 286 | 2 286 |
| C | Minimum possible supply number | A/B | 0,20 | 0,22 | 0,23 | 0,24 |
| D | Supply number at regional level | National directive for the regional level | 4 | 4 | 4 | 4 |
| E | Gap | (A/D)-B | - 2 169 | - 2 162 | - 2 155 | - 2 149 |

At the quarterly supply rate (4 per year), the cold chain availability at the Odienné regional depot, for positive storage, shows a surplus which indicates that it would not be necessary to reinforce the current storage capacity if the pentavalent is introduced into the programme.

5.2.8. Man Region : INHP MAN Depot

Availability of the cold chain at the MAN regional depot

| Number of units | Total positive capacity (litres) |  | Volume factor |
| --- | --- | --- | --- |
| 1 positive cold chain | Gross | Net |  |
|  | 8 000 | 2 286 | 3,5 |
|  | Total Negative Capacity (litres) |  |  |
| 1 negative cold chain | Gross | net |  |
|  | 20 000 | 5 714 | 3,5 |

Adequacy of the storage capacity for requirements

|  |  |  | Values in |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2008 | 2009 | 2010 | 2011 |
|  | Positive storage temperature |  |  |  |  |  |
| A | Annual storage volume required (litres) | Volume of all vaccines except oral polio and VAR | 2 983 | 3 165 | 3 366 | 3 511 |
| B | Existing storage capacity (litres) | Net available volume | 2 286 | 2 286 | 2 286 | 2 286 |
| C | Minimum possible supply number | A/B | 1,31 | 1,38 | 1,47 | 1,54 |
| D | Supply number at regional level | National directive for the regional level | 4 | 4 | 4 | 4 |
| E | Gap | (A/D)-B | - 1 540 | - 1 495 | - 1 444 | - 1 408 |
| F | Storage at a negative temperature |  |  |  |  |  |
| G | Annual storage volume required (litres) | Volume of oral polio +VAR | 742 | 785 | 820 | 856 |
| H | Existing storage capacity (litres) | Net available volume | 5 714 | 5 714 | 5 714 | 5 714 |
| I | Minimum possible number of supplies | G/H | 0,13 | 0,14 | 0,14 | 0,15 |
| J | Supply number at regional level | National directive for regional level | 4 | 4 | 4 | 4 |
| K | Gap | (G/J)-H | - 5 529 | - 5 518 | - 5 509 | - 5 500 |

At the quarterly supply rate (4 supplies per year), the cold chain availability at the Man regional depot, both for negative and positive storage shows a surplus. It would not be necessary to reinforce the current storage capacity if the pentavalent is introduced into the programme.

5.2.9 Gagno Region : INHP GAGNOA Depot

Availability of the cold chain at the Gagnoa regional depot

| Number of units | Total positive capacity (litres) |  | Volume factor |
| --- | --- | --- | --- |
| 1 positive cold chain | Gross | Net |  |
|  | 8 000 | 2 286 | 3,5 |
|  | Total negative capacity (litres) |  |  |
| 1 negative cold chain | Gross | Net |  |
|  | 0 | 0 | 3,5 |

Adequacy of the storage capacity for requirements

|  |  |  | Values in |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2008 | 2009 | 2010 | 2011 |
|  | Positive storage temperature |  |  |  |  |  |
| A | Annual storage volume required (litres) | Volume of all vaccines except oral polio and VAR | 1 501 | 1 591 | 1 686 | 1 759 |
| B | Existing storage capacity (litres) | Net available volume | 2 286 | 2 286 | 2 286 | 2 286 |
| C | Minimum possible supply number | A/B | 0,66 | 0,70 | 0,74 | 0,77 |
| D | Supply number at regional level | National directive for the regional level | 4 | 4 | 4 | 4 |
| E | Gap | (A/D)-B | - 1 910 | - 1 888 | - 1 864 | - 1 846 |

At the quarterly supply rate (4 per year), the cold chain availability at the Gagnoa regional depot, for positive storage, shows a surplus which indicates that it would not be necessary to reinforce the current storage capacity if the pentavalent is introduced into the programme.

Regarding the mass immunization campaign against measles (follow-up campaign) in 2009, the vaccine stock (VAR) to immunize the population covered by the Gagnoa regional depot during this campaign is estimated at 139000 doses and will need a net volume of 487 litres which the positive quarterly capacity surplus (1865 litres) will be able to accommodate adequately.

5.2.10. San Pedro Region : INHP SAN PEDRO Depot

Availability of the cold chain at the San Pedro depot

| Number of units | Total positive capacity (litres) |  | Volume factor |
| --- | --- | --- | --- |
| 1 positive cold chain | Gross | Net |  |
|  | 12 000 | 3 429 | 3,5 |
|  | Total negative capacity (litres) |  |  |
| 1 negative cold chain | Gross | net |  |
|  | 20 000 | 5 714 | 3,5 |

Adequacy of the storage capacity for requirements

|  |  |  | Values in |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2008 | 2009 | 2010 | 2011 |
|  | Positive storage temperature |  |  |  |  |  |
| A | Annual storage volume required (litres) | Volume of all vaccines except oral polio and VAR | 3 573 | 3 790 | 4 031 | 4 205 |
| B | Existing storage capacity (litres) | Net available volume | 3 429 | 3 429 | 3 429 | 3 429 |
| C | Minimum possible supply number | A/B | 1,04 | 1,11 | 1,18 | 1,23 |
| D | Supply number at regional level | National directive for the regional level | 4 | 4 | 4 | 4 |
| E | Gap | (A/D)-B | - 2 535 | - 2 481 | - 2 421 | - 2 377 |
| F | Storage at a negative temperature |  |  |  |  |  |
| G | Annual storage volume required (litres) | Volume of oral polio +VAR | 889 | 940 | 982 | 1 026 |
| H | Existing storage capacity (litres) | Net available volume | 5 714 | 5 714 | 5 714 | 5 714 |
| I | Minimum possible number of supplies | G/H | 0,16 | 0,16 | 0,17 | 0,18 |
| J | Supply number at regional level | National directive for regional level | 4 | 4 | 4 | 4 |
| K | Gap | (G/J)-H | - 5 492 | - 5 479 | - 5 469 | - 5 458 |

At the quarterly supply rate (4 supplies per year), the cold chain availability at the San Pedro regional depot, both for negative and positive storage shows a surplus. It would not be necessary to reinforce the current storage capacity if the pentavalent is introduced into the programme.

Kindly complete all the boxes corresponding to the number of years over which the PPgV or the updated multi-annual plan is spread. It is possible that the plan is spread over more than 5 years or less..

The infant mortality rate used for the period 2007-2011 is 117 per 1000. Source : UNICEF Report 2007 The State of the World's Children.

Formula for calculating a rate of loss of vaccine (in percentage): [ ( A – B ) / A ] x 100. A being the number of doses of DTC distributed according to the supply register, corrected by the volume of stocks at the beginning and end of the supply period and B the number of vaccinations carried out with the same vaccine during the same period. For new vaccines, see the table   after table 7.1.

From 2008, the pentavalent vaccine will be introduced in vials of one dose.

All vaccines are stored at a positive temperature (+5°C) with the exception of the oral polio vaccine and the measles vaccine which are kept at a temperature below zero (-20°C).