Global Alliance for Vaccines and Immunisation (GAVI)

APPLICATION FORM FOR COUNTRY PROPOSALS

For Support to:

Immunisation Services, Injection Safety

and New and Under-Used Vaccines

Please return a signed copy of the document to:

GAVI Alliance Secretariat; c/o UNICEF, Palais des Nations, 1211 Geneva 10, Switzerland.

Enquiries to: Dr Ivone Rizzo, irizzo@gavialliance.org or representatives of a GAVI partner agency.  All documents and attachments must be in English or French, preferably in electronic form.

## CONTENTS

| SECTION | SUPPORT | PAGE |
| --- | --- | --- |
| 1. | Executive Summary | ALL | 2 |
| 2. | Signatures of the Government and National Coordinating Bodies | ALL | 3 |
| 3. | Immunisation Programme Data | ALL | 5 |
| 4. | Immunisation Services Support (ISS) | ISS | 10 |
| 5. | Injection Safety Support (INS) | INS | 12 |
| 6. | New and Under-Used Vaccine Support (NVS) | NVS | 13 |
| 7. | Additional comments and recommendations from the National Coordinating Body (ICC/HSCC) | ALL | 21 |
| 8. | Documents required for each type of support | ALL | 22 |
| Annex 1 – Banking Form | ISS + NVS | 23 |
| Annex 2 – Excel Spreadsheet | NVS |  |

## Executive Summary

One of the main priority under the National Development Strategy is to reform the health system through reduction in infectious diseases and control of vaccine preventable diseases.  Regardless the health care reform initiated by the MOH, the health system is still curative and vertical. The resources available to support the health sector are limited. The Ministry of Health (MoH) is in charge of the health sector planning, policy development and budgeting and is also responsible for management and financing of the Republican level health care facilities such as tertiary clinics, research institutes and vertically organized structures, among them Republican Center of Immunoprophylaxis. Currently RCIP operates on the basis of the bylaw approved by the MoH and has a separate budget, which is formed from the central health budget. RCIP is responsible for planning, monitoring of EPI activities, provision of vaccines and supplies including reporting/registration documentation, data analysis, methodological guidance, and surveillance of vaccine preventable diseases. Immunization is one of the main primary health care services and is delivered by Primary Health Care (PHC) facilities and Maternity units.

The National Immunization Program (NIP) faced serious disruption of vaccination during the early 1990’s. Shortage of vaccine and safe injection materials supply, cold chain equipment, lack of motivation of health staff, etc. resulted in decline of coverage rates and breakup of vaccine preventable diseases.  Nevertheless, the Government with the support of different international agencies managed to revive the immunization service in the country. For the last five years Immunization coverage was officially reported at over 90 percent for all vaccines, but according to the decision of MoH to use State Statistical Agency demographic data to identify denominators for health services, denominator has been significantly increased (from 158,000 to 186,126) and relatively coverage rates were decreased.

Despite recent socio-economic hardships National Immunization Program of Tajikistan has made a significant progress in modernizing policies and strategies and in improving managerial capacity. Tajikistan EPI program conducted several successful campaigns starting from diphtheria campaign in 1996 and the latest measles campaign in 2005. Routine immunization coverage rates exceeded 80% for all EPI antigens used in Tajikistan.

Intensive collaboration with WHO, UNICEF, JICA, TICA and other international partners has brought a better performance in important aspects of immunization policies and practices, such as safer cold chain, adoption of injection safety principles and medical waste utilization after immunization activities, etc. Immunization services are free of charge. An adequate amount of AD syringes and safety boxes is supplied to the health facilities.

Tajikistan put as a priority introduction of new vaccine as there is political and epidemiological necessity to introduce it. Hib vaccine in its Pentavalent presentation may compensate discontinuation of GAVI support for Hep B along with relieving burden on financing of other antigens and immunization supplies. Although Hib disease burden is not thoroughly assessed, introduction of Hib-containing Pentavalent vaccines is planned based of WHO position paper of November 2006 and cost-effectiveness of introduction.

Introducing the vaccine by using the GAVI opportunity will not only enable a dramatic reduction in the burden of disease and contribute its share to the achievements of the Millennium Development Goals, but will lead to cost savings in the long term and help to improve the quality of immunization services as well. The Government of Tajikistan has already proved its financial commitment by taking over 2.8% in 2008 of the vaccine costs starting from 2007. The Government funds will be used for operational activities, such as printing of forms, monitoring and supportive supervision visits. Specific strategies are being worked on to be able to fund the Hib vaccine after the 5-year GAVI support period ends; including raising additional funds and improving the efficiency of immunization programme (see the cMYP).

2. Signatures of the Government and National Coordinating Bodies

## Government and the Inter-Agency Coordinating Committee for Immunisation

The Government of Tajikistan would like to expand the existing partnership with the GAVI Alliance for the improvement of the infants routine immunisation programme of the country, and specifically hereby requests for GAVI support for introduction of Pentavalent vaccine

The Government of Tajikistan commits itself to developing national immunisation services on a sustainable basis in accordance with the comprehensive Multi-Year Plan presented with this document.  The Government requests that the GAVI Alliance and its partners contribute financial and technical assistance to support immunisation of children as outlined in this application.

Table N°………of page ……of this application shows the amount of support in either supply or cash that is required from the GAVI Alliance.   Table N° ……of page ……of this application shows the Government financial commitment for the procurement of this new vaccine (NVS support only).

| Minister of Health: | Minister of Finance: |
| --- | --- |
| Signature: …………………………………… | Signature: …………………………………… |
| Name: Dr. Ranohon Abdurakhmanova | Name:Mr. Safarali Najmiddinov |
| Date: 28.09.07 | Date: 28.09.07 |

National Coordinating Body - Inter-Agency Coordinating Committee for Immunisation:

We the members of the ICC met on the 26.09.07 to review this proposal. At that meeting we endorsed this proposal on the basis of the supporting documentation which is attached.

  - The endorsed minutes of this meeting are attached as DOCUMENT NUMBER: ………

| Name/Title | Agency/Organisation | Signature |
| --- | --- | --- |
| Dr. Mirzoev A, Deputy Ministry of Health | Ministry of Health |  |
| Dr. Miraliev S, Head of International Relations and Reform | Ministry of Health |  |
| Dr. Kurbanov Sh., Head of MCH Department | Ministry of Health |  |
| Dr. Saifiddinov S, Head of Health Services | Ministry of Health |  |
| Mr. Naimi A, Senior Specialist | Ministry of Finance |  |
| Dr. Jabirov Sh., General Director | Republican Center for Immunoprophylaxis |  |
| Dr. Turkov S., Deputy Direcor | Republican Center for Immunoprophylaxis |  |
| Dr. Umeda Sadykova, Assistant Health Program Officer | UNICEF |  |
| Dr. Jaborov S, Programme Officer | JICA |  |
| Dr. Nazira Artykova, Liaison Officer | WHO |  |
| Mr. Kolchin V | World Bank |  |
| Dr. Gafurova L, Senior Specialist | Asian Development Bank |  |
| Dr. Arvind Daial, Health Program Advisor | Aga Khan Foundation |  |
| Dr. Mehry Shoismatulloeva, EPI Officer | WHO |  |

In case the GAVI Secretariat has queries on this submission, please contact:

| Name: Dr Shamsiddin Jabirov | Title: General Director, RCIP |
| --- | --- |
| Tel No.:+992372 272694 | Address: Chapaev Str. 8, Dushanbe, Tajikistan |
| Fax No.:+992372 211073 | …………………………………… |
| Email: immune@rci.tajik.net | …………………………………… |

The GAVI Secretariat is unable to return documents and attachments to individual countries.  Unless otherwise specified, documents may be shared with the GAVI partners and collaborators.

## The Inter-Agency Coordinating Committee for Immunisation

Agencies and partners (including development partners and CSOs) supporting immunisation services are co-ordinated and organised through an inter-agency coordinating mechanism (ICC/HSCC).  The ICC/HSCC are responsible for coordinating and guiding the use of the GAVI ISS and NVS support.  Please provide information about the ICC/HSCC in your country in the spaces below.

Profile of the ICC

| Name of the ICC: .…………………………………………………………………………………… |
| --- |
| Date of constitution of the current ICC: June 2002 |
| Organisational structure Stand alone structure…………………………………………. |
| Frequency of meetings: 4 times a year |
| Composition: |
| Function | Title / Organization | Name |
| Chair | Deputy Ministry of Health | Dr. Mirzoev A |
| Secretary | Epidemiologist, Republican Center for Immunoprophylaxis | Dr. Nazarkhudoeva |
| Members | Head of International Relations and Reform Head of MCH Department Head of Health Services Senior Specialist, Ministry of Finance General Director, RCIP Deputy Direcor, RCIP UNICEF Representative Health Program Officer Head/Representative of WHO Programme Officer Liaison Officer Officer, World Bank Senior Specialist Health Program Advisor EPI Officer | Dr. Miraliev S, Dr. Kurbanov Sh. Dr. Saifiddinov S Mr. Naimi A Dr. Jabirov Sh Dr. Turkov S Yukie Mokuo Dr. Sabir Kurbanov Dr. Santino Severoni Dr. Jaborov S Dr. Nazira Artykova Mr. Kolchin V Dr. Gafurova L Dr. Arvind Daial Dr. Mehry Shoismatulloeva |

Major functions and responsibilities of the ICC:

The ICC of the MoH, chaired by the Minister of Health, has been established as a means for policy-level coordination of initiatives and projects related to immunization program.  The ICC is not limited only to the coordination of GAVI support, but aims to enhance coordination and synergies between different EPI interventions in the longer term. The ICC is a stand alone committee that will work to coordinate the EPI activities in the country. The Republican Center for Immunoprophylaxis is the leading department for coordination between MoH and other stakeholders, including all other EPI relate partners and the Ministry of Finance.

Overall role and function of ICC include coordination of all activities and projects and joint decision making processes. It is seen a body that will oversee al EPI related projects that will implemented in the country. Particularly the ICC will:

- Coordinate preparation, review, approve and submit proposals on GAVI applications

- Supervise the implementation and monitor the progress of GAVI funded activities being implemented

- Assess the impact of GAVI funded activities

- Ensure regular information sharing and communication between all partners involved

Three major strategies to enhance the ICC’s role and functions in the next 12 months:

1.	Involve more partners and stakeholders into the ICC membership

2.	Involve more decision makers into ICC in order to address and advocate EPI issues

3.	Improve the quality of meetings through better information sharing and follow up after meetings

## 3.    Immunisation Programme Data

Please complete the tables below, using data from available sources.  Please identify the source of the data, and the date. Where possible use the most recent data, and attach the source document.

  - Please refer to the Comprehensive Multi-Year Plan for Immunisation (or equivalent plan), and attach a complete copy (with an executive summary) as DOCUMENT NUMBER ………………..

  - Please refer to the two most recent annual WHO/UNICEF Joint Reporting Forms on Vaccine Preventable Diseases and attach them as DOCUMENT NUMBERS …………………………..

  - Please refer to Health Sector Strategy documents, budgetary documents, and other reports, surveys etc, as appropriate.

Table 3.1: Basic facts for the year 2006 (the most recent; specify dates of data provided)

|  | Figure | Date | Source |
| --- | --- | --- | --- |
| Total population | 712,800 | January 2007 | State Statistical Agency, and Health care facilities |
| Infant mortality rate (per 1000) | 14.2 | January 2007 | Official statistics of MoH, State Statistical Agency and Centre of Health Information System |
| Surviving Infants* | 176, 706 | January 2007 | Statistical Agency and Centre of Health Information System |
| GNI per capita (US$) | 390$USD | January 2007 | Statistical Agency |
| Percentage of GDP allocated to Health | 1.1% | January 2007 | Statistical Agency |
| Percentage of Government expenditure on Health | 25.0% | January 2007 | Statistical Agency |

* Surviving infants = Infants surviving the first 12 months of life

Please provide some additional information on the planning and budgeting context in your country:

Please indicate the name and date of the relevant planning document for health

The National Development Strategy of the Republic of Tajikistan for the Period to 2015, The Strategy of the Republic of Tajikistan on the Health of the Population to 2010, Poverty Reduction Strategy (PRS) and The Strategy of the Republic of Tajikistan on the Health of the Population to 2010 identify the major priority directions for health system development in the country: Conception of Health Care Reform of the Republic of Tajikistan was developed and approved by the Government of Tajikistan in 2002. It provides a general framework for health reform directions and supports the strategies and interventions outlined in other strategy and policy documents. The main developmental strategies for the health care reform defined in this Conception.

The Ministry of Finance (MoF) is the main government body responsible for overall budgeting process and the health sector in Tajikistan is financed through the central and local taxation and donor support.  The Ministry of Health (MoH) is in charge of the health sector planning, policy development and budgeting and is also responsible for management and financing of the Republican level health care facilities such as tertiary clinics, research institutes and vertically organized structures, among them Republican Center of Immunoprophylaxis.  Primary and secondary level facilities are subordinated to the local administrations - “Hukumats” and their financing is performed through the local budget. The general budget of Government of Tajikistan approved for 2007. The budget for 2008 is under consideration. Health budget is 1.1% of GDP.

Is the cMYP (or updated Multi-Year Plan) aligned with this document (timing, content etc)

The Ministry of Health developed and approved Financial Sustainability Plan for National Immunization Program in 2002. Tajikistan was identified as the first country to start supporting the Comprehensive Multi-Year Planning (cMYP) process.  WHO/EURO initiated the joint mission of WHO, UNICEF and World Bank to support the Ministry of Health to develop the cMYP. The cMYP missions considered being the best opportunity to address systematically the issue of sustainability of the National Immunization Program (NIP) including the vaccine sustainability planning. Developing a cMYP is also an opportunity to consolidate existing plans into a single document that addresses global, national and sub-national immunization objectives and strategies, and that also evaluates the costs and financing of that plan.

The Ministry of Health does not have the detailed implementation plan similar to cMYP, therefore the cMYP has been developed based on the existing Conception of Health Care Reform of the Republic of Tajikistan as well ad Strategy of the Republic of Tajikistan on the Health of the Population to 2010.

The cMYP has been revised in August-September 2007, and aligned with the health budget.

Please indicate the national planning budgeting cycle for health

The Ministry of Finance (MoF) is the main government body responsible for an overall budgeting process. The health sector in Tajikistan is financed through the central and local taxation and donor support.  The MoH determines the structure and capacities of the Republican health entities (national tertiary-level facilities, research institutes, vertical structures e.g. Republican Immunization Center) that are financed from the central budget while district level facilities are subordinated to and financed by the local administration - “Hukumat”.  International financial institutions, (the World Bank and Asian Development Bank), UN agencies, bilateral donors and international NGOs are active in Tajikistan health sector mobilizing own resources and allocating through independent projects. The national planning budgeting cycle for health formed annually jointly by Ministry of Finance and Ministry of Health based on the planned activities of MoH and with consideration of limited resources of Government.

Please indicate the national planning cycle for immunization

The Immunization Programme of the Republic of Tajikistan in 2003 – 2010. This document has been developed in close cooperation with all partners and members of the Interagency Coordination Committee (ICC). The programme has been framed within the policy framework for National Health Reform, in which decentralization and local development are fundamental policies to allow improved and enhanced access of the population to PHC services. The plan addresses improvement of immunization services management, capacity building, safety of injections, and ensuring of financial sustainability of immunizations services.

Currently RCIP operates on the basis of the bylaw approved by the MoH and has a separate budget, which is formed from the central health budget. RCIP is responsible for planning, monitoring of EPI activities, provision of vaccines and supplies including reporting/registration documentation, data analysis, methodological guidance, and surveillance of vaccine preventable diseases. The National Immunization Program (NIP) in Tajikistan is financed from three sources: the central budget (National government), local budget (sub-national government) and international donors. Traditionally almost all direct costs of the NIP (vaccines, injection materials, program activities) have been covered by donors/EPI partners. Only recently the GoT committed to allocate approximately 2 million Somoni (521,512 USD) for the procurement of vaccines (for routine immunization) from 2008. For the overall strategic management the MoH approved the National Immunization Plan (2003) and later the Financial Sustainability Plan (2002-2007) developed by the RCIP with the support of development partners (WHO, UNICEF, WHO, etc.). Besides the strategic plan there are separate plans for certain program components, which are in line with WHO guidelines. Strategic planning function of the program is being strengthened with an Interagency Coordination Committee (ICC) in terms of coordination and partnership, but ICC potential as a coordination tool is not used in full capacity. The

Table 3.2: 	Current Vaccination Schedule: Traditional, New Vaccines and Vitamin A Supplement (refer to cMYP pages)

| Vaccine (do not use trade name) | Ages of administration (by routine immunisation services) | Indicate by an “x” if given in: | Comments |
| --- | --- | --- | --- |
|  |  | Entire country | Only part of the country |  |
| OPV-0 + Hep 1 | Within 24 hour after birth | X |  |  |
| BCG | 3-5 days after birth | X |  |  |
| DTP-1 OPV-1 HepB-2 | 2 months | X |  |  |
| DTP-2 OPV-2 | 3 months | X |  |  |
| DTP-3 OPV-3 HepB-3 | 4 moths | X |  |  |
| Measles-1 OPV-4 | 12 months | X |  |  |
| DTP-4 | 16-23 months | X |  |  |
| Measles-2 DT | 6 years | X |  |  |
| Vitamin A | 6 months – 57 moths Postpartum women | X |  | Funded by UNICEF |

Comment: the MoH plans to change calendar upon approval of current application through adding pentavalent vaccine (DTP+Hib+HepB) three times (2,3,4 moths)

Table 3.3: Trends of immunisation coverage and disease burden

(as per last two annual WHO/UNICEF Joint Reporting Form on Vaccine Preventable Diseases)

| Trends of immunisation coverage (in percentage) | Vaccine preventable disease burden |
| --- | --- |
| Vaccine | Reported | Survey | Disease | Number of reported cases |
|  | 2005 | 2006 | 2005 | 200… |  | 2005 | 2006 |
| BCG | 79.3 | 80,5 | 95,1 |  | Tuberculosis* | 526 | 631 |
| DTP | DTP1 | 82.0 | 82,5 |  |  | Diphtheria | 3 | 2 |
|  | DTP3 | 80,2 | 80,6 | 80,6 |  | Pertussis | 23 | 22 |
| Polio 3 | 80,6 | 79,5 | 73,0 |  | Polio | - | - |
| Measles (first dose) | 81,0 | 80,6 | 85,6 |  | Measles | - | 3 |
| TT2+ (Pregnant women) | - | - | - |  | NN Tetanus | - | - |
| Hib3 | - | - | - |  | Hib ** | - | - |
| Yellow Fever | - | - | - |  | Yellow fever | - | - |
| HepB3 | 78,6 | 78,7 | 68,5 |  | hepB sero-prevalence* | - | - |
| Vit A supplement | Mothers (<6 weeks post-delivery) | 79,0 | 82,0 |  |  |  |  |  |
|  | Infants (>6 months) | 80,0 | 81,3 |  |  |  |  |  |

Comments: The national immunization coverage data worsened due to the changes of denominator (target group) in 2006.

* If available

** Note: JRF asks for Hib meningitis

If survey data is included in the table above, please indicate the years the surveys were conducted, the full title and if available, the age groups the data refers to:

MICS survey – conducted by UNICEF in 2005

Table 3.4: Baseline and annual targets (refer to cMYP pages)

| Number | Baseline and targets |
| --- | --- |
|  | Base 2006 | Year 1 2008 | Year 2 2009 | Year 3 2010 | Year 4 2011 | Year 5 2012 |
| Births | 188,991 | 194,853 | 201,495 | 206,029 |  |  |
| Infants’ deaths | 12,285 | 12,665 | 12,090 | 11,538 |  |  |
| Surviving infants | 176,706 | 182,187 | 189,405 | 194,491 |  |  |
| Pregnant women | 188,991 | 194,853 | 201,495 | 206,029 |  |  |
| Target population vaccinated with BCG | 152,200 | 175,367 | 187,390 | 195,727 |  |  |
| BCG coverage* | 80,5 | 90,0 | 93,0 | 95,0 |  |  |
| Target population vaccinated with OPV3 | 139,597 | 153,037 | 162,888 | 175,041 |  |  |
| OPV3 coverage** | 79,0 | 82,0 | 84,0 | 86,0 |  |  |
| Target population vaccinated with DTP3*** | 142,425 | 149,393 | 159,100 | 167,267 |  |  |
| DTP3 coverage** | 80,6 | 82,0 | 84,0 | 86,0 |  |  |
| Target population vaccinated with DTP1*** | 144,899 | 163,822 | 171,873 | 181,994 |  |  |
| Wastage rate in base-year and planned thereafter | 1,25 | 1,25 | 1,25 | 1,25 |  |  |
| Target population vaccinated with 3rd dose of …HepB3……….. | 139,067 | 149,393 | 159,100 | 167,267 |  |  |
| …………. Coverage** | 78,7 | 82,0 | 84,0 | 86,0 |  |  |
| Target population vaccinated with 1st dose of …HepB1………….. | 141,365 | 163,822 | 173,182 | 181,994 |  |  |
| Wastage1 rate in base-year and planned thereafter | 1,15 | 1,15 | 1,15 | 1,15 |  |  |
| Target population vaccinated with 1st dose of Measles | 141,365 | 149,393 | 159,100 | 167,267 |  |  |
| Target population vaccinated with 2nd dose of Measles | 139,598 | 158,237 | 168,054 | 176,340 |  |  |
| Measles coverage** | 80,0 | 82,0 | 84,0 | 86,0 |  |  |
| Pregnant women vaccinated with TT+ |  | - | - | - |  |  |
| TT+ coverage**** |  | - | - | - |  |  |
| Vit A supplement | 2006 6-59months |  | 694,134 | 712,342 | 732,124 |  |  |
|  | 2006 Pas/women |  | 135,350 | 156,672 | 160,876 |  |  |
| Annual DTP Drop out rate [ ( DTP1 - DTP3 ) / DTP1 ] x 100 |  | 2,2 | 2,2 | 2,1 |  |  |
| Annual Measles Drop out rate (for countries applying for YF) |  | - | - | - |  |  |

*  Number of infants vaccinated out  of total births

**  Number of infants vaccinated out of surviving infants

***  Indicate total number of children vaccinated with either DTP alone or combined

**** Number of pregnant women vaccinated with TT+ out of total pregnant women

Table 3.5: Summary of current and future immunisation budget (The data presented in this table reflect cMYP scenario with introduction of DTP-Hib-HepB vaccine)

|  | Estimated costs per annum in US$ (,000) |
| --- | --- |
| Cost category | Base year | Year 1 2008… | Year 2 2009… | Year 3 2010… | Year 4 2011… | Year 5 2012… |
| Routine Recurrent Cost |  |  |  |  |  |  |
| Vaccines (routine vaccines only) |  |  |  |  |  |  |
| Traditional vaccines | 524,210 | 570,931 | 488,546 | 516,095 |  |  |
| New and underused vaccines | 200,917 | 1,322,229 | 2,329,357 | 2,492,547 |  |  |
| Injection supplies | 167,214 | 275,670 | 305,047 | 322,743 |  |  |
| Personnel |  |  |  |  |  |  |
| Salaries of full-time NIP health workers (immunisation specific) | 92,208 | 98,663 | 105,569 | 112,959 |  |  |
| Per-diems for outreach vaccinators / mobile teams | 25,782 | 27,587 | 29,518 | 31,564 |  |  |
| Transportation | 58,634 | 104,797 | 157,257 | 165,735 |  |  |
| Maintenance and overheads | 169,062 | 173,488 | 181,187 | 188,213 |  |  |
| Training | 52,000 | 353,780 | 275,860 | 78,740 |  |  |
| Social mobilisation and IEC | 13,500 | 38,760 | 26,800 | 5,800 |  |  |
| Disease surveillance | 52,878 | 79,900 | 77,900 | 15,600 |  |  |
| Program management | 77,182 | 100,700 | 94,083 | 34,000 |  |  |
| Other |  | 21,000 | 35,000 | 30,000 |  |  |
| Subtotal Recurrent Costs | 1,433,587 | 3,167,504 | 4,106,124 | 3,994,016 |  |  |
| Routine Capital Costs |  |  |  |  |  |  |
| Vehicles |  |  |  |  |  |  |
| Cold chain equipment |  | 103,786 | 53,219 | 36,050 |  |  |
| Other capital equipment |  | 6,375 | 6,503 | 6,633 |  |  |
| Subtotal Capital Costs |  | 110,161 | 59,722 | 42,683 |  |  |
| Campaigns |  |  |  |  |  |  |
| Polio |  |  |  |  |  |  |
| Measles |  |  |  |  |  |  |
| Yellow Fever |  |  |  |  |  |  |
| MNT campaigns |  |  |  |  |  |  |
| Other campaigns |  |  |  |  |  |  |
| Subtotal Campaign Costs |  |  |  |  |  |  |
| GRAND TOTAL | 2,022,095 | 3,907,369 | 4,839,628 | 4,757,646 |  |  |

Please list in the tables below the funding sources for each type of cost category (if known). Please try and indicate which immunisation program costs are covered from the Government budget, and which costs are covered by development partners (or the GAVI Alliance), and name the partners.

Table 3.6: Summary of current and future financing and sources of funds (The data presented in this table reflect cMYP scenario with introduction of DTP-Hib-HepB vaccine)

|  |  | Estimated financing per annum in US$ (,000) |
| --- | --- | --- |
| Cost category | Funding source | 2006 | Year 1 2008 | Year 2 2009 | Year 3 2010 | Year 4 20… | Year 5 20… |
| Routine Recurrent Cost |  |  |  |  |  |  |
|  | 1.Government | 121,671 | 614,822 | 593,357 | 617,169 |  |  |
|  | 2. Sub-national | 117,398 | 140,169 | 168,992 | 154,468 |  |  |
|  | 3.UNICEF | 270,975 | 111,486 | 172,000 |  |  |  |
|  | 4.WHO | 117,000 | 160,000 |  |  |  |  |
|  | 5.JICA | 225,303 | 382,908 |  |  |  |  |
|  | 6.TICA | 91,567 |  |  |  |  |  |
|  | 7.GAVI | 368,131 | 1,654,048 |  |  |  |  |
| Routine Capital Costs | 0 |  |  |  |  |  |
|  | UNICEF |  | 28,000 | 10,000 |  |  |  |
|  | GAVI |  |  | 15,400 |  |  |  |
| Other cost | 1. Sub-national | 588,508 | 629,704 | 673,783 | 720,948 |  |  |
| 2. | 2. |  |  |  |  |  |  |
| 3. | 3. |  |  |  |  |  |  |
| 4. | 4. |  |  |  |  |  |  |
| 5. | 5. |  |  |  |  |  |  |
| Campaigns | 0 | 0 | 0 | 0 |  |  |
| 1. | 1. |  |  |  |  |  |  |
| 2. | 2. |  |  |  |  |  |  |
| 3. | 3. |  |  |  |  |  |  |
| 4. | 4. |  |  |  |  |  |  |
| 5. | 5. |  |  |  |  |  |  |
| GRAND TOTAL | 1,900,553 | 2,995,394 | 3,631,789 | 3,818,368 |  |  |

## 4.    Immunisation Services Support (ISS)

Please indicate below the total amount of funds you expect to receive through ISS:

Table 4.1: Estimate of fund expected from ISS

|  | Base Year | Year 1 2008 | Year 2 2009 | Year 3 2010 | Year 4 2011 | Year 5 2012 |
| --- | --- | --- | --- | --- | --- | --- |
| DTP3 Coverage rate |  |  |  |  |  |  |
| Number of infants reported / planned to be vaccinated with DTP3 (as in Table 3.4) |  |  |  |  |  |  |
| Number of additional infants that annually are reported / planned to be vaccinated with DTP3 |  |  |  |  |  |  |
| Funds expected ($20 per additional infant) |  |  |  |  |  |  |

*  Projected figures

**  As per duration of the cMYP

If you have received ISS support from GAVI in the past, please describe below any major lessons learned, and how these will affect the use of ISS funds in future.

Please state what the funds were used for, at what level, and if this was the best use of the flexible funds; mention the management and monitoring arrangements; who had responsibility for authorising payments and approving plans for expenditure; and if you will continue this in future.

| Major Lessons Learned from Phase 1 | Implications for Phase 2 |
| --- | --- |

If you have not received ISS support before, please indicate:

a) when you would like the support to begin:

b) when you would like the first DQA to occur:

c) how you propose to channel the funds from GAVI into the country:

d) how you propose to manage the funds in-country:

e) who will be responsible for authorising and approving expenditures:

  - Please complete the banking form (annex 1) if required

## 5.   Injection Safety Support

  - Please attach the National Policy on Injection Safety including safe medical waste disposal (or reference the appropriate section of the Comprehensive Multi-Year Plan for Immunisation), and confirm the status of the document: DOCUMENT NUMBER………………

  - Please attach a copy of any action plans for improving injection safety and safe management of sharps waste in the immunisation system (and reference the Comprehensive Multi-Year Plan for Immunisation).  DOCUMENT NUMBER………………….

Table 5.1: Current cost of injection safety supplies for routine immunisation

Please indicate the current cost of the injection safety supplies for routine immunisation.

|  | Annual requirements | Cost per item (US$) | Total Cost (US$) |
| --- | --- | --- | --- |
| Year | Syringes | Safety Boxes | Syringes | Safety Boxes |  |
| 2006… |  |  |  |  |  |

Table 5.2: Estimated supply for safety of vaccination with   БЦЖ   vaccine

(Please use one table for each vaccine BCG(1 dose), DTP(3 doses), TT(2 doses) 1, Measles(1 dose) and Yellow Fever(1 dose), and number them from 5.1 to 5.5)

|  |  | Formula | Year 1 2008 | Year 2 2009 | Year 3 2010 | Year 4 2011 | Year 5 20… |
| --- | --- | --- | --- | --- | --- | --- | --- |
| A | Number of children to be vaccinated 2 | # |  |  |  |  |  |
| B | Percentage of vaccines requested from GAVI 3 | % |  |  |  |  |  |
| C | Number of doses per child | # |  |  |  |  |  |
| D | Number of doses | A x B/100 x C |  |  |  |  |  |
| E | Standard vaccine wastage factor 4 | Either 2.0 or 1.6 |  |  |  |  |  |
| F | Number of doses (including wastage) | A x B/100 x C x E |  |  |  |  |  |
| G | Vaccines buffer stock 5 | F x 0.25 |  |  |  |  |  |
| H | Number of doses per vial | # |  |  |  |  |  |
| I | Total vaccine doses | F + G |  |  |  |  |  |
| J | Number of AD syringes (+ 10% wastage) requested | (D + G) x 1.11 |  |  |  |  |  |
| K | Reconstitution syringes (+ 10% wastage) requested 6 | I / H x 1.11 |  |  |  |  |  |
| L | Total of safety boxes (+ 10% of extra need) requested | (J + K) / 100 x 1.11 |  |  |  |  |  |

1 GAVI supports the procurement of AD syringes to deliver two doses of TT to pregnant women. If the immunisation policy of the country includes all Women in Child Bearing Age (WCBA), GAVI/The Vaccine Fund will contribute to a maximum of two doses for Pregnant Women (estimated as total births)

2 To insert the number of infants that will complete vaccinations with all scheduled doses of a specific vaccine.

3 Estimates of 100% of target number of children is adjusted if a phased-out of GAVI/VF support is intended.

4 A standard wastage factor of 2.0 for BCG and of 1.6 for DTP, Measles, TT, and YF vaccines is used for calculation of INS support

5 The buffer stock for vaccines and AD syringes is set at 25%. This is added to the first stock of doses required to introduce the vaccination in any given geographic area. Write zero under other years. In case of a phased introduction with the buffer stock spread over several years, the formula should read: [ F – number of doses (incl. wastage) received in previous year ] * 0.25.

6 It applies only for lyophilized vaccines; write zero for other vaccines.

  - If you do not intend to procure your supplies through UNICEF, please provide evidence that the alternative supplier complies with WHO requirements by attaching supporting documents as available.

## 6.   New and Under-Used Vaccines (NVS)

Please give a summary of the cMYP sections that refer to the introduction of new and under-used vaccines. Outline the key points that informed the decision-making process (data considered etc): Although the increase in the government’s financing of vaccines and injections improved significantly the financial situation of the NIP, the overall financial sustainability is under high risk considering that the total funding gap remains very high due to absence of secured financing of operational and other resource requirements of routine immunization. The Government of Tajikistan, specifically the MoH and RCIP officials the first of all and the EPI partners has to be commended for their steady efforts that resulted in the tenfold increase of the share of government’s financing of the NIP. It improved the financial sustainability of the NIP concerning vaccine supply however the program is likely to fail to meet targets if the funds for operational resource requirements and capital costs are not secured. Introduction of the Pentavalent vaccine offers a good opportunity to add a new antigen to routine immunization calendar at a very low cost. Tajikistan considered applying for support for introduction of Hib Pentavalent vaccine due to WHO global recommendation on inclusion of Hib conjugate vaccine in all infant routine immunization programs even with a lack of local surveillance data. From the financial sustainability stand point it is cost-effective to introduce DTP-HepB-Hib vaccine that allows decreasing the funding gap during the next three years. Considering the urgency of improving the financial sustainability of the MoH decided to apply to the GAVI for the NVS by September 28 to secure financial support from the beginning of 2008. The cost-effectiveness of the introduction of DTP-Hib-HepB vaccine has been conducted by WHO expert and shared during the previous ICC meetings and has been finalised and agreed during the joint EPI mission in August-September 2007. Given the short time allocated for proposal development the MoH/RCIP and EPI partners expressed commitment to mobilize their resources to meet the challenge and produce quality application in time. Tajikistan is planning to introduce new Pentavalent vaccine in 2008; therefore vaccination schedule has been revised and in case of new vaccine introduction it will be changed as shown in table below. The cMYP reflects all financial expenditures related with Pentavalent introduction. The advantages of introduction of Pentavalent vaccine. The ICC meetings provided good opportunity to get all partners and stakeholders to get more understanding on the EPI priorities including the needs of introduction of Pentavalent vaccine. The participants realized the importance and appropriateness of introduction of new vaccine into national immunization calendar.

Revised Vaccination schedule

| Antigen | 12 h | 3-5 d | 2 mo | 3 mo | 4 mo | 12 mo | 16-23 mo | 6 y | 14 y | 16 y | 26,36, 46,56 y |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| BCG |  |  |  |  |  |  |  |  |  |  |  |
| DTP |  |  |  |  |  |  |  |  |  |  |  |
| DTP-HepB-HiB |  |  |  |  |  |  |  |  |  |  |  |
| DT |  |  |  |  |  |  |  |  |  |  |  |
| OPV |  |  |  |  |  |  |  |  |  |  |  |
| HepB |  |  |  |  |  |  |  |  |  |  |  |
| Measles |  |  |  |  |  |  |  |  |  |  |  |
| TD |  |  |  |  |  |  |  |  |  |  |  |

Please summarise the cold chain capacity and readiness to accommodate new vaccines, stating how the cold chain expansion (if required) will be financed, and when it will be in place. Please use attached excel annex 2a (Tab 6) on the Cold Chain. Please indicate the additional cost, if capacity is not available and the source of funding to close the gap RCIP has a complete inventory of all cold chain equipment at all levels. An inventory study and then assessment to identify cold chain needs has been conducted in 2004 and 2006 by UNICEF. Need assessment is based on current implementation level of the immunization program. It does not cover introduction of new vaccines, therefore it’s in line with the cMYP basic scenario. The assessment identifies upgrade and replacement of cold chain equipment amounting 327,000 $. This plan includes procurement of cold chain equipment mainly for district level and vaccine carrier and cold box type of equipment for operational level below district level from 2008 till 2010. This plan is fully incorporated into cMYP. In 2006 the Effective Vaccine Store Management (EVSM) assessment has been conducted to evaluate the vaccine storage at the National level as well as condition of the cold store and transportation of vaccines into the 6 regions. The assessment covers the process starting from procurement of vaccines up to its use according with the 10 criteria. The assessment revealed 67% available storage capacity. Based on the calculation done by the EVSM assessment team (using the Model Quality Plan) the cold store space available was around 20% larger than the peak level requested for vaccines stored in the interval +2 to +8oC. the same calculation for freeze space showed that the space available is more that three times larger than the peak volume of vaccines stored in -20 oC. The capacity of existing cold chain equipment presently allows storing sufficient amount of vaccines for the country. At the national, regional and district levels there are sufficient capacity of cold rooms to store additional amount of vaccines. Two biggest regions of the Republic also have sufficient space to store more vaccines. The Integrated Assessment of Immunization quality and safety revealed that the national level the volume of plus cold rooms comprising 20m3 that allow storing up to 10 mln doses of vaccine. The vaccine peak volume had never exceeded the storage capacity, even at the time of mass immunization campaigns.

Table 6.1: Capacity and cost (for positive storage) (Refer to Tab 6 of Annex 2a or Annex 2b)

|  |  | Formula | Year 1 2008 | Year 2 2009 | Year 3 2010 | Year 4 2011 | Year 5 2012 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| A | Annual positive volume requirement, including new vaccine litres | Sum-product of total vaccine doses multiplied by unit packed volume of the vaccine | 11,587 liters | 11,982 | 12,251 |  |  |
| B | Annual positive capacity, including new vaccine litres | # | 11,224 | 11,224 | 11,224 |  |  |
| C | Estimated minimum number of shipments per year required for the actual cold chain capacity | A / B |  |  |  |  |  |
| D | Number of consignments / shipments per year | Based on national vaccine shipment plan | 2 | 2 | 2 |  |  |
| E | Gap (if any) | ((A / D) - B) | 5,430 | 5,233 | 5,098 |  |  |
| F | Estimated cost for expansion | US $ | 2,000 | 2,000 | 2,000 |  |  |

Please briefly describe how your country plans to move towards attaining financial sustainability for

the new vaccines you intend to introduce, how the country will meet the co-financing payments, and any other issues regarding financial sustainability you have considered (refer to the cMYP):

The analysis revealed that although the 10 times increase in the government’s financing of vaccines and injections improved significantly the financial situation of the NIP, the overall financial sustainability is under high risk considering that the total funding gap remains very high due to absence of secured financing of operational and other resource requirements of routine immunization.

It is important to mention that immunization is an inexpensive program that only costs around 31 cents in per capita terms (including vaccines, injections, and operational cost. The main strategy financial sustainability of the program should be based on prioritization of immunization program by the government and increasing domestic financial allocations towards the program. In addition, the comparison of three scenarios by resource requirement for vaccines and corresponding funding gaps shows that from that financial sustainability and stand point it is cost-effective to introduce DTP-Hib-HepB vaccine that allows decreasing the funding gap by $0.9 million during next 3 years. The implication of the introduction of new vaccine on financial sustainability (only for routine immunization considering costs of vaccines and injection supplies) is reflected in cMYP (Figure 17)

The Ministry of Health is confident that the country will meet the co-financial payments The Government will allocate 2,8% in 2008, 2,9% in 2009 and 3% in 2010 out of the overall health budget. The RCIP will continue negotiations with Government on budget increase.  The Government is confident. Detailed description of financial situation for each scenario and effects of the introduction of new vaccines on financial sustainability of the NIP are presented in detail in financial analysis of cMYP. There is a little room for the reduction of the financial gap through increasing efficiency and effectiveness of the NIP (considering the current and projected wastage rates. The further acceleration of advocacy efforts of key stakeholders aimed at increasing the allocation of the public funds to the NIP is considered as a primary financial sustainability strategy of the NIP. The advocacy interventions will be built on the recent success achieved due to concerted advocacy efforts of the EPI partners. The mobilization of additional funds from external resources is considered as a part of the advocacy strategy rather than a separate financial sustainability strategy: any additional external funding has to encourage the government to spend more on the NIP instead of replacing the state funds. This can be achieved through the introduction of incentive schemes similar to matching grants when donor funds will be disbursed in a certain proportion to additional public assignations to the NIP; another powerful mechanism could be a direct budget support already provided to the Government of Tajikistan by donors if the public financing of the NIP is included in the set of performance indicators agreed between the donor and the GoT  (tranches of the direct budget support are conditional upon.) The application of abovementioned incentive based donor financing schemes calls for more intensive and productive coordination of donors in the country. Finally, another set of activities within the advocacy strategy ensuring financial sustainability in long run is related to the introduction of a so called policy based budgeting; the GoT intends to switch to a Medium Term Expenditure Framework budgeting practice supported by the development partners. It implies that budget projection will be linked to concrete sectoral (health) policy objectives (within a broader set of policy objectives defined in the national development strategy) including immunization related objectives.

Table 6.2: Assessment of burden of relevant diseases (if available):

There is lack of proper information and strong evidence of Hib diseases in Tajikistan due to unavailability of special studies, assessments or surveillance data. The Ministry of Health revered to regional estimates and recent WHO position paper on Hib.

| Disease | Title of the assessment | Date | Results |
| --- | --- | --- | --- |
| Hib | WHO Position paper on Haemophilius Influenzae type b conjugate vaccine (Weekly Epidemiological record) | 24.11.2006 |  |

If new or under-used vaccines have already been introduced in your country, please give details of the lessons learnt from storage capacity, protection from accidental freezing, staff training, cold chain, logistics, drop out rate, wastage rate etc., and suggest solutions to address them:

| Lessons Learned | Solutions / Action Points |
| --- | --- |
| The capacity of cold chain allowed to store sufficient amount of vaccine |  |
| While introducing Hep B vaccine the RCIP used the strategy of distribution 1 dose vials in the rural areas and 10 doses vials in bigger settlements in order to minimize wastage rates | It is desirable to have 1 or two doses vaccine presentation, given that 70% of population lives in rural areas |
| The RCIP received freezing indicators to control Hep B vaccine | Currently the RCIP is in process of establishing of computerized system for freezing control |
| MoH introduced the Hep B vaccine throughout the country, but it was challenging to measure the efficiency due to the lack of proper surveillance system for Hep B including laboratory diagnostics | Strengthen surveillance through improvement of laboratory system and training. Establishing sentinel surveillance for Hib might be solution. |
| Introduction of Hep B vaccine started from maternity houses. Gradual introduction of HepB vaccine in the country created difficulties to monitor Hep B immunization coverage and reporting. | It is preferable to introduce new vaccines simultaneously throughout the country. |
| Training of health staff on immunization issues, but due to the high turnover of medical personnel more tanning sessions is required | Provision of training to new health care staff |
| Advocacy, communication and social mobilization activities were conducted, but more emphasis should be given to explain about vaccine safety | Elaborate proper IEC materials for caretakers (parents, mothers) |

Please list the vaccines to be introduced with support from the GAVI Alliance (and presentation):

The MoH made decision to introduce the one dose liquid Hip conjugate vaccine it its pentavalent presentation (DTP+Hib+Hep-B).

The Government intention is to include MR vaccine into routine immunization calendar by 2009. It is expected that the Government will increase the financing of the program and will therefore allow introducing MR vaccine. The MR introduction scenario reflected in details in cMYP.

First Preference Vaccine

As reported in the cMYP, the country plans to introduce Hib antigen vaccinations, using Pentavalent vaccine, in 1 doses per vial of liquid form.

Please refer to the excel spreadsheet Annex 2a or Annex 2b (for Rotavirus and Pneumo vaccines) and proceed as follows:

  - Please complete the “Country Specifications” Table in Tab 1 of Annex 2a or Annex 2b, using the data available in the other Tabs: Tab 3 for the commodities price list, Tab 5 for the vaccine wastage factor and Tab 4 for the minimum co-financing levels per dose.

- Please summarise the list of specifications of the vaccines and the related vaccination programme in Table 6.3 below, using the population data (from Table 3.4 of this application) and the price list and co-financing levels (in Tables B, C, and D of Annex 2a or Annex 2b).

  - Then please copy the data from Annex 2a or 2b (Tab “Support Requested”) into Tables 6.4 and 6.5 (below) to summarize the support requested, and co-financed by GAVI and by the country.

  - Please submit the electronic version of the excel spreadsheets Annex 2a or 2b together with the application

Table 6.3: Specifications of vaccinations with new vaccine

| Vaccine: DTP-Hib-HepB 1 dose liquid presentation | Use data in: |  | Year 1 2008 | Year 2 2009 | Year 3 2010 |
| --- | --- | --- | --- | --- | --- |
| Number of children to be vaccinated with the third dose | Table 3.4 | # | 75,915 | 159,100 | 167,267 |
| Target immunisation coverage with the third dose | Table 3.4 | # | 82 | 84 | 86 |
| Number of children to be vaccinated with the first dose | Table 3.4 | # | 77,891 | 171,873 | 181,994 |
| Estimated vaccine wastage factor | Annex 2a or 2b Table E - tab 5 | # | 1,05 | 1,05 | 1,05 |
| Country co-financing per dose * | Annex 2a or 2b Table D - tab 4 | $ | 0,3 | 0,3 | 0,3 |

* Total price pre dose includes vaccine cost, plus freight, supplies, insurance, fees, etc

Table 6.4: Portion of supply to be co-financed by the country (and cost estimate, US$)

Introduction of Pentavalent vaccine is expected to start in mid 2008, therefore, figures for the Year 1 are less than the following years.

| Vaccine: DTP-Hib-HepB 1 dose liquid presentation |  | Year 1 2008 | Year 2 2009 | Year 3 2010 |
| --- | --- | --- | --- | --- |
| Number of vaccine doses | # | 285 000 | 519 513 | 563 600 |
| Number of AD syringes | # | 285 000 | 519 513 | 563 600 |
| Number of re-constitution syringes | # |  |  |  |
| Number of safety boxes | # | 3 250 | 6 525 | 6 150 |
| Total value to be co-financed by country | $ | $92 500 | $185 000 | $174 500 |

Table 6.5: Portion of supply to be procured by the GAVI Alliance (and cost estimate, US$)

| Vaccine: DTP-Hib-HepB 1 dose liquid presentation |  | Year 1 2008 | Year 2 2009 | Year 3 2010 |
| --- | --- | --- | --- | --- |
| Number of vaccine doses | # | 14 700 | 29 400 | 27 700 |
| Number of AD syringes | # | 14 700 | 29 600 | 28 200 |
| Number of re-constitution syringes | # |  |  |  |
| Number of safety boxes | # | 175 | 350 | 325 |
| Total value to be co-financed by GAVI | $ | $1 060 000 | $2 127 000 | $2 009 000 |

  - Please refer to http://www.unicef.org/supply/index_gavi.html for the most recent GAVI Alliance Vaccine Product Selection Menu, and review the GAVI Alliance NVS Support Country Guidelines to identify the appropriate country category, and the minimum country co-financing level for each category.

Second Preference Vaccine

If the first preference of vaccine is in limited supply or currently not available, please indicate below the alternative vaccine presentation

Lyophilized 2 dose Pentavalent vaccine will be introduce in case if there is a limited supply for first choice.

- Please complete tables 6.3 – 6.4 for the new vaccine presentation

- Please complete the excel spreadsheets Annex 2a or Annex 2b for the new vaccine presentation and submit them alongside the application.

Procurement and Management of New and Under-Used Vaccines

a) Please show how the support will operate and be managed including procurement of vaccines (GAVI expects that most countries will procure vaccine and injection supplies through UNICEF):

The procurement mechanism of Pentavalent vaccine has been discussed among partners and based on previous experience, the MoH will use procurement services of UNICEF. The MoH will transfer co-payment amount required for Pentavalent vaccine through UNICEF supply division.

b) If an alternative mechanism for procurement and delivery of supply (financed by the country or the GAVI Alliance) is requested, please document:

NO

c) Please describe the introduction of the vaccines (refer to cMYP)

Tajikistan put as a priority introduction of new vaccine as there is political and epidemiological necessity to introduce it. Hib vaccine in its Pentavalent presentation may compensate discontinuation of GAVI support for Hep B along with relieving burden on financing of other antigens and immunization supplies. Although Hib disease burden is not thoroughly assessed, introduction of Hib-containing Pentavalent vaccines is planned based of WHO position paper of November 2006 and cost-effectiveness of introduction. Introduction of the vaccine by using the GAVI opportunity will not only enable a dramatic reduction in the burden of disease and contribute its share to the achievements of the Millennium Development Goals, but will lead to cost savings in the long term and help to improve the quality of immunization services as well.

A number of meetings and consultations with experts took place in order to discuss the feasibility of introduction of Pentavalent vaccine in the country. The cost-effectiveness analysis has been conducted by WHO expert. The issue of new vaccine introduction has been discussed thoroughly discussed during the joint EPI mission in September 2007. The aim of the mission was to provide technical assistance to the MoH in setting out policy priorities related to the NIP by reviewing the technical sub-cluster issues (vaccine forecast, financial analysis, and the implication of new vaccine introductions). (Minutes of the conducted meetings attached).

Detailed description of financial situation for each scenario and effects of the introduction of new vaccines on financial sustainability of the NIP are presented in the attached cMYP and Pentavalent Introduction Plan.

d) Please indicate how funds should be transferred by the GAVI Alliance (not applicable)

e) Please indicate how the co-financing amounts will be paid (and who is responsible for this)

The co-financing amounts will be paid according with the co-financing level for Pentavelent vaccine on the annual basis. Funds will be transferred through National Bank of Tajikistan to UNICEF supply division unit in Copenhagen. The Republican Center of Immunoprophylaxis will provide the bank details later.

f) Please outline how coverage of the new vaccine will be monitored and reported (refer to cMYP)

Adding a vaccine will generally require updating the forms and vaccination cards used for recording and reporting, forms for ordering vaccines and vaccine stock ledgers, and any other forms that are used in the immunization programme. The Ministry of Health plans to update all the forms including children’s immunization cards. With the introduction of Pentavalent vaccine, all EPI forms will need to be revised and reprinted. These include:

-immunization schedules and cards

-Vaccine stock forms and cards

-vaccination tally sheets, vaccination registers and computer programs

-new information materials for parents and training material for health care workers will need to be developed

Apart from that the human resource capacity will be strengthened through the provision of training and conducting supportive supervision visits to all levels.

New and Under-Used Vaccine Introduction Grant

Table 6.5: calculation of lump-sum

| Year of New Vaccine introduction | N° of births (from table 3.4) | Share per birth in US$ | Total in US$ |
| --- | --- | --- | --- |
| 2008 | 197,205 | $ 0.30 | 100,000 |

Please indicate in the tables below how the one-time Introduction Grant will be used to support the costs of vaccine introduction and critical pre-introduction activities (refer to the cMYP).

Table 6.6: Cost (and finance) to introduce the first preference vaccine (US$)

| Cost Category | Full needs for new vaccine introduction | Funded with new vaccine introduction grant |
| --- | --- | --- |
|  | US$ | US$ |
| Training | 39,000 | 18,000 |
| Social Mobilization, IEC and Advocacy | 18,000 | 12,000 |
| Cold Chain Equipment & Maintenance | 11,000 | 6,000 |
| Vehicles and Transportation | 328,000 | 32,000 |
| Programme Management | 12,000 | 5,000 |
| Surveillance and Monitoring | 17,000 | 12,000 |
| Human Resources | 19,200 | 5,000 |
| Waste Management | 39,000 | 10,000 |
| Technical assistance |  |  |
| Other (please specify) |  |  |
| Other (please specify) |  |  |
| Other (please specify) |  |  |
| Other (please specify) |  |  |
| Total | 483,000 | 100,000 |

  - Please complete the banking form (annex 1) if required

Please complete a table similar to the one above for the second choice vaccine (if relevant) and title it Table 6.7: Cost (and finance) to introduce the second preference vaccine (US$)

## 7. Additional comments and recommendations from the National Coordinating Body (ICC)

The members of the ICC committee admitted the importance and benefits of Pentavalent vaccine introduction. They also agreed with the time submission of the NVS Application to GAVI Secretariat.

## 8.   Documents required for each type of support

| Type of Support | Document | DOCUMENT NUMBER | Duration * |
| --- | --- | --- | --- |
| ALL | WHO / UNICEF Joint Reporting Form (last two) |  |  |
| ALL | Comprehensive Multi-Year Plan (cMYP) |  |  |
| ALL | Endorsed minutes of the National Coordinating Body meeting where the GAVI proposal was endorsed |  |  |
| ALL | Endorsed minutes of the ICC/HSCC meeting where the GAVI proposal was discussed |  |  |
| ALL | Minutes of the three most recent ICC/HSCC meetings |  |  |
| ALL | ICC/HSCC workplan for the forthcoming 12 months |  |  |
| Injection Safety | National Policy on Injection Safety including safe medical waste disposal (if separate from cMYP) |  |  |
| Injection Safety | Action plans for improving injection safety and safe management of sharps waste (if separate from cMYP) |  |  |
| Injection Safety | Evidence that alternative supplier complies with WHO requirements (if not procuring supplies from UNICEF) |  |  |
| New and Under-used Vaccines | Plan for introduction of the new vaccine (if not already included in the cMYP) |  |  |

* Please indicate the duration of the plan / assessment / document where appropriate

ANNEX 1

| Banking Form |
| --- |
| SECTION 1 (To be completed by payee) |
| In accordance with the decision on financial support made by the GAVI Alliance dated . . . . . . . . . . . , the Government of . . . . . . . . . . . . . . . . . . . hereby requests that a payment be made, via electronic bank transfer, as detailed below: |
| Name of Institution: (Account Holder) |  |
| Address: |  |
| City – Country: |  |
| Telephone No.: |  | Fax No.: |  |
| Amount in USD: | (To be filled in by GAVI Secretariat) | Currency of the bank account: |  |
| For credit to: Bank account’s title |  |
| Bank account No.: |  |
| At: Bank’s name |  |
| Is the bank account exclusively to be used by this program? | YES ( ) NO ( ) |
| By whom is the account audited? |  |
| Signature of Government’s authorizing official: By signing below, the authorizing official confirms that the bank account mentioned above is known to the Ministry of Finance and is under the oversight of the Auditor General. |
| Name: |  | Seal: |
| Title: |  |  |
| Signature: |  |  |
| Date: |  |  |
| Address and Phone number |  |  |
| Fax number |  |  |
| Email address: |  |  |

| SECTION 2 (To be completed by the Bank) |
| --- |
| FINANCIAL INSTITUTION | CORRESPONDENT BANK (In the United States) |
| Bank Name: |  |  |
| Branch Name: |  |  |
| Address: |  |  |
| City – Country: |  |  |
| Swift code: |  |  |
| Sort code: |  |  |
| ABA No.: |  |  |
| Telephone No.: |  |  |
| Fax No.: |  |  |
| Bank Contact Name and Phone Number: |  |  |
| I certify that the account No. . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . is held by (Institution name) . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . .at this banking institution. |
| The account is to be signed jointly by at least …… (number of signatories) of the following authorized signatories: | Name of bank’s authorizing official: |
| 1 Name: Title: |  | Signature: |  |
|  |  | Date: |  |
| 2 Name: Title: |  | Seal: |
| 3 Name: Title: |  |  |
| 4 Name: Title: |  |  |

COVERING LETTER

(To be completed by UNICEF representative on letter-headed paper)

### TO:    GAVI Alliance – Secretariat

### Att. Dr Julian Lob-Levyt

### Executive Secretary

C/o UNICEF

Palais des Nations

CH 1211 Geneva 10

Switzerland

| On the ……………………………… I received the original of the BANKING DETAILS form, which is attached. I certify that the form does bear the signatures of the following officials: |
| --- |
|  | Name |  |  | Title |
| Government’s authorizing official |  |  |  |  |
| Bank’s authorizing official |  |  |  |  |
| Signature of UNICEF Representative: |
| Name |  |
| Signature |  |
| Date |  |

# Footnotes

National Development Strategy of the Republic of Tajikistan till 2015. Section 7, pp 41-44

The Strategy of the Republic of Tajikistan on the Health of the Population to 2010.

The formula to calculate a vaccine wastage rate (in percentage): [ ( A – B ) / A ] x 100.   Whereby : A = The number of doses distributed for use according to the supply  records with correction for stock balance at the end of the supply period; B =  the number of  vaccinations with the same vaccine in the same period. For new vaccines check table (  after Table 7.1.

Table D1 should be used for the first vaccine, with tables D2 and D3 for the second and third vaccine co-financed by the country

The Grant will be based on a maximum award of $0.30 per infant in the birth cohort with a minimum starting grant award of $100,000