IRC Recommendation: Approval with clarifications

Clarifications:

1. Is the Project Manager aware that the amount of available funding from GAVI for the project is US$ 226,000, which is a significant difference when compared to the requested US$ 155,000? This difference could be used to readjust some aspects of the budget that appear weak at present (see main body of report), or used to ensure training and social mobilisation funds for the Education Sector for training of teachers.

Response

Budget has being adjusted See table on Item 6 Qn 29 on main document

Year 2 Target is as follows

| Target Population for year 2 ( 9-13 yrs ) |  |  |  |
| --- | --- | --- | --- |
| District | Non GVT school | Government school | Total |
| HAI | 171 | 2,362 | 2,532 |
| MOSHI RURAL | 221 | 5,583 | 5,805 |
| MOSHI URBAN | 273 | 1,736 | 2,009 |
| ROMBO | 72 | 3,815 | 3,887 |
| SIHA | 17 | 1,384 | 1,401 |
| Kilimanjaro Total | 754 | 14,879 | 15,634 |
| population Growth rate 2.9% |  |  |  |

2. Please provide further clarification on the following areas of the current budget items:

- A budget breakdown showing funds for the first and second years;

- Allocation for training seems small compared to the need of training 1,250 Vaccinators and 6,365 Teachers in the four selected districts of the Kilimanjaro Region;

- This also relates to social mobilisation, for which only the launching is budgeted.

- Please clarify financial contribution from other partners to assure redundancy in funding will not occur. One way of doing this very clearly could be to rework the present excellent timeline. Consider adding two columns for each planned activity in the timeline, one for funding amount needed/ funding responsibility and one on overall responsibility for implementation; this would clarify to GAVI funding expected from other sources vs. funding from GAVI for each line item.

Response

Has being developed refer Item 6 Qn 29

3. What other specific strategies and approaches are anticipated to allow reaching of the out of school girls to ensure that they are all enrolled and that they do not drop out until they are fully immunised? Is there an intention to develop and issue a home-based HPV Immunisation record to each girl? If not, why?

Response

- Other specific strategies and approaches to reach out of school girls

  - Use special campaigns which are done annually during the African Child and immunization days

  - The Vitamin A campaigns which are done bi-annually will be utilized to reach these girls as well

  - Community advocacy and sensitization meetings, Focal media, Radio and TV programme.

  - There are home based care programs in HIV and AIDS, which can be linked to follow up the out of school girls

  - Use of  RED/REC  Strategy