|  |  |  |  |  | [V2.7]. |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| GAVI Alliance. |  |  |  |  |  |  |  |
| Application Form for Country Proposals. |  |  |  |  |  |  |  |
| For Support to:. |  |  |  |  |  |  |  |
| Routine New Vaccines Support. Preventive Campaign Support. |  |  |  |  |  |  |  |
| Submitted by. |  |  |  |  |  |  |  |
| The Government of. |  |  |  |  |  |  |  |
| Rwanda. |  |  |  |  |  |  |  |
| Date of submission: 8/31/2012. |  |  |  |  |  |  |  |
| Deadline for submission: 8/31/2012. |  |  |  |  |  |  |  |
| Select Start and End Year of your Comprehensive Multi-Year Plan (cMYP). |  |  |  |  |  |  |  |
| Start Year. | 2012. |  |  |  |  |  |  |
|  |  |  | End Year. | 2017. |  |  |  |
| Form revised in 2012. |  |  |  |  |  |  |  |
| (To be used with Guidelines of September 2012). |  |  |  |  |  |  |  |
| Please submit the Proposal using the online platform. https://AppsPortal.gavialliance.org/PDExtranet. |  |  |  |  |  |  |  |
| Enquiries to: proposals@gavialliance.org or representatives of a GAVI partner agency. The documents can be shared with GAVI partners, collaborators and general public. The Proposal and attachments must be submitted in English, French, Spanish, or Russian.. Note: Please ensure that the application has been received by the GAVI Secretariat on or before the day of the deadline.. The GAVI Secretariat is unable to return submitted documents and attachments to countries. Unless otherwise specified, documents will be shared with the GAVI Alliance partners and the general public.. |  |  |  |  |  |  |  |

GAVI ALLIANCE GRANT TERMS AND CONDITIONS. FUNDING USED SOLELY FOR APPROVED PROGRAMMES. The applicant country ("Country") confirms that all funding provided by the GAVI Alliance will be used and applied for the sole purpose of fulfilling the programme(s) described in the Country's application. Any significant change from the approved programme(s) must be reviewed and approved in advance by the GAVI Alliance. All funding decisions for the application are made at the discretion of the GAVI Alliance Board and are subject to IRC processes and the availability of funds.. AMENDMENT TO THE APPLICATION. The Country will notify the GAVI Alliance in its Annual Progress Report if it wishes to propose any change to the programme(s) description in its application.The GAVI Alliance will document any change approved by the GAVI Alliance, and the Country's application will be amended.. RETURN OF FUNDS. The Country agrees to reimburse to the GAVI Alliance all funding amounts that are not used for the programme(s) described in its application. The country's reimbursement must be in US dollars and be provided, unless otherwise decided by the GAVI Alliance, within sixty (60) days after the Country receives the GAVI Alliance's request for a reimbursement and be paid to the account or accounts as directed by the GAVI Alliance.. SUSPENSION/ TERMINATION. The GAVI Alliance may suspend all or part of its funding to the Country if it has reason to suspect that funds have been used for purpose other than for the programmes described in the Country's application, or any GAVI Alliance-approved amendment to the application.The GAVI Alliance retains the right to terminate its support to the Country for the programmes described in its application if a misuse of GAVI Alliance funds is confirmed.. ANTICORRUPTION. The Country confirms that funds provided by the GAVI Alliance shall not be offered by the Country to any third person, nor will the Country seek in connection with its application any gift, payment or benefit directly or indirectly that could be construed as an illegal or corrupt practice.. AUDITS AND RECORDS. The Country will conduct annual financial audits, and share these with the GAVI Alliance, as requested. The GAVI Alliance reserves the right, on its own or through an agent, to perform audits or other financial management assessment to ensure the accountability of funds disbursed to the Country.. The Country will maintain accurate accounting records documenting how GAVI Alliance funds are used. The Country will maintain its accounting records in accordance with its government-approved accounting standards for at least three years after the date of last disbursement of GAVI Alliance funds. If there is any claims of misuse of funds, Country will maintain such records until the audit findings are final. The Country agrees not to assert any documentary privilege against the GAVI Alliance in connection with any audit.. CONFIRMATION OF LEGAL VALIDITY. The Country and the signatories for the Country confirm that its application, and Annual Progress Report, are accurate and correct and form legally binding obligations on the Country, under the Country's law, to perform the programmes described in its application, as amended, if applicable, in the APR.. CONFIRMATION OF COMPLIANCE WITH THE GAVI ALLIANCE TRANSPARANCY AND ACCOUNTABILITY POLICY. The Country confirms that it is familiar with the GAVI Alliance Transparency and Accountability Policy (TAP) and complies with the requirements therein.. USE OF COMMERCIAL BANK ACCOUNTS. The Country is responsible for undertaking the necessary due diligence on all commercial banks used to manage GAVI cash-based support. The Country confirms that it will take all responsibility for replenishing GAVI cash support lost due to bank insolvency, fraud or any other unforeseen event.. ARBITRATION. Any dispute between the Country and the GAVI Alliance arising out of or relating to its application that is not settled amicably within a reasonable period of time, will be submitted to arbitration at the request of either the GAVI Alliance or the Country. The arbitration will be conducted in accordance with the then-current UNCITRAL Arbitration Rules. The parties agree to be bound by the arbitration award, as the final adjudication of any such dispute. The place of arbitration will be Geneva, Switzerland. . The languages of the arbitration will be English or French.. For any dispute for which the amount at issue is US$ 100,000 or less, there will be one arbitrator appointed by the GAVI Alliance. For any dispute for which the amount at issue is greater than US $100,000 there will be three arbitrators appointed as follows: The GAVI Alliance and the Country will each appoint one arbitrator, and the two arbitrators so appointed will jointly appoint a third arbitrator who shall be the chairperson.. The GAVI Alliance will not be liable to the country for any claim or loss relating to the programmes described in the application, including without limitation, any financial loss, reliance claims, any harm to property, or personal injury or death. Country is solely responsible for all aspects of managing and implementing the programmes described in its application..

1. Application Specification. Please specify for which type of GAVI support you would like to apply to..

Type of Support; Vaccine; Start Year; End Year; Preferred second presentation[1]. Routine New Vaccines Support; HPV quadrivalent, 1 dose(s) per vial, LIQUID; 2014; 2017. Preventive Campaign Support; MR, 10 dose(s) per vial, LYOPHILISED; 2013; 2013.

[1] This "Preferred second presentation" will be used in case there is no supply available for the preferred presentation of the selected vaccine ("Vaccine" column). If left blank, it will be assumed that the country will prefer waiting until the selected vaccine becomes available..

Note for HPV and MR: These prices are indicative only as GAVI has not procured HPV and MR vaccines for GAVI countries yet. Prices will be finalised through tender processes in Q3. GAVI will only fund HPV vaccines if an acceptable price reduction is secured from the current price indicated. The MR price is based on the current price to UNICEF.

2. Table of Contents.

1. Application Specification. 2. Table of Contents. 3. Executive Summary. 4. Signatures. 4.1. Signatures of the Government and National Coordinating Bodies. 4.1.1. Government and the Inter-Agency Coordinating Committee for Immunisation. 4.1.2. National Coordinating Body - Inter-Agency Coordinating Committee for Immunisation. 4.1.3. The Inter-Agency Coordinating Committee for Immunisation. 4.2. National Immunization Technical Advisory Group for Immunisation. 4.2.1. The NITAG Group for Immunisation. 5. Immunisation Programme Data. 5.1. Basic facts. 5.1.1 HPV specific facts. 5.1.2 MCV Immunisation coverage. 5.2. Baseline and Annual Targets (NVS Routine Support). 5.2.1 HPV specific targets. 5.3. Baseline and Annual Targets for Preventive Campaign(s). 5.3.1 Baseline and annual targets (MR campaign). 6. New and Under-Used Vaccines (NVS Routine). 6.1. Assessment of burden of relevant diseases (if available). 6.1.1 HPV burden specific information. 6.1.2 Delivery strategy for HPV vaccine. 6.2 Requested vaccine (HPV quadrivalent, 1 dose(s) per vial, LIQUID). 6.2.1 Co-financing information. 6.2.2 Specifications of vaccinations with new vaccine. 6.2.3 Portion of supply to be procured by the country (and cost estimate, US$). 6.2.4 Portion of supply to be procured by the GAVI Alliance (and cost estimate, US$). 6.2.5 New and Under-Used Vaccine Introduction Grant. 7. NVS Preventive Campains. 7.1. Assessment of burden of relevant diseases related to campaigns (if available). 7.2 Requested for MR, 10 dose(s) per vial, LYOPHILISED campaign support. 7.2.1 Summary for MR campaign support. 7.2.2 Grant Support for Operational Costs of the MR Campaign. 7.2.3 Evidence of introduction of RCV in routine programme. 7.2.4 Introduction planning for RCV. 7.2.5 Measles surveillance indicators. 7.2.6 Rubella Containing Vaccine introduction Grant. 8. Procurement and Management. 8.1. Procurement and Management of New and Under-Used Vaccines Routine. 8.2. Procurement and Management for NVS Preventive Campaign(s). 8.2.1 Procurement and Management for MR, 10 dose(s) per vial, LYOPHILISED campaign. 8.3. Vaccine Management (EVSM/EVM/VMA). 9. Additional Comments and Recommendations from the National Coordinating Body (ICC/HSCC). 10. Attachments. 11. Annexes. Annex 1 - NVS Routine Support. Annex 1.1 HPV quadrivalent, 1 dose(s) per vial, LIQUID. Table Annex 1.1 A Rounded up portion of supply that is procured by the country and estimate of relative costs in US$. Table Annex 1.1 B Rounded up portion of supply that is procured by GAVI and estimate of relative costs in US$. Table Annex 1.1 C Summary table for vaccine HPV quadrivalent, 1 dose(s) per vial, LIQUID. Table Annex 1.1 D Estimated numbers for HPV quadrivalent, 1 dose(s) per vial, LIQUID, associated injection safety material and related co-financing budget (page 1). Annex 2 - NVS Routine – Preferred Second Presentation. Annex 3 - NVS Preventive campaign(s). Table Annex 3.1 C Summary table for vaccine MR, 10 dose(s) per vial, LYOPHILISED. Table Annex 3.1 D Estimated numbers for MR, 10 dose(s) per vial, LYOPHILISED, associated injection safety material and related co-financing budget (page 1). Annex 4. Table Annex 4A: Commodities Cost. Table Annex 4B: Freight cost as percentage of value. Table Annex 4C: Low - Minimum country's co-payment per dose of co-financed vaccine.. Table Annex 4D: Wastage rates and factors. Table Annex 4E: Vaccine maximum packed volumes. 12. Banking Form.

3. Executive Summary.

Please provide a summary of your country's proposal, including the following the information:. l; For each specific request, NVS routine support or NVS campaign :. ¡; The duration of support. ¡; The total amount of funds. ¡; Details of the vaccine(s), if applicable. l; Relevant baseline data, including:. ¡; DTP3 and Measles coverage data (as reported on the WHO/UNICEF Joint Reporting Form). ¡; Birth cohort, targets and immunisation coverage by vaccines. l; Country preparedness. ¡; Summary of EVM assessment. l; The nature of stakeholders' participation in developing this proposal. ¡; Inter-Agency Coordinating Committee. EXECUTIVE SUMMARY The Rwanda's Vaccine Preventable Diseases Division has a goal, the one to contribute to the reduction of morbidity and mortality due to vaccine preventable diseases among the children < 5 years old. For this reason, In 2002, national EPI put in place a pediatric bacterial meningitis surveillance system (PBMS) in one of the Universities Teaching Hospital and realized that meningitis and pneumonia were among the big killers of children before the age of 5. At the same year, EPI introduced a DTP containing vaccine (combined with HepB and Hib vaccine). In 2008, data from HMIS identified severe diarrheal disease as the third leading cause of death among children < 5 years of age in Rwanda. Since 2002 to date, Rwanda achieved and maintained high measles coverage rates (>80%). In addition, every 2-3 years, EPI team conducted a high quality measles -SIAs and reached the very high coverage (>95%). The measles case-based surveillance system, initiated since 2007, identified high proportion of rubella cases among the measles suspected cases. Because of this, EPI Rwanda wants to take advantage of measles platform of 2 doses of measles vaccine to introduce, accelerate control and elimination activities of both measles and rubella. Cervical cancer remains the most common cancer among Rwandan's women. The World Health Organization ranks Rwanda among the countries with highest cervical cancers worldwide with incidence estimated to 49.4/100,000. Because of this, Government of Rwanda signed a memorandum of understanding (MOU) with MERCK to introduce human papilloma virus vaccine (HPV vaccine) to immunize and prevent the majority of adolescent girls (9-14 years of age) nationwide. According to this MOU, MERCK donated HPV vaccine to EPI Rwanda for a period of three years (2011 - 2013) and Rwanda was supposed to pay for injection material and for operational costs. As GAVI just opened the opportunity to support eligible countries with HPV vaccine, Rwanda wants to take this opportunity and apply for this vaccine beyond 2013. Government of Rwanda is fully committed in achieving the mid decade goals 4 and 5 (MDG 4 and 5) by 2015. For this reason, it takes all the available opportunities to reduce significantely the mortality and morbidity among the targeted population. For 2013, Government has decided to introduce both MR vaccine and in 2014, HPV vaccine. The expected support . from GAVI will be: (a) For MR vaccine, the initial wide age-range campaign (9 months to 14 years old), nationwide (in 2013). This initial catch-up campaign, Rwanda expects to receive from GAVI bandled MR vaccine, AD syringes, reconstitution syringes and safety boxes. In addition, GAVI will pay 80% of total operational costs, which has been estimated to $3, 279,392 and the remaining 20% will be paid by the country. MR vaccine will be in 10 dose per vial, Lyophilized. (b) For HPV vaccine, the expected support will be for 4 years with the specified support: (a) One cash grant estimated to $1,088,371 in 2014 and (b) Vaccine costs paid for $0.80 per child of birth cohort as the country will pay $.0.20 (from 2014 to 2017). HPV quadrivalent, 1 dose per vial, Liquid. Birth cohort: 2011 (419878), 2013 (441996), 2014 (453488), 2015 (465278), 2016 (477376), 2017 (489787). These figures are based on 2002 census projection which can be subjected to changes once 2012 census is done. Relevant baseline data (WHO/UNICEF Joint Reporting Form) in 2011: BCG 99% OPV3 93% DTP3 97% Measles 95% Based on the provision of the Rwandan National Immunization Program 2011-2015 and following the country plan to introduce new vaccines using GAVI co-financing mechanism, and EVM assessment was carried out between 4-27 July 2011, and evidence based plan to improve management, monitoring and supervision of the country immunization supply chain was developed. In 2011, Rwanda conducted EVM and identified areas for improvement as follows: - All vaccine shipments should have vaccines arrival reports - A temperature monitoring study should be carried out according to WHO/IVB/05.01 study protocol - A temperature mapping exercise should carried out at all cold rooms, and freezer rooms - Continuous temperature monitoring devices should be used at all levels( fridge tags, multilogs) - Current net capacity of the cold rooms should be improved with additional shelves - All cold rooms and freezer rooms at central cold store should be fitted with dual refrigeration units - Need for SMT at the central level - Separate stock record for vaccine and diluent - EPI guideline should be revised according to WHO recommendations - Refresher training for vaccine store managers at all levels. The key stakeholders from Ministry of health, UNICEF, WHO and USAID/MCHIP jointly meet as EPI Advisory committee which is part of ICC to develop this proposal and present it to senior ICC members comprising of Minister of health, Minister of Education, Ministry of Finance, Heads of agencies and private sectors..

| 4. Signatures. |  |  |
| --- | --- | --- |
| 4.1. Signatures of the Government and National Coordinating Bodies. |  |  |
| 4.1.1. Government and the Inter-Agency Coordinating Committee for Immunisation. |  |  |
| The Government of Rwanda would like to expand the existing partnership with the GAVI Alliance for the improvement of the infants routine immunisation programme of the country, and specifically hereby requests for GAVI support for. |  |  |
|  | HPV quadrivalent, 1 dose(s) per vial, LIQUID routine introduction. MR, 10 dose(s) per vial, LYOPHILISED preventive campaigns. |  |
| The Government of Rwanda commits itself to developing national immunisation services on a sustainable basis in accordance with the Comprehensive Multi-Year Plan presented with this document. The Government requests that the GAVI Alliance and its partners contribute financial and technical assistance to support immunisation of children as outlined in this application.. |  |  |
| Table(s) 6.2.4 in the NVS Routine section of this application shows the amount of support in either supply or cash that is required from the GAVI Alliance. Table(s) 6.2.3 of this application shows the Government financial commitment for the procurement of this new vaccine (NVS support only).. |  |  |
| Following the regulations of the internal budgeting and financing cycles the Government will annually release its portion of the co-financing funds in the month of October.. |  |  |
| The payment for the first year of co-financed support will be around October 2013 for MR, 10 dose(s) per vial, LYOPHILISED.. The payment for the first year of co-financed support will be around October 2014 for HPV quadrivalent, 1 dose(s) per vial, LIQUID.. |  |  |
| Please note that this application will not be reviewed or approved by the Independent Review Committee (IRC) without the signatures of both the Minister of Health and Minister of Finance or their delegated authority.. |  |  |
| Minister of Health (or delegated authority); Minister of Finance (or delegated authority). Name; Dr Agnes BINAGWAHO; Name; Mr John RWANGOMBWA. Date; Date. Signature; Signature. |  |  |
| Proof of involvement of the Ministry of Education will also be required for HPV Routine Support. The Ministry of Education will either have to be involved in the ICC process (preferred option) or provide its signature... Minister of Education (or delegated authority). Name; Dr Vincent BIRUTA. Date. Signature.. Minister of Education signature is as DOCUMENT NUMBER: 3... |  |  |
| This report has been compiled by (these persons may be contacted in case the GAVI Secretatiat has queries on this document):. |  |  |
| Full name; Position; Telephone; Email. GATERA Maurice; EPI Manager; +250785152534; gamaurice2003@yahoo.fr. |  |  |
| 4.1.2. National Coordinating Body - Inter-Agency Coordinating Committee for Immunisation. |  |  |
| We the members of the ICC, HSCC, or equivalent committee [1] met on the 15/08/2012 to review this proposal. At that meeting we endorsed this proposal on the basis of the supporting documentation which is attached.. |  |  |
| [1] Inter-agency Coordinating Committee or Health Sector Coordinating Committee, or equivalent committee which has the authority to endorse this application in the country in question.. |  |  |
| The endorsed minutes of this meeting are attached as document number 4.. |  |  |
| Name/Title*; Agency/Organisation*; Signature. Dr ANTOINE MUYOMBANO; INTERNATIONAL ROTARY CLUB. Dr DANIEL NGAMIJE; SINGLE PROJECT IMPLEMENTATION UNIT (SPIU). Dr DELANYO DEVLO; WHO. Dr FIDELE NGABO; MATERNAL AND CHILD HEALTH UNIT, MOH. Dr NOALA SKINNER; UNICEF. Mr ERNEST RWAGASANA; BUFMAR. Mr GEORGE GAHENDA; URUNANA DEVELOPMENT COMMUNICATION. Mr PETER MALNAK; USAID. |  |  |
| 4.1.3. The Inter-Agency Coordinating Committee for Immunisation. |  |  |
| Agencies and partners (including development partners and NGOs) supporting immunisation services are co-ordinated and organised through an inter-agency coordinating mechanism (ICC, HSCC, or equivalent committee). The ICC, HSCC, or equivalent committee is responsible for coordinating and guiding the use of the GAVI NVS routine support and/or campaign support. Please provide information about the ICC, HSCC, or equivalent committee in your country in the table below.. |  |  |
| Profile of the ICC, HSCC, or equivalent committee. |  |  |
| Name of the committee; ICC. Year of constitution of the current committee; 1996. Organisational structure (e.g., sub-committee, stand-alone); Stand alone committee. Frequency of meetings; Quarterly. |  |  |
| Composition. |  |  |
| Function; Title / Organisation; Name. Chair; Minister of Health, Ministry of Health; Dr AGNES BINAGWAHO. Secretary; Head of VPDD, Vaccine Preventable Diseases Division; Mr MAURICE GATERA. Members; EPI Focal person, WHO; Dr RUGAMBWA CELSE. EPI Focal person, WHO; Dr MALIFA BALDE MAMADOU. CHIEF, HEALTH AND NUTRIRION SECTION, UNICEF; Dr FRIDAY NWAIGWE. HEALTH OFFICER, UNICEF; Dr DENISE ILIBAGIZA. SUPERVISION OFFICER, VPDD; Mr EMMANUEL NZARAMBA. IMMUNIZATION EPIDEMIOLOGIST SPECIALIST; Mr HASSAN SIBOMANA. COLD CHAIN OFFICER, VPDD; Mr ANICET RWASANGABO. DIRECTOR OF IMMUNIZATION SYSTEM& SAFETY, VPDD; Mr JERED MUHOZA. VPD SURVEILLANCE OFFICER, VPDD; Ms MATHILDE BATAMULIZA. SURVEILLANCE SAMPLE COLLECTING&REPORTING OFFICER, VPDD; Ms ANASTASIE MUKAMUSONI. MATERNAL AND CHILD HEALTH SPECIALIST, USAID; Mr ERIC KAGAME. IMMUNIZATION TECHNICAL ADVISOR, UASID/MCHIP; Dr AUGUSTIN GATERA. DIRECTOR, URUNANA DEVELOPMENT COMMUNICATION; Mr GEORGE GAHENDA. DIRECTOR, BUFMAR; Mr ERNEST RWAGASANA. DIRECTOR, INTERNATIONAL ROTARY CLUB; Dr ANTOINE MUYOMBANO. COORDINATOR, SPIU; Dr DANIEL NGAMIJE. MATERNAL AND CHILD HEALTH DIVISION, MOH; Dr FIDELE NGABO. |  |  |
| Major functions and responsibilities of the ICC/HSCC:. |  |  |
| 1. Share technical, financial and logistics information related to immunization services; 2. Coordinate and guide the use of GAVI and partners funds for immunization 3. Coordinate partners' interventions to better support immunization program 4. Support technically and financially the EPI program in order to meet the targeted goals 5. Advocacy and resource mobilization to support the program. |  |  |
| Three major strategies to enhance the committee's role and functions in the next 12 months. |  |  |
| 1.; Technical ICC with working sub-committees (Technical, Logistics, Surveillance and Social mobilization) to meet on the monthly basis. Each sub committee, to meet and discuss key issues and report to the large ICC committee, once every month. 2.; Strategic or political ICC, comprised by the Minster of Health or delegate, Minister of Finance or delegate and the heads of partners' Agencies, to meet on quarterly basis. They make decision on critical issues presented by Technical ICC and endorse some policy documents and/or proposals to be submitted to GAVI. 3.; Technical ICC to monitor, on monthly basis, performance of the Program and discuss the approaches for improvement.. |  |  |
| 4.2. National Immunization Technical Advisory Group for Immunisation. |  |  |
| (If it has been established in the country). |  |  |
| We the members of the NITAG met on the to review this proposal. At that meeting we endorsed this proposal on the basis of the supporting documentation which is attached.. |  |  |
| The endorsed minutes of this meeting are attached as document number 4.. |  |  |

4.2.1. The NITAG Group for Immunisation.

Profile of the NITAG.

Name of the NITAG; N/A. Year of constitution of the current NITAG. Organisational structure (e.g., sub-committee, stand-alone); N/A. Frequency of meetings; N/A.

Composition.

Function; Title / Organisation; Name. Chair. Secretary. Members.

Major functions and responsibilities of the NITAG.

N/A.

Three major strategies to enhance the NITAG's role and functions in the next 12 months.

1.; N/A. 2.; N/A. 3.; N/A.

5. Immunisation Programme Data.

5.1. Basic facts.

Please complete the tables below, using data from available sources. Please identify the source of the data, and the date. Where possible use the most recent data and attach the source document..

▪; Please refer to the Comprehensive Multi-Year Plan for Immunisation (cMYP) (or equivalent plan) and attach a complete copy (with an Executive Summary) as DOCUMENT NUMBER : 6. ▪; Please attach relevant Vaccine Introduction Plans as DOCUMENT NUMBER : 7. ▪; Please refer to the two most recent annual WHO/UNICEF Joint Reporting Forms (JRF) on Vaccine Preventable Diseases. ▪; Please refer to Health Sector Strategy documents, budgetary documents, and other reports, surveys etc, as appropriate..

For the year 2011 (most recent; specify dates of data provided).

Figure; Year; Source. Total population; 10,240,932; 2011; 2002 Census projection based on 2.6 % growth rate. Infant mortality rate (per 1000); 50; 2011; Demographic health Survey 2011. Surviving infants[1]; 337,706; 2011; Ministry of Health. GNI per capita (US$); 570; 2011; World Bank Branch, 2011. Total Health Expenditure (THE) as a percentage of GDP; 48; %; 2011; MOF. General government expenditure on health (GGHE) as % of General government expenditure; 16; %; 2011; MOF.

[1] Surviving infants = Infants surviving the first 12 months of life.

Please provide some additional information on the planning and budgeting context in your country. Additional information on Planning and budgeting: Planning process is conducted by each health program. Developed plans are sent to the MOH for consolidation. MOH integrates different plans received from health programs/ services and come up with the national health plan. EPI plan is part of this plan which comes from cMYP (where all the objectives and strategies were defined for specific year of the cycle of the cMYP). Please indicate the name and date of the relevant planning document for health. Relevant planning documents and date: 1. National Development Plan 2. Comprehensive Multi-Year Plan (cMYP 2013-2017) 3. Annual EPI Plan 2013 4. New & underused vaccine introduction plans (HPV 2014 and MSD/RCV 2013). Is the CMYP (or updated Multi-Year Plan) aligned with the document (timing, content, etc.). Yes. Please indicate the national planning budgeting cycle for health. July-June of proceeding year. Please indicate the national planning cycle for immunisation. July-June of proceeding year. Please indicate if sex disaggregated data (SDD) is used in immunisation routine reporting systems. No sex disaggregated data. Please indicate if gender aspects relating to introduction of a new vaccine have been addressed in the introduction plan. Yes it has been addressed in the introduction of new vaccines : every Rwandan child has equal opportunity to be vaccinated. Please describe any recent evidence of socio-economic and/or gender barriers to the immunisation programme through studies or surveys?. No study or survey on socio-economic or gender barriers to the immunization program conducted. Country should provide an outline of all preparatory activities for vaccine(s) introduction. Preparatory activities for new vaccine introduction: - \Assessment of the magnitude of the problem and inform decision makers on new vaccine introduction - Initiate the development of proposal with all the required documents (Updated cMYP, introduction plan) - Call for ICC to endorse the proposal before submission - Submit proposal to GAVI Secretariat - If approved by GAVI, the preparation phase stats (advocacy for vaccine introduction support, upgrade cold chain, revision of EPI management tools, training of health workers, surveillance for the disease and AEFI, development of key messages to parents and health workers).

5.1.1 HPV specific facts.. Please demonstrate country’s ability to deliver a complete multi-dose series of vaccines to at least 50% of the target vaccination cohort in an average size district using a similar strategy to the one proposed for HPV vaccine delivery. For each district, fill-in:.. District Information. Name of the district; Nyarungenge. Size of population of the district; 280,926. Describe how the district is divided into rural and urban areas:; 100% Urban. District Information. Name of the district; Gasabo. Size of population of the district; 452,822. Describe how the district is divided into rural and urban areas:; 100% Urban. District Information. Name of the district; Kicukiro. Size of population of the district; 280,442. Describe how the district is divided into rural and urban areas:; 100% Urban. District Information. Name of the district; Nyaza. Size of population of the district; 298,688. Describe how the district is divided into rural and urban areas:; 30% Urban 70% Rural. District Information. Name of the district; Gisangara. Size of population of the district; 316,486. Describe how the district is divided into rural and urban areas:; 100% Rural. District Information. Name of the district; Nyarunguru. Size of population of the district; 292,028. Describe how the district is divided into rural and urban areas:; 100% Rural. District Information. Name of the district; Huye. Size of population of the district; 327,669. Describe how the district is divided into rural and urban areas:; 35% Urban 65% Rural. District Information. Name of the district; Nyamagabe. Size of population of the district; 354,506. Describe how the district is divided into rural and urban areas:; 10% Urban 90% Rural. District Information. Name of the district; Ruhango. Size of population of the district; 319,053. Describe how the district is divided into rural and urban areas:; 30% Urban 70% Rural. District Information. Name of the district; Muhanga. Size of population of the district; 340,693. Describe how the district is divided into rural and urban areas:; 40% Urban 60% Rural. District Information. Name of the district; Kamonyi. Size of population of the district; 327,303. Describe how the district is divided into rural and urban areas:; 10% Urban 90% Rural. District Information. Name of the district; Karongi. Size of population of the district; 334,051. Describe how the district is divided into rural and urban areas:; 15% Urban 85% Rural. District Information. Name of the district; Rutsiro. Size of population of the district; 336,538. Describe how the district is divided into rural and urban areas:; 100% Rural. District Information. Name of the district; Rubavu. Size of population of the district; 397,046. Describe how the district is divided into rural and urban areas:; 30% Urban 70% Rural. District Information. Name of the district; Nyabihu. Size of population of the district; 338,993. Describe how the district is divided into rural and urban areas:; 15% Urban 85% Rural. District Information. Name of the district; Ngororero. Size of population of the district; 354,536. Describe how the district is divided into rural and urban areas:; 10% Urban 90% Rural. District Information. Name of the district; Rusizi. Size of population of the district; 405,686. Describe how the district is divided into rural and urban areas:; 20% Urban 80% Rural. District Information. Name of the district; Nyamasheke. Size of population of the district; 391,359. Describe how the district is divided into rural and urban areas:; 5% Urban 95% Rural. District Information. Name of the district; Rulindo. Size of population of the district; 301,267. Describe how the district is divided into rural and urban areas:; 5% Urban 95% Rural. District Information. Name of the district; Gakenke. Size of population of the district; 380,006. Describe how the district is divided into rural and urban areas:; 10% Urban 90% Rural. District Information. Name of the district; Musanze. Size of population of the district; 376,615. Describe how the district is divided into rural and urban areas:; 40% Urban 60% Rural. District Information. Name of the district; Burera. Size of population of the district; 363,960. Describe how the district is divided into rural and urban areas:; 5% Urban 95% Rural. District Information. Name of the district; Gicumbi. Size of population of the district; 409,567. Describe how the district is divided into rural and urban areas:; 20% Urban 80% Rural. District Information. Name of the district; Rwamagana. Size of population of the district; 291,223. Describe how the district is divided into rural and urban areas:; 10% urban 90% Rural. District Information. Name of the district; Nyagatare. Size of population of the district; 371,310. Describe how the district is divided into rural and urban areas:; 15% Urban 85% Rural. District Information. Name of the district; Gatsibo. Size of population of the district; 398,387. Describe how the district is divided into rural and urban areas:; 10% Urban 90% Rural. District Information. Name of the district; Kayonza. Size of population of the district; 290,055. Describe how the district is divided into rural and urban areas:; 15% Urban 85% Rural. District Information. Name of the district; Kirehe. Size of population of the district; 316,874. Describe how the district is divided into rural and urban areas:; 5% Urban 95% Rural. District Information. Name of the district; Ngoma. Size of population of the district; 315,079. Describe how the district is divided into rural and urban areas:; 20% Urban 80% Rural. District Information. Name of the district; Bugesera. Size of population of the district; 334,275. Describe how the district is divided into rural and urban areas:; 10% Urban 90% Rural.. Please specify what was the multi-dose vaccine used (HPV/TT/others)? What was the vaccination schedule?. Multi-dose vaccines used: - Oral polio vaccine (OPV): At birth OPV0, at 6 weeks after birth OPV1, at 10 weeks OPV 2, at 14 weeks OPV 3 - DPT-HepB-Hib/ PCV13/RotaTeq: at 6 weeks, 1st dose, at 10 weeks 2nd dose, at 14 weeks 3rd dose - TT for pregnant mothers: at 1st contact TT1, after 4 weeks TT2, 6 months later TT3, one year later TT4, another 1 year later TT5 - HPV for adolescent girls (9-14 years old): at 1st contact HPV1, 2 months later HPV2, 4 months later HPV3. Describe the vaccination strategy used (school based, health centre based, mixed)? How was it carried out, who carried it out, who was the lead department/agency? What age/sex was the multi-dose vaccine delivered to? If it was school based, how many schools were targeted? Was it age based or grade based?. The Ministry of health and Ministry of Education agreed on introduction of HPV vaccine using the mixed approach as school based targeting adolescent girls aged 9-14 years and health center based targeting adolescent girls aged 12 years.The following steps were discussed and implemented: - Clear communication between Ministry of Health and Ministry of Education on how adolescent girls will be identified and immunized at schools - Essential Information, instructions and training were provided to key players and students on how immunization session will be conducted and data collected - Key messages on HPV vaccine for parents and community in general to address their concern for this vaccine. What was the number of targeted population? What was the number in target population who started the multi-dose series? What was the number in the target population who received all doses. Targeted population (adolescent girls) for HPV in 2011: 94141 Target who started 1st multi dose series: 91752 Target who completed all doses: 88927. Please provide the source of data for estimation of the target population:. According to the report from the general census of the population and habitat (RGPH) conducted in 2002, the population of Rwanda was estimated to 8,128,553 inhabitants. Taking into account the national population growth rate of 2.6%, the population of Rwanda was estimated to 9,981,415 inhabitants in 2010. Projection for 2011 estimated the same population to be 10.240,932 inhabitants. If applicable, please detail what additional people beside the target population also received the vaccine:. Not applicable (NA).. Table 5.1.1: (Please refer to WHO/UNICEF JRF).. Girl age; HPV 1st dose; HPV 2st dose; HPV 3st dose. 9 years old; 22; 29; 26. 10 year old; 163; 151; 125. 11 year old; 1,941; 1,847; 1,736. 12 year old; 8,527; 7,792; 7,183. 13 year old; 13,542; 13,392; 13,301. 14 year old; 21,186; 20,647; 20,719. 15+ year old; 46,371; 45,846; 45,764. Unknown.. Was there an evaluation of the ‘project’? If so, who performed it? Please provide a short summary of the evaluation methodology and/or provide the evaluation report if available (Document number No: 9). Refer to section 10. Attachments. The evaluation is planned to take place in early October 2012....

5.1.2 MCV Immunisation coverage.. Please provide information concerning routine immunisation coverage related to measle-containing vaccines (MCV).. Table 5.1.2: MCV Immunisation coverage.. Coverage; 2005; 2006; 2007. Administrative1); WHO/UNICEF2); Administrative1); WHO/UNICEF2); Administrative1); WHO/UNICEF2). Measles 1st dose (%); 89; 89; 95; 95; 101; 99. Measles 2st dose (%); 0; 0; 0; 0; 0; 0. Supplementary Immunization Activities (SIA) (%); 107.. Coverage; 2008; 2009; 2010. Administrative1); WHO/UNICEF2); Administrative1); WHO/UNICEF2); Administrative1); WHO/UNICEF2). Measles 1st dose (%); 92; 92; 93; 93; 95; 95. Measles 2st dose (%); 0; 0; 0; 0; 0; 0. Supplementary Immunization Activities (SIA) (%); 101.. Coverage; 2011. Administrative1); WHO/UNICEF2). Measles 1st dose (%); 95; 95. Measles 2st dose (%); 0; 0. Supplementary Immunization Activities (SIA) (%).... Note:. 1)National reported Administrative Coverage. 2)WHO/UNICEF estimated coverage. Was the last Measles Supplementary Immunization Activities (SIA) administrative coverage or results of a survey of acceptable methodology Results of a survey. Please describe survey methodology:. The source of immunization coverage provided for two last year 2010 and 2011, is DHS 2010....

5.2. Baseline and Annual Targets (NVS Routine Support)..

Please refer to cMYP pages to assist in filling-in this section..

Number; Base Year; Baseline and Targets; Baseline and Targets; Baseline and Targets. 2011; 2014; 2015; 2016. Total births; 355,480; 383,935; 393,917; 404,159. Total infants’ deaths; 17,774; 19,197; 19,696; 20,208. Total surviving infants; 337,706; 364,738; 374,221; 383,951. Total pregnant women; 355,480; 383,935; 393,917; 404,159. Target population vaccinated with BCG; 338,552; 365,652; 375,159; 384,913. BCG coverage; 95 %; 95 %; 95 %; 95 %. Target population vaccinated with OPV3. OPV3 coverage; 94 %; 95 %; 95 %; 95 %. Number of infants vaccinated (to be vaccinated) with DTP1; 328,099; 365,652; 375,159; 384,913. Number of infants vaccinated (to be vaccinated) with DTP3; 317,824; 345,449; 354,421; 363,646. DTP3 coverage; 94 %; 95 %; 95 %; 95 %. Wastage[1] rate in base-year and planned thereafter (%) for DTP; 5; 5; 5; 5. Wastage[1] factor in base-year and planned thereafter for DTP; 1.05; 1.05; 1.05; 1.05. Number of girls in the target cohort; 94141; 107289; 110078; 112940. Target population vaccinated with 1st dose of HPV quadrivalent; 91,752; 107,289; 110,078; 112,940. Target population vaccinated with 3rd dose of HPV quadrivalent; 88,927; 104,070; 106,775; 109,552. HPV quadrivalent coverage 1st dose; 94 %; 97 %; 97 %; 97 %. HPV quadrivalent coverage 3st dose; 97 %; 100 %; 100 %; 100 %. First Presentation: HPV quadrivalent, 1 dose(s) per vial, LIQUID. Wastage[1] rate in base-year and planned thereafter (%); 5; 5; 5; 5. Wastage[1] factor in base-year and planned thereafter (%); 1.00; 1.05; 1.05; 1.05. Maximum wastage rate value for HPV quadrivalent, 1 dose(s) per vial, LIQUID; 5 %; 5 %; 5 %; 5 %. Target population vaccinated with 1st dose of Measles; 296,108; 321,023; 329,361; 337,933. Measles coverage; 88 %; 88 %; 88 %; 88 %. Number of infants vaccinated (to be vaccinated) with 1st dose of TT+; 254,898; 275,678; 282,845; 290,199. TT+ coverage; 72 %; 72 %; 72 %; 72 %. Annual DTP Drop out rate [ ( DTP1 – DTP3 ) / DTP1 ] x 100; 3 %; 6 %; 6 %; 6 %.. [1] Number of infants vaccinated out of total births. [2] Number of infants vaccinated out of total surviving infants. [3] Indicate total number of children vaccinated with either DTP alone or combined. [4] Number of pregnant women vaccinated with TT+ out of total pregnant women. [5] The formula to calculate a vaccine wastage rate (in percentage): [ ( A - B ) / A ] x 100. Whereby: A = the number of doses distributed for use according to the supply records with correction for stock balance at the end of the supply period; B = the number of vaccinations with the same vaccine in the same period...

Number; Baseline and Targets. 2017. Total births; 414,667. Total infants’ deaths; 20,733. Total surviving infants; 393,934. Total pregnant women; 414,667. Target population vaccinated with BCG; 394,921. BCG coverage; 95 %. Target population vaccinated with OPV3. OPV3 coverage; 95 %. Number of infants vaccinated (to be vaccinated) with DTP1; 394,921. Number of infants vaccinated (to be vaccinated) with DTP3; 375,526. DTP3 coverage; 95 %. Wastage[1] rate in base-year and planned thereafter (%) for DTP; 5. Wastage[1] factor in base-year and planned thereafter for DTP; 1.05. Number of girls in the target cohort; 117070. Target population vaccinated with 1st dose of HPV quadrivalent; 117,070. Target population vaccinated with 3rd dose of HPV quadrivalent; 113,558. HPV quadrivalent coverage 1st dose; 97 %. HPV quadrivalent coverage 3st dose; 100 %. First Presentation: HPV quadrivalent, 1 dose(s) per vial, LIQUID. Wastage[1] rate in base-year and planned thereafter (%); 5. Wastage[1] factor in base-year and planned thereafter (%); 1.05. Maximum wastage rate value for HPV quadrivalent, 1 dose(s) per vial, LIQUID; 5 %. Target population vaccinated with 1st dose of Measles; 348,973. Measles coverage; 89 %. Number of infants vaccinated (to be vaccinated) with 1st dose of TT+; 297,746. TT+ coverage; 72 %. Annual DTP Drop out rate [ ( DTP1 – DTP3 ) / DTP1 ] x 100; 5 %.. [1] Number of infants vaccinated out of total births. [2] Number of infants vaccinated out of total surviving infants. [3] Indicate total number of children vaccinated with either DTP alone or combined. [4] Number of pregnant women vaccinated with TT+ out of total pregnant women. [5] The formula to calculate a vaccine wastage rate (in percentage): [ ( A - B ) / A ] x 100. Whereby: A = the number of doses distributed for use according to the supply records with correction for stock balance at the end of the supply period; B = the number of vaccinations with the same vaccine in the same period...

5.2.1 HPV specific targets. Single year cohort of girls to be vaccinated with HPV should be within the WHO-recommended target population of 9-13 years old girls. Please specify the source of data that was used to estimate the number of girls in target and reported in the above table under “Target population vaccinated with HPV“. The source of data was obtained from Ministry of Education (2011). Number of adolescent girls (9-14 years old) were counted by class, that is from primary 6. Survey was conducted by community health workers which estimated the proportion of out school girls to be about 1%. For the remaining of the years of the cMYP life cycle, projection was made based on the total population and this will be corrected by the census findings which is ongoing..

| 5.3. Baseline and Annual Targets for Preventive Campaign(s).. |  |
| --- | --- |
| 5.3.1 Baseline and annual targets (MR campaign). Please specify cohort for rubella-containing vaccines (RCV):. RCV Start 9 months. RCV End 14 years. Cohort population = population 9 months - 14 years old. GAVI supports no more than 15 cohorts. If the application is not within 9 months to 15 years, please provide justification. N/A.. Table 5.3.1 Baseline NVS preventive campaign figures for MR.. Number; Base Year; Baseline and Targets. 2011; 2013. Total births; 355,480; 374,205. Total population 9 months - 14 years old; 4,786,278; 5,045,219. Target population vaccinated with MR; 0; 5,045,219. MR (campaign) coverage (%) [1]; 0.00 %; 100.00 %. Wastage rate in base year and thereafter (%) for MR (campaign); 0; 15. Wastage factor in base year and thereafter for MR; 1; 1.18.. [1] Number of persons vaccinated out of total births... |  |

6. New and Under-Used Vaccines (NVS Routine).

6.1. Assessment of burden of relevant diseases (if available).

Disease; Title of the assessment; Date; Results. No assessment was conducted.

If new or under-used vaccines have already been introduced in your country, please give details of the lessons learned from previous introduction(s) specifically for: storage capacity, protection from accidental freezing, staff training, cold chain, logistics, coverage and drop-out rates, wastage rate, etc., and suggest action points to address them..

Lessons Learned; Action Points. Cold chain expansion and management are key area to address when planning for new vaccine introduction; 1. In 2011, EPI with support from its partners conducted EVM and develop an Improvement plan to prepare the introduction of rotavirus vaccine and HPV vaccine and advocate for cold chain expansion; 2. EPI updated the inventory of cold chain equipment based on the revision of cold chain capacity.. Planning for cold chain storage capacity, transportation and vaccine management is very important when planning for new vaccine introduction. This will help to minimize wastage (vaccine damage by heat and freezing); Additional cold chain monitoring devices was procured by the Government and its Partners (USAID). Training and Supportive supervision was intensified by central EPI staff.. Training of health workers is an important area to focus while planning for new vaccine introduction; EPI staff, with technical support from partners, adapted training module for new vaccine introduction, trained the trainers and the health workers using a pooled approach.. Developing specific key messages to address concerns of parents and of health workers is very important for the acceptation of the new vaccine; Key messages were developed, media for transmission of messages identified and used.. Revision of recording , reporting tools and of the immunization policy documents (even of immunization data base) is important; Partners assisted the program with the revision of EPI management tools (recording, reporting and EPI policy documents).

Please list the vaccines to be introduced with support from the GAVI Alliance (and presentation).

1. Human papilloma virus vaccine (HPV), liquid 1 dose per vial 2. Measles -rubella vaccine (MR), lyophilized 10 doses per vial . The GAVI will support initial MR catch-up campaign..

6.1.1 HPV burden specific information. Has the country undertaken an assessment of the burden of cervical cancer? If so, describe the burden, and when and how the assessment was done. If not, countries may report on Globocan data (available on the WHO HPV information Centre website at http://www.who.int/hpvcentre/en).. Yes, some assessment has been conducted in the country. The WHO ranks Rwanda among the country worldwide with highest cervical cancer incident estimated at 49.4/ 1000000. Data from the population based cancer registry in Butare which functioned during the early 1990s showed cervical cancer responsible for 22.5% of cancers among women. In a retrospective study of cancer cases from two University Teaching Hospitals (Centre Hospitalier Universite de Kigali (CHUK) and Centre Hospitalier Universite de Butare (CHUB) seen from 2000 through 2004, cervical cancer accounted for 27.3% of cancers among the women and was the most common malignancy encounted in all age groups. Describe the existing cervical cancer prevention and control activities.. Existing cervical cancer prevention and control activities in Rwanda: - Mass sensitization through community education and advocacy - Prevention of human papilloma virus (HPV) infection through vaccination ( HPV vaccination) - Screening and treatment of pre-cancerous lesion (second prevention) - Treatment of cervical cancer. Has the country developed a roadmap or strategy for establishing or strengthening a national comprehensive approach to cervical cancer prevention and control? Yes. If Yes, please attach and refer to section 10. Attachments. (Document N°10). If No, are there plans for the country to develop such a roadmap or strategy in the future? Please describe- when, who will be leading the development of the plan, and which agencies will be involved.. N/A. 6.1.2 Delivery strategy for HPV vaccine. Please specify the chosen age cohort for HPV vaccination: 12 years old. Please describe the HPV vaccination strategy and plan (when vaccinations will be scheduled, who will do vaccinations, how will the vaccine logistics be assured, coordination between the schools and health personnel, the plan to ensure all three doses are delivered, and plans for reaching girls who may be absent on the day of scheduled vaccinations, etc.). The Government of Rwanda received HPV vaccine from Merck Company as a donation for three years (2011-2013). using school based approach, the vaccine was used to immunize adolescent girls (9-14 years of age) while health center based approach was used for adolescent girls out of school. The HPV vaccine was delivered through campaigns where the first dose was given at the first contact, second dose at two months later and third dose at four months following the second dose. Cold chain and logistics used in the routine immunization system were also used in the HPV vaccine storage and distribution. Strong coordination and collaboration was established between health services and schools ( information, instruction and training). Irrespective of the strategy, provide a description of existing health services and/or health education currently being provided to young adolescents (both girls and/or boys) within the 9-13 year old age group:. a. For health services (this can include: what health services are provided, to which age/sex group, whether it’s mandatory or voluntary, regularly or ad-hoc, in school or out of school, who provides these (government, NGOs), how often, what is the uptake in the community, how is it perceived by the community.). Health and Education Sectors do collaborate to carry out some key health interventions in schools which includes, reproductive health (RH), nutrition, personal hygiene, de-worming and vitamin A supplementation. The interventions do not take gender into account, boys and girls are equally benefited to the intervention. Some of interventions are included in their culliculum. b. For health education (this can include: the topic, whether it is national, sub-national, in school or out of school, who provides the education, how often, is it in the school curriculum, are there NGOs providing these? How is it perceived by the community? Has there been an evaluation and if so, how was it evaluated and what were the findings?). Health education topics includes: - Reproductive health ( sex education) - Nutrition - De worming - Personal hygiene - HIV/AIDS The health education is part of their daily subjects at school, its is national for both in school and out of school. The education package is given by trained teachers in schools while in the community is given by trained community health workers. In schools it is given regularly given that it is a part of curriculum but for the out of school, it depends on how the session is organized with availability of a community health workers. No evaluation was made to assess the perception of the community.. Please describe the communications plan for HPV vaccination strategy (what activities will be done to educate and raise awareness of the vaccination plan to the target population, their parents/guardians, the wider community, community leaders, groups of influence, etc; who will provide this education and what materials will be used; how often will these activities occur vis-a-vis the proposed vaccination schedule.). A communication strategy for HPV vaccine introduction involves ensuring that local authority and community members are equipped with information they need to make informed decision and or give informed advise about cervical cancer prevention including HPV vaccination and screening where appropriate. The strategies are focusing on the following: - Behavior change communication (BCC) - Advocacy messages - Information and communication materials - Community education sessions - Media campaign - Launching ceremony. Please select strategy that the country will choose to deliver the HPV vaccine: Mixed strategy. School-based strategy. Rwanda strategy to deliver HPV vaccine does not include a "School-based strategy".. INTRUCTIONS. Description should include:. Primary/secondary/tertiary, grades in each category, majority age in each grade. Number of schools in the country (public/government schools, private school, or other categorization if possible and relevant for the country). What is the school year (which month to which month). When are the school holidays? (Approximated months, days if possible). When are the major examinations? (Approximated month).. Academic calendar year starts in January and ends in November. School year is divided in three terms (Jan - March, April - July and Sept - November) Between first and second terms, there is a three vacation, between the second and the the third terms, again three weeks vacation. Between tho academic calendar years, there is a ten weeks vacation. Final exam is scheduled in November. Number of primary schools: 2543 (Public: Private: ) Number secondary schools :1362 Number of tertiary schools: 31. Please specify whether girls will be vaccinated by selection of a Specific grade. Table 6.1.2 a.. Number of; Base year; Target year. 2011; 2014. Target population of girls in chosen age; 99,337; 106,182. Girls of chosen age enrolled in schools; 92,699; 99,087...

If girls are to be vaccinated by a specific grade, please specify grade and provide the below data relative to the target grade:. Table 6.1.2 b.. Age of girls in grade; Number of girls in grade / age; % of girls in targeted population. 8 years old; 0; 0. 9 years old; 21; 0. 10 years old; 193; 0. 11 years old; 2,037; 2. 12 years old; 8,669; 9. 13 years old; 13,667; 14. 14 years old; 21,322; 23. 15 years old; 46,034; 50. TOTAL girls 9-13 years old; 24,587; 26. TOTAL girls 14 years old and above; 67,356; 73. TOTAL; 91,943; 100.. Note:. 1) To add new Age of girls in grade, click on the New item icon in the Action line. Use the Delete item icon to delete a specific Age of girls in Grade.. Please provide a source for the enrolment data (e.g., national statistics office, MOE, recent census, school registers, etc.). - Report from Ministry of Health for HPV campaign conducted in 2011 - Rwanda education Statistics 2011. How will the school-based strategy capture those girls not in school? (Will out-of-school girls be invited to join school-attending girls on the days of vaccination? Will separate outreach sessions be scheduled for them? Will existing outreach posts be used? Will out-of-school girls be asked to come to the local health center? Will vaccination nurses do home visits?). All out of school girls are immunized at the health center level. - All out o school girls are registered by the community health workers in their health catchment area - Registers are kept at health centers - Information on vaccination days and sessions are communicated - During the immunization sessions, two vaccination cards are provided, one remain at health center, and second is given to the client - Follow up is made by community health workers to ensure compliance of the following doses. If any, please describe special considerations to be made for marginalised or migrating populations?. The first priority is the eligible girls registered at schools and one registered in the community. However, in case of migration, the EPI program is considering to take care of the eligible group depending on the number.... Health center-based strategy. Please describe the health system and services for the target population at the health centers:(This can include: Number and type of health centers in the country by level (national, sub-national, district), (by public/government, private, or other categorization relevant for the country and if available). What services for 9-13 year old girls are routinely available in these health centers? What are the general operating day/times for service delivery in the health centers? How vaccinations are delivered in the existing health centers? By whom, to what populations, etc.). The health system in Rwanda is divided into three levels: - Referral Hospitals; 4 - District hospitals; 42 - Health centers; 456. How will the health centre-based strategy capture all the girls who are eligible?. - Health centers works closely with community health workers to identify and register all eligible girls - Sensitization of the community to ensure that all eligible girls are aware of a date and a place of immunization site - Monitoring and evaluation to identify the defaulters and take appropriate action. If applicable, please describe special considerations to be made for marginalised or migrating populations?. N/A...

| 6.2. Requested vaccine (HPV quadrivalent, 1 dose(s) per vial, LIQUID) As reported in the cMYP, the country plans to introduce HPV quadrivalent, using HPV quadrivalent, 1 dose(s) per vial, LIQUID.. 6.2.1. Co-financing information. If you would like to co-finance higher amount than minimum, please overwrite information in the Your co-financing row... Country group; Low.. Year 1; Year 2; Year 3. 2014; 2015; 2016. Minimum co-financing; 0.20; 0.20; 0.20. Your co-financing (please change if higher); 0.20; 0.20; 0.20.. Year 1. 2017. Minimum co-financing; 0.20. Your co-financing (please change if higher); 0.20.. 6.2.2. Specifications of vaccinations with new vaccine.. Data from; Year 1; Year 2; Year 3. 2014; 2015; 2016. Number of children to be vaccinated with the first dose; Table 5.2; #; 107,289; 110,078; 112,940. Number of children to be vaccinated with the third dose; Table 5.2; #; 104,070; 106,775; 109,552. Immunisation coverage with the third dose; Table 5.2; #; 97.00 %; 97.00 %; 97.00 %. Country co-financing per dose [1]; Table 6.2.1; $; 0.2; 0.2; 0.2.. [1] Total price per-dose includes vaccine cost, plus insurance, etc... Data from; Year 1. 2017. Number of children to be vaccinated with the first dose; Table 5.2; #; 117,070. Number of children to be vaccinated with the third dose; Table 5.2; #; 113,558. Immunisation coverage with the third dose; Table 5.2; #; 97.00 %. Country co-financing per dose [1]; Table 6.2.1; $; 0.2.. [1] Total price per-dose includes vaccine cost, plus insurance, etc.... |  |
| --- | --- |

6.2.3. Portion of supply to be procured by the country (and cost estimate, US$)... 2014; 2015; 2016. Number of vaccine doses; #; 16,400; 13,500; 13,900. Number of AD syringes; #; 0; 0; 0. Number of re-constitution syringes; #; 0; 0; 0. Total value to be co-financed by country; $; 84,500; 70,000; 72,000.. 2017. Number of vaccine doses; #; 14,400. Number of AD syringes; #; 0. Number of re-constitution syringes; #; 0. Total value to be co-financed by country; $; 74,500... 6.2.4. Portion of supply to be procured by the GAVI Alliance (and cost estimate, US$).. 2014; 2015; 2016. Number of vaccine doses; #; 406,200; 335,500; 344,200. Number of AD syringes; #; 451,100; 369,000; 378,600. Number of re-constitution syringes; #; 0; 0; 0. Total value to be co-financed by country; $; 2,125,000; 1,755,000; 1,800,500.. 2017. Number of vaccine doses; #; 357,700. Number of AD syringes; #; 393,500. Number of re-constitution syringes; #; 0. Total value to be co-financed by country; $; 1,871,000....

6.2.5. New and Under-Used Vaccine Introduction Grant.. Please indicate in the tables below the full costs/needs and how the one-time Introduction Grant [1] will be used to support the costs of vaccine introduction and critical pre-introduction activities (refer to the cMYP). GAVI’s support may not be enough to cover the full needs so please indicate in the table below how much and who will be complementing the funds needed.. Calculation of lump-sum for the HPV quadrivalent, 1 dose(s) per vial, LIQUID.. Year of New Vaccine Introduction; Girls in cohort (From Table 5.2); Share per Girls in cohort in US$; Total in US$. 2014; 107,289; 2.40; 257,494.. [1] The Grant will be based on a maximum award of $2.40 per infant in the birth cohort with a minimum starting grant award of $100,000.. Cost (and finance) to introduce the HPV quadrivalent, 1 dose(s) per vial, LIQUID US$.. Cost Category Full needs for new vaccine introduction in US$; Funded with GAVI introduction grant in US$. Training; 152,920; 152,920. Social Mobilization, IEC and advocacy; 37,080; 37,080. Cold Chain Equipment & Maintenance; 0; 0. Vehicles and Transportation; 9,500; 9,500. Programme Management; 10,000; 10,000. Surveillance and Monitoring; 47,994; 47,994. Human Resources; 0; 0. Waste Management; 0; 0. Technical Assistance; 0; 0. Other (please specify). Total; 257,494; 257,494..... Please describe others sources of funding if available to cover your full needs.. The GAVI will cover the cost 100%....

7. NVS Preventive Campains

7.1. Assessment of burden of relevant diseases related to campaigns (if available).

Disease; Title of the assessment; Date; Results. No assessment conducted.

If MR vaccines have already been introduced in your country during campaigns, please give details of the lessons learned from previous introduction(s) specifically for: storage capacity, protection from accidental freezing, staff training, cold chain, logistics, coverage and drop-out rates, wastage rate, etc., and suggest action points to address them..

Lessons Learned; Action Points. N/A, MR vaccines have not been introduced in the country during the campaign..

7.1.1 Epidemiology and disease burden for Measles-Rubella. Please select at least one of the following information sources to justify RCV diseases burden results:. Epidemiological information on burden of disease:. þ; 1 - Rubella data from the measles case-based surveillance system (including the age distribution of rubella cases). o; 2 - Rubella seroprevalence surveys. o; 3 - Congenital Rubella Syndrome (CRS) burden information, e.g. retrospective search, modelled estimates for CRS burden, prospective surveillance. o; 4 - Other.

7.2.Requested for MR, 10 dose(s) per vial, LYOPHILISED campaign support. 7.2.1. Summary for MR campaign support. Please give a summary of the cMYP and/or the MR, 10 dose(s) per vial, LYOPHILISED campaign introduction plan sections that refer to the introduction of MR, 10 dose(s) per vial, LYOPHILISED campaign. Outline the key points that informed the decision-making process (data considered etc):. In the last 5 years, Rwandan EPI achieved a highmeasles coverage (>80%) in the routine and conducted some high qualitymeasles -SIA (95%). Unfortunately, some measles outbreaks continue to occur insome districts (pockets of low coverage). The measles case-based surveillancesystem, initiated in 2007 has identified high proportion of rubella cases thatsuggested that rubella remains a public health problem in Rwanda. Unfortunatelyno study was conducted to assess congenital rubella syndrome. Based on thesefindings and taking the opportunity presented by the measles and rubellaplatform of two measles doses and of the WHO recommendations, Governmentof Rwanda plans to use the opportunity offered by GAVI and introduce MRvaccine as a second dose of measles vaccine and, at the same time, move forwardto achieve the elimination goal of both measles and rubella. Please summarise (1) the waste management plan and (2) the cold chain capacity and readiness to accommodate new vaccines, stating how the cold chain expansion (if required) will be financed, and when it will be in place.Please indicate if the supplies for the campaign will have any impact in the shipment plans for your routine vaccines and how it will be handled:. Rwandan EPI conducted EVM in 2011 and based onfindings, developed an improvement plan. As the country was getting ready tointroduce both HPV vaccine (2011) and rotavirus vaccine (2012), some partnersand Government procured cold chain equipment to accommodate these new vaccines.With measles second dose and the wide range of MR vaccine campaign, targetingchildren 9 months old to 14 years old, most of districts will needadditional cold chain. In addition, central level will need an additionalpositive cold room. During the strategic ICC meeting planned to take place and endorse theproposal, an advocacy session will be conducted to encourage partners to commitfor new cold chain equipment. All the wastes generated by vaccine, will be collected in safety boxes andincinerated (health centers or at district hospitals... 7.2.2. Grant Support for Operational Costs of the MR Campaign.. Please indicate in the tables below how the support Grant [1] will be used to support the operational costs of the campaign and other critical pre-introduction activities. GAVI's support may not be enough to cover the full needs so please indicate in the table below how much and who will be complementing the funds needed (refer to the cMYP and the MR, 10 dose(s) per vial, LYOPHILISED campaign introduction plan)... Table 7.2.2: calculation of grant to support the operational costs of the campaigns.. Year of MR support; Target population vaccinated (from Table 5.3); Share per population 9 months-14 years old in US$; Total in US$. 2013; 5,045,219; 0.65; 3,279,392.. [1] The Grant will be based on a maximum award of $0.65$ per cohort population.. Cost (and finance) of the MR, 10 dose(s) per vial, LYOPHILISED campaign US$.. Cost Category Full needs for new vaccine introduction in US$; Funded with GAVI introduction grant in US$. 2013; 2013. Training; 306,667; 306,667. Social Mobilization, IEC and advocacy; 230,000; 230,000. Cold Chain Equipment & Maintenance; 937,400; 937,400. Vehicles and Transportation; 20,800; 20,800. Programme Management; 385,294; 385,294. Surveillance and Monitoring; 68,769; 68,769. Human Resources; 624,500; 624,500. Waste Management; 134,933; 134,933. Technical Assistance; 80,500; 80,500. Planning; 66,667; 66,667. Volunteer incentives; 350,250; 350,250. Other (please specify). Internal post campaign evaluation; 70,175; 70,175. Data management and report dissemination; 62,507; 3,437. Total; 3,338,462; 3,279,392..... Please describe others sources of funding if available to cover your full needs.. The government of Rwanda and development partners will cover 20% identified as a gap... 7.2.3 Evidence of introduction of RCV in routine programme.. Please provide evidence that the country can finance the introduction of Rubella-Containing-Vaccine (RCV) into the routine programme through one of the following:.. o; 1 - A commercial contract for purchase of MR/MMR (Meales Rubella/Meales Mumps Rubella) vaccine together with shipping documents, invoice, etc.. o; 2 - Proof that RCV has been integrated into the cMYP with the budget line for vaccines increased to include purchase of RCV as part of the health sector budget to indicate that RCV funds are allocated. o; 3 - A letter from the Minister of Finance or Budget ensuring additional funding for RCV purchase. o; 4 - An MOU between government and donor(s) (or other written document that proves donor commitment) for at least one year for purchase of RCV for use in the routine programme. þ; 5 - Other.. Document N°.. Please briefly describe the document used as evidence:.. Approval signature of this proposal from Ministry of Finance. See attachment... 7.2.4 Introduction planning for RCV.. Countries should describe their plan for introduction including surveillance activities:.. Does Rwanda’s cMYP include a plan for the introduction of RCV into the national programme? Yes.. Please describe a Plan Of Action (POA) for the introduction of RCV into the national programme or provide the POA as an attachment - Refer to section 10. Attachments. (Document N° ).. Refer to the attachment.....

INSTRUCTIONS. Components of the POA/cMYP should include:. a. Comprehensive vaccination strategy for the introduction of RCV including a description of:. i. Initial Measles and rubella (MR) campaign. ii. Replacing Measles containing vaccine (MCV) with Measles and rubella (MR) / Measles, mumps, and rubella (MMR) in the routine childhood vaccination programme. iii. Strategies for targeting Women of Childbearing Age (WCBA), such as vaccination during routine services, post-partum, at 1st well baby visit, SIAs. iv. Linkage to the current routine immunisation schedule. v. Linkage to measles second dose, if applicable. vi. Description of how the country plans to continue to maintain high MR/MMR vaccine coverage either through routine immunisation or through Supplementary Immunization Activities (SIAs). b. A brief description of the following surveillance activities:. i. Integration of Rubella surveillance with case-based measles surveillance. ii. Congenital Rubella Syndrome (CRS) surveillance or plans to establish sentinel site CRS surveillance. iii. Adverse Event Following Immunization (AEFI) surveillance. c. Vaccine coverage monitoring and reporting. d. The communication strategy for the introduction of RCV.. 7.2.5 Measles surveillance indicators.. Please provide information on the following indicators of the quality of measles surveillance for at least two years prior to application (if available):.. Surveillance indicator; 2010; 2011. Reporting rate at national level 1); 5; 3. 100,000; 100,000. Laboratory confirmation rate (%) 2); 11; 7.. Note:. 1) Reporting rate at national level = number of discarded measles cases per 100,000 population per year. 2) Laboratory confirmation rate (%) = number of suspected cases with specimens collected for testing divided by the number of suspected cases not confirmed through epidemiological linkage.....

7.2.6 Rubella Containing Vaccine introduction Grant.. Has a Rubella Containing vaccine already been introduced nationally on a routine basis? No.. Calculation of lump-sum for the MR, 10 dose(s) per vial, LYOPHILISED.. Please indicate in the tables below how the one-time Introduction Grant[1] will be used to support the costs of vaccine introduction and critical pre-introduction activities (refer to the cMYP). GAVI’s support may not be enough to cover the full needs so please indicate in the table below how much and who will be complementing the funds needed... Year of New Vaccine Introduction; Births (From Table 5.3); Share per Birth in US$; Total in US$. 2013; 374,205; 0.80; 299,364.. [1] The Grant will be based on a maximum award of $0.80 per infant in the birth cohort with a minimum starting grant award of $100,000.. Cost (and finance) to introduce the MR, 10 dose(s) per vial, LYOPHILISED US$.. Cost Category Full needs for new vaccine introduction in US$; Funded with GAVI introduction grant in US$. Training; 0; 0. Social Mobilization, IEC and advocacy; 250,000; 50,000. Cold Chain Equipment & Maintenance; 75,000; 22,000. Vehicles and Transportation; 0; 0. Programme Management; 170,000; 90,000. Surveillance and Monitoring; 236,598; 125,000. Human Resources; 0; 0. Waste Management; 80,000; 12,364. Technical Assistance; 20,000. Other (please specify). Total; 831,598; 299,364..........

8. Procurement and Management.

8.1. Procurement and Management of New and Under-Used Vaccines Routine.

Note: The PCV vaccine must be procured through UNICEF to be able to access the price awarded by the Advance Market Commitment (AMC)..

a) Please show how the support will operate and be managed including procurement of vaccines (GAVI expects that most countries will procure vaccine and injection supplies through UNICEF):. As in the past, for vaccines and injection supplies, Government of Rwanda will use UNICEF channels for procurement. For introduction cash grant for all vaccine, management will be done according to GAVI principle through ICC.. b) If an alternative mechanism for procurement and delivery of vaccine supply (financed by the country or the GAVI Alliance) is requested, please document. l; Other vaccines or immunisation commodities procured by the country and descriptions of the mechanism used.. l; The functions of the National Regulatory Authority (as evaluated by WHO) to show they comply with WHO requirements for procurement of vaccines and supply of assured quality.. No alternative mechanism for procurement and delivery of vaccines supply is used in Rwanda. All vaccines and injection supplies are procured through UNICEF channels.. c) Please describe the introduction of the vaccines (refer to cMYP). Introduction of vaccines: 1. Measles second dose (MSD) and measles -rubella vaccine (MR vaccine ) introduction Rwanda ha large experience for new vaccine introduction. In 2002, EPI introduced HepB and Hib vaccines; in 2009, it introduced PCV7 vaccine; in 2011, HPV vaccine was introduced with support from Merck. Recently, May 2012, Rwanda just introduced rotavirus vaccine. With respect to measles vaccine, EPI Rwanda already achieved high coverage of measles vaccine in the routine (> \80%). The program conducted some measles SIAs and also achieved the very high coverage (>95%). In addition, measles case-based surveillance demonstrated high proportion of rubella cases among suspected measles cases in lab. Taking into account the measles/ rubella platform initiative, GoR would like to take the opportunity to introduce MR vaccine as Measles Second Dose and, at the same time, initiate the rubella elimination goal. 2. Human papilloma virus vaccine (HPV vaccine); In 2011, Rwanda signed a MOU with Merck and received HPV vaccine as a donation. While Merck donated HPV vaccine, Rwanda paid for injection supplies and for all operational costs. The donation was for three years (2011-2013) Given that the donation will end in 2013 and GAVI opens this window for this vaccine, Rwanda plans to apply for this vaccine. Rwanda has already very good experience with this vaccine which achieved a coverage of > 95% for the three series. Rwanda conducted EVM and used findings to develop an improved CCL plan. With support from partners, more cold chain equipment have been procurred and distributed to health facilities. Cold chain inventory are on the process of being updated to identify new needs.. d) Please indicate how funds should be transferred by the GAVI Alliance (if applicable). As from the past, Rwanda has a Banking Account for GAVI at Central Bank of Kigali (CBK). GAVI Alliance will, as in the past, transfer fund to this Bnanking Account. Country accepts and agrees the outlined GAVI terms and conditions in the application form.. e) Please indicate how the co-financing amounts will be paid (and who is responsible for this). Amount of fund for low income countries for HPV vaccine co-financing for low income countries (as the case for Rwanda with GNI of $ 570 per capita) which is $0.20 per dose has been fixed. Ministry of Health will instruct the Ministry of Finance to transfer fund to UNICEF Copenhagen based on the GAVI estimates (secured resource of funding from the Government).. f) Please outline how coverage of the new vaccine will be monitored and reported (refer to cMYP). a) Administratively, coverage will be monitored through monthly reports at the health centers to the national level and quarterly though review meetings. b) annually reports coverage will be reported to GAVI through annual progress reports (APR) using MOH/WHO/UNICEF joint reporting form..

8.2. Procurement and Management for NVS Preventive Campaign(s).

8.2.1. Procurement and Management for MR, 10 dose(s) per vial, LYOPHILISED campaign. a) Please show how the support will operate and be managed including procurement of vaccines (GAVI expects that countries will procure vaccine and injection supplies through UNICEF):. As for other vaccines, GAVI will transfer funds to UNICEF Copenhagen for vaccines and injection supplies procurement. UNICEF will procure vaccines and injection materials and deliver to country.. b) Please indicate when you are planning to conduct the campaign (month and year) and how the campaign is going to be rolled out (e.g. in different phases or one time).. One time nationwide MR vaccination campaign will be conducted in ...... 2013. The preparation phase will start in ... 2013.. c) Please outline how coverage of the new vaccine will be monitored and reported (refer to the cMYP and/or the MR, 10 dose(s) per vial, LYOPHILISED campaign introduction plan). Administrative coverage data will be collected and reported during and immediately after the campaign. After the campaign, the country plans to conduct independance monitors will assess the quality of the campaign and confirm the administrative coverage data reported. Two weeks after the campaign, EPI plans to hold an evaluation meeting and develop a report that will be shared with more partners..

8.3. Vaccine Management (EVSM/EVM/VMA).

Did the country have Effective Vaccine Management Assessment (VMA) in the past? Yes. When was the last VMA conducted? July 2011. Did the country have Effective Vaccine Store Management (EVSM) in the past? No. Did the country have Effective Vaccine Management (EVM) in the past? Yes. When was the EVM conducted? July 2011. If your country conducted either EVSM or VMA in the past two years, please attach relevant reports. (Document N°13). A VMA report must be attached from those countries which have introduced a New and Underused Vaccine with GAVI support before 2008.. Please note that Effective Vaccine Store Management (EVSM) and Vaccine Management Assessment(VMA) tools have been replaced by an integrated Effective Vaccine Management (EVM) tool. The information on EVM tool can be found at http://www.who.int/immunization_delivery/systems_policy/logistics/en/index6.html. For countries which conducted EVSM, VMA or EVM in the past, please report on activities carried out as part of either action plan or improvement plan prepared after the EVSM/VMA/EVM.. The EVM was conducted in July 2011 and identified the following area of improvement (temperature monitoring, cold and dry storage, transport capacity, cold chain building, stock management, distribution and vaccine management) - The multilog devices has been procured awaiting to be installed - Non function fridge tag replacement was initiated - Additional shelves in the cold rooms is in the tendering process - The UNICEF proposed to procure three cold units - A functional computerized stock management system has been put in place, training on SMT done and put in used at central level. - Vaccine package for transportation is now done according to WHO guidelines with proper ice pack conditioned during transportation. Does the country plan to conduct an Effective Vaccine Management (EVM) Assessment in the future? Yes. When is the next Effective Vaccine Management (EVM) Assessment planned? July 2014. Under new guidelines, it will be mandatory for the countries to conduct an EVM prior to an application for introduction of new vaccine..

9. Additional Comments and Recommendations from the National Coordinating Body (ICC/HSCC).

Comments and Recommendations from the National Coordinating Body (ICC/HSCC).

10. Attachments.

10.1. List of documents attached to this proposal.

Document Number; Document; Section; Mandatory; File. MoH and MoF signatures.pdf. 1; MoH Signature (or delegated authority) of Proposal; File desc:. Date/time: 8/31/2012 5:31:33 AM. Size: 1061903. MoH and MoF signatures.pdf. 2; MoF Signature (or delegated authority) of Proposal; File desc:. Date/time: 8/31/2012 5:35:15 AM. Size: 1061903. ICC members signatures.pdf. 3; Signatures of ICC or HSCC or equivalent in Proposal; File desc:. Date/time: 8/31/2012 5:39:54 AM. Size: 1439963. icc meeting report endorsing the proposal.pdf. 4; Minutes of ICC/HSCC meeting endorsing Proposal; File desc:. Date/time: 8/31/2012 5:47:58 AM. Size: 2826403. Revised_cMYP_08.12.doc. 5; comprehensive Multi Year Plan - cMYP; File desc:. Date/time: 8/31/2012 8:32:33 AM. Size: 13522432. cMYP_Costing_Tool_RWA_En-1.xls. 6; cMYP Costing tool for financial analysis; File desc:. Date/time: 8/31/2012 6:01:14 AM. Size: 3540480. cMYP_Costing_Tool_RWA_En-1.xls. 7; Plan for NVS introduction (if not part of cMYP); 5.1; File desc:. Date/time: 8/31/2012 6:31:53 AM. Size: 3540480. EVM improvement implementation plan.doc. 8; Improvement plan based on EVM; File desc:. Date/time: 8/31/2012 8:44:26 AM. Size: 72192. HPV_intro_plan.doc. 10; HPV roadmap or strategy; 6.1.1; File desc:. Date/time: 8/31/2012 8:35:18 AM. Size: 347136. Rubella_plan_intro_RW_08.12..doc. 12; Plan Of Action for RCV introduction; 7.c.4; File desc:. Date/time: 8/31/2012 8:36:19 AM. Size: 412160.

11. Annexes... Annex 1 - NVS Routine Support

Annex 1.1 - NVS Routine Support (HPV quadrivalent, 1 dose(s) per vial, LIQUID). Table Annex 1.1 A: Rounded up portion of supply that is procured by the country and estimate of relative costs in US$.. 2014; 2015; 2016. Number of vaccine doses; #; 16,400; 13,500; 13,900. Number of AD syringes; #; 0; 0; 0. Number of re-constitution syringes; #; 0; 0; 0. Total value to be co-financed by country; $; 84,500; 70,000; 72,000.. 2017. Number of vaccine doses; #; 14,400. Number of AD syringes; #; 0. Number of re-constitution syringes; #; 0. Total value to be co-financed by country; $; 74,500... Table Annex 1.1 B: Rounded up portion of supply that is procured by GAVI and estimate of relative costs in US$.. 2014; 2015; 2016. Number of vaccine doses; #; 406,200; 335,500; 344,200. Number of AD syringes; #; 451,100; 369,000; 378,600. Number of re-constitution syringes; #; 0; 0; 0. Total value to be co-financed by country; $; 2,125,000; 1,755,000; 1,800,500.. 2017. Number of vaccine doses; #; 357,700. Number of AD syringes; #; 393,500. Number of re-constitution syringes; #; 0. Total value to be co-financed by country; $; 1,871,000....

Table Annex 1.1 C: Summary table for vaccine HPV quadrivalent, 1 dose(s) per vial, LIQUID. ID Data from; 2014; 2015; 2016. Number of surviving infants; Table 5.2; #; 364,738; 374,221; 383,951. Number of children to be vaccinated with the first dose; Table 5.2; #; 107,289; 110,078; 112,940. Number of children to be vaccinated with the third dose; Table 5.2; #; 104,070; 106,775; 109,552. Immunisation coverage with the third dose; Table 5.2; %; 97.00 %; 97.00 %; 97.00 %. Number of doses per child; Parameter; #; 3; 3; 3. Estimated vaccine wastage factor; Table 5.2; #; 1.05; 1.05; 1.05. Number of doses per vial; Parameter; #; 1; 1; 1. AD syringes required; Parameter; #; Yes; Yes; Yes. Reconstitution syringes required; Parameter; #; No; No; No. Safety boxes required; Parameter; #; No; No; No. g; Vaccine price per dose; Table Annexes 4A; $; 5; 5; 5. cc; Country co-financing per dose; Table 6.4.1; $; 0.2; 0.2; 0.2. ca; AD syringe price per unit; Table Annexes 4A; $; 0.0465; 0.0465; 0.0465. cr; Reconstitution syringe price per unit; Table Annexes 4A; $; 0; 0; 0. cs; Safety box price per unit; Table Annexes 4A; $; 0.0058; 0.0058; 0.0058. fv; Freight cost as % of vaccines value; Table Annexes 4B; %; 4.00 %; 4.00 %; 4.00 %. fd; Freight cost as % of devices value; Parameter; %; 10.00 %; 10.00 %; 10.00 %.. ID; Data from; 2017. Number of surviving infants; Table 5.2; #; 393,934. Number of children to be vaccinated with the first dose; Table 5.2; #; 117,070. Number of children to be vaccinated with the third dose; Table 5.2; #; 113,558. Immunisation coverage with the third dose; Table 5.2; %; 97.00 %. Number of doses per child; Parameter; #; 3. Estimated vaccine wastage factor; Table 5.2; #; 1.05. Number of doses per vial; Parameter; #; 1. AD syringes required; Parameter; #; Yes. Reconstitution syringes required; Parameter; #; No. Safety boxes required; Parameter; #; No. g; Vaccine price per dose; Table Annexes 4A; $; 5. cc; Country co-financing per dose; Table 6.4.1; $; 0.2. ca; AD syringe price per unit; Table Annexes 4A; $; 0.0465. cr; Reconstitution syringe price per unit; Table Annexes 4A; $; 0. cs; Safety box price per unit; Table Annexes 4A; $; 0.0058. fv; Freight cost as % of vaccines value; Table Annexes 4B; %; 4.00 %. fd; Freight cost as % of devices value; Parameter; %; 10.00 %....

Table Annex 1.1 D: Estimated numbers for HPV quadrivalent, 1 dose(s) per vial, LIQUID, associated injection safety material and related co-financing budget (page 1) Formula; 2014. Total; Government; GAVI. A; Country co-finance; 3.86 %. B; Number of children to be vaccinated with the first dose; Table 1; 107,289; 4,147; 103,142. C; Number of doses per child; Vaccine parameter (schedule); 3.00. D; Number of doses needed; B x C; 321,867; 12,440; 309,427. E; Estimated vaccine wastage factor; Wastage factor table; 1.05. F; Number of doses needed including wastage; D x E; 337,961; 13,062; 324,899. G; Vaccines buffer stock; (F – F of previous year) * 0.25; 84,491; 3,266; 81,225. I; Total vaccine doses needed; F + G; 422,452; 16,327; 406,125. J; Number of doses per vial; Vaccine parameter; 1.00. K; Number of AD syringes (+ 10% wastage) needed; (D + G) x 1.11; 451,058; 0; 451,058. L; Reconstitution syringes (+ 10% wastage) needed; I / J * 1.11; 0; 0; 0. N; Cost of vaccines needed; I x g; 2,112,260; 81,634; 2,030,626. O; Cost of AD syringes needed; K x ca; 20,975; 0; 20,975. P; Cost of reconstitution syringes needed; L x cr; 0; 0; 0. Q; Cost of safety boxes needed; M x cs; 0.00; 0; 0. R; Freight cost for vaccines needed; N x fv; 73,930; 2,858; 71,072. S; Freight cost for devices needed; (O+P+Q) x fd; 2,098; 0; 2,098. T; Total fund needed; (N+O+P+Q+R+S); 2,209,263; 84,491; 2,124,772. U; Total country co-financing; I 3 cc; 84,491. V; Country co-financing % of GAVI supported proportion; U / T; 3.86 %... Table Annex 1.1 D: Estimated numbers for HPV quadrivalent, 1 dose(s) per vial, LIQUID, associated injection safety material and related co-financing budget (page 2). Formula; 2015. Total; Government; GAVI. A; Country co-finance; 3.86 %. B; Number of children to be vaccinated with the first dose; Table 1; 110,078; 4,255; 105,823. C; Number of doses per child; Vaccine parameter (schedule); 3.00. D; Number of doses needed; B x C; 330,234; 12,763; 317,471. E; Estimated vaccine wastage factor; Wastage factor table; 1.05. F; Number of doses needed including wastage; D x E; 346,746; 13,401; 333,345. G; Vaccines buffer stock; (F – F of previous year) * 0.25; 2,197; 85; 2,112. I; Total vaccine doses needed; F + G; 348,943; 13,486; 335,457. J; Number of doses per vial; Vaccine parameter; 1.00. K; Number of AD syringes (+ 10% wastage) needed; (D + G) x 1.11; 368,999; 0; 368,999. L; Reconstitution syringes (+ 10% wastage) needed; I / J * 1.11; 0; 0; 0. N; Cost of vaccines needed; I x g; 1,744,715; 67,429; 1,677,286. O; Cost of AD syringes needed; K x ca; 17,159; 0; 17,159. P; Cost of reconstitution syringes needed; L x cr; 0; 0; 0. Q; Cost of safety boxes needed; M x cs; 0.00; 0; 0. R; Freight cost for vaccines needed; N x fv; 61,066; 2,361; 58,705. S; Freight cost for devices needed; (O+P+Q) x fd; 1,716; 0; 1,716. T; Total fund needed; (N+O+P+Q+R+S); 1,824,656; 69,789; 1,754,867. U; Total country co-financing; I 3 cc; 69,789. V; Country co-financing % of GAVI supported proportion; U / T; 3.86 %... Table Annex 1.1 D: Estimated numbers for HPV quadrivalent, 1 dose(s) per vial, LIQUID, associated injection safety material and related co-financing budget (page 3). Formula; 2016. Total; Government; GAVI. A; Country co-finance; 3.86 %. B; Number of children to be vaccinated with the first dose; Table 1; 112,940; 4,365; 108,575. C; Number of doses per child; Vaccine parameter (schedule); 3.00. D; Number of doses needed; B x C; 338,820; 13,095; 325,725. E; Estimated vaccine wastage factor; Wastage factor table; 1.05. F; Number of doses needed including wastage; D x E; 355,761; 13,750; 342,011. G; Vaccines buffer stock; (F – F of previous year) * 0.25; 2,254; 88; 2,166. I; Total vaccine doses needed; F + G; 358,015; 13,837; 344,178. J; Number of doses per vial; Vaccine parameter; 1.00. K; Number of AD syringes (+ 10% wastage) needed; (D + G) x 1.11; 378,593; 0; 378,593. L; Reconstitution syringes (+ 10% wastage) needed; I / J * 1.11; 0; 0; 0. N; Cost of vaccines needed; I x g; 1,790,075; 69,182; 1,720,893. O; Cost of AD syringes needed; K x ca; 17,605; 0; 17,605. P; Cost of reconstitution syringes needed; L x cr; 0; 0; 0. Q; Cost of safety boxes needed; M x cs; 0.00; 0; 0. R; Freight cost for vaccines needed; N x fv; 62,653; 2,422; 60,231. S; Freight cost for devices needed; (O+P+Q) x fd; 1,761; 0; 1,761. T; Total fund needed; (N+O+P+Q+R+S); 1,872,094; 71,603; 1,800,491. U; Total country co-financing; I 3 cc; 71,603. V; Country co-financing % of GAVI supported proportion; U / T; 3.86 %... Table Annex 1.1 D: Estimated numbers for HPV quadrivalent, 1 dose(s) per vial, LIQUID, associated injection safety material and related co-financing budget (page 4). Formula; 2017. Total; Government; GAVI. A; Country co-finance; 3.86 %. B; Number of children to be vaccinated with the first dose; Table 1; 117,070; 4,525; 112,545. C; Number of doses per child; Vaccine parameter (schedule); 3.00. D; Number of doses needed; B x C; 351,210; 13,574; 337,636. E; Estimated vaccine wastage factor; Wastage factor table; 1.05. F; Number of doses needed including wastage; D x E; 368,771; 14,253; 354,518. G; Vaccines buffer stock; (F – F of previous year) * 0.25; 3,253; 126; 3,127. I; Total vaccine doses needed; F + G; 372,024; 14,378; 357,646. J; Number of doses per vial; Vaccine parameter; 1.00. K; Number of AD syringes (+ 10% wastage) needed; (D + G) x 1.11; 393,454; 0; 393,454. L; Reconstitution syringes (+ 10% wastage) needed; I / J * 1.11; 0; 0; 0. N; Cost of vaccines needed; I x g; 1,860,120; 71,889; 1,788,231. O; Cost of AD syringes needed; K x ca; 18,296; 0; 18,296. P; Cost of reconstitution syringes needed; L x cr; 0; 0; 0. Q; Cost of safety boxes needed; M x cs; 0.00; 0; 0. R; Freight cost for vaccines needed; N x fv; 65,105; 2,517; 62,588. S; Freight cost for devices needed; (O+P+Q) x fd; 1,830; 0; 1,830. T; Total fund needed; (N+O+P+Q+R+S); 1,945,351; 74,405; 1,870,946. U; Total country co-financing; I 3 cc; 74,405. V; Country co-financing % of GAVI supported proportion; U / T; 3.86 %......

Annex 2 - NVS Routine – Preferred Second Presentation.

No NVS Routine – Preferred Second Presentation requested this year.

Annex 3 - NVS Preventive campaign(s)... Annex 3.1 - NVS Preventive campaign(s) (MR, 10 dose(s) per vial, LYOPHILISED). Table Annex 3.1 C: Summary table for CAMPAIGN MR, 10 dose(s) per vial, LYOPHILISED.. Data from; 2013. Total campaign population; Table 5.3.1; #; 5,045,219. Immunization coverage; Table 5.3.1; %; 100.00 %. Number of persons to be vaccinated; Table 5.3.1; #; 5,045,219. Number of doses per persons; Parameter; #; 1. Estimated vaccine wastage factor; Table 5.3.1; #; 1.18. Number of doses per vial; Parameter; #; 10. AD syringes required; Parameter; #; Yes. Reconstitution syringes required; Parameter; #; Yes. Safety boxes required; Parameter; #; Yes. Vaccine price per dose; Table Annexes 4A; $; 0.494. AD syringe price per unit; Table Annexes 4A; $; 0.0465. Reconstitution syringe price per unit; Table Annexes 4A; $; 0.0037. Safety box price per unit; Table Annexes 4A; $; 0.0058. Freight cost as % of vaccines value; Table Annexes 4B; %; 13.00 %. Freight cost as % of devices value; Parameter; %; 0...

Table Annex 3.1 D: Estimated number of MR, 10 dose(s) per vial, LYOPHILISED associated injection safety material and related co-financing budget (page 1). Formula; GAVI. 2013. B; Number of persons to be vaccinated with the first dose; 5,045,219. C; Number of doses per persons; 1. D; Number of doses needed; B x C; 5,045,219. E; Estimated vaccine wastage factor; Wastage factor table; 1.18. F; Number of doses needed including wastage; D x E; 5,953,359. G; Vaccines buffer stock; (F – F of previous year) * 0.25; 1,488,340. I; Total vaccine doses needed; F + G; 7,441,699. J; Number of doses per vial; Vaccine parameter; 10. K; Number of AD syringes (+ 10% wastage) needed; (D + G) x 1.11; 7,252,251. L; Reconstitution syringes (+ 10% wastage) needed; I / J * 1.11; 826,029. M; Total of safety boxes (+ 10% of extra need) needed; (K + L) /100 * 1.11; 89,669. N; Cost of vaccines needed; I x g; 0.494. O; Cost of AD syringes needed; K x ca; 337,229.6715. P; Cost of reconstitution syringes needed; L x cr; 3,057. Q; Cost of safety boxes needed; M x cs; 521. R; Freight cost for vaccines needed; N x fv; 0. S; Freight cost for devices needed; (O+P+Q) x fd; 0. T; Total fund needed; (N+O+P+Q+R+S); 4,017,007.6715... Note: There is no cofinancing for NVS preventive campaigns...

| Annex 4. |  |  |  |
| --- | --- | --- | --- |
| Table Annex 4A: Commodities Cost. |  |  |  |
| Vaccine; Presentation; 2013; 2014; 2015; 2016. DTP-HepB, 10 dose(s) per vial, LIQUID; 10. DTP-HepB-Hib, 1 dose(s) per vial, LIQUID; 1; 2.017; 1.986; 1.933; 1.927. DTP-HepB-Hib, 10 dose(s) per vial, LIQUID; 10; 2.017; 1.986; 1.933; 1.927. DTP-HepB-Hib, 2 dose(s) per vial, LYOPHILISED; 2; 2.017; 1.986; 1.933; 1.927. HPV bivalent, 2 dose(s) per vial, LIQUID; 2; 5.000; 5.000; 5.000; 5.000. HPV quadrivalent, 1 dose(s) per vial, LIQUID; 1; 5.000; 5.000; 5.000; 5.000. Measles, 10 dose(s) per vial, LYOPHILISED; 10; 0.242; 0.242; 0.242; 0.242. Meningogoccal, 10 dose(s) per vial, LIQUID; 10; 0.520; 0.520; 0.520; 0.520. MR, 10 dose(s) per vial, LYOPHILISED; 10; 0.494; 0.494; 0.494; 0.494. Pneumococcal (PCV10), 2 dose(s) per vial, LIQUID; 2; 3.500; 3.500; 3.500; 3.500. Pneumococcal (PCV13), 1 dose(s) per vial, LIQUID; 1; 3.500; 3.500; 3.500; 3.500. Rotavirus, 2-dose schedule; 1; 2.550; 2.550; 2.550; 2.550. Rotavirus, 3-dose schedule; 1; 3.500; 3.500; 3.500; 3.500. Yellow Fever, 10 dose(s) per vial, LYOPHILISED; 10; 0.900; 0.900; 0.900; 0.900. Yellow Fever, 5 dose(s) per vial, LYOPHILISED; 5; 0.900; 0.900; 0.900; 0.900. |  |  |  |
| Note for HPV and MR: These prices are indicative only as GAVI has not procured HPV and MR vaccines for GAVI countries yet. Prices will be finalised through tender processes in Q3. GAVI will only fund HPV vaccines if an acceptable price reduction is secured from the current price indicated. The MR price is based on the current price to UNICEF. |  |  |  |
| Supply; Form; 2013; 2014; 2015; 2016. AD-SYRINGE; SYRINGE; 0.047; 0.047; 0.047; 0.047. RECONSTIT-SYRINGE-PENTAVAL; SYRINGE; 0.047; 0.047; 0.047; 0.047. RECONSTIT-SYRINGE-YF; SYRINGE; 0.004; 0.004; 0.004; 0.004. SAFETY-BOX; SAFETYBOX; 0.006; 0.006; 0.006; 0.006. |  |  |  |
| Note: WAP - weighted average price (to be used for any presentation: For DTP-HepB-Hib, it applies to 1 dose liquid, 2 dose lyophilised and 10 dose liquid. For Yellow Fever, it applies to 5 dose lyophilised and 10 dose lyophilised). |  |  |  |
| Table Annex 4B: Freight cost as percentage of value. |  |  |  |
| Vaccine Antigen; Vaccine Type; No Threshold; 500,000$. <=; >. DTP-HepB; HEPBHIB; 2.00 %. DTP-HepB-Hib; HEPBHIB; 23.80 %; 6.00 %. HPV bivalent; HPV; 3.50 %. HPV quadrivalent; HPV; 3.50 %. Measles; MEASLES; 14.00 %. Meningogoccal; MENINACONJUGATE; 10.20 %. MR; MR; 13.20 %. Pneumococcal (PCV10); PNEUMO; 3.00 %. Pneumococcal (PCV13); PNEUMO; 6.00 %. Rotavirus; ROTA; 5.00 %. Yellow Fever; YF; 7.80 %. |  |  |  |
| Table Annex 4C: Low - Minimum country's co-payment per dose of co-financed vaccine.. |  |  |  |
| Vaccine; 2014; 2015; 2016. HPV quadrivalent, 1 dose(s) per vial, LIQUID; 0.2; 0.2; 0.2. |  |  |  |
| Vaccine; 2017. HPV quadrivalent, 1 dose(s) per vial, LIQUID; 0.2. |  |  |  |
| Table Annex 4D: Wastage rates and factors. |  |  |  |
| Countries are expected to plan for a maximal wastage rate of:. |  |  |  |
| • 50% - for a lyophilised vaccine in 10 or 20-dose vial,. |  |  |  |
| • 25% - for a liquid vaccine in 10 or 20-dose vial or a lyophilised vaccine in 5-dose vial,. |  |  |  |
| • 10% - for a lyophilised/liquid vaccine in 2-dose vial, and. |  |  |  |
| • 5% - for a liquid vaccine in 1-dose vial. |  |  |  |
| Vaccine wastage rate; 5%; 10%; 15%; 20%; 25%; 30%; 35%; 40%; 45%; 50%; 55%; 60%. Equivalent wastage factor; 1.05; 1.11; 1.18; 1.25; 1.33; 1.43; 1.54; 1.67; 1.82; 2; 2.22; 2.5. |  |  |  |
| Vaccine; Vaccine wastage rate; VaccineWastageFactor. MR, 10 dose(s) per vial, LYOPHILISED; 0%; 1. |  |  |  |
| Table Annex 4E: Vaccine maximum packed volumes. |  |  |  |
| Vaccine product; Designation; Vaccine formulation; Admin route; No. Of doses in the schedule; Presentation (doses/vial, prefilled); Packed volume vaccine (cm3/dose); Packed volume diluents (cm3/dose). BCG; BCG; lyophilized; ID; 1; 20; 1.2; 0.7. Diphtheria-Tetanus-Pertussis; DTP; liquid; IM; 3; 20; 2.5. Diphtheria-Tetanus-Pertussis; DTP; liquid; IM; 3; 10; 3. Diphtheria-Tetanus; DT; liquid; IM; 3; 10; 3. Tetanus-Diphtheria; Td; liquid; IM; 2; 10; 3. Tetanus Toxoid; TT; liquid; IM; 2; 10; 3. Tetanus Toxoid; TT; liquid; IM; 2; 20; 2.5. Tetanus Toxoid UniJect; TT; liquid; IM; 2; Uniject; 12. Measles; Measles; lyophilized; SC; 1; 1; 26.1; 20. Measles; Measles; lyophilized; SC; 1; 2; 13.1; 13.1. Measles; Measles; lyophilized; SC; 1; 5; 5.2; 7. Measles; Measles; lyophilized; SC; 1; 10; 3.5; 4. Measles-Rubella freeze dried; MR; lyophilized; SC; 1; 1; 26.1; 26.1. Measles-Rubella freeze dried; MR; lyophilized; SC; 1; 2; 13.1; 13.1. Measles-Rubella freeze dried; MR; lyophilized; SC; 1; 5; 5.2; 7. Measles-Rubella freeze dried; MR; lyophilized; SC; 1; 10; 2.5; 4. Measles-Mumps-Rubella freeze dried; MMR; lyophilized; SC; 1; 1; 26.1; 26.1. Measles-Mumps-Rubella freeze dried; MMR; lyophilized; SC; 1; 2; 13.1; 13.1. Measles-Mumps-Rubella freeze dried; MMR; lyophilized; SC; 1; 5; 5.2; 7. Measles-Mumps-Rubella freeze dried; MMR; lyophilized; SC; 1; 10; 3; 4. Polio; OPV; liquid; Oral; 4; 10; 2. Polio; OPV; liquid; Oral; 4; 20; 1. Yellow fever; YF; lyophilized; SC; 1; 5; 6.5; 7. Yellow fever; YF; lyophilized; SC; 1; 10; 2.5; 3. Yellow fever; YF; lyophilized; SC; 1; 20; 1.5; 2. Yellow fever; YF; lyophilized; SC; 1; 50; 0.7; 1. DTP-HepB combined; DTP-HepB; liquid; IM; 3; 1; 9.7. DTP-HepB combined; DTP-HepB; liquid; IM; 3; 2; 6. DTP-HepB combined; DTP-HepB; liquid; IM; 3; 10; 3. Hepatitis B; HepB; liquid; IM; 3; 1; 18. Hepatitis B; HepB; liquid; IM; 3; 2; 13. Hepatitis B; HepB; liquid; IM; 3; 6; 4.5. Hepatitis B; HepB; liquid; IM; 3; 10; 4. Hepatitis B UniJect; HepB; liquid; IM; 3; Uniject; 12. Hib liquid; Hib_liq; liquid; IM; 3; 1; 15. Hib liquid; Hib_liq; liquid; IM; 3; 10; 2.5. Hib freeze-dried; Hib_lyo; lyophilized; IM; 3; 1; 13; 35. Hib freeze-dried; Hib_lyo; lyophilized; IM; 3; 2; 6. Hib freeze-dried; Hib_lyo; lyophilized; IM; 3; 10; 2.5; 3. DTP liquid + Hib freeze-dried; DTP+Hib; liquid+lyop.; IM; 3; 1; 45. DTP-Hib combined liquid; DTP+Hib; liquid+lyop.; IM; 3; 10; 12. DTP-Hib combined liquid; DTP-Hib; liquid; IM; 3; 1; 32.3. DTP-HepB liquid + Hib freeze-dried; DTP-Hib; liquid; IM; 3; 10; 2.5. DTP-HepB liquid + Hib freeze-dried; DTP-HepB+Hib; liquid+lyop.; IM; 3; 1; 22. DTP-HepB-Hib liquid; DTP-HepB+Hib; liquid+lyop.; IM; 3; 2; 11. DTP-HepB-Hib liquid; DTP-HepB-Hib; liquid; IM; 3; 10; 4.4. DTP-HepB-Hib liquid; DTP-HepB-Hib; liquid; IM; 3; 2; 13.1. DTP-HepB-Hib liquid; DTP-HepB-Hib; liquid; IM; 3; 1; 19.2. Meningitis A/C; MV_A/C; lyophilized; SC; 1; 10; 2.5; 4. Meningitis A/C; MV_A/C; lyophilized; SC; 1; 50; 1.5; 3. Meningococcal A/C/W/; MV_A/C/W; lyophilized; SC; 1; 50; 1.5; 3. Meningococcal A/C/W/Y; MV_A/C/W/Y; lyophilized; SC; 1; 10; 2.5; 4. Meningitis W135; MV_W135; lyophilized; SC; 1; 10; 2.5; 4. Meningitis A conjugate; Men_A; lyophilized; SC; 2; 10; 2.6; 4. Japanese Encephalitis; JE_lyo; lyophilized; SC; 3; 10; 15. Japanese Encephalitis; JE_lyo; lyophilized; SC; 3; 10; 8.1; 8.1. Japanese Encephalitis; JE_lyo; lyophilized; SC; 3; 5; 2.5; 2.9. Japanese Encephalitis; JE_lyo; lyophilized; SC; 3; 1; 12.6; 11.5. Japanese Encephalitis; JE_liq; liquid; SC; 3; 10; 3.4. Rota vaccine; Rota_lyo; lyophilized; Oral; 2; 1; 156. Rota vaccine; Rota_liq; liquid; Oral; 2; 1; 17.1. Rota vaccine; Rota_liq; liquid; Oral; 3; 1; 45.9. Pneumo. conjugate vaccine 7-valent; PCV-7; liquid; IM; 3; PFS; 55.9. Pneumo. conjugate vaccine 7-valent; PCV-7; liquid; IM; 3; 1; 21. Pneumo. conjugate vaccine 10-valent; PCV-10; liquid; IM; 3; 1; 11.5. Pneumo. conjugate vaccine 10-valent; PCV-10; liquid; IM; 3; 2; 4.8. Pneumo. conjugate vaccine 13-valent; PCV-13; liquid; IM; 3; 1; 12. Polio inactivated; IPV; liquid; IM; 3; PFS; 107.4. Polio inactivated; IPV; liquid; IM; 3; 10; 2.5. Polio inactivated; IPV; liquid; IM; 3; 1; 15.7. Human Papilomavirus vaccine; HPV; liquid; IM; 3; 1; 15. Human Papilomavirus vaccine; HPV; liquid; IM; 3; 2; 5.7. Monovalent OPV-1; mOPV1; liquid; Oral; 20; 1.5. Monovalent OPV-3; mOPV3; liquid; Oral; 20; 1.5. |  |  |  |

| 12. Banking Form |  |
| --- | --- |
| In accordance with the decision on financial support made by the GAVI Alliance, the Government of Rwanda hereby requests that a payment be made via electronic bank transfer as detailed below:. Name of Institution (Account Holder):; Ministry of Health, Rwanda. Address:; PO Box 84. City Country:; Kigali, Rwanda. Telephone no.:; +250 785152534; Fax no.:. Currency of the bank account:; USD. For credit to:. Bank account's title:; MINISANTE GLOBAL ALLIANCE FOR VACCINE AND IMMUNIZATION. Bank account no.:; 3201097. Bank's name:; National Bank of Rwanda. |  |
| Is the bank account exclusively to be used by this program? True. |  |
| By who is the account audited? General Auditor's Office. |  |
| Signature of Government's authorizing official. |  |
| Seal. Name:; Dr Uzziel NDAGIJIMANA. Title:; Permanent Secretary, Ministry of Health. Signature:. Date:. |  |
| FINANCIAL INSTITUTION. Bank Name:; NATIONAL BANK OF RWANDA. Branch Name:; HEAD OFFICE. Address:; BNR, AVENUE PAUL VI, 250, KIGALI. City Country:; KIGALI. Swift Code:; BNRWRWR. Sort Code:. ABA No.:. Telephone No.:. FAX No.:. | CORRESPONDENT BANK. (In the United States). |
| I certify that the account No 3201097 is held by MINISANTE at this banking institution. The account is to be signed jointly by at least 2 (number of signatories) of the following authorized signatories:. 1; Name:; Dr Uzziel NDAGIJIMANA. Title:; PERMANENT SECRETARY, MINISTRY OF HEALTH. 2; Name:; Dr Daniel NGAMIJE. Title:; COORDINATOR, SINGLE PROJECT IMPLEMENTATION UNIT(SPIU). 3; Name:. Title:. |  |
| Name of bank's authorizing official. Signature:. Date:. Seal:. |  |