|  |  |  |  |  | [V2.9]. |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| GAVI Alliance. |  |  |  |  |  |  |  |
| Application Form for Country Response To Conditions. |  |  |  |  |  |  |  |
| For Support to:. |  |  |  |  |  |  |  |
| Preventive Campaign Support. |  |  |  |  |  |  |  |
| Submitted by. |  |  |  |  |  |  |  |
| The Government of. |  |  |  |  |  |  |  |
| Bangladesh. |  |  |  |  |  |  |  |
| Date of submission: 1/28/2013. |  |  |  |  |  |  |  |
| Deadline for submission: 2/1/2013. |  |  |  |  |  |  |  |
| Select Start and End Year of your Comprehensive Multi-Year Plan (cMYP). |  |  |  |  |  |  |  |
| Start Year. | 2011. |  |  |  |  |  |  |
|  |  |  | End Year. | 2016. |  |  |  |
| Form revised in 2012. |  |  |  |  |  |  |  |
| (To be used with Guidelines of December 2012). |  |  |  |  |  |  |  |
| Please submit the Proposal using the online platform. https://AppsPortal.gavialliance.org/PDExtranet. |  |  |  |  |  |  |  |
| Enquiries to: proposals@gavialliance.org or representatives of a GAVI partner agency. The documents can be shared with GAVI partners, collaborators and general public. The Proposal and attachments must be submitted in English, French, Spanish, or Russian.. Note: Please ensure that the application has been received by the GAVI Secretariat on or before the day of the deadline.. The GAVI Secretariat is unable to return submitted documents and attachments to countries. Unless otherwise specified, documents will be shared with the GAVI Alliance partners and the general public.. |  |  |  |  |  |  |  |

GAVI ALLIANCE GRANT TERMS AND CONDITIONS. FUNDING USED SOLELY FOR APPROVED PROGRAMMES. The applicant country ("Country") confirms that all funding provided by the GAVI Alliance will be used and applied for the sole purpose of fulfilling the programme(s) described in the Country's application. Any significant change from the approved programme(s) must be reviewed and approved in advance by the GAVI Alliance. All funding decisions for the application are made at the discretion of the GAVI Alliance Board and are subject to IRC processes and the availability of funds.. AMENDMENT TO THE APPLICATION. The Country will notify the GAVI Alliance in its Annual Progress Report if it wishes to propose any change to the programme(s) description in its application.The GAVI Alliance will document any change approved by the GAVI Alliance, and the Country's application will be amended.. RETURN OF FUNDS. The Country agrees to reimburse to the GAVI Alliance all funding amounts that are not used for the programme(s) described in its application. The country's reimbursement must be in US dollars and be provided, unless otherwise decided by the GAVI Alliance, within sixty (60) days after the Country receives the GAVI Alliance's request for a reimbursement and be paid to the account or accounts as directed by the GAVI Alliance.. SUSPENSION/ TERMINATION. The GAVI Alliance may suspend all or part of its funding to the Country if it has reason to suspect that funds have been used for purpose other than for the programmes described in the Country's application, or any GAVI Alliance-approved amendment to the application.The GAVI Alliance retains the right to terminate its support to the Country for the programmes described in its application if a misuse of GAVI Alliance funds is confirmed.. ANTICORRUPTION. The Country confirms that funds provided by the GAVI Alliance shall not be offered by the Country to any third person, nor will the Country seek in connection with its application any gift, payment or benefit directly or indirectly that could be construed as an illegal or corrupt practice.. AUDITS AND RECORDS. The Country will conduct annual financial audits, and share these with the GAVI Alliance, as requested. The GAVI Alliance reserves the right, on its own or through an agent, to perform audits or other financial management assessment to ensure the accountability of funds disbursed to the Country.. The Country will maintain accurate accounting records documenting how GAVI Alliance funds are used. The Country will maintain its accounting records in accordance with its government-approved accounting standards for at least three years after the date of last disbursement of GAVI Alliance funds. If there is any claims of misuse of funds, Country will maintain such records until the audit findings are final. The Country agrees not to assert any documentary privilege against the GAVI Alliance in connection with any audit.. CONFIRMATION OF LEGAL VALIDITY. The Country and the signatories for the Country confirm that its application, and Annual Progress Report, are accurate and correct and form legally binding obligations on the Country, under the Country's law, to perform the programmes described in its application, as amended, if applicable, in the APR.. CONFIRMATION OF COMPLIANCE WITH THE GAVI ALLIANCE TRANSPARANCY AND ACCOUNTABILITY POLICY. The Country confirms that it is familiar with the GAVI Alliance Transparency and Accountability Policy (TAP) and complies with the requirements therein.. USE OF COMMERCIAL BANK ACCOUNTS. The Country is responsible for undertaking the necessary due diligence on all commercial banks used to manage GAVI cash-based support. The Country confirms that it will take all responsibility for replenishing GAVI cash support lost due to bank insolvency, fraud or any other unforeseen event.. ARBITRATION. Any dispute between the Country and the GAVI Alliance arising out of or relating to its application that is not settled amicably within a reasonable period of time, will be submitted to arbitration at the request of either the GAVI Alliance or the Country. The arbitration will be conducted in accordance with the then-current UNCITRAL Arbitration Rules. The parties agree to be bound by the arbitration award, as the final adjudication of any such dispute. The place of arbitration will be Geneva, Switzerland. . The languages of the arbitration will be English or French.. For any dispute for which the amount at issue is US$ 100,000 or less, there will be one arbitrator appointed by the GAVI Alliance. For any dispute for which the amount at issue is greater than US $100,000 there will be three arbitrators appointed as follows: The GAVI Alliance and the Country will each appoint one arbitrator, and the two arbitrators so appointed will jointly appoint a third arbitrator who shall be the chairperson.. The GAVI Alliance will not be liable to the country for any claim or loss relating to the programmes described in the application, including without limitation, any financial loss, reliance claims, any harm to property, or personal injury or death. Country is solely responsible for all aspects of managing and implementing the programmes described in its application..

1. Application Specification. Please specify for which type of GAVI support you would like to apply to..

Type of Support; Vaccine; Start Year; End Year; Preferred second presentation[1]. Preventive Campaign Support; MR, 10 dose(s) per vial, LYOPHILISED; 2013; 2013.

[1] This "Preferred second presentation" will be used in case there is no supply available for the preferred presentation of the selected vaccine ("Vaccine" column). If left blank, it will be assumed that the country will prefer waiting until the selected vaccine becomes available..

Note for HPV and MR: These prices are indicative only as GAVI has not procured HPV and MR vaccines for GAVI countries yet. Prices will be finalised through tender processes in Q3. GAVI will only fund HPV vaccines if an acceptable price reduction is secured from the current price indicated. The MR price is based on the current price to UNICEF.

2. Table of Contents.

1. Application Specification. 2. Table of Contents. 3. Executive Summary. 4. Signatures. 4.1. Signatures of the Government and National Coordinating Bodies. 4.1.1. Government and the Inter-Agency Coordinating Committee for Immunisation. 4.1.2. National Coordinating Body - Inter-Agency Coordinating Committee for Immunisation. 4.1.3. The Inter-Agency Coordinating Committee for Immunisation. 4.2. National Immunization Technical Advisory Group for Immunisation. 4.2.1. The NITAG Group for Immunisation. 5. Immunisation Programme Data. 5.1. Basic facts. 5.1.1 MCV Immunisation coverage. 5.2. Baseline and Annual Targets (NVS Routine Support). 5.3. Baseline and Annual Targets for Preventive Campaign(s). 5.3.1 Baseline and annual targets (MR campaign). 6. New and Under-Used Vaccines (NVS Routine). 7. NVS Preventive Campains. 7.1. Assessment of burden of relevant diseases related to campaigns (if available). 7.2 Requested for MR, 10 dose(s) per vial, LYOPHILISED campaign support. 7.2.1 Summary for MR campaign support. 7.2.2 Grant Support for Operational Costs of the MR Campaign. 7.2.3 Evidence of introduction of RCV in routine programme. 7.2.4 Introduction planning for RCV. 7.2.5 Measles surveillance indicators. 7.2.6 Rubella Containing Vaccine introduction Grant. 8. Procurement and Management. 8.1. Procurement and Management of New and Under-Used Vaccines Routine. 8.2. Procurement and Management for NVS Preventive Campaign(s). 8.2.1 Procurement and Management for MR, 10 dose(s) per vial, LYOPHILISED campaign. 8.3. Vaccine Management (EVSM/EVM/VMA). 9. Additional Comments and Recommendations from the National Coordinating Body (ICC/HSCC). 10. Attachments. 11. Annexes. Annex 1 - NVS Routine Support. Annex 2 - NVS Routine – Preferred Second Presentation. Annex 3 - NVS Preventive campaign(s). Table Annex 3.1 C Summary table for vaccine MR, 10 dose(s) per vial, LYOPHILISED. Table Annex 3.1 D Estimated numbers for MR, 10 dose(s) per vial, LYOPHILISED, associated injection safety material and related co-financing budget (page 1). Annex 4. Table Annex 4A: Commodities Cost. Table Annex 4B: Freight cost as percentage of value. Table Annex 4C: Low - Minimum country's co-payment per dose of co-financed vaccine.. Table Annex 4D: Wastage rates and factors. Table Annex 4E: Vaccine maximum packed volumes. 12. Banking Form.

3. Executive Summary.

Please provide a summary of your country's proposal, including the following the information:. l; For each specific request, NVS routine support or NVS campaign :. ¡; The duration of support. ¡; The total amount of funds. ¡; Details of the vaccine(s), if applicable. l; Relevant baseline data, including:. ¡; DTP3 and Measles coverage data (as reported on the WHO/UNICEF Joint Reporting Form). ¡; Birth cohort, targets and immunisation coverage by vaccines. l; Country preparedness. ¡; Summary of EVM assessment. l; The nature of stakeholders' participation in developing this proposal. ¡; Inter-Agency Coordinating Committee. Bangladesh applies to GAVI for Measles Rubella campaign to be conducted in 2013. This will be one time nation wide campaign in the last quarter of 2013<?xml:namespace prefix = o ns = "urn:schemas-microsoft-com:office:office" /> Total amount of funds requested, will be 33,138,394 US$ for vaccines and injection supplies, and 33,586,453 USD for the operational costs. MR Lyophilized 10 dose vaccine is requested. Total doses requirement is calculated using 15% wastage rate Birth cohort is estimated at 3,400.454 in 2012 and 3,499,739 in 2013. Target of 9 months-15 year population for MR campaign in 2013 is 51,671,466. Bangladesh NIP achieved significant success in many areas of EPI in terms of reaching high coverage with traditional vaccines via routine immunization and control of polio and measles via supplementary immunization campaigns. The country successfully introduced Hep B and Hib vaccines with GAVI support and reached 95-96 % coverage in recent years. The DTP3 (Pentavalent) coverage was 96% in 2010 & 95% in 2011 and Measles 1st dose coverage was 94% in 2010 & 98% in 2011. Country intends to maintain BCG coverage at the level of 98% despite of the fact that only 32% of birth is attended by skilled medical personnel, OPV and Pentavalent coverage at the level of 95% and TT coverage of Child Bearing Age Women at the level of 80%. However challenges still remain in terms of sustaining the desired level of protection against measles as well as decreasing further child morbidity and mortality caused by acute respiratory diseases and diarrhoea. An updated cMYP 2011-2016 reflects NIP's priorities, objectives and strategies based on the situational analysis. According to the cMYP, Bangladesh intends to introduce Measles 2nd dose in 2012, PCV in 2013 and Rota and Hep-B birth dose in 2014 as per the recommendations of National committee on Immunization practice chaired by the Secretary to the Ministry of Health and Family Welfare. Country is well prepared to conduct the campaign based on extensive experiences gained through conducting measles catch-up campaign in 2006 by vaccinating 35 million children in three weeks and measles follow-up campaign in 2010 by vaccinating 35 million children in two weeks. Those campaign has reached administrative coverage of 100%. External monitoring by international observers have shown that coverage and quality of the campaign is very good. (refer attached reports): Cold chain assessment was conducted in 2010 followed by EVM assessment in April 2011. As per the recommendation of the EVM assessment conducted in 2011 EPI with UNICEF support is in process to increase the cold storage capacity to accommodate MCV2 and PCV10 by installing 10 WICs which will provide additional 97.5 cubic meters (net). After introducing MCV2 and PCV vaccines additional 29.5 cubic meter net space will be available which can be used to accommodate some of the MR campaign vaccine. Total space required for MR campaign vaccine is 173 cubic meter (net) space. The shortage of space (172.5-29.5=143) could be addressed by hiring temporary cold store at the central level. District level has 118 cubic meters net cold storage space at +2° to +8°, which is adequate for the introduction of MCV2 and PCV10 vaccines. Sub-districts level has 177 cubic meters net cold storage space at +2° to +8° and after introduction of MCV2 and PCV10 vaccines there will be 132 cubic meter excess space. In addition WHO supported on going and planned procurements will increase the districts capacity by 9.7 cubic meters and sub-districts capacity by 35 cubic meters. So in total there will be 177 cubic meter (net ) space available at the field level to accommodate MR campaign vaccine. Meanwhile there is ongoing improvement of national, district and sub-district level cold chain capacity through GAVI HSS funds and new vaccine introduction funds In terms of cold chain storage capacity. Bangladesh has already achieved more than 90% MCV1 coverage during last five years and planned to introduce measles second dose with GAVI support in September 2012. In September 2012 measles first dose will be replaced by MR vaccine and MR single dose will be given to girls at 15 years through national resources. During 2010 and 2011 Bangladesh has achieved recommend surveillance indicators of measles case based surveillance: non measles suspected measles case rate of more than 2 per 100,000 population and more than 80% laboratory confirmation of suspected measles cases. Hence Bangladesh can sustain the effect of proposed MR campaign in last quarter of 2013 to reach measles and rubella elimination in 2016 as envisaged in cMYP. All immunization stakeholders fully participated in developing this proposal. Proposal has been developed through an intensive consultative process between the EPI authorized personnel and EPI partners. It was underpinned by substantial update of strategies, key activities and financial projections that was reflected in the current version of the cMYP with all details related to the introduction of new vaccines (there is no standalone introduction plan). Technical issues were discussed and endorsed by health officials and major issues including the cMYP and application was approved by the ICC..

| 4. Signatures. |  |  |
| --- | --- | --- |
| 4.1. Signatures of the Government and National Coordinating Bodies. |  |  |
| 4.1.1. Government and the Inter-Agency Coordinating Committee for Immunisation. |  |  |
| The Government of Bangladesh would like to expand the existing partnership with the GAVI Alliance for the improvement of the infants routine immunisation programme of the country, and specifically hereby requests for GAVI support for. |  |  |
|  | MR, 10 dose(s) per vial, LYOPHILISED preventive campaigns. |  |
| The Government of Bangladesh commits itself to developing national immunisation services on a sustainable basis in accordance with the Comprehensive Multi-Year Plan presented with this document. The Government requests that the GAVI Alliance and its partners contribute financial and technical assistance to support immunisation of children as outlined in this application.. |  |  |
| Table(s) in the NVS Routine section of this application shows the amount of support in either supply or cash that is required from the GAVI Alliance. Table(s) of this application shows the Government financial commitment for the procurement of this new vaccine (NVS support only).. |  |  |
| Following the regulations of the internal budgeting and financing cycles the Government will annually release its portion of the co-financing funds in the month of September.. |  |  |
| The payment for the first year of co-financed support will be around September 2013 for MR, 10 dose(s) per vial, LYOPHILISED.. |  |  |
| Please note that this application will not be reviewed or approved by the Independent Review Committee (IRC) without the signatures of both the Minister of Health and Minister of Finance or their delegated authority.. |  |  |
| Minister of Health (or delegated authority); Minister of Finance (or delegated authority). Name; Md. Humayun Kabir, Senior Secretary, Ministry of Health and Family Welfare; Name; Shahabuddin Ahmed, Additional Secretary, Ministry of Finance. Date; Date. Signature; Signature. |  |  |
| This report has been compiled by (these persons may be contacted in case the GAVI Secretatiat has queries on this document):. |  |  |
| Full name; Position; Telephone; Email. Dr Jayantha Liyanage; Medical Officer-EPI, IVD, WHO, Bangladesh; +880-2-8831415 Ext. 309; Cell: +8801711535387; liyanagej@searo.who.int. Dr Jucy Merina Adhikari; Immunization Specialist, Health Section, Unicef, Bangladesh; +880-2-8852266 Ext. 7144; jmadhikari@unicef.org. Dr Md Shamsuzzaman; Deputy Programme Manager-EPI, DGHS, MOH&FW; +880-2-8821910-13; zaman1712@yahoo.com. Dr. Md. Tajul Islam A Bari; Programme Manager-EPI & Surveillance, DGHS,MOH&FW; +880-2-8821910-13; tajulepi@yahoo.com. |  |  |
| 4.1.2. National Coordinating Body - Inter-Agency Coordinating Committee for Immunisation. |  |  |
| We the members of the ICC, HSCC, or equivalent committee [1] met on the 27/08/2012 to review this proposal. At that meeting we endorsed this proposal on the basis of the supporting documentation which is attached.. |  |  |
| [1] Inter-agency Coordinating Committee or Health Sector Coordinating Committee, or equivalent committee which has the authority to endorse this application in the country in question.. |  |  |
| The endorsed minutes of this meeting are attached as document number 4.. |  |  |
| Name/Title*; Agency/Organisation*; Signature. Dr. Bushra Binte Alam, Senior Health Specialist; World Bank. Dr. Kaosar Afsana, Director, BRAC Health Program; BRAC. Dr. Lianne Kuppens, Chief, Health Section; UNICEF - Bangladesh. Dr. Shehlina Ahmed, Health Advisor; DFID. Dr. Thushara E.I Fernando, WHO Representative; WHO- Bangladesh. Gregory Adams, Acting Director, Population, Health & Nutrition; USAID. Maki Nagai, Representative; JICA. Md. Anisur Rahman, Joint Secretary(Municipality); Local Government Division, Ministry of Local Government, Rural Development & Co-operatives. PDG Salim Reza, Chairman; Rotary International. Peggy Thorpe, First Secretary, Develoment; CIDA. |  |  |
| 4.1.3. The Inter-Agency Coordinating Committee for Immunisation. |  |  |
| Agencies and partners (including development partners and NGOs) supporting immunisation services are co-ordinated and organised through an inter-agency coordinating mechanism (ICC, HSCC, or equivalent committee). The ICC, HSCC, or equivalent committee is responsible for coordinating and guiding the use of the GAVI NVS routine support and/or campaign support. Please provide information about the ICC, HSCC, or equivalent committee in your country in the table below.. |  |  |
| Profile of the ICC, HSCC, or equivalent committee. |  |  |
| Name of the committee; Inter-Agency Coordination Committee (ICC). Year of constitution of the current committee; 2001. Organisational structure (e.g., sub-committee, stand-alone); Technical Sub-Committee. Frequency of meetings; 3-4 meetings per year. |  |  |
| Composition. |  |  |
| Function; Title / Organisation; Name. Chair; Senior Secretary, Ministry of Health and Family Welfare; Md. Humayun Kabir. Secretary; Director-PHC and Line Director-MNC&AH; Dr Syed Abu Jafar Md. Musa. Members; Joint Secretary(Municipality), Local Government Division, Ministry of Local Government, Rural Development & Co-operatives; Md. Anisur Rahman,. Senior Health Advisor, DFID; Dr. Shehlina Ahmed. Deputy Executive Director, Health, BRAC; Faruque Ahmed. First Secretary, Embassy of Japan; NA. Chief, Health & Nutrition Section, UNICEF; Dr. Lianne Kuppens. Senior Health Specialist, World Bank; Dr. Bushra Binte Alam,. Chairman, Rotary International; PDG Salim Reza. Co-Chairman, National Polio Plus Comittee; Prof. Jalal U Ahmed. |  |  |
| Major functions and responsibilities of the ICC/HSCC:. |  |  |
| 1. ICC review and approve all EPI activities including GAVI related activities and budgets which are recommended by the Technical Sub-committee 2. ICC review and monitor all EPI related activities, budget and expenditure statements 3. ICC assess APR and approve before sending to GAVI Secretariat 4. ICC assess APR and approve NV proposal before sending to GAVI Secretariat. |  |  |
| Three major strategies to enhance the committee's role and functions in the next 12 months. |  |  |
| 1.; To organize at least 3 or more ICC meetings in next 12 months to review the activities and to provide quick decisions for accomplishing activities. <?xml:namespace prefix = o />. 2.; To review the existing committee and to involve new members from other Multisectoral Partners Agencies, Civil Society Organizations, Professional bodies and more participation from Local Goverment like City Corporations.. 3.; To co-ordinate partner agencies and GAVI Secretariat for developing coordinated efforts to introduce New and Underutilized Vaccine in routine EPI to save millions of lives and to conduct supplementary immunization campaign such as MR campaign.. |  |  |
| 4.2. National Immunization Technical Advisory Group for Immunisation. |  |  |
| (If it has been established in the country). |  |  |
| We the members of the NITAG met on the to review this proposal. At that meeting we endorsed this proposal on the basis of the supporting documentation which is attached.. |  |  |
| The endorsed minutes of this meeting are attached as document number 4.. |  |  |

4.2.1. The NITAG Group for Immunisation.

Profile of the NITAG.

Name of the NITAG. Year of constitution of the current NITAG. Organisational structure (e.g., sub-committee, stand-alone). Frequency of meetings.

Composition.

Function; Title / Organisation; Name. Chair. Secretary. Members.

Major functions and responsibilities of the NITAG.

Three major strategies to enhance the NITAG's role and functions in the next 12 months.

1.. 2.. 3..

5. Immunisation Programme Data.

5.1. Basic facts.

Please complete the tables below, using data from available sources. Please identify the source of the data, and the date. Where possible use the most recent data and attach the source document..

▪; Please refer to the Comprehensive Multi-Year Plan for Immunisation (cMYP) (or equivalent plan) and attach a complete copy (with an Executive Summary) as DOCUMENT NUMBER : 6. ▪; Please attach relevant Vaccine Introduction Plans as DOCUMENT NUMBER : 7. ▪; Please refer to the two most recent annual WHO/UNICEF Joint Reporting Forms (JRF) on Vaccine Preventable Diseases. ▪; Please refer to Health Sector Strategy documents, budgetary documents, and other reports, surveys etc, as appropriate..

For the year 2011 (most recent; specify dates of data provided).

Figure; Year; Source. Total population; 149,772,364; 2011; 2011 National Census. Infant mortality rate (per 1000); 43; 2011; BDHS. Surviving infants[1]; 3,254,214; 2011; Based on BDHS andWHO-UNICEF JRF. GNI per capita (US$); 640; 2011; World Bank data. Total Health Expenditure (THE) as a percentage of GDP; 5; %; 2011; Ministry of Finance, Budget 2011. General government expenditure on health (GGHE) as % of General government expenditure; 6; %; 2011; Ministry of Finance, Budget 2011.

[1] Surviving infants = Infants surviving the first 12 months of life.

Please provide some additional information on the planning and budgeting context in your country. There are two major policy planning documents that outline sector priorities, strategies, interventions and resources: a) Strategic Plan for Health Population and Nutrition Sector Development Programme (HPNSDP) 2011-2016 b) Programme Implementation Plan (PIP) of HPNSDP 2011 - 2016. Please indicate the name and date of the relevant planning document for health. a) Strategic Plan for Health Population and Nutrition Sector Development Programme (HPNSDP) 2011-2016 b) Programme Implementation Plan (PIP) of HPNSDP 2011 - 2016. Is the CMYP (or updated Multi-Year Plan) aligned with the document (timing, content, etc.). Yes, the current cMYP developed in 2010 covers the same period as HPNSDP 2011 - 2016. Please indicate the national planning budgeting cycle for health. National budgeting cycle for health covers 1 year and start from July 1 of each year and ends on June 30 of the next year. Please indicate the national planning cycle for immunisation. National Planning cycle for immunization is harmonized with national budgeting cycle for health. Please indicate if sex disaggregated data (SDD) is used in immunisation routine reporting systems. Sex disaggregated date is not used in routine immunization reporting system, however this data is available in coverage evaluation survey report. Please indicate if gender aspects relating to introduction of a new vaccine have been addressed in the introduction plan. No. Please describe any recent evidence of socio-economic and/or gender barriers to the immunisation programme through studies or surveys?. There are no socio-economic or gender barriers to the immunization programme.. Country should provide an outline of all preparatory activities for vaccine(s) introduction. The preparatory activities is based on the experience of measles catch-up campaign and measles follow-up campaign conducted in 2006 & in 2010 respectively. Following would be key preparatory activities 1) Development of training materials, IEC materials and record keeping & reporting forms 2) Training of field workers and supervisors 3) Development of Microplan 4) Advocacy, social mobilization and planning meetings at national and sub-national level 5) Vaccine and logistics procurement management and distribution including addressing the cold chain capacity at national, district and sub district levels 6) Human resource management 7) Programme supervision and monitoring 8) AEFI reporting system and management 9) Waste management.

5.1.1 MCV Immunisation coverage.. Please provide information concerning routine immunisation coverage related to measle-containing vaccines (MCV).. Table 5.1.1: MCV Immunisation coverage.. Coverage; 2005; 2006; 2007. Administrative1); WHO/UNICEF2); Administrative1); WHO/UNICEF2); Administrative1); WHO/UNICEF2). Measles 1st dose (%); 94; 94; 92; 92; 95; 95. Measles 2st dose (%); 0; 0; 0; 0; 0; 0. Supplementary Immunization Activities (SIA) (%); 0; 0; 101; 87; 0; 0.. Coverage; 2008; 2009; 2010. Administrative1); WHO/UNICEF2); Administrative1); WHO/UNICEF2); Administrative1); WHO/UNICEF2). Measles 1st dose (%); 96; 96; 98; 98; 94; 94. Measles 2st dose (%); 0; 0; 0; 0; 0; 0. Supplementary Immunization Activities (SIA) (%); 0; 0; 0; 0; 100; 88.. Coverage; 2011. Administrative1); WHO/UNICEF2). Measles 1st dose (%); 96; 96. Measles 2st dose (%); 0; 0. Supplementary Immunization Activities (SIA) (%); 0; 0.... Note:. 1)National reported Administrative Coverage. 2)WHO/UNICEF estimated coverage. Was the last Measles Supplementary Immunization Activities (SIA) administrative coverage or results of a survey of acceptable methodology Results of a survey. Please describe survey methodology:. WHO 30 cluster Coverage Evaluation Survey methodology was followed to conduct measles supplementary activities (SIA) survey in each district and city corporation (total 72 units) and data was collected after taking interview of parents and on the basis of immunization history....

5.2. Baseline and Annual Targets (NVS Routine Support)

No NVS Routine Support is requested.

| 5.3. Baseline and Annual Targets for Preventive Campaign(s).. |  |
| --- | --- |
| 5.3.1 Baseline and annual targets (MR campaign). Please specify cohort for rubella-containing vaccines (RCV):. RCV Start 9 months. RCV End 15 years. Cohort population = population 9 months - 15 years old. GAVI supports no more than 15 cohorts. If the application is not within 9 months to 15 years, please provide justification. NA.. Table 5.3.1 Baseline NVS preventive campaign figures for MR.. Number; Base Year; Baseline and Targets. 2011; 2013. Total births; 3,400,432; 3,499,760. Total population 9 months - 15 years old; 51,671,466; 51,671,466. Target population vaccinated with MR; 0; 51,671,466. MR (campaign) coverage (%) [1]; 0.00 %; 100.00 %. Wastage rate in base year and thereafter (%) for MR (campaign); 0; 15. Wastage factor in base year and thereafter for MR; 1; 1.18.. [1] Number of persons vaccinated out of total births... |  |

6. New and Under-Used Vaccines (NVS Routine)

No NVS Routine Support is requested.

7. NVS Preventive Campains

7.1. Assessment of burden of relevant diseases related to campaigns (if available).

Disease; Title of the assessment; Date; Results. Measles and Rubella; Review of the yearly measles and rubella surveillance data; August 2012; Background: In 2004, Bangladesh accelerated measles control activities. According to WHO/UNICEF estimated MCV1 coverage was 81% in 2004 and 89% of the total cases from serologically confirmed measles outbreaks in 2004 and 2005 were under 10 years old children. In March 2006, measles catch up campaign was conducted targeting children of 9 months -10 years. The reported coverage of the campaign was 101% and survey evaluated coverage was 87%. Vaccination cards were not given during the campaign and hence the campaign coverage has been evaluated in the survey by history only. After the campaign, measles incidence became low (5-10 per million populations, source: clinical cases + serologically confirmed outbreak cases + epi linked)). As a follow-up strategy measles Follow-up campaign was conducted in January 2010 targeting children of 9 months-5 years. The reported coverage was 100% and survey evaluated coverage was 88%. Vaccination cards were not given during the campaign and hence the campaign coverage has been evaluated in the survey by history only. Current rubella and measles situation: Serologically and epidemiological linked rubella incidence in Bangladesh was 37 per million population in 2011 and 87 per million population in 2010. Rubella epidemics come ones in 2-3 years and year 2010 was an epidemic year. The age distribution of cases reported from laboratory confirmed rubella outbreaks have shown that 77% cases in 2011 and 84% of cases in 2010 were among under 15 year old children. In 2010 WHO/UNICEF estimated MCV1 coverage was 94%. However incidence of measles (clinical cases+sero confirm outbreak cases and epi linked) increased from 5.2 per million pop in 2010 to 37.3 per one million population (788 in 2010, 5625 in 2011). 86% of cases from the laboratory confirmed outbreaks were among children of under 15 years. Bangladesh will introduce MR vaccine as measles first dose from September 2012. Simultaneously MR vaccine will be given to adolescent girls who are coming for TT vaccination at the age of 15 years. Vaccine that would be spared after infant vaccination will be used for adolescent girl, hence no additional MR vaccine will be required. The TT2 coverage for girls is above 80%. Measles second dose will be given at 15-18 months from September 2012 through GAVI funds “Sero-prevalence of Rubella among urban and rural Bangladeshi Women” a small scale study conducted by A Nessa, MN Islam, S Tabassum, SU Munshi, M Ahmed and R Karim which was published in Indian Journal of Medical Microbiology, Year:2008, Volumn: 26, Page; 94-95 shows that 78.69% of 1-5 years, 47.55% of 6-10 years, 33.34% of 11-15 years, 22.59% of 16-20 years, 18.08% of 21-25 years, 16.42% of 26-30 years, 19.05% of 31-35 years, 11.67% of 36-40years, 9.68% of 41-45 years age groups women are seronegative for rubella specific IgG. Conclusion: Bangladesh has achieved more than 90% MCV1 coverage. Two measles supplementary immunization activities have been conducted in 2006 and 2010. Measles second dose will be introduced in 2012. MR will replace measles first dose. MR vaccination campaign targeting children 9 months-15 years will enable to drastically reduce the circulation of both measles and rubella virus circulation and reach measles and rubella elimination. Bangladesh has a strong surveillance system to monitor the progress..

If MR vaccines have already been introduced in your country during campaigns, please give details of the lessons learned from previous introduction(s) specifically for: storage capacity, protection from accidental freezing, staff training, cold chain, logistics, coverage and drop-out rates, wastage rate, etc., and suggest action points to address them..

Lessons Learned; Action Points. Although Bangladesh has not introduced MR vaccine, however Bangladesh has conducted measles catch-up campaign targeting 35 million children under 10 years in 2006. This together with measles follow up campaign in 2010 have provided a wide range of experiences. Some of the key lessons from those campaigns are: High political and financial commitment of government and active coordination among partners agencies were the key for successful conduction of campaign. A separate storage premises for campaign vaccine and logistics helps in better management In case of limited storage capacity against a huge requirement of vaccine phase- wise import and delivery on a well planned schedule is critical Necessity of effective and quality training at all level before campaign. Advocacy and planning meetings with different stakeholder at various level is useful to create awareness among the community. Timely formulation of a good micro-plan is key to achieving campaign success AEFI management system, daily monitoring of coverage data from vaccination centers to the district levels is crucial Necessity of experienced cold chain and logistic consultants; Commitment from the Government and parnter agencies is secured before the campaign Development of detail micro-plan for the campaign Training and orientation of all key professionals will be conducted in advance Conduction of advocacy and planning meetings will be considered before and during campaign Preparations for the cold chain requirements at national and district level Development of vaccine and logistics management and distribution plan.

7.1.1 Epidemiology and disease burden for Measles-Rubella. Please select at least one of the following information sources to justify RCV diseases burden results:. Epidemiological information on burden of disease:. þ; 1 - Rubella data from the measles case-based surveillance system (including the age distribution of rubella cases). þ; 2 - Rubella seroprevalence surveys. o; 3 - Congenital Rubella Syndrome (CRS) burden information, e.g. retrospective search, modelled estimates for CRS burden, prospective surveillance. o; 4 - Other.

7.2.Requested for MR, 10 dose(s) per vial, LYOPHILISED campaign support. 7.2.1. Summary for MR campaign support. Please give a summary of the cMYP and/or the MR, 10 dose(s) per vial, LYOPHILISED campaign introduction plan sections that refer to the introduction of MR, 10 dose(s) per vial, LYOPHILISED campaign. Outline the key points that informed the decision-making process (data considered etc):. cMYP has recognized the introduction of RCV in the national immunization schedule. Accordingly MR vaccine will be introduced to National immunization programme at 9 months in September 2012. At the same time MR vaccine will be offered to women at 15 years with TT first dose vaccination and measles second dose will be offered to children at 15-18 months. Since 2003, Bangladesh has strengthened measles surveillance. Initially it was outbreak based surveillance but improved to case based surveillance with laboratory confirmation of all cases in 2009. Data from routine surveillance from 2003 has provided substantial amount of data on rubella and measles epidemiology in Bangladesh. Accordingly, Serologically and epi linked rubella incidence in Bangladesh in 2011 is 37 per one million population. The incidence of rubella was 87 per one million population in the epidemic year of 2010. Age distribution of out breaks has shown that 83% of cases are less than 15 years in 2009 and 2010, and 77% of cases were less than 15 years in 2011. Age distribution of cases from measles outbreaks reported in 2011 has shown that 84% of cases are under 15 years. Accordingly campaign covering age group 9 months-15 years will reduce both rubella and measles virus circulation and enable to achieve measles and rubella elimination. The campaign would be supplementary to more than 90% evaluated MCV coverage for last 5 years, measles second dose, MR vaccination at 9 months and 15 years (for women). Once the MR camapign is conducted Bangladesh would have implemented all recomended immunization strategies for measles and rubella elimination. Bangladesh has a good surveillance system to monitor the progress. Please summarise (1) the waste management plan and (2) the cold chain capacity and readiness to accommodate new vaccines, stating how the cold chain expansion (if required) will be financed, and when it will be in place.Please indicate if the supplies for the campaign will have any impact in the shipment plans for your routine vaccines and how it will be handled:. Waste management plan:<?xml:namespace prefix = o /> During the campaign filled safety boxes will be returned to vaccine storage centers at the end of each session together with the empty vaccine carrier and the tally sheet for the session. If incinerators are available in these centers, safety boxes will be incinerated. Where there are no incinerators, safety boxes will be burned in a pit under the supervision of the manager of the institue who will keep a written record of the process. After burning unburned remnants like needles will be covered by a layer of soil. Cold chain capacity and readiness In 2006, Bangladesh vaccinated 35 million children in three weeks during measles catch-up campaign. The key approaches used for enhancing cold chain capacity and management were 1. Hiring additional cold chain space of 420 cubic meters near Dhaka international airport. Ensuring adequate power supply, temperature management and EPI cold chain engineers to this facility 2. Assessment of district and upazila level cold chain capacity to plan the phasing of vaccine supply from national level to districts 3. Mobilizing district and upazila level cold chain space out side the health department to prepare the ice packs. This enabled to use maximum cold chain space in health department to keep the vaccines. External independent monitoring has shown that in all vaccination centers VVM was either in stage 1 or 2 and above approaches has worked well. Bangladesh is planning to introduce Pneumococal vaccine in 2013. As per the recommendation of the EVM assessment conducted in 2011 UNICEF is in process to increase the cold storage capacity to accommodate MCV2 and PCV10 by installing 10 WICs which will provide additional 97.5 cubic meters (net). After accommodating these vaccines there will be 29.5 cubic meter (net) excess space which will be used to accommodate some of the MR campaign vaccine. Total space required for MR campaign vaccine is 173 cubic meter (net) space. The shortage of space of (172.5-29.5) 143 cubic meter will be addressed by hiring cold store at the central level. District level has 118 cubic meters net cold storage space at +2° to +8° which is adequate for the introduction of MCV2 and PCV10 vaccines. Sub-districts level has 177 cubic meters net cold storage space at +2° to +8° and after introduction of MCV2 and PCV10 vaccines there will be 132 cubic meter excess space. In addition WHO has provided 126 ILRs in 2011 and is in the process to procure 144 ILR and 30 Solar Refrigerators by 2012 which will increase the districts capacity by 9.7 cubic meters and sub-districts capacity by 35 cubic meters. So in total there will be 177 cubic meter (net ) space available at the field level to accommodate MR campaign vaccine. Meanwhile there is ongoing improvement of national, district and sub-district level cold chain capacity through GAVI HSS funds and new vaccine introduction funds. With these improvements and implementing strategies used in 2006 campaign to meet the cold chain needs it would be possible to ensure cold chain requirements for the MR vaccination campaign to be held in last quarter of 2013... 7.2.2. Grant Support for Operational Costs of the MR Campaign.. Please indicate in the tables below how the support Grant [1] will be used to support the operational costs of the campaign and other critical pre-introduction activities. GAVI's support may not be enough to cover the full needs so please indicate in the table below how much and who will be complementing the funds needed (refer to the cMYP and the MR, 10 dose(s) per vial, LYOPHILISED campaign introduction plan)... Table 7.2.2: calculation of grant to support the operational costs of the campaigns.. Year of MR support; Target population vaccinated (from Table 5.3); Share per population 9 months-15 years old in US$; Total in US$. 2013; 51,671,466; 0.65; 33,586,453.. [1] The Grant will be based on a maximum award of $0.65$ per cohort population.. Cost (and finance) of the MR, 10 dose(s) per vial, LYOPHILISED campaign US$.. Cost Category Full needs for new vaccine introduction in US$; Funded with GAVI introduction grant in US$. 2013; 2013. Training; 2,746,830; 0. Social Mobilization, IEC and advocacy; 2,788,484; 0. Cold Chain Equipment & Maintenance; 5,671,287; 0. Vehicles and Transportation; 3,808,332; 0. Programme Management; 6,275,198; 0. Surveillance and Monitoring; 5,257,165; 0. Human Resources; 325,635; 0. Waste Management; 206,877; 0. Technical Assistance; 250,000; 0. Planning; 200,098; 0. Volunteer incentives; 2,145,958; 0. Other (please specify). Finger Marker; 289,916. Improve Cold Chain Capacity at Central level; 3,411,886. Campaign evaluation (coverage evaluation survey); 208,845. Total; 33,586,511; 0..... Please describe others sources of funding if available to cover your full needs.. 7.2.3 Evidence of introduction of RCV in routine programme.. Please provide evidence that the country can finance the introduction of Rubella-Containing-Vaccine (RCV) into the routine programme through one of the following:.. þ; 1 - A commercial contract for purchase of MR/MMR (Meales Rubella/Meales Mumps Rubella) vaccine together with shipping documents, invoice, etc.. þ; 2 - Proof that RCV has been integrated into the cMYP with the budget line for vaccines increased to include purchase of RCV as part of the health sector budget to indicate that RCV funds are allocated. þ; 3 - A letter from the Minister of Finance or Budget ensuring additional funding for RCV purchase. þ; 4 - An MOU between government and donor(s) (or other written document that proves donor commitment) for at least one year for purchase of RCV for use in the routine programme. o; 5 - Other.. 7.2.4 Introduction planning for RCV.. Countries should describe their plan for introduction including surveillance activities:.. Does Bangladesh’s cMYP include a plan for the introduction of RCV into the national programme? Yes.. Please describe a Plan Of Action (POA) for the introduction of RCV into the national programme or provide the POA as an attachment - Refer to section 10. Attachments. (Document N° ).. Bangladesh Plan of Action (PoA) for measles and rubella elimination has evolved over the years from the national plan for sustainable measles mortality reduction to elimination. The comprehensive vaccination strategy for the introduction of RCV include: <?xml:namespace prefix = o /> - Measles and rubella (MR) campaign to be conducted in last quarter of 2013 targeting children 9 months-15 years - Replacing Measles containing vaccine (MCV1 ) at 9 months by Measles and rubella (MR) in the routine childhood vaccination programme from September 2012 - Bangladesh provides 5 doses of TT vaccine for women starting from 15 years in routine vaccination programme as a component of sustaining maternal and neonatal tetanus elimination status. From September 2012, this opportunity will be used to provide a single dose MR vaccine when women come for TT vaccine at the age of 15 years. - Measles second dose will be given to children at 15-18 months National MCV1 coverage is more than 90% and all districts have achieved more than 80% MCV1 coverage. Once MR vaccine will replace Measles vaccine, high routine immunization coverage for both measles and rubella vaccines will be maintained. If measles second dose coverage also increases as first dose coverage, that will ensure that children who do not get first dose as well who got first dose but did not develop immunity will be immunized. After 2013, based on epidemiology of measles and rubella necessity and timing of supplementary MR campaigns in the future will be decided. Surveillance for rubella and measles would include: Since 2009 case-based measles surveillance is conducted with serological confirmation for measles and rubella. Non measles suspected measles rate was more than 2 per 100,000 populations in successive years. Laboratory confirmation has been more than 80% Sentinel surveillance for Congenital Rubella Syndrome (CRS) surveillance will be started in selected sites from fourth quarter of 2012. These sites will be pediatrics units, ophthalmology units, neonatology units, cardiology units and ENT units where CRS cases are likely to be reported Adverse Event Following Immunization (AEFI) surveillance is well established in Bangladesh and 1197 AEFI were reported in 2011 and out of them 45 were severe AEFI. As per national guidelines all severe AEFI cases need to be fully investigated and in 2011, 98% has been investigated Vaccine coverage monitoring and reporting Micro plans are prepared before the beginning of the year. As per the micro plans immunization sessions are conducted. Immunization coverage is monitored by union in monthly upazila meetings and coverage of upazials is monitored by district in district monthly meetings. National level closely monitors the coverage by districts and upazila. In addition coverage evaluation surveys are conducted yearly by districts. The communication strategy for the introduction of RCV Comprehensive communication strategy targeting adolescents and school going children and their parents would be developed before the beginning of the MR campaign. In addition communication strategies for routine child hood immunization and TT vaccines will include rubella vaccination......

INSTRUCTIONS. Components of the POA/cMYP should include:. a. Comprehensive vaccination strategy for the introduction of RCV including a description of:. i. Initial Measles and rubella (MR) campaign. ii. Replacing Measles containing vaccine (MCV) with Measles and rubella (MR) / Measles, mumps, and rubella (MMR) in the routine childhood vaccination programme. iii. Strategies for targeting Women of Childbearing Age (WCBA), such as vaccination during routine services, post-partum, at 1st well baby visit, SIAs. iv. Linkage to the current routine immunisation schedule. v. Linkage to measles second dose, if applicable. vi. Description of how the country plans to continue to maintain high MR/MMR vaccine coverage either through routine immunisation or through Supplementary Immunization Activities (SIAs). b. A brief description of the following surveillance activities:. i. Integration of Rubella surveillance with case-based measles surveillance. ii. Congenital Rubella Syndrome (CRS) surveillance or plans to establish sentinel site CRS surveillance. iii. Adverse Event Following Immunization (AEFI) surveillance. c. Vaccine coverage monitoring and reporting. d. The communication strategy for the introduction of RCV.. 7.2.5 Measles surveillance indicators.. Please provide information on the following indicators of the quality of measles surveillance for at least two years prior to application (if available):.. Surveillance indicator; 2010; 2011. Reporting rate at national level 1); 10; 5. 100,000; 100,000. Laboratory confirmation rate (%) 2); 81; 92.. Note:. 1) Reporting rate at national level = number of discarded measles cases per 100,000 population per year. 2) Laboratory confirmation rate (%) = number of suspected cases with specimens collected for testing divided by the number of suspected cases not confirmed through epidemiological linkage.....

7.2.6 Rubella Containing Vaccine introduction Grant.. Has a Rubella Containing vaccine already been introduced nationally on a routine basis? Yes.....

8. Procurement and Management.

8.1. Procurement and Management of New and Under-Used Vaccines Routine.

No NVS Routine Support is requested.

8.2. Procurement and Management for NVS Preventive Campaign(s).

8.2.1. Procurement and Management for MR, 10 dose(s) per vial, LYOPHILISED campaign. a) Please show how the support will operate and be managed including procurement of vaccines (GAVI expects that countries will procure vaccine and injection supplies through UNICEF):. Vaccine and logistics will be procured by UNICEF through their procurement mechanism. Once vaccines reach Bangladesh, logistic management will be done by National EPI with the technical assistance of UNICEF and WHO.. b) Please indicate when you are planning to conduct the campaign (month and year) and how the campaign is going to be rolled out (e.g. in different phases or one time).. Campaign will be conducted in last quarter of 2013 and it will be one time. c) Please outline how coverage of the new vaccine will be monitored and reported (refer to the cMYP and/or the MR, 10 dose(s) per vial, LYOPHILISED campaign introduction plan). The coverage of the campaign will be monitored on daily basis. Assigned first line supervisor will visit areas covered by the vaccinator of the previous day and conduct a survey in 20 house holds to identify any missed target population. In addition, second line supervisors from upazila, district, division and HQ will also conduct house hold survey by using check list. Independent observers will also monitor the programme by using a checklist. Analysis of these monitoring checklist will help to identify areas with low coverage and to take appropriate action. The vaccinator from each of the center will send the tally sheet to the upazila health complex at the end of the session. The upazila manager will compile all these reports and calculate the coverage against the target. The coverage report of the upazilas will be sent to district and from the district to national level on daily basis..

8.3. Vaccine Management (EVSM/EVM/VMA).

Did the country have Effective Vaccine Management Assessment (VMA) in the past? Yes. When was the last VMA conducted? March 2004. Did the country have Effective Vaccine Store Management (EVSM) in the past? Yes. When was the last EVSM conducted? March 2004. Did the country have Effective Vaccine Management (EVM) in the past? Yes. When was the EVM conducted? April 2011. If your country conducted either EVSM or VMA in the past two years, please attach relevant reports. (Document N°13). A VMA report must be attached from those countries which have introduced a New and Underused Vaccine with GAVI support before 2008.. Please note that Effective Vaccine Store Management (EVSM) and Vaccine Management Assessment(VMA) tools have been replaced by an integrated Effective Vaccine Management (EVM) tool. The information on EVM tool can be found at http://www.who.int/immunization_delivery/systems_policy/logistics/en/index6.html. For countries which conducted EVSM, VMA or EVM in the past, please report on activities carried out as part of either action plan or improvement plan prepared after the EVSM/VMA/EVM.. Calibration of temperature monitoring device plan has been developed Works are under way to increase the capacity of cold space and dry space at central EPI Plan has been developed to install fire extinguisher at EPI store SOP on vaccine management updated and planned for refreshers training Introduced uniform formula for forecasting of vaccine needs at all level Introduced new batch cards and vaccine stock registers. Does the country plan to conduct an Effective Vaccine Management (EVM) Assessment in the future? Yes. When is the next Effective Vaccine Management (EVM) Assessment planned? March 2014. Under new guidelines, it will be mandatory for the countries to conduct an EVM prior to an application for introduction of new vaccine..

9. Additional Comments and Recommendations from the National Coordinating Body (ICC/HSCC).

Comments and Recommendations from the National Coordinating Body (ICC/HSCC).

Members of ICC meeting held on 27 August 2012 recommended to conduct MR vaccination campaign for children 9 months-15 years as part of overall plan for measles and rubella elimination in <?xml:namespace prefix = st1 />Bangladesh.

10. Attachments.

10.1. List of documents attached to this proposal.

Document Number; Document; Section; Mandatory; File. Signature_MoH & MoF.pdf. 1; MoH Signature (or delegated authority) of Proposal; File desc: MoH Signature. Date/time: 8/28/2012 3:30:19 AM. Size: 283179. Signature_MoH & MoF.pdf. 2; MoF Signature (or delegated authority) of Proposal; File desc: Mof Signature. Date/time: 8/28/2012 3:30:35 AM. Size: 283179. Signature_ICC member.pdf. 3; Signatures of ICC or HSCC or equivalent in Proposal; File desc: Signatures of ICC members. Date/time: 8/29/2012 6:26:00 AM. Size: 304759. ICC meeting minutes.pdf. 4; Minutes of ICC/HSCC meeting endorsing Proposal; File desc: Minutes of ICC meeting. Date/time: 8/29/2012 6:26:20 AM. Size: 541384. cMYP Bangladesh 2011-2016.pdf. 5; comprehensive Multi Year Plan - cMYP; File desc: Bangladesh cMYP 2011-2016. Date/time: 8/25/2012 2:53:00 AM. Size: 2908386. BNG cMYP Costing 2011 Final.xls. 6; cMYP Costing tool for financial analysis; File desc: cMYP Costing. Date/time: 8/25/2012 3:02:01 AM. Size: 4118016. Implemetation Plan.pdf. 7; Plan for NVS introduction (if not part of cMYP); 5.1; File desc: Implementation plan. Date/time: 8/29/2012 6:26:47 AM. Size: 231883. EVM Improvement Plan.pdf. 8; Improvement plan based on EVM; File desc: EVM Improvement Plan. Date/time: 8/28/2012 1:07:46 AM. Size: 550060. Shipping and commercial Invoice.pdf. 11; Evidence of introduction of RCV in routine programme; 7.c.3; File desc: Evidence of introduction of RCV in routine programme. Date/time: 8/30/2012 5:44:16 AM. Size: 1187395. Summmary of reply to conditions.pdf. 14; Summary of response to conditions; 3; File desc:. Date/time: 1/22/2013 3:46:51 AM. Size: 988211.

11. Annexes.

Annex 1 - NVS Routine Support.

No NVS Routine Support is requested.

Annex 2 - NVS Routine – Preferred Second Presentation.

No NVS Routine – Preferred Second Presentation requested this year.

Annex 3 - NVS Preventive campaign(s)... Annex 3.1 - NVS Preventive campaign(s) (MR, 10 dose(s) per vial, LYOPHILISED). Table Annex 3.1 C: Summary table for CAMPAIGN MR, 10 dose(s) per vial, LYOPHILISED.. Data from; 2013. Total campaign population; Table 5.3.1; #; 51,671,466. Immunization coverage; Table 5.3.1; %; 100.00 %. Number of persons to be vaccinated; Table 5.3.1; #; 51,671,466. Number of doses per persons; Parameter; #; 1. Estimated vaccine wastage factor; Table 5.3.1; #; 1.18. Number of doses per vial; Parameter; #; 10. AD syringes required; Parameter; #; Yes. Reconstitution syringes required; Parameter; #; Yes. Safety boxes required; Parameter; #; Yes. Vaccine price per dose; Table Annexes 4A; $; 0.524. AD syringe price per unit; Table Annexes 4A; $; 0.0465. Reconstitution syringe price per unit; Table Annexes 4A; $; 0.037. Safety box price per unit; Table Annexes 4A; $; 0.58. Freight cost as % of vaccines value; Table Annexes 4B; %; 13.00 %. Freight cost as % of devices value; Parameter; %; 10.00 %...

Table Annex 3.1 D: Estimated number of MR, 10 dose(s) per vial, LYOPHILISED associated injection safety material and related co-financing budget (page 1). Formula; GAVI. 2013. B; Number of persons to be vaccinated with the first dose; 51,671,466. C; Number of doses per persons; 1. D; Number of doses needed; B x C; 51,671,466. E; Estimated vaccine wastage factor; Wastage factor table; 1.18. F; Number of doses needed including wastage; D x E; 60,972,330. G; Vaccines buffer stock; 0; 0. I; Total vaccine doses needed; (((F + G) / Vaccine package size) + 1) * Vaccine package size; 60,972,430. J; Number of doses per vial; Vaccine parameter; 10. K; Number of AD syringes (+ 10% wastage) needed; (D + G) x 1.11; 57,355,328. L; Reconstitution syringes (+ 10% wastage) needed; I / J * 1.11; 6,767,940. M; Total of safety boxes (+ 10% of extra need) needed; (K + L) /100 * 1.11; 711,769. N; Cost of vaccines needed; I x g; 0.524. O; Cost of AD syringes needed; K x ca; 2,667,022.752. P; Cost of reconstitution syringes needed; L x cr; 250,414. Q; Cost of safety boxes needed; M x cs; 412,827. R; Freight cost for vaccines needed; N x fv; 0. S; Freight cost for devices needed; (O+P+Q) x fd; 333,027. T; Total fund needed; (N+O+P+Q+R+S); 35,612,844.752... Note: There is no cofinancing for NVS preventive campaigns...

| Annex 4. |  |  |
| --- | --- | --- |
| Table Annex 4A: Commodities Cost. |  |  |
| Vaccine; Presentation; 2013; 2014; 2015; 2016. DTP-HepB-Hib, 1 dose(s) per vial, LIQUID; 1; 2.017; 1.986; 1.933; 1.927. DTP-HepB-Hib, 10 dose(s) per vial, LIQUID; 10; 2.017; 1.986; 1.933; 1.927. DTP-HepB-Hib, 2 dose(s) per vial, LYOPHILISED; 2; 2.017; 1.986; 1.933; 1.927. HPV bivalent, 2 dose(s) per vial, LIQUID; 2; 5.000; 5.000; 5.000; 5.000. HPV quadrivalent, 1 dose(s) per vial, LIQUID; 1; 5.000; 5.000; 5.000; 5.000. Measles, 10 dose(s) per vial, LYOPHILISED; 10; 0.242; 0.242; 0.242; 0.242. Meningogoccal, 10 dose(s) per vial, LIQUID; 10; 0.520; 0.520; 0.520; 0.520. MR, 10 dose(s) per vial, LYOPHILISED; 10; 0.524; 0.555; 0.578; 0.606. Pneumococcal (PCV10), 2 dose(s) per vial, LIQUID; 2; 3.500; 3.500; 3.500; 3.500. Pneumococcal (PCV13), 1 dose(s) per vial, LIQUID; 1; 3.500; 3.500; 3.500; 3.500. Rotavirus, 2-dose schedule; 1; 2.550; 2.550; 2.550; 2.550. Rotavirus, 3-dose schedule; 1; 3.500; 3.500; 3.500; 3.500. Yellow Fever, 10 dose(s) per vial, LYOPHILISED; 10; 0.900; 0.900; 0.900; 0.900. Yellow Fever, 5 dose(s) per vial, LYOPHILISED; 5; 0.900; 0.900; 0.900; 0.900. |  |  |
| Note for HPV and MR: These prices are indicative only as GAVI has not procured HPV and MR vaccines for GAVI countries yet. Prices will be finalised through tender processes in Q3. GAVI will only fund HPV vaccines if an acceptable price reduction is secured from the current price indicated. The MR price is based on the current price to UNICEF. |  |  |
| Supply; Form; 2013; 2014; 2015; 2016. AD-SYRINGE; SYRINGE; 0.047; 0.047; 0.047; 0.047. RECONSTIT-SYRINGE-PENTAVAL; SYRINGE; 0.037; 0.037; 0.037; 0.037. RECONSTIT-SYRINGE-YF; SYRINGE; 0.037; 0.037; 0.037; 0.037. SAFETY-BOX; SAFETYBOX; 0.580; 0.580; 0.580; 0.580. |  |  |
| Note: WAP - weighted average price (to be used for any presentation: For DTP-HepB-Hib, it applies to 1 dose liquid, 2 dose lyophilised and 10 dose liquid. For Yellow Fever, it applies to 5 dose lyophilised and 10 dose lyophilised). |  |  |
| Table Annex 4B: Freight cost as percentage of value. |  |  |
| Vaccine Antigen; Vaccine Type; No Threshold; 500,000$. <=; >. DTP-HepB-Hib; HEPBHIB; 23.80 %; 6.00 %. HPV bivalent; HPV; 3.50 %. HPV quadrivalent; HPV; 3.50 %. Measles; MEASLES; 14.00 %. Meningogoccal; MENINACONJUGATE; 10.20 %. MR; MR; 13.20 %. Pneumococcal (PCV10); PNEUMO; 3.00 %. Pneumococcal (PCV13); PNEUMO; 6.00 %. Rotavirus; ROTA; 5.00 %. Yellow Fever; YF; 7.80 %. |  |  |
| Table Annex 4C: Low - Minimum country's co-payment per dose of co-financed vaccine.. |  |  |
| Vaccine. |  |  |
| Table Annex 4D: Wastage rates and factors. |  |  |
| Countries are expected to plan for a maximal wastage rate of:. |  |  |
| • 50% - for a lyophilised vaccine in 10 or 20-dose vial,. |  |  |
| • 25% - for a liquid vaccine in 10 or 20-dose vial or a lyophilised vaccine in 5-dose vial,. |  |  |
| • 10% - for a lyophilised/liquid vaccine in 2-dose vial, and. |  |  |
| • 5% - for a liquid vaccine in 1-dose vial. |  |  |
| Vaccine wastage rate; 5%; 10%; 15%; 20%; 25%; 30%; 35%; 40%; 45%; 50%; 55%; 60%. Equivalent wastage factor; 1.05; 1.11; 1.18; 1.25; 1.33; 1.43; 1.54; 1.67; 1.82; 2; 2.22; 2.5. |  |  |
| Vaccine; Vaccine wastage rate; VaccineWastageFactor. MR, 10 dose(s) per vial, LYOPHILISED; 15 %; 1.18. |  |  |
| Table Annex 4E: Vaccine maximum packed volumes. |  |  |
| Vaccine product; Designation; Vaccine formulation; Admin route; No. Of doses in the schedule; Presentation (doses/vial, prefilled); Packed volume vaccine (cm3/dose); Packed volume diluents (cm3/dose). BCG; BCG; lyophilized; ID; 1; 20; 1.2; 0.7. Diphtheria-Tetanus-Pertussis; DTP; liquid; IM; 3; 20; 2.5. Diphtheria-Tetanus-Pertussis; DTP; liquid; IM; 3; 10; 3. Diphtheria-Tetanus; DT; liquid; IM; 3; 10; 3. Tetanus-Diphtheria; Td; liquid; IM; 2; 10; 3. Tetanus Toxoid; TT; liquid; IM; 2; 10; 3. Tetanus Toxoid; TT; liquid; IM; 2; 20; 2.5. Tetanus Toxoid UniJect; TT; liquid; IM; 2; Uniject; 12. Measles; Measles; lyophilized; SC; 1; 1; 26.1; 20. Measles; Measles; lyophilized; SC; 1; 2; 13.1; 13.1. Measles; Measles; lyophilized; SC; 1; 5; 5.2; 7. Measles; Measles; lyophilized; SC; 1; 10; 3.5; 4. Measles-Rubella freeze dried; MR; lyophilized; SC; 1; 1; 26.1; 26.1. Measles-Rubella freeze dried; MR; lyophilized; SC; 1; 2; 13.1; 13.1. Measles-Rubella freeze dried; MR; lyophilized; SC; 1; 5; 5.2; 7. Measles-Rubella freeze dried; MR; lyophilized; SC; 1; 10; 2.5; 4. Measles-Mumps-Rubella freeze dried; MMR; lyophilized; SC; 1; 1; 26.1; 26.1. Measles-Mumps-Rubella freeze dried; MMR; lyophilized; SC; 1; 2; 13.1; 13.1. Measles-Mumps-Rubella freeze dried; MMR; lyophilized; SC; 1; 5; 5.2; 7. Measles-Mumps-Rubella freeze dried; MMR; lyophilized; SC; 1; 10; 3; 4. Polio; OPV; liquid; Oral; 4; 10; 2. Polio; OPV; liquid; Oral; 4; 20; 1. Yellow fever; YF; lyophilized; SC; 1; 5; 6.5; 7. Yellow fever; YF; lyophilized; SC; 1; 10; 2.5; 3. Yellow fever; YF; lyophilized; SC; 1; 20; 1.5; 2. Yellow fever; YF; lyophilized; SC; 1; 50; 0.7; 1. DTP-HepB combined; DTP-HepB; liquid; IM; 3; 1; 9.7. DTP-HepB combined; DTP-HepB; liquid; IM; 3; 2; 6. DTP-HepB combined; DTP-HepB; liquid; IM; 3; 10; 3. Hepatitis B; HepB; liquid; IM; 3; 1; 18. Hepatitis B; HepB; liquid; IM; 3; 2; 13. Hepatitis B; HepB; liquid; IM; 3; 6; 4.5. Hepatitis B; HepB; liquid; IM; 3; 10; 4. Hepatitis B UniJect; HepB; liquid; IM; 3; Uniject; 12. Hib liquid; Hib_liq; liquid; IM; 3; 1; 15. Hib liquid; Hib_liq; liquid; IM; 3; 10; 2.5. Hib freeze-dried; Hib_lyo; lyophilized; IM; 3; 1; 13; 35. Hib freeze-dried; Hib_lyo; lyophilized; IM; 3; 2; 6. Hib freeze-dried; Hib_lyo; lyophilized; IM; 3; 10; 2.5; 3. DTP liquid + Hib freeze-dried; DTP+Hib; liquid+lyop.; IM; 3; 1; 45. DTP-Hib combined liquid; DTP+Hib; liquid+lyop.; IM; 3; 10; 12. DTP-Hib combined liquid; DTP-Hib; liquid; IM; 3; 1; 32.3. DTP-HepB liquid + Hib freeze-dried; DTP-Hib; liquid; IM; 3; 10; 2.5. DTP-HepB liquid + Hib freeze-dried; DTP-HepB+Hib; liquid+lyop.; IM; 3; 1; 22. DTP-HepB-Hib liquid; DTP-HepB+Hib; liquid+lyop.; IM; 3; 2; 11. DTP-HepB-Hib liquid; DTP-HepB-Hib; liquid; IM; 3; 10; 4.4. DTP-HepB-Hib liquid; DTP-HepB-Hib; liquid; IM; 3; 2; 13.1. DTP-HepB-Hib liquid; DTP-HepB-Hib; liquid; IM; 3; 1; 19.2. Meningitis A/C; MV_A/C; lyophilized; SC; 1; 10; 2.5; 4. Meningitis A/C; MV_A/C; lyophilized; SC; 1; 50; 1.5; 3. Meningococcal A/C/W/; MV_A/C/W; lyophilized; SC; 1; 50; 1.5; 3. Meningococcal A/C/W/Y; MV_A/C/W/Y; lyophilized; SC; 1; 10; 2.5; 4. Meningitis W135; MV_W135; lyophilized; SC; 1; 10; 2.5; 4. Meningitis A conjugate; Men_A; lyophilized; SC; 2; 10; 2.6; 4. Japanese Encephalitis; JE_lyo; lyophilized; SC; 3; 10; 15. Japanese Encephalitis; JE_lyo; lyophilized; SC; 3; 10; 8.1; 8.1. Japanese Encephalitis; JE_lyo; lyophilized; SC; 3; 5; 2.5; 2.9. Japanese Encephalitis; JE_lyo; lyophilized; SC; 3; 1; 12.6; 11.5. Japanese Encephalitis; JE_liq; liquid; SC; 3; 10; 3.4. Rota vaccine; Rota_lyo; lyophilized; Oral; 2; 1; 156. Rota vaccine; Rota_liq; liquid; Oral; 2; 1; 17.1. Rota vaccine; Rota_liq; liquid; Oral; 3; 1; 45.9. Pneumo. conjugate vaccine 7-valent; PCV-7; liquid; IM; 3; PFS; 55.9. Pneumo. conjugate vaccine 7-valent; PCV-7; liquid; IM; 3; 1; 21. Pneumo. conjugate vaccine 10-valent; PCV-10; liquid; IM; 3; 1; 11.5. Pneumo. conjugate vaccine 10-valent; PCV-10; liquid; IM; 3; 2; 4.8. Pneumo. conjugate vaccine 13-valent; PCV-13; liquid; IM; 3; 1; 12. Polio inactivated; IPV; liquid; IM; 3; PFS; 107.4. Polio inactivated; IPV; liquid; IM; 3; 10; 2.5. Polio inactivated; IPV; liquid; IM; 3; 1; 15.7. Human Papilomavirus vaccine; HPV; liquid; IM; 3; 1; 15. Human Papilomavirus vaccine; HPV; liquid; IM; 3; 2; 5.7. Monovalent OPV-1; mOPV1; liquid; Oral; 20; 1.5. Monovalent OPV-3; mOPV3; liquid; Oral; 20; 1.5. |  |  |

| 12. Banking Form |  |
| --- | --- |
| In accordance with the decision on financial support made by the GAVI Alliance, the Government of Bangladesh hereby requests that a payment be made via electronic bank transfer as detailed below:. Name of Institution (Account Holder):; Ministry of Health and Family Welfare, Bangladesh. Address:; Bangladesh Secretariat, Dhaka-1000. City Country:; Dhaka, Bangladesh. Telephone no.:; +88-02-7169637; 9880530 (Office); Fax no.:; +88-02-8821914; +88-02-9559216. Currency of the bank account:; USD Account. For credit to:. Bank account's title:; Global Alliance for Vaccines and Immunization (GAVI). Bank account no.:; FCAD 00011. Bank's name:; Sonali Bank, Local Office, 35-44, Motijheel C/A, Dhaka, Bangladesh. |  |
| Is the bank account exclusively to be used by this program? True. |  |
| By who is the account audited? Foreign Aided Project Audit Directorate. |  |
| Signature of Government's authorizing official. |  |
| Seal. Name:; Md. Shafiqul Islam Laskar. Title:; Joint Secretary (PH&WHO), MOH&FW, Bangladesh Secretariat, Dhaka. Signature:. Date:; 28/08/2012. |  |
| FINANCIAL INSTITUTION. Bank Name:; Sonali Bank. Branch Name:; Sonali Bank, Local Office,. Address:; 35-44, Motijheel C/A, Dhaka-1000, Bangladesh. City Country:; Dhaka, Bangladesh. Swift Code:; BSONBDDH. Sort Code:. ABA No.:. Telephone No.:; +88-02-9550426-36; +88-02-9560962. FAX No.:; +88-02-9568002; +88-02-9561410. | CORRESPONDENT BANK. (In the United States). Standard Chatered bank. Trade Services, 1 Evertrust Plaza, Suite 1101, 11th Floor. Jersey City, New Jersey 07302, USA. New Jersey, USA. SCBLUS33. 62621 scbusaui. (023) 420117,. |
| I certify that the account No FCAD 00011 is held by Global Alliance for Vaccines and Immunization (GAVI) at this banking institution. The account is to be signed jointly by at least 2 (number of signatories) of the following authorized signatories:. 1; Name:; Md Shafiqul Islam Lasker. Title:; Joint Secretary (PH&WHO), MOH&FW, Bangladesh Secretariat, Dhaka. 2; Name:; Dr. Md. Tajul Islam A Bari. Title:; Programme Manager-EPI & Surveillance, DGHS, MOH&FW. 3; Name:. Title:. |  |
| Name of bank's authorizing official. Md Kamrul Hasan Bhuiyan. Signature:. Date:; 8/28/2012 12:00:00 AM. Seal:. |  |