|  |  |  |  |  | [V2.7]. |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| GAVI Alliance. |  |  |  |  |  |  |  |
| Application Form for Country Proposals. |  |  |  |  |  |  |  |
| For Support to:. |  |  |  |  |  |  |  |
| Preventive Campaign Support. |  |  |  |  |  |  |  |
| Submitted by. |  |  |  |  |  |  |  |
| The Government of. |  |  |  |  |  |  |  |
| Ghana. |  |  |  |  |  |  |  |
| Date of submission: 8/31/2012. |  |  |  |  |  |  |  |
| Deadline for submission: 8/31/2012. |  |  |  |  |  |  |  |
| Select Start and End Year of your Comprehensive Multi-Year Plan (cMYP). |  |  |  |  |  |  |  |
| Start Year. | 2010. |  |  |  |  |  |  |
|  |  |  | End Year. | 2014. |  |  |  |
| Form revised in 2012. |  |  |  |  |  |  |  |
| (To be used with Guidelines of September 2012). |  |  |  |  |  |  |  |
| Please submit the Proposal using the online platform. https://AppsPortal.gavialliance.org/PDExtranet. |  |  |  |  |  |  |  |
| Enquiries to: proposals@gavialliance.org or representatives of a GAVI partner agency. The documents can be shared with GAVI partners, collaborators and general public. The Proposal and attachments must be submitted in English, French, Spanish, or Russian.. Note: Please ensure that the application has been received by the GAVI Secretariat on or before the day of the deadline.. The GAVI Secretariat is unable to return submitted documents and attachments to countries. Unless otherwise specified, documents will be shared with the GAVI Alliance partners and the general public.. |  |  |  |  |  |  |  |

GAVI ALLIANCE GRANT TERMS AND CONDITIONS. FUNDING USED SOLELY FOR APPROVED PROGRAMMES. The applicant country ("Country") confirms that all funding provided by the GAVI Alliance will be used and applied for the sole purpose of fulfilling the programme(s) described in the Country's application. Any significant change from the approved programme(s) must be reviewed and approved in advance by the GAVI Alliance. All funding decisions for the application are made at the discretion of the GAVI Alliance Board and are subject to IRC processes and the availability of funds.. AMENDMENT TO THE APPLICATION. The Country will notify the GAVI Alliance in its Annual Progress Report if it wishes to propose any change to the programme(s) description in its application.The GAVI Alliance will document any change approved by the GAVI Alliance, and the Country's application will be amended.. RETURN OF FUNDS. The Country agrees to reimburse to the GAVI Alliance all funding amounts that are not used for the programme(s) described in its application. The country's reimbursement must be in US dollars and be provided, unless otherwise decided by the GAVI Alliance, within sixty (60) days after the Country receives the GAVI Alliance's request for a reimbursement and be paid to the account or accounts as directed by the GAVI Alliance.. SUSPENSION/ TERMINATION. The GAVI Alliance may suspend all or part of its funding to the Country if it has reason to suspect that funds have been used for purpose other than for the programmes described in the Country's application, or any GAVI Alliance-approved amendment to the application.The GAVI Alliance retains the right to terminate its support to the Country for the programmes described in its application if a misuse of GAVI Alliance funds is confirmed.. ANTICORRUPTION. The Country confirms that funds provided by the GAVI Alliance shall not be offered by the Country to any third person, nor will the Country seek in connection with its application any gift, payment or benefit directly or indirectly that could be construed as an illegal or corrupt practice.. AUDITS AND RECORDS. The Country will conduct annual financial audits, and share these with the GAVI Alliance, as requested. The GAVI Alliance reserves the right, on its own or through an agent, to perform audits or other financial management assessment to ensure the accountability of funds disbursed to the Country.. The Country will maintain accurate accounting records documenting how GAVI Alliance funds are used. The Country will maintain its accounting records in accordance with its government-approved accounting standards for at least three years after the date of last disbursement of GAVI Alliance funds. If there is any claims of misuse of funds, Country will maintain such records until the audit findings are final. The Country agrees not to assert any documentary privilege against the GAVI Alliance in connection with any audit.. CONFIRMATION OF LEGAL VALIDITY. The Country and the signatories for the Country confirm that its application, and Annual Progress Report, are accurate and correct and form legally binding obligations on the Country, under the Country's law, to perform the programmes described in its application, as amended, if applicable, in the APR.. CONFIRMATION OF COMPLIANCE WITH THE GAVI ALLIANCE TRANSPARANCY AND ACCOUNTABILITY POLICY. The Country confirms that it is familiar with the GAVI Alliance Transparency and Accountability Policy (TAP) and complies with the requirements therein.. USE OF COMMERCIAL BANK ACCOUNTS. The Country is responsible for undertaking the necessary due diligence on all commercial banks used to manage GAVI cash-based support. The Country confirms that it will take all responsibility for replenishing GAVI cash support lost due to bank insolvency, fraud or any other unforeseen event.. ARBITRATION. Any dispute between the Country and the GAVI Alliance arising out of or relating to its application that is not settled amicably within a reasonable period of time, will be submitted to arbitration at the request of either the GAVI Alliance or the Country. The arbitration will be conducted in accordance with the then-current UNCITRAL Arbitration Rules. The parties agree to be bound by the arbitration award, as the final adjudication of any such dispute. The place of arbitration will be Geneva, Switzerland. . The languages of the arbitration will be English or French.. For any dispute for which the amount at issue is US$ 100,000 or less, there will be one arbitrator appointed by the GAVI Alliance. For any dispute for which the amount at issue is greater than US $100,000 there will be three arbitrators appointed as follows: The GAVI Alliance and the Country will each appoint one arbitrator, and the two arbitrators so appointed will jointly appoint a third arbitrator who shall be the chairperson.. The GAVI Alliance will not be liable to the country for any claim or loss relating to the programmes described in the application, including without limitation, any financial loss, reliance claims, any harm to property, or personal injury or death. Country is solely responsible for all aspects of managing and implementing the programmes described in its application..

1. Application Specification. Please specify for which type of GAVI support you would like to apply to..

Type of Support; Vaccine; Start Year; End Year; Preferred second presentation[1]. Preventive Campaign Support; MR, 10 dose(s) per vial, LYOPHILISED; 2013; 2013.

[1] This "Preferred second presentation" will be used in case there is no supply available for the preferred presentation of the selected vaccine ("Vaccine" column). If left blank, it will be assumed that the country will prefer waiting until the selected vaccine becomes available..

Note for HPV and MR: These prices are indicative only as GAVI has not procured HPV and MR vaccines for GAVI countries yet. Prices will be finalised through tender processes in Q3. GAVI will only fund HPV vaccines if an acceptable price reduction is secured from the current price indicated. The MR price is based on the current price to UNICEF.

2. Table of Contents.

1. Application Specification. 2. Table of Contents. 3. Executive Summary. 4. Signatures. 4.1. Signatures of the Government and National Coordinating Bodies. 4.1.1. Government and the Inter-Agency Coordinating Committee for Immunisation. 4.1.2. National Coordinating Body - Inter-Agency Coordinating Committee for Immunisation. 4.1.3. The Inter-Agency Coordinating Committee for Immunisation. 4.2. National Immunization Technical Advisory Group for Immunisation. 4.2.1. The NITAG Group for Immunisation. 5. Immunisation Programme Data. 5.1. Basic facts. 5.1.1 MCV Immunisation coverage. 5.2. Baseline and Annual Targets (NVS Routine Support). 5.3. Baseline and Annual Targets for Preventive Campaign(s). 5.3.1 Baseline and annual targets (MR campaign). 6. New and Under-Used Vaccines (NVS Routine). 7. NVS Preventive Campains. 7.1. Assessment of burden of relevant diseases related to campaigns (if available). 7.2 Requested for MR, 10 dose(s) per vial, LYOPHILISED campaign support. 7.2.1 Summary for MR campaign support. 7.2.2 Grant Support for Operational Costs of the MR Campaign. 7.2.3 Evidence of introduction of RCV in routine programme. 7.2.4 Introduction planning for RCV. 7.2.5 Measles surveillance indicators. 7.2.6 Rubella Containing Vaccine introduction Grant. 8. Procurement and Management. 8.1. Procurement and Management of New and Under-Used Vaccines Routine. 8.2. Procurement and Management for NVS Preventive Campaign(s). 8.2.1 Procurement and Management for MR, 10 dose(s) per vial, LYOPHILISED campaign. 8.3. Vaccine Management (EVSM/EVM/VMA). 9. Additional Comments and Recommendations from the National Coordinating Body (ICC/HSCC). 10. Attachments. 11. Annexes. Annex 1 - NVS Routine Support. Annex 2 - NVS Routine – Preferred Second Presentation. Annex 3 - NVS Preventive campaign(s). Table Annex 3.1 C Summary table for vaccine MR, 10 dose(s) per vial, LYOPHILISED. Table Annex 3.1 D Estimated numbers for MR, 10 dose(s) per vial, LYOPHILISED, associated injection safety material and related co-financing budget (page 1). Annex 4. Table Annex 4A: Commodities Cost. Table Annex 4B: Freight cost as percentage of value. Table Annex 4C: Intermediate - Minimum country's co-payment per dose of co-financed vaccine.. Table Annex 4D: Wastage rates and factors. Table Annex 4E: Vaccine maximum packed volumes. 12. Banking Form.

3. Executive Summary.

Please provide a summary of your country's proposal, including the following the information:. l; For each specific request, NVS routine support or NVS campaign :. ¡; The duration of support. ¡; The total amount of funds. ¡; Details of the vaccine(s), if applicable. l; Relevant baseline data, including:. ¡; DTP3 and Measles coverage data (as reported on the WHO/UNICEF Joint Reporting Form). ¡; Birth cohort, targets and immunisation coverage by vaccines. l; Country preparedness. ¡; Summary of EVM assessment. l; The nature of stakeholders' participation in developing this proposal. ¡; Inter-Agency Coordinating Committee. Ghana has been implementing measles reduction strategies such as strengthening routine immunization, catch up and follow up SIAs and effective surveillance since the late 1990s. These strategies have led to significant reduction in the incidence of morbidity and mortality due to measles in the past 9 years. Suspected cases of measles have reduced significantly and no deaths attributable to measles have been recorded in the country since 2003 after first mass catch-up campaign for children aged 9 months – 14 years in December 2002 (initial phase in Central region,2001) A4-year mass campaign cycle was initially adopted following the 2002 catch-up and subsequent follow-up campaigns have successfully been conducted in 2006 and 2010. However,in 2011, a year after the last measles mass vaccination was held; the country reportedsix (6) measles outbreaks. The 2011 Measles surveillance data also shows that out of 1,744 suspected cases that were reported, 120 (6.8%) were confirmed positive. As of 28th August 2012, about 1,120 suspected cases has been reported out of which 174 (15.5%) have been confirmed positive. There has also been increasing trend of rubella in the country. In 2011, out of a total of 1,600 measles negatives that were tested for rubella, about 582 (36%) were confirmed positive for rubella. Confirmed rubella cases have been increasing over the years from 135 confirmed cases in 2009 to 160 confirmed cases in 2010.Rubella is among the small number of viral diseases considered to be potentially eradicable. As a result, the Government of Ghana has taken the decision to conduct the next round of measles vaccination campaign in 2013 using measles-rubella vaccine. Thecampaign will target all persons aged 1 – 14 years old. A total of 11,571,539 persons have therefore been targeted for the campaign. Measles-Rubella vaccines will subsequently be introduced nationwide into routine immunizationin 2014. Ghana have had a consistently high routine measles vaccination coverage from 93% in 2009 and 2010 and 91% in 2011 as reported in the WHO-UNICEF Estimate. It is hoped that the measles-rubella vaccine will also have this high coverage. Activities to be implemented include micro planning and training at all levels, socialmobilization, logistics distribution and mass vaccination at fixed posts in allcommunities including hard-to-reach areas as well as waste management. The cost of the 7-day exercise (tentatively planned to be conductedin October 2013) is estimated at US$ 19,368,032 which will cover procurement of vaccines and supplies, social mobilization activities, planning and training, health worker incentives and operational costs. The entire cost of all logistics (US$ 11,104,271) will be covered by the Global Alliance for Vaccines and Immunization (GAVI) as well as 91% (US$ 7,521,500) of the cost of operations. The rest of the operational cost (US$ 740,260) is expected to becovered by the Government of Ghana with the support of partners. The campaign will be implemented by the Ministry of Health, coordinated by the ICC through the Expanded Programme on Immunization..

| 4. Signatures. |  |  |
| --- | --- | --- |
| 4.1. Signatures of the Government and National Coordinating Bodies. |  |  |
| 4.1.1. Government and the Inter-Agency Coordinating Committee for Immunisation. |  |  |
| The Government of Ghana would like to expand the existing partnership with the GAVI Alliance for the improvement of the infants routine immunisation programme of the country, and specifically hereby requests for GAVI support for. |  |  |
|  | MR, 10 dose(s) per vial, LYOPHILISED preventive campaigns. |  |
| The Government of Ghana commits itself to developing national immunisation services on a sustainable basis in accordance with the Comprehensive Multi-Year Plan presented with this document. The Government requests that the GAVI Alliance and its partners contribute financial and technical assistance to support immunisation of children as outlined in this application.. |  |  |
| Table(s) in the NVS Routine section of this application shows the amount of support in either supply or cash that is required from the GAVI Alliance. Table(s) of this application shows the Government financial commitment for the procurement of this new vaccine (NVS support only).. |  |  |
| Following the regulations of the internal budgeting and financing cycles the Government will annually release its portion of the co-financing funds in the month of September.. |  |  |
| The payment for the first year of co-financed support will be around September 2013 for MR, 10 dose(s) per vial, LYOPHILISED.. |  |  |
| Please note that this application will not be reviewed or approved by the Independent Review Committee (IRC) without the signatures of both the Minister of Health and Minister of Finance or their delegated authority.. |  |  |
| Minister of Health (or delegated authority); Minister of Finance (or delegated authority). Name; Mr. Alban Sumana Bagbin; Name; Dr Kwabena Duffuor. Date; Date. Signature; Signature. |  |  |
| This report has been compiled by (these persons may be contacted in case the GAVI Secretatiat has queries on this document):. |  |  |
| Full name; Position; Telephone; Email. Dr. Daniel YAYEMAIN; Child Health Specialist, UNICEF-Ghana; +233244606315; dyayemain@unicef.org. Dr. Kwadwo Odei Antwi-Agyei; National EPI Manager/Ghana Health Service; +233244326637; kodeiantwiagyei@gmail.com. Mr. Daniel OSEI; Deputy Director, Planning and Budget, GHS; +233244364221; dan.osei@ghsmail.org. Mr. John Frederick DADZIE; Deputy EPI Manager/Ghana Health Service; +233243206102; jfdadzie@yahoo.co.uk. Mr. Stanley Diamenu; EPI Focal Point/World Health Organization; +233244312896; diamenus@gh.afro.who.int. |  |  |
| 4.1.2. National Coordinating Body - Inter-Agency Coordinating Committee for Immunisation. |  |  |
| We the members of the ICC, HSCC, or equivalent committee [1] met on the 30/08/2012 to review this proposal. At that meeting we endorsed this proposal on the basis of the supporting documentation which is attached.. |  |  |
| [1] Inter-agency Coordinating Committee or Health Sector Coordinating Committee, or equivalent committee which has the authority to endorse this application in the country in question.. |  |  |
| The endorsed minutes of this meeting are attached as document number 4.. |  |  |
| Name/Title*; Agency/Organisation*; Signature. Dr. Frank Nyornator; Ag. Director General/Ghana Health Service. Dr. Iddrissa Sow; Country Representative/World Health Organization. Dr. Iyabode Olusanmi; Country Representative/UNICEF. Dr. Joseph Amankwa; Director of Public Health/Ghana Health Service. Dr. K. O. Antwi-Agyei; EPI Programme Manager, Ghana Health Service. Dr. Victoria Adabayeri; Paediatrician/Paediatric Society of Ghana. Mr. Dan Osei; Ag. Director, PPME/Ghana Health Service. Mr. Sam Worentetu; Chairman/Ghana National Polio Plus Committee of Rotary. |  |  |
| 4.1.3. The Inter-Agency Coordinating Committee for Immunisation. |  |  |
| Agencies and partners (including development partners and NGOs) supporting immunisation services are co-ordinated and organised through an inter-agency coordinating mechanism (ICC, HSCC, or equivalent committee). The ICC, HSCC, or equivalent committee is responsible for coordinating and guiding the use of the GAVI NVS routine support and/or campaign support. Please provide information about the ICC, HSCC, or equivalent committee in your country in the table below.. |  |  |
| Profile of the ICC, HSCC, or equivalent committee. |  |  |
| Name of the committee; EPI Inter-Agency Coordinating Committee. Year of constitution of the current committee; 2001. Organisational structure (e.g., sub-committee, stand-alone); Stand-alone. Frequency of meetings; Quarterly and Emergencies. |  |  |
| Composition. |  |  |
| Function; Title / Organisation; Name. Chair; Ag. Director General, Ghana Health service; Dr. Frank Nyornator. Secretary; EPI Programme Manager, Ghana Health Service; Dr. K. O. Antwi-Agyei. Members; Ag. Director, PPME/Ghana Health Service; Mr. Dan Osei. Director/Disease Control Department; Dr. S. Kyei-Faried. Vitamin A Programme Manager/Nutrition Department; Ms. Esi Foriwaa Amoaful. Paediatrician/Paediatric Society of Ghana; Dr. Victoria M. Adabayeri. EPI Officer/World Health Organization; Mr. Stanley Diamenu. Surveillance Officer/WHO; Dr. Vincent Ahove. Health Desk Officer/USAID; Mrs. Juliana Pwamang. Chairman/Ghana National Polio Plus Committee of Rotary; Mr. Sam Worentetu. Director of Public Health/Ghana Health Service; Dr. Joseph Amankwa. Country Representative/World Health Organization; Dr. Iddrissa Sow. Health Communication Specialist/ Health Promotion Department; Mrs. Eleanor Sey. Vice Chairman/Coalition of NGOs in Health; Mrs. Cecilia Senoo. |  |  |
| Major functions and responsibilities of the ICC/HSCC:. |  |  |
| - To foster solid partnership by collating all available inputs and resources from inside and outside the country in order to maximize resources for the good of the child - Support national level to review and support work plans such as NIDs, EPI annual plans, EPI 5 year plans, surveillance plan etc - Enhance transparency and accountability by reviewing use of funds and other resources together with the EPI Programme at regular intervals - Support and encourage information sharing and feedback at national and or implementing levels within the country and interested partners outside the country - Ensure that the Programme Manager receives both technical and political support that helps to validate his or her authority on issues pertaining to EPI. - Address technical issues as and when they arise such as introduction new antigens, strengthening immunization services etc. |  |  |
| Three major strategies to enhance the committee's role and functions in the next 12 months. |  |  |
| 1.; Refresher orientation ontheir terms of reference and responsibilities: Periodically, the Inter-Agency Coordination Committee is orientated on its terms of reference as the highest decision making body on immunization in Ghana. The opportunity is also taken to through more light on the roles and responsibilities of the ICC.. 2.; Regular update by thetechnical committee on emerging issues: The Technical Sub-committee of the ICC which is composed of the EPI/MOH, UNICEF and WHO periodically update the ICC through quarterly and emergency meetings as well as circulars through the email. This make the ICC abreast with current issues in the programme and advice accordingly.. 3.; Occasional study tour byselected members to other countries: Members of the ICC are often made to go on study tour both within and outside the country to have first hand information on immunization in terms of field practice and policy.. |  |  |
| 4.2. National Immunization Technical Advisory Group for Immunisation. |  |  |
| (If it has been established in the country). |  |  |
| We the members of the NITAG met on the to review this proposal. At that meeting we endorsed this proposal on the basis of the supporting documentation which is attached.. |  |  |
| The endorsed minutes of this meeting are attached as document number 4.. |  |  |

4.2.1. The NITAG Group for Immunisation.

Profile of the NITAG.

Name of the NITAG. Year of constitution of the current NITAG. Organisational structure (e.g., sub-committee, stand-alone). Frequency of meetings.

Composition.

Function; Title / Organisation; Name. Chair. Secretary. Members.

Major functions and responsibilities of the NITAG.

Three major strategies to enhance the NITAG's role and functions in the next 12 months.

1.. 2.. 3..

5. Immunisation Programme Data.

5.1. Basic facts.

Please complete the tables below, using data from available sources. Please identify the source of the data, and the date. Where possible use the most recent data and attach the source document..

▪; Please refer to the Comprehensive Multi-Year Plan for Immunisation (cMYP) (or equivalent plan) and attach a complete copy (with an Executive Summary) as DOCUMENT NUMBER : 6. ▪; Please attach relevant Vaccine Introduction Plans as DOCUMENT NUMBER : 7. ▪; Please refer to the two most recent annual WHO/UNICEF Joint Reporting Forms (JRF) on Vaccine Preventable Diseases. ▪; Please refer to Health Sector Strategy documents, budgetary documents, and other reports, surveys etc, as appropriate..

For the year 2011 (most recent; specify dates of data provided).

Figure; Year; Source. Total population; 24,658,823; 2010; PHC/Ghana Statistical Service. Infant mortality rate (per 1000); 50; 2008; Demographic and Health Survey. Surviving infants[1]; 969,813; 2011; PPME/Ghana Health Service. GNI per capita (US$); 43,980; 2011; World Bank. Total Health Expenditure (THE) as a percentage of GDP; 6; %; 2008; EPI Comprehensive Multi-year Plan. General government expenditure on health (GGHE) as % of General government expenditure; 1; %; 2008; EPI Comprehensive Multi-year Plan.

[1] Surviving infants = Infants surviving the first 12 months of life.

Please provide some additional information on the planning and budgeting context in your country. Until January 2009 there was a five-year planning and budgeting cycle for the health sector which is led by the Minister of Health with the support of health partners. Thefirst Programme of Work (POW) was from 1997-2001. The second POW was from 2002-2006 and the third POW spanned from 2007-2011. However, from January 2009 the planning cycle has been changed to 4 years. Currently, the planning document for health spans from 2010 - 2013.. Please indicate the name and date of the relevant planning document for health. The planning document for health in Ghana is the Health Sector Medium Term Development Plan. The plan is for 2010 - 2013.. Is the CMYP (or updated Multi-Year Plan) aligned with the document (timing, content, etc.). The EPI cMYP (2010 - 2014) is aligned with the Health Sector Medium Term Development Plan (2010 -- 2013), however, the cMYP covers a 5-year period whereas the health sector planning document is for 4 years. With regards to the content, the cMYP has been updated to incorporate the introduction of measles-rubella vaccine for mass vaccination campaign in 2013 and subsequent introduction in routine immunization in 2014. A Mass vaccination campaign with measles only which was planned for 2014 in the cYMP has been cancelled.. Please indicate the national planning budgeting cycle for health. The national planning and budgeting isprepared annually between May - October each year for the ensuing year.. Please indicate the national planning cycle for immunisation. A 5-yearcomprehensive Multi-Year Plan (cMYP) is developed to guide the immunization programme. The current cMYP covers 2010 - 2014. Annual plans are also developed in the last quarter of each year for the ensuing year.. Please indicate if sex disaggregated data (SDD) is used in immunisation routine reporting systems. Sex-disaggregationon immunization data in the routine reporting system is not implemented inGhana. Please indicate if gender aspects relating to introduction of a new vaccine have been addressed in the introduction plan. Yes,this has been considered in the country's introduction plan. With reference tothe Ghana Demographic and Health Survey 2008, there is no disparity for service utilization between the two sex groups as far as immunization is concerned.. Please describe any recent evidence of socio-economic and/or gender barriers to the immunisation programme through studies or surveys?. The Ghana Demographic and Health Survey (2008) shows that there are no barriers to immunization with regards to socio-economic and gender barriers. This is evidenced by the measles coverage of 88.5% for males and 91.7% for females and Penta-1 coverage of 97.9% for males and 98.2% for females in the report. There is also no disparity in immunization rates with regards to mother's education, wealth quintile, region or residence (rural/urban).. Country should provide an outline of all preparatory activities for vaccine(s) introduction. Ghana's outline for all preparatory activities are as follows: - ICC Technical Sub-committee meeting - Preparation of briefing notes for ICC and key stakeholders - Preparation and completion of application documents - Meeting with ICC and HSCC for endorsement - Briefing and subsequent endorsement by MoH and MoFEP - Submission of proposal to GAVI - Formation of Measles-Rubella Introduction Planning Committee and Sub-committees - Sub-committees meetings - Training/Orientation of health workers - Advocacy, Communication and Social mobilization - Press briefing - National Launching - Campaign Implementation - Coverage Survey by Independent monitors - National Review of vaccine introduction - Post-introduction evaluation.

5.1.1 MCV Immunisation coverage.. Please provide information concerning routine immunisation coverage related to measle-containing vaccines (MCV).. Table 5.1.1: MCV Immunisation coverage.. Coverage; 2005; 2006; 2007. Administrative1); WHO/UNICEF2); Administrative1); WHO/UNICEF2); Administrative1); WHO/UNICEF2). Measles 1st dose (%); 83; 83; 85; 85; 89; 95. Measles 2st dose (%); 0; 0; 0; 0; 0; 0. Supplementary Immunization Activities (SIA) (%); 0; 0; 79; 79; 0; 0.. Coverage; 2008; 2009; 2010. Administrative1); WHO/UNICEF2); Administrative1); WHO/UNICEF2); Administrative1); WHO/UNICEF2). Measles 1st dose (%); 86; 86; 89; 93; 88; 93. Measles 2st dose (%); 0; 0; 0; 0; 0; 0. Supplementary Immunization Activities (SIA) (%); 0; 0; 0; 0; 93; 93.. Coverage; 2011. Administrative1); WHO/UNICEF2). Measles 1st dose (%); 88; 91. Measles 2st dose (%); 0; 0. Supplementary Immunization Activities (SIA) (%); 0; 0.... Note:. 1)National reported Administrative Coverage. 2)WHO/UNICEF estimated coverage. Was the last Measles Supplementary Immunization Activities (SIA) administrative coverage or results of a survey of acceptable methodology Results of a survey. Please describe survey methodology:. The study wascross-sectional in approach and had children 9 months – 59 months as theprimary study population and caregivers of these children as the second studypopulation. Cluster sampling method was used to select the clusters and simplerandom sampling was used for the selection of houses (or households). Data wascollected through interviews using structured interview guide and observation(finger marking). Qualityassurance was ensured through: A 3-day training of monitors, data collectors and supervisors Pre-testing of the data collection tools Two monitors/data collectors per team Field supervision of data collectors Out of 4,288 children studied, 4,025 (93.9%) were vaccinated (evidenced by finger marking)....

5.2. Baseline and Annual Targets (NVS Routine Support)

No NVS Routine Support is requested.

| 5.3. Baseline and Annual Targets for Preventive Campaign(s).. |  |
| --- | --- |
| 5.3.1 Baseline and annual targets (MR campaign). Please specify cohort for rubella-containing vaccines (RCV):. RCV Start 1 year. RCV End 14 years. Cohort population = population 1 year - 14 years old. GAVI supports no more than 15 cohorts. If the application is not within 9 months to 15 years, please provide justification. Ghana's application is within GAVI's cohort... Table 5.3.1 Baseline NVS preventive campaign figures for MR.. Number; Base Year; Baseline and Targets. 2010; 2013. Total births; 998,698; 1,090,948. Total population 1 year - 14 years old; 4,317,817; 11,571,539. Target population vaccinated with MR; 4,002,842; 11,571,539. MR (campaign) coverage (%) [1]; 92.71 %; 100.00 %. Wastage rate in base year and thereafter (%) for MR (campaign); 4; 10. Wastage factor in base year and thereafter for MR; 1.04; 1.11.. [1] Number of persons vaccinated out of total births... |  |

6. New and Under-Used Vaccines (NVS Routine)

No NVS Routine Support is requested.

7. NVS Preventive Campains

7.1. Assessment of burden of relevant diseases related to campaigns (if available).

Disease; Title of the assessment; Date; Results. Rubella; Fever-Rash Surveillance System in Ghana; 2003 - 2006; Out of a total of 1,479 suspected cases, 462 were confirmed as rubella. The disease mostly affect children aged 1 - 4 years, followed by 5 - 9 years and then 10 - 14 years. Incidence is usually highest n the first half of the year.. Rubella; Seroprevalence Study; 2003; Out of 2,704 pregnant women who were tested for rubella, 2,504 (92.6%) were positive. Rubella seropositivity was highest among pregnant women aged 35 years and above. Followed by 30-34 years group, then, 25-29 years group, then 20-24 and finally, 15-19 years group.. Rubella; Congenital Rubella Syndrome Study; 2004 - 2006; The study showed minimum incidence of 0.4/1000 live births among 128 infants who were enrolled.. Measles; Measles Surveillance; Jan 2012 - 28 August 2012; A total of 1,120 suspected measles cases have been reported out of which 174 (15.5%) have been confirmed as positive.. Measles; Measles Surveillance; Jan 2011 - Dec 2011; A total of 1,744 suspected measles cases were reported out of which 120 (6.8%) were confirmed as positive..

If MR vaccines have already been introduced in your country during campaigns, please give details of the lessons learned from previous introduction(s) specifically for: storage capacity, protection from accidental freezing, staff training, cold chain, logistics, coverage and drop-out rates, wastage rate, etc., and suggest action points to address them..

Lessons Learned; Action Points. Storage Capacity The expansion of the cold chain capacity at regional (walk-in-cold-room for every region) and district (TCW 3000 for almost all districts) levels ensured sufficient storage capacity for the vaccine ordered.; There is need to conduct cold chain inventory nationwide and cold chain capacity assessment in health facilities to assess the available storage capacity. Training Standardized training materials as well as field guide proved very useful in the preparation of health workers for the 2010 Measles Campaign; Guidelines should be prepared, printed and ready to be distributed before vaccine arrives in the country. Intensive training of staff will be required (vaccine administration, injection safety, data management, AEFI, cold chain). Logistics The Logistics Sub-committee set up at all levels ensured that all logistics were distributed to the periphery before the start of the 2010 Measles campaign; Logistics sub-committees will be constituted at all levels to develop logistics distribution plan to ensure successful and timely delivery of all logistics. Coverage Regular monitoring and supervision ensured quality data and coverage; Plans to monitor and supervise all levels should be put in place prior to the campaign. Public education and communication Sufficient sensitization provided adequate public education for the measles campaign. Fact sheets/fliers and posters were provided to all concerned.; Health educational and promotional activities should be well planned and implemented prior to new vaccine introduction. Take home information for parents, caregivers and all stakeholders should be provided. Committed staff Strong national, regional and district levels staff commitment contributed to the success of the campaign; Must have an incentive scheme for the health workers to boost morale and motivate them. Political Support Strong political support led to a successful implementation of the campaign. Political leaders used multiple public fora to create awareness; Enlist support from political leaders and major stakeholders before the new vaccines are introduced. Surveillance Strong surveillance system with lab component strengthened. Adverse Event Following Immunization (AEFI) surveillance activities were intensified to detect and investigate all cases; AEFI surveillance must also be strengthened.

7.1.1 Epidemiology and disease burden for Measles-Rubella. Please select at least one of the following information sources to justify RCV diseases burden results:. Epidemiological information on burden of disease:. þ; 1 - Rubella data from the measles case-based surveillance system (including the age distribution of rubella cases). þ; 2 - Rubella seroprevalence surveys. þ; 3 - Congenital Rubella Syndrome (CRS) burden information, e.g. retrospective search, modelled estimates for CRS burden, prospective surveillance. o; 4 - Other.

7.2.Requested for MR, 10 dose(s) per vial, LYOPHILISED campaign support. 7.2.1. Summary for MR campaign support. Please give a summary of the cMYP and/or the MR, 10 dose(s) per vial, LYOPHILISED campaign introduction plan sections that refer to the introduction of MR, 10 dose(s) per vial, LYOPHILISED campaign. Outline the key points that informed the decision-making process (data considered etc):. Ghana planned to conduct nationwide measles supplementaryimmunization activity in 2014 as contained in the countries Measles ControlStrategic Plan. However, current data has informed the decision to conductmeasles campaign in 2013 instead of 2014. In 2011, a year after the lastmeasles mass vaccination was held; the country reported six (6) measlesoutbreaks. The 2011 Measles surveillance data also shows that out of 1,744suspected cases that were reported, 120 (6.8%) were confirmed positive. As of 28th August 2012, about 1,120 suspected cases has been reported outof which 174 (15.5%) have been confirmed positive. <?xml:namespace prefix = o /> There has also been increasing trend of rubella in thecountry. In 2011, out of a total of 1,600 measles negatives that were testedfor rubella, about 582 (36%) were confirmed positive for rubella. Confirmedrubella cases have been increasing over the years from 135 confirmed cases in2009 to 160 confirmed cases in 2010. Rubella is among the small number of viraldiseases considered to be potentially eradicable. With the successful introduction of Pneumococcal conjugateand Rotavirus vaccines in May 2012, Ghana has again taken another bold decisionto introduce Measles-Rubella vaccine to replace the measles vaccine. Theintroduction into routine immunization will be preceded by mass immunizationcampaign in 2013 for children aged 1-14 years old. The decision taken by the technical committee of the ICC on 29th August 2012 at the WHO Country Office was based on the reviewof surveillance data since 2003 and the report of the sero-prevalence and CRS studies conducted in the country. It also considered the WHO Africa Region’srecommendation for Ghana to consider introducing the measles rubella vaccine. Please summarise (1) the waste management plan and (2) the cold chain capacity and readiness to accommodate new vaccines, stating how the cold chain expansion (if required) will be financed, and when it will be in place.Please indicate if the supplies for the campaign will have any impact in the shipment plans for your routine vaccines and how it will be handled:. Injection safety and wastage management - Training ofvaccinators (health workers) and support staff (assistant of vaccinator) willinclude the use and safe disposal of injection materials and the detection andmanagement of AEFI including anaphylactic shock. Only AD syringes with safety boxes will beused during the campaign and each vaccination site will be equipped withemergency kits including adrenalin and hydrocortisone. Hub-cutters will also be used to defang the hub of syringes into acompact container to reduce risk. The waste will be incinerated in theincinerators (De-Monfort) at the district level. All safety boxes shall becollected at the end of each session to the district level for incineration.The country has procured 20 mobile incinerators and have distributed to districts to support the management of injection waste<?xml:namespace prefix = o /> Cold Chain capacity - The current cold chain capacity in thecountry is adequate to support the Measles-Rubella Campaign. Cold chain capacity atthe national level is adequate to take vaccines and distribute to regions. Thesub-national cold room is the Northern Region has adequate capacity for thevaccines. Walk-in-cold-rooms with capacity of 30,000 litres have also been installed for all regions. TCW 3000 has been providedto almost every district level in the country. Health facilities are also usingTCW 2000 for vaccine storage. There are plans to procure cold boxes and vaccinecarriers to improve vaccine management in the country. The supplies for the campaign will be adequately stored without any negative impact on routine vaccines... 7.2.2. Grant Support for Operational Costs of the MR Campaign.. Please indicate in the tables below how the support Grant [1] will be used to support the operational costs of the campaign and other critical pre-introduction activities. GAVI's support may not be enough to cover the full needs so please indicate in the table below how much and who will be complementing the funds needed (refer to the cMYP and the MR, 10 dose(s) per vial, LYOPHILISED campaign introduction plan)... Table 7.2.2: calculation of grant to support the operational costs of the campaigns.. Year of MR support; Target population vaccinated (from Table 5.3); Share per population 1 year-14 years old in US$; Total in US$. 2013; 11,571,539; 0.65; 7,521,500.. [1] The Grant will be based on a maximum award of $0.65$ per cohort population.. Cost (and finance) of the MR, 10 dose(s) per vial, LYOPHILISED campaign US$.. Cost Category Full needs for new vaccine introduction in US$; Funded with GAVI introduction grant in US$. 2013; 2013. Training; 516,422; 516,422. Social Mobilization, IEC and advocacy; 179,952; 179,952. Cold Chain Equipment & Maintenance; 52,083; 40,453. Vehicles and Transportation; 720,214; 0. Programme Management; 41,615; 41,615. Surveillance and Monitoring; 174,271; 174,271. Human Resources; 4,424,427; 4,424,427. Waste Management; 1,033,173; 1,033,173. Technical Assistance; 5,208; 5,208. Planning; 109,104; 109,104. Volunteer incentives; 5,208; 0. Other (please specify). Printing of vaccination cards; 937,500; 937,500. Printing of data collection tools; 59,375; 59,375. Printing of field guide and final report; 5,209; 0. Total; 8,263,761; 7,521,500..... Please describe others sources of funding if available to cover your full needs.. As indicated in Table 7.2.2, GAVI will contribute US$ 7,521,500.00 whilst the Government ofGhana, with support of partners in the country will contribute the remainingtotal of US$ 742,260.40 <?xml:namespace prefix = o />COMMENT FOR VIG (section 7.2.6) The rest of the cost of the new vaccine introduction (US$ 148,075) will be covered by the Government of Ghana with the support of partners... 7.2.3 Evidence of introduction of RCV in routine programme.. Please provide evidence that the country can finance the introduction of Rubella-Containing-Vaccine (RCV) into the routine programme through one of the following:.. o; 1 - A commercial contract for purchase of MR/MMR (Meales Rubella/Meales Mumps Rubella) vaccine together with shipping documents, invoice, etc.. þ; 2 - Proof that RCV has been integrated into the cMYP with the budget line for vaccines increased to include purchase of RCV as part of the health sector budget to indicate that RCV funds are allocated. o; 3 - A letter from the Minister of Finance or Budget ensuring additional funding for RCV purchase. o; 4 - An MOU between government and donor(s) (or other written document that proves donor commitment) for at least one year for purchase of RCV for use in the routine programme. þ; 5 - Other.. Document N°.. Please briefly describe the document used as evidence:.. The Measles-Rubella Introduction Plan describes how the MR campaign will be conducted and the subsequent introduction of MR into routine immunization from 2014... 7.2.4 Introduction planning for RCV.. Countries should describe their plan for introduction including surveillance activities:.. Does Ghana’s cMYP include a plan for the introduction of RCV into the national programme? Yes.. Please describe a Plan Of Action (POA) for the introduction of RCV into the national programme or provide the POA as an attachment - Refer to section 10. Attachments. (Document N° ).. In order toachieve successful campaign and subsequent introduction into the routineimmunization programme,the following strategies and activities will beimplemented: <?xml:namespace prefix = o /> 1. Highadvocacy and social mobilization for effective partnership, collaboration andpublic support 2. Formation of Planning Committee and sub-committees 3. Developmentof data collection tools (tally sheets, summary sheet, rapid convenientmonitoring, summary of rapid convenient monitoring, AEFI forms etc.) andreference materials 4. Orientationof staff on the new vaccine, immunization safety and waste management 5. Upgrading ofcold storage capacity in the regions to accommodate required vaccines 6. Forecastingand availability of vaccines in the regions 7. Surveillanceto show impact of the preventive campaign and monitoring of adverse effects following immunization (AEFI) 8. Monitoringand evaluation for information for corrective measures and future decision onthe immunization programme......

INSTRUCTIONS. Components of the POA/cMYP should include:. a. Comprehensive vaccination strategy for the introduction of RCV including a description of:. i. Initial Measles and rubella (MR) campaign. ii. Replacing Measles containing vaccine (MCV) with Measles and rubella (MR) / Measles, mumps, and rubella (MMR) in the routine childhood vaccination programme. iii. Strategies for targeting Women of Childbearing Age (WCBA), such as vaccination during routine services, post-partum, at 1st well baby visit, SIAs. iv. Linkage to the current routine immunisation schedule. v. Linkage to measles second dose, if applicable. vi. Description of how the country plans to continue to maintain high MR/MMR vaccine coverage either through routine immunisation or through Supplementary Immunization Activities (SIAs). b. A brief description of the following surveillance activities:. i. Integration of Rubella surveillance with case-based measles surveillance. ii. Congenital Rubella Syndrome (CRS) surveillance or plans to establish sentinel site CRS surveillance. iii. Adverse Event Following Immunization (AEFI) surveillance. c. Vaccine coverage monitoring and reporting. d. The communication strategy for the introduction of RCV.. 7.2.5 Measles surveillance indicators.. Please provide information on the following indicators of the quality of measles surveillance for at least two years prior to application (if available):.. Surveillance indicator; 2010; 2011. Reporting rate at national level 1); 2; 6. 100,000; 100,000. Laboratory confirmation rate (%) 2).. Note:. 1) Reporting rate at national level = number of discarded measles cases per 100,000 population per year. 2) Laboratory confirmation rate (%) = number of suspected cases with specimens collected for testing divided by the number of suspected cases not confirmed through epidemiological linkage.....

7.2.6 Rubella Containing Vaccine introduction Grant.. Has a Rubella Containing vaccine already been introduced nationally on a routine basis? No.. Calculation of lump-sum for the MR, 10 dose(s) per vial, LYOPHILISED.. Please indicate in the tables below how the one-time Introduction Grant[1] will be used to support the costs of vaccine introduction and critical pre-introduction activities (refer to the cMYP). GAVI’s support may not be enough to cover the full needs so please indicate in the table below how much and who will be complementing the funds needed... Year of New Vaccine Introduction; Births (From Table 5.3); Share per Birth in US$; Total in US$. 2013; 1,090,948; 0.80; 872,758.. [1] The Grant will be based on a maximum award of $0.80 per infant in the birth cohort with a minimum starting grant award of $100,000.. Cost (and finance) to introduce the MR, 10 dose(s) per vial, LYOPHILISED US$.. Cost Category Full needs for new vaccine introduction in US$; Funded with GAVI introduction grant in US$. Training; 260,417; 260,417. Social Mobilization, IEC and advocacy; 104,167; 104,167. Cold Chain Equipment & Maintenance; 26,042; 26,042. Vehicles and Transportation; 104,167; 0. Programme Management; 26,042; 0. Surveillance and Monitoring; 104,167; 104,167. Human Resources; 260,417; 260,417. Waste Management; 52,083; 52,083. Technical Assistance; 5,208; 0. Other (please specify). Planning; 52,083; 52,083. Printing of manual and final report; 26,042; 13,382. Total; 1,020,835; 872,758..........

8. Procurement and Management.

8.1. Procurement and Management of New and Under-Used Vaccines Routine.

No NVS Routine Support is requested.

8.2. Procurement and Management for NVS Preventive Campaign(s).

8.2.1. Procurement and Management for MR, 10 dose(s) per vial, LYOPHILISED campaign. a) Please show how the support will operate and be managed including procurement of vaccines (GAVI expects that countries will procure vaccine and injection supplies through UNICEF):. Ghanaoperates the bundling system. All vaccines and other injection supplies are procuredfor Government by UNICEF. Just as the old vaccines, procurement of the MR vaccine will also be done through the existing system.. b) Please indicate when you are planning to conduct the campaign (month and year) and how the campaign is going to be rolled out (e.g. in different phases or one time).. The campaignis scheduled for 6th – 9th November 2013 nationwide andall persons within the age group of 1 – 14 years will be vaccinated. Subsequentlywe plan to periodically vaccinate children 1 – 4 years in a campaign mode every3 or 4 years depending on surveillance data. The Government of Ghana willintroduce MR vaccine into the routine immunization in 2014.. c) Please outline how coverage of the new vaccine will be monitored and reported (refer to the cMYP and/or the MR, 10 dose(s) per vial, LYOPHILISED campaign introduction plan). The MR vaccinewill be used to conduct nationwide mass campaign. During the campaign, dailyreporting teams will be set-up at all levels (National, regional, district andsub-district) who will collate and report data to the next higher level. Adaily reporting template will be developed by the National EPI Sub-TechnicalCommittee and will be shared with all levels. The daily reporting template willbe designed to capture all information on tally sheet book which will also be developedand used by vaccinators at vaccination points. For routineimmunization with MR, the coverage data will be captured as part of theexisting system..

8.3. Vaccine Management (EVSM/EVM/VMA).

Did the country have Effective Vaccine Management Assessment (VMA) in the past? Yes. When was the last VMA conducted? May 2001. Did the country have Effective Vaccine Store Management (EVSM) in the past? No. Did the country have Effective Vaccine Management (EVM) in the past? Yes. When was the EVM conducted? September 2010. If your country conducted either EVSM or VMA in the past two years, please attach relevant reports. (Document N°13). A VMA report must be attached from those countries which have introduced a New and Underused Vaccine with GAVI support before 2008.. Please note that Effective Vaccine Store Management (EVSM) and Vaccine Management Assessment(VMA) tools have been replaced by an integrated Effective Vaccine Management (EVM) tool. The information on EVM tool can be found at http://www.who.int/immunization_delivery/systems_policy/logistics/en/index6.html. For countries which conducted EVSM, VMA or EVM in the past, please report on activities carried out as part of either action plan or improvement plan prepared after the EVSM/VMA/EVM.. - Goal – to improve on the vaccine and cold chain capacity in the country as recommended by the assessment report. - Main objective – to achieve the standard EVM scores of 80% and above for all indicators at all levels - Strategies · Cascadedtraining for staff at all levels in the regions · Coldchain storage expansion in all regions and some districts · Replacementof cold chain equipment at all levels in the regions · Regularmonitoring and supportive supervision. Does the country plan to conduct an Effective Vaccine Management (EVM) Assessment in the future? Yes. When is the next Effective Vaccine Management (EVM) Assessment planned? June 2013. Under new guidelines, it will be mandatory for the countries to conduct an EVM prior to an application for introduction of new vaccine..

9. Additional Comments and Recommendations from the National Coordinating Body (ICC/HSCC).

Comments and Recommendations from the National Coordinating Body (ICC/HSCC).

We, themembers of the ICC endorse the Measles-Rubella Vaccine Application. We hopethat the campaign planned for 2013 with this vaccine will help reduce thethreat of measles and put the country on the right path to eradicate rubella inthe country and subsequently improve the health status of children and for thatmatter, the entire country..

10. Attachments.

10.1. List of documents attached to this proposal.

Document Number; Document; Section; Mandatory; File. Signature of MoH (Chief Director).pdf. 1; MoH Signature (or delegated authority) of Proposal; File desc: Signature of the Chief Director of the Ministry of Health. Date/time: 8/31/2012 11:40:11 AM. Size: 755977. Signature of MoH & MoFEP.pdf. 2; MoF Signature (or delegated authority) of Proposal; File desc:. Date/time: 9/17/2012 11:15:15 AM. Size: 765500. Signatures of ICC.pdf. 3; Signatures of ICC or HSCC or equivalent in Proposal; File desc: The signature of members of the ICC endorsing the Measles-Rubella application. Date/time: 8/31/2012 8:20:38 AM. Size: 1338150. Minutes ICC_30 08 12_GHS.pdf. 4; Minutes of ICC/HSCC meeting endorsing Proposal; File desc: Minutes of the Emergency ICC meeting where the Measles-Rubella Application was discussed and endorsed. Date/time: 8/31/2012 11:43:50 AM. Size: 1351485. Revised cMYP 2010 - 2014_MS Word (2011)_Revised August 12.doc. 5; comprehensive Multi Year Plan - cMYP; File desc: The EPI cMYP 2010 - 2014 revised to include the Measles-Rubella campaign in 2013 and introduction into routine in 2014. Date/time: 8/31/2012 8:24:53 AM. Size: 1154048. Revised Ghana cMYP_Costing_Tool_Vs.2.5_ver1.0_MR_160812.xlsm. 6; cMYP Costing tool for financial analysis; File desc: This is an excel tool for costing immunizations in Ghana. Measles-Rubella campaign and introduction into routine immunization has been factored in it. Date/time: 8/31/2012 9:25:14 AM. Size: 1556930. Plan for New Vaccine Support for Measles-Rubella Vaccine 2014.doc. 7; Plan for NVS introduction (if not part of cMYP); 5.1; File desc: This is the Introduction Plan for Measles-Rubella Vaccine into routine immunization. Date/time: 8/31/2012 10:47:25 AM. Size: 635392. Status of Implementation of EVM Improvement Plan.docx. 8; Improvement plan based on EVM; File desc: Document describes the status of implementation of the recommendations of the EVM conducted in the country in 2010. Date/time: 8/31/2012 9:22:06 AM. Size: 15520. EPI_Log_Forecasting_Tool_26-Apr-11_Current_220812.xls. 11; Evidence of introduction of RCV in routine programme; 7.c.3; File desc: Measles-Rubella vaccine has been factored in the logistics forecasting tool. Date/time: 8/31/2012 11:01:45 AM. Size: 4383744. Measles-Rubella Campaign Plan 2013.doc. 12; Plan Of Action for RCV introduction; 7.c.4; File desc: Plan for MR Campaign. Date/time: 8/31/2012 11:04:20 AM. Size: 486912.

11. Annexes.

Annex 1 - NVS Routine Support.

No NVS Routine Support is requested.

Annex 2 - NVS Routine – Preferred Second Presentation.

No NVS Routine – Preferred Second Presentation requested this year.

Annex 3 - NVS Preventive campaign(s)... Annex 3.1 - NVS Preventive campaign(s) (MR, 10 dose(s) per vial, LYOPHILISED). Table Annex 3.1 C: Summary table for CAMPAIGN MR, 10 dose(s) per vial, LYOPHILISED.. Data from; 2013. Total campaign population; Table 5.3.1; #; 11,571,539. Immunization coverage; Table 5.3.1; %; 100.00 %. Number of persons to be vaccinated; Table 5.3.1; #; 11,571,539. Number of doses per persons; Parameter; #; 1. Estimated vaccine wastage factor; Table 5.3.1; #; 1.11. Number of doses per vial; Parameter; #; 10. AD syringes required; Parameter; #; Yes. Reconstitution syringes required; Parameter; #; Yes. Safety boxes required; Parameter; #; Yes. Vaccine price per dose; Table Annexes 4A; $; 0.494. AD syringe price per unit; Table Annexes 4A; $; 0.0465. Reconstitution syringe price per unit; Table Annexes 4A; $; 0.0037. Safety box price per unit; Table Annexes 4A; $; 0.0058. Freight cost as % of vaccines value; Table Annexes 4B; %; 13.00 %. Freight cost as % of devices value; Parameter; %; 0...

Table Annex 3.1 D: Estimated number of MR, 10 dose(s) per vial, LYOPHILISED associated injection safety material and related co-financing budget (page 1). Formula; GAVI. 2013. B; Number of persons to be vaccinated with the first dose; 11,571,539. C; Number of doses per persons; 1. D; Number of doses needed; B x C; 11,571,539. E; Estimated vaccine wastage factor; Wastage factor table; 1.11. F; Number of doses needed including wastage; D x E; 12,844,409. G; Vaccines buffer stock; (F – F of previous year) * 0.25; 3,211,103. I; Total vaccine doses needed; F + G; 16,055,512. J; Number of doses per vial; Vaccine parameter; 10. K; Number of AD syringes (+ 10% wastage) needed; (D + G) x 1.11; 16,408,733. L; Reconstitution syringes (+ 10% wastage) needed; I / J * 1.11; 1,782,162. M; Total of safety boxes (+ 10% of extra need) needed; (K + L) /100 * 1.11; 201,919. N; Cost of vaccines needed; I x g; 0.494. O; Cost of AD syringes needed; K x ca; 763,006.0845. P; Cost of reconstitution syringes needed; L x cr; 6,594. Q; Cost of safety boxes needed; M x cs; 1,172. R; Freight cost for vaccines needed; N x fv; 0. S; Freight cost for devices needed; (O+P+Q) x fd; 0. T; Total fund needed; (N+O+P+Q+R+S); 8,702,195.0845... Note: There is no cofinancing for NVS preventive campaigns...

| Annex 4. |  |  |
| --- | --- | --- |
| Table Annex 4A: Commodities Cost. |  |  |
| Vaccine; Presentation; 2013; 2014; 2015; 2016. DTP-HepB, 10 dose(s) per vial, LIQUID; 10. DTP-HepB-Hib, 1 dose(s) per vial, LIQUID; 1; 2.017; 1.986; 1.933; 1.927. DTP-HepB-Hib, 10 dose(s) per vial, LIQUID; 10; 2.017; 1.986; 1.933; 1.927. DTP-HepB-Hib, 2 dose(s) per vial, LYOPHILISED; 2; 2.017; 1.986; 1.933; 1.927. HPV bivalent, 2 dose(s) per vial, LIQUID; 2; 5.000; 5.000; 5.000; 5.000. HPV quadrivalent, 1 dose(s) per vial, LIQUID; 1; 5.000; 5.000; 5.000; 5.000. Measles, 10 dose(s) per vial, LYOPHILISED; 10; 0.242; 0.242; 0.242; 0.242. Meningogoccal, 10 dose(s) per vial, LIQUID; 10; 0.520; 0.520; 0.520; 0.520. MR, 10 dose(s) per vial, LYOPHILISED; 10; 0.494; 0.494; 0.494; 0.494. Pneumococcal (PCV10), 2 dose(s) per vial, LIQUID; 2; 3.500; 3.500; 3.500; 3.500. Pneumococcal (PCV13), 1 dose(s) per vial, LIQUID; 1; 3.500; 3.500; 3.500; 3.500. Rotavirus, 2-dose schedule; 1; 2.550; 2.550; 2.550; 2.550. Rotavirus, 3-dose schedule; 1; 3.500; 3.500; 3.500; 3.500. Yellow Fever, 10 dose(s) per vial, LYOPHILISED; 10; 0.900; 0.900; 0.900; 0.900. Yellow Fever, 5 dose(s) per vial, LYOPHILISED; 5; 0.900; 0.900; 0.900; 0.900. |  |  |
| Note for HPV and MR: These prices are indicative only as GAVI has not procured HPV and MR vaccines for GAVI countries yet. Prices will be finalised through tender processes in Q3. GAVI will only fund HPV vaccines if an acceptable price reduction is secured from the current price indicated. The MR price is based on the current price to UNICEF. |  |  |
| Supply; Form; 2013; 2014; 2015; 2016. AD-SYRINGE; SYRINGE; 0.047; 0.047; 0.047; 0.047. RECONSTIT-SYRINGE-PENTAVAL; SYRINGE; 0.047; 0.047; 0.047; 0.047. RECONSTIT-SYRINGE-YF; SYRINGE; 0.004; 0.004; 0.004; 0.004. SAFETY-BOX; SAFETYBOX; 0.006; 0.006; 0.006; 0.006. |  |  |
| Note: WAP - weighted average price (to be used for any presentation: For DTP-HepB-Hib, it applies to 1 dose liquid, 2 dose lyophilised and 10 dose liquid. For Yellow Fever, it applies to 5 dose lyophilised and 10 dose lyophilised). |  |  |
| Table Annex 4B: Freight cost as percentage of value. |  |  |
| Vaccine Antigen; Vaccine Type; No Threshold; 500,000$. <=; >. DTP-HepB; HEPBHIB; 2.00 %. DTP-HepB-Hib; HEPBHIB; 23.80 %; 6.00 %. HPV bivalent; HPV; 3.50 %. HPV quadrivalent; HPV; 3.50 %. Measles; MEASLES; 14.00 %. Meningogoccal; MENINACONJUGATE; 10.20 %. MR; MR; 13.20 %. Pneumococcal (PCV10); PNEUMO; 3.00 %. Pneumococcal (PCV13); PNEUMO; 6.00 %. Rotavirus; ROTA; 5.00 %. Yellow Fever; YF; 7.80 %. |  |  |
| Table Annex 4C: Intermediate - Minimum country's co-payment per dose of co-financed vaccine.. |  |  |
| Vaccine. |  |  |
| Table Annex 4D: Wastage rates and factors. |  |  |
| Countries are expected to plan for a maximal wastage rate of:. |  |  |
| • 50% - for a lyophilised vaccine in 10 or 20-dose vial,. |  |  |
| • 25% - for a liquid vaccine in 10 or 20-dose vial or a lyophilised vaccine in 5-dose vial,. |  |  |
| • 10% - for a lyophilised/liquid vaccine in 2-dose vial, and. |  |  |
| • 5% - for a liquid vaccine in 1-dose vial. |  |  |
| Vaccine wastage rate; 5%; 10%; 15%; 20%; 25%; 30%; 35%; 40%; 45%; 50%; 55%; 60%. Equivalent wastage factor; 1.05; 1.11; 1.18; 1.25; 1.33; 1.43; 1.54; 1.67; 1.82; 2; 2.22; 2.5. |  |  |
| Vaccine; Vaccine wastage rate; VaccineWastageFactor. MR, 10 dose(s) per vial, LYOPHILISED; 4%; 1.04. |  |  |
| Table Annex 4E: Vaccine maximum packed volumes. |  |  |
| Vaccine product; Designation; Vaccine formulation; Admin route; No. Of doses in the schedule; Presentation (doses/vial, prefilled); Packed volume vaccine (cm3/dose); Packed volume diluents (cm3/dose). BCG; BCG; lyophilized; ID; 1; 20; 1.2; 0.7. Diphtheria-Tetanus-Pertussis; DTP; liquid; IM; 3; 20; 2.5. Diphtheria-Tetanus-Pertussis; DTP; liquid; IM; 3; 10; 3. Diphtheria-Tetanus; DT; liquid; IM; 3; 10; 3. Tetanus-Diphtheria; Td; liquid; IM; 2; 10; 3. Tetanus Toxoid; TT; liquid; IM; 2; 10; 3. Tetanus Toxoid; TT; liquid; IM; 2; 20; 2.5. Tetanus Toxoid UniJect; TT; liquid; IM; 2; Uniject; 12. Measles; Measles; lyophilized; SC; 1; 1; 26.1; 20. Measles; Measles; lyophilized; SC; 1; 2; 13.1; 13.1. Measles; Measles; lyophilized; SC; 1; 5; 5.2; 7. Measles; Measles; lyophilized; SC; 1; 10; 3.5; 4. Measles-Rubella freeze dried; MR; lyophilized; SC; 1; 1; 26.1; 26.1. Measles-Rubella freeze dried; MR; lyophilized; SC; 1; 2; 13.1; 13.1. Measles-Rubella freeze dried; MR; lyophilized; SC; 1; 5; 5.2; 7. Measles-Rubella freeze dried; MR; lyophilized; SC; 1; 10; 2.5; 4. Measles-Mumps-Rubella freeze dried; MMR; lyophilized; SC; 1; 1; 26.1; 26.1. Measles-Mumps-Rubella freeze dried; MMR; lyophilized; SC; 1; 2; 13.1; 13.1. Measles-Mumps-Rubella freeze dried; MMR; lyophilized; SC; 1; 5; 5.2; 7. Measles-Mumps-Rubella freeze dried; MMR; lyophilized; SC; 1; 10; 3; 4. Polio; OPV; liquid; Oral; 4; 10; 2. Polio; OPV; liquid; Oral; 4; 20; 1. Yellow fever; YF; lyophilized; SC; 1; 5; 6.5; 7. Yellow fever; YF; lyophilized; SC; 1; 10; 2.5; 3. Yellow fever; YF; lyophilized; SC; 1; 20; 1.5; 2. Yellow fever; YF; lyophilized; SC; 1; 50; 0.7; 1. DTP-HepB combined; DTP-HepB; liquid; IM; 3; 1; 9.7. DTP-HepB combined; DTP-HepB; liquid; IM; 3; 2; 6. DTP-HepB combined; DTP-HepB; liquid; IM; 3; 10; 3. Hepatitis B; HepB; liquid; IM; 3; 1; 18. Hepatitis B; HepB; liquid; IM; 3; 2; 13. Hepatitis B; HepB; liquid; IM; 3; 6; 4.5. Hepatitis B; HepB; liquid; IM; 3; 10; 4. Hepatitis B UniJect; HepB; liquid; IM; 3; Uniject; 12. Hib liquid; Hib_liq; liquid; IM; 3; 1; 15. Hib liquid; Hib_liq; liquid; IM; 3; 10; 2.5. Hib freeze-dried; Hib_lyo; lyophilized; IM; 3; 1; 13; 35. Hib freeze-dried; Hib_lyo; lyophilized; IM; 3; 2; 6. Hib freeze-dried; Hib_lyo; lyophilized; IM; 3; 10; 2.5; 3. DTP liquid + Hib freeze-dried; DTP+Hib; liquid+lyop.; IM; 3; 1; 45. DTP-Hib combined liquid; DTP+Hib; liquid+lyop.; IM; 3; 10; 12. DTP-Hib combined liquid; DTP-Hib; liquid; IM; 3; 1; 32.3. DTP-HepB liquid + Hib freeze-dried; DTP-Hib; liquid; IM; 3; 10; 2.5. DTP-HepB liquid + Hib freeze-dried; DTP-HepB+Hib; liquid+lyop.; IM; 3; 1; 22. DTP-HepB-Hib liquid; DTP-HepB+Hib; liquid+lyop.; IM; 3; 2; 11. DTP-HepB-Hib liquid; DTP-HepB-Hib; liquid; IM; 3; 10; 4.4. DTP-HepB-Hib liquid; DTP-HepB-Hib; liquid; IM; 3; 2; 13.1. DTP-HepB-Hib liquid; DTP-HepB-Hib; liquid; IM; 3; 1; 19.2. Meningitis A/C; MV_A/C; lyophilized; SC; 1; 10; 2.5; 4. Meningitis A/C; MV_A/C; lyophilized; SC; 1; 50; 1.5; 3. Meningococcal A/C/W/; MV_A/C/W; lyophilized; SC; 1; 50; 1.5; 3. Meningococcal A/C/W/Y; MV_A/C/W/Y; lyophilized; SC; 1; 10; 2.5; 4. Meningitis W135; MV_W135; lyophilized; SC; 1; 10; 2.5; 4. Meningitis A conjugate; Men_A; lyophilized; SC; 2; 10; 2.6; 4. Japanese Encephalitis; JE_lyo; lyophilized; SC; 3; 10; 15. Japanese Encephalitis; JE_lyo; lyophilized; SC; 3; 10; 8.1; 8.1. Japanese Encephalitis; JE_lyo; lyophilized; SC; 3; 5; 2.5; 2.9. Japanese Encephalitis; JE_lyo; lyophilized; SC; 3; 1; 12.6; 11.5. Japanese Encephalitis; JE_liq; liquid; SC; 3; 10; 3.4. Rota vaccine; Rota_lyo; lyophilized; Oral; 2; 1; 156. Rota vaccine; Rota_liq; liquid; Oral; 2; 1; 17.1. Rota vaccine; Rota_liq; liquid; Oral; 3; 1; 45.9. Pneumo. conjugate vaccine 7-valent; PCV-7; liquid; IM; 3; PFS; 55.9. Pneumo. conjugate vaccine 7-valent; PCV-7; liquid; IM; 3; 1; 21. Pneumo. conjugate vaccine 10-valent; PCV-10; liquid; IM; 3; 1; 11.5. Pneumo. conjugate vaccine 10-valent; PCV-10; liquid; IM; 3; 2; 4.8. Pneumo. conjugate vaccine 13-valent; PCV-13; liquid; IM; 3; 1; 12. Polio inactivated; IPV; liquid; IM; 3; PFS; 107.4. Polio inactivated; IPV; liquid; IM; 3; 10; 2.5. Polio inactivated; IPV; liquid; IM; 3; 1; 15.7. Human Papilomavirus vaccine; HPV; liquid; IM; 3; 1; 15. Human Papilomavirus vaccine; HPV; liquid; IM; 3; 2; 5.7. Monovalent OPV-1; mOPV1; liquid; Oral; 20; 1.5. Monovalent OPV-3; mOPV3; liquid; Oral; 20; 1.5. |  |  |

| 12. Banking Form |  |
| --- | --- |
| In accordance with the decision on financial support made by the GAVI Alliance, the Government of Ghana hereby requests that a payment be made via electronic bank transfer as detailed below:. Name of Institution (Account Holder):; Ghana Health Service. Address:; Private Mail Bag, Ministries Post Office. City Country:; Accra - Ghana. Telephone no.:; +233302686486; Fax no.:; +233302686486. Currency of the bank account:; US Dollar. For credit to:. Bank account's title:; GHS Earmarked USD Accounts. Bank account no.:; 1101-530640-226. Bank's name:; Ecobank Ghana Limited. |  |
| Is the bank account exclusively to be used by this program? False. |  |
| By who is the account audited? Ghana Audit Service and Ernst and Young. |  |
| Signature of Government's authorizing official. |  |
| Seal. Name:; Dr Frank Nyonator. Title:; Director General, Ghana Health Service. Signature:. Date:. |  |
| FINANCIAL INSTITUTION. Bank Name:; Ecobank Ghana Limited. Branch Name:; Head Office Branch. Address:; 19th Seventh Avenue, Ridge West. City Country:; Accra - Ghana. Swift Code:; ECOCGHAC. Sort Code:; NA. ABA No.:; NA. Telephone No.:; +233303680436/9. FAX No.:; +233303679523. | CORRESPONDENT BANK. (In the United States). Citibank NA. 111 Wall Street, New York. NY 100043. USA. CITIUS33. |
| I certify that the account No is held by at this banking institution. The account is to be signed jointly by at least (number of signatories) of the following authorized signatories:. 1; Name:; Dr Frank Nyonator. Title:; Director General, Ghana Health Service. 2; Name:; Dr Joseph Amankwa. Title:; Director Public Health. 3; Name:; Ramatu Ude Umanta. Title:; Ag Director, Finance. |  |
| Name of bank's authorizing official. Signature:. Date:. Seal:. |  |