GAVI Alliance

Application Form for Country Proposals

For Support to New and Under-Used Vaccines (NVS)

Submitted by

The Government of

Myanmar

Date of submission: Not submitted yet

Deadline for submission: 1 Jun 2011

Select Start and End Year of your Comprehensive Multi-Year Plan (cMYP)

| Start Year | 2012 | End Year | 2016 |
| --- | --- | --- | --- |

Revised in January 2011

(To be used with Guidelines of December 2010)

Please submit the Proposal using the online platform https://AppsPortal.gavialliance.org/PDExtranet.

Enquiries to: proposals@gavialliance.org or representatives of a GAVI partner agency. The documents can be shared with GAVI partners, collaborators and general public. The Proposal and attachments must be submitted in English, French, Spanish, or Russian.

Note: Please ensure that the application has been received by the GAVI Secretariat on or before the day of the deadline.

The GAVI Secretariat is unable to return submitted documents and attachments to countries. Unless otherwise specified, documents will be shared with the GAVI Alliance partners and the general public.

GAVI ALLIANCE GRANT TERMS AND CONDITIONS FUNDING USED SOLELY FOR APPROVED PROGRAMMES The applicant country (“Country”) confirms that all funding provided by the GAVI Alliance will be used and applied for the sole purpose of fulfilling the programme(s) described in the Country’s application. Any significant change from the approved programme(s) must be reviewed and approved in advance by the GAVI Alliance. All funding decisions for the application are made at the discretion of the GAVI Alliance Board and are subject to IRC processes and the availability of funds. AMENDMENT TO THE APPLICATION The Country will notify the GAVI Alliance in its Annual Progress Report if it wishes to propose any change to the programme(s) description in its application. The GAVI Alliance will document any change approved by the GAVI Alliance, and the Country’s application will be amended. RETURN OF FUNDS The Country agrees to reimburse to the GAVI Alliance all funding amounts that are not used for the programme(s) described in its application. The country’s reimbursement must be in US dollars and be provided, unless otherwise decided by the GAVI Alliance, within sixty (60) days after the Country receives the GAVI Alliance’s request for a reimbursement and be paid to the account or accounts as directed by the GAVI Alliance. SUSPENSION/ TERMINATION The GAVI Alliance may suspend all or part of its funding to the Country if it has reason to suspect that funds have been used for purpose other than for the programmes described in the Country’s application, or any GAVI Alliance-approved amendment to the application. The GAVI Alliance retains the right to terminate its support to the Country for the programmes described in its application if a misuse of GAVI Alliance funds is confirmed. ANTICORRUPTION The Country confirms that funds provided by the GAVI Alliance shall not be offered by the Country to any third person, nor will the Country seek in connection with its application any gift, payment or benefit directly or indirectly that could be construed as an illegal or corrupt practice. AUDITS AND RECORDS The Country will conduct annual financial audits, and share these with the GAVI Alliance, as requested. The GAVI Alliance reserves the right, on its own or through an agent, to perform audits or other financial management assessment to ensure the accountability of funds disbursed to the Country. The Country will maintain accurate accounting records documenting how GAVI Alliance funds are used. The Country will maintain its accounting records in accordance with its government-approved accounting standards for at least three years after the date of last disbursement of GAVI Alliance funds. If there is any claims of misuse of funds, Country will maintain such records until the audit findings are final. The Country agrees not to assert any documentary privilege against the GAVI Alliance in connection with any audit. CONFIRMATION OF LEGAL VALIDITY The Country and the signatories for the Country confirm that its application, and Annual Progress Report, are accurate and correct and form legally binding obligations on the Country, under the Country’s law, to perform the programmes described in its application, as amended, if applicable, in the APR. CONFIRMATION OF COMPLIANCE WITH THE GAVI ALLIANCE TRANSPARANCY AND ACCOUNTABILITY POLICY The Country confirms that it is familiar with the GAVI Alliance Transparency and Accountability Policy (TAP) and complies with the requirements therein. USE OF COMMERCIAL BANK ACCOUNTS The Country is responsible for undertaking the necessary due diligence on all commercial banks used to manage GAVI cash-based support. The Country confirms that it will take all responsibility for replenishing GAVI cash support lost due to bank insolvency, fraud or any other unforeseen event. ARBITRATION Any dispute between the Country and the GAVI Alliance arising out of or relating to its application that is not settled amicably within a reasonable period of time, will be submitted to arbitration at the request of either the GAVI Alliance or the Country. The arbitration will be conducted in accordance with the then-current UNCITRAL Arbitration Rules. The parties agree to be bound by the arbitration award, as the final adjudication of any such dispute. The place of arbitration will be Geneva, Switzerland. The language of the arbitration will be English. For any dispute for which the amount at issue is US$ 100,000 or less, there will be one arbitrator appointed by the GAVI Alliance. For any dispute for which the amount at issue is greater than US $100,000 there will be three arbitrators appointed as follows: The GAVI Alliance and the Country will each appoint one arbitrator, and the two arbitrators so appointed will jointly appoint a third arbitrator who shall be the chairperson. The GAVI Alliance will not be liable to the country for any claim or loss relating to the programmes described in the application, including without limitation, any financial loss, reliance claims, any harm to property, or personal injury or death. Country is solely responsible for all aspects of managing and implementing the programmes described in its application.

# Application Specification

Please specify for which type of GAVI support you would like to apply to.

Important note: To enable proper functioning of the form, please first select the cMYP years on the previous page.

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Type of Support | Vaccine | Start Year | End Year | Preferred second presentation[1] | Action |
| --- | --- | --- | --- | --- | --- |
| New Vaccines Support | Measles, 10 doses/vial, Lyophilised | 2012 | 2016 |  |  |

[1] This "Preferred second presentation" will be used in case there is no supply available for the preferred presentation of the selected vaccine ("Vaccine" column). If left blank, it will be assumed that the country will prefer waiting until the selected vaccine becomes available.

# Table of Contents

Sections

Main

Cover Page

GAVI Alliance Grants Terms and Conditions

1. Application Specification

2. Table of Contents

3. Executive Summary

4. Signatures

4.1. Signatures of the Government and National Coordinating Bodies

4.1.1. Government and the Inter-Agency Coordinating Committee for Immunisation

4.1.2. National Coordinating Body - Inter-Agency Coordinating Committee for Immunisation

4.1.3. The Inter-Agency Coordinating Committee for Immunisation

4.2. National Immunization Technical Advisory Group for Immunisation

4.2.1. The NITAG Group for Immunisation

5. Immunisation Programme Data

5.1. Basic facts

5.2. Current vaccination schedule

5.3. Trends of immunisation coverage and disease burden

5.4. Baseline and Annual Targets

Table 1: baseline figures

5.5. Summary of current and future immunisation budget

5.6. Summary of current and future financing and sources of funds

6. NVS

6.1. Capacity and cost (for positive storage)

6.2. Assessment of burden of relevant diseases (if available)

6.3.1. Requested vaccine ( Measles, 10 doses/vial, Lyophilised )

6.3.2. Co-financing information

6.3.3. Wastage factor

6.3.4. Specifications of vaccinations with new vaccine

6.3.5. Portion of supply to be procured by the country (and cost estimate, US$)

6.3.6. Portion of supply to be procured by the GAVI Alliance (and cost estimate, US$)

6.3.7. New and Under-Used Vaccine Introduction Grant

7. Procurement and Management of New and Under-Used Vaccines

7.1. Vaccine management (EVSM/EVM/VMA)

8. Additional Comments and Recommendations

9. Annexes

Annex 1

Annex 1.1 - Measles, 10 doses/vial, Lyophilised

Table 1.1  A - Rounded up portion of supply that is procured by the country and estimate of related cost in US$

Table 1.1  B - Rounded up portion of supply that is procured by GAVI and estimate of related cost in US$.

Table 1.1  C - Summary table for vaccine Measles, 10 doses/vial, Lyophilised

Table 1.1  D - Estimated number of doses for vaccine Measles, 10 doses/vial, Lyophilised associated injection safety material and related co-financing budget

Annex 2

10. Attachments

10.1 Documents required for NVS support

10.2 Attachments

Banking Form

# Executive Summary

GAVI Alliance has supported Myanmar since 2002. Phase 1 of GAVI support for ISS, NVS and INS was implemented from 2002 to 2007 in Myanmar. Major activities supported by GAVI-ISS were training,micro planning,operational cost for outreach services ,monitoring and supervision. NVS and INS supported the introduction of Hepatitis B vaccine and Injection Safety equipment since 2003. Hepatitis B vaccine was introduced in phases from 2003 to 2005 along with injection safety equipment i.e. AD syringes and safety boxes, which significantly contributed for achieving and sustaining high coverage of all antigens. 

The country has received three additional supports: in 2003, 2007, and in 2008 by Measles Initiative for Measles control activiteis . These extra supports were utilized for strengthening of EPI units at Central, States and Divisions level, supported supplementary immunization activities and catch-up campaigns in the country and upgrading and expansion of the of cold chain system and its storage capacity at central store and sub-depots. 

Myanmar has a well-functioning Inter-Agency Coordinating Committee(ICC) which meets regularly to review the implementation of plans and programme and advise the Department of Health on the utilization of funds on the basis of the review. The last ICC meeting was held on 2nd May 2011, which has endorsed this Measles 2nd dose application submission to GAVI . MOH in clloboration with UNICEF will conduct an EVM assesment in August 2011 .

The country has a strong surveillance system and network monitored by Central Epidemiology Unit with teams of Special Diseases Control Units stationed at States and Regions, supported by a network of Regional surveillance Officers. A total of 17 Diseases are Under National Surveillance (DUNS) system since 1978. Measles is one of the diseases under this surveillance system.

Measles surveillance started with Diseases under national surveillance in 1978 and was then integrated into the Health Management Information System(HMIS) in 1995. Outbreak investigation was initiated in 1998 for clinical confirmation of cases. This was integrated in 1999 with the AFP and Neonatal Tetanus surveillance system. Laboratory confirmation of serum samples from outbreaks was started. Case based surveillance with both clinical and laboratory confirmation of cases was initiated in 2008.

Accelerated Measles mortality and morbidity reduction efforts were introduced in 1995 in 87 Yangon urban areas and in Mandalay in 1997. In 2001 the First Measles Control Plan of Action was formulated for the years 2002-2006 with the objective of reducing the annual number of cases and deaths due to measles in Myanmar up to 50% by 2003 relative to 1999 estimates. And under this plan three phases of SIA's targeting 9 months to 5 years age children were conducted countrywide from 2002-2004 with 88% coverage.

In 2007, a plan of Comprehensive Strategies Package for Measles Control (CSPMC) in Myanmar was formulated, and 3 phases nationwide SIA were planned for children in age group of 9 months to 15 years. However due to some unavoidable reasons the actual activity was conducted only in 9 months to 5 year old children. This activity was supported by funding from UN foundation/ Measles initiative
. As vaccines planned for 9- 15 years target children has already arrived in country, the balance Measles vaccine were utilized to offer second dose for children at 18 months age in selected townships. Leftover stock from 2007 campaign has been utilized to boost immunity in children and response to outbreak. These figures were reported as Measles second dose (MCV2 in 2008, 2009 & 2010 JRF reports). Using Emergency funds UNICEF also procured some additional measles vaccine to be used in Emergency cyclone NAGRIS, in 2008, GIRI cyclone area in 2010 which was also used and some times reported as second dose coverage’s. However there is no planned budget and procurement of Measles second dose vaccine for Myanmar’s EPI program. 



Myanmar is now applying to GAVI to support second dose of Measles vaccine in order to provide regular Measles 2nd dose to all eligible children at age of 18 months.

Myanmar is eligible to apply because it has ;
1) Mainitanied MCV1 coverage above 80% for last three consecutive years
2) WHO Regional office /SEARO endorsement to introduce MCV 2 routinelY
3) Myanamr has been using only donated MCV 2 vaccines and Emergency vaccination support in select areas ( GAVI secretariat has confirmed in writting that Myanmar is there for eligible to apply for this support .) 

the over all impact of the measles SIA together with provision of 2nd dose for 18 month children in select townships has proven effective in reducing measles cases and number and size of outbreak . TO maintian pop immunity level Myanmar plans to conduct a nation wide Measles SIA in Last quarter of 2011 targeting children 9months to 5 years. The timmming is ideal for Myanamr to introduce a sustained routine 2nd dose of MCV at age of 18 months thorugh out country after the SIA. This wil help to prevent susceptibles accumulating in the new birth cohorts.

In view of the above facts this proposal is being submitted to GAVI to support Myanmar for measles vaccines second dose to immunize an annual birth cohort of 1.5 million. This support will help Myanmar accelerate the efforts towards reaching the goal of measles elimination. This would in turn accelerate the efforts Myanmar to reach the MDG 4 targets in time.

# Signatures

# Signatures of the Government and National Coordinating Bodies

# Government and the Inter-Agency Coordinating Committee for Immunisation

The Government of Myanmar would like to expand the existing partnership with the GAVI Alliance for the improvement of the infants routine immunisation programme of the country, and specifically hereby requests for GAVI support for Measles 10 doses/vial Lyophilised introduction.

The Government of Myanmar commits itself to developing national immunisation services on a sustainable basis in accordance with the Comprehensive Multi-Year Plan (cMYP) presented with this document. The Government requests that the GAVI Alliance and its partners contribute financial and technical assistance to support immunisation of children as outlined in this application.

Tables 6.(n).5. (where (n) depends on the vaccine) in the NVS section of this application shows the amount of support in either supply or cash that is required from the GAVI Alliance. Tables 6.(n).4. of this application shows the Government financial commitment for the procurement of this new vaccine (NVS support only).

Following the regulations of the internal budgeting and financing cycles the Government will annually release its portion of the co-financing funds in the month of .

Please note that this application will not be reviewed or approved by the Independent Review Committee (IRC) without the signatures of both the Minister of Health & Minister of Finance or their delegated authority.

Enter the family name in capital letters.

| Minister of Health (or delegated authority) |  | Minister of Finance (or delegated authority) |  |
| --- | --- | --- | --- |
| Name | HE Professor Dr Pe Thet Khin | Name | U Kyaw Htay |
| Date |  | Date |  |
| Signature |  | Signature |  |

This report has been compiled by

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

Enter the family name in capital letters.

| Full name | Position | Telephone | Email | Action |
| --- | --- | --- | --- | --- |
| Dr Dr Kyaw Kan Kaung | Project Manager EPI ( DOH) | + 95 67 421205; 420437 | kyawkankaungmo@gmail.com |  |

# National Coordinating Body - Inter-Agency Coordinating Committee for Immunisation

We the members of the ICC, HSCC, or equivalent committee[1] met on the 02.05.2011 to review this proposal. At that meeting we endorsed this proposal on the basis of the supporting documentation which is attached.

[1] Inter-agency Coordinating Committee or Health Sector Coordinating Committee, or equivalent committee which has the authority to endorse this application in the country in question.

The endorsed minutes of this meeting are attached as DOCUMENT NUMBER: 1.

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

Enter the family name in capital letters.

| Name/Title | Agency/Organisation | Signature | Action |
| --- | --- | --- | --- |

In case the GAVI Secretariat has queries on this submission, please contact

Enter the family name in capital letters.

| Name | Dr Kyaw Kan Kaung | Title | Project Manager EPI ( DOH) |
| --- | --- | --- | --- |
| Tel no | + 95 67 421205; 420437 |  |  |
| Fax no | + 95 67 421205 | Address | Department of Health, Disease Control Unit, Minstry of Health, Govt of the Union Of Myanmar, NAYPYITAW |
| Email | kyawkankaungmo@gmail.com |  |  |

# The Inter-Agency Coordinating Committee for Immunisation

Agencies and partners (including development partners and NGOs) supporting immunisation services are co-ordinated and organised through an inter-agency coordinating mechanism (ICC, HSCC, or equivalent committee). The ICC, HSCC, or equivalent committee is responsible for coordinating and guiding the use of the GAVI NVS support. Please provide information about the ICC, HSCC, or equivalent committee in your country in the table below.

Profile of the ICC, HSCC, or equivalent committee

| Name of the committee | ICC |
| --- | --- |
| Year of constitution of the current committee | 2002-2003 |
| Organisational structure (e.g., sub-committee, stand-alone) | Stand alone |
| Frequency of meetings | Minimum 2-3 times per year and also need based ( outbreaks, SIA, etc) |

Composition

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

Enter the family name in capital letters.

| Function | Title / Organisation | Name |  |
| --- | --- | --- | --- |
| Chair | DG DOH | Dr. Saw Lwin |  |
| Secretary | Director (Epidemiology), DOH | Dr Soe Lwin Nyein, |  |
| Members | Dy Director General, DOH is also currently IC DG | Dr. Saw Lwin | Action |
|  | Deputy Director(Epidemiology), DOH | Dr Than Htein Win, |  |
|  | Director(Finance), DoH | U Kyaw Htay |  |
|  | Program Manager (EPI),DOH | Dr. Kyaw Kan Kaung |  |
|  | Country Representative, UNICEF | Dr. Ramesh Shrestha |  |
|  | WHO Representative | Dr. H.S.B Tennakoon |  |
|  | Medical Officer, EPI , WHO | Dr. Vinod Kumar Bura |  |
|  | Chief, Young Child Survival and Development, UNICEF | Dr. Marinus Gotink |  |

Major functions and responsibilities of the committee

In Myanamr Inter-agency Coordinating Committees(ICC) have been formed to improve coordination among partners insupport of immunization programs and control of vaccine-preventable diseases. The following Major Functions are undertaken by the ICC 1) Leadership and active participation from the MOH to guide the EPI program . 2) Collective monitoring and evaluation of Immunization activities. 3) Input and assistance from other MOH departments ,UN agencies like WHO and UNICEF for appropriate decision-making for support and program continuity. This includes joint Collaboration , joint prioritization, the establishment of common goals and objectives, and harmonized work plans with MOH. 4) Resource mobilization internally as well as by donors 5) Review and Approve on the GAVI supported activities 6) Review needs for SIA or other additonal immunization activity. Coordinated Implementation and Monitoring 7) Review and endosre EPI plans for disease burden study, cold chain assessment, or New vaccine intorduction

Three major strategies to enhance the committee's role and functions in the next 12 months

| 1. | Formation of sub working groups on key programs with the intent of discussing and monitoring the plan and programme and providing specific inputs to the ICC |
| --- | --- |
| 2. | Annual joint meetings with the National committee on Immunization practice |
| 3. | Expansion of the ICC membership by incorporating local representatives of Countries, UN organizations, bi laterals, and NGOs (National and International ) Professional bodies , supporting and working on EPI / child health in the country |

# National Immunization Technical Advisory Group for Immunisation

(If it has been established in the country)

We the members of the NITAG met on the to review this proposal. At that meeting we endorsed this proposal on the basis of the supporting documentation which is attached.

The endorsed minutes of this meeting are attached as DOCUMENT NUMBER: .

In case the GAVI Secretariat has queries on this submission, please contact

Enter the family name in capital letters.

| Name |  | Title |  |
| --- | --- | --- | --- |
| Tel no |  |  |  |
| Fax no |  | Address |  |
| Email |  |  |  |

# The NITAG Group for Immunisation

Profile of the NITAG

| Name of the NITAG |  |
| --- | --- |
| Year of constitution of the current NITAG |  |
| Organisational structure (e.g., sub-committee, stand-alone) |  |
| Frequency of meetings |  |

Composition

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

Enter the family name in capital letters.

| Function | Title / Organisation | Name |  |
| --- | --- | --- | --- |
| Chair |  |  |  |
| Secretary |  |  |  |
| Members |  |  | Action |

Major functions and responsibilities of the NITAG

Three major strategies to enhance the NITAG’s role and functions in the next 12 months

| 1. |  |
| --- | --- |
| 2. |  |
| 3. |  |

# Immunisation Programme Data

Please complete the tables below, using data from available sources. Please identify the source of the data, and the date. Where possible use the most recent data and attach the source document.

- Please refer to the Comprehensive Multi-Year Plan for Immunisation (cMYP) (or equivalent plan) and attach a complete copy (with an Executive Summary) as DOCUMENT NUMBER 2

- Please refer to the two most recent annual WHO/UNICEF Joint Reporting Forms (JRF) on Vaccine Preventable Diseases.

- Please refer to Health Sector Strategy documents, budgetary documents, and other reports, surveys etc, as appropriate.

# Basic facts

For the year 2010 (most recent; specify dates of data provided)

|  | Figure |  | Year | Source |
| --- | --- | --- | --- | --- |
| Total population | 60,168,393 |  | 2010 | EPI, CSO |
| Infant mortality rate (per 1000) | 54 |  | 2009 | World Health Statistics 2011 |
| Surviving Infants[1] | 1,504,210 |  | 2010 | JRF, EPI 2010 |
| GNI per capita (US$) | 781 |  | 2011 | National Health Accounts,WHO |
| Total Health Expenditure (THE) as a percentage of GDP | 2.80 | % | 2005 | World Health Report,2006 |
| General government expenditure on health (GGHE) as % of General government expenditure | 10.00 | % | 2010 | National Health Account,WHO |

[1] Surviving infants = Infants surviving the first 12 months of life

Please provide some additional information on the planning and budgeting context in your country; also indicate the name and date of the relevant planning document for health

National Health Policy - 1993 Myanmar Health Vision 2002----2030 is the over all guiding doccument National Health Plan 2006-2011, new National Health plan 2012-2016 is under process of formulation Hence the present C MYP was revised with a new doccument (cMYP 2012 to 2016 for EPI) so that this doccument is in line with the New national health plan 2012-2016

Is the cMYP (or updated Multi-Year Plan) aligned with this document (timing, content, etc.)?

The present cMYP is for the period 2007 -2011. Now a new c MPY has been drafted for the period of 2012-2016 which is in line with the new vaccine application and also aligne with the New National Health plan 2012-2016 The current cMYP 2007-2011 had set an Objective No 2 , Reduction of Measles mortality and morbidity. Both c MYP have measles mortality reduction OR elimination plans including introduction of MCV2. The measles 2nd dose introduction was planned for 2007 in the 2-007-2011 cMYP, but was introduced using only donated vaccine left over from the measles SIA in selected townships. Now Myanmar is applying to GAVI for a second dose of MCV to meet the above objectives and reach measles elimination goals

Please indicate the national planning budgeting cycle for health

MOH Annual plan and budget is from April to March every year

Please indicate the national planning cycle for immunisation

MOH Annual plan and budget April to March every year

Please indicate if sex disaggregated data (SDD) is used in immunisation routine reporting systems

N

Please indicate if gender aspects relating to introduction of a new vaccine have been addressed in the introduction plan

All children irrespective of the Gender are being immunized by the National EPI program, It has been observed in VPD surveillance data that there is no significant difference in diseases among males and females. The country policy is to provide free Immunization sercives hence there is no barrier among males and female children. Even in births there is no gender difference.

# Current vaccination schedule

Traditional, New Vaccines and Vitamin A supplement (refer to cMYP pages)

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Vaccine (do not use trade name) | Ages of administration (by routine immunisation services) | Given in entire country | Comments | Action |
| --- | --- | --- | --- | --- |
| BCG | 6 weeks | Yes |  |  |
| Polio | 6,10,14 weeks | Yes |  |  |
| DTP | 6,10,14 weeks | Yes |  |  |
| HepB | 6,10,14 weeks | Yes |  |  |
| Measles | 9 month | Yes | 2008 to 2010 , MCV2 was given in high risk townships as an optimal utilization of balance vaccine from 2007 SIA & Emergency |  |
| TT+ | First dose on first AN contact & Second dose after 4 weeks interval | Yes |  |  |
| Vitamin A | 6 months to 5 years twice a year | Yes |  |  |

# Trends of immunisation coverage and disease burden

(as per last two annual WHO/UNICEF Joint Reporting Form on Vaccine Preventable Diseases)

| Trends of immunisation coverage (percentage) |  |  |  |  |  | Vaccine preventable disease burden |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Vaccine |  | Reported |  | Survey |  | Disease | Number of reported cases |  |
|  |  | 2009 | 2010 |  |  |  | 2009 | 2010 |
| BCG |  | 93 | 93 |  |  | Tuberculosis |  |  |
| DTP | DTP1 | 93 | 93 |  |  | Diphtheria | 19 | 4 |
|  | DTP3 | 90 | 90 |  |  | Pertussis | 3 | 0 |
| Polio 3 |  | 90 | 90 |  |  | Polio | 0 | 1 |
| Measles (first dose) |  | 87 | 88 |  |  | Measles | 217 | 190 |
| TT2+ (Pregnant women) |  | 87 | 86 |  |  | NN Tetanus | 34 | 15 |
| Hib3 |  |  |  |  |  | Hib[2] |  |  |
| Yellow Fever |  |  |  |  |  | Yellow fever |  |  |
| HepB3 |  | 90 | 90 |  |  | HepBsero-prevalence[1] |  |  |
| Vitamin A supplement Mothers (< 6 weeks post-delivery) |  |  |  |  |  |  |  |  |
| Vitamin A supplement Infants (>6 months) |  |  |  |  |  |  |  |  |

[1] If available

[2] Note: JRF asks for Hib meningitis

If survey data is included in the table above, please indicate the years the surveys were conducted, the full title and if available, the age groups the data refers to

No survey was undertaken

# Baseline and Annual Targets

(refer to cMYP pages)

Table 1: baseline figures

| Number | Base Year | Baseline and Targets |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2010 | 2012 | 2013 | 2014 | 2015 | 2016 |  |
| Total births | 1,564,378 | 1,510,745 | 1,519,321 | 1,527,254 | 1,521,058 | 1,513,433 |  |
| Total infants' deaths | 60,168 | 55,898 | 54,696 | 51,972 | 50,195 | 46,916 |  |
| Total surviving infants | 1,504,210 | 1,454,847 | 1,464,625 | 1,475,282 | 1,470,863 | 1,466,517 |  |
| Total pregnant women | 1,624,547 | 1,586,282 | 1,580,093 | 1,588,344 | 1,566,689 | 1,558,836 |  |
| Number of infants vaccinated (to be vaccinated) with BCG | 1,401,203 | 1,404,993 | 1,412,968 | 1,435,619 | 1,429,794 | 1,437,761 |  |
| BCG coverage (%)[1] | 90% | 93% | 93% | 94% | 94% | 95% |  |
| Number of infants vaccinated (to be vaccinated) with OPV3 | 1,359,916 | 1,353,008 | 1,362,101 | 1,386,808 | 1,382,611 | 1,393,190 |  |
| OPV3 coverage (%)[2] | 90% | 93% | 93% | 94% | 94% | 95% |  |
| Number of infants vaccinated (or to be vaccinated) with DTP1[3] | 1,400,792 | 1,387,701 | 1,397,027 | 1,415,110 | 1,410,828 | 1,421,622 |  |
| Number of infants vaccinated (to be vaccinated) with DTP3[3] | 1,356,921 | 1,353,008 | 1,362,101 | 1,386,808 | 1,382,611 | 1,393,190 |  |
| DTP3 coverage (%)[2] | 90% | 93% | 93% | 94% | 94% | 95% |  |
| Wastage[1] rate in base-year and planned thereafter for DTP (%) | 45% | 40% | 15% | 15% | 15% | 15% |  |
| Wastage[1] factor in base-year and planned thereafter for DTP | 1.82 | 1.67 | 1.18 | 1.18 | 1.18 | 1.18 |  |
| Infants vaccinated (to be vaccinated) with 1st dose of Measles | 1,328,383 | 1,309,363 | 1,332,809 | 1,357,301 | 1,367,902 | 1,378,525 |  |
| Measles coverage (%)[2] | 88% | 90% | 91% | 92% | 93% | 94% |  |
| Infants vaccinated (to be vaccinated) with 2nd dose of Measles | 1,125,019 | 1,163,878 | 1,171,700 | 1,254,028 | 132,776 | 1,319,865 |  |
| Pregnant women vaccinated with TT+ | 1,397,499 | 1,427,654 | 1,437,885 | 1,461,277 | 1,457,021 | 1,480,894 |  |
| TT+ coverage (%)[4] | 86% | 90% | 91% | 92% | 93% | 95% |  |
| Vit A supplement to mothers within 6 weeks from delivery |  |  |  |  |  |  |  |
| Vit A supplement to infants after 6 months |  |  |  |  |  |  |  |
| Annual DTP Drop-out rate[ ( DTP1 - DTP3 ) / DTP1 ] x 100[5] | 3% | 3% | 3% | 2% | 2% | 2% |  |

[1] Number of infants vaccinated out of total births

[2] Number of infants vaccinated out of total surviving infants

[3] Indicate total number of children vaccinated with either DTP alone or combined

[4] Number of pregnant women vaccinated with TT+ out of total pregnant women

[5] The formula to calculate a vaccine wastage rate (in percentage):[ ( A – B ) / A ] x 100. Whereby: A = the number of doses distributed for use according to the supply records with correction for stock balance at the end of the supply period; B = the number of vaccinations with the same vaccine in the same period.

# Summary of current and future immunisation budget

(or refer to cMYP pages)

|  | Estimated costs per annum in US$ (in thousand US$) |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Cost category | Base Year | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |  |
|  | 2010 | 2012 | 2013 | 2014 | 2015 | 2016 |  |  |  |  |
| Routine Recurrent Cost |  |  |  |  |  |  |  |  |  |  |
| Vaccines (routine vaccines only) | 2,507,241 | 5,907,969 | 18,551,572 | 17,164,068 | 18,249,966 | 19,685,354 |  |  |  |  |
| Traditional vaccines | 2,507,241 | 4,514,988 | 3,724,965 | 3,663,490 | 3,779,305 | 3,779,895 |  |  |  |  |
| New and underused vaccines |  | 1,392,981 | 14,826,607 | 13,500,578 | 14,470,661 | 15,905,459 |  |  |  |  |
| Injection supplies | 415,504 | 1,620,699 | 1,219,052 | 1,476,001 | 1,615,940 | 1,790,676 |  |  |  |  |
| Personnel | 505,927 | 1,497,674 | 1,527,627 | 1,558,179 | 1,589,343 | 1,621,130 |  |  |  |  |
| Salaries of full-time NIP health workers (immunisation specific) | 12,185 | 65,214 | 66,518 | 67,848 | 69,205 | 70,589 |  |  |  |  |
| Per-diems for outreach vaccinators / mobile teams | 493,742 | 1,432,460 | 1,461,109 | 1,490,331 | 1,520,138 | 1,550,541 |  |  |  |  |
| Transportation | 156,309 | 75,589 | 77,154 | 78,757 | 80,305 | 68,353 |  |  |  |  |
| Maintenance and overheads | 429,499 | 2,181,653 | 2,269,295 | 2,317,686 | 2,508,848 | 2,559,980 |  |  |  |  |
| Training | 42,473 | 616,384 | 632,280 | 648,294 | 658,577 | 668,381 |  |  |  |  |
| Social mobilisation and IEC | 21,766 | 770,480 | 790,351 | 810,367 | 823,221 | 835,476 |  |  |  |  |
| Disease surveillance | 395,923 | 1,540,960 | 1,580,701 | 1,620,734 | 1,646,442 | 1,670,952 |  |  |  |  |
| Program management |  | 1,386,864 | 1,422,631 | 1,458,661 | 1,481,798 | 1,503,857 |  |  |  |  |
| Other | 3,446 | 0 | 0 | 0 | 0 | 0 |  |  |  |  |
| Subtotal Recurrent Costs | 4,478,088 | 15,598,272 | 28,070,663 | 27,132,747 | 28,654,440 | 30,404,159 |  |  |  |  |
| Routine Capital Costs |  |  |  |  |  |  |  |  |  |  |
| Vehicle | 0 | 61,792 | 63,464 | 65,179 | 66,483 | 1,391 |  |  |  |  |
| Cold chain equipment | 167,134 | 8,031,627 | 8,544,949 | 2,460,072 | 2,737,035 | 1,480,567 |  |  |  |  |
| Other capital equipment | 11,774 | 2,668,810 | 2,668,810 | 2,668,810 | 2,668,810 | 2,668,810 |  |  |  |  |
| Subtotal Capital Costs | 178,908 | 10,762,229 | 11,277,223 | 5,194,061 | 5,472,328 | 4,150,768 |  |  |  |  |
| Campaigns |  |  |  |  |  |  |  |  |  |  |
| Polio | 1,268,591 | 3,440,299 | 3,557,580 | 3,686,894 | 0 | 0 |  |  |  |  |
| Measles | 0 | 0 | 0 | 6,000,527 | 0 | 0 |  |  |  |  |
| Yellow Fever | 0 | 0 | 0 | 0 |  | 0 |  |  |  |  |
| MNT campaigns | 50,000 | 1,872,120 | 0 | 2,193,539 | 0 | 2,582,898 |  |  |  |  |
| Other campaigns |  |  |  |  |  |  |  |  |  |  |
| Subtotal Campaign Costs | 1,318,591 | 5,312,419 | 3,557,580 | 11,880,960 | 0 | 2,582,898 |  |  |  |  |
| GRAND TOTAL | 5,975,587 | 31,672,920 | 42,905,466 | 44,207,768 | 34,126,768 | 37,137,825 |  |  |  |  |

# Summary of current and future financing and sources of funds

Please list in the tables below the funding sources for each type of cost category (if known). Please try and indicate which immunisation program costs are covered from the Government budget, and which costs are covered by development partners (or the GAVI Alliance), and name the partners (or refer to cMYP).

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

|  |  | Estimated costs per annum in US$ (in thousand US$) |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Cost category | Funding source | Base Year | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |  |
|  |  | 2010 | 2012 | 2013 | 2014 | 2015 | 2016 |  |  |  |  |
| Routine Recurrent Cost |  |  |  |  |  |  |  |  |  |  |  |
| Personal,Transportation,Maintainance Overhead | Government | 68,050 | 2,245,883 | 2,330,681 | 2,376,918 | 2,572,918 | 1,524,004 |  |  |  |  |
| Tradational Vaccine,Injection supplies,cold chain maintenance&OverHead, Short Term Training, IEC , Social Mobilization | UNICEF | 1,960,000 | 2,319,528 | 2,386,222 | 2,413,342 | 2,432,336 | 2,347,984 |  |  |  |  |
| Short Term Training, IECs, Social Mobilization,Disease Surveillance, Programme Management | WHO | 120,000 | 1,693,960 | 1,734,701 | 1,774,734 | 1,800,442 | 1,824,952 |  |  |  |  |
| New &Underused Vaccine, | GAVI | 0 | 1,436,710 | 10,997,438 | 9,212,755 | 9,378,445 | 9,698,490 |  |  |  |  |
| Under Used Vacine | Government Cofinancing | 0 |  | 1,201,854 | 983,283 | 975,961 | 985,295 |  |  |  |  |
| Others | JCV | 400,000 |  |  |  |  |  |  |  |  |  |
| Routine Capital Costs |  |  |  |  |  |  |  |  |  |  |  |
| Vehicle, cold chain Equipment | GAVI |  | 190,000 |  |  |  |  |  |  |  |  |
| Other Capital cost | Government | 7,149 |  |  |  |  |  |  |  |  |  |
|  | UNICEF | 250,000 |  |  |  |  |  |  |  |  |  |
|  | JCV/JICA | 100,000 |  |  |  |  |  |  |  |  |  |
| Campaigns |  |  |  |  |  |  |  |  |  |  |  |
| Polio,Measles ,TT | Others |  | 3,136,376 | 1,889,299 | 7,858,921 | 0 | 1,374,807 |  |  |  |  |
| GRAND TOTAL |  | 2,905,199 | 11,022,457 | 20,540,195 | 24,619,953 | 17,160,102 | 17,755,532 |  |  |  |  |

# New and Under-Used Vaccines (NVS)

Please summarise the cold chain capacity and readiness to accommodate new vaccines, stating how the cold chain expansion (if required) will be financed, and when it will be in place. Please indicate the additional cost, if capacity is not available and the source of funding to close the gap.

Myanmar has a good storage capacity and network of cold stores and cold room or sub-depot. These are 22 in number and situated all over the country. In 2008 the new central cold room was built and the facility consists of 3 Walk In Coolers room ( 30m3) and 4 Walk in Freezers. The total net cold storage capacity at the national store is 23.1m3 at +2°C to +8°C and 7.7m3 at -15°C to -25°C. Expansion of cold chain system network is planned by building hybrid solar system in seven sub-depots and one facility in one populous hilly region which will accommodate a walk in cooler and freezer each. The current national storage capacity at +2 to +8 degree is 21,429 liters where as for freezers ( -15 to -25 degree it is 20,513 liters. This capacity is adequate at National level for present program as well as MCV2. The storage capacity at the intermediate levels is adequate. The upkeep and running costs for these new facilities will be funded jointly by UNICEF-WHO funding sources.

Please give a summary of the cMYP sections that refer to the introduction of new and under-used vaccines. Outline the key points that informed the decision-making process (data considered etc)

Under the main strategy of protecting more children in a changing world, Objective 2 of cMYP 2007-2011 is to reduce measles mortality and morbidity by 95% compared to 2001 level by 2010.The strategy is to introduce a second dose measles immunization either through regular follow-up measles campaigns or routine immunization at 18 months of age. Finally ICC advocated the introduction of measles second dose at the age of 18 months and Department of Health introduced second opportunity in selected areas and disaster affected areas where routine measles immunization coverage or measles SIA coverage was high. In the new c MYP this objective is also there, also rountine surveilance data on measles cases, age group , and WHO HQ estimate were taken into full condsideration on this

# Capacity and cost (for positive storage)

|  |  | Formula | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2012 | 2013 | 2014 | 2015 | 2016 |  |  |  |
| A | Annual positive volume requirement, including new vaccine (litres or m3) Litres | Sum-product of total vaccine doses multiplied by unit packed volume of the vaccine | 101,132 | 80,251 | 77,656 | 75,670 | 73,900 |  |  |  |
| B | Existing net positive cold chain capacity (litres or m3) Litres | # | 145,611 | 145,611 | 145,611 | 145,611 | 145,611 |  |  |  |
| C | Estimated minimum number of shipments per year required for the actual cold chain capacity | A / B | 1 | 1 | 1 | 1 | 1 |  |  |  |
| D | Number of consignments / shipments per year | Based on national vaccine shipment plan | 3 | 3 | 3 | 3 | 3 |  |  |  |
| E | Gap (if any) | ((A / D) - B) | -111,900 | -118,861 | -119,726 | -120,388 | -120,978 |  |  |  |
| F | Estimated additional cost of cold chain | US$ | 1,969 | 6,184 | 5,721 | 6,083 | 6,562 |  |  |  |

Please briefly describe how your country plans to move towards attaining financial sustainability for the new vaccines you intend to introduce, how the country will meet the co-financing payments, and any other issues regarding financial sustainability you have considered (refer to the cMYP)

A Financial Sustainability Plan(FSP) was made in 2004. Discussions are going on for identifiying funds to support the EPI costs.

# Assessment of burden of relevant diseases (if available)

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Disease | Title of the assessment | Date | Results |  |
| --- | --- | --- | --- | --- |
| Measles WHO HQ assesment | WHO estimates of child deaths due to measles, 2000-2009 | Feb 2011 | WHO HQ estimate that measles mortality in Myanmar has decreased 67% from 3300 deaths in 2000 to 1100 in 2009 |  |
| Mealses Routine surveillance program |  | Jan -Dec 2010 | 190 cases of measles including outbreaks |  |

If new or under-used vaccines have already been introduced in your country, please give details of the lessons learned from storage capacity, protection from accidental freezing, staff training, cold chain, logistics, drop-out rate, wastage rate etc., and suggest action points to address them

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Lessons Learned | Action Points |  |
| --- | --- | --- |
| 1) Storage Capacity- Cold chain capacity should be adequate to accommodate new vaccine 2) Protection from accidental freezing : As Hep B vaccine is Freeze sensitive all precautions were taken in advance 3) Staff Training : As Hep B was a new vaccine being introduced after a gap of 5-6 years, the staff needed to be trained. also sice there has been a high torn over of stadd 4) Wastage rate : As it was a high cost vaccine all efforts were put in place to minimize wastage. | 1) To cope up the introduction of new vaccine and its volume load new cold rooms were put in place in 3 places and Hep B vaccines was stored in a specific cooler adjusted to 4-6 Celsius degree at central cold room. 2) Alarm system was installed to the cooler and cold chain engineer checks 2 times a day for temperature. The temperature recording system was also installed inside the cooler. The shelves for ice packs for conditioning of frozen ice-packs were arranged before packing the Hep B vaccines in the cold boxes which were going to other sub-depots. Freeze tags and Frigde tag has been introduced in Myanmar in 2010 supported by WHO to reduce vaccine wastge and monitor cold chain effectively. 3) Introduction of Hep B vaccine handbooks were developed and used in staff training in all levels. Epidemiology, about vaccine ,its sensitivity to cold, doses and vials, how to store, collect, distribute and give injection , and immunization schedules were included in the handbook. this was found helpful. 4) To reduce wastage rate, microplanning needs to be improved at seesion level, also community demand generation, defaulter trackingg needs to be in place |  |

Please list the vaccines to be introduced with support from the GAVI Alliance (and presentation)

1) MCV 2nd dose - 10 dose vial presentation

# 6.3.1. Requested vaccine ( Measles, 10 doses/vial, Lyophilised )

As reported in the cMYP, the country plans to introduce Measles, 10 doses/vial, Lyophilised vaccine.

# 6.3.2. Co-financing information

No Co-financing for Measles

# 6.3.3. Wastage factor

Please indicate wastage rate:

Countries are expected to plan for a maximal wastage rate of:

- 50% - for a lyophilised vaccine in 10 or 20-dose vial,

- 25% - for a liquid vaccine in 10 or 20-dose vial or a lyophilised vaccine in 5-dose vial,

- 10% - for a lyophilised/liquid vaccine in 2-dose vial, and

- 5% - for a liquid vaccine in 1-dose vial

Note: Selection of this field has direct impact on automatic calculations of support you are requesting and should not be left empty.

|  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2012 | 2013 | 2014 | 2015 | 2016 |  |  |  |
| Vaccine wastage rate in % | 40% | 35% | 30% | 30% | 25% |  |  |  |
| Equivalent wastage factor | 1.67 | 1.54 | 1.43 | 1.43 | 1.33 |  |  |  |

# 6.3.4. Specifications of vaccinations with new vaccine

|  | Data from |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2012 | 2013 | 2014 | 2015 | 2016 |  |  |  |
| Number of children to be vaccinated with the first dose | Table 1 | # | 1,309,363 | 1,332,809 | 1,357,301 | 1,367,902 | 1,378,525 |  |  |  |
| Number of children to be vaccinated with the third dose[1] | Table 1 | # | 1,163,878 | 1,171,700 | 1,254,028 | 132,776 | 1,319,865 |  |  |  |
| Immunisation coverage with the third dose | Table 1 | # | 90.00% | 91.00% | 92.00% | 93.00% | 94.00% |  |  |  |
| Estimated vaccine wastage factor | Table 6.(n).3[3] | # | 1.67 | 1.54 | 1.43 | 1.43 | 1.33 |  |  |  |
| Country co-financing per dose[2] | Table 6.(n).2[3] | $ | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |  |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Total price per-dose includes vaccine cost, plus freight, supplies, insurance, visa costs etc.

[3] Where (n) depends on the vaccine

# 6.3.5. Portion of supply to be procured by the country (and cost estimate, US$)

|  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2012 | 2013 | 2014 | 2015 | 2016 |  |  |  |
| Number of vaccine doses | # | 0 | 0 | 0 | 0 | 0 |  |  |  |
| Number of AD syringes | # | 0 | 0 | 0 | 0 | 0 |  |  |  |
| Number of re-constitution syringes | # | 0 | 0 | 0 | 0 | 0 |  |  |  |
| Number of safety boxes | # | 0 | 0 | 0 | 0 | 0 |  |  |  |
| Total value to be co-financed by country | $ | 0 | 0 | 0 | 0 | 0 |  |  |  |

# 6.3.6. Portion of supply to be procured by the GAVI Alliance (and cost estimate, US$)

|  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2012 | 2013 | 2014 | 2015 | 2016 |  |  |  |
| Number of vaccine doses | # | 2,429,600 | 1,804,500 | 1,793,300 | 189,900 | 2,146,900 |  |  |  |
| Number of AD syringes | # | 1,831,300 | 1,300,600 | 1,392,000 | 147,400 | 1,899,500 |  |  |  |
| Number of re-constitution syringes | # | 269,700 | 200,300 | 199,100 | 21,100 | 238,300 |  |  |  |
| Number of safety boxes | # | 23,325 | 16,675 | 17,675 | 1,875 | 23,750 |  |  |  |
| Total value to be co-financed by GAVI | $ | 776,000 | 572,500 | 575,500 | 61,000 | 704,500 |  |  |  |

# 6.3.7. New and Under-Used Vaccine Introduction Grant

Please indicate in the tables below how the one-time Introduction Grant[1] will be used to support the costs of vaccine introduction and critical pre-introduction activities (refer to the cMYP).

Calculation of lump-sum for the Measles, 10 doses/vial, Lyophilised

If the total is lower than US$100,000, it is automatically rounded up to US$100,000

| Year of New Vaccine Introduction | Births (from Table 1) | Share per Birth in US$ | Total in US$ |
| --- | --- | --- | --- |
| 2012 | 1,510,745 | 0.30 | 453,500 |

[1] The Grant will be based on a maximum award of $0.30 per infant in the birth cohort with a minimum starting grant award of $100,000

Cost (and finance) to introduce the Measles, 10 doses/vial, Lyophilised (US$)

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Cost Category | Full needs for new vaccine introduction in US$ | Funded with new vaccine introduction grant in US$ |  |
| --- | --- | --- | --- |
| Training | 10,000 | 10,000 |  |
| Social Mobilization, IEC and Advocacy | 75,000 | 75,000 |  |
| Cold Chain Equipment & Maintenance | 75,000 | 75,000 |  |
| Vehicles and Transportation | 150,000 | 150,000 |  |
| Programme Management | 10,000 | 20,000 |  |
| Surveillance and Monitoring | 60,000 | 50,000 |  |
| Human Resources | 20,000 | 20,000 |  |
| Waste Management | 10,000 | 10,000 |  |
| Technical assistance | 20,000 | 20,000 |  |
| printing imm cards, formats, HW guidelines | 50000 | 25000 |  |
| Totals | 480,000 | 455,000 |  |

# Procurement and Management of New and Under-Used Vaccines

Note: The PCV vaccine must be procured through UNICEF

- Please show how the support will operate and be managed including procurement of vaccines (GAVI expects that most countries will procure vaccine and injection supplies through UNICEF)

All Procurement of the MCV2 vaccine will be done through UN supplies, through UNICEF Myanmar as for routine immunization

- If an alternative mechanism for procurement and delivery of supply (financed by the country or the GAVI Alliance) is requested, please document

- Other vaccines or immunisation commodities procured by the country and descriptions of the mechanism used.

- The functions of the National Regulatory Authority (as evaluated by WHO) to show they comply with WHO requirements for procurement of vaccines and supply of assured quality.

MCV

- Please describe the introduction of the vaccines (refer to cMYP)

Measles second dose will be planned to deliver in all townships through current vacinators (midwives) who are delivering other traditional antigens including Measles second dose in some townships. Rountine Systematic introduction will start in 2012. Revision of child vaccination cards, tally forms and registers, wall monitoring charts, training of staff on MCV2, cold chain capacity/logistics, social mobilization and IEC for parents so they know to bring their children back again for MCV2 at 18 months.

- Please indicate how funds should be transferred by the GAVI Alliance (if applicable)

Fund will be transferred through WHO country office/regional office

- Please indicate how the co-financing amounts will be paid (and who is responsible for this)

not applicable

- Please outline how coverage of the new vaccine will be monitored and reported (refer to cMYP)

Immunization cards and health facility tally sheets, registers, wall monitoring charts, stock management forms, etc will be revised to include a routine 2nd dose of measles and staff trained to record and calculate MCV2 targets and coverage correctly. Monthly coverage from lowest reporting unit, subcenter level, will be collected using standardized reporting format. Township medical office will compile coverage and other data and send to State/Regional level, where data are compiled through Health Management Information System. HMIS State/regional level data are then transfer to Department of Health Planning and Central EPI quarterly. Township and State/Regional level data are also compiled by Special Disease Control Units team leaders and RSO. In addtion to this at township level monthly review of Coverages by TMO . At state level Quartly review and at national level 6 monthly review meetings will be conducted to review progress and address contrains and challenges. Periodic monitoring will be done by TMO, SDC units staff in their respective areas. MOH central level will also draw monthly monitoring plans for HRA. VPD survillnce data will be reviewed along with immunization coverages data , dieases data etc..

# Vaccine Management (EVSM/EVM/VMA)

When was the last Effective Vaccine Store Management (EVSM) conducted?   - 2004

When was the last Effective Vaccine Management (EVM) or Vaccine Management Assessment (VMA) conducted?   -

- If your country conducted either EVSM, EVM, or VMA in the past three years, please attach relevant reports. (Document N°)

- A VMA report must be attached from those countries which have introduced a New and Underused Vaccine with GAVI support before 2008.

- Please note that EVSM and VMA tools have been replaced by an integrated Effective Vaccine Management (EVM) tool. The information on EVM tool can be found at http://www.who.int/immunization_delivery/systems_policy/logistics/en/index6.html

- For countries which conducted EVSM, VMA or EVM in the past, please report on activities carried out as part of either action plan or improvement plan prepared after the EVSM/VMA/EVM.

Cold chain system strengthening Activities carried out after last assessment: 1. Rehabilitation of Central Cold Store 2. Procurement of cold chain equipment (solar refrigerators) to improve five sub-depots 3. Creation of new sub-depot at Kalay (Northern Sagaing Region) 4. Support for cold chain management: training of cold chain engineers, cold chain key persons and transportation 5. New generation temperature monitoring tools introduced in EPI program Fridge tags, and freeze tags supported by WHO

- When is the next Effective Vaccine Management (EVM) Assessment planned? July   - 2011

- Under new guidelines, it will be mandatory for the countries to conduct an EVM prior to an application for introduction of new vaccine.

# Additional Comments and Recommendations

Comments and Recommendations from the National Coordinating Body (ICC/HSCC)

In its effrots to reach measles elimination goal, Measles second dose need to be available for all children at 18 months of age with systematic planning. In addition, MCV 1 coverage has already surpassed 80% in Myanmar and MCV 2 coverage in some high risk townships reached 75%. Measles SIAs in 2007 achieved more than 90% and follow up campaign in 2011 is planned to reached more than 90% of 9 months to 5 years old children. These achievement, Myanmar can achieve 95% coverage in 2015, which is essential for Measles elimination. Because of potential to contribute regional Measles goal, existing capacity and disease burden, ICC is fully endorsed this Measles second dose proposal. MCV2 contributes to Myanmar's efforts related to GIVS strategic area "Protecting More" by reaching older age groups with vaccination, and providing greater immunity to measles.

# Annexes

# Annex 1

# Annex 1.1 – Measles, 10 doses/vial, Lyophilised

Table 1.1 A - Rounded up portion of supply that is procured by the country and estimate of related cost in US$

| Required supply item |  | 2012 | 2013 | 2014 | 2015 | 2016 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of vaccine doses | # | 0 | 0 | 0 | 0 | 0 |  |  |  |
| Number of AD syringes | # | 0 | 0 | 0 | 0 | 0 |  |  |  |
| Number of re-constitution syringes | # | 0 | 0 | 0 | 0 | 0 |  |  |  |
| Number of safety boxes | # | 0 | 0 | 0 | 0 | 0 |  |  |  |
| Total value to be co-financed by the country | $ | 0 | 0 | 0 | 0 | 0 |  |  |  |

Table 1.1  B - Rounded up portion of supply that is procured by GAVI and estimate of related cost in US$.

| Required supply item |  | 2012 | 2013 | 2014 | 2015 | 2016 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of vaccine doses | # | 2,429,600 | 1,804,500 | 1,793,300 | 189,900 | 2,146,900 |  |  |  |
| Number of AD syringes | # | 1,831,300 | 1,300,600 | 1,392,000 | 147,400 | 1,899,500 |  |  |  |
| Number of re-constitution syringes | # | 269,700 | 200,300 | 199,100 | 21,100 | 238,300 |  |  |  |
| Number of safety boxes | # | 23,325 | 16,675 | 17,675 | 1,875 | 23,750 |  |  |  |
| Total value to be co-financed by the country | $ | 776,000 | 572,500 | 575,500 | 61,000 | 704,500 |  |  |  |

Table 1.1  C - Summary table for Measles, 10 doses/vial, Lyophilised

|  | Data from |  | 2012 | 2013 | 2014 | 2015 | 2016 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of Surviving infants | Table 1 | # | 1,454,847 | 1,464,625 | 1,475,282 | 1,470,863 | 1,466,517 |  |  |  |
| Number of children to be vaccinated with the third dose[1] | Table 1 | # | 1,163,878 | 1,171,700 | 1,254,028 | 132,776 | 1,319,865 |  |  |  |
| Immunisation coverage with the last dose | Table 1 | # | 90.00% | 91.00% | 92.00% | 93.00% | 94.00% |  |  |  |
| Number of children to be vaccinated with the first dose | Table 1 | # | 1,309,363 | 1,332,809 | 1,357,301 | 1,367,902 | 1,378,525 |  |  |  |
| Number of doses per child |  | # | 1 | 1 | 1 | 1 | 1 |  |  |  |
| Estimated vaccine wastage factor | Table 6.(n).3[2] | # | 1.67 | 1.54 | 1.43 | 1.43 | 1.33 |  |  |  |
| Number of doses per vial |  | # | 10 | 10 | 10 | 10 | 10 |  |  |  |
| AD syringes required |  | # | Yes | Yes | Yes | Yes | Yes |  |  |  |
| Reconstitution syringes required |  | # | Yes | Yes | Yes | Yes | Yes |  |  |  |
| Safety boxes required |  | # | Yes | Yes | Yes | Yes | Yes |  |  |  |
| Vaccine price per dose |  | $ | 0.240 | 0.240 | 0.240 | 0.240 | 0.240 |  |  |  |
| Country co-financing per dose | Table 6.(n).2[2] | $ | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |  |  |  |
| AD syringe price per unit |  | $ | 0.053 | 0.053 | 0.053 | 0.053 | 0.053 |  |  |  |
| Reconstitution syringe price per unit |  | $ | 0.038 | 0.038 | 0.038 | 0.038 | 0.038 |  |  |  |
| Safety box price per unit |  | $ | 0.640 | 0.640 | 0.640 | 0.640 | 0.640 |  |  |  |
| Freight cost as % of vaccines value |  | % | 10.00 | 10.00 | 10.00 | 10.00 | 10.00 |  |  |  |
| Freight cost as % of devices value |  | % | 10.00 | 10.00 | 10.00 | 10.00 | 10.00 |  |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Where (n) depends on the vaccine

# Table 1.1 D - Estimated number of doses for Measles, 10 doses/vial, Lyophilised associated injection safety material and related co-financing budget (page 1)

|  |  | Formula | 2012 |  |  | 2013 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Total | Government | GAVI | Total | Government | GAVI |
| A | Country Co-finance |  | 0.00% |  |  | 0.00% |  |  |
| B | Number of children to be vaccinated with the first dose[1] | Table 1 (baseline & annual targets) | 1,163,878 | 0 | 1,163,878 | 1,171,700 | 0 | 1,171,700 |
| C | Number of doses per child | Vaccine parameter | 1 | 1 | 1 | 1 | 1 | 1 |
| D | Number of doses needed | B * C | 1,163,878 | 0 | 1,163,878 | 1,171,700 | 0 | 1,171,700 |
| E | Estimated vaccine wastage factor | Table 6.(n).3. in NVS section[2] | 1.67 | 1.67 | 1.67 | 1.54 | 1.54 | 1.54 |
| F | Number of doses needed including wastage | D * E | 1,943,677 | 0 | 1,943,677 | 1,804,418 | 0 | 1,804,418 |
| G | Vaccines buffer stock | (F - F of previous year) * 0.25 | 485,920 | 0 | 485,920 | 0 | 0 | 0 |
| I | Total vaccine doses needed | F + G | 2,429,597 | 0 | 2,429,597 | 1,804,418 | 0 | 1,804,418 |
| J | Number of doses per vial | Vaccine parameter | 10 | 10 | 10 | 10 | 10 | 10 |
| K | Number of AD syringes (+ 10% wastage) needed | (D + G) * 1.11 | 1,831,276 | 0 | 1,831,276 | 1,300,587 | 0 | 1,300,587 |
| L | Reconstitution syringes (+ 10% wastage) needed | I / J * 1.11 | 269,686 | 0 | 269,686 | 200,291 | 0 | 200,291 |
| M | Total of safety boxes (+ 10% of extra need) needed | (K + L) / 100 x 1.11 | 23,321 | 0 | 23,321 | 16,660 | 0 | 16,660 |
| N | Cost of vaccines needed | I * vaccine price per dose | 583,104 | 0 | 583,104 | 433,061 | 0 | 433,061 |
| O | Cost of AD syringes needed | K * AD syringe price per unit | 97,058 | 0 | 97,058 | 68,932 | 0 | 68,932 |
| P | Cost of reconstitution syringes needed | L * reconstitution price per unit | 10,249 | 0 | 10,249 | 7,612 | 0 | 7,612 |
| Q | Cost of safety boxes needed | M * safety box price per unit | 14,926 | 0 | 14,926 | 10,663 | 0 | 10,663 |
| R | Freight cost for vaccines needed | N * freight cost as % of vaccines value | 58,311 | 0 | 58,311 | 43,307 | 0 | 43,307 |
| S | Freight cost for devices needed | (O + P + Q) * freight cost as % of devices value | 12,224 | 0 | 12,224 | 8,721 | 0 | 8,721 |
| T | Total fund needed | (N + O + P + Q + R + S) | 775,872 | 0 | 775,872 | 572,296 | 0 | 572,296 |
| U | Total country co-financing | I * country co-financing per dose | 0 |  |  | 0 |  |  |
| V | Country co-financing % of GAVI supported proportion | U / T | 0.00% |  |  | 0.00% |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Where (n) depends on the vaccine

# Table 1.1 D - Estimated number of doses for Measles, 10 doses/vial, Lyophilised associated injection safety material and related co-financing budget (page 2)

|  |  | Formula | 2014 |  |  | 2015 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Total | Government | GAVI | Total | Government | GAVI |
| A | Country Co-finance |  | 0.00% |  |  | 0.00% |  |  |
| B | Number of children to be vaccinated with the first dose[1] | Table 1 (baseline & annual targets) | 1,254,028 | 0 | 1,254,028 | 132,776 | 0 | 132,776 |
| C | Number of doses per child | Vaccine parameter (schedule) | 1 | 1 | 1 | 1 | 1 | 1 |
| D | Number of doses needed | B * C | 1,254,028 | 0 | 1,254,028 | 132,776 | 0 | 132,776 |
| E | Estimated vaccine wastage factor | Table 6.(n).3. in NVS section[2] | 1.43 | 1.43 | 1.43 | 1.43 | 1.43 | 1.43 |
| F | Number of doses needed including wastage | D * E | 1,793,261 | 0 | 1,793,261 | 189,870 | 0 | 189,870 |
| G | Vaccines buffer stock | (F - F of previous year) * 0.25 | 0 | 0 | 0 | 0 | 0 | 0 |
| I | Total vaccine doses needed | F + G | 1,793,261 | 0 | 1,793,261 | 189,870 | 0 | 189,870 |
| J | Number of doses per vial | Vaccine parameter | 10 | 10 | 10 | 10 | 10 | 10 |
| K | Number of AD syringes (+ 10% wastage) needed | (D + G) * 1.11 | 1,391,972 | 0 | 1,391,972 | 147,382 | 0 | 147,382 |
| L | Reconstitution syringes (+ 10% wastage) needed | I / J * 1.11 | 199,052 | 0 | 199,052 | 21,076 | 0 | 21,076 |
| M | Total of safety boxes (+ 10% of extra need) needed | (K + L) / 100 x 1.11 | 17,661 | 0 | 17,661 | 1,870 | 0 | 1,870 |
| N | Cost of vaccines needed | I * vaccine price per dose | 430,383 | 0 | 430,383 | 45,569 | 0 | 45,569 |
| O | Cost of AD syringes needed | K * AD syringe price per unit | 73,775 | 0 | 73,775 | 7,812 | 0 | 7,812 |
| P | Cost of reconstitution syringes needed | L * reconstitution price per unit | 7,564 | 0 | 7,564 | 801 | 0 | 801 |
| Q | Cost of safety boxes needed | M * safety box price per unit | 11,304 | 0 | 11,304 | 1,197 | 0 | 1,197 |
| R | Freight cost for vaccines needed | N * freight cost as % of vaccines value | 43,039 | 0 | 43,039 | 4,557 | 0 | 4,557 |
| S | Freight cost for devices needed | (O + P + Q) * freight cost as % of devices value | 9,265 | 0 | 9,265 | 981 | 0 | 981 |
| T | Total fund needed | (N + O + P + Q + R + S) | 575,330 | 0 | 575,330 | 60,917 | 0 | 60,917 |
| U | Total country co-financing | I * country co-financing per dose | 0 |  |  | 0 |  |  |
| V | Country co-financing % of GAVI supported proportion | U / T | 0.00% |  |  | 0.00% |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Where (n) depends on the vaccine

# Table 1.1 D -: Estimated number of doses for Measles, 10 doses/vial, Lyophilised associated injection safety material and related co-financing budget (page 3)

|  |  | Formula | 2016 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Total | Government | GAVI | Total | Government | GAVI |
| A | Country Co-finance |  | 0.00% |  |  |  |  |  |
| B | Number of children to be vaccinated with the first dose[1] | Table 1 (baseline & annual targets) | 1,319,865 | 0 | 1,319,865 |  |  |  |
| C | Number of doses per child | Vaccine parameter (schedule) | 1 | 1 | 1 | 1 | 1 | 1 |
| D | Number of doses needed | B * C | 1,319,865 | 0 | 1,319,865 |  |  |  |
| E | Estimated vaccine wastage factor | Table 6.(n).3. in NVS section[2] | 1.33 | 1.33 | 1.33 |  |  |  |
| F | Number of doses needed including wastage | D * E | 1,755,421 | 0 | 1,755,421 |  |  |  |
| G | Vaccines buffer stock | (F - F of previous year) * 0.25 | 391,388 | 0 | 391,388 |  |  |  |
| I | Total vaccine doses needed | F + G | 2,146,809 | 0 | 2,146,809 |  |  |  |
| J | Number of doses per vial | Vaccine parameter | 10 | 10 | 10 | 10 | 10 | 10 |
| K | Number of AD syringes (+ 10% wastage) needed | (D + G) * 1.11 | 1,899,491 | 0 | 1,899,491 |  |  |  |
| L | Reconstitution syringes (+ 10% wastage) needed | I / J * 1.11 | 238,296 | 0 | 238,296 |  |  |  |
| M | Total of safety boxes (+ 10% of extra need) needed | (K + L) / 100 x 1.11 | 23,730 | 0 | 23,730 |  |  |  |
| N | Cost of vaccines needed | I * vaccine price per dose | 515,235 | 0 | 515,235 |  |  |  |
| O | Cost of AD syringes needed | K * AD syringe price per unit | 100,674 | 0 | 100,674 |  |  |  |
| P | Cost of reconstitution syringes needed | L * reconstitution price per unit | 9,056 | 0 | 9,056 |  |  |  |
| Q | Cost of safety boxes needed | M * safety box price per unit | 15,188 | 0 | 15,188 |  |  |  |
| R | Freight cost for vaccines needed | N * freight cost as % of vaccines value | 51,524 | 0 | 51,524 |  |  |  |
| S | Freight cost for devices needed | (O + P + Q) * freight cost as % of devices value | 12,492 | 0 | 12,492 |  |  |  |
| T | Total fund needed | (N + O + P + Q + R + S) | 704,169 | 0 | 704,169 |  |  |  |
| U | Total country co-financing | I * country co-financing per dose | 0 |  |  |  |  |  |
| V | Country co-financing % of GAVI supported proportion | U / T | 0.00% |  |  |  |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Where (n) depends on the vaccine

# Annex 2

Estimated prices of supply and related freight cost: 2011 from UNICEF Supply Division; 2012 onwards: GAVI Secretariat

Table A - Commodities Cost

| Vaccine | Presentation | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| AD syringe | 0 | 0.053 | 0.053 | 0.053 | 0.053 | 0.053 | 0.053 | 0.053 |
| DTP-HepB | 2 | 1.600 |  |  |  |  |  |  |
| DTP-HepB | 10 | 0.620 | 0.620 | 0.620 | 0.620 | 0.620 | 0.620 | 0.620 |
| DTP-HepB-Hib | WAP | 2.580 | 2.470 | 2.320 | 2.030 | 1.850 | 1.850 | 1.850 |
| DTP-HepB-Hib | WAP | 2.580 | 2.470 | 2.320 | 2.030 | 1.850 | 1.850 | 1.850 |
| DTP-HepB-Hib | WAP | 2.580 | 2.470 | 2.320 | 2.030 | 1.850 | 1.850 | 1.850 |
| DTP-Hib | 10 | 3.400 | 3.400 | 3.400 | 3.400 | 3.400 | 3.200 | 3.200 |
| HepB monoval | 1 |  |  |  |  |  |  |  |
| HepB monoval | 2 |  |  |  |  |  |  |  |
| Hib monoval | 1 | 3.400 |  |  |  |  |  |  |
| Measles | 10 | 0.240 | 0.240 | 0.240 | 0.240 | 0.240 | 0.240 | 0.240 |
| Pneumococcal(PCV10) | 2 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 |
| Pneumococcal(PCV13) | 1 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 |
| Reconstit syringe for Pentaval (2ml) | 0 | 0.032 | 0.032 | 0.032 | 0.032 | 0.032 | 0.032 | 0.032 |
| Reconstit syringe for YF | 0 | 0.038 | 0.038 | 0.038 | 0.038 | 0.038 | 0.038 | 0.038 |
| Rotavirus 2-dose schedule | 1 | 7.500 | 6.000 | 5.000 | 4.000 | 3.600 | 3.600 | 3.600 |
| Rotavirus 3-dose schedule | 1 | 5.500 | 4.000 | 3.333 | 2.667 | 2.400 | 2.400 | 2.400 |
| Safety box | 0 | 0.640 | 0.640 | 0.640 | 0.640 | 0.640 | 0.640 | 0.640 |
| Yellow Fever | WAP | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 |
| Yellow Fever | WAP | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 |

Note: WAP - weighted average price (to be used for any presentation: For DTP-HepB-Hib, it applies to 1 dose liquid, 2 dose lyophilised and 10 dose liquid. For Yellow Fever, it applies to 5 dose lyophilised and 10 dose lyophilised)

Table B - Commodities Freight Cost

| Vaccines | Group | No Threshold | 200’000 $ |  | 250’000 $ |  | 2’000’000 $ |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | <= | > | <= | > | <= | > |
| Yellow Fever | Yellow Fever |  | 20% |  |  |  | 10% | 5% |
| DTP+HepB | HepB and or Hib | 2% |  |  |  |  |  |  |
| DTP-HepB-Hib | HepB and or Hib |  |  |  | 15% | 3,50% |  |  |
| Pneumococcal vaccine (PCV10) | Pneumococcal | 5% |  |  |  |  |  |  |
| Pneumococcal vaccine (PCV13) | Pneumococcal | 5% |  |  |  |  |  |  |
| Rotavirus | Rotavirus | 5% |  |  |  |  |  |  |
| Measles | Measles | 10% |  |  |  |  |  |  |

Table C - Low - Minimum country's co-payment per dose of co-financed vaccine.

| vaccine | 2012 | 2013 | 2014 | 2015 | 2016 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Measles, 10 doses/vial, Lyophilised | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |  |  |

Table D - Wastage rates and factors

Countries are expected to plan for a maximal wastage rate of:

- 50% - for a lyophilised vaccine in 10 or 20-dose vial,

- 25% - for a liquid vaccine in 10 or 20-dose vial or a lyophilised vaccine in 5-dose vial,

- 10% - for a lyophilised/liquid vaccine in 2-dose vial, and

- 5% - for a liquid vaccine in 1-dose vial

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2 | 2.22 | 2.5 |

WHO International shipping guidelines: maximum packed volumes of vaccines

Table E - Vaccine maximum packed volumes

| Vaccine product | Designation | Vaccine formulation | Admin route | No. Of doses in the schedule | Presentation (doses/vial, prefilled) | Packed volume vaccine (cm3/dose) | Packed volume diluents (cm3/dose) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| BCG | BCG | lyophilized | ID | 1 | 20 | 1.2 | 0.7 |
| Diphtheria-Tetanus-Pertussis | DTP | liquid | IM | 3 | 20 | 2.5 |  |
| Diphtheria-Tetanus-Pertussis | DTP | liquid | IM | 3 | 10 | 3.0 |  |
| Diphtheria-Tetanus | DT | liquid | IM | 3 | 10 | 3.0 |  |
| Tetanus-Diphtheria | Td | liquid | IM | 2 | 10 | 3.0 |  |
| Tetanus Toxoid | TT | liquid | IM | 2 | 10 | 3.0 |  |
| Tetanus Toxoid | TT | liquid | IM | 2 | 20 | 2.5 |  |
| Tetanus Toxoid UniJect | TT | liquid | IM | 2 | Uniject | 12.0 |  |
| Measles | Measles | lyophilized | SC | 1 | 1 | 26.1 | 20.0 |
| Measles | Measles | lyophilized | SC | 1 | 2 | 13.1 | 13.1 |
| Measles | Measles | lyophilized | SC | 1 | 5 | 5.2 | 7.0 |
| Measles | Measles | lyophilized | SC | 1 | 10 | 3.5 | 4.0 |
| Measles-Rubella freeze dried | MR | lyophilized | SC | 1 | 1 | 26.1 | 26.1 |
| Measles-Rubella freeze dried | MR | lyophilized | SC | 1 | 2 | 13.1 | 13.1 |
| Measles-Rubella freeze dried | MR | lyophilized | SC | 1 | 5 | 5.2 | 7.0 |
| Measles-Rubella freeze dried | MR | lyophilized | SC | 1 | 10 | 2.5 | 4.0 |
| Measles-Mumps-Rubella freeze dried | MMR | lyophilized | SC | 1 | 1 | 26.1 | 26.1 |
| Measles-Mumps-Rubella freeze dried | MMR | lyophilized | SC | 1 | 2 | 13.1 | 13.1 |
| Measles-Mumps-Rubella freeze dried | MMR | lyophilized | SC | 1 | 5 | 5.2 | 7.0 |
| Measles-Mumps-Rubella freeze dried | MMR | lyophilized | SC | 1 | 10 | 3.0 | 4.0 |
| Polio | OPV | liquid | Oral | 4 | 10 | 2.0 |  |
| Polio | OPV | liquid | Oral | 4 | 20 | 1.0 |  |
| Yellow fever | YF | lyophilized | SC | 1 | 5 | 6.5 | 7.0 |
| Yellow fever | YF | lyophilized | SC | 1 | 10 | 2.5 | 3.0 |
| Yellow fever | YF | lyophilized | SC | 1 | 20 | 1.5 | 2.0 |
| Yellow fever | YF | lyophilized | SC | 1 | 50 | 0.7 | 1.0 |
| DTP-HepB combined | DTP-HepB | liquid | IM | 3 | 1 | 9.7 |  |
| DTP-HepB combined | DTP-HepB | liquid | IM | 3 | 2 | 6.0 |  |
| DTP-HepB combined | DTP-HepB | liquid | IM | 3 | 10 | 3.0 |  |
| Hepatitis B | HepB | liquid | IM | 3 | 1 | 18.0 |  |
| Hepatitis B | HepB | liquid | IM | 3 | 2 | 13.0 |  |
| Hepatitis B | HepB | liquid | IM | 3 | 6 | 4.5 |  |
| Hepatitis B | HepB | liquid | IM | 3 | 10 | 4.0 |  |
| Hepatitis B UniJect | HepB | liquid | IM | 3 | Uniject | 12.0 |  |
| Hib liquid | Hib_liq | liquid | IM | 3 | 1 | 15.0 |  |
| Hib liquid | Hib_liq | liquid | IM | 3 | 10 | 2.5 |  |
| Hib freeze-dried | Hib_lyo | lyophilized | IM | 3 | 1 | 13.0 | 35.0 |
| Hib freeze-dried | Hib_lyo | lyophilized | IM | 3 | 2 | 6.0 |  |
| Hib freeze-dried | Hib_lyo | lyophilized | IM | 3 | 10 | 2.5 | 3.0 |
| DTP liquid + Hib freeze-dried | DTP+Hib | liquid+lyop. | IM | 3 | 1 | 45.0 |  |
| DTP-Hib combined liquid | DTP+Hib | liquid+lyop. | IM | 3 | 10 | 12.0 |  |
| DTP-Hib combined liquid | DTP-Hib | liquid | IM | 3 | 1 | 32.3 |  |
| DTP-HepB liquid + Hib freeze-dried | DTP-Hib | liquid | IM | 3 | 10 | 2.5 |  |
| DTP-HepB liquid + Hib freeze-dried | DTP-HepB+Hib | liquid+lyop. | IM | 3 | 1 | 22.0 |  |
| DTP-HepB-Hib liquid | DTP-HepB+Hib | liquid+lyop. | IM | 3 | 2 | 11.0 |  |
| DTP-HepB-Hib liquid | DTP-HepB-Hib | liquid | IM | 3 | 10 | 4.4 |  |
| DTP-HepB-Hib liquid | DTP-HepB-Hib | liquid | IM | 3 | 2 | 13.1 |  |
| DTP-HepB-Hib liquid | DTP-HepB-Hib | liquid | IM | 3 | 1 | 19.2 |  |
| Meningitis A/C | MV_A/C | lyophilized | SC | 1 | 10 | 2.5 | 4.0 |
| Meningitis A/C | MV_A/C | lyophilized | SC | 1 | 50 | 1.5 | 3.0 |
| Meningococcal A/C/W/ | MV_A/C/W | lyophilized | SC | 1 | 50 | 1.5 | 3.0 |
| Meningococcal A/C/W/Y | MV_A/C/W/Y | lyophilized | SC | 1 | 10 | 2.5 | 4.0 |
| Meningitis W135 | MV_W135 | lyophilized | SC | 1 | 10 | 2.5 | 4.0 |
| Meningitis A conjugate | Men_A | lyophilized | SC | 2 | 10 | 2.6 | 4.0 |
| Japanese Encephalitis | JE_lyo | lyophilized | SC | 3 | 10 | 15.0 |  |
| Japanese Encephalitis | JE_lyo | lyophilized | SC | 3 | 10 | 8.1 | 8.1 |
| Japanese Encephalitis | JE_lyo | lyophilized | SC | 3 | 5 | 2.5 | 2.9 |
| Japanese Encephalitis | JE_lyo | lyophilized | SC | 3 | 1 | 12.6 | 11.5 |
| Japanese Encephalitis | JE_liq | liquid | SC | 3 | 10 | 3.4 |  |
| Rota vaccine | Rota_lyo | lyophilized | Oral | 2 | 1 | 156.0 |  |
| Rota vaccine | Rota_liq | liquid | Oral | 2 | 1 | 17.1 |  |
| Rota vaccine | Rota_liq | liquid | Oral | 3 | 1 | 45.9 |  |
| Pneumo. conjugate vaccine 7-valent | PCV-7 | liquid | IM | 3 | PFS | 55.9 |  |
| Pneumo. conjugate vaccine 7-valent | PCV-7 | liquid | IM | 3 | 1 | 21.0 |  |
| Pneumo. conjugate vaccine 10-valent | PCV-10 | liquid | IM | 3 | 1 | 11.5 |  |
| Pneumo. conjugate vaccine 10-valent | PCV-10 | liquid | IM | 3 | 2 | 4.8 |  |
| Pneumo. conjugate vaccine 13-valent | PCV-13 | liquid | IM | 3 | 1 | 12.0 |  |
| Polio inactivated | IPV | liquid | IM | 3 | PFS | 107.4 |  |
| Polio inactivated | IPV | liquid | IM | 3 | 10 | 2.5 |  |
| Polio inactivated | IPV | liquid | IM | 3 | 1 | 15.7 |  |
| Human Papilomavirus vaccine | HPV | liquid | IM | 3 | 1 | 15.0 |  |
| Human Papilomavirus vaccine | HPV | liquid | IM | 3 | 2 | 5.7 |  |
| Monovalent OPV-1 | mOPV1 | liquid | Oral |  | 20 | 1.5 |  |
| Monovalent OPV-3 | mOPV3 | liquid | Oral |  | 20 | 1.5 |  |

# Attachments

# List of Supporting Documents Attached to this Proposal

| Document | Section | Document Number | Mandatory[1] |
| --- | --- | --- | --- |
| MoH Signature (or delegated authority) of Proposal |  | 1 | Yes |
| MoF Signature (or delegated authority) of Proposal |  | Missing | Yes |
| Signatures of ICC or HSCC or equivalent in Proposal |  | 2 | Yes |
| Minutes of ICC/HSCC meeting endorsing Proposal |  | 3 | Yes |
| comprehensive Multi Year Plan - cMYP |  | 7(No file loaded) | Yes |
| cMYP Costing tool for financial analysis |  | 8(No file loaded) | Yes |
| Minutes of last three ICC/HSCC meetings |  | 4 | Yes |
| Improvement plan based on EVM |  | Missing | Yes |
| WHO/UNICEF Joint Reporting Form (JRF) |  | 6 |  |
| ICC/HSCC workplan for forthcoming 12 months |  |  |  |
| National policy on injection safety |  |  |  |
| Action plans for improving injection safety |  |  |  |
| Plan for NVS introduction (if not part of cMYP) |  |  |  |
| Banking details |  |  |  |

[1] Please indicate the duration of the plan / assessment / document where appropriate

# Attachments

List of all the mandatory and optional documents attached to this form

Note: Use the Upload file arrow icon to upload the document. Use the Delete item icon to delete a line. To add new lines click on the New item icon in the Action column.

| ID | File type | File name |  | New file | Actions |
| --- | --- | --- | --- | --- | --- |
|  | Description | Date and Time | Size |  |  |
| 1 | File Type: MoH Signature (or delegated authority) of Proposal * File Desc: Endorsments from Health Minister and authorised official from Finance Ministry for Measles proposal | File name: I:\Attachment\Myanmar_Health Minister_Finance offical Authroity_sign for Measles_GAVI proposal.JPG Date/Time: 29.05.2011 12:46:26 Size: 1 MB |  |  |  |
| 2 | File Type: Signatures of ICC or HSCC or equivalent in Proposal * File Desc: File with signature of ICC members to endorse Measles proposal | File name: I:\Attachment\ICC members signature_2nd May2011_Myanmar.JPG Date/Time: 29.05.2011 12:50:33 Size: 930 KB |  |  |  |
| 3 | File Type: Minutes of ICC/HSCC meeting endorsing Proposal * File Desc: 2nd may 2011 ICC meeting minutes to endorse measles proposal | File name: C:\Documents and Settings\burav\Desktop\drkkk\Minutes of 2nd May ICC meeting_Myanmar.pdf Date/Time: 29.05.2011 13:17:07 Size: 889 KB |  |  |  |
| 4 | File Type: Minutes of last three ICC/HSCC meetings * File Desc: minutes of past ICC meeting in 2011 | File name: I:\Attachment\ICC Agenda,articipants List & meeting minute (20-1-2011).doc Date/Time: 29.05.2011 13:21:48 Size: 93 KB |  |  |  |
| 5 | File Type: other File Desc: EVM plans for July_Aug 2011 by UNICEF_MOH | File name: C:\Documents and Settings\burav\Desktop\drkkk\EVM planning.msg Date/Time: 29.05.2011 13:24:22 Size: 84 KB |  |  |  |
| 6 | File Type: WHO/UNICEF Joint Reporting Form (JRF) File Desc: 2010_JRF submiited by MOH_Myanmar | File name: C:\Documents and Settings\burav\My Documents\JRF\2010\JRF_2010_MYANMAR.pdf Date/Time: 29.05.2011 13:38:35 Size: 5 MB |  |  |  |
| 7 | File Type: comprehensive Multi Year Plan - cMYP * File Desc: Myanmar's c MYP 2012-2016 | File name: Date/Time: Size: |  |  |  |
| 8 | File Type: cMYP Costing tool for financial analysis * File Desc: New WHO costing tool 2.5 version used for financial analysis | File name: Date/Time: Size: |  |  |  |
| 9 | File Type: other File Desc: | File name: Date/Time: Size: |  |  |  |

Banking Form

| In accordance with the decision on financial support made by the GAVI Alliance, the Government of Myanmar hereby requests that a payment be made via electronic bank transfer as detailed below: |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Name of Institution (Account Holder): |  |  |  |  |  |
| Address: |  |  |  |  |  |
| City Country: |  |  |  |  |  |
| Telephone no.: |  | Fax no.: |  |  |  |
| Currency of the bank account: |  |  |  |  |  |
| For credit to: |  |  |  |  |  |
| Bank account's title: |  |  |  |  |  |
| Bank account no.: |  |  |  |  |  |
| Bank's name: |  |  |  |  |  |

Is the bank account exclusively to be used by this program?

By who is the account audited?

Signature of Government’s authorizing official

| Name: |  | Seal |
| --- | --- | --- |
| Title: |  |  |
| Signature: |  |  |
| Date: |  |  |

| FINANCIAL INSTITUTION |  | CORRESPONDENT BANK (In the United States) |  |
| --- | --- | --- | --- |
| Bank Name: |  |  |  |
| Branch Name: |  |  |  |
| Address: |  |  |  |
| City Country: |  |  |  |
| Swift Code: |  |  |  |
| Sort Code: |  |  |  |
| ABA No.: |  |  |  |
| Telephone No.: |  |  |  |
| FAX No.: |  |  |  |

I certify that the account no is held by (Institution name) at this banking institution.

| The account is to be signed jointly by at least 0 (number of signatories) of the following authorized signatories: |  |  |
| --- | --- | --- |
| 1 |  |  |
|  | Name: |  |
|  | Title: |  |
| 2 |  |  |
|  | Name: |  |
|  | Title: |  |
| 3 |  |  |
|  | Name: |  |
|  | Title: |  |
| 4 |  |  |
|  | Name: |  |
|  | Title: |  |

Name of bank’s authorizing official

Signature:

Date:

Seal: