GAVI Alliance

Application Form for Country Proposals

For Support to New and Under-Used Vaccines (NVS)

Submitted by

The Government of

Angola

Date of submission: 01.06.2011 18:31:10

Deadline for submission: 1 Jun 2011

Select Start and End Year of your Comprehensive Multi-Year Plan (cMYP)

| Start Year | 2011 | End Year | 2015 |
| --- | --- | --- | --- |

Revised in January 2011

(To be used with Guidelines of December 2010)

Please submit the Proposal using the online platform https://AppsPortal.gavialliance.org/PDExtranet.

Enquiries to: proposals@gavialliance.org or representatives of a GAVI partner agency. The documents can be shared with GAVI partners, collaborators and general public. The Proposal and attachments must be submitted in English, French, Spanish, or Russian.

Note: Please ensure that the application has been received by the GAVI Secretariat on or before the day of the deadline.

The GAVI Secretariat is unable to return submitted documents and attachments to countries. Unless otherwise specified, documents will be shared with the GAVI Alliance partners and the general public.

GAVI ALLIANCE GRANT TERMS AND CONDITIONS FUNDING USED SOLELY FOR APPROVED PROGRAMMES The applicant country (“Country”) confirms that all funding provided by the GAVI Alliance will be used and applied for the sole purpose of fulfilling the programme(s) described in the Country’s application. Any significant change from the approved programme(s) must be reviewed and approved in advance by the GAVI Alliance. All funding decisions for the application are made at the discretion of the GAVI Alliance Board and are subject to IRC processes and the availability of funds. AMENDMENT TO THE APPLICATION The Country will notify the GAVI Alliance in its Annual Progress Report if it wishes to propose any change to the programme(s) description in its application. The GAVI Alliance will document any change approved by the GAVI Alliance, and the Country’s application will be amended. RETURN OF FUNDS The Country agrees to reimburse to the GAVI Alliance all funding amounts that are not used for the programme(s) described in its application. The country’s reimbursement must be in US dollars and be provided, unless otherwise decided by the GAVI Alliance, within sixty (60) days after the Country receives the GAVI Alliance’s request for a reimbursement and be paid to the account or accounts as directed by the GAVI Alliance. SUSPENSION/ TERMINATION The GAVI Alliance may suspend all or part of its funding to the Country if it has reason to suspect that funds have been used for purpose other than for the programmes described in the Country’s application, or any GAVI Alliance-approved amendment to the application. The GAVI Alliance retains the right to terminate its support to the Country for the programmes described in its application if a misuse of GAVI Alliance funds is confirmed. ANTICORRUPTION The Country confirms that funds provided by the GAVI Alliance shall not be offered by the Country to any third person, nor will the Country seek in connection with its application any gift, payment or benefit directly or indirectly that could be construed as an illegal or corrupt practice. AUDITS AND RECORDS The Country will conduct annual financial audits, and share these with the GAVI Alliance, as requested. The GAVI Alliance reserves the right, on its own or through an agent, to perform audits or other financial management assessment to ensure the accountability of funds disbursed to the Country. The Country will maintain accurate accounting records documenting how GAVI Alliance funds are used. The Country will maintain its accounting records in accordance with its government-approved accounting standards for at least three years after the date of last disbursement of GAVI Alliance funds. If there is any claims of misuse of funds, Country will maintain such records until the audit findings are final. The Country agrees not to assert any documentary privilege against the GAVI Alliance in connection with any audit. CONFIRMATION OF LEGAL VALIDITY The Country and the signatories for the Country confirm that its application, and Annual Progress Report, are accurate and correct and form legally binding obligations on the Country, under the Country’s law, to perform the programmes described in its application, as amended, if applicable, in the APR. CONFIRMATION OF COMPLIANCE WITH THE GAVI ALLIANCE TRANSPARANCY AND ACCOUNTABILITY POLICY The Country confirms that it is familiar with the GAVI Alliance Transparency and Accountability Policy (TAP) and complies with the requirements therein. USE OF COMMERCIAL BANK ACCOUNTS The Country is responsible for undertaking the necessary due diligence on all commercial banks used to manage GAVI cash-based support. The Country confirms that it will take all responsibility for replenishing GAVI cash support lost due to bank insolvency, fraud or any other unforeseen event. ARBITRATION Any dispute between the Country and the GAVI Alliance arising out of or relating to its application that is not settled amicably within a reasonable period of time, will be submitted to arbitration at the request of either the GAVI Alliance or the Country. The arbitration will be conducted in accordance with the then-current UNCITRAL Arbitration Rules. The parties agree to be bound by the arbitration award, as the final adjudication of any such dispute. The place of arbitration will be Geneva, Switzerland. The language of the arbitration will be English. For any dispute for which the amount at issue is US$ 100,000 or less, there will be one arbitrator appointed by the GAVI Alliance. For any dispute for which the amount at issue is greater than US $100,000 there will be three arbitrators appointed as follows: The GAVI Alliance and the Country will each appoint one arbitrator, and the two arbitrators so appointed will jointly appoint a third arbitrator who shall be the chairperson. The GAVI Alliance will not be liable to the country for any claim or loss relating to the programmes described in the application, including without limitation, any financial loss, reliance claims, any harm to property, or personal injury or death. Country is solely responsible for all aspects of managing and implementing the programmes described in its application.

# Application Specification

Please specify for which type of GAVI support you would like to apply to.

Important note: To enable proper functioning of the form, please first select the cMYP years on the previous page.

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Type of Support | Vaccine | Start Year | End Year | Preferred second presentation[1] | Action |
| --- | --- | --- | --- | --- | --- |
| New Vaccines Support | Pneumococcal (PCV13), 1 doses/vial, Liquid | 2012 | 2015 | Pneumococcal (PCV10), 2 doses/vial, Liquid |  |
| New Vaccines Support | Rotavirus 2-dose schedule | 2013 | 2015 |  |  |

[1] This "Preferred second presentation" will be used in case there is no supply available for the preferred presentation of the selected vaccine ("Vaccine" column). If left blank, it will be assumed that the country will prefer waiting until the selected vaccine becomes available.

# Table of Contents

Sections

Main

Cover Page

GAVI Alliance Grants Terms and Conditions

1. Application Specification

2. Table of Contents

3. Executive Summary

4. Signatures

4.1. Signatures of the Government and National Coordinating Bodies

4.1.1. Government and the Inter-Agency Coordinating Committee for Immunisation

4.1.2. National Coordinating Body - Inter-Agency Coordinating Committee for Immunisation

4.1.3. The Inter-Agency Coordinating Committee for Immunisation

4.2. National Immunization Technical Advisory Group for Immunisation

4.2.1. The NITAG Group for Immunisation

5. Immunisation Programme Data

5.1. Basic facts

5.2. Current vaccination schedule

5.3. Trends of immunisation coverage and disease burden

5.4. Baseline and Annual Targets

Table 1: baseline figures

5.5. Summary of current and future immunisation budget

5.6. Summary of current and future financing and sources of funds

6. NVS

6.1. Capacity and cost (for positive storage)

6.2. Assessment of burden of relevant diseases (if available)

6.3.1. Requested vaccine ( Pneumococcal (PCV13), 1 doses/vial, Liquid )

6.3.2. Co-financing information

6.3.3. Wastage factor

6.3.4. Specifications of vaccinations with new vaccine

6.3.5. Portion of supply to be procured by the country (and cost estimate, US$)

6.3.6. Portion of supply to be procured by the GAVI Alliance (and cost estimate, US$)

6.3.7. New and Under-Used Vaccine Introduction Grant

6.4.1. Requested vaccine ( Rotavirus 2-dose schedule )

6.4.2. Co-financing information

6.4.3. Wastage factor

6.4.4. Specifications of vaccinations with new vaccine

6.4.5. Portion of supply to be procured by the country (and cost estimate, US$)

6.4.6. Portion of supply to be procured by the GAVI Alliance (and cost estimate, US$)

6.4.7. New and Under-Used Vaccine Introduction Grant

7. Procurement and Management of New and Under-Used Vaccines

7.1. Vaccine management (EVSM/EVM/VMA)

8. Additional Comments and Recommendations

9. Annexes

Annex 1

Annex 1.1 - Pneumococcal (PCV13), 1 doses/vial, Liquid

Table 1.1  A - Rounded up portion of supply that is procured by the country and estimate of related cost in US$

Table 1.1  B - Rounded up portion of supply that is procured by GAVI and estimate of related cost in US$.

Table 1.1  C - Summary table for vaccine Pneumococcal (PCV13), 1 doses/vial, Liquid

Table 1.1  D - Estimated number of doses for vaccine Pneumococcal (PCV13), 1 doses/vial, Liquid associated injection safety material and related co-financing budget

Annex 1.2 - Rotavirus 2-dose schedule

Table 1.2  A - Rounded up portion of supply that is procured by the country and estimate of related cost in US$

Table 1.2  B - Rounded up portion of supply that is procured by GAVI and estimate of related cost in US$.

Table 1.2  C - Summary table for vaccine Rotavirus 2-dose schedule

Table 1.2  D - Estimated number of doses for vaccine Rotavirus 2-dose schedule associated injection safety material and related co-financing budget

Annex 2

10. Attachments

10.1 Documents required for NVS support

10.2 Attachments

Banking Form

# Executive Summary

The Republic of Angola is one of the largest countries on the African continent, situated on the west coast of southern Africa, with a land area of 1,246,700 km2. Its total population was estimated for the year 2011 in 20.867.981 inhabitants. The main demographic ndicators are:
- Births: 1,043,399 (5% Estimated Birth Rate for 2011) 
- Surviving infants: 907.757 (4,35% of total population)
- Pregnant women: 1,043,399 (5% of total population)
- Annual population growth: 2.8%

The Government of the Republic of Angola gives great importance to the provision of sound primary health care services to its population in order to reduce one of the world’s highest child mortality rates. 

The Angolan Government policy of administrative decentralization is creating enabling environment at municipal level (district) to overcome the inequalities in health. Ministry of Health strategy of “Revitalization of District Health System” is in process of expansion to deliver countrywide an integrated package of basic preventive and curative health care services through the public health facility network, complemented by outreach and mobile team activities to cover hard to reach population. 

Angola has received support from GAVI for strengthening immunization services from 2003 to 2007 and for the introduction of pentavalent vaccine countrywide in 2006. This support from GAVI had contributed to improving both quality and quantity of country performance. The national immunization coverage (DTP/Pentavalent-3) was increased from 46% in 2006 to 91% in 2010. The number of health districts with vaccine coverage above 80% was gradually improved from 16/164 in 2006 to 99/164 in 2010.
The Angolan comprehensive EPI Multiyear Plan updated for the period of 2011-2015 intends to increase and sustain national immunization coverage over 90% and achieves at least 80% of immunization coverage in every district with all traditional, underused and new vaccines included in the national immunization schedule. 

The strategies proposed by the EPI Multiyear Plan to overcome the system barriers taken into account field-based lessons from program implementation in the past ten years, and are oriented to create conditions for immunization sustainability due that form relevant part of the government policy of strengthening of the municipal(district) health system.

The priorities for 2011-2015 aimed at improvement of immunization coverage, introduction of new vaccines and immunization safety improvement namely: (1) human resource capacity building giving priority to local level; (2) increasing the cold chain store capacity, to storage all the planned vaccines and improve immunization waste disposal; (3) Increase community demand for immunization; (4) strengthening of integrated disease surveillance and routine immunization data quality. 

The introduction of Pneumo and Rotavirus vaccines is one of the key priority interventions of EPI Multiyear Plan, that will address the second and third leading causes of child dead in the Country and will contribute to achievement of the Millennium Development Goal of reduction by one third the children under 5 years old mortality. MoH Planning Directorate, Maternal and Child Health Program, development partners including pediatric society and "Immunization Enlarged Technical Committee" participated in the elaboration of EPI Multiyear Plan and fully endorse the introduction of Pneumo and Rotavirus vaccines.

The expected results are: (1) Stop Poliovirus transmission in the Country (2) Reduce measles mortality rate by 98%, (3) Achieve virtual elimination of maternal and neonatal tetanus, (4) Reduce the mortality and morbidity by pneumonia and meningitis caused by Streptococcus pneumonia and Haemophilus influenzae type b, reduce severe diarrhoeal disease and mortality caused by Rotavirus, and burden of disease of Tuberculosis, Hepatitis B, Diphtheria, Whooping cough and Yellow Fever diseases. 

Angolan economy was one of the fastest growing economies in the world, therefore has conditions to provide financial sustainability and in order to build upon its successes the Government of Angola endorsed by "Immunization Enlarged Technical Committee", and EPI Interagency Coordination Committee, would like to provide additional life saving vaccines to his population through its routine immunization program. 

The Government of Republic of Angola, consequently request assistance from GAVI for the period 2012 - 2015 to introduce countrywide Pneumococcal vaccine (PCV-13 liquid monodoses)at the end quarter of 2012 and Rotavirus vaccine (2 doses schedule vial mono dose) Contrywide and at the end quarter of 2013 these vaccines will be administered into the routine immunization system.

The Angolan Goverment will co-finance the cost of these new vaccines starting in the first year of support, having planned to cover 100% of the costs of both new vaccines in 2017.The total ammount requested to GAVI untill 2015 for Pneumo vaccine is estimated in USD 26,509,000 and for Rotavirus vaccine USD 17,300,000. The estimated Angolan Goverment co-finance amount for Pneumo vaccine is USD 22,402,500 and for Rotavírus vaccine USD 8,262,000.

# Signatures

# Signatures of the Government and National Coordinating Bodies

# Government and the Inter-Agency Coordinating Committee for Immunisation

The Government of Angola would like to expand the existing partnership with the GAVI Alliance for the improvement of the infants routine immunisation programme of the country, and specifically hereby requests for GAVI support for Pneumococcal (PCV13) 1 doses/vial Liquid , Rotavirus 2-dose schedule introduction.

The Government of Angola commits itself to developing national immunisation services on a sustainable basis in accordance with the Comprehensive Multi-Year Plan (cMYP) presented with this document. The Government requests that the GAVI Alliance and its partners contribute financial and technical assistance to support immunisation of children as outlined in this application.

Tables 6.(n).5. (where (n) depends on the vaccine) in the NVS section of this application shows the amount of support in either supply or cash that is required from the GAVI Alliance. Tables 6.(n).4. of this application shows the Government financial commitment for the procurement of this new vaccine (NVS support only).

Following the regulations of the internal budgeting and financing cycles the Government will annually release its portion of the co-financing funds in the month of September .

Please note that this application will not be reviewed or approved by the Independent Review Committee (IRC) without the signatures of both the Minister of Health & Minister of Finance or their delegated authority.

Enter the family name in capital letters.

| Minister of Health (or delegated authority) |  | Minister of Finance (or delegated authority) |  |
| --- | --- | --- | --- |
| Name | Dr. José VIEIRA DÍAS VAN DÚNEM | Name | Dr. Carlos Alberto LÓPES |
| Date |  | Date |  |
| Signature |  | Signature |  |

This report has been compiled by

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

Enter the family name in capital letters.

| Full name | Position | Telephone | Email | Action |
| --- | --- | --- | --- | --- |
| Dr. Alda MORAIS PEDRO DE SOUSA | EPI Manager | 244 912 501232 | aldamorais@yahoo.com.br |  |

# National Coordinating Body - Inter-Agency Coordinating Committee for Immunisation

We the members of the ICC, HSCC, or equivalent committee[1] met on the 26.05.2011 to review this proposal. At that meeting we endorsed this proposal on the basis of the supporting documentation which is attached.

[1] Inter-agency Coordinating Committee or Health Sector Coordinating Committee, or equivalent committee which has the authority to endorse this application in the country in question.

The endorsed minutes of this meeting are attached as DOCUMENT NUMBER: 4.

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

Enter the family name in capital letters.

| Name/Title | Agency/Organisation | Signature | Action |
| --- | --- | --- | --- |
| Evelise FRESTA/ Vice-Minister of Health | MoH |  |  |
| Adelaide de CARVALHO/National Director of Public Health | MoH |  |  |
| Rui GAMA VAZ/ Representative | WHO |  |  |
| Koenraad VANORMELINGEN/Representative | UNICEF |  |  |
| Heather SMITH/Health Officer | USAID |  |  |
| Silvia NAGY/ Representative Rotary | Rotary International |  |  |
| Ana PINTO /National Coordinator | CORE GROUP |  |  |
| Walter QUIFICA/Secretary General | Red Cross |  |  |

In case the GAVI Secretariat has queries on this submission, please contact

Enter the family name in capital letters.

| Name | Adelaide de CARVALHO | Title | National Director of Public Health |
| --- | --- | --- | --- |
| Tel no | +244 912213724 |  |  |
| Fax no | +244 222330435 | Address | Rua 1º Congresso do MPLA Nº67 Maianga- Luanda Angola |
| Email | laide67@hotmail.com |  |  |

# The Inter-Agency Coordinating Committee for Immunisation

Agencies and partners (including development partners and NGOs) supporting immunisation services are co-ordinated and organised through an inter-agency coordinating mechanism (ICC, HSCC, or equivalent committee). The ICC, HSCC, or equivalent committee is responsible for coordinating and guiding the use of the GAVI NVS support. Please provide information about the ICC, HSCC, or equivalent committee in your country in the table below.

Profile of the ICC, HSCC, or equivalent committee

| Name of the committee | Inter Agency Coordination Committee |
| --- | --- |
| Year of constitution of the current committee | 1995 |
| Organisational structure (e.g., sub-committee, stand-alone) | a) Technical Sub-Commission b) Logistic Sub-Commission c) Social Mobilization Sub-Commission |
| Frequency of meetings | Weekly/By Monthly |

Composition

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

Enter the family name in capital letters.

| Function | Title / Organisation | Name |  |
| --- | --- | --- | --- |
| Chair | Vice Minister of Health | Evelise FRESTA |  |
| Secretary | National Director of Public Health/MoH | Adelaide de CARVALHO |  |
| Members | Representative WHO | Rui GAMA VAZ | Action |
|  | Representative UNICEF | Koenraad VANORMELINGEN |  |
|  | Health Officer/UNICEF | Heather SMITH |  |
|  | Representative ROTARY INTERNATIONAL | Silvia NAGY |  |
|  | National Coordinator CORE GRUP | Ana PINTO |  |
|  | Secretary General RED CROSS | Walter QUIFICA |  |

Major functions and responsibilities of the committee

• Coordination • Resource mobilization • Follow up programme implementation • Review plans and budgets • Advocacy and promotion of social mobilization • Give orientations

Three major strategies to enhance the committee's role and functions in the next 12 months

| 1. | Ensure that regular meetings are held as planned |
| --- | --- |
| 2. | Ensure that the minutes and support documentation are circulated to members in advance |
| 3. | Ensure that the ICC is periodically briefed about the level of implementation of planned immunization and surveillance activities |

# National Immunization Technical Advisory Group for Immunisation

(If it has been established in the country)

We the members of the NITAG met on the 24.05.2011 to review this proposal. At that meeting we endorsed this proposal on the basis of the supporting documentation which is attached.

The endorsed minutes of this meeting are attached as DOCUMENT NUMBER: 5.

In case the GAVI Secretariat has queries on this submission, please contact

Enter the family name in capital letters.

| Name | Margarida Maria ALACOQUE | Title | Coordinator |
| --- | --- | --- | --- |
| Tel no | +244 928133460 |  |  |
| Fax no |  | Address | Rua Comandante Stora Nº 93/95 Alvalade Maianga - Luanda P BOX 12227 |
| Email | waendelao@gmail.com |  |  |

# The NITAG Group for Immunisation

Profile of the NITAG

| Name of the NITAG | Immunization Technical Committee |
| --- | --- |
| Year of constitution of the current NITAG | 2008 |
| Organisational structure (e.g., sub-committee, stand-alone) | Stand-alone |
| Frequency of meetings | Quarterly |

Composition

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

Enter the family name in capital letters.

| Function | Title / Organisation | Name |  |
| --- | --- | --- | --- |
| Chair | Coordinator/ Pediatric Association | Margarida Maria ALACOQUE GASPAR CORREIA |  |
| Secretary | Othon Pediatric Clinique | Xiomara TOMAS |  |
| Members | Pediatric Association / University Agostinho Neto | Francisco DOMINGOS | Action |
|  | Pediatric Association / University Agostinho Neto | Cesar FREITAS |  |
|  | Luanda Provincial Directorate of Health | Isilda NEVES |  |
|  | Pediatric Association | Elsa M. C. BARBOSA GOMES |  |

Major functions and responsibilities of the NITAG

1. Give technical advisory on immunization to Ministry of Health 2. Analyze immunization technical documents and reports and give recommendations 3. Organize technical events for share information

Three major strategies to enhance the NITAG’s role and functions in the next 12 months

| 1. | Include members with Public Health an Epidemiology Background |
| --- | --- |
| 2. | Share with Immunization Technical Committee WHO Technical docs & MoH reports, bulletins and EPI montlhy performance indicators (immunization and surveillance) |
| 3. | Invite to Inmmunization Technical Committe relevant individuals from other provinces than Luanda |

# Immunisation Programme Data

Please complete the tables below, using data from available sources. Please identify the source of the data, and the date. Where possible use the most recent data and attach the source document.

- Please refer to the Comprehensive Multi-Year Plan for Immunisation (cMYP) (or equivalent plan) and attach a complete copy (with an Executive Summary) as DOCUMENT NUMBER 6

- Please refer to the two most recent annual WHO/UNICEF Joint Reporting Forms (JRF) on Vaccine Preventable Diseases.

- Please refer to Health Sector Strategy documents, budgetary documents, and other reports, surveys etc, as appropriate.

# Basic facts

For the year 2010 (most recent; specify dates of data provided)

|  | Figure |  | Year | Source |
| --- | --- | --- | --- | --- |
| Total population | 20,299,592 |  | 2010 | Ministry of Health - EPI |
| Infant mortality rate (per 1000) | 130 |  | 2010 | WHO Global Health Statistics (Before this report available was utilized in 2010 previous rate 150 per 1000 |
| Surviving Infants[1] | 862,733 |  | 2010 | Ministry of Health - EPI |
| GNI per capita (US$) | 4,793 |  | 2010 | http://www.who.int/nha/country |
| Total Health Expenditure (THE) as a percentage of GDP | 86.00 | % | 2010 | http://www.who.int/nha/country |
| General government expenditure on health (GGHE) as % of General government expenditure | 80.30 | % | 2010 | http://www.who.int/nha/country |

[1] Surviving infants = Infants surviving the first 12 months of life

Please provide some additional information on the planning and budgeting context in your country; also indicate the name and date of the relevant planning document for health

The national cicle of plannning is every five years. 2011-2015 The operational planning and budgeting is annual The main guiding document of Ministry of Health is the Project for Strenthening of Municipal Health System.2011-2015

Is the cMYP (or updated Multi-Year Plan) aligned with this document (timing, content, etc.)?

The EPI Multiyear Plan 2011-2015 is aligned in timing and in strategies with the Angolan Government ongoing strategy of decentralization to the municipal level, is aligned too with the orientations of national Health Policy document approved by Presidential Decree, and with the Project for Strengthening the Municipal Health System supported by the World Bank (ProjectID P111840, September 2010- December 2015.See attachment Nº14 The EPI Multiyear Plan intend to strengthen the municipalities (districts) through the RED strategy mplementation and enhance the health services package of delivery integrating the Pneumo and Rotavirus vaccines that will increase the power of the health package for the reduction of child mortality.

Please indicate the national planning budgeting cycle for health

Five years 2011-2015 and annual

Please indicate the national planning cycle for immunisation

Five years 2011-2015 Annual plan of action.

Please indicate if sex disaggregated data (SDD) is used in immunisation routine reporting systems

The routine immunization data was not segregated by sex, because was not observed sex inequalities in the access to immunization services.

Please indicate if gender aspects relating to introduction of a new vaccine have been addressed in the introduction plan

The gender aspects will be addressed during the mid term evaluation, on immunization coverage surveys, in his surveys will be included the sex segregation of immunization indicators.

# Current vaccination schedule

Traditional, New Vaccines and Vitamin A supplement (refer to cMYP pages)

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Vaccine (do not use trade name) | Ages of administration (by routine immunisation services) | Given in entire country | Comments | Action |
| --- | --- | --- | --- | --- |
| BCG | At birth | Yes | One dose |  |
| Polio | At birth, 2, 4 & 6 Months | Yes | 4 doses |  |
| Penta | At 2, 4 & 6 Months | Yes | 3 doses |  |
| Measles | At 9 Months | Yes | 1 dose |  |
| Yellow Fewer | At 9 Months | Yes | 1 dose |  |
| TT | Pregnant and women at childbearing age (15-49 year old) | Yes | CBAW 5 doses. Pregant womwn >=2 doses of TT |  |
| Vitamin A | 6-59 Months | Yes | 2 doses by year |  |

# Trends of immunisation coverage and disease burden

(as per last two annual WHO/UNICEF Joint Reporting Form on Vaccine Preventable Diseases)

| Trends of immunisation coverage (percentage) |  |  |  |  |  | Vaccine preventable disease burden |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Vaccine |  | Reported |  | Survey |  | Disease | Number of reported cases |  |
|  |  | 2009 | 2010 | 2009 | 2009 |  | 2009 | 2010 |
| BCG |  | 83 | 93 |  |  | Tuberculosis | 22,488 | 21,145 |
| DTP | DTP1 | 93 | 108 |  |  | Diphtheria | 0 | 0 |
|  | DTP3 | 73 | 91 |  |  | Pertussis | 1,127 | 2,539 |
| Polio 3 |  | 73 | 92 |  |  | Polio | 33 | 33 |
| Measles (first dose) |  | 77 | 93 |  |  | Measles | 2,807 | 1,190 |
| TT2+ (Pregnant women) |  | 77 | 87 |  |  | NN Tetanus | 66 | 13 |
| Hib3 |  | 73 | 91 |  |  | Hib[2] | 6 | 1 |
| Yellow Fever |  | 40 | 40 |  |  | Yellow fever | 0 | 0 |
| HepB3 |  | 73 | 91 |  |  | HepBsero-prevalence[1] | 80 |  |
| Vitamin A supplement Mothers (< 6 weeks post-delivery) |  | 35 | 46 |  |  |  |  |  |
| Vitamin A supplement Infants (>6 months) |  | 14 | 19 |  |  |  |  |  |

[1] If available

[2] Note: JRF asks for Hib meningitis

If survey data is included in the table above, please indicate the years the surveys were conducted, the full title and if available, the age groups the data refers to

Not available immunization surveys

# Baseline and Annual Targets

(refer to cMYP pages)

Table 1: baseline figures

| Number | Base Year | Baseline and Targets |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2010 | 2012 | 2013 | 2014 | 2015 |  |  |
| Total births | 1,014,980 | 1,072,614 | 1,102,647 | 1,133,522 | 1,165,260 |  |  |
| Total infants' deaths | 152,247 | 139,440 | 143,344 | 147,358 | 151,484 |  |  |
| Total surviving infants | 862,733 | 933,174 | 959,303 | 986,164 | 1,013,776 |  |  |
| Total pregnant women | 1,014,980 | 1,072,614 | 1,102,647 | 1,133,522 | 1,165,260 |  |  |
| Number of infants vaccinated (to be vaccinated) with BCG | 939,341 | 997,531 | 1,036,489 | 1,065,510 | 1,106,997 |  |  |
| BCG coverage (%)[1] | 93% | 93% | 94% | 94% | 95% |  |  |
| Number of infants vaccinated (to be vaccinated) with OPV3 | 790,045 | 867,852 | 901,745 | 926,994 | 963,087 |  |  |
| OPV3 coverage (%)[2] | 92% | 93% | 94% | 94% | 95% |  |  |
| Number of infants vaccinated (or to be vaccinated) with DTP1[3] | 933,759 | 933,174 | 959,303 | 986,164 | 1,013,776 |  |  |
| Number of infants vaccinated (to be vaccinated) with DTP3[3] | 783,757 | 867,852 | 901,745 | 926,994 | 963,087 |  |  |
| DTP3 coverage (%)[2] | 91% | 93% | 94% | 94% | 95% |  |  |
| Wastage[1] rate in base-year and planned thereafter for DTP (%) | 5% | 15% | 15% | 15% | 15% |  |  |
| Wastage[1] factor in base-year and planned thereafter for DTP | 1.05 | 1.18 | 1.18 | 1.18 | 1.18 |  |  |
| Target population vaccinated with 1st dose of Pneumococcal |  | 933,174 | 959,303 | 986,164 | 1,013,776 |  |  |
| Target population vaccinated with 3rd dose of Pneumococcal |  | 867,852 | 901,745 | 926,994 | 963,087 |  |  |
| Pneumococcal coverage (%)[2] | 0% | 93% | 94% | 94% | 95% |  |  |
| Target population vaccinated with 1st dose of Rotavirus |  |  | 767,443 | 838,239 | 912,399 |  |  |
| Target population vaccinated with last dose of Rotavirus |  |  | 671,512 | 739,623 | 811,021 |  |  |
| Rotavirus coverage (%)[2] | 0% | 0% | 70% | 75% | 80% |  |  |
| Infants vaccinated (to be vaccinated) with 1st dose of Measles | 801,168 | 867,852 | 901,745 | 926,994 | 963,087 |  |  |
| Measles coverage (%)[2] | 93% | 93% | 94% | 94% | 95% |  |  |
| Pregnant women vaccinated with TT+ | 882,432 | 997,531 | 1,036,489 | 1,065,510 | 1,106,997 |  |  |
| TT+ coverage (%)[4] | 87% | 93% | 94% | 94% | 95% |  |  |
| Vit A supplement to mothers within 6 weeks from delivery | 304,494 | 653,222 | 1,014,436 | 1,054,175 | 1,083,692 |  |  |
| Vit A supplement to infants after 6 months | 683,950 | 746,539 | 882,559 | 917,132 | 942,812 |  |  |
| Annual DTP Drop-out rate[ ( DTP1 - DTP3 ) / DTP1 ] x 100[5] | 16% | 7% | 6% | 6% | 5% |  |  |

[1] Number of infants vaccinated out of total births

[2] Number of infants vaccinated out of total surviving infants

[3] Indicate total number of children vaccinated with either DTP alone or combined

[4] Number of pregnant women vaccinated with TT+ out of total pregnant women

[5] The formula to calculate a vaccine wastage rate (in percentage):[ ( A – B ) / A ] x 100. Whereby: A = the number of doses distributed for use according to the supply records with correction for stock balance at the end of the supply period; B = the number of vaccinations with the same vaccine in the same period.

# Summary of current and future immunisation budget

(or refer to cMYP pages)

|  | Estimated costs per annum in US$ (in thousand US$) |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Cost category | Base Year | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |  |
|  | 2010 | 2012 | 2013 | 2014 | 2015 |  |  |  |  |  |
| Routine Recurrent Cost |  |  |  |  |  |  |  |  |  |  |
| Vaccines (routine vaccines only) | 9,987,800 | 22,044,873 | 32,445,162 | 28,909,758 | 28,680,747 |  |  |  |  |  |
| Traditional vaccines | 1,472,957 | 1,150,021 | 1,223,779 | 1,232,622 | 1,288,370 |  |  |  |  |  |
| New and underused vaccines | 8,514,843 | 20,894,852 | 31,221,383 | 27,677,136 | 27,392,377 |  |  |  |  |  |
| Injection supplies | 1,033,451 | 1,400,632 | 1,410,803 | 1,455,160 | 1,518,487 |  |  |  |  |  |
| Personnel | 1,738,808 | 2,558,294 | 2,915,518 | 3,318,603 | 3,699,279 |  |  |  |  |  |
| Salaries of full-time NIP health workers (immunisation specific) | 134,217 | 355,909 | 391,500 | 430,650 | 473,715 |  |  |  |  |  |
| Per-diems for outreach vaccinators / mobile teams | 1,604,591 | 2,202,385 | 2,524,018 | 2,887,953 | 3,225,564 |  |  |  |  |  |
| Transportation | 963,213 | 703,144 | 612,123 | 551,549 | 497,736 |  |  |  |  |  |
| Maintenance and overheads | 902,713 | 1,602,896 | 1,949,068 | 2,247,523 | 497,736 |  |  |  |  |  |
| Training | 188,075 | 322,261 | 203,038 | 103,318 | 108,484 |  |  |  |  |  |
| Social mobilisation and IEC | 106,300 | 446,513 | 358,864 | 218,791 | 229,731 |  |  |  |  |  |
| Disease surveillance | 1,200,800 | 1,391,133 | 1,485,687 | 1,586,812 | 1,694,976 |  |  |  |  |  |
| Program management | 255,780 | 420,948 | 524,192 | 485,171 | 607,287 |  |  |  |  |  |
| Other | 238,137 | 289,457 | 319,126 | 351,837 | 387,900 |  |  |  |  |  |
| Subtotal Recurrent Costs | 16,615,077 | 31,180,151 | 42,223,581 | 39,228,522 | 37,922,363 |  |  |  |  |  |
| Routine Capital Costs |  |  |  |  |  |  |  |  |  |  |
| Vehicle | 197,200 | 353 | 424,385 | 473,804 | 314 |  |  |  |  |  |
| Cold chain equipment | 757,771 |  | 1,369,185 | 1,530,414 |  |  |  |  |  |  |
| Other capital equipment | 56,684 | 180 | 180,205 | 180,205 | 180 |  |  |  |  |  |
| Subtotal Capital Costs | 1,011,655 | 533 | 1,973,775 | 2,184,423 | 494 |  |  |  |  |  |
| Campaigns |  |  |  |  |  |  |  |  |  |  |
| Polio | 14,471,126 | 13,319,932 | 14,194,254 | 15,132,868 | 16,140,730 |  |  |  |  |  |
| Measles |  |  |  |  | 8,698,418 |  |  |  |  |  |
| Yellow Fever |  |  |  |  |  |  |  |  |  |  |
| MNT campaigns |  |  |  |  |  |  |  |  |  |  |
| Other campaigns |  |  |  |  |  |  |  |  |  |  |
| Subtotal Campaign Costs | 14,471,126 | 13,319,932 | 14,194,254 | 15,132,868 | 24,839,148 |  |  |  |  |  |
| GRAND TOTAL | 32,097,858 | 44,500,616 | 58,391,610 | 56,545,813 | 62,762,005 |  |  |  |  |  |

# Summary of current and future financing and sources of funds

Please list in the tables below the funding sources for each type of cost category (if known). Please try and indicate which immunisation program costs are covered from the Government budget, and which costs are covered by development partners (or the GAVI Alliance), and name the partners (or refer to cMYP).

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

|  |  | Estimated costs per annum in US$ (in thousand US$) |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Cost category | Funding source | Base Year | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |  |
|  |  | 2010 | 2012 | 2013 | 2014 | 2015 |  |  |  |  |  |
| Routine Recurrent Cost |  |  |  |  |  |  |  |  |  |  |  |
| Traditional vaccines | Goverment | 1,472,957 | 1,150,021 | 1,223,779 | 1,232,622 | 1,288,370 |  |  |  |  |  |
| New and underused vaccines | Goverment | 644,186 | 8,402,090 | 10,735,144 | 15,001,947 | 19,976,864 |  |  |  |  |  |
| Injection supplies | Goverment | 812,220 | 1,151,370 | 1,161,541 | 1,281,849 | 1,428,000 |  |  |  |  |  |
| Salaries of full-time NIP health workers | Goverment | 134,217 | 355,909 | 391,500 | 430,650 | 473,715 |  |  |  |  |  |
| Per-diems for outreach vaccinators / mobile teams & supervision | Goverment | 658,441 | 1,162,000 | 996,000 | 996,000 | 996,000 |  |  |  |  |  |
| Transportation | Goverment | 292,500 | 648,144 | 557,124 | 511,549 | 457,736 |  |  |  |  |  |
| Maintenance and overheads | Goverment | 318,662 | 1,602,896 | 1,949,068 | 2,247,523 | 2,550,192 |  |  |  |  |  |
| Training | Goverment | 16,200 | 125,261 | 83,038 | 73,318 | 108,484 |  |  |  |  |  |
| Social mobilisation and IEC | Goverment | 0 | 256,513 | 50,000 | 50,000 | 129,731 |  |  |  |  |  |
| Disease surveillance | Goverment | 0 | 391,133 | 350,000 | 400,000 | 744,976 |  |  |  |  |  |
| Program management | Goverment | 25,000 | 305,000 | 524,192 | 408,795 | 390,000 |  |  |  |  |  |
| Other | Goverment | 238,137 | 289,457 | 319,126 | 351,837 | 387,900 |  |  |  |  |  |
| Routine Capital Costs |  |  |  |  |  |  |  |  |  |  |  |
| Vehicle | Goverment | 0 | 63,021 | 192,385 | 473,804 | 197,965 |  |  |  |  |  |
| Cold chain equipment | Goverment | 324,567 | 733,601 | 1,269,185 | 765,000 | 465,000 |  |  |  |  |  |
| Other capital equipment | Goverment | 8,000 | 180,205 | 180,205 | 180,205 | 180,205 |  |  |  |  |  |
| Campaigns |  |  |  |  |  |  |  |  |  |  |  |
| Polio | Goverment | 4,754,824 | 7,601,629 | 2,806,378 | 7,601,629 | 7,601,629 |  |  |  |  |  |
| Measles | Goverment | 0 |  | 4,465,784 |  | 5,350,000 |  |  |  |  |  |
| Partners contr. Costing Tool | See Costing tool partners |  |  |  |  |  |  |  |  |  |  |
| GRAND TOTAL |  | 9,699,911 | 24,418,250 | 27,254,449 | 32,006,728 | 42,726,767 |  |  |  |  |  |

# New and Under-Used Vaccines (NVS)

Please summarise the cold chain capacity and readiness to accommodate new vaccines, stating how the cold chain expansion (if required) will be financed, and when it will be in place. Please indicate the additional cost, if capacity is not available and the source of funding to close the gap.

Actually the net capacity of the MoH central cold room for positive storage of routine vaccines is only 10.7 m3 insufficient to cover the national needs of routine vaccines currently in use, namely: BCG, measles, tetanus toxoid, Pentavalent, Hepatitis B and yellow fever vaccines. These vaccines including three months of buffer stock require additionally between 6 -13 m3 of storage capacity (considering Pentavalent mono dose or multidose 10 doses/vial). To cover this gap the MoH rent and control private cold rooms in Luanda. The central negative cold room storage capacity for routine polio vaccine is 10.7 m3 which is more than sufficient for routine vaccines. It is planned by the Central Government the installation between second semester of 2011 and 2012 of 2 cold rooms with a total net positive storage capacity of 90 cubic meters enough to receive all routine vaccines including the Rotavirus and Pneumo vaccines until 2020. Central level redistributed the vaccine to the provinces on quarterly bases. The positive storage capacity at 2nd level (provinces) is enough for the actual routine needs except for the Province of Luanda. To solve this problem the frequency of shipments for this province was increased to 6 by year. For the future new vaccines introduction exist potential gaps at provincial and district levels that are being covering between 2011 to 2012 mainly by central and provincial goverment, and by oil companies and UNICEF contributions. The Policy is to provide cold rooms and respective generators for each province (2nd level) with total population greater than 700,000 inhabitants and refrigerators for the other provinces. The summary of plan of cold chain improvement and sources of funding is presented in Attachment 9.

Please give a summary of the cMYP sections that refer to the introduction of new and under-used vaccines. Outline the key points that informed the decision-making process (data considered etc)

The introduction of new vaccines respond to prioritization of preventable diseases of epidemiological importance in the burden of mortality and morbidity of the country ( 2nd case od death Pneumonia, 3rd cause of death Diarrhoea), as well as long-term financial sustainability to ensure its uninterrupted supply of vaccines introduced. The MoH intends to sequencially introduce the Pneumo and Rotavirus vaccine nationwide ( Pneumo in the second semester of 2012 and Rotavirus in the second semester of 2013), given its importance to accelerate the reduction of mortality of children under 5 years old. Every vaccine will be introduced by provinces not in simultaneus but gradually in 3-4 months, securing acomplishment of defined preconditios and close supervision of national technical interagency team. The main planned preparatory activities are sumarized below: - Finalize the national assessment of effective vaccine management (EVM) compile the additional requirements of cold chain and plan of action(June 6-20); - Continue the distribution of refrigerators and other cold chain equipament purchased to prioritary provinces and districts; - Continue to increase storage capacity of the positive cold chain at all levels (prioritizing central and provincial level;June-December 2011. Is expected to achieve at central level at the end of 2011, net capacity of 45 m3 and ad the end 2012, 90 m3. - Update, print, and distribute technical manual, immunization card and records of information system;(July -september 2011) - Certify by WHO/AFRO Luanda Pediatric Hospital as "National Reference Sentinel Site" for bacterial pediatrics meningitis, and acute diarrhea; - Training in cascate of health staff (manual norms records etc.) Financial sustainability will be given by the Angolan Goverment. Note: The estimates cost of cold chain in the table below considers not only the estimated additional cost, by the needs of repositionof old equipments.

# Capacity and cost (for positive storage)

|  |  | Formula | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| A | Annual positive volume requirement, including new vaccine (litres or m3) m3 | Sum-product of total vaccine doses multiplied by unit packed volume of the vaccine | 27 | 52 | 54 | 55 |  |  |  |  |
| B | Existing net positive cold chain capacity (litres or m3) m3 | # | 45 | 90 | 90 | 90 |  |  |  |  |
| C | Estimated minimum number of shipments per year required for the actual cold chain capacity | A / B | 1 | 1 | 1 | 1 |  |  |  |  |
| D | Number of consignments / shipments per year | Based on national vaccine shipment plan | 4 | 4 | 4 | 4 |  |  |  |  |
| E | Gap (if any) | ((A / D) - B) | -38 | -77 | -77 | -76 |  |  |  |  |
| F | Estimated additional cost of cold chain | US$ | 1,213,601 | 1,369,185 | 1,530,414 |  |  |  |  |  |

Please briefly describe how your country plans to move towards attaining financial sustainability for the new vaccines you intend to introduce, how the country will meet the co-financing payments, and any other issues regarding financial sustainability you have considered (refer to the cMYP)

Angola is in a phase of rapid economic growth that translates it into major investments in urban in-frastructure, substantial improvement of road network, construction and rehabilitation of physical infrastructure in education and health to increase access of population to social services. This phase of development of the country, calls for investment in child health that will give returns in health wellness and future economic development. The recently approved Health Policies define national priorities for management and expend public resources: (1) Reduction of maternal and child mortality, (2) Control of communicable diseases and non-communicable diseases, (3) Adequacy of human resources and technologies of health, (4) As-surance of sustainable financing, (5) Efficient management of resources in the health system. In this context immunizations are one of the priority interventions of relatively low cost and high effectiveness to contribute in the accelerated reduction of child mortality and morbidity from EPI target diseases. The history of government financing of EPI in Angola shows an important transition in the last 10 years from a program totally dependent on external cooperation to a program where the costs are gradually being assumed by the government including routine immunization vaccines, injection supplies and operation expenses of vaccination campaigns that are being taken almost entirety by the Angolan Government, but given the multiple needs and limitations of the Angolan health system, the country still needs additional external support for the development of EPI in particular to undertake the challenge of introducing new vaccines that could contribute to achieving the Millennium goals of reducing mortality children under 5 years old. According to the available data, the ensured financing represents aroud 30% of the average of the financing needed between 2012 and 2015. If in terms of vaccines supply it doesn’t look like a problem, the county should start thinking of the other alternatives from 2012. However the major challenge for the country is that it is no longer eligible to GAVI and the total costs of the new vaccines will be afforded by the country in 2017. Nevertheless, these concerns should be moderated with the support of the oil companies to the vaccination activities, to which the Government would present this cMYP during a round table on vaccination financing in the context of emergency plan. If the Government succeed to mobilize the adherence of oil Companies and institutions such as European Union, World Bank Project during the round table, the financing considered as probable would considerable reduce the financing gap.

# Assessment of burden of relevant diseases (if available)

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Disease | Title of the assessment | Date | Results |  |
| --- | --- | --- | --- | --- |
| Streptococus pneumonia | Study of Bacteial meningitis in Pediatric Hospital of Luanda | 2005-2010 | The available information on Streptococcus pneumonia and Haemophilus influenzae type b responsible for severe invasive disease such as pneumonia and meningitis that is currently preventable diseases, coming from the Paediatric Hospital of Luanda that since 2002 until the present collect the continuous manner cerebrospinal fluid samples from patients with meningitis. Pediatric bacterial meningitis with positive collection of bacterial pathogens in samples of cerebrospinal fluid in the period 2005 to 2010 shows a dramatic and sustained reduction in the proportion of cases of meningitis attributable to Haemophilus influenzae type b of about 40% in 2006 (year of introduction of Pentavalent vaccine in Angola) to 5% in 2010. On the other hand it is possible to infer the same impact in other invasive diseases like pneumonia caused by Hib, given the high effectiveness of the vaccine (Hib component of the Pentavalent vaccine). |  |
| Rotavirus | Study of Prevalence of Rotavirus infection in children under 5 years old with severe diarrhea | May 2009-December 2010 | Rotavirus is an important cause of severe diarrhea worldwide, in Angola, according to information collected at the Paediatric Hospital of Luanda in about a third of cases of severe acute diarrhea investigated was found Rotavirus antigen. During the period May 2009 to December 2010 a study was conducted in the Paediatric Hospital of Luanda by collecting stool samples of children under 5 years who attended the emergency service of this hospital for acute diarrhea. The result of the previous table shows that the groups of children 2-11 months of age are most af-fected by Rotavirus. In the same investigation was confirmed rotavirus circulation throughout the year. |  |

If new or under-used vaccines have already been introduced in your country, please give details of the lessons learned from storage capacity, protection from accidental freezing, staff training, cold chain, logistics, drop-out rate, wastage rate etc., and suggest action points to address them

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Lessons Learned | Action Points |  |
| --- | --- | --- |
| 1. Is necessary to have a buffer space of cold chain storage capacity around 30-40% to receive eventual unexpected consignements. 2. The local level health centers must be considered to increase the cold chain capacity. 3. Training and close supervison is mandatory to avoid miss undertanding at local levels when change the vaccine presentation. | 1. secure additional cold chain at all levels before the introduction new vaccines. 2. Gradual introduction district by district in every province in order to secure close support. |  |

Please list the vaccines to be introduced with support from the GAVI Alliance (and presentation)

Pneumo vaccine PVC-13 vial mono dose Rotavirus vaccine 2 doses schedule vial mono dose

# 6.3.1. Requested vaccine ( Pneumococcal (PCV13), 1 doses/vial, Liquid )

As reported in the cMYP, the country plans to introduce Pneumococcal (PCV13), 1 doses/vial, Liquid vaccine.

# 6.3.2. Co-financing information

If you would like to co-finance higher amount than minimum, please overwrite information in the “Your co-financing” row.

Note: Selection of this field has direct impact on automatic calculations of support you are requesting and should not be left empty.

| Country group | Graduating |
| --- | --- |

|  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| Minimum co-financing | 0.70 | 1.40 | 2.10 | 2.80 |  |  |  |  |
| Your co-financing (please change if higher) | 0.70 | 1.40 | 2.10 | 2.80 |  |  |  |  |

# 6.3.3. Wastage factor

Please indicate wastage rate:

Countries are expected to plan for a maximal wastage rate of:

- 50% - for a lyophilised vaccine in 10 or 20-dose vial,

- 25% - for a liquid vaccine in 10 or 20-dose vial or a lyophilised vaccine in 5-dose vial,

- 10% - for a lyophilised/liquid vaccine in 2-dose vial, and

- 5% - for a liquid vaccine in 1-dose vial

Note: Selection of this field has direct impact on automatic calculations of support you are requesting and should not be left empty.

|  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| Vaccine wastage rate in % | 5% | 5% | 5% | 5% |  |  |  |  |
| Equivalent wastage factor | 1.05 | 1.05 | 1.05 | 1.05 |  |  |  |  |

# 6.3.4. Specifications of vaccinations with new vaccine

|  | Data from |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| Number of children to be vaccinated with the first dose | Table 1 | # | 933,174 | 959,303 | 986,164 | 1,013,776 |  |  |  |  |
| Number of children to be vaccinated with the third dose[1] | Table 1 | # | 867,852 | 901,745 | 926,994 | 963,087 |  |  |  |  |
| Immunisation coverage with the third dose | Table 1 | # | 93.00% | 94.00% | 94.00% | 95.00% |  |  |  |  |
| Estimated vaccine wastage factor | Table 6.(n).3[3] | # | 1.05 | 1.05 | 1.05 | 1.05 |  |  |  |  |
| Country co-financing per dose[2] | Table 6.(n).2[3] | $ | 0.70 | 1.40 | 2.10 | 2.80 |  |  |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Total price per-dose includes vaccine cost, plus freight, supplies, insurance, visa costs etc.

[3] Where (n) depends on the vaccine

# 6.3.5. Portion of supply to be procured by the country (and cost estimate, US$)

|  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| Number of vaccine doses | # | 686,700 | 1,137,400 | 1,753,900 | 2,403,900 |  |  |  |  |
| Number of AD syringes | # | 733,200 | 1,202,800 | 1,854,700 | 2,542,200 |  |  |  |  |
| Number of re-constitution syringes | # |  |  |  |  |  |  |  |  |
| Number of safety boxes | # | 8,150 | 13,375 | 20,600 | 28,225 |  |  |  |  |
| Total value to be co-financed by country | $ | 2,572,500 | 4,259,500 | 6,568,000 | 9,002,500 |  |  |  |  |

# 6.3.6. Portion of supply to be procured by the GAVI Alliance (and cost estimate, US$)

|  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| Number of vaccine doses | # | 2,987,700 | 1,905,100 | 1,373,800 | 811,300 |  |  |  |  |
| Number of AD syringes | # | 3,190,000 | 2,014,600 | 1,452,800 | 857,900 |  |  |  |  |
| Number of re-constitution syringes | # |  |  |  |  |  |  |  |  |
| Number of safety boxes | # | 35,425 | 22,375 | 16,125 | 9,525 |  |  |  |  |
| Total value to be co-financed by GAVI | $ | 11,191,000 | 7,134,500 | 5,145,000 | 3,038,500 |  |  |  |  |

# 6.3.7. New and Under-Used Vaccine Introduction Grant

Please indicate in the tables below how the one-time Introduction Grant[1] will be used to support the costs of vaccine introduction and critical pre-introduction activities (refer to the cMYP).

Calculation of lump-sum for the Pneumococcal (PCV13), 1 doses/vial, Liquid

If the total is lower than US$100,000, it is automatically rounded up to US$100,000

| Year of New Vaccine Introduction | Births (from Table 1) | Share per Birth in US$ | Total in US$ |
| --- | --- | --- | --- |
| 2012 | 1,072,614 | 0.30 | 322,000 |

[1] The Grant will be based on a maximum award of $0.30 per infant in the birth cohort with a minimum starting grant award of $100,000

Cost (and finance) to introduce the Pneumococcal (PCV13), 1 doses/vial, Liquid (US$)

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Cost Category | Full needs for new vaccine introduction in US$ | Funded with new vaccine introduction grant in US$ |  |
| --- | --- | --- | --- |
| Training | 511,350 | 181,350 |  |
| Social Mobilization, IEC and Advocacy | 404,250 |  |  |
| Cold Chain Equipment & Maintenance | 1,010,468 |  |  |
| Vehicles and Transportation | 1,233,681 |  |  |
| Programme Management | 433,784 | 95,650 |  |
| Surveillance and Monitoring | 1,302,718 |  |  |
| Human Resources | 2,120,091 |  |  |
| Waste Management | 180,205 |  |  |
| Technical assistance | 45,000 | 45,000 |  |
| Total |  |  |  |
| Totals | 7,241,547 | 322,000 |  |

# 6.4.1. Requested vaccine ( Rotavirus 2-dose schedule )

As reported in the cMYP, the country plans to introduce Rotavirus 2-dose schedule vaccine.

# 6.4.2. Co-financing information

If you would like to co-finance higher amount than minimum, please overwrite information in the “Your co-financing” row.

Note: Selection of this field has direct impact on automatic calculations of support you are requesting and should not be left empty.

| Country group | Graduating |
| --- | --- |

|  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2013 | 2014 | 2015 |  |  |  |  |  |
| Minimum co-financing | 0.72 | 1.44 | 2.16 |  |  |  |  |  |
| Your co-financing (please change if higher) | 0.72 | 1.44 | 2.16 |  |  |  |  |  |

# 6.4.3. Wastage factor

Please indicate wastage rate:

Countries are expected to plan for a maximal wastage rate of:

- 50% - for a lyophilised vaccine in 10 or 20-dose vial,

- 25% - for a liquid vaccine in 10 or 20-dose vial or a lyophilised vaccine in 5-dose vial,

- 10% - for a lyophilised/liquid vaccine in 2-dose vial, and

- 5% - for a liquid vaccine in 1-dose vial

Note: Selection of this field has direct impact on automatic calculations of support you are requesting and should not be left empty.

|  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2013 | 2014 | 2015 |  |  |  |  |  |
| Vaccine wastage rate in % | 5% | 5% | 5% |  |  |  |  |  |
| Equivalent wastage factor | 1.05 | 1.05 | 1.05 |  |  |  |  |  |

# 6.4.4. Specifications of vaccinations with new vaccine

|  | Data from |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2013 | 2014 | 2015 |  |  |  |  |  |
| Number of children to be vaccinated with the first dose | Table 1 | # | 767,443 | 838,239 | 912,399 |  |  |  |  |  |
| Number of children to be vaccinated with the third dose[1] | Table 1 | # | 671,512 | 739,623 | 811,021 |  |  |  |  |  |
| Immunisation coverage with the third dose | Table 1 | # | 70.00% | 75.00% | 80.00% |  |  |  |  |  |
| Estimated vaccine wastage factor | Table 6.(n).3[3] | # | 1.05 | 1.05 | 1.05 |  |  |  |  |  |
| Country co-financing per dose[2] | Table 6.(n).2[3] | $ | 0.72 | 1.44 | 2.16 |  |  |  |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Total price per-dose includes vaccine cost, plus freight, supplies, insurance, visa costs etc.

[3] Where (n) depends on the vaccine

# 6.4.5. Portion of supply to be procured by the country (and cost estimate, US$)

|  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2013 | 2014 | 2015 |  |  |  |  |  |
| Number of vaccine doses | # | 275,900 | 615,200 | 1,114,900 |  |  |  |  |  |
| Number of AD syringes | # |  |  |  |  |  |  |  |  |
| Number of re-constitution syringes | # |  |  |  |  |  |  |  |  |
| Number of safety boxes | # | 3,075 | 6,850 | 12,375 |  |  |  |  |  |
| Total value to be co-financed by country | $ | 1,450,500 | 2,588,500 | 4,223,000 |  |  |  |  |  |

# 6.4.6. Portion of supply to be procured by the GAVI Alliance (and cost estimate, US$)

|  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2013 | 2014 | 2015 |  |  |  |  |  |
| Number of vaccine doses | # | 1,738,700 | 1,182,400 | 840,200 |  |  |  |  |  |
| Number of AD syringes | # |  |  |  |  |  |  |  |  |
| Number of re-constitution syringes | # |  |  |  |  |  |  |  |  |
| Number of safety boxes | # | 19,300 | 13,125 | 9,350 |  |  |  |  |  |
| Total value to be co-financed by GAVI | $ | 9,142,000 | 4,975,500 | 3,182,500 |  |  |  |  |  |

# 6.4.7. New and Under-Used Vaccine Introduction Grant

Please indicate in the tables below how the one-time Introduction Grant[1] will be used to support the costs of vaccine introduction and critical pre-introduction activities (refer to the cMYP).

Calculation of lump-sum for the Rotavirus 2-dose schedule

If the total is lower than US$100,000, it is automatically rounded up to US$100,000

| Year of New Vaccine Introduction | Births (from Table 1) | Share per Birth in US$ | Total in US$ |
| --- | --- | --- | --- |
| 2013 | 1,102,647 | 0.30 | 331,000 |

[1] The Grant will be based on a maximum award of $0.30 per infant in the birth cohort with a minimum starting grant award of $100,000

Cost (and finance) to introduce the Rotavirus 2-dose schedule (US$)

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Cost Category | Full needs for new vaccine introduction in US$ | Funded with new vaccine introduction grant in US$ |  |
| --- | --- | --- | --- |
| Training | 322,261 | 100,000 |  |
| Social Mobilization, IEC and Advocacy | 446,513 | 50,000 |  |
| Cold Chain Equipment & Maintenance |  |  |  |
| Vehicles and Transportation | 1,916,745 |  |  |
| Programme Management | 420,948 | 121,000 |  |
| Surveillance and Monitoring | 1,391,133 |  |  |
| Human Resources | 2,558,295 |  |  |
| Waste Management | 180 |  |  |
| Technical assistance | 60,000 | 60,000 |  |
| Totals | 7,116,075 | 331,000 |  |

# Procurement and Management of New and Under-Used Vaccines

Note: The PCV vaccine must be procured through UNICEF

- Please show how the support will operate and be managed including procurement of vaccines (GAVI expects that most countries will procure vaccine and injection supplies through UNICEF)

The process of purchasing of new vaccines and its injection supplies will follow the same procedures than Pentavalent vaccine. The UNICEF will be in charge of the process of purchasing. The custom clearance will be in charge of Ministry of Health. The vaccines and supplies received will stored at central level and redistributed to provinces on quarterly bases.

- If an alternative mechanism for procurement and delivery of supply (financed by the country or the GAVI Alliance) is requested, please document

- Other vaccines or immunisation commodities procured by the country and descriptions of the mechanism used.

- The functions of the National Regulatory Authority (as evaluated by WHO) to show they comply with WHO requirements for procurement of vaccines and supply of assured quality.

N/A

- Please describe the introduction of the vaccines (refer to cMYP)

The introduction of new vaccines must be respond to prioritization of preventable diseases of epidemiological importance in the burden of mortality and morbidity of the country, as well as long-term financial sustainability to ensure uninterrupted supply of introduced vaccines. The MoH intends to introduce the Pneumo vaccine (last quarter of 2012) and Rotavirus vaccine (last quarter of 2013) to reduce the Pneumonia and diarrhea burden of diseases. The preparatory workshop and activities will be start in the third quarter of 2011. The introduction will begin in urban areas and gradually will be extend to the rural areas. For Rota vaccine the vaccine initially will be offered exclusively in fix post after gradually will administrate by outreach and mobile teams. The pre-conditions for introduce new vaccines will listed below: - Finalization of national assessment of effective vaccine and cold chain management (EVM) and correspondent plan of action to overcome the problems. - Increased storage capacity of the central positive cold chain from 10.7 m3 to 30-50m3 in 2011, and duplicate this capacity in 2012; - Continue the process of increasing positive cold chain capacity at provinces and districts levels with storage gaps including main health facilities; - Update of Technical standards and records of information system; - Accreditation of "Sentinel Surveillance System of Bacterial Meningitis Pediatrics, and Severe Acute Diarrhea" initially in the Paediatric Hospital of Luanda; - Intensive training and close supervision of health staff by MoH supervisors and partners.

- Please indicate how funds should be transferred by the GAVI Alliance (if applicable)

For the introduction grant, the Ministry has an EPI specific bank account in the “Banco de Fomento Angola”. This account was open to receive GAVI funds in 2003 funds and still is active. For the release the GAVI funds two authorized signatures are required: 1-The signature of National Director of Public Health or Vice Minister of Health and, 2-The signature of National EPI Manager. The management of these funds consists of the following steps: -Technical staff of Ministry of Health and technicians of partner’s agencies elaborate a plan of action with detailed budget for use of GAVI, government and other partner’s funds. -Approval of this plan with budget by the ICC during a meeting for this purpose and chaired by the Vice Minister of Health and with the participation of Representatives of WHO, UNICEF, CORE and other partners. -For every activity to be implemented, a written request of funds is made by the EPI manager to the National Director of Public Health or to the Vice-Minister of Health. -The National Director of Public Health or the Vice Minister of Health authorizes the use and the transference of funds to the implementing level. -Transfer the funds to account of implementing level. -Monitoring the implementation of activities and use of funds by the central level of Ministry of Health and partners agencies. -Quarterly report of status of liquidations during the ICC

- Please indicate how the co-financing amounts will be paid (and who is responsible for this)

The payment co-financing amounts by the Ministry of Health will be made through UNICEF, the steps are the following: 1. Signature of agreement for vaccine purchasing between UNICEF and MoH 2. Transfering the funds from MoH to UNICEF acording forecast prepared by EPI 3. Purchasing of vaccine and injection supplies by UNICEF. 4. Reception of vaccines, injection supplies and purchasing documentation by MoH 5. MoH sending comprovatives of purchasing to GAVI.

- Please outline how coverage of the new vaccine will be monitored and reported (refer to cMYP)

The data of coverage of Pneumo and Rotavirus will be monitored in every level: 1. At health facility and district will be monitored the coverage using the coverage monitoring chart actually used only for pentavalent). This chart permit to monitor additionally the drop out. 2. During the monthly data analysis meetings at provincial level. 3. The supervisors chek list include key points for verify the acuracy, completenes and timeliness of routine EPI data of records and reports. 4. Central level monthly data analysis and feed back of performance indicators will include new vaccines.ICC and partners receive monthly sumary reports by district. The flow of reports is the following: 1. Health facilities send monthly report to district. 2. District consolidate the health facilities report and send two copies: one for Province and other for central level. 3. Province consolidate and analyse the data of district and send to central level the original of district reports to central level. 4.Central level introduce the data in Central data base(epi-info)and send monthly to AFRO/WHO. 5. Anually the data is reprted by JRF WHO /UNICEF

# Vaccine Management (EVSM/EVM/VMA)

When was the last Effective Vaccine Store Management (EVSM) conducted?   -

When was the last Effective Vaccine Management (EVM) or Vaccine Management Assessment (VMA) conducted?   -

- If your country conducted either EVSM, EVM, or VMA in the past three years, please attach relevant reports. (Document N°)

- A VMA report must be attached from those countries which have introduced a New and Underused Vaccine with GAVI support before 2008.

- Please note that EVSM and VMA tools have been replaced by an integrated Effective Vaccine Management (EVM) tool. The information on EVM tool can be found at http://www.who.int/immunization_delivery/systems_policy/logistics/en/index6.html

- For countries which conducted EVSM, VMA or EVM in the past, please report on activities carried out as part of either action plan or improvement plan prepared after the EVSM/VMA/EVM.

The Country was not conducted EVSM, EVM or VMA. The first EVM assesment in Angola is presently in progress. The final results and Plan of Action for Improving Injection Safety will be ready June 20th 2011

- When is the next Effective Vaccine Management (EVM) Assessment planned? June  - 2012

- Under new guidelines, it will be mandatory for the countries to conduct an EVM prior to an application for introduction of new vaccine.

# Additional Comments and Recommendations

Comments and Recommendations from the National Coordinating Body (ICC/HSCC)

Angola carried out in the last 5 years significant progress in increasing numbers of children vaccinated during routine immunization sessions. This effort was largely due to the great political engagement of the Government promoting immunizations, this commitment is reflected in the rapid increase in the number of health services that perform routine vaccination (730 in 2007 to 939 in 2010) and by 3 to 4 rounds of vaccination per year using outreach and mobile teams to meet hard to reach populations. On other hand Government contributions are increasing creating conditions for sustainability, in particular the recent intensive involvement of provincial governments and local municipal administrators in local funding and support immunization program activities. Clearly there is much to be done to achieve a harmonious and sustainable development of all components of the program in particular with regard to cold chain and human resource capacity building, requiring major challenges to maintain and increase the motivation of local authorities, people and health staff to achieve greater health benefits of immunizations. The introduction of new vaccines such as Pneumo, and Rotavirus is an important tool to accelerate the reduction of child mortality and achieves by Angola the fourth Millennium Goal, so as for overall EPI improvement. In other perspective given that the new vaccines have the potential to prevent diseases that affect the daily lives of people and overload health services, undoubtedly is a great opportunity to improve the heath staff motivation and increase awareness and public adherence to immunizations. The introduction of new vaccines involves a large effort to mobilize human, financial and technological resources in a narrow period of time to create the optimum conditions for introduction of these vaccines. In this regard we think the country is on track, as the government call a conference of local donors, with a favorable response mainly from oil companies, European Union and friend countries who already made significant donations are being directed mainly to cover gaps in cold chain and logistic of transport. In conclusion the ICC member strongly recommends the introduction the new vaccines.

# Annexes

# Annex 1

# Annex 1.1 – Pneumococcal (PCV13), 1 doses/vial, Liquid

Table 1.1 A - Rounded up portion of supply that is procured by the country and estimate of related cost in US$

| Required supply item |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of vaccine doses | # | 686,700 | 1,137,400 | 1,753,900 | 2,403,900 |  |  |  |  |
| Number of AD syringes | # | 733,200 | 1,202,800 | 1,854,700 | 2,542,200 |  |  |  |  |
| Number of re-constitution syringes | # |  |  |  |  |  |  |  |  |
| Number of safety boxes | # | 8,150 | 13,375 | 20,600 | 28,225 |  |  |  |  |
| Total value to be co-financed by the country | $ | 2,572,500 | 4,259,500 | 6,568,000 | 9,002,500 |  |  |  |  |

Table 1.1  B - Rounded up portion of supply that is procured by GAVI and estimate of related cost in US$.

| Required supply item |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of vaccine doses | # | 2,987,700 | 1,905,100 | 1,373,800 | 811,300 |  |  |  |  |
| Number of AD syringes | # | 3,190,000 | 2,014,600 | 1,452,800 | 857,900 |  |  |  |  |
| Number of re-constitution syringes | # |  |  |  |  |  |  |  |  |
| Number of safety boxes | # | 35,425 | 22,375 | 16,125 | 9,525 |  |  |  |  |
| Total value to be co-financed by the country | $ | 11,191,000 | 7,134,500 | 5,145,000 | 3,038,500 |  |  |  |  |

Table 1.1  C - Summary table for Pneumococcal (PCV13), 1 doses/vial, Liquid

|  | Data from |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of Surviving infants | Table 1 | # | 933,174 | 959,303 | 986,164 | 1,013,776 |  |  |  |  |
| Number of children to be vaccinated with the third dose[1] | Table 1 | # | 867,852 | 901,745 | 926,994 | 963,087 |  |  |  |  |
| Immunisation coverage with the last dose | Table 1 | # | 93.00% | 94.00% | 94.00% | 95.00% |  |  |  |  |
| Number of children to be vaccinated with the first dose | Table 1 | # | 933,174 | 959,303 | 986,164 | 1,013,776 |  |  |  |  |
| Number of doses per child |  | # | 3 | 3 | 3 | 3 |  |  |  |  |
| Estimated vaccine wastage factor | Table 6.(n).3[2] | # | 1.05 | 1.05 | 1.05 | 1.05 |  |  |  |  |
| Number of doses per vial |  | # | 1 | 1 | 1 | 1 |  |  |  |  |
| AD syringes required |  | # | Yes | Yes | Yes | Yes |  |  |  |  |
| Reconstitution syringes required |  | # | No | No | No | No |  |  |  |  |
| Safety boxes required |  | # | Yes | Yes | Yes | Yes |  |  |  |  |
| Vaccine price per dose |  | $ | 3.500 | 3.500 | 3.500 | 3.500 |  |  |  |  |
| Country co-financing per dose | Table 6.(n).2[2] | $ | 0.70 | 1.40 | 2.10 | 2.80 |  |  |  |  |
| AD syringe price per unit |  | $ | 0.053 | 0.053 | 0.053 | 0.053 |  |  |  |  |
| Reconstitution syringe price per unit |  | $ |  |  |  |  |  |  |  |  |
| Safety box price per unit |  | $ | 0.640 | 0.640 | 0.640 | 0.640 |  |  |  |  |
| Freight cost as % of vaccines value |  | % | 5.00 | 5.00 | 5.00 | 5.00 |  |  |  |  |
| Freight cost as % of devices value |  | % | 10.00 | 10.00 | 10.00 | 10.00 |  |  |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Where (n) depends on the vaccine

# Table 1.1 D - Estimated number of doses for Pneumococcal (PCV13), 1 doses/vial, Liquid associated injection safety material and related co-financing budget (page 1)

|  |  | Formula | 2012 |  |  | 2013 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Total | Government | GAVI | Total | Government | GAVI |
| A | Country Co-finance |  | 18.69% |  |  | 37.38% |  |  |
| B | Number of children to be vaccinated with the first dose[1] | Table 1 (baseline & annual targets) | 933,174 | 174,398 | 758,776 | 959,303 | 358,626 | 600,677 |
| C | Number of doses per child | Vaccine parameter | 3 | 3 | 3 | 3 | 3 | 3 |
| D | Number of doses needed | B * C | 2,799,522 | 523,193 | 2,276,329 | 2,877,909 | 1,075,878 | 1,802,031 |
| E | Estimated vaccine wastage factor | Table 6.(n).3. in NVS section[2] | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 |
| F | Number of doses needed including wastage | D * E | 2,939,499 | 549,353 | 2,390,146 | 3,021,805 | 1,129,672 | 1,892,133 |
| G | Vaccines buffer stock | (F - F of previous year) * 0.25 | 734,875 | 137,339 | 597,536 | 20,577 | 7,693 | 12,884 |
| I | Total vaccine doses needed | F + G | 3,674,374 | 686,691 | 2,987,683 | 3,042,382 | 1,137,365 | 1,905,017 |
| J | Number of doses per vial | Vaccine parameter | 1 | 1 | 1 | 1 | 1 | 1 |
| K | Number of AD syringes (+ 10% wastage) needed | (D + G) * 1.11 | 3,923,181 | 733,190 | 3,189,991 | 3,217,320 | 1,202,764 | 2,014,556 |
| L | Reconstitution syringes (+ 10% wastage) needed | I / J * 1.11 |  |  |  |  |  |  |
| M | Total of safety boxes (+ 10% of extra need) needed | (K + L) / 100 x 1.11 | 43,548 | 8,139 | 35,409 | 35,713 | 13,351 | 22,362 |
| N | Cost of vaccines needed | I * vaccine price per dose | 12,860,309 | 2,403,417 | 10,456,892 | 10,648,337 | 3,980,776 | 6,667,561 |
| O | Cost of AD syringes needed | K * AD syringe price per unit | 207,929 | 38,860 | 169,069 | 170,518 | 63,747 | 106,771 |
| P | Cost of reconstitution syringes needed | L * reconstitution price per unit |  |  |  |  |  |  |
| Q | Cost of safety boxes needed | M * safety box price per unit | 27,871 | 5,209 | 22,662 | 22,857 | 8,545 | 14,312 |
| R | Freight cost for vaccines needed | N * freight cost as % of vaccines value | 643,016 | 120,171 | 522,845 | 532,417 | 199,039 | 333,378 |
| S | Freight cost for devices needed | (O + P + Q) * freight cost as % of devices value | 23,580 | 4,407 | 19,173 | 19,338 | 7,230 | 12,108 |
| T | Total fund needed | (N + O + P + Q + R + S) | 13,762,705 | 2,572,062 | 11,190,643 | 11,393,467 | 4,259,335 | 7,134,132 |
| U | Total country co-financing | I * country co-financing per dose | 2,572,062 |  |  | 4,259,335 |  |  |
| V | Country co-financing % of GAVI supported proportion | U / T | 18.69% |  |  | 37.38% |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Where (n) depends on the vaccine

# Table 1.1 D - Estimated number of doses for Pneumococcal (PCV13), 1 doses/vial, Liquid associated injection safety material and related co-financing budget (page 2)

|  |  | Formula | 2014 |  |  | 2015 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Total | Government | GAVI | Total | Government | GAVI |
| A | Country Co-finance |  | 56.08% |  |  | 74.77% |  |  |
| B | Number of children to be vaccinated with the first dose[1] | Table 1 (baseline & annual targets) | 986,164 | 553,002 | 433,162 | 1,013,776 | 757,981 | 255,795 |
| C | Number of doses per child | Vaccine parameter (schedule) | 3 | 3 | 3 | 3 | 3 | 3 |
| D | Number of doses needed | B * C | 2,958,492 | 1,659,005 | 1,299,487 | 3,041,328 | 2,273,941 | 767,387 |
| E | Estimated vaccine wastage factor | Table 6.(n).3. in NVS section[2] | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 |
| F | Number of doses needed including wastage | D * E | 3,106,417 | 1,741,955 | 1,364,462 | 3,193,395 | 2,387,639 | 805,756 |
| G | Vaccines buffer stock | (F - F of previous year) * 0.25 | 21,153 | 11,862 | 9,291 | 21,745 | 16,259 | 5,486 |
| I | Total vaccine doses needed | F + G | 3,127,570 | 1,753,817 | 1,373,753 | 3,215,140 | 2,403,897 | 811,243 |
| J | Number of doses per vial | Vaccine parameter | 1 | 1 | 1 | 1 | 1 | 1 |
| K | Number of AD syringes (+ 10% wastage) needed | (D + G) * 1.11 | 3,307,406 | 1,854,662 | 1,452,744 | 3,400,012 | 2,542,122 | 857,890 |
| L | Reconstitution syringes (+ 10% wastage) needed | I / J * 1.11 |  |  |  |  |  |  |
| M | Total of safety boxes (+ 10% of extra need) needed | (K + L) / 100 x 1.11 | 36,713 | 20,588 | 16,125 | 37,741 | 28,219 | 9,522 |
| N | Cost of vaccines needed | I * vaccine price per dose | 10,946,495 | 6,138,359 | 4,808,136 | 11,252,990 | 8,413,638 | 2,839,352 |
| O | Cost of AD syringes needed | K * AD syringe price per unit | 175,293 | 98,298 | 76,995 | 180,201 | 134,733 | 45,468 |
| P | Cost of reconstitution syringes needed | L * reconstitution price per unit |  |  |  |  |  |  |
| Q | Cost of safety boxes needed | M * safety box price per unit | 23,497 | 13,177 | 10,320 | 24,155 | 18,061 | 6,094 |
| R | Freight cost for vaccines needed | N * freight cost as % of vaccines value | 547,325 | 306,919 | 240,406 | 562,650 | 420,683 | 141,967 |
| S | Freight cost for devices needed | (O + P + Q) * freight cost as % of devices value | 19,879 | 11,148 | 8,731 | 20,436 | 15,280 | 5,156 |
| T | Total fund needed | (N + O + P + Q + R + S) | 11,712,489 | 6,567,897 | 5,144,592 | 12,040,432 | 9,002,392 | 3,038,040 |
| U | Total country co-financing | I * country co-financing per dose | 6,567,897 |  |  | 9,002,392 |  |  |
| V | Country co-financing % of GAVI supported proportion | U / T | 56.08% |  |  | 74.77% |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Where (n) depends on the vaccine

# Annex 1.2 – Rotavirus 2-dose schedule

Table 1.2 A - Rounded up portion of supply that is procured by the country and estimate of related cost in US$

| Required supply item |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of vaccine doses | # |  | 275,900 | 615,200 | 1,114,900 |  |  |  |  |
| Number of AD syringes | # |  |  |  |  |  |  |  |  |
| Number of re-constitution syringes | # |  |  |  |  |  |  |  |  |
| Number of safety boxes | # |  | 3,075 | 6,850 | 12,375 |  |  |  |  |
| Total value to be co-financed by the country | $ |  | 1,450,500 | 2,588,500 | 4,223,000 |  |  |  |  |

Table 1.2  B - Rounded up portion of supply that is procured by GAVI and estimate of related cost in US$.

| Required supply item |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of vaccine doses | # |  | 1,738,700 | 1,182,400 | 840,200 |  |  |  |  |
| Number of AD syringes | # |  |  |  |  |  |  |  |  |
| Number of re-constitution syringes | # |  |  |  |  |  |  |  |  |
| Number of safety boxes | # |  | 19,300 | 13,125 | 9,350 |  |  |  |  |
| Total value to be co-financed by the country | $ |  | 9,142,000 | 4,975,500 | 3,182,500 |  |  |  |  |

Table 1.2  C - Summary table for Rotavirus 2-dose schedule

|  | Data from |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of Surviving infants | Table 1 | # |  | 959,303 | 986,164 | 1,013,776 |  |  |  |  |
| Number of children to be vaccinated with the third dose[1] | Table 1 | # |  | 671,512 | 739,623 | 811,021 |  |  |  |  |
| Immunisation coverage with the last dose | Table 1 | # |  | 70.00% | 75.00% | 80.00% |  |  |  |  |
| Number of children to be vaccinated with the first dose | Table 1 | # |  | 767,443 | 838,239 | 912,399 |  |  |  |  |
| Number of doses per child |  | # |  | 2 | 2 | 2 |  |  |  |  |
| Estimated vaccine wastage factor | Table 6.(n).3[2] | # |  | 1.05 | 1.05 | 1.05 |  |  |  |  |
| Number of doses per vial |  | # |  | 1 | 1 | 1 |  |  |  |  |
| AD syringes required |  | # |  | No | No | No |  |  |  |  |
| Reconstitution syringes required |  | # |  | No | No | No |  |  |  |  |
| Safety boxes required |  | # |  | Yes | Yes | Yes |  |  |  |  |
| Vaccine price per dose |  | $ |  | 5.000 | 4.000 | 3.600 |  |  |  |  |
| Country co-financing per dose | Table 6.(n).2[2] | $ |  | 0.72 | 1.44 | 2.16 |  |  |  |  |
| AD syringe price per unit |  | $ |  | 0.053 | 0.053 | 0.053 |  |  |  |  |
| Reconstitution syringe price per unit |  | $ |  |  |  |  |  |  |  |  |
| Safety box price per unit |  | $ |  | 0.640 | 0.640 | 0.640 |  |  |  |  |
| Freight cost as % of vaccines value |  | % |  | 5.00 | 5.00 | 5.00 |  |  |  |  |
| Freight cost as % of devices value |  | % |  | 10.00 | 10.00 | 10.00 |  |  |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Where (n) depends on the vaccine

# Table 1.2 D - Estimated number of doses for Rotavirus 2-dose schedule associated injection safety material and related co-financing budget (page 1)

|  |  | Formula | 2013 |  |  | 2014 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Total | Government | GAVI | Total | Government | GAVI |
| A | Country Co-finance |  | 13.69% |  |  | 34.22% |  |  |
| B | Number of children to be vaccinated with the first dose[1] | Table 1 (baseline & annual targets) | 767,443 | 105,093 | 662,350 | 838,239 | 286,863 | 551,376 |
| C | Number of doses per child | Vaccine parameter | 2 | 2 | 2 | 2 | 2 | 2 |
| D | Number of doses needed | B * C | 1,534,886 | 210,186 | 1,324,700 | 1,676,478 | 573,725 | 1,102,753 |
| E | Estimated vaccine wastage factor | Table 6.(n).3. in NVS section[2] | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 |
| F | Number of doses needed including wastage | D * E | 1,611,631 | 220,696 | 1,390,935 | 1,760,302 | 602,412 | 1,157,890 |
| G | Vaccines buffer stock | (F - F of previous year) * 0.25 | 402,908 | 55,174 | 347,734 | 37,168 | 12,720 | 24,448 |
| I | Total vaccine doses needed | F + G | 2,014,539 | 275,870 | 1,738,669 | 1,797,470 | 615,131 | 1,182,339 |
| J | Number of doses per vial | Vaccine parameter | 1 | 1 | 1 | 1 | 1 | 1 |
| K | Number of AD syringes (+ 10% wastage) needed | (D + G) * 1.11 |  |  |  |  |  |  |
| L | Reconstitution syringes (+ 10% wastage) needed | I / J * 1.11 |  |  |  |  |  |  |
| M | Total of safety boxes (+ 10% of extra need) needed | I / 100 x 1.11 | 22,362 | 3,063 | 19,299 | 19,952 | 6,828 | 13,124 |
| N | Cost of vaccines needed | I * vaccine price per dose | 10,072,695 | 1,379,346 | 8,693,349 | 7,189,880 | 2,460,524 | 4,729,356 |
| O | Cost of AD syringes needed | K * AD syringe price per unit |  |  |  |  |  |  |
| P | Cost of reconstitution syringes needed | L * reconstitution price per unit |  |  |  |  |  |  |
| Q | Cost of safety boxes needed | M * safety box price per unit | 14,312 | 1,960 | 12,352 | 12,770 | 4,371 | 8,399 |
| R | Freight cost for vaccines needed | N * freight cost as % of vaccines value | 503,635 | 68,968 | 434,667 | 359,494 | 123,027 | 236,467 |
| S | Freight cost for devices needed | (O + P + Q) * freight cost as % of devices value | 1,432 | 197 | 1,235 | 1,277 | 438 | 839 |
| T | Total fund needed | (N + O + P + Q + R + S) | 10,592,074 | 1,450,469 | 9,141,605 | 7,563,421 | 2,588,357 | 4,975,064 |
| U | Total country co-financing | I * country co-financing per dose | 1,450,469 |  |  | 2,588,357 |  |  |
| V | Country co-financing % of GAVI supported proportion | U / T | 13.69% |  |  | 34.22% |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Where (n) depends on the vaccine

# Table 1.2 D - Estimated number of doses for Rotavirus 2-dose schedule associated injection safety material and related co-financing budget (page 2)

|  |  | Formula | 2015 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Total | Government | GAVI | Total | Government | GAVI |
| A | Country Co-finance |  | 57.02% |  |  |  |  |  |
| B | Number of children to be vaccinated with the first dose[1] | Table 1 (baseline & annual targets) | 912,399 | 520,296 | 392,103 |  |  |  |
| C | Number of doses per child | Vaccine parameter (schedule) | 2 | 2 | 2 | 2 | 2 | 2 |
| D | Number of doses needed | B * C | 1,824,798 | 1,040,591 | 784,207 |  |  |  |
| E | Estimated vaccine wastage factor | Table 6.(n).3. in NVS section[2] | 1.05 | 1.05 | 1.05 |  |  |  |
| F | Number of doses needed including wastage | D * E | 1,916,038 | 1,092,620 | 823,418 |  |  |  |
| G | Vaccines buffer stock | (F - F of previous year) * 0.25 | 38,934 | 22,203 | 16,731 |  |  |  |
| I | Total vaccine doses needed | F + G | 1,954,972 | 1,114,823 | 840,149 |  |  |  |
| J | Number of doses per vial | Vaccine parameter | 1 | 1 | 1 | 1 | 1 | 1 |
| K | Number of AD syringes (+ 10% wastage) needed | (D + G) * 1.11 |  |  |  |  |  |  |
| L | Reconstitution syringes (+ 10% wastage) needed | I / J * 1.11 |  |  |  |  |  |  |
| M | Total of safety boxes (+ 10% of extra need) needed | I / 100 x 1.11 | 21,701 | 12,375 | 9,326 |  |  |  |
| N | Cost of vaccines needed | I * vaccine price per dose | 7,037,900 | 4,013,360 | 3,024,540 |  |  |  |
| O | Cost of AD syringes needed | K * AD syringe price per unit |  |  |  |  |  |  |
| P | Cost of reconstitution syringes needed | L * reconstitution price per unit |  |  |  |  |  |  |
| Q | Cost of safety boxes needed | M * safety box price per unit | 13,889 | 7,921 | 5,968 |  |  |  |
| R | Freight cost for vaccines needed | N * freight cost as % of vaccines value | 351,895 | 200,668 | 151,227 |  |  |  |
| S | Freight cost for devices needed | (O + P + Q) * freight cost as % of devices value | 1,389 | 793 | 596 |  |  |  |
| T | Total fund needed | (N + O + P + Q + R + S) | 7,405,073 | 4,222,740 | 3,182,333 |  |  |  |
| U | Total country co-financing | I * country co-financing per dose | 4,222,740 |  |  |  |  |  |
| V | Country co-financing % of GAVI supported proportion | U / T | 57.02% |  |  |  |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Where (n) depends on the vaccine

# Annex 2

Estimated prices of supply and related freight cost: 2011 from UNICEF Supply Division; 2012 onwards: GAVI Secretariat

Table A - Commodities Cost

| Vaccine | Presentation | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| AD syringe | 0 | 0.053 | 0.053 | 0.053 | 0.053 | 0.053 | 0.053 | 0.053 |
| DTP-HepB | 2 | 1.600 |  |  |  |  |  |  |
| DTP-HepB | 10 | 0.620 | 0.620 | 0.620 | 0.620 | 0.620 | 0.620 | 0.620 |
| DTP-HepB-Hib | WAP | 2.580 | 2.470 | 2.320 | 2.030 | 1.850 | 1.850 | 1.850 |
| DTP-HepB-Hib | WAP | 2.580 | 2.470 | 2.320 | 2.030 | 1.850 | 1.850 | 1.850 |
| DTP-HepB-Hib | WAP | 2.580 | 2.470 | 2.320 | 2.030 | 1.850 | 1.850 | 1.850 |
| DTP-Hib | 10 | 3.400 | 3.400 | 3.400 | 3.400 | 3.400 | 3.200 | 3.200 |
| HepB monoval | 1 |  |  |  |  |  |  |  |
| HepB monoval | 2 |  |  |  |  |  |  |  |
| Hib monoval | 1 | 3.400 |  |  |  |  |  |  |
| Measles | 10 | 0.240 | 0.240 | 0.240 | 0.240 | 0.240 | 0.240 | 0.240 |
| Pneumococcal(PCV10) | 2 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 |
| Pneumococcal(PCV13) | 1 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 |
| Reconstit syringe for Pentaval (2ml) | 0 | 0.032 | 0.032 | 0.032 | 0.032 | 0.032 | 0.032 | 0.032 |
| Reconstit syringe for YF | 0 | 0.038 | 0.038 | 0.038 | 0.038 | 0.038 | 0.038 | 0.038 |
| Rotavirus 2-dose schedule | 1 | 7.500 | 6.000 | 5.000 | 4.000 | 3.600 | 3.600 | 3.600 |
| Rotavirus 3-dose schedule | 1 | 5.500 | 4.000 | 3.333 | 2.667 | 2.400 | 2.400 | 2.400 |
| Safety box | 0 | 0.640 | 0.640 | 0.640 | 0.640 | 0.640 | 0.640 | 0.640 |
| Yellow Fever | WAP | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 |
| Yellow Fever | WAP | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 |

Note: WAP - weighted average price (to be used for any presentation: For DTP-HepB-Hib, it applies to 1 dose liquid, 2 dose lyophilised and 10 dose liquid. For Yellow Fever, it applies to 5 dose lyophilised and 10 dose lyophilised)

Table B - Commodities Freight Cost

| Vaccines | Group | No Threshold | 200’000 $ |  | 250’000 $ |  | 2’000’000 $ |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | <= | > | <= | > | <= | > |
| Yellow Fever | Yellow Fever |  | 20% |  |  |  | 10% | 5% |
| DTP+HepB | HepB and or Hib | 2% |  |  |  |  |  |  |
| DTP-HepB-Hib | HepB and or Hib |  |  |  | 15% | 3,50% |  |  |
| Pneumococcal vaccine (PCV10) | Pneumococcal | 5% |  |  |  |  |  |  |
| Pneumococcal vaccine (PCV13) | Pneumococcal | 5% |  |  |  |  |  |  |
| Rotavirus | Rotavirus | 5% |  |  |  |  |  |  |
| Measles | Measles | 10% |  |  |  |  |  |  |

Table C - Graduating - Minimum country's co-payment per dose of co-financed vaccine.

| vaccine | 2012 | 2013 | 2014 | 2015 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Pneumococcal(PCV13), 1 doses/vial, Liquid | 0.70 | 1.40 | 2.10 | 2.80 |  |  |  |
| Rotavirus 2-dose schedule |  | 0.72 | 1.44 | 2.16 |  |  |  |

Table D - Wastage rates and factors

Countries are expected to plan for a maximal wastage rate of:

- 50% - for a lyophilised vaccine in 10 or 20-dose vial,

- 25% - for a liquid vaccine in 10 or 20-dose vial or a lyophilised vaccine in 5-dose vial,

- 10% - for a lyophilised/liquid vaccine in 2-dose vial, and

- 5% - for a liquid vaccine in 1-dose vial

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2 | 2.22 | 2.5 |

WHO International shipping guidelines: maximum packed volumes of vaccines

Table E - Vaccine maximum packed volumes

| Vaccine product | Designation | Vaccine formulation | Admin route | No. Of doses in the schedule | Presentation (doses/vial, prefilled) | Packed volume vaccine (cm3/dose) | Packed volume diluents (cm3/dose) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| BCG | BCG | lyophilized | ID | 1 | 20 | 1.2 | 0.7 |
| Diphtheria-Tetanus-Pertussis | DTP | liquid | IM | 3 | 20 | 2.5 |  |
| Diphtheria-Tetanus-Pertussis | DTP | liquid | IM | 3 | 10 | 3.0 |  |
| Diphtheria-Tetanus | DT | liquid | IM | 3 | 10 | 3.0 |  |
| Tetanus-Diphtheria | Td | liquid | IM | 2 | 10 | 3.0 |  |
| Tetanus Toxoid | TT | liquid | IM | 2 | 10 | 3.0 |  |
| Tetanus Toxoid | TT | liquid | IM | 2 | 20 | 2.5 |  |
| Tetanus Toxoid UniJect | TT | liquid | IM | 2 | Uniject | 12.0 |  |
| Measles | Measles | lyophilized | SC | 1 | 1 | 26.1 | 20.0 |
| Measles | Measles | lyophilized | SC | 1 | 2 | 13.1 | 13.1 |
| Measles | Measles | lyophilized | SC | 1 | 5 | 5.2 | 7.0 |
| Measles | Measles | lyophilized | SC | 1 | 10 | 3.5 | 4.0 |
| Measles-Rubella freeze dried | MR | lyophilized | SC | 1 | 1 | 26.1 | 26.1 |
| Measles-Rubella freeze dried | MR | lyophilized | SC | 1 | 2 | 13.1 | 13.1 |
| Measles-Rubella freeze dried | MR | lyophilized | SC | 1 | 5 | 5.2 | 7.0 |
| Measles-Rubella freeze dried | MR | lyophilized | SC | 1 | 10 | 2.5 | 4.0 |
| Measles-Mumps-Rubella freeze dried | MMR | lyophilized | SC | 1 | 1 | 26.1 | 26.1 |
| Measles-Mumps-Rubella freeze dried | MMR | lyophilized | SC | 1 | 2 | 13.1 | 13.1 |
| Measles-Mumps-Rubella freeze dried | MMR | lyophilized | SC | 1 | 5 | 5.2 | 7.0 |
| Measles-Mumps-Rubella freeze dried | MMR | lyophilized | SC | 1 | 10 | 3.0 | 4.0 |
| Polio | OPV | liquid | Oral | 4 | 10 | 2.0 |  |
| Polio | OPV | liquid | Oral | 4 | 20 | 1.0 |  |
| Yellow fever | YF | lyophilized | SC | 1 | 5 | 6.5 | 7.0 |
| Yellow fever | YF | lyophilized | SC | 1 | 10 | 2.5 | 3.0 |
| Yellow fever | YF | lyophilized | SC | 1 | 20 | 1.5 | 2.0 |
| Yellow fever | YF | lyophilized | SC | 1 | 50 | 0.7 | 1.0 |
| DTP-HepB combined | DTP-HepB | liquid | IM | 3 | 1 | 9.7 |  |
| DTP-HepB combined | DTP-HepB | liquid | IM | 3 | 2 | 6.0 |  |
| DTP-HepB combined | DTP-HepB | liquid | IM | 3 | 10 | 3.0 |  |
| Hepatitis B | HepB | liquid | IM | 3 | 1 | 18.0 |  |
| Hepatitis B | HepB | liquid | IM | 3 | 2 | 13.0 |  |
| Hepatitis B | HepB | liquid | IM | 3 | 6 | 4.5 |  |
| Hepatitis B | HepB | liquid | IM | 3 | 10 | 4.0 |  |
| Hepatitis B UniJect | HepB | liquid | IM | 3 | Uniject | 12.0 |  |
| Hib liquid | Hib_liq | liquid | IM | 3 | 1 | 15.0 |  |
| Hib liquid | Hib_liq | liquid | IM | 3 | 10 | 2.5 |  |
| Hib freeze-dried | Hib_lyo | lyophilized | IM | 3 | 1 | 13.0 | 35.0 |
| Hib freeze-dried | Hib_lyo | lyophilized | IM | 3 | 2 | 6.0 |  |
| Hib freeze-dried | Hib_lyo | lyophilized | IM | 3 | 10 | 2.5 | 3.0 |
| DTP liquid + Hib freeze-dried | DTP+Hib | liquid+lyop. | IM | 3 | 1 | 45.0 |  |
| DTP-Hib combined liquid | DTP+Hib | liquid+lyop. | IM | 3 | 10 | 12.0 |  |
| DTP-Hib combined liquid | DTP-Hib | liquid | IM | 3 | 1 | 32.3 |  |
| DTP-HepB liquid + Hib freeze-dried | DTP-Hib | liquid | IM | 3 | 10 | 2.5 |  |
| DTP-HepB liquid + Hib freeze-dried | DTP-HepB+Hib | liquid+lyop. | IM | 3 | 1 | 22.0 |  |
| DTP-HepB-Hib liquid | DTP-HepB+Hib | liquid+lyop. | IM | 3 | 2 | 11.0 |  |
| DTP-HepB-Hib liquid | DTP-HepB-Hib | liquid | IM | 3 | 10 | 4.4 |  |
| DTP-HepB-Hib liquid | DTP-HepB-Hib | liquid | IM | 3 | 2 | 13.1 |  |
| DTP-HepB-Hib liquid | DTP-HepB-Hib | liquid | IM | 3 | 1 | 19.2 |  |
| Meningitis A/C | MV_A/C | lyophilized | SC | 1 | 10 | 2.5 | 4.0 |
| Meningitis A/C | MV_A/C | lyophilized | SC | 1 | 50 | 1.5 | 3.0 |
| Meningococcal A/C/W/ | MV_A/C/W | lyophilized | SC | 1 | 50 | 1.5 | 3.0 |
| Meningococcal A/C/W/Y | MV_A/C/W/Y | lyophilized | SC | 1 | 10 | 2.5 | 4.0 |
| Meningitis W135 | MV_W135 | lyophilized | SC | 1 | 10 | 2.5 | 4.0 |
| Meningitis A conjugate | Men_A | lyophilized | SC | 2 | 10 | 2.6 | 4.0 |
| Japanese Encephalitis | JE_lyo | lyophilized | SC | 3 | 10 | 15.0 |  |
| Japanese Encephalitis | JE_lyo | lyophilized | SC | 3 | 10 | 8.1 | 8.1 |
| Japanese Encephalitis | JE_lyo | lyophilized | SC | 3 | 5 | 2.5 | 2.9 |
| Japanese Encephalitis | JE_lyo | lyophilized | SC | 3 | 1 | 12.6 | 11.5 |
| Japanese Encephalitis | JE_liq | liquid | SC | 3 | 10 | 3.4 |  |
| Rota vaccine | Rota_lyo | lyophilized | Oral | 2 | 1 | 156.0 |  |
| Rota vaccine | Rota_liq | liquid | Oral | 2 | 1 | 17.1 |  |
| Rota vaccine | Rota_liq | liquid | Oral | 3 | 1 | 45.9 |  |
| Pneumo. conjugate vaccine 7-valent | PCV-7 | liquid | IM | 3 | PFS | 55.9 |  |
| Pneumo. conjugate vaccine 7-valent | PCV-7 | liquid | IM | 3 | 1 | 21.0 |  |
| Pneumo. conjugate vaccine 10-valent | PCV-10 | liquid | IM | 3 | 1 | 11.5 |  |
| Pneumo. conjugate vaccine 10-valent | PCV-10 | liquid | IM | 3 | 2 | 4.8 |  |
| Pneumo. conjugate vaccine 13-valent | PCV-13 | liquid | IM | 3 | 1 | 12.0 |  |
| Polio inactivated | IPV | liquid | IM | 3 | PFS | 107.4 |  |
| Polio inactivated | IPV | liquid | IM | 3 | 10 | 2.5 |  |
| Polio inactivated | IPV | liquid | IM | 3 | 1 | 15.7 |  |
| Human Papilomavirus vaccine | HPV | liquid | IM | 3 | 1 | 15.0 |  |
| Human Papilomavirus vaccine | HPV | liquid | IM | 3 | 2 | 5.7 |  |
| Monovalent OPV-1 | mOPV1 | liquid | Oral |  | 20 | 1.5 |  |
| Monovalent OPV-3 | mOPV3 | liquid | Oral |  | 20 | 1.5 |  |

# Attachments

# List of Supporting Documents Attached to this Proposal

| Document | Section | Document Number | Mandatory[1] |
| --- | --- | --- | --- |
| MoH Signature (or delegated authority) of Proposal |  | 1 | Yes |
| MoF Signature (or delegated authority) of Proposal |  | 2 | Yes |
| Signatures of ICC or HSCC or equivalent in Proposal |  | 3 | Yes |
| Minutes of ICC/HSCC meeting endorsing Proposal |  | 4 | Yes |
| comprehensive Multi Year Plan - cMYP |  | 5 | Yes |
| cMYP Costing tool for financial analysis |  | 6 | Yes |
| Minutes of last three ICC/HSCC meetings |  | 7 | Yes |
| Improvement plan based on EVM |  | 8 | Yes |
| WHO/UNICEF Joint Reporting Form (JRF) |  | 9 |  |
| ICC/HSCC workplan for forthcoming 12 months |  | 10 |  |
| National policy on injection safety |  | 11 |  |
| Action plans for improving injection safety |  | 15 |  |
| Plan for NVS introduction (if not part of cMYP) |  |  |  |
| Banking details |  | 13 |  |

[1] Please indicate the duration of the plan / assessment / document where appropriate

# Attachments

List of all the mandatory and optional documents attached to this form

Note: Use the Upload file arrow icon to upload the document. Use the Delete item icon to delete a line. To add new lines click on the New item icon in the Action column.

| ID | File type | File name |  | New file | Actions |
| --- | --- | --- | --- | --- | --- |
|  | Description | Date and Time | Size |  |  |
| 1 | File Type: MoH Signature (or delegated authority) of Proposal * File Desc: Signature of Dr. Jose Vieira Dias Van-Dunem Ministry of Health | File name: 01. Ministry of Health signature.pdf Date/Time: 01.06.2011 15:41:50 Size: 537 KB |  |  |  |
| 2 | File Type: MoF Signature (or delegated authority) of Proposal * File Desc: Ministry of Finance Dr. Carlos Alberto Lopes signature | File name: 02 Ministry of Finance signature.pdf Date/Time: 01.06.2011 15:46:49 Size: 590 KB |  |  |  |
| 3 | File Type: Signatures of ICC or HSCC or equivalent in Proposal * File Desc: Signatures of ICC members | File name: 03 ICC members signature in proposal.pdf Date/Time: 01.06.2011 15:51:47 Size: 657 KB |  |  |  |
| 4 | File Type: Minutes of ICC/HSCC meeting endorsing Proposal * File Desc: Approval GAVI proposal and EPI MYP by ICC and Technical enlarged Immunization Commitee | File name: 04 Endorsing proposal Minutes ICC and Technical.doc Date/Time: 01.06.2011 16:19:45 Size: 181 KB |  |  |  |
| 5 | File Type: comprehensive Multi Year Plan - cMYP * File Desc: EPI Comprehensive Multiyear Plan 2011-2015 | File name: 6. ANG EPI Multiyear Plan 2011 2015.doc Date/Time: 01.06.2011 16:26:23 Size: 2 MB |  |  |  |
| 6 | File Type: cMYP Costing tool for financial analysis * File Desc: cMYP Costing Tool | File name: 7. ANG COSTING TOOL.xls Date/Time: 01.06.2011 16:38:19 Size: 3 MB |  |  |  |
| 7 | File Type: Minutes of last three ICC/HSCC meetings * File Desc: Minutes of the 7th, 8th and 9th ICC meetings | File name: 8. Minutes of last three ICC Meetings.doc Date/Time: 01.06.2011 17:07:13 Size: 241 KB |  |  |  |
| 8 | File Type: Improvement plan based on EVM * File Desc: Interim Report EVM Assesment | File name: 09. EVM interim report.doc Date/Time: 01.06.2011 17:17:23 Size: 1 MB |  |  |  |
| 9 | File Type: WHO/UNICEF Joint Reporting Form (JRF) File Desc: Immunization WHO UNICEF Joint Report Form 2010 | File name: 10. WHO UNICEF JRF 2010.xls Date/Time: 01.06.2011 17:22:39 Size: 445 KB |  |  |  |
| 10 | File Type: ICC/HSCC workplan for forthcoming 12 months File Desc: Inter Agency Coordiantion Committee Plan June 2011-2012 | File name: 11. ICC WORKPLAN.doc Date/Time: 01.06.2011 17:26:38 Size: 57 KB |  |  |  |
| 11 | File Type: National policy on injection safety File Desc: National Policy of Injectin safety | File name: 12. INJECTION SAFETY POLICY.doc Date/Time: 01.06.2011 17:29:35 Size: 69 KB |  |  |  |
| 12 | File Type: other File Desc: National Health Police | File name: 13. NATIONAL HEALTH POLICY.pdf Date/Time: 01.06.2011 17:34:26 Size: 1 MB |  |  |  |
| 13 | File Type: Banking details File Desc: Data of finantial Institution and authorized signatures | File name: Angola bank details.doc Date/Time: 01.06.2011 18:20:13 Size: 437 KB |  |  |  |
| 14 | File Type: other File Desc: Angola EPI Annual Plan of Action 2011 | File name: Angola EPI Annual Plan of action 2011.xls Date/Time: 01.06.2011 18:22:05 Size: 39 KB |  |  |  |
| 15 | File Type: Action plans for improving injection safety File Desc: Justification for not presenting InjectionSafety Plan | File name: Angola ACTION PLAN FOR IMPROVING INJECTION SAFETY.doc Date/Time: 14.06.2011 04:23:13 Size: 121 KB |  |  |  |