GAVI Alliance

Application Form for Country Proposals

For Support to New and Under-Used Vaccines (NVS)

Submitted by

The Government of

Afghanistan

Date of submission: Not submitted yet

Deadline for submission: 1 Jun 2011

Select Start and End Year of your Comprehensive Multi-Year Plan (cMYP)

| Start Year | 2011 | End Year | 2015 |
| --- | --- | --- | --- |

Revised in January 2011

(To be used with Guidelines of December 2010)

Please submit the Proposal using the online platform https://AppsPortal.gavialliance.org/PDExtranet.

Enquiries to: proposals@gavialliance.org or representatives of a GAVI partner agency. The documents can be shared with GAVI partners, collaborators and general public. The Proposal and attachments must be submitted in English, French, Spanish, or Russian.

Note: Please ensure that the application has been received by the GAVI Secretariat on or before the day of the deadline.

The GAVI Secretariat is unable to return submitted documents and attachments to countries. Unless otherwise specified, documents will be shared with the GAVI Alliance partners and the general public.

GAVI ALLIANCE GRANT TERMS AND CONDITIONS FUNDING USED SOLELY FOR APPROVED PROGRAMMES The applicant country (“Country”) confirms that all funding provided by the GAVI Alliance will be used and applied for the sole purpose of fulfilling the programme(s) described in the Country’s application. Any significant change from the approved programme(s) must be reviewed and approved in advance by the GAVI Alliance. All funding decisions for the application are made at the discretion of the GAVI Alliance Board and are subject to IRC processes and the availability of funds. AMENDMENT TO THE APPLICATION The Country will notify the GAVI Alliance in its Annual Progress Report if it wishes to propose any change to the programme(s) description in its application. The GAVI Alliance will document any change approved by the GAVI Alliance, and the Country’s application will be amended. RETURN OF FUNDS The Country agrees to reimburse to the GAVI Alliance all funding amounts that are not used for the programme(s) described in its application. The country’s reimbursement must be in US dollars and be provided, unless otherwise decided by the GAVI Alliance, within sixty (60) days after the Country receives the GAVI Alliance’s request for a reimbursement and be paid to the account or accounts as directed by the GAVI Alliance. SUSPENSION/ TERMINATION The GAVI Alliance may suspend all or part of its funding to the Country if it has reason to suspect that funds have been used for purpose other than for the programmes described in the Country’s application, or any GAVI Alliance-approved amendment to the application. The GAVI Alliance retains the right to terminate its support to the Country for the programmes described in its application if a misuse of GAVI Alliance funds is confirmed. ANTICORRUPTION The Country confirms that funds provided by the GAVI Alliance shall not be offered by the Country to any third person, nor will the Country seek in connection with its application any gift, payment or benefit directly or indirectly that could be construed as an illegal or corrupt practice. AUDITS AND RECORDS The Country will conduct annual financial audits, and share these with the GAVI Alliance, as requested. The GAVI Alliance reserves the right, on its own or through an agent, to perform audits or other financial management assessment to ensure the accountability of funds disbursed to the Country. The Country will maintain accurate accounting records documenting how GAVI Alliance funds are used. The Country will maintain its accounting records in accordance with its government-approved accounting standards for at least three years after the date of last disbursement of GAVI Alliance funds. If there is any claims of misuse of funds, Country will maintain such records until the audit findings are final. The Country agrees not to assert any documentary privilege against the GAVI Alliance in connection with any audit. CONFIRMATION OF LEGAL VALIDITY The Country and the signatories for the Country confirm that its application, and Annual Progress Report, are accurate and correct and form legally binding obligations on the Country, under the Country’s law, to perform the programmes described in its application, as amended, if applicable, in the APR. CONFIRMATION OF COMPLIANCE WITH THE GAVI ALLIANCE TRANSPARANCY AND ACCOUNTABILITY POLICY The Country confirms that it is familiar with the GAVI Alliance Transparency and Accountability Policy (TAP) and complies with the requirements therein. USE OF COMMERCIAL BANK ACCOUNTS The Country is responsible for undertaking the necessary due diligence on all commercial banks used to manage GAVI cash-based support. The Country confirms that it will take all responsibility for replenishing GAVI cash support lost due to bank insolvency, fraud or any other unforeseen event. ARBITRATION Any dispute between the Country and the GAVI Alliance arising out of or relating to its application that is not settled amicably within a reasonable period of time, will be submitted to arbitration at the request of either the GAVI Alliance or the Country. The arbitration will be conducted in accordance with the then-current UNCITRAL Arbitration Rules. The parties agree to be bound by the arbitration award, as the final adjudication of any such dispute. The place of arbitration will be Geneva, Switzerland. The language of the arbitration will be English. For any dispute for which the amount at issue is US$ 100,000 or less, there will be one arbitrator appointed by the GAVI Alliance. For any dispute for which the amount at issue is greater than US $100,000 there will be three arbitrators appointed as follows: The GAVI Alliance and the Country will each appoint one arbitrator, and the two arbitrators so appointed will jointly appoint a third arbitrator who shall be the chairperson. The GAVI Alliance will not be liable to the country for any claim or loss relating to the programmes described in the application, including without limitation, any financial loss, reliance claims, any harm to property, or personal injury or death. Country is solely responsible for all aspects of managing and implementing the programmes described in its application.

# Application Specification

Please specify for which type of GAVI support you would like to apply to.

Important note: To enable proper functioning of the form, please first select the cMYP years on the previous page.

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Type of Support | Vaccine | Start Year | End Year | Preferred second presentation[1] | Action |
| --- | --- | --- | --- | --- | --- |
| New Vaccines Support | Pneumococcal (PCV13), 1 doses/vial, Liquid | 2013 | 2015 | Pneumococcal (PCV10), 2 doses/vial, Liquid |  |

[1] This "Preferred second presentation" will be used in case there is no supply available for the preferred presentation of the selected vaccine ("Vaccine" column). If left blank, it will be assumed that the country will prefer waiting until the selected vaccine becomes available.

# Table of Contents

Sections

Main

Cover Page

GAVI Alliance Grants Terms and Conditions

1. Application Specification

2. Table of Contents

3. Executive Summary

4. Signatures

4.1. Signatures of the Government and National Coordinating Bodies

4.1.1. Government and the Inter-Agency Coordinating Committee for Immunisation

4.1.2. National Coordinating Body - Inter-Agency Coordinating Committee for Immunisation

4.1.3. The Inter-Agency Coordinating Committee for Immunisation

4.2. National Immunization Technical Advisory Group for Immunisation

4.2.1. The NITAG Group for Immunisation

5. Immunisation Programme Data

5.1. Basic facts

5.2. Current vaccination schedule

5.3. Trends of immunisation coverage and disease burden

5.4. Baseline and Annual Targets

Table 1: baseline figures

5.5. Summary of current and future immunisation budget

5.6. Summary of current and future financing and sources of funds

6. NVS

6.1. Capacity and cost (for positive storage)

6.2. Assessment of burden of relevant diseases (if available)

6.3.1. Requested vaccine ( Pneumococcal (PCV13), 1 doses/vial, Liquid )

6.3.2. Co-financing information

6.3.3. Wastage factor

6.3.4. Specifications of vaccinations with new vaccine

6.3.5. Portion of supply to be procured by the country (and cost estimate, US$)

6.3.6. Portion of supply to be procured by the GAVI Alliance (and cost estimate, US$)

6.3.7. New and Under-Used Vaccine Introduction Grant

7. Procurement and Management of New and Under-Used Vaccines

7.1. Vaccine management (EVSM/EVM/VMA)

8. Additional Comments and Recommendations

9. Annexes

Annex 1

Annex 1.1 - Pneumococcal (PCV13), 1 doses/vial, Liquid

Table 1.1  A - Rounded up portion of supply that is procured by the country and estimate of related cost in US$

Table 1.1  B - Rounded up portion of supply that is procured by GAVI and estimate of related cost in US$.

Table 1.1  C - Summary table for vaccine Pneumococcal (PCV13), 1 doses/vial, Liquid

Table 1.1  D - Estimated number of doses for vaccine Pneumococcal (PCV13), 1 doses/vial, Liquid associated injection safety material and related co-financing budget

Annex 2

10. Attachments

10.1 Documents required for NVS support

10.2 Attachments

Banking Form

# Executive Summary

Background of Pneumococcal vaccine application: 

The Ministry of Public Health (MOPH)of Afghanistan and ICC in Afghanistan are determined to take all available opportunities to reduce the childhood morbidity, mortality and disability due to vaccine preventable diseases by providing quality immunization services to all eligible population using existing vaccines and introduing new vaccine/s into national immunization program. The availability of Pneumococcal vaccine through GAVI support for introduction into the routine EPI services in GAVI eligible countries has caught the interest of both MOPH and its partners in Expanded Program on Immunization. 

Based on WHO recommendation and position paper on pneumococcal vaccine and expected contribution of pneumococcal vaccine towards reduction of child mortality in Afghanistan, the ICC held on 29th December 2010 directed EPI to put pneumococcal and Rotavirus vaccines on the agenda of NITAG for recommendation.The National Immunization Technical Advisory Group (NITAG) meetings held on 13th and 15th March 2011 discussed the introduction of Pneumococcal and Rota virus vaccine in EPI. The NITAG has recommended to MOPH to introduce pneumococcal vaccine into national immunization program first. The subsequent ICC meeting held on 14th May 2011 approved that Afghanistan should introduce the pneumococcal vaccine (PCV13) in its EPI Schedule in January 2013 and request GAVI for provision of Pneumococcal vaccine, in the form of single-dose liquid under its window of new and underused vaccines. 

Recent years have seen improvement of overall national immunization coverage, including the newly introduced vaccines (Hepatitis B and and Hib). An improved computerized recording/reporting tool enabling assessment of “timely” immunization by one year of age as well as vaccine management indicators has been introduced, and there is generally complete and regular reporting of data.

The overall immunization coverage is improving as summarized in table N01

Table 1 : Reported immunization coverage in percentage 2007-2010
----------------------------------------------------------------------------------------------------------
	 2007	 2008	 2009	 2010
----------------------------------------------------------------------------------------------------------
DPT3	 85 85 83 87
----------------------------------------------------------------------------------------------------------			
MCV1	 75 75 76 79			
. (Source : WHO/UNICEF Joint Reporting Forms for the respective years)
----------------------------------------------------------------------------------------------------------

Disease surveillance is improving, with clear and up-to-date national guidelines, case- based reporting for priority diseases and the introduction of computerized surveillance data management. 
The supply management system is working well, with no stock-outs in the last 12 months, and important progress has been made at the national vaccine store since it was assessed in 2007. Comprehensive Multi-Year Plan (cMYP): 

The cMYP was revised in 2010 and again updated in April 2011 to include plan of introduction of PCV13 vaccine from January 2013, and rotavirus in 2014. Financial analysis was also revised to include co-financing for PCV13 and rotavirus vaccines. The new cMYP is aligned to be valid with current MOPH budgetary cycle of Afghanistan fiscal year i.e upto the end of December 2015. During the period 2011-2015, the coverage target for children (0-11 m) to be immunized with DPT3 has been set to be at least 95% at national level and at least 80% each district. 
A coverage Evaluation Survey (CES) to validate the reported coverage is under prepration to be conducted by mid 2011. The CES will also determine the coverage according to gender . If any discrepancy in coverage among gender is discovered EPI Afghanistan will adopt appropriate strategies to rectify this. 
Cold chain: 

EPI Log Forecasting tool has been used to estimate the cold space required at various levels considering the likely introduction of PCV13 in 2013 and Rota virus vaccine in 2014. Accordinly, the total cold chain need for the country for 2011-2015 is estimated. The country is shifting from single - dose Penta to 10 dose in June 2011 and there is no need for for cold chain equipment for 2012 & 2013 as the requirement has been addressed in 2011. The requirement for cold chain equipment for the period 2011-2015 is calculated using EPI log-forecasting is attached and are summarized in table N02 below: 

Table2 : Additional Cold chain requirements					
	 2011	 2014	 2015	 2011--2015
---------------------------------------------------------------------------------------------------
Type of Equipment	No	Cost	No	Cost	No	Cost	No	Cost
---------------------------------------------------------------------------------------------------
National Level	 	 	 	 	 	 	 	 
WICR-80m3	1	 123,472 	 	 	 	 	1	 123,472 
WIFR-80m3	1	 156,887 	 	 	 	 	1	 156,887 
Regional Level	 	 	 	 	 	 	 	 - 
WICR-60m3	1	 108,125 	 	 	 	 	1	 108,125 
WICR-15m3	1	 43,028 	 	 	 	 	1	 43,028 
HBC-340/IL	0 14 16,744 	9 10,764 	23	 27,508 
Provincial Level	 	 	 	 	 	 	 	 - 
FCW 200	1	 1,172 	 	 	 	 	1	 1,172 
HBC-340/IL	41	 49,036 	32 38,272 	 1	 1,196 74 88,504 
----------------------------------------------------------------------------------------------------- 
Total	 	 481,720 55,016 	 	 11,960 	 548,696 
-----------------------------------------------------------------------------------------------------


Introduction of vaccine: 

A plan of action has been prepared for introduction of the PCV13 vaccine. This includes advocacy, proper recording and reporting, and monitoring, besides training on routine EPI aspects including vaccine management and vaccine wastage reduction. These activities will cost around US$ 597,059 and would be funded by the GAVI support for introduction of the new vaccine. 

Financial sustainability: 

Despite the fact that GOA has planned to gradually increase its contribution towards NIP, given the current geo-political and economic condition of the country, support of EPI donors for NIP will be crucial at least for a few more years. Therefore MoPH and NIP have developed strategies to work towards financial suitability of NIP which not only target GOA but also the EPI donors. A frame work for monitoring the implementation of the financial sustainability strategies has been developed as part of the updated cMYP.
Through this application , GOA requests GAVI to support EPI Afghanistan by providing with PCV13 single dose liquid vaccine for the time being for the period 2013-15 as detailed in table 3 below in addition to the Vaccine introduction grant amounting to $597,059

Table 3 : Traget population and co sharing of PCV13 
------------------------------------------------------------------------------------------------------------------
	 2013	 2014	2015	 Total (2013-15)
------------------------------------------------------------------------------------------------------------------
Number of surviving infants 1,289,655 1,320,607 1,352,302 3,962,564
------------------------------------------------------------------------------------------------------------------				
Number of children targeted with 1st dose of PCV13 1,147,793 1,188,547 1,217,072 3,553,412
------------------------------------------------------------------------------------------------------------------				
Coverage Target for PCV13 %	 89 90 90
------------------------------------------------------------------------------------------------------------------			
No of vaccine doses required	 4,530,763 3,785,478 3,865,904 12,182,145
------------------------------------------------------------------------------------------------------------------			
Total cost of vaccine including freight (US$) 19,789,000 16,296,000 16,687,500 52,772,500 
------------------------------------------------------------------------------------------------------------------				
Total cost of Injection safety supplies (US$) 373,932 320,924 327,863 1,022,719
------------------------------------------------------------------------------------------------------------------				
Total Cost ( Vaccines + Inj safety equipment) (US$) 16,231,602 13,570,096 13,858,525 43,660,223
------------------------------------------------------------------------------------------------------------------				
Amount to be paid by GAVI 	 18,670,000 15,374,000 15,743,500 49,787,500
------------------------------------------------------------------------------------------------------------------			
Amount to be paid by country 			 1,119,000 922,000 944,000 2,985,000
------------------------------------------------------------------------------------------------------------------
Source: cMYP 2011-2015

# Signatures

# Signatures of the Government and National Coordinating Bodies

# Government and the Inter-Agency Coordinating Committee for Immunisation

The Government of Afghanistan would like to expand the existing partnership with the GAVI Alliance for the improvement of the infants routine immunisation programme of the country, and specifically hereby requests for GAVI support for Pneumococcal (PCV13) 1 doses/vial Liquid introduction.

The Government of Afghanistan commits itself to developing national immunisation services on a sustainable basis in accordance with the Comprehensive Multi-Year Plan (cMYP) presented with this document. The Government requests that the GAVI Alliance and its partners contribute financial and technical assistance to support immunisation of children as outlined in this application.

Tables 6.(n).5. (where (n) depends on the vaccine) in the NVS section of this application shows the amount of support in either supply or cash that is required from the GAVI Alliance. Tables 6.(n).4. of this application shows the Government financial commitment for the procurement of this new vaccine (NVS support only).

Following the regulations of the internal budgeting and financing cycles the Government will annually release its portion of the co-financing funds in the month of July .

Please note that this application will not be reviewed or approved by the Independent Review Committee (IRC) without the signatures of both the Minister of Health & Minister of Finance or their delegated authority.

Enter the family name in capital letters.

| Minister of Health (or delegated authority) |  | Minister of Finance (or delegated authority) |  |
| --- | --- | --- | --- |
| Name | DR. SURAYA DALIL, A/Minister | Name | Mr. Hazrat Omar Zakhelwal, Minister of Finance |
| Date |  | Date |  |
| Signature |  | Signature |  |

This report has been compiled by

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

Enter the family name in capital letters.

| Full name | Position | Telephone | Email | Action |
| --- | --- | --- | --- | --- |
| Dr. AGHA GUL DOST | National EPI Manager | +93 799814812 | nationalepi05@yahoo.com |  |

# National Coordinating Body - Inter-Agency Coordinating Committee for Immunisation

We the members of the ICC, HSCC, or equivalent committee[1] met on the to review this proposal. At that meeting we endorsed this proposal on the basis of the supporting documentation which is attached.

[1] Inter-agency Coordinating Committee or Health Sector Coordinating Committee, or equivalent committee which has the authority to endorse this application in the country in question.

The endorsed minutes of this meeting are attached as DOCUMENT NUMBER: 4.

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

Enter the family name in capital letters.

| Name/Title | Agency/Organisation | Signature | Action |
| --- | --- | --- | --- |
| Dr. Suraya DALIL, A/ Minister of Public Health | MOPH |  |  |
| Dr. M. Taoufiq MASHAL, DG Preventive Medicine | MOPH |  |  |
| Dr. Ahmad Jan NAIM, DG Policy & Plan | MOPH |  |  |
| Dr. Agha Gul DOST, National EPI Manager | MOPH |  |  |
| Dr. A. Wali GHAYOUR, HSS/CSO Focal Point | MOPH |  |  |
| Mr. Shafiq AKBARI, Director of Finance | MOPH |  |  |
| Dr. Zahra MOHAMMAD, Program Officer, EPI | UNICEF |  |  |
| Dr. Adriana ZARRELI, Chief Health & Nutrition | UNICEF |  |  |
| Dr. Arshad QUDUS, Medical Officer, PEI | WHO |  |  |
| Dr. A. Shakoor WACIQI, NPO, EPI | WHO |  |  |
| Dr. Iqbal ROSHANI, Representative | USAID |  |  |
| Dr. SAYEED, Representative | WB |  |  |
| Dr. Ghulam Haider RAFIQI, Representative | MSH |  |  |
| Dr. Zahid RASOOLI, Representative | EU |  |  |
| Mr. Waheed POPALZAI | MoF |  |  |
| Dr. WASIULLAH, Representative | BDN (NGO) |  |  |

In case the GAVI Secretariat has queries on this submission, please contact

Enter the family name in capital letters.

| Name | Dr. Agha Gul DOST | Title | National EPI Manager |
| --- | --- | --- | --- |
| Tel no | +93 799814812 |  |  |
| Fax no |  | Address | Ministry of Public Health Great Masoud Square Kabul, Afghanistan |
| Email | nationalepi05@yahoo.com |  |  |

# The Inter-Agency Coordinating Committee for Immunisation

Agencies and partners (including development partners and NGOs) supporting immunisation services are co-ordinated and organised through an inter-agency coordinating mechanism (ICC, HSCC, or equivalent committee). The ICC, HSCC, or equivalent committee is responsible for coordinating and guiding the use of the GAVI NVS support. Please provide information about the ICC, HSCC, or equivalent committee in your country in the table below.

Profile of the ICC, HSCC, or equivalent committee

| Name of the committee | Inter-agency coordination committee for immunization |
| --- | --- |
| Year of constitution of the current committee | 2004 |
| Organisational structure (e.g., sub-committee, stand-alone) | Stand - alone |
| Frequency of meetings | Quarterly and need - base |

Composition

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

Enter the family name in capital letters.

| Function | Title / Organisation | Name |  |
| --- | --- | --- | --- |
| Chair | Minister of Public Health | Dr. Suraya DALIL |  |
| Secretary | National EPI Manager | Dr. Agha Gul DOST |  |
| Members | See document N0 4 |  | Action |

Major functions and responsibilities of the committee

1. Review & endorse the EPI annual plan of actions 2. Follow-up on the implementation of the annual and multi-year plan of actions of immunization 3. Review progress reports on performance of immunization programs and utilization of fund 4. Advocacy for strengthening immunization program and financial sustainability 4. Review & endorse the final settlement of accounts and annual reports

Three major strategies to enhance the committee's role and functions in the next 12 months

| 1. | Coordinated with all partners and stakeholders for provision of managerial, technical and financial support in conducting national immunization coverage evaluation survey. |
| --- | --- |
| 2. | Ensure mobilization of resources from government, donors and private sector & budgeting and reporting for immunization programs including introduction of new vaccine/s. |
| 3. | Strengthen and oversee the quality of communication activties by creating a sub-social mobilization planning committee under ICC to formulate strategies for immunization advocacy and communication. |

# National Immunization Technical Advisory Group for Immunisation

(If it has been established in the country)

We the members of the NITAG met on the 15.03.2011 to review this proposal. At that meeting we endorsed this proposal on the basis of the supporting documentation which is attached.

The endorsed minutes of this meeting are attached as DOCUMENT NUMBER: 5.

In case the GAVI Secretariat has queries on this submission, please contact

Enter the family name in capital letters.

| Name | Dr. Ghulam Haider Rafiqi | Title | Program Manager, Capcity Building |
| --- | --- | --- | --- |
| Tel no | +93 706155628 |  |  |
| Fax no |  | Address | Ayoub Khan Mina, MSH Office, Kabul, Afghanistan |
| Email | grafiqi@msh.org |  |  |

# The NITAG Group for Immunisation

Profile of the NITAG

| Name of the NITAG | National Immunization Technical Advisory Group (NITAG) |
| --- | --- |
| Year of constitution of the current NITAG | 2009 |
| Organisational structure (e.g., sub-committee, stand-alone) | Stand-alone |
| Frequency of meetings | Two per year and need-base |

Composition

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

Enter the family name in capital letters.

| Function | Title / Organisation | Name |  |
| --- | --- | --- | --- |
| Chair | Program Manager for Capcity Building, MSH | Dr. Ghulam Haider RAFIQI |  |
| Secretary | National EPI Manager | Dr. Agha Gul DOST |  |
| Members | Lecturer for post-graduate medical doctors | Dr.Rafi RAHMANI | Action |
|  | Lecture, Medical University, Pediatrician | Drs. Farida Momand |  |
|  | Lecturer in Kabul Medical University, internal medicine | Dr.Farid Danish |  |
|  | Advisor to health promotion, researcher | Dr.Shafiqullah Hemat |  |
|  | Lecturer for post-graduate doctors, Specialist, internal medicine | Dr. Sayed Abdulah Sadat |  |
|  | National EPI Manager | Dr. Dost |  |
|  | Director of Preventive Medicine & PHC, MOPH | Dr. Toufiq Mashal |  |
|  | M & E Officer, NEPI, MOPH | Dr. Roqia Naser |  |
|  | Medical coordinator AHDS (NGOs | Dr.Mohammad Kabir |  |
|  | EPI Specialist, UNICEF | Dr. Zahra |  |
|  | National Professional Officer, EPI, WHO | Dr. A. Shakoor |  |
|  | Pediatrician, MOHE | Dr.Ishaq Mashir |  |

Major functions and responsibilities of the NITAG

NITAG advises and guides the national government, ministry of health, national immunization programs, and/or other relevant institutions and organizations on: 1. Policy analysis and strategy formulation for the control of vaccine preventable diseases through immunization, 2. Monitoring of immunization program, and collection and identification of important data for policy decisions and making, 3. Optimal scientific recommendations and development for the use of vaccines and control of vaccine preventable diseases based on the particular circumstances of the country.

Three major strategies to enhance the NITAG’s role and functions in the next 12 months

| 1. | Review national immunization policy and provide recommendations for strengthening routine immunization programs |
| --- | --- |
| 2. | Advise MOPH and other Ministries for inter-sectoral cooperation and mobilization of resources for immunization program including introduction of new vaccine/s |
| 3. | Assess EPI human resource situation and provide advice/recommendations to MOPH and MoF for improving technical capacity of personnel, filling gaps in human resources particularly in remote and difficult to-reach areas and retention of staff. |

# Immunisation Programme Data

Please complete the tables below, using data from available sources. Please identify the source of the data, and the date. Where possible use the most recent data and attach the source document.

- Please refer to the Comprehensive Multi-Year Plan for Immunisation (cMYP) (or equivalent plan) and attach a complete copy (with an Executive Summary) as DOCUMENT NUMBER 6

- Please refer to the two most recent annual WHO/UNICEF Joint Reporting Forms (JRF) on Vaccine Preventable Diseases.

- Please refer to Health Sector Strategy documents, budgetary documents, and other reports, surveys etc, as appropriate.

# Basic facts

For the year (most recent; specify dates of data provided)

|  | Figure |  | Year | Source |
| --- | --- | --- | --- | --- |
| Total population | 28,728,596 |  | 2010 | UNIDATA |
| Infant mortality rate (per 1000) | 129 |  | 2006 | Household Survey by JH University, India, 2006). |
| Surviving Infants[1] | 1,289,655 |  | 2010 | UNIDATA |
| GNI per capita (US$) | 486 |  | 2009 | WHO NHA 2009 |
| Total Health Expenditure (THE) as a percentage of GDP | 42.00 | % | 2009 | WHO NHA 2009 |
| General government expenditure on health (GGHE) as % of General government expenditure | 23.60 | % | 2009 | WHO NHA 2009 |

[1] Surviving infants = Infants surviving the first 12 months of life

Please provide some additional information on the planning and budgeting context in your country; also indicate the name and date of the relevant planning document for health

In November 2000, Afghanistan submitted the first national Multi-Year Plan of Action (cMYP) for EPI for 2001 to 2005. The cMYP 2001-2005 served as a national operational plan for immunization system development and immunization service delivery and also to meet the condition for accessing the Global Alliance for Vaccine and Immunization (GAVI) grant for Immunization System Strengthening and Injection Safety. In spite of many obstacles familiar to post crisis countries, most of the objectives of the MYPoA 2001-2005 have been accomplished with the support of GAVI, partners and international donors. The cMYP 2006-2010 had been developed in 2006 and updated in the beginning of 2007 and aligned to be valid throughout current MOPH budgetary cycle of the Afghanistan. However as the EPI reporting is undertaken on calendar year basis, the activities in the plan are therefore included till end 2010. The second cMYP was different from the first cMYP. EPI functions are implemented in close coordination and collaboration with other relevant departments of the Ministry of Public Health, partners such as WHO and UNICEF as well as new implementing partners in the field. As an operational plan for meeting the commitment

Is the cMYP (or updated Multi-Year Plan) aligned with this document (timing, content, etc.)?

The updated cMYP period for immunization is 2011-2015 and is aligned with Health Sector Strategic Plan; the cMYP includes provision of introduction of pneumococcal vaccine in beginning 2013 and Rota virus vaccine in 2014. New vaccines introduction for achieving MDGs is part of the Health Sector Strageic plan.

Please indicate the national planning budgeting cycle for health

MOPH have been required to prepare a five year program budget (2011-2015) to bring the normal practice of three-year budget cycle to five years. The national planning budgeting cycle for health sector include: - Annual plan - Mid-term expenditure framework The national planning budgeting cycle for health has been every three years in the past. However MOPH have been required to prepare a five-year program budget (2011-2015).

Please indicate the national planning cycle for immunisation

The planning cycle for immunization used to be every five years and updated annually. However as explained in above paragraph, it is currently for five years (2011-2015).

Please indicate if sex disaggregated data (SDD) is used in immunisation routine reporting systems

Currently no SDD is used in routine immunization

Please indicate if gender aspects relating to introduction of a new vaccine have been addressed in the introduction plan

The EPI services are provided irresperctive of the gender. Currently there is no evidence that EPI services are skewed towards one gender. However in the CES planned for mid 2011 this issue would be asseees. If inequality of EPI coverage for gender is found appropriate strategies will be undertaken to rectify the situation.

# Current vaccination schedule

Traditional, New Vaccines and Vitamin A supplement (refer to cMYP pages)

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Vaccine (do not use trade name) | Ages of administration (by routine immunisation services) | Given in entire country | Comments | Action |
| --- | --- | --- | --- | --- |
| BCG | Birth to 11 months | Yes |  |  |
| DTP-HepatitisB-Hib | 6, 10, 14 weeks | Yes |  |  |
| OPV | Birth, 6, 10, 14 weeks, 9 months | Yes |  |  |
| Measles | 9 months and 18 months | Yes |  |  |
| TT+ | Women of 15-45 years, 1st contact pregnancy+M1+M6+Y1+Y1 | Yes |  |  |
| Vitamin A |  |  | Twice a year during NIDs to all children under age 6 months -5years |  |

# Trends of immunisation coverage and disease burden

(as per last two annual WHO/UNICEF Joint Reporting Form on Vaccine Preventable Diseases)

| Trends of immunisation coverage (percentage) |  |  |  |  |  | Vaccine preventable disease burden |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Vaccine |  | Reported |  | Survey |  | Disease | Number of reported cases |  |
|  |  | 2009 | 2010 | 2006 |  |  | 2009 | 2010 |
| BCG |  | 82 | 87 | 70 |  | Tuberculosis |  |  |
| DTP | DTP1 | 94 | 99 |  |  | Diphtheria |  |  |
|  | DTP3 | 83 | 87 | 35 |  | Pertussis |  |  |
| Polio 3 |  | 83 | 87 | 70 |  | Polio | 31 | 25 |
| Measles (first dose) |  | 76 | 79 | 63 |  | Measles | 2,861 | 1,989 |
| TT2+ (Pregnant women) |  | 68 | 75 |  |  | NN Tetanus | 19 | 23 |
| Hib3 |  | 83 | 87 |  |  | Hib[2] | 0 | 3 |
| Yellow Fever |  |  |  |  |  | Yellow fever |  |  |
| HepB3 |  | 83 | 87 |  |  | HepBsero-prevalence[1] |  |  |
| Vitamin A supplement Mothers (< 6 weeks post-delivery) |  |  |  |  |  |  |  |  |
| Vitamin A supplement Infants (>6 months) |  |  |  |  |  |  |  |  |

[1] If available

[2] Note: JRF asks for Hib meningitis

If survey data is included in the table above, please indicate the years the surveys were conducted, the full title and if available, the age groups the data refers to

There is discrepancy between reported immunization coverage and NRVA 2007/2008. The NRVA (National Risk and Vulnerability Assesment) report published indicates the vaccination coverage among children 12-23 month as follow:BCG-74%, OPV3-71%, DPT3-43%, measles-56%, TT2-67%. The MOPH has planned immunization coverage evaluation survey in the midle 2011.

# Baseline and Annual Targets

(refer to cMYP pages)

Table 1: baseline figures

| Number | Base Year | Baseline and Targets |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2010 | 2013 | 2014 | 2015 |  |  |  |
| Total births | 1,376,369 | 1,480,661 | 1,516,196 | 1,552,585 |  |  |  |
| Total infants' deaths | 177,552 | 191,006 | 195,589 | 200,283 |  |  |  |
| Total surviving infants | 1,198,817 | 1,289,655 | 1,320,607 | 1,352,302 |  |  |  |
| Total pregnant women | 1,376,369 | 1,480,661 | 1,516,196 | 1,552,585 |  |  |  |
| Number of infants vaccinated (to be vaccinated) with BCG | 1,199,858 | 1,317,788 | 1,364,576 | 1,397,326 |  |  |  |
| BCG coverage (%)[1] | 87% | 89% | 90% | 90% |  |  |  |
| Number of infants vaccinated (to be vaccinated) with OPV3 | 1,037,889 | 1,147,792 | 1,188,546 | 1,217,072 |  |  |  |
| OPV3 coverage (%)[2] | 87% | 89% | 90% | 90% |  |  |  |
| Number of infants vaccinated (or to be vaccinated) with DTP1[3] | 1,185,135 | 1,263,861 | 1,294,194 | 1,325,255 |  |  |  |
| Number of infants vaccinated (to be vaccinated) with DTP3[3] | 1,037,889 | 1,147,792 | 1,188,546 | 1,217,072 |  |  |  |
| DTP3 coverage (%)[2] | 87% | 89% | 90% | 90% |  |  |  |
| Wastage[1] rate in base-year and planned thereafter for DTP (%) | 5% | 25% | 25% | 25% |  |  |  |
| Wastage[1] factor in base-year and planned thereafter for DTP | 1.05 | 1.33 | 1.33 | 1.33 |  |  |  |
| Target population vaccinated with 1st dose of Pneumococcal | 0 | 1,263,861 | 1,294,194 | 1,325,255 |  |  |  |
| Target population vaccinated with 3rd dose of Pneumococcal | 0 | 1,147,792 | 1,188,546 | 1,217,072 |  |  |  |
| Pneumococcal coverage (%)[2] | 0% | 89% | 90% | 90% |  |  |  |
| Infants vaccinated (to be vaccinated) with 1st dose of Measles | 946,750 | 1,096,206 | 1,162,134 | 1,217,071 |  |  |  |
| Measles coverage (%)[2] | 79% | 85% | 88% | 90% |  |  |  |
| Pregnant women vaccinated with TT+ | 1,376,369 | 1,184,528 | 1,288,766 | 1,397,326 |  |  |  |
| TT+ coverage (%)[4] | 100% | 80% | 85% | 90% |  |  |  |
| Vit A supplement to mothers within 6 weeks from delivery |  |  |  |  |  |  |  |
| Vit A supplement to infants after 6 months |  |  |  |  |  |  |  |
| Annual DTP Drop-out rate[ ( DTP1 - DTP3 ) / DTP1 ] x 100[5] | 12% | 9% | 8% | 8% |  |  |  |

[1] Number of infants vaccinated out of total births

[2] Number of infants vaccinated out of total surviving infants

[3] Indicate total number of children vaccinated with either DTP alone or combined

[4] Number of pregnant women vaccinated with TT+ out of total pregnant women

[5] The formula to calculate a vaccine wastage rate (in percentage):[ ( A – B ) / A ] x 100. Whereby: A = the number of doses distributed for use according to the supply records with correction for stock balance at the end of the supply period; B = the number of vaccinations with the same vaccine in the same period.

# Summary of current and future immunisation budget

(or refer to cMYP pages)

|  | Estimated costs per annum in US$ (in thousand US$) |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Cost category | Base Year | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |  |
|  | 2009 | 2013 | 2014 | 2015 |  |  |  |  |  |  |
| Routine Recurrent Cost |  |  |  |  |  |  |  |  |  |  |
| Vaccines (routine vaccines only) | 16,207,393 | 31,466,086 | 54,455,469 | 51,513,072 |  |  |  |  |  |  |
| Traditional vaccines | 1,807,393 | 3,121,958 | 3,270,630 | 3,238,314 |  |  |  |  |  |  |
| New and underused vaccines | 14,400,000 | 28,344,128 | 51,184,839 | 48,274,758 |  |  |  |  |  |  |
| Injection supplies | 1,260,000 | 1,142,885 | 1,214,147 | 1,283,800 |  |  |  |  |  |  |
| Personnel | 1,403,000 | 2,156,842 | 2,284,148 | 2,404,025 |  |  |  |  |  |  |
| Salaries of full-time NIP health workers (immunisation specific) | 1,089,000 | 1,735,075 | 1,830,566 | 1,920,173 |  |  |  |  |  |  |
| Per-diems for outreach vaccinators / mobile teams | 314,000 | 421,767 | 453,582 | 483,852 |  |  |  |  |  |  |
| Transportation | 738,918 | 1,033,173 | 1,144,814 | 1,296,886 |  |  |  |  |  |  |
| Maintenance and overheads | 2,116,528 | 2,619,720 | 2,748,865 | 2,861,078 |  |  |  |  |  |  |
| Training | 726,480 | 628,516 | 656,472 | 685,672 |  |  |  |  |  |  |
| Social mobilisation and IEC | 100,468 | 785,644 | 820,590 | 857,090 |  |  |  |  |  |  |
| Disease surveillance | 62,250 | 1,571,289 | 1,641,180 | 1,714,179 |  |  |  |  |  |  |
| Program management | 190,000 | 1,414,160 | 1,477,062 | 1,542,762 |  |  |  |  |  |  |
| Other | 14,000 | 0 | 0 | 0 |  |  |  |  |  |  |
| Subtotal Recurrent Costs | 22,819,037 | 42,818,315 | 66,442,747 | 64,158,564 |  |  |  |  |  |  |
| Routine Capital Costs |  |  |  |  |  |  |  |  |  |  |
| Vehicle | 103,383 | 135,544 | 152,604 | 181,524 |  |  |  |  |  |  |
| Cold chain equipment | 596,766 | 696,759 | 722,882 | 749,242 |  |  |  |  |  |  |
| Other capital equipment | 0 | 19,584 | 19,584 | 19,584 |  |  |  |  |  |  |
| Subtotal Capital Costs | 700,149 | 851,887 | 895,070 | 950,350 |  |  |  |  |  |  |
| Campaigns |  |  |  |  |  |  |  |  |  |  |
| Polio | 14,239,527 |  |  |  |  |  |  |  |  |  |
| Measles | 2,173,320 |  |  | 5,145,631 |  |  |  |  |  |  |
| Yellow Fever |  |  |  |  |  |  |  |  |  |  |
| MNT campaigns |  |  |  |  |  |  |  |  |  |  |
| Other campaigns |  |  |  |  |  |  |  |  |  |  |
| Subtotal Campaign Costs | 16,412,847 | 0 | 0 | 5,145,631 |  |  |  |  |  |  |
| GRAND TOTAL | 39,932,033 | 43,670,202 | 67,337,817 | 70,254,545 |  |  |  |  |  |  |

# Summary of current and future financing and sources of funds

Please list in the tables below the funding sources for each type of cost category (if known). Please try and indicate which immunisation program costs are covered from the Government budget, and which costs are covered by development partners (or the GAVI Alliance), and name the partners (or refer to cMYP).

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

|  |  | Estimated costs per annum in US$ (in thousand US$) |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Cost category | Funding source | Base Year | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |  |
|  |  | 2009 | 2013 | 2014 | 2015 |  |  |  |  |  |  |
| Routine Recurrent Cost |  |  |  |  |  |  |  |  |  |  |  |
| traditional and under used vaccines | UNICEF, GAVI | 16,207,393 | 31,466,086 | 54,455,469 | 51,513,071 |  |  |  |  |  |  |
| New vaccine (pneumo) | GAVI | 0 | 18,711,835 | 41,124,179 | 37,766,536 |  |  |  |  |  |  |
| Injection supplies | UNICEF, GAVI | 1,260,000 | 1,142,885 | 1,214,147 | 1,283,800 |  |  |  |  |  |  |
| Personnel | MOPH, GAVI, WB, EC, USAID, ARCS, | 1,403,040 | 1,735,075 | 1,830,566 | 1,920,173 |  |  |  |  |  |  |
| Transportation | UNICEF, GAVI, MOPH | 738,918 | 1,033,173 | 1,144,814 | 1,296,886 |  |  |  |  |  |  |
| Maintenance and pverheads | MOPH, UNICEF, GAVI | 2,116,528 | 2,619,720 | 2,748,865 | 2,861,078 |  |  |  |  |  |  |
| Short-term training | WHO, GAVI, UNICEF | 219,000 | 628,516 | 656,472 | 685,672 |  |  |  |  |  |  |
| IEC/social mobilization | MOPH, GAVI, UNICEF, WHO | 100,468 | 785,644 | 820,590 | 857,090 |  |  |  |  |  |  |
| Disease surveillance | WHO, GAVI | 62,250 | 1,571,289 | 1,641,180 | 1,714,179 |  |  |  |  |  |  |
| Program management | GAVI, MOPH | 190,000 | 1,414,160 | 1,477,062 | 1,542,762 |  |  |  |  |  |  |
| Other routine recurrent cost | MOPH | 14,000 | 0 | 0 | 0 |  |  |  |  |  |  |
| Routine Capital Costs |  |  |  |  |  |  |  |  |  |  |  |
| Vehicles | GAVI | 103,383 | 135,544 | 152,604 | 181,524 |  |  |  |  |  |  |
| Cold chain equipment | GAVI, UNICEF | 596,766 | 696,759 | 722,882 | 749,242 |  |  |  |  |  |  |
| Other capital equipment | MOPH | 0 | 19,584 | 19,584 | 19,584 |  |  |  |  |  |  |
| Campaigns |  |  |  |  |  |  |  |  |  |  |  |
| Polio NIDs | UNICEF, WHO | 14,239,527 |  |  |  |  |  |  |  |  |  |
| Measles SIAs | UNICEF, WHO, GAVI | 2,173,320 |  |  | 5,145,631 |  |  |  |  |  |  |
| TT SIAs | UNICEF, WHO | 2,804,065 |  |  |  |  |  |  |  |  |  |
| GRAND TOTAL |  | 42,228,658 | 61,960,270 | 108,008,414 | 107,537,228 |  |  |  |  |  |  |

# New and Under-Used Vaccines (NVS)

Please summarise the cold chain capacity and readiness to accommodate new vaccines, stating how the cold chain expansion (if required) will be financed, and when it will be in place. Please indicate the additional cost, if capacity is not available and the source of funding to close the gap.

The NIP had added 10 new walk-in cold rooms to the national and regional cold stores to accommodate new (Pentavalent) vaccines in 2009. During the previous cMYP, the programme started the rehabilitation of the cold chain in the provinces resulting in an improvement of cold chain functionality. The cold chain system is well function at all levels. The central vaccine store in Kabul comprises of 6 walk-in cold rooms, 5 of which operate at +4°C , and 1 operate at –20°C giving a combined installed capacity of some 100 cubic meters. The central store provides adequate storage space for present and future needs for all infants vaccines as well as for potential booster doses. . In addition to 16 cold rooms/freezer rooms, during the past 5 years, 7new cold rooms had been installed in the regions. EPI Log Forecasting tool has been used to estimate the cold space required at various levels considering the highly likely introduction of PCV13 in 2013 and Rota virus vaccine in 2014. As the country would be switching over to 10 dose liquid vaccine of Pentavalent from mid 2011, it has lessened the need for cold chain capacity which otherwise would have been required if 1 dose liquid Penta is continued.

Please give a summary of the cMYP sections that refer to the introduction of new and under-used vaccines. Outline the key points that informed the decision-making process (data considered etc)

In line with WHO EMRO immunization goals and in anticipation of the new effective vaccines to be included into national immunization program, Afghanistan has started lab-base surveillance of Rotavirus, Pneumcoccal pneumonia and Meningitis in late 2007 to estimate the burden of diseases under the surveillance. The data available since 2008 shows >50% as proportion of rota virus cases out of the total reported gastroentritis cases. The data generated from pneumococcal pneumonia and Meningitis surveillance are under analysis. Other than the data from the surveilience net works , currently there is a scaricity of reliable Afghanistan data related to disease caused by Pneumococcus and rotavirus. However WHO recomends in its position papers to introduce these vaccines in the countrires at the earliest. Consequently NITAG has recommended to introduce PCV13 in 2013 and Rota virus vaccine in 2014. Afghanistan has planned to apply for GAVI support for introducing PCV13 into NEPI in 2013 and Rotavirus vaccine in 2014.

# Capacity and cost (for positive storage)

|  |  | Formula | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2013 | 2014 | 2015 |  |  |  |  |  |
| A | Annual positive volume requirement, including new vaccine (litres or m3) Litres | Sum-product of total vaccine doses multiplied by unit packed volume of the vaccine | 134,463 | 191,559 | 194,360 |  |  |  |  |  |
| B | Existing net positive cold chain capacity (litres or m3) Litres | # | 37,411 | 51,175 | 54,486 |  |  |  |  |  |
| C | Estimated minimum number of shipments per year required for the actual cold chain capacity | A / B | 4 | 4 | 4 |  |  |  |  |  |
| D | Number of consignments / shipments per year | Based on national vaccine shipment plan | 5 | 8 | 8 |  |  |  |  |  |
| E | Gap (if any) | ((A / D) - B) | -10,518 | -27,230 | -30,191 |  |  |  |  |  |
| F | Estimated additional cost of cold chain | US$ | 481,720 | 55,016 | 11,960 |  |  |  |  |  |

Please briefly describe how your country plans to move towards attaining financial sustainability for the new vaccines you intend to introduce, how the country will meet the co-financing payments, and any other issues regarding financial sustainability you have considered (refer to the cMYP)

The resource requiremet as % of Government health expenditure on routine immunization will increase from 8% in 2009 to 20% in 2015 . Though this appears to be a significant increase but considering the long term investment in health , GOA willl ultimately achieve the benefits and will facilate for achieving of MDG4 goals through investment in immunization. The GOA desires to achieve financial sustainability for EPI at the earliest. It plans to co-finance the new vaccine through available national resources and improve the level of co-financing and options for financial sustainability by adapting the following strategies based on the country context: 1. Mobilize government resources for NIP: - NIP requirement (co-financing for new vaccine) has included in National Development Budget. - NIP is one of the important components of BPHS for government financial commitment. - Regular update of NIP five year plan and budgeting as part of health sector and with the active participation of partners. 2. Mobilize donor funding for immunization: - Advocate with donors to specify required funding for EPI from support provided for BPHS - Identify new donors for NIP through CGHN and other forums 3. Mobilize resources from private sector - Assisting in developing related policy and guidelines - Identify potential private providers especially in hard to reach areas - Promote financial contribution of private sector in provision of support to different immunization initiatives such as mass campaigns 4. Ensure reliability of resources: - Build financial management capacity at all levels to ensure timely report and improve planning. - Incorporate the NIP requirement in MoPH annual budget. - Review/ update NIP requirement regularly 5. Promote integration and maximize efficiency of immunization

# Assessment of burden of relevant diseases (if available)

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Disease | Title of the assessment | Date | Results |  |
| --- | --- | --- | --- | --- |
| Hib & Pneumococcal Meningitis | Meningitis Project in 6 Hospitals | January 2008 | Though the data (6 cases of pneumococcal pneumonia) tested/reported from all hospitals are not sufficient for decision-making, but based on clinical, epdemiological and experiences the NITAG has recommended introduction of pneumococcal vaccine in NIP. |  |

If new or under-used vaccines have already been introduced in your country, please give details of the lessons learned from storage capacity, protection from accidental freezing, staff training, cold chain, logistics, drop-out rate, wastage rate etc., and suggest action points to address them

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Lessons Learned | Action Points |  |
| --- | --- | --- |
| 1. Pre-introduction assessment of cold chain storage capacity | - Assessment was carried out and the plan for increasing capacity has been prepared. - The process of procurement of additional cold chain equipment and installation completed timely before the introduction Hib vaccine |  |
| 2. Pre-introduction assessment and preparation of training materials | - Assessment of the vaccinators’ knowledge on vaccine management - Preparation of training materials on vaccine management and injection safety - Preparatio of information about the disease, new vaccine and new immunization schedule |  |
| 3. Early starting of social mobilization activities for introduction of DPT-HepB-Hib vaccine | Preparation, printing, and distribution of social mobilization materials - Advocacy meetings - Mass media messages - Press release about the disease and the availability of vaccine |  |

Please list the vaccines to be introduced with support from the GAVI Alliance (and presentation)

PCV13 , liquid , single dose vial

# 6.3.1. Requested vaccine ( Pneumococcal (PCV13), 1 doses/vial, Liquid )

As reported in the cMYP, the country plans to introduce Pneumococcal (PCV13), 1 doses/vial, Liquid vaccine.

# 6.3.2. Co-financing information

If you would like to co-finance higher amount than minimum, please overwrite information in the “Your co-financing” row.

Note: Selection of this field has direct impact on automatic calculations of support you are requesting and should not be left empty.

| Country group | Low |
| --- | --- |

|  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2013 | 2014 | 2015 |  |  |  |  |  |
| Minimum co-financing | 0.20 | 0.20 | 0.20 |  |  |  |  |  |
| Your co-financing (please change if higher) | 0.20 | 0.20 | 0.20 |  |  |  |  |  |

# 6.3.3. Wastage factor

Please indicate wastage rate:

Countries are expected to plan for a maximal wastage rate of:

- 50% - for a lyophilised vaccine in 10 or 20-dose vial,

- 25% - for a liquid vaccine in 10 or 20-dose vial or a lyophilised vaccine in 5-dose vial,

- 10% - for a lyophilised/liquid vaccine in 2-dose vial, and

- 5% - for a liquid vaccine in 1-dose vial

Note: Selection of this field has direct impact on automatic calculations of support you are requesting and should not be left empty.

|  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2013 | 2014 | 2015 |  |  |  |  |  |
| Vaccine wastage rate in % | 5% | 5% | 5% |  |  |  |  |  |
| Equivalent wastage factor | 1.05 | 1.05 | 1.05 |  |  |  |  |  |

# 6.3.4. Specifications of vaccinations with new vaccine

|  | Data from |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2013 | 2014 | 2015 |  |  |  |  |  |
| Number of children to be vaccinated with the first dose | Table 1 | # | 1,263,861 | 1,294,194 | 1,325,255 |  |  |  |  |  |
| Number of children to be vaccinated with the third dose[1] | Table 1 | # | 1,147,792 | 1,188,546 | 1,217,072 |  |  |  |  |  |
| Immunisation coverage with the third dose | Table 1 | # | 89.00% | 90.00% | 90.00% |  |  |  |  |  |
| Estimated vaccine wastage factor | Table 6.(n).3[3] | # | 1.05 | 1.05 | 1.05 |  |  |  |  |  |
| Country co-financing per dose[2] | Table 6.(n).2[3] | $ | 0.20 | 0.20 | 0.20 |  |  |  |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Total price per-dose includes vaccine cost, plus freight, supplies, insurance, visa costs etc.

[3] Where (n) depends on the vaccine

# 6.3.5. Portion of supply to be procured by the country (and cost estimate, US$)

|  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2013 | 2014 | 2015 |  |  |  |  |  |
| Number of vaccine doses | # | 265,800 | 219,000 | 224,300 |  |  |  |  |  |
| Number of AD syringes | # | 283,800 | 231,600 | 237,200 |  |  |  |  |  |
| Number of re-constitution syringes | # |  |  |  |  |  |  |  |  |
| Number of safety boxes | # | 3,150 | 2,575 | 2,650 |  |  |  |  |  |
| Total value to be co-financed by country | $ | 995,500 | 820,500 | 840,000 |  |  |  |  |  |

# 6.3.6. Portion of supply to be procured by the GAVI Alliance (and cost estimate, US$)

|  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2013 | 2014 | 2015 |  |  |  |  |  |
| Number of vaccine doses | # | 4,710,800 | 3,881,700 | 3,974,800 |  |  |  |  |  |
| Number of AD syringes | # | 5,029,800 | 4,104,700 | 4,203,200 |  |  |  |  |  |
| Number of re-constitution syringes | # |  |  |  |  |  |  |  |  |
| Number of safety boxes | # | 55,850 | 45,575 | 46,675 |  |  |  |  |  |
| Total value to be co-financed by GAVI | $ | 17,644,500 | 14,536,500 | 14,885,500 |  |  |  |  |  |

# 6.3.7. New and Under-Used Vaccine Introduction Grant

Please indicate in the tables below how the one-time Introduction Grant[1] will be used to support the costs of vaccine introduction and critical pre-introduction activities (refer to the cMYP).

Calculation of lump-sum for the Pneumococcal (PCV13), 1 doses/vial, Liquid

If the total is lower than US$100,000, it is automatically rounded up to US$100,000

| Year of New Vaccine Introduction | Births (from Table 1) | Share per Birth in US$ | Total in US$ |
| --- | --- | --- | --- |
| 2013 | 1,480,661 | 0.30 | 444,500 |

[1] The Grant will be based on a maximum award of $0.30 per infant in the birth cohort with a minimum starting grant award of $100,000

Cost (and finance) to introduce the Pneumococcal (PCV13), 1 doses/vial, Liquid (US$)

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Cost Category | Full needs for new vaccine introduction in US$ | Funded with new vaccine introduction grant in US$ |  |
| --- | --- | --- | --- |
| Training | 182,585 | 182,585 |  |
| Social Mobilization, IEC and Advocacy | 95,782 | 95,782 |  |
| Cold Chain Equipment & Maintenance | 0 | 0 |  |
| Vehicles and Transportation | 62,134 | 62,134 |  |
| Programme Management | 56,348 | 56,348 |  |
| Surveillance and Monitoring | 97,654 | 97,654 |  |
| Human Resources | 34,260 | 34,260 |  |
| Waste Management | 43,296 | 43,296 |  |
| Technical assistance | 25,000 | 25,000 |  |
| Totals | 597,059 | 597,059 |  |

# Procurement and Management of New and Under-Used Vaccines

Note: The PCV vaccine must be procured through UNICEF

- Please show how the support will operate and be managed including procurement of vaccines (GAVI expects that most countries will procure vaccine and injection supplies through UNICEF)

The vaccine PCV13 would be provided by UNICEF to the country on behalf of GAVI.

- If an alternative mechanism for procurement and delivery of supply (financed by the country or the GAVI Alliance) is requested, please document

- Other vaccines or immunisation commodities procured by the country and descriptions of the mechanism used.

- The functions of the National Regulatory Authority (as evaluated by WHO) to show they comply with WHO requirements for procurement of vaccines and supply of assured quality.

NA

- Please describe the introduction of the vaccines (refer to cMYP)

The new vaccine pneumococcal will be introduced into all the country at once starting on January 1st, 2013. The preparatory steps taking place before the introduction of the new vaccine include: - Pre-introduction assessment for evaluation of cold chain capacity - Preparation, printing, and distribution of social mobilization materials and implementation of social mobilization activities - Preparation, printing and distribution of recording and reporting materials - Preparation and printing of the training materials - TOT for trainers - Training of service providers on new vaccine - Updating of immunization guideline and inclusion of new vaccine - Updating of checklist for monitoring and supervision - Strengthening of AEFI surveillance through refresher training course Post introduction steps will include: - Post-introduction monitoring in addition to regular routine EPI monitoring. - Quarterly review meetings and an evaluation in 2010

- Please indicate how funds should be transferred by the GAVI Alliance (if applicable)

The GAVI fund support for introduction of new vaccine should be channelled into the country through the existing system and banking account of the ISS fund. Note: the details of banking form were submitted to GAVI for ISS support.

- Please indicate how the co-financing amounts will be paid (and who is responsible for this)

The co-financing amount i.e the country share will be paid to local UNICEF office on yearly basis by the Government of Afghanistan. The amount will be paid each year latest by end January.

- Please outline how coverage of the new vaccine will be monitored and reported (refer to cMYP)

The coverage of new vaccine (PCV13) would be monitored and reported as part of the routine EPI. However ICC in its monthly/bimonthly meeting would be closely monitoring the district , provincial and national coverage of PCV13.

# Vaccine Management (EVSM/EVM/VMA)

When was the last Effective Vaccine Store Management (EVSM) conducted? September   - 2007

When was the last Effective Vaccine Management (EVM) or Vaccine Management Assessment (VMA) conducted?   -

- If your country conducted either EVSM, EVM, or VMA in the past three years, please attach relevant reports. (Document N°)

- A VMA report must be attached from those countries which have introduced a New and Underused Vaccine with GAVI support before 2008.

- Please note that EVSM and VMA tools have been replaced by an integrated Effective Vaccine Management (EVM) tool. The information on EVM tool can be found at http://www.who.int/immunization_delivery/systems_policy/logistics/en/index6.html

- For countries which conducted EVSM, VMA or EVM in the past, please report on activities carried out as part of either action plan or improvement plan prepared after the EVSM/VMA/EVM.

A data-base was developed and used up to the introduction of VSSM in 2010. The VSSM is in use at national, regional and provincial levels The new version of EPI log-forecasting is used at national level The vaccine forecasting is based on population figures given by UNIDATA. UNICEF provides vaccine product information at least three days before the arrival of vaccines and the VARs are usually sent to UNICEF within 24 hours. Additional cold rooms are installed at national and regional levels and ILRs are installed at provincial levels to accommodate all routine vaccines including OPV for NIDs. A multi channel temperature recorder is provided by UNICEF. The AC/heaters are installed to keep the vaccine packing area within the required range. The audible temperature alarms are installed. The National cold room is connected with regular city power supply with generator back-up. All the recommendations made by EMRO and WHO HQ were met and the Afghanistan National Cold Store was internationally certified.

- When is the next Effective Vaccine Management (EVM) Assessment planned? July   - 2011

- Under new guidelines, it will be mandatory for the countries to conduct an EVM prior to an application for introduction of new vaccine.

# Additional Comments and Recommendations

Comments and Recommendations from the National Coordinating Body (ICC/HSCC)

EPI Afghanistan will be shifting from single dose to 10 dose vial of Pentavalent vaccine from 1 July 2011. This change was accepted by EPI Afghanistan with the understanding that total Co- financing share of country would not be increased because of this shift. This was reinforced by communication from GAVI ( e-mail of Dr Mercy Ahun dated 19 January 2011) , clearly stating that the cost saving in co-financing would be approximately 12%. We understand that with 10 dose vials the wastage rate increases compared to single dose vials and consequently more doses are required. We request this difference to be accommodated by GAVI as overall GAVI would be making considerable savings on the value of pentavalent vaccine to be supplied to Afghanistan . We’ll highly appreciate if you kindly confirm to us that the yearly country co financing amount would not exceed the amount if single dose Pentavalent vaccine was supplied to the country.

# Annexes

# Annex 1

# Annex 1.1 – Pneumococcal (PCV13), 1 doses/vial, Liquid

Table 1.1 A - Rounded up portion of supply that is procured by the country and estimate of related cost in US$

| Required supply item |  | 2013 | 2014 | 2015 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of vaccine doses | # | 265,800 | 219,000 | 224,300 |  |  |  |  |  |
| Number of AD syringes | # | 283,800 | 231,600 | 237,200 |  |  |  |  |  |
| Number of re-constitution syringes | # |  |  |  |  |  |  |  |  |
| Number of safety boxes | # | 3,150 | 2,575 | 2,650 |  |  |  |  |  |
| Total value to be co-financed by the country | $ | 995,500 | 820,500 | 840,000 |  |  |  |  |  |

Table 1.1  B - Rounded up portion of supply that is procured by GAVI and estimate of related cost in US$.

| Required supply item |  | 2013 | 2014 | 2015 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of vaccine doses | # | 4,710,800 | 3,881,700 | 3,974,800 |  |  |  |  |  |
| Number of AD syringes | # | 5,029,800 | 4,104,700 | 4,203,200 |  |  |  |  |  |
| Number of re-constitution syringes | # |  |  |  |  |  |  |  |  |
| Number of safety boxes | # | 55,850 | 45,575 | 46,675 |  |  |  |  |  |
| Total value to be co-financed by the country | $ | 17,644,500 | 14,536,500 | 14,885,500 |  |  |  |  |  |

Table 1.1  C - Summary table for Pneumococcal (PCV13), 1 doses/vial, Liquid

|  | Data from |  | 2013 | 2014 | 2015 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of Surviving infants | Table 1 | # | 1,289,655 | 1,320,607 | 1,352,302 |  |  |  |  |  |
| Number of children to be vaccinated with the third dose[1] | Table 1 | # | 1,147,792 | 1,188,546 | 1,217,072 |  |  |  |  |  |
| Immunisation coverage with the last dose | Table 1 | # | 89.00% | 90.00% | 90.00% |  |  |  |  |  |
| Number of children to be vaccinated with the first dose | Table 1 | # | 1,263,861 | 1,294,194 | 1,325,255 |  |  |  |  |  |
| Number of doses per child |  | # | 3 | 3 | 3 |  |  |  |  |  |
| Estimated vaccine wastage factor | Table 6.(n).3[2] | # | 1.05 | 1.05 | 1.05 |  |  |  |  |  |
| Number of doses per vial |  | # | 1 | 1 | 1 |  |  |  |  |  |
| AD syringes required |  | # | Yes | Yes | Yes |  |  |  |  |  |
| Reconstitution syringes required |  | # | No | No | No |  |  |  |  |  |
| Safety boxes required |  | # | Yes | Yes | Yes |  |  |  |  |  |
| Vaccine price per dose |  | $ | 3.500 | 3.500 | 3.500 |  |  |  |  |  |
| Country co-financing per dose | Table 6.(n).2[2] | $ | 0.20 | 0.20 | 0.20 |  |  |  |  |  |
| AD syringe price per unit |  | $ | 0.053 | 0.053 | 0.053 |  |  |  |  |  |
| Reconstitution syringe price per unit |  | $ |  |  |  |  |  |  |  |  |
| Safety box price per unit |  | $ | 0.640 | 0.640 | 0.640 |  |  |  |  |  |
| Freight cost as % of vaccines value |  | % | 5.00 | 5.00 | 5.00 |  |  |  |  |  |
| Freight cost as % of devices value |  | % | 10.00 | 10.00 | 10.00 |  |  |  |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Where (n) depends on the vaccine

# Table 1.1 D - Estimated number of doses for Pneumococcal (PCV13), 1 doses/vial, Liquid associated injection safety material and related co-financing budget (page 1)

|  |  | Formula | 2013 |  |  | 2014 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Total | Government | GAVI | Total | Government | GAVI |
| A | Country Co-finance |  | 5.34% |  |  | 5.34% |  |  |
| B | Number of children to be vaccinated with the first dose[1] | Table 1 (baseline & annual targets) | 1,263,861 | 67,486 | 1,196,375 | 1,294,194 | 69,118 | 1,225,076 |
| C | Number of doses per child | Vaccine parameter | 3 | 3 | 3 | 3 | 3 | 3 |
| D | Number of doses needed | B * C | 3,791,583 | 202,456 | 3,589,127 | 3,882,582 | 207,353 | 3,675,229 |
| E | Estimated vaccine wastage factor | Table 6.(n).3. in NVS section[2] | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 |
| F | Number of doses needed including wastage | D * E | 3,981,163 | 212,579 | 3,768,584 | 4,076,712 | 217,720 | 3,858,992 |
| G | Vaccines buffer stock | (F - F of previous year) * 0.25 | 995,291 | 53,145 | 942,146 | 23,888 | 1,276 | 22,612 |
| I | Total vaccine doses needed | F + G | 4,976,454 | 265,724 | 4,710,730 | 4,100,600 | 218,996 | 3,881,604 |
| J | Number of doses per vial | Vaccine parameter | 1 | 1 | 1 | 1 | 1 | 1 |
| K | Number of AD syringes (+ 10% wastage) needed | (D + G) * 1.11 | 5,313,431 | 283,717 | 5,029,714 | 4,336,182 | 231,578 | 4,104,604 |
| L | Reconstitution syringes (+ 10% wastage) needed | I / J * 1.11 |  |  |  |  |  |  |
| M | Total of safety boxes (+ 10% of extra need) needed | (K + L) / 100 x 1.11 | 58,980 | 3,150 | 55,830 | 48,132 | 2,571 | 45,561 |
| N | Cost of vaccines needed | I * vaccine price per dose | 17,417,589 | 930,032 | 16,487,557 | 14,352,100 | 766,486 | 13,585,614 |
| O | Cost of AD syringes needed | K * AD syringe price per unit | 281,612 | 15,037 | 266,575 | 229,818 | 12,274 | 217,544 |
| P | Cost of reconstitution syringes needed | L * reconstitution price per unit |  |  |  |  |  |  |
| Q | Cost of safety boxes needed | M * safety box price per unit | 37,748 | 2,016 | 35,732 | 30,805 | 1,646 | 29,159 |
| R | Freight cost for vaccines needed | N * freight cost as % of vaccines value | 870,880 | 46,502 | 824,378 | 717,605 | 38,325 | 679,280 |
| S | Freight cost for devices needed | (O + P + Q) * freight cost as % of devices value | 31,936 | 1,706 | 30,230 | 26,063 | 1,392 | 24,671 |
| T | Total fund needed | (N + O + P + Q + R + S) | 18,639,765 | 995,291 | 17,644,474 | 15,356,391 | 820,120 | 14,536,271 |
| U | Total country co-financing | I * country co-financing per dose | 995,291 |  |  | 820,120 |  |  |
| V | Country co-financing % of GAVI supported proportion | U / T | 5.34% |  |  | 5.34% |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Where (n) depends on the vaccine

# Table 1.1 D - Estimated number of doses for Pneumococcal (PCV13), 1 doses/vial, Liquid associated injection safety material and related co-financing budget (page 2)

|  |  | Formula | 2015 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Total | Government | GAVI | Total | Government | GAVI |
| A | Country Co-finance |  | 5.34% |  |  |  |  |  |
| B | Number of children to be vaccinated with the first dose[1] | Table 1 (baseline & annual targets) | 1,325,255 | 70,777 | 1,254,478 |  |  |  |
| C | Number of doses per child | Vaccine parameter (schedule) | 3 | 3 | 3 | 3 | 3 | 3 |
| D | Number of doses needed | B * C | 3,975,765 | 212,329 | 3,763,436 |  |  |  |
| E | Estimated vaccine wastage factor | Table 6.(n).3. in NVS section[2] | 1.05 | 1.05 | 1.05 |  |  |  |
| F | Number of doses needed including wastage | D * E | 4,174,554 | 222,946 | 3,951,608 |  |  |  |
| G | Vaccines buffer stock | (F - F of previous year) * 0.25 | 24,461 | 1,307 | 23,154 |  |  |  |
| I | Total vaccine doses needed | F + G | 4,199,015 | 224,252 | 3,974,763 |  |  |  |
| J | Number of doses per vial | Vaccine parameter | 1 | 1 | 1 | 1 | 1 | 1 |
| K | Number of AD syringes (+ 10% wastage) needed | (D + G) * 1.11 | 4,440,251 | 237,136 | 4,203,115 |  |  |  |
| L | Reconstitution syringes (+ 10% wastage) needed | I / J * 1.11 |  |  |  |  |  |  |
| M | Total of safety boxes (+ 10% of extra need) needed | (K + L) / 100 x 1.11 | 49,287 | 2,633 | 46,654 |  |  |  |
| N | Cost of vaccines needed | I * vaccine price per dose | 14,696,553 | 784,881 | 13,911,672 |  |  |  |
| O | Cost of AD syringes needed | K * AD syringe price per unit | 235,334 | 12,569 | 222,765 |  |  |  |
| P | Cost of reconstitution syringes needed | L * reconstitution price per unit |  |  |  |  |  |  |
| Q | Cost of safety boxes needed | M * safety box price per unit | 31,544 | 1,685 | 29,859 |  |  |  |
| R | Freight cost for vaccines needed | N * freight cost as % of vaccines value | 734,828 | 39,245 | 695,583 |  |  |  |
| S | Freight cost for devices needed | (O + P + Q) * freight cost as % of devices value | 26,688 | 1,426 | 25,262 |  |  |  |
| T | Total fund needed | (N + O + P + Q + R + S) | 15,724,947 | 839,803 | 14,885,144 |  |  |  |
| U | Total country co-financing | I * country co-financing per dose | 839,803 |  |  |  |  |  |
| V | Country co-financing % of GAVI supported proportion | U / T | 5.34% |  |  |  |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Where (n) depends on the vaccine

# Annex 2

Estimated prices of supply and related freight cost: 2011 from UNICEF Supply Division; 2012 onwards: GAVI Secretariat

Table A - Commodities Cost

| Vaccine | Presentation | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| AD syringe | 0 | 0.053 | 0.053 | 0.053 | 0.053 | 0.053 | 0.053 | 0.053 |
| DTP-HepB | 2 | 1.600 |  |  |  |  |  |  |
| DTP-HepB | 10 | 0.620 | 0.620 | 0.620 | 0.620 | 0.620 | 0.620 | 0.620 |
| DTP-HepB-Hib | WAP | 2.580 | 2.470 | 2.320 | 2.030 | 1.850 | 1.850 | 1.850 |
| DTP-HepB-Hib | WAP | 2.580 | 2.470 | 2.320 | 2.030 | 1.850 | 1.850 | 1.850 |
| DTP-HepB-Hib | WAP | 2.580 | 2.470 | 2.320 | 2.030 | 1.850 | 1.850 | 1.850 |
| DTP-Hib | 10 | 3.400 | 3.400 | 3.400 | 3.400 | 3.400 | 3.200 | 3.200 |
| HepB monoval | 1 |  |  |  |  |  |  |  |
| HepB monoval | 2 |  |  |  |  |  |  |  |
| Hib monoval | 1 | 3.400 |  |  |  |  |  |  |
| Measles | 10 | 0.240 | 0.240 | 0.240 | 0.240 | 0.240 | 0.240 | 0.240 |
| Pneumococcal(PCV10) | 2 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 |
| Pneumococcal(PCV13) | 1 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 |
| Reconstit syringe for Pentaval (2ml) | 0 | 0.032 | 0.032 | 0.032 | 0.032 | 0.032 | 0.032 | 0.032 |
| Reconstit syringe for YF | 0 | 0.038 | 0.038 | 0.038 | 0.038 | 0.038 | 0.038 | 0.038 |
| Rotavirus 2-dose schedule | 1 | 7.500 | 6.000 | 5.000 | 4.000 | 3.600 | 3.600 | 3.600 |
| Rotavirus 3-dose schedule | 1 | 5.500 | 4.000 | 3.333 | 2.667 | 2.400 | 2.400 | 2.400 |
| Safety box | 0 | 0.640 | 0.640 | 0.640 | 0.640 | 0.640 | 0.640 | 0.640 |
| Yellow Fever | WAP | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 |
| Yellow Fever | WAP | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 |

Note: WAP - weighted average price (to be used for any presentation: For DTP-HepB-Hib, it applies to 1 dose liquid, 2 dose lyophilised and 10 dose liquid. For Yellow Fever, it applies to 5 dose lyophilised and 10 dose lyophilised)

Table B - Commodities Freight Cost

| Vaccines | Group | No Threshold | 200’000 $ |  | 250’000 $ |  | 2’000’000 $ |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | <= | > | <= | > | <= | > |
| Yellow Fever | Yellow Fever |  | 20% |  |  |  | 10% | 5% |
| DTP+HepB | HepB and or Hib | 2% |  |  |  |  |  |  |
| DTP-HepB-Hib | HepB and or Hib |  |  |  | 15% | 3,50% |  |  |
| Pneumococcal vaccine (PCV10) | Pneumococcal | 5% |  |  |  |  |  |  |
| Pneumococcal vaccine (PCV13) | Pneumococcal | 5% |  |  |  |  |  |  |
| Rotavirus | Rotavirus | 5% |  |  |  |  |  |  |
| Measles | Measles | 10% |  |  |  |  |  |  |

Table C - Low - Minimum country's co-payment per dose of co-financed vaccine.

| vaccine | 2013 | 2014 | 2015 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Pneumococcal(PCV13), 1 doses/vial, Liquid | 0.20 | 0.20 | 0.20 |  |  |  |  |

Table D - Wastage rates and factors

Countries are expected to plan for a maximal wastage rate of:

- 50% - for a lyophilised vaccine in 10 or 20-dose vial,

- 25% - for a liquid vaccine in 10 or 20-dose vial or a lyophilised vaccine in 5-dose vial,

- 10% - for a lyophilised/liquid vaccine in 2-dose vial, and

- 5% - for a liquid vaccine in 1-dose vial

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2 | 2.22 | 2.5 |

WHO International shipping guidelines: maximum packed volumes of vaccines

Table E - Vaccine maximum packed volumes

| Vaccine product | Designation | Vaccine formulation | Admin route | No. Of doses in the schedule | Presentation (doses/vial, prefilled) | Packed volume vaccine (cm3/dose) | Packed volume diluents (cm3/dose) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| BCG | BCG | lyophilized | ID | 1 | 20 | 1.2 | 0.7 |
| Diphtheria-Tetanus-Pertussis | DTP | liquid | IM | 3 | 20 | 2.5 |  |
| Diphtheria-Tetanus-Pertussis | DTP | liquid | IM | 3 | 10 | 3.0 |  |
| Diphtheria-Tetanus | DT | liquid | IM | 3 | 10 | 3.0 |  |
| Tetanus-Diphtheria | Td | liquid | IM | 2 | 10 | 3.0 |  |
| Tetanus Toxoid | TT | liquid | IM | 2 | 10 | 3.0 |  |
| Tetanus Toxoid | TT | liquid | IM | 2 | 20 | 2.5 |  |
| Tetanus Toxoid UniJect | TT | liquid | IM | 2 | Uniject | 12.0 |  |
| Measles | Measles | lyophilized | SC | 1 | 1 | 26.1 | 20.0 |
| Measles | Measles | lyophilized | SC | 1 | 2 | 13.1 | 13.1 |
| Measles | Measles | lyophilized | SC | 1 | 5 | 5.2 | 7.0 |
| Measles | Measles | lyophilized | SC | 1 | 10 | 3.5 | 4.0 |
| Measles-Rubella freeze dried | MR | lyophilized | SC | 1 | 1 | 26.1 | 26.1 |
| Measles-Rubella freeze dried | MR | lyophilized | SC | 1 | 2 | 13.1 | 13.1 |
| Measles-Rubella freeze dried | MR | lyophilized | SC | 1 | 5 | 5.2 | 7.0 |
| Measles-Rubella freeze dried | MR | lyophilized | SC | 1 | 10 | 2.5 | 4.0 |
| Measles-Mumps-Rubella freeze dried | MMR | lyophilized | SC | 1 | 1 | 26.1 | 26.1 |
| Measles-Mumps-Rubella freeze dried | MMR | lyophilized | SC | 1 | 2 | 13.1 | 13.1 |
| Measles-Mumps-Rubella freeze dried | MMR | lyophilized | SC | 1 | 5 | 5.2 | 7.0 |
| Measles-Mumps-Rubella freeze dried | MMR | lyophilized | SC | 1 | 10 | 3.0 | 4.0 |
| Polio | OPV | liquid | Oral | 4 | 10 | 2.0 |  |
| Polio | OPV | liquid | Oral | 4 | 20 | 1.0 |  |
| Yellow fever | YF | lyophilized | SC | 1 | 5 | 6.5 | 7.0 |
| Yellow fever | YF | lyophilized | SC | 1 | 10 | 2.5 | 3.0 |
| Yellow fever | YF | lyophilized | SC | 1 | 20 | 1.5 | 2.0 |
| Yellow fever | YF | lyophilized | SC | 1 | 50 | 0.7 | 1.0 |
| DTP-HepB combined | DTP-HepB | liquid | IM | 3 | 1 | 9.7 |  |
| DTP-HepB combined | DTP-HepB | liquid | IM | 3 | 2 | 6.0 |  |
| DTP-HepB combined | DTP-HepB | liquid | IM | 3 | 10 | 3.0 |  |
| Hepatitis B | HepB | liquid | IM | 3 | 1 | 18.0 |  |
| Hepatitis B | HepB | liquid | IM | 3 | 2 | 13.0 |  |
| Hepatitis B | HepB | liquid | IM | 3 | 6 | 4.5 |  |
| Hepatitis B | HepB | liquid | IM | 3 | 10 | 4.0 |  |
| Hepatitis B UniJect | HepB | liquid | IM | 3 | Uniject | 12.0 |  |
| Hib liquid | Hib_liq | liquid | IM | 3 | 1 | 15.0 |  |
| Hib liquid | Hib_liq | liquid | IM | 3 | 10 | 2.5 |  |
| Hib freeze-dried | Hib_lyo | lyophilized | IM | 3 | 1 | 13.0 | 35.0 |
| Hib freeze-dried | Hib_lyo | lyophilized | IM | 3 | 2 | 6.0 |  |
| Hib freeze-dried | Hib_lyo | lyophilized | IM | 3 | 10 | 2.5 | 3.0 |
| DTP liquid + Hib freeze-dried | DTP+Hib | liquid+lyop. | IM | 3 | 1 | 45.0 |  |
| DTP-Hib combined liquid | DTP+Hib | liquid+lyop. | IM | 3 | 10 | 12.0 |  |
| DTP-Hib combined liquid | DTP-Hib | liquid | IM | 3 | 1 | 32.3 |  |
| DTP-HepB liquid + Hib freeze-dried | DTP-Hib | liquid | IM | 3 | 10 | 2.5 |  |
| DTP-HepB liquid + Hib freeze-dried | DTP-HepB+Hib | liquid+lyop. | IM | 3 | 1 | 22.0 |  |
| DTP-HepB-Hib liquid | DTP-HepB+Hib | liquid+lyop. | IM | 3 | 2 | 11.0 |  |
| DTP-HepB-Hib liquid | DTP-HepB-Hib | liquid | IM | 3 | 10 | 4.4 |  |
| DTP-HepB-Hib liquid | DTP-HepB-Hib | liquid | IM | 3 | 2 | 13.1 |  |
| DTP-HepB-Hib liquid | DTP-HepB-Hib | liquid | IM | 3 | 1 | 19.2 |  |
| Meningitis A/C | MV_A/C | lyophilized | SC | 1 | 10 | 2.5 | 4.0 |
| Meningitis A/C | MV_A/C | lyophilized | SC | 1 | 50 | 1.5 | 3.0 |
| Meningococcal A/C/W/ | MV_A/C/W | lyophilized | SC | 1 | 50 | 1.5 | 3.0 |
| Meningococcal A/C/W/Y | MV_A/C/W/Y | lyophilized | SC | 1 | 10 | 2.5 | 4.0 |
| Meningitis W135 | MV_W135 | lyophilized | SC | 1 | 10 | 2.5 | 4.0 |
| Meningitis A conjugate | Men_A | lyophilized | SC | 2 | 10 | 2.6 | 4.0 |
| Japanese Encephalitis | JE_lyo | lyophilized | SC | 3 | 10 | 15.0 |  |
| Japanese Encephalitis | JE_lyo | lyophilized | SC | 3 | 10 | 8.1 | 8.1 |
| Japanese Encephalitis | JE_lyo | lyophilized | SC | 3 | 5 | 2.5 | 2.9 |
| Japanese Encephalitis | JE_lyo | lyophilized | SC | 3 | 1 | 12.6 | 11.5 |
| Japanese Encephalitis | JE_liq | liquid | SC | 3 | 10 | 3.4 |  |
| Rota vaccine | Rota_lyo | lyophilized | Oral | 2 | 1 | 156.0 |  |
| Rota vaccine | Rota_liq | liquid | Oral | 2 | 1 | 17.1 |  |
| Rota vaccine | Rota_liq | liquid | Oral | 3 | 1 | 45.9 |  |
| Pneumo. conjugate vaccine 7-valent | PCV-7 | liquid | IM | 3 | PFS | 55.9 |  |
| Pneumo. conjugate vaccine 7-valent | PCV-7 | liquid | IM | 3 | 1 | 21.0 |  |
| Pneumo. conjugate vaccine 10-valent | PCV-10 | liquid | IM | 3 | 1 | 11.5 |  |
| Pneumo. conjugate vaccine 10-valent | PCV-10 | liquid | IM | 3 | 2 | 4.8 |  |
| Pneumo. conjugate vaccine 13-valent | PCV-13 | liquid | IM | 3 | 1 | 12.0 |  |
| Polio inactivated | IPV | liquid | IM | 3 | PFS | 107.4 |  |
| Polio inactivated | IPV | liquid | IM | 3 | 10 | 2.5 |  |
| Polio inactivated | IPV | liquid | IM | 3 | 1 | 15.7 |  |
| Human Papilomavirus vaccine | HPV | liquid | IM | 3 | 1 | 15.0 |  |
| Human Papilomavirus vaccine | HPV | liquid | IM | 3 | 2 | 5.7 |  |
| Monovalent OPV-1 | mOPV1 | liquid | Oral |  | 20 | 1.5 |  |
| Monovalent OPV-3 | mOPV3 | liquid | Oral |  | 20 | 1.5 |  |

# Attachments

# List of Supporting Documents Attached to this Proposal

| Document | Section | Document Number | Mandatory[1] |
| --- | --- | --- | --- |
| MoH Signature (or delegated authority) of Proposal |  | 2, 3, 8(No file loaded) | Yes |
| MoF Signature (or delegated authority) of Proposal |  | Missing | Yes |
| Signatures of ICC or HSCC or equivalent in Proposal |  | Missing | Yes |
| Minutes of ICC/HSCC meeting endorsing Proposal |  | 6, 7 | Yes |
| comprehensive Multi Year Plan - cMYP |  | Missing | Yes |
| cMYP Costing tool for financial analysis |  | 1 | Yes |
| Minutes of last three ICC/HSCC meetings |  | 5 | Yes |
| Improvement plan based on EVM |  | Missing | Yes |
| WHO/UNICEF Joint Reporting Form (JRF) |  | 4 |  |
| ICC/HSCC workplan for forthcoming 12 months |  |  |  |
| National policy on injection safety |  |  |  |
| Action plans for improving injection safety |  |  |  |
| Plan for NVS introduction (if not part of cMYP) |  |  |  |
| Banking details |  |  |  |

[1] Please indicate the duration of the plan / assessment / document where appropriate

# Attachments

List of all the mandatory and optional documents attached to this form

Note: Use the Upload file arrow icon to upload the document. Use the Delete item icon to delete a line. To add new lines click on the New item icon in the Action column.

| ID | File type | File name |  | New file | Actions |
| --- | --- | --- | --- | --- | --- |
|  | Description | Date and Time | Size |  |  |
| 1 | File Type: cMYP Costing tool for financial analysis * File Desc: 1 file loaded | File name: C:\Documents and Settings\abdulghafoora\Desktop\GAVI_Final\AFG cMYP_Costing_PneumoRota (19 Apr 11) F.zip Date/Time: 29.05.2011 03:06:14 Size: 832 KB |  |  |  |
| 2 | File Type: MoH Signature (or delegated authority) of Proposal * File Desc: 1 file lloaded | File name: C:\Documents and Settings\abdulghafoora\Desktop\GAVI_Final\AFG_EPI_Log_Forecasting_(16 April 2011) F.xls Date/Time: 29.05.2011 03:08:49 Size: 270 MB |  |  |  |
| 3 | File Type: MoH Signature (or delegated authority) of Proposal * File Desc: 1 file loded | File name: C:\Documents and Settings\abdulghafoora\Desktop\GAVI_Final\AfgcMYP11-15- updated Apr 2011)Final.zip Date/Time: 29.05.2011 03:09:55 Size: 133 MB |  |  |  |
| 4 | File Type: WHO/UNICEF Joint Reporting Form (JRF) File Desc: 1 file loaded | File name: C:\Documents and Settings\abdulghafoora\Desktop\AfgJRF2010.xls Date/Time: 29.05.2011 03:16:27 Size: 240 KB |  |  |  |
| 5 | File Type: Minutes of last three ICC/HSCC meetings * File Desc: 1 file loaded | File name: C:\Documents and Settings\abdulghafoora\Desktop\GAVI_Final\ICC_May_11.doc Date/Time: 29.05.2011 03:22:50 Size: 84 KB |  |  |  |
| 6 | File Type: Minutes of ICC/HSCC meeting endorsing Proposal * File Desc: 1 file loaded | File name: C:\Documents and Settings\abdulghafoora\Desktop\GAVI_Final\MinuteICCJan10_Revised.doc Date/Time: 29.05.2011 03:25:19 Size: 68 KB |  |  |  |
| 7 | File Type: Minutes of ICC/HSCC meeting endorsing Proposal * File Desc: 1 file loaded | File name: C:\Documents and Settings\abdulghafoora\Desktop\GAVI_Final\ICC Min Dec10 MASHAL.doc Date/Time: 29.05.2011 03:27:59 Size: 79 KB |  |  |  |
| 8 | File Type: MoH Signature (or delegated authority) of Proposal * File Desc: | File name: Date/Time: Size: |  |  |  |

Banking Form

| In accordance with the decision on financial support made by the GAVI Alliance, the Government of Afghanistan hereby requests that a payment be made via electronic bank transfer as detailed below: |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Name of Institution (Account Holder): |  |  |  |  |  |
| Address: |  |  |  |  |  |
| City Country: |  |  |  |  |  |
| Telephone no.: |  | Fax no.: |  |  |  |
| Currency of the bank account: |  |  |  |  |  |
| For credit to: |  |  |  |  |  |
| Bank account's title: |  |  |  |  |  |
| Bank account no.: |  |  |  |  |  |
| Bank's name: |  |  |  |  |  |

Is the bank account exclusively to be used by this program?

By who is the account audited?

Signature of Government’s authorizing official

| Name: |  | Seal |
| --- | --- | --- |
| Title: |  |  |
| Signature: |  |  |
| Date: |  |  |

| FINANCIAL INSTITUTION |  | CORRESPONDENT BANK (In the United States) |  |
| --- | --- | --- | --- |
| Bank Name: |  |  |  |
| Branch Name: |  |  |  |
| Address: |  |  |  |
| City Country: |  |  |  |
| Swift Code: |  |  |  |
| Sort Code: |  |  |  |
| ABA No.: |  |  |  |
| Telephone No.: |  |  |  |
| FAX No.: |  |  |  |

I certify that the account no is held by (Institution name) at this banking institution.

| The account is to be signed jointly by at least 0 (number of signatories) of the following authorized signatories: |  |  |
| --- | --- | --- |
| 1 |  |  |
|  | Name: |  |
|  | Title: |  |
| 2 |  |  |
|  | Name: |  |
|  | Title: |  |
| 3 |  |  |
|  | Name: |  |
|  | Title: |  |
| 4 |  |  |
|  | Name: |  |
|  | Title: |  |

Name of bank’s authorizing official

Signature:

Date:

Seal: