GAVI Alliance

Application Form for Country Proposals

For Support to New and Under-Used Vaccines (NVS)

Submitted by

The Government of

Bangladesh

Date of submission: 12.05.2011 05:09:22

Deadline for submission: 1 Jun 2011

Select Start and End Year of your Comprehensive Multi-Year Plan (cMYP)

| Start Year | 2011 | End Year | 2016 |
| --- | --- | --- | --- |

Revised in January 2011

(To be used with Guidelines of December 2010)

Please submit the Proposal using the online platform https://AppsPortal.gavialliance.org/PDExtranet.

Enquiries to: proposals@gavialliance.org or representatives of a GAVI partner agency. The documents can be shared with GAVI partners, collaborators and general public. The Proposal and attachments must be submitted in English, French, Spanish, or Russian.

Note: Please ensure that the application has been received by the GAVI Secretariat on or before the day of the deadline.

The GAVI Secretariat is unable to return submitted documents and attachments to countries. Unless otherwise specified, documents will be shared with the GAVI Alliance partners and the general public.

GAVI ALLIANCE GRANT TERMS AND CONDITIONS FUNDING USED SOLELY FOR APPROVED PROGRAMMES The applicant country (“Country”) confirms that all funding provided by the GAVI Alliance will be used and applied for the sole purpose of fulfilling the programme(s) described in the Country’s application. Any significant change from the approved programme(s) must be reviewed and approved in advance by the GAVI Alliance. All funding decisions for the application are made at the discretion of the GAVI Alliance Board and are subject to IRC processes and the availability of funds. AMENDMENT TO THE APPLICATION The Country will notify the GAVI Alliance in its Annual Progress Report if it wishes to propose any change to the programme(s) description in its application. The GAVI Alliance will document any change approved by the GAVI Alliance, and the Country’s application will be amended. RETURN OF FUNDS The Country agrees to reimburse to the GAVI Alliance all funding amounts that are not used for the programme(s) described in its application. The country’s reimbursement must be in US dollars and be provided, unless otherwise decided by the GAVI Alliance, within sixty (60) days after the Country receives the GAVI Alliance’s request for a reimbursement and be paid to the account or accounts as directed by the GAVI Alliance. SUSPENSION/ TERMINATION The GAVI Alliance may suspend all or part of its funding to the Country if it has reason to suspect that funds have been used for purpose other than for the programmes described in the Country’s application, or any GAVI Alliance-approved amendment to the application. The GAVI Alliance retains the right to terminate its support to the Country for the programmes described in its application if a misuse of GAVI Alliance funds is confirmed. ANTICORRUPTION The Country confirms that funds provided by the GAVI Alliance shall not be offered by the Country to any third person, nor will the Country seek in connection with its application any gift, payment or benefit directly or indirectly that could be construed as an illegal or corrupt practice. AUDITS AND RECORDS The Country will conduct annual financial audits, and share these with the GAVI Alliance, as requested. The GAVI Alliance reserves the right, on its own or through an agent, to perform audits or other financial management assessment to ensure the accountability of funds disbursed to the Country. The Country will maintain accurate accounting records documenting how GAVI Alliance funds are used. The Country will maintain its accounting records in accordance with its government-approved accounting standards for at least three years after the date of last disbursement of GAVI Alliance funds. If there is any claims of misuse of funds, Country will maintain such records until the audit findings are final. The Country agrees not to assert any documentary privilege against the GAVI Alliance in connection with any audit. CONFIRMATION OF LEGAL VALIDITY The Country and the signatories for the Country confirm that its application, and Annual Progress Report, are accurate and correct and form legally binding obligations on the Country, under the Country’s law, to perform the programmes described in its application, as amended, if applicable, in the APR. CONFIRMATION OF COMPLIANCE WITH THE GAVI ALLIANCE TRANSPARANCY AND ACCOUNTABILITY POLICY The Country confirms that it is familiar with the GAVI Alliance Transparency and Accountability Policy (TAP) and complies with the requirements therein. USE OF COMMERCIAL BANK ACCOUNTS The Country is responsible for undertaking the necessary due diligence on all commercial banks used to manage GAVI cash-based support. The Country confirms that it will take all responsibility for replenishing GAVI cash support lost due to bank insolvency, fraud or any other unforeseen event. ARBITRATION Any dispute between the Country and the GAVI Alliance arising out of or relating to its application that is not settled amicably within a reasonable period of time, will be submitted to arbitration at the request of either the GAVI Alliance or the Country. The arbitration will be conducted in accordance with the then-current UNCITRAL Arbitration Rules. The parties agree to be bound by the arbitration award, as the final adjudication of any such dispute. The place of arbitration will be Geneva, Switzerland. The language of the arbitration will be English. For any dispute for which the amount at issue is US$ 100,000 or less, there will be one arbitrator appointed by the GAVI Alliance. For any dispute for which the amount at issue is greater than US $100,000 there will be three arbitrators appointed as follows: The GAVI Alliance and the Country will each appoint one arbitrator, and the two arbitrators so appointed will jointly appoint a third arbitrator who shall be the chairperson. The GAVI Alliance will not be liable to the country for any claim or loss relating to the programmes described in the application, including without limitation, any financial loss, reliance claims, any harm to property, or personal injury or death. Country is solely responsible for all aspects of managing and implementing the programmes described in its application.

# Application Specification

Please specify for which type of GAVI support you would like to apply to.

Important note: To enable proper functioning of the form, please first select the cMYP years on the previous page.

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Type of Support | Vaccine | Start Year | End Year | Preferred second presentation[1] | Action |
| --- | --- | --- | --- | --- | --- |
| New Vaccines Support | Measles, 10 doses/vial, Lyophilised | 2012 | 2016 |  |  |
| New Vaccines Support | Pneumococcal (PCV10), 2 doses/vial, Liquid | 2013 | 2016 |  |  |

[1] This "Preferred second presentation" will be used in case there is no supply available for the preferred presentation of the selected vaccine ("Vaccine" column). If left blank, it will be assumed that the country will prefer waiting until the selected vaccine becomes available.

# Table of Contents

Sections

Main

Cover Page

GAVI Alliance Grants Terms and Conditions

1. Application Specification

2. Table of Contents

3. Executive Summary

4. Signatures

4.1. Signatures of the Government and National Coordinating Bodies

4.1.1. Government and the Inter-Agency Coordinating Committee for Immunisation

4.1.2. National Coordinating Body - Inter-Agency Coordinating Committee for Immunisation

4.1.3. The Inter-Agency Coordinating Committee for Immunisation

4.2. National Immunization Technical Advisory Group for Immunisation

4.2.1. The NITAG Group for Immunisation

5. Immunisation Programme Data

5.1. Basic facts

5.2. Current vaccination schedule

5.3. Trends of immunisation coverage and disease burden

5.4. Baseline and Annual Targets

Table 1: baseline figures

5.5. Summary of current and future immunisation budget

5.6. Summary of current and future financing and sources of funds

6. NVS

6.1. Capacity and cost (for positive storage)

6.2. Assessment of burden of relevant diseases (if available)

6.3.1. Requested vaccine ( Measles, 10 doses/vial, Lyophilised )

6.3.2. Co-financing information

6.3.3. Wastage factor

6.3.4. Specifications of vaccinations with new vaccine

6.3.5. Portion of supply to be procured by the country (and cost estimate, US$)

6.3.6. Portion of supply to be procured by the GAVI Alliance (and cost estimate, US$)

6.3.7. New and Under-Used Vaccine Introduction Grant

6.4.1. Requested vaccine ( Pneumococcal (PCV10), 2 doses/vial, Liquid )

6.4.2. Co-financing information

6.4.3. Wastage factor

6.4.4. Specifications of vaccinations with new vaccine

6.4.5. Portion of supply to be procured by the country (and cost estimate, US$)

6.4.6. Portion of supply to be procured by the GAVI Alliance (and cost estimate, US$)

6.4.7. New and Under-Used Vaccine Introduction Grant

7. Procurement and Management of New and Under-Used Vaccines

7.1. Vaccine management (EVSM/EVM/VMA)

8. Additional Comments and Recommendations

9. Annexes

Annex 1

Annex 1.1 - Measles, 10 doses/vial, Lyophilised

Table 1.1  A - Rounded up portion of supply that is procured by the country and estimate of related cost in US$

Table 1.1  B - Rounded up portion of supply that is procured by GAVI and estimate of related cost in US$.

Table 1.1  C - Summary table for vaccine Measles, 10 doses/vial, Lyophilised

Table 1.1  D - Estimated number of doses for vaccine Measles, 10 doses/vial, Lyophilised associated injection safety material and related co-financing budget

Annex 1.2 - Pneumococcal (PCV10), 2 doses/vial, Liquid

Table 1.2  A - Rounded up portion of supply that is procured by the country and estimate of related cost in US$

Table 1.2  B - Rounded up portion of supply that is procured by GAVI and estimate of related cost in US$.

Table 1.2  C - Summary table for vaccine Pneumococcal (PCV10), 2 doses/vial, Liquid

Table 1.2  D - Estimated number of doses for vaccine Pneumococcal (PCV10), 2 doses/vial, Liquid associated injection safety material and related co-financing budget

Annex 2

10. Attachments

10.1 Documents required for NVS support

10.2 Attachments

Banking Form

# Executive Summary

Bangladesh applies to GAVI for NVS to introduce 2 vaccines:

Measles:

Duration of support: 2012 – 2016

Total amount of funds requested: 
18,440,079 US$ for vaccines and injection supplies equivalent to 62,181,029 doses (as calculated in cMYP and not $11,580,563 for vaccines and Injection supplies if calculated by the Application Form (AF) with wastage rate 50% and 1 as “number of doses per child” equivalent to 37,686,300 doses)
1,195,000 US$ Introduction Grant (out of the total budget of $2,226,000;remaining amount will be financed by GoB and Partner agencies.)


MCV Lyophilized 10 dose vaccine is requested (the only formulation available according to the Application and cMYP Costing tool). Total doses needed are calculated using 70% wastage rate that is higher than the recommended maximum wastage rate (50%). Therefore, actual number of doses requested (62,181,029) exceeds the number of doses 37,686,300 calculated by the AF.

The high wastage rate (70%) is explained by specifics of immunization service delivery in Bangladesh: as it is indicated in the cMYP up to 98% of vaccinations is delivered via outreach services. In average 3 children are vaccinated per vaccination site per day. Therefore, when 10 dose vials is used and the WHO open vial policy is not applicable (as in case of MCV), 7 doses out of 10 are lost.


PCV

Duration of support: 2013 – 2016

Total amount of funds requested: 
170,270,500 US$ for vaccines and injection supplies equivalent to 45,478,800 doses.
1,213,000 US$ introduction grant(out of the total budget of $1,994,000; remaining amount will be financed by GoB and Partner agencies.)

PCV10 2 doses vial liquid presentation was selected considering cold chain space requirements and country’s ability to upgrade the cold chain in 2012. The second available presentation was not selected because it cannot be accommodated in 2013 considering that funds are secured only for additional 30 m3 net volume positive cold chain upgrade (enough to handle PCV10 2 dose liquid presentation requiring 28 m3 volume)



Baseline Data:

DTP3 coverage was 96% in 2009 and 95% in 2010 (reported) vs. 87% and 89% (survey) respectively.

Measles 1st dose coverage was 98% in 2009 and 94% in 2010 vs. 94% (survey) in 2009 and 2010.

Birth cohort is estimated at 3,983,990 in 2012, 4,041,758 in 2013, 4,100,364 in 2014, 4,159,819 in 2015 and 4,220,136 in 2016.

Bangladesh NIP achieved significant success in many areas of EPI in terms of reaching high coverage with traditional vaccines via routine 
immunization and control of polio and measles via supplementary immunization campaigns.

Bangladesh successfully introduced Hep B and Hib vaccines with GAVI support and reached 95-96 % coverage in recent years.
Country intends to maintain a) BCG coverage at the level of 98% (despite of the fact that only 25% of birth is attended by skilled medical personnel), b) OPV and Pentavalent coverage at the level of 95% and TT coverage of Child Bearing Age Women at the level of 80%.

However challenges still remain in terms of sustaining the desired level of protection against measles as well as decreasing further child morbidity and mortality caused by acute respiratory diseases and diarrhoea.

An updated cMYP 2011-2016 reflects NIP's priorities, objectives and strategies based on the situational analysis. 

According to the cMYP, Bangladesh intends to introduce Measles 2nd dose in 2012, PCV in 2013 and Rota ad HepB birth dose in 2014 (based on the recommendations of National committee on Immunization practice chaired by the Secretary to the Ministry of Health and Family Welfare).


Country Preparedness:

Cold chain assessment was conducted in 2010 followed by EVM assessment in April 2011. In terms of cold chain storage capacity it was revealed that positive cold chain storage capacity is adequate at district and sub-district (Upazila) levels to accommodate MCV2 and PCV vaccines.

Additional 70 cubic meters net positive cold chain storage space is needed to address the current deficit and requirements of MCV2 and PCV vaccines at the National level. With UNICEF support country is ready to a) install 40 cubic meters (net) positive cold chain equipment (4 walk-in cooler) in 2011 to accommodate Measles 2nd dose vaccines (requiring 13 cubic meters) and to cover the current space deficit for vaccines in use (27 cubic meters) at the national level and b) install additional 30 cubic meters (net) positive cold chain equipment in 2012 to accommodate PCV vaccines (requiring 28 cubic meters space at the national level).

The Improvement Plan envisages interventions to strengthen the entire logistics system. It was endorsed by ICC in April 2011. According the cMYP, detail action plan with budget will be prepared to start implementation of the Improvement Plan and meet its milestones. Next EVM Assessment is planned in the 1st half of 2013 to assess success in the implementation of the current Improvement Plan and country’s readiness for the introduction of Rota and HepB birth dose vaccines.



The nature of stakeholders’ participation in developing this proposal:

The current proposal has been developed through an intensive consultative process between the EPI authorized personnel and traditional EPI partners. It was underpinned by substantial update of strategies, key activities and financial projections that was reflected in the current version of the cMYP with all details related to the introduction of new vaccines (there is no standalone introduction plan). Technical issues were discussed and endorsed by health officials and major issues including the cMYP and application were approved by the ICC.

# Signatures

# Signatures of the Government and National Coordinating Bodies

# Government and the Inter-Agency Coordinating Committee for Immunisation

The Government of Bangladesh would like to expand the existing partnership with the GAVI Alliance for the improvement of the infants routine immunisation programme of the country, and specifically hereby requests for GAVI support for Measles 10 doses/vial Lyophilised , Pneumococcal (PCV10) 2 doses/vial Liquid introduction.

The Government of Bangladesh commits itself to developing national immunisation services on a sustainable basis in accordance with the Comprehensive Multi-Year Plan (cMYP) presented with this document. The Government requests that the GAVI Alliance and its partners contribute financial and technical assistance to support immunisation of children as outlined in this application.

Tables 6.(n).5. (where (n) depends on the vaccine) in the NVS section of this application shows the amount of support in either supply or cash that is required from the GAVI Alliance. Tables 6.(n).4. of this application shows the Government financial commitment for the procurement of this new vaccine (NVS support only).

Following the regulations of the internal budgeting and financing cycles the Government will annually release its portion of the co-financing funds in the month of August.

Please note that this application will not be reviewed or approved by the Independent Review Committee (IRC) without the signatures of both the Minister of Health & Minister of Finance or their delegated authority.

Enter the family name in capital letters.

| Minister of Health (or delegated authority) |  | Minister of Finance (or delegated authority) |  |
| --- | --- | --- | --- |
| Name | Md Humayun Kabir, Secretary, Ministry of Health and Family Welfare | Name | Kazi Shofiqul Azam, Joint Secretary, Ministry of Finance |
| Date |  | Date |  |
| Signature |  | Signature |  |

This report has been compiled by

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

Enter the family name in capital letters.

| Full name | Position | Telephone | Email | Action |
| --- | --- | --- | --- | --- |
| Dr. Md. Shamsul Ashraf Khan | Program Manager, Child Health and Limited Curative Care, DGHS, MOH&FW | +880-2-8821910-13 | shamsul.shelly@yahoo.com |  |
| Dr. Md. Tawheed Hassan | Deputy Program Manager, EPI, DGHS, MOH&FW | +880-2-8821910-13 | tawheed55@yahoo.com |  |
| Dr Serguei Diorditsa | Medical Officer, IVD, WHO, Bangladesh | +880-2-9899540 Ext. 109 | diorditsas@searo.who.int |  |
| Dr. Jucy Merina Adhikari | Immunization Specialist, Health and Nutrition Section, Unicef Bangladesh | +880-2-8852266 Ext. 7144 | jmadhikari@unicef.org |  |

# National Coordinating Body - Inter-Agency Coordinating Committee for Immunisation

We the members of the ICC, HSCC, or equivalent committee[1] met on the 08.05.2011 to review this proposal. At that meeting we endorsed this proposal on the basis of the supporting documentation which is attached.

[1] Inter-agency Coordinating Committee or Health Sector Coordinating Committee, or equivalent committee which has the authority to endorse this application in the country in question.

The endorsed minutes of this meeting are attached as DOCUMENT NUMBER: 1.

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

Enter the family name in capital letters.

| Name/Title | Agency/Organisation | Signature | Action |
| --- | --- | --- | --- |
| Md. Abdul Malek, Joint Secretary (Development) | Ministry of Local Government & Rural Development |  |  |
| Dr. Shehlina Ahmed, Health Advisor | DFID |  |  |
| Faruque Ahmed, Director, Health Programme | BRAC |  |  |
| Peggy Thorpe, First Secretary, Development | CIDA |  |  |
| Khadijat Mojidi, Director, Population, Health & Nutrition | USAID |  |  |
| Dr. Bushra Binte Alam, Senior Health Specialist | World Bank |  |  |
| PDG Salim Reza, Chairman | Rotary International |  |  |
| Dr. Arun Bhadra Thapa, Ag. WHO Representative | WHO |  |  |
| Dr. Birthe Locatelli Rossi,Chief, Health & Nutrition Section | UNICEF |  |  |
| Maki Nagai, Representative | JICA |  |  |

In case the GAVI Secretariat has queries on this submission, please contact

Enter the family name in capital letters.

| Name | Dr. Md. Shamsul Ashraf Khan | Title | Program Manager, Child Health and Limited Curative Care, |
| --- | --- | --- | --- |
| Tel no | +880-2-8821910-13 |  |  |
| Fax no | +880-2-8821914 | Address | EPI Bhaban, Directorate General of Health Servises, Mohakhali, Dhaka-1212, Bangladesh |
| Email | shamsul.shelly@yahoo.com |  |  |

# The Inter-Agency Coordinating Committee for Immunisation

Agencies and partners (including development partners and NGOs) supporting immunisation services are co-ordinated and organised through an inter-agency coordinating mechanism (ICC, HSCC, or equivalent committee). The ICC, HSCC, or equivalent committee is responsible for coordinating and guiding the use of the GAVI NVS support. Please provide information about the ICC, HSCC, or equivalent committee in your country in the table below.

Profile of the ICC, HSCC, or equivalent committee

| Name of the committee | Inter-Agency Coordination Committee (ICC) |
| --- | --- |
| Year of constitution of the current committee | 2001 |
| Organisational structure (e.g., sub-committee, stand-alone) | Technical Sub-Committee |
| Frequency of meetings | 3-4 meetings per year |

Composition

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

Enter the family name in capital letters.

| Function | Title / Organisation | Name |  |
| --- | --- | --- | --- |
| Chair | Secretary, Ministry of Health and Family Welfare | Md. Humayun Kabir |  |
| Secretary | Director-PHC and Line Director-ESD | DR A B M Jahangir Alam |  |
| Members | Joint Secretary (Development) Ministry of LGRD | Md. Abdul Malek | Action |
|  | Senior Health Advisor, DFID | Dr. Shehlina Ahmed |  |
|  | Deputy Executive Director, Health, BRAC | Faruque Ahmed |  |
|  | First Secretary, Embassy of Japan |  |  |
|  | Chief, Health & Nutrition Section, UNICEF | Dr. Birthe Locatelli Rossi |  |
|  | Senior Health Specialist, World Bank | Dr. Bushra Binte Alam, |  |
|  | Chairman, Rotary International | PDG Salim Reza |  |
|  | Co-Chairman, National Polio Plus Comittee | Prof. Jalal U Ahmed |  |

Major functions and responsibilities of the committee

1. ICC review and approves all EPI activities including GAVI related activities and budgets which are recommended by the Technical Sub-committee 2. ICC reviews and monitor all EPI related activities, budget and expenditute statements 3. ICC assesses APR and approves before sending to GAVI Secretariat

Three major strategies to enhance the committee's role and functions in the next 12 months

| 1. | To organize at least 3 or more ICC meetings in next 12 months to review the activities and to provide quick decisions for accomplishing activities. |
| --- | --- |
| 2. | To review the existing committee and to involve new members from other Multisectoral Partners Agencies, Civil Society Organizations, Professional bodies and more participation from Local Goverment like City Corporations. |
| 3. | To cooddinate partner agencies and GAVI Secretariat for developing coodinated efforts to introduce New and Underutilized Vaccine in routine EPI to save millions of lives. |

# National Immunization Technical Advisory Group for Immunisation

(If it has been established in the country)

We the members of the NITAG met on the 13.04.2010 to review this proposal. At that meeting we endorsed this proposal on the basis of the supporting documentation which is attached.

The endorsed minutes of this meeting are attached as DOCUMENT NUMBER: 2.

In case the GAVI Secretariat has queries on this submission, please contact

Enter the family name in capital letters.

| Name | Dr. Md. Shamsul Ashraf Khan | Title | Program Manager, Child Health and Limited Curative Care, |
| --- | --- | --- | --- |
| Tel no | +880-2-8821910-13 |  |  |
| Fax no | +880-2-8821914 | Address | EPI Bhaban, Directorate General of Health Servises, Mohakhali, Dhaka-1212, Bangladesh |
| Email | shamsul.shelly@yahoo.com |  |  |

# The NITAG Group for Immunisation

Profile of the NITAG

| Name of the NITAG | National Committee for Immunization Practices (NCIP) |
| --- | --- |
| Year of constitution of the current NITAG | 2008 |
| Organisational structure (e.g., sub-committee, stand-alone) | Scientific and Technical Sub-committee of NCIP |
| Frequency of meetings | 2 Meetings |

Composition

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

Enter the family name in capital letters.

| Function | Title / Organisation | Name |  |
| --- | --- | --- | --- |
| Chair | Secretary, Ministry of Health and Family Welfare | Md Humayun Kabir |  |
| Secretary | Director, PHC and Line Director - ESD, DGHS | Dr. A. B. M.. Jahangir Alam |  |
| Members | Principal, Sir Salimullah Medical College | Prof. M A Azhar | Action |
|  | Director, IEDCR | Prof. Mahmudur Rahman |  |
|  | Director General, Directorate General of Drug Administration | Major General Md Abul Kalam Azad |  |
|  | Head of department of Immunology, BIRDEM | Prof. Sawkat Hasan |  |
|  | Deputy Secretary, MOH&FW | Iffatara Mahmood |  |
|  | Director Disease Control | Dr Benazir Ahmed |  |
|  | Secretary General, Bangladesh Medical Associaltion | Prof. Dr Sharfuddin Ahmed |  |
|  | Professor of Paediatrics, Dhaka Medical College | Prof. M Ekhlasur Rahman |  |
|  | Medical Officer, WHO-IVD | Dr Serguei Diorditsa |  |
|  | Immunization Specialist, UNICEF | Dr Jucy Merina Adhikari |  |
|  | Prof. Department of Microbiology, Dhaka Shishu Hospital | Prof. Samir Kumar Shaha |  |
|  | Director, National Institute of Preventive and Social Medicine | Prof. Saruj Kumar Majumdar |  |
|  | President, Bangladesh Paediatrics Association |  |  |
|  | Program Manager, EPI, DGHS | Dr Md Shamsul Ashraf Khan |  |

Major functions and responsibilities of the NITAG

Take decision on national policy on immunization Approve different sub-committee and finalize their responsibilities Review proposals and recommendations of different sub-committees

Three major strategies to enhance the NITAG’s role and functions in the next 12 months

| 1. | Conduct regular meetings |
| --- | --- |
| 2. | Coordination among different stake holders including GAVI |
| 3. | Participation in different national and international seminars/conference |

# Immunisation Programme Data

Please complete the tables below, using data from available sources. Please identify the source of the data, and the date. Where possible use the most recent data and attach the source document.

- Please refer to the Comprehensive Multi-Year Plan for Immunisation (cMYP) (or equivalent plan) and attach a complete copy (with an Executive Summary) as DOCUMENT NUMBER 3

- Please refer to the two most recent annual WHO/UNICEF Joint Reporting Forms (JRF) on Vaccine Preventable Diseases.

- Please refer to Health Sector Strategy documents, budgetary documents, and other reports, surveys etc, as appropriate.

# Basic facts

For the year 2009 (most recent; specify dates of data provided)

|  | Figure |  | Year | Source |
| --- | --- | --- | --- | --- |
| Total population | 146,191,325 |  | 2009 | WHO-SEARO IVD Annual EPI Reporting form (March 2010) |
| Infant mortality rate (per 1000) | 52 |  | 2009 | BDHS 2007 |
| Surviving Infants[1] | 3,617,183 |  | 2009 | JRF 2010 |
| GNI per capita (US$) | 520 |  | 2009 | cMYP |
| Total Health Expenditure (THE) as a percentage of GDP | 1.04 | % | 2010 | Ministry of Finance, Budget 2010 |
| General government expenditure on health (GGHE) as % of General government expenditure | 6.15 | % | 2010 | Ministry of Finance, Budget 2010 |

[1] Surviving infants = Infants surviving the first 12 months of life

Please provide some additional information on the planning and budgeting context in your country; also indicate the name and date of the relevant planning document for health

There are two major policy planning documents that outline sector priorities, strategies, interventions and resources: a) Health Population and Nutrition Sector Strategic Plan (2011-2016) b) Program Implementation Plan (PIP); Health Population and Nutrition Sector Development Program (HPNSDP) 2011-2016

Is the cMYP (or updated Multi-Year Plan) aligned with this document (timing, content, etc.)?

Yes, the current cMYP developed in 2010 covers the same period as HPNSDP 2011 - 2016

Please indicate the national planning budgeting cycle for health

National budgeting cycle for health covers 1 year and starts on July 1 of each year and ends on June 30 of the next year

Please indicate the national planning cycle for immunisation

National planning cycle for immunization is harmonized with national budgeting cycle for health

Please indicate if sex disaggregated data (SDD) is used in immunisation routine reporting systems

Not in routine immunization reporting system, but this data is available in EPI Coverage Evaluation Survey.

Please indicate if gender aspects relating to introduction of a new vaccine have been addressed in the introduction plan

No

# Current vaccination schedule

Traditional, New Vaccines and Vitamin A supplement (refer to cMYP pages)

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Vaccine (do not use trade name) | Ages of administration (by routine immunisation services) | Given in entire country | Comments | Action |
| --- | --- | --- | --- | --- |
| BCG | at birth | Yes |  |  |
| Polio | 1st Dose -6 weeks, 2nd Dose-10 weeks, 3rd Dose -14 weeks, 4th Dose - 38 Weeks | Yes |  |  |
| Measles | 9 months / 38 weeks | Yes |  |  |
| Penta | 1st Dose -6 weeks, 2nd Dose-10 weeks, 3rd Dose -14 weeks | Yes |  |  |
| Vitamin A | With measles | Yes |  |  |

# Trends of immunisation coverage and disease burden

(as per last two annual WHO/UNICEF Joint Reporting Form on Vaccine Preventable Diseases)

| Trends of immunisation coverage (percentage) |  |  |  |  |  | Vaccine preventable disease burden |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Vaccine |  | Reported |  | Survey |  | Disease | Number of reported cases |  |
|  |  | 2009 | 2010 | 2009 | 2010 |  | 2009 | 2010 |
| BCG |  | 94 | 94 | 99 | 99 | Tuberculosis |  |  |
| DTP | DTP1 | 97 | 98 | 99 | 98 | Diphtheria | 23 | 27 |
|  | DTP3 | 96 | 95 | 87 | 89 | Pertussis | 16 | 17 |
| Polio 3 |  | 96 | 95 | 94 | 94 | Polio | 0 | 0 |
| Measles (first dose) |  | 98 | 94 | 88 | 85 | Measles | 718 | 788 |
| TT2+ (Pregnant women) |  | 37 | 37 | 95 | 95 | NN Tetanus | 121 | 117 |
| Hib3 |  |  | 95 |  |  | Hib[2] |  |  |
| Yellow Fever |  |  |  |  |  | Yellow fever |  |  |
| HepB3 |  | 96 | 95 |  | 89 | HepBsero-prevalence[1] |  |  |
| Vitamin A supplement Mothers (< 6 weeks post-delivery) |  | 69 | 69 | 39 | 39 |  |  |  |
| Vitamin A supplement Infants (>6 months) |  | 98 | 94 | 82 | 93 |  |  |  |

[1] If available

[2] Note: JRF asks for Hib meningitis

If survey data is included in the table above, please indicate the years the surveys were conducted, the full title and if available, the age groups the data refers to

EPI Coverage Evaluation Survey (CES) 2010 EPI Coverage Evaluation Survey (CES) 2009

# Baseline and Annual Targets

(refer to cMYP pages)

Table 1: baseline figures

| Number | Base Year | Baseline and Targets |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2009 | 2012 | 2013 | 2014 | 2015 | 2016 |  |
| Total births | 3,815,594 | 3,983,990 | 4,041,758 | 4,100,364 | 4,159,819 | 4,220,136 |  |
| Total infants' deaths | 198,411 | 207,167 | 210,171 | 213,219 | 216,311 | 219,447 |  |
| Total surviving infants | 3,617,183 | 3,776,823 | 3,831,587 | 3,887,145 | 3,943,508 | 4,000,689 |  |
| Total pregnant women | 5,116,696 | 5,342,515 | 5,419,982 | 5,498,571 | 5,578,301 | 5,659,186 |  |
| Number of infants vaccinated (to be vaccinated) with BCG | 3,600,085 | 3,904,310 | 3,960,923 | 4,018,356 | 4,076,622 | 4,135,734 |  |
| BCG coverage (%)[1] | 94% | 98% | 98% | 98% | 98% | 98% |  |
| Number of infants vaccinated (to be vaccinated) with OPV3 | 3,456,739 | 3,512,445 | 3,563,376 | 3,615,045 | 3,667,463 | 3,720,641 |  |
| OPV3 coverage (%)[2] | 96% | 93% | 93% | 93% | 93% | 93% |  |
| Number of infants vaccinated (or to be vaccinated) with DTP1[3] | 3,524,038 | 3,587,982 | 3,640,007 | 3,692,787 | 3,746,333 | 3,800,655 |  |
| Number of infants vaccinated (to be vaccinated) with DTP3[3] | 3,470,505 | 3,512,445 | 3,563,376 | 3,615,045 | 3,667,463 | 3,720,641 |  |
| DTP3 coverage (%)[2] | 96% | 93% | 93% | 93% | 93% | 93% |  |
| Wastage[1] rate in base-year and planned thereafter for DTP (%) | 45% | 5% | 5% | 5% | 5% | 5% |  |
| Wastage[1] factor in base-year and planned thereafter for DTP | 1.82 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 |  |
| Target population vaccinated with 1st dose of Pneumococcal |  |  | 3,256,849 | 3,498,430 | 3,746,333 | 3,800,655 |  |
| Target population vaccinated with 3rd dose of Pneumococcal |  |  | 3,180,217 | 3,420,687 | 3,667,463 | 3,720,641 |  |
| Pneumococcal coverage (%)[2] | 0% | 0% | 83% | 88% | 93% | 93% |  |
| Infants vaccinated (to be vaccinated) with 1st dose of Measles | 3,558,866 | 3,399,140 | 3,448,428 | 3,498,430 | 3,746,333 | 3,800,655 |  |
| Measles coverage (%)[2] | 98% | 90% | 90% | 90% | 95% | 95% |  |
| Infants vaccinated (to be vaccinated) with 2nd dose of Measles |  | 3,210,299 | 3,448,428 | 3,498,430 | 3,746,333 | 3,800,655 |  |
| Pregnant women vaccinated with TT+ | 1,887,111 |  |  |  |  |  |  |
| TT+ coverage (%)[4] | 37% | 0% | 0% | 0% | 0% | 0% |  |
| Vit A supplement to mothers within 6 weeks from delivery | 2,633,704 |  |  |  |  |  |  |
| Vit A supplement to infants after 6 months | 3,546,421 | 3,399,140 | 3,448,428 | 3,498,430 | 3,746,333 | 3,800,655 |  |
| Annual DTP Drop-out rate[ ( DTP1 - DTP3 ) / DTP1 ] x 100[5] | 2% | 2% | 2% | 2% | 2% | 2% |  |

[1] Number of infants vaccinated out of total births

[2] Number of infants vaccinated out of total surviving infants

[3] Indicate total number of children vaccinated with either DTP alone or combined

[4] Number of pregnant women vaccinated with TT+ out of total pregnant women

[5] The formula to calculate a vaccine wastage rate (in percentage):[ ( A – B ) / A ] x 100. Whereby: A = the number of doses distributed for use according to the supply records with correction for stock balance at the end of the supply period; B = the number of vaccinations with the same vaccine in the same period.

# Summary of current and future immunisation budget

(or refer to cMYP pages)

|  | Estimated costs per annum in US$ (in thousand US$) |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Cost category | Base Year | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |  |
|  | 2009 | 2012 | 2013 | 2014 | 2015 | 2016 |  |  |  |  |
| Routine Recurrent Cost |  |  |  |  |  |  |  |  |  |  |
| Vaccines (routine vaccines only) | 47,002,312 | 71,392,687 | 116,563,855 | 156,659,585 | 147,873,707 | 156,750,875 |  |  |  |  |
| Traditional vaccines | 21,718,961 | 28,430,230 | 28,397,642 | 28,771,571 | 29,383,469 | 39,531,148 |  |  |  |  |
| New and underused vaccines | 25,283,351 | 42,962,457 | 88,166,213 | 127,888,014 | 118,490,238 | 117,219,727 |  |  |  |  |
| Injection supplies | 3,558,042 | 20,482,503 | 22,088,241 | 22,372,041 | 22,871,468 | 27,121,574 |  |  |  |  |
| Personnel | 23,552,092 | 25,907,302 | 28,579,808 | 31,437,789 | 34,581,567 | 38,039,724 |  |  |  |  |
| Salaries of full-time NIP health workers (immunisation specific) | 23,182,157 | 25,500,373 | 28,130,478 | 30,943,526 | 34,037,878 | 37,441,666 |  |  |  |  |
| Per-diems for outreach vaccinators / mobile teams | 369,935 | 406,929 | 449,330 | 494,263 | 543,689 | 598,058 |  |  |  |  |
| Transportation | 200,738 | 241,505 | 272,802 | 291,268 | 311,140 | 178,150 |  |  |  |  |
| Maintenance and overheads | 866,506 | 1,611,069 | 3,270,678 | 2,743,918 | 2,995,254 | 3,357,371 |  |  |  |  |
| Training | 210,000 | 230,000 | 215,000 | 215,000 | 215,000 | 230,000 |  |  |  |  |
| Social mobilisation and IEC | 50,000 | 1,466,000 | 1,414,000 | 100,000 | 105,000 | 110,000 |  |  |  |  |
| Disease surveillance | 1,915,300 | 2,164,610 | 2,447,519 | 2,768,685 | 3,133,430 | 3,547,832 |  |  |  |  |
| Program management | 258,189 | 288,598 | 310,778 | 324,892 | 351,119 | 379,657 |  |  |  |  |
| Other | 1,147,129 | 1,204,485 | 1,264,710 | 1,327,945 | 1,394,342 | 1,464,060 |  |  |  |  |
| Subtotal Recurrent Costs | 78,760,308 | 124,988,759 | 176,427,391 | 218,241,123 | 213,832,027 | 231,179,243 |  |  |  |  |
| Routine Capital Costs |  |  |  |  |  |  |  |  |  |  |
| Vehicle | 0 | 122,400 | 52,020 | 0 | 0 | 0 |  |  |  |  |
| Cold chain equipment | 0 | 5,285,167 | 19,462,763 | 2,129,844 | 1,360,617 | 1,968,235 |  |  |  |  |
| Other capital equipment | 0 | 38,760 | 2,081 | 2,122 | 2,165 | 5,520 |  |  |  |  |
| Subtotal Capital Costs | 0 | 5,446,327 | 19,516,864 | 2,131,966 | 1,362,782 | 1,973,755 |  |  |  |  |
| Campaigns |  |  |  |  |  |  |  |  |  |  |
| Polio | 9,955,398 | 7,722,957 | 7,834,940 | 7,948,547 | 8,063,800 | 8,180,725 |  |  |  |  |
| Measles | 6,575,200 |  |  |  |  |  |  |  |  |  |
| Yellow Fever |  |  |  |  |  |  |  |  |  |  |
| MNT campaigns |  |  |  |  |  |  |  |  |  |  |
| Other campaigns |  |  |  |  |  |  |  |  |  |  |
| Subtotal Campaign Costs | 16,530,598 | 7,722,957 | 7,834,940 | 7,948,547 | 8,063,800 | 8,180,725 |  |  |  |  |
| GRAND TOTAL | 95,290,906 | 138,158,043 | 203,779,195 | 228,321,636 | 223,258,609 | 241,333,723 |  |  |  |  |

# Summary of current and future financing and sources of funds

Please list in the tables below the funding sources for each type of cost category (if known). Please try and indicate which immunisation program costs are covered from the Government budget, and which costs are covered by development partners (or the GAVI Alliance), and name the partners (or refer to cMYP).

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

|  |  | Estimated costs per annum in US$ (in thousand US$) |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Cost category | Funding source | Base Year | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |  |
|  |  | 2009 | 2012 | 2013 | 2014 | 2015 | 2016 |  |  |  |  |
| Routine Recurrent Cost |  |  |  |  |  |  |  |  |  |  |  |
| Traditional Vaccines | Pooled Funds | 21,718,961 | 25,260,059 | 25,626,354 | 25,997,936 | 26,374,906 | 36,517,903 |  |  |  |  |
| Traditional Vaccines | GAVI |  | 3,170,171 | 2,771,289 | 2,773,635 | 3,008,564 | 3,013,246 |  |  |  |  |
| Underused Vaccines | Pooled Funds | 5,470,779 | 6,575,437 | 5,355,693 | 5,972,872 | 6,551,937 | 6,637,924 |  |  |  |  |
| Underused Vaccines | GAVI | 18,728,140 | 34,112,831 | 34,607,499 | 35,109,308 | 35,618,393 | 36,134,859 |  |  |  |  |
| Underused Vaccines | Goverment's co-financing | 1,084,432 | 2,274,189 | 2,307,167 | 2,340,621 | 2,374,560 | 2,408,991 |  |  |  |  |
| New vaccines | Pooled Funds |  |  |  |  |  |  |  |  |  |  |
| New vaccines | GAVI |  |  | 43,324,658 | 80,478,548 | 70,019,921 | 68,002,213 |  |  |  |  |
| New vaccines | Government co-financing |  |  | 2,571,196 | 3,986,665 | 3,925,428 | 4,035,740 |  |  |  |  |
| Injection Supplies | Pooled Funds | 3,097,105 | 18,830,061 | 19,144,414 | 19,547,076 | 19,906,401 | 24,134,228 |  |  |  |  |
| Injection Supplies | GAVI | 460,937 | 1,652,442 | 2,943,827 | 2,824,965 | 2,965,067 | 2,987,346 |  |  |  |  |
| Personnel | Government | 23,182,157 | 25,907,302 | 28,579,808 | 31,437,789 | 34,581,568 | 38,039,724 |  |  |  |  |
| Personnel | GAVI | 369,935 |  |  |  |  |  |  |  |  |  |
| Transportation | Government | 200,738 | 227,377 | 272,802 | 291,268 | 311,140 | 178,150 |  |  |  |  |
| Maintenance and overhead | Government | 771,506 | 1,611,069 | 3,270,678 | 2,743,918 | 2,995,254 | 3,357,371 |  |  |  |  |
| Short-term training | Government | 210,000 |  |  |  |  |  |  |  |  |  |
| IEC/social mobilization | GAVI |  | 1,123,000 | 1,139,000 |  |  |  |  |  |  |  |
| IEC/social mobilization | WHO |  | 31,000 | 31,000 |  |  |  |  |  |  |  |
| IEC/social mobilization | UNICEF | 50,000 |  |  |  |  |  |  |  |  |  |
| Disease surveillance | Government |  | 835,670 | 919,237 | 1,011,161 | 1,112,278 | 1,223,506 |  |  |  |  |
| Disease surveillance | WHO | 1,915,300 | 1,328,940 | 1,528,282 | 1,757,524 | 2,021,152 | 2,324,326 |  |  |  |  |
| Programme management | GAVI |  | 10,000 | 10,000 |  |  |  |  |  |  |  |
| Programme management | WHO | 258,189 |  |  |  |  |  |  |  |  |  |
| Other routine recurrent costs | USAID | 644,870 |  |  |  |  |  |  |  |  |  |
| Other routine recurrent costs | ADB | 502,259 |  |  |  |  |  |  |  |  |  |
| Routine Capital Costs |  |  |  |  |  |  |  |  |  |  |  |
| Cold Chain Equipment | UNICEF |  | 1,750,000 |  |  |  |  |  |  |  |  |
| Vehicles | GAVI |  | 50,000 | 50,000 |  |  |  |  |  |  |  |
| Campaigns |  |  |  |  |  |  |  |  |  |  |  |
| Polio | Government | 11,181,213 | 8,984,578 | 9,178,849 | 9,380,113 | 9,588,741 | 9,805,130 |  |  |  |  |
| Polio | WHO | 735,489 | 756,972 | 806,346 | 858,940 | 914,964 | 974,643 |  |  |  |  |
| Polio | UNICEF | 490,326 | 504,648 | 537,564 | 572,627 | 609,976 | 649,762 |  |  |  |  |
| Measles | Government | 7,801,014 |  |  |  |  |  |  |  |  |  |
| Measles | WHO | 735,489 |  |  |  |  |  |  |  |  |  |
| Measles | UNICEF | 490,326 |  |  |  |  |  |  |  |  |  |
| GRAND TOTAL |  | 100,099,165 | 134,995,746 | 184,975,663 | 227,084,966 | 222,880,250 | 240,425,062 |  |  |  |  |

# New and Under-Used Vaccines (NVS)

Please summarise the cold chain capacity and readiness to accommodate new vaccines, stating how the cold chain expansion (if required) will be financed, and when it will be in place. Please indicate the additional cost, if capacity is not available and the source of funding to close the gap.

There is a need to upgrade cold chain capacity (+2 to +8) at the central level 40 m3 net volume for covering current deficit and intoduction of MCV2. No need to upgrade at sub national level. Funds are secured from UNICEF (1 million USD) for 4 WIC to be installed in 2011. Additional net 30 m3 cold chain capacity (+2 to +8)at the central level is needed for PCV introduction in 2013. Three WIC to be installed in with financial support from UNICEF. No need of additional space at the sub-national level. In addition to the above mentioned upgrade comprehensive improvement of cold chain and logistics will take place in 2012-13 in accordance with EVM assessment improvement plan. Along with other logistical issues it will address the requirement of cold chain space (at the National and District levels) of about 620 m3 for Rota and Hep-B birth dose in 2014.

Please give a summary of the cMYP sections that refer to the introduction of new and under-used vaccines. Outline the key points that informed the decision-making process (data considered etc)

With the GAVI co-financing support EPI programme in Bangladesh successfully introduced the Hib + Hep B vaccine in to the EPI schedule in the form of Pentavalent vaccine in 2009. In 2008 National Committee for Immunization practice (NICP) was established with the Chairmanship of Secretary, Ministry of Health and Family Welfare to consider and assess feasibility of introduction of new and underused vaccines (such as Pneumococcal vaccine, Rota vaccine, Birth dose of hepatitis B vaccine, second dose of measles vaccine and Td vaccine) in to the national EPI programme in coming years. They have appointed Scientific and technical sub-committee. That committee produced recommendations based on the analysis of global, regional practices and the country needs. A. Pneumococcal vaccine Diseases caused by Streptococcus pneumoniae (S. pneumoniae or pneumococcus) are a major public health problem worldwide. Serious diseases that are often caused by pneumococci include pneumonia, meningitis and febrile bacteraemia; otitis media, sinusitis and bronchitis are more common but less serious manifestations of infection. In 2005, WHO estimated that 1.6 million people die of pneumococcal disease every year; this estimate includes the deaths of 0.7–1 million children3 aged <5 years, most of whom live in developing countries. In Bangladesh the study was conducted and uncovered the substantial diseases burden affecting children living in impoverish communities. Pneumococcus was found consistently a leading cause of severe pneumonia, invasive disease and death among hospitalized children. In Bangladesh the authors estimated the PCV could prevent an incredible one million episodes of pneumonia each year. The results of active multicentre surveillance network in Bangladesh also showed invasive pneumococcal disease to be the most prevailing in early life, with 48% of patient aged less than 6 months, and 72 % aged less than 12 months. In 2010 meeting of National Committee on Immunization and practices considered PCV vaccine as one of the priority to be introduce in Bangladesh to reduce child mortality. During this meeting the NCIP discussed the recommendations on PCV introduction as per WHO position paper and also considered the national data from the studies and active surveillance activities conducted in Bangladesh. NCIP recommended PCV to be introduced in National EPI in Bangladesh. B. Second dose of measles vaccine In accordance with Global and Regional strategy to reduce measles mortality down to 2000 estimates, National EPI prepared A National Plan for reduction of measles mortality in Bangladesh during 2004-2010. In accordance with this plan the measles second dose was provided as measles catch up campaign in 2005-2006 to vaccinate more than 35 million children aged from 9 month to 10 years. Measles follow up campaign was conducted in 2010 to immunize children aged 9 month to 5 years. The achievements are dramatic: more than 80% of deaths related to measles are averted. In Bangladesh the CES 2010 showed that the mean coverage of measles was 85%. With 85% vaccine effectiveness actual protection was given to only 72% of annual birth cohorts (85% x 85% = 72%). In other words, at least 28% remained susceptible to measles. It was decide in the national measles control plan 2004-2010 that measles second dose will be introduce into routine EPI after the follow up campaign to sustain the achievement of measles mortality reduction. In addition Bangladesh National EPI supported the recommendation of SEARO to eliminate measles by 2016. National Committee on Immunization and practices during its meeting in 2010 supported the National EPI proposal to eliminate measles in Bangladesh by 2016 and recommended to introduce MCV21 into routine EPI in Bangladesh.

# Capacity and cost (for positive storage)

|  |  | Formula | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2012 | 2013 | 2014 | 2015 | 2016 |  |  |  |
| A | Annual positive volume requirement, including new vaccine (litres or m3) m3 | Sum-product of total vaccine doses multiplied by unit packed volume of the vaccine | 600 | 711 | 711 | 711 | 711 |  |  |  |
| B | Existing net positive cold chain capacity (litres or m3) m3 | # | 110 | 150 | 180 | 180 | 180 |  |  |  |
| C | Estimated minimum number of shipments per year required for the actual cold chain capacity | A / B | 6 | 5 | 4 | 4 | 4 |  |  |  |
| D | Number of consignments / shipments per year | Based on national vaccine shipment plan | 4 | 4 | 4 | 4 | 4 |  |  |  |
| E | Gap (if any) | ((A / D) - B) | 40 | 28 | -2 | -2 | -2 |  |  |  |
| F | Estimated additional cost of cold chain | US$ | 1,000,000 | 750,000 |  |  |  |  |  |  |

Please briefly describe how your country plans to move towards attaining financial sustainability for the new vaccines you intend to introduce, how the country will meet the co-financing payments, and any other issues regarding financial sustainability you have considered (refer to the cMYP)

MCV2 does not require co-financing by the country as per GAVI policy. The government of Bangladesh is committed to cofinance for PCV vaccine in 2013-2016 and it will be about USD 9.61 m from pooled fund. There is no risk to financial sustainability for funding of vaccines and injection safety supplies by the government (see section III of cMYP for details).

# Assessment of burden of relevant diseases (if available)

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Disease | Title of the assessment | Date | Results |  |
| --- | --- | --- | --- | --- |

If new or under-used vaccines have already been introduced in your country, please give details of the lessons learned from storage capacity, protection from accidental freezing, staff training, cold chain, logistics, drop-out rate, wastage rate etc., and suggest action points to address them

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Lessons Learned | Action Points |  |
| --- | --- | --- |
| High political and financial commitment of government and active coordination among partners agencies were the key for successful introduction. | Commitment from the Government and parnter agencies is secured for the introduction of MCV2 and PCV |  |
| Effective and quality training at all level before introduction of new vaccine is a must. | Training and guidance of all key professionals will be conducted in advance. |  |
| Advocacy and planning meetings with different stakeholder at various level is useful to creat awareness among the community. | Importance of advocacy efforts will be considered during the introduciton of MCV2 and PCV |  |
| In context of EPI service delivery strastegy smaller dose presentation of vaccine vial reduces wastage of vaccine |  |  |

Please list the vaccines to be introduced with support from the GAVI Alliance (and presentation)

1. Measle containaing vaccine 10 dose vials (in order to minimize vaccine wastage country is open to consider smaller dose presentation of vaccine if available acknowledging its implication on cold chain capacity) 2. PCV 2 dose liquid vaccine

# 6.3.1. Requested vaccine ( Measles, 10 doses/vial, Lyophilised )

As reported in the cMYP, the country plans to introduce Measles, 10 doses/vial, Lyophilised vaccine.

# 6.3.2. Co-financing information

No Co-financing for Measles

# 6.3.3. Wastage factor

Please indicate wastage rate:

Countries are expected to plan for a maximal wastage rate of:

- 50% - for a lyophilised vaccine in 10 or 20-dose vial,

- 25% - for a liquid vaccine in 10 or 20-dose vial or a lyophilised vaccine in 5-dose vial,

- 10% - for a lyophilised/liquid vaccine in 2-dose vial, and

- 5% - for a liquid vaccine in 1-dose vial

Note: Selection of this field has direct impact on automatic calculations of support you are requesting and should not be left empty.

|  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2012 | 2013 | 2014 | 2015 | 2016 |  |  |  |
| Vaccine wastage rate in % | 50% | 50% | 50% | 50% | 50% |  |  |  |
| Equivalent wastage factor | 2.00 | 2.00 | 2.00 | 2.00 | 2.00 |  |  |  |

# 6.3.4. Specifications of vaccinations with new vaccine

|  | Data from |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2012 | 2013 | 2014 | 2015 | 2016 |  |  |  |
| Number of children to be vaccinated with the first dose | Table 1 | # | 3,399,140 | 3,448,428 | 3,498,430 | 3,746,333 | 3,800,655 |  |  |  |
| Number of children to be vaccinated with the third dose[1] | Table 1 | # | 3,210,299 | 3,448,428 | 3,498,430 | 3,746,333 | 3,800,655 |  |  |  |
| Immunisation coverage with the third dose | Table 1 | # | 90.00% | 90.00% | 90.00% | 95.00% | 95.00% |  |  |  |
| Estimated vaccine wastage factor | Table 6.(n).3[3] | # | 2.00 | 2.00 | 2.00 | 2.00 | 2.00 |  |  |  |
| Country co-financing per dose[2] | Table 6.(n).2[3] | $ | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |  |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Total price per-dose includes vaccine cost, plus freight, supplies, insurance, visa costs etc.

[3] Where (n) depends on the vaccine

# 6.3.5. Portion of supply to be procured by the country (and cost estimate, US$)

|  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2012 | 2013 | 2014 | 2015 | 2016 |  |  |  |
| Number of vaccine doses | # | 0 | 0 | 0 | 0 | 0 |  |  |  |
| Number of AD syringes | # | 0 | 0 | 0 | 0 | 0 |  |  |  |
| Number of re-constitution syringes | # | 0 | 0 | 0 | 0 | 0 |  |  |  |
| Number of safety boxes | # | 0 | 0 | 0 | 0 | 0 |  |  |  |
| Total value to be co-financed by country | $ | 0 | 0 | 0 | 0 | 0 |  |  |  |

# 6.3.6. Portion of supply to be procured by the GAVI Alliance (and cost estimate, US$)

|  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2012 | 2013 | 2014 | 2015 | 2016 |  |  |  |
| Number of vaccine doses | # | 8,025,800 | 7,016,000 | 7,021,900 | 7,616,700 | 7,628,500 |  |  |  |
| Number of AD syringes | # | 5,345,200 | 3,960,000 | 3,911,100 | 4,296,100 | 4,248,900 |  |  |  |
| Number of re-constitution syringes | # | 890,900 | 778,800 | 779,500 | 845,500 | 846,800 |  |  |  |
| Number of safety boxes | # | 69,225 | 52,600 | 52,075 | 57,075 | 56,575 |  |  |  |
| Total value to be co-financed by GAVI | $ | 2,516,500 | 2,153,000 | 2,151,500 | 2,337,000 | 2,337,000 |  |  |  |

# 6.3.7. New and Under-Used Vaccine Introduction Grant

Please indicate in the tables below how the one-time Introduction Grant[1] will be used to support the costs of vaccine introduction and critical pre-introduction activities (refer to the cMYP).

Calculation of lump-sum for the Measles, 10 doses/vial, Lyophilised

If the total is lower than US$100,000, it is automatically rounded up to US$100,000

| Year of New Vaccine Introduction | Births (from Table 1) | Share per Birth in US$ | Total in US$ |
| --- | --- | --- | --- |
| 2012 | 3,983,990 | 0.30 | 1,195,500 |

[1] The Grant will be based on a maximum award of $0.30 per infant in the birth cohort with a minimum starting grant award of $100,000

Cost (and finance) to introduce the Measles, 10 doses/vial, Lyophilised (US$)

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Cost Category | Full needs for new vaccine introduction in US$ | Funded with new vaccine introduction grant in US$ |  |
| --- | --- | --- | --- |
| Training | 1,125,000 | 1,095,000 |  |
| Social Mobilization, IEC and Advocacy | 41,000 | 40,000 |  |
| Cold Chain Equipment & Maintenance | 1,000,000 | 0 |  |
| Vehicles and Transportation | 50,000 | 50,000 |  |
| Programme Management |  |  |  |
| Surveillance and Monitoring | 10,000 | 10,000 |  |
| Human Resources |  |  |  |
| Waste Management |  |  |  |
| Technical assistance |  |  |  |
| Totals | 2,226,000 | 1,195,000 |  |

# 6.4.1. Requested vaccine ( Pneumococcal (PCV10), 2 doses/vial, Liquid )

As reported in the cMYP, the country plans to introduce Pneumococcal (PCV10), 2 doses/vial, Liquid vaccine.

# 6.4.2. Co-financing information

If you would like to co-finance higher amount than minimum, please overwrite information in the “Your co-financing” row.

Note: Selection of this field has direct impact on automatic calculations of support you are requesting and should not be left empty.

| Country group | Low |
| --- | --- |

|  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2013 | 2014 | 2015 | 2016 |  |  |  |  |
| Minimum co-financing | 0.20 | 0.20 | 0.20 | 0.20 |  |  |  |  |
| Your co-financing (please change if higher) | 0.20 | 0.20 | 0.20 | 0.20 |  |  |  |  |

# 6.4.3. Wastage factor

Please indicate wastage rate:

Countries are expected to plan for a maximal wastage rate of:

- 50% - for a lyophilised vaccine in 10 or 20-dose vial,

- 25% - for a liquid vaccine in 10 or 20-dose vial or a lyophilised vaccine in 5-dose vial,

- 10% - for a lyophilised/liquid vaccine in 2-dose vial, and

- 5% - for a liquid vaccine in 1-dose vial

Note: Selection of this field has direct impact on automatic calculations of support you are requesting and should not be left empty.

|  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2013 | 2014 | 2015 | 2016 |  |  |  |  |
| Vaccine wastage rate in % | 5% | 5% | 5% | 5% |  |  |  |  |
| Equivalent wastage factor | 1.05 | 1.05 | 1.05 | 1.05 |  |  |  |  |

# 6.4.4. Specifications of vaccinations with new vaccine

|  | Data from |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2013 | 2014 | 2015 | 2016 |  |  |  |  |
| Number of children to be vaccinated with the first dose | Table 1 | # | 3,256,849 | 3,498,430 | 3,746,333 | 3,800,655 |  |  |  |  |
| Number of children to be vaccinated with the third dose[1] | Table 1 | # | 3,180,217 | 3,420,687 | 3,667,463 | 3,720,641 |  |  |  |  |
| Immunisation coverage with the third dose | Table 1 | # | 83.00% | 88.00% | 93.00% | 93.00% |  |  |  |  |
| Estimated vaccine wastage factor | Table 6.(n).3[3] | # | 1.05 | 1.05 | 1.05 | 1.05 |  |  |  |  |
| Country co-financing per dose[2] | Table 6.(n).2[3] | $ | 0.20 | 0.20 | 0.20 | 0.20 |  |  |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Total price per-dose includes vaccine cost, plus freight, supplies, insurance, visa costs etc.

[3] Where (n) depends on the vaccine

# 6.4.5. Portion of supply to be procured by the country (and cost estimate, US$)

|  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2013 | 2014 | 2015 | 2016 |  |  |  |  |
| Number of vaccine doses | # | 684,800 | 598,700 | 640,700 | 641,700 |  |  |  |  |
| Number of AD syringes | # | 731,200 | 633,500 | 677,900 | 678,500 |  |  |  |  |
| Number of re-constitution syringes | # |  |  |  |  |  |  |  |  |
| Number of safety boxes | # | 8,125 | 7,050 | 7,525 | 7,550 |  |  |  |  |
| Total value to be co-financed by country | $ | 2,565,000 | 2,242,500 | 2,399,500 | 2,403,000 |  |  |  |  |

# 6.4.6. Portion of supply to be procured by the GAVI Alliance (and cost estimate, US$)

|  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2013 | 2014 | 2015 | 2016 |  |  |  |  |
| Number of vaccine doses | # | 12,139,100 | 10,611,700 | 11,355,600 | 11,373,200 |  |  |  |  |
| Number of AD syringes | # | 12,961,100 | 11,227,600 | 12,014,200 | 12,025,300 |  |  |  |  |
| Number of re-constitution syringes | # |  |  |  |  |  |  |  |  |
| Number of safety boxes | # | 143,875 | 124,625 | 133,375 | 133,500 |  |  |  |  |
| Total value to be co-financed by GAVI | $ | 45,468,500 | 39,740,000 | 42,526,000 | 42,591,500 |  |  |  |  |

# 6.4.7. New and Under-Used Vaccine Introduction Grant

Please indicate in the tables below how the one-time Introduction Grant[1] will be used to support the costs of vaccine introduction and critical pre-introduction activities (refer to the cMYP).

Calculation of lump-sum for the Pneumococcal (PCV10), 2 doses/vial, Liquid

If the total is lower than US$100,000, it is automatically rounded up to US$100,000

| Year of New Vaccine Introduction | Births (from Table 1) | Share per Birth in US$ | Total in US$ |
| --- | --- | --- | --- |
| 2013 | 4,041,758 | 0.30 | 1,213,000 |

[1] The Grant will be based on a maximum award of $0.30 per infant in the birth cohort with a minimum starting grant award of $100,000

Cost (and finance) to introduce the Pneumococcal (PCV10), 2 doses/vial, Liquid (US$)

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Cost Category | Full needs for new vaccine introduction in US$ | Funded with new vaccine introduction grant in US$ |  |
| --- | --- | --- | --- |
| Training | 1,125,000 | 1,095,000 |  |
| Social Mobilization, IEC and Advocacy | 59,000 | 58,000 |  |
| Cold Chain Equipment & Maintenance | 750,000 | 0 |  |
| Vehicles and Transportation | 50,000 | 50,000 |  |
| Programme Management |  |  |  |
| Surveillance and Monitoring | 10,000 | 10,000 |  |
| Human Resources |  |  |  |
| Waste Management |  |  |  |
| Technical assistance |  |  |  |
| Totals | 1,994,000 | 1,213,000 |  |

# Procurement and Management of New and Under-Used Vaccines

Note: The PCV vaccine must be procured through UNICEF

- Please show how the support will operate and be managed including procurement of vaccines (GAVI expects that most countries will procure vaccine and injection supplies through UNICEF)

The country portion of PCV vaccines will be purchased via UNICEF procurement mechanism (as all other routine vaccines in the NIP).

- If an alternative mechanism for procurement and delivery of supply (financed by the country or the GAVI Alliance) is requested, please document

- Other vaccines or immunisation commodities procured by the country and descriptions of the mechanism used.

- The functions of the National Regulatory Authority (as evaluated by WHO) to show they comply with WHO requirements for procurement of vaccines and supply of assured quality.

Not applicable

- Please describe the introduction of the vaccines (refer to cMYP)

For details see section II.C.2 of cMYP Vaccines will be introduced in one phase. All guideline and forms will be revised and produced. Nation wide training of managers and field workers will be conducted. Advocacy and social mobilization activities will be carried out with the support of partners. In addition to these core activities, two refrigerated trucks will be procured during introduction of PCV to increase efficiency of distribution of vaccine to districts.

- Please indicate how funds should be transferred by the GAVI Alliance (if applicable)

N/A

- Please indicate how the co-financing amounts will be paid (and who is responsible for this)

USD 9.61 m from pooled fund (World Bank)

- Please outline how coverage of the new vaccine will be monitored and reported (refer to cMYP)

The coverage data of each ward/union at the lower administrative unit is compiled at sub-district level and reviewed at sub-district level monthly meeting and provide feedback to the field workers. The compiled data from the sub-district sent to district level and compiled and shared with the manager at district monthly meeting and sent to national level for compilation and feedback. Divisional coordination meeting arranged quarterly to review the coverage data and to provede feedback. In addition the supervisors of all level regularly supervise the EPI sessions and monitor the coverage data and provide on job feedback.

# Vaccine Management (EVSM/EVM/VMA)

When was the last Effective Vaccine Store Management (EVSM) conducted?   -

When was the last Effective Vaccine Management (EVM) or Vaccine Management Assessment (VMA) conducted? April   - 2011

- If your country conducted either EVSM, EVM, or VMA in the past three years, please attach relevant reports. (Document N°4)

- A VMA report must be attached from those countries which have introduced a New and Underused Vaccine with GAVI support before 2008.

- Please note that EVSM and VMA tools have been replaced by an integrated Effective Vaccine Management (EVM) tool. The information on EVM tool can be found at http://www.who.int/immunization_delivery/systems_policy/logistics/en/index6.html

- For countries which conducted EVSM, VMA or EVM in the past, please report on activities carried out as part of either action plan or improvement plan prepared after the EVSM/VMA/EVM.

Bangladesh conducted EVM Assessment in April 2011. Based on this assessment Improvement Plan has been developed. The Improvement Plan was reviewed and endorsed by ICC. Detailed action plan with budget will be drafted this year to start implementation of the Improvement Plan. Acitities will be carried out in accordance with the Improvement Plan will be reported in the next year.

- When is the next Effective Vaccine Management (EVM) Assessment planned? April   - 2013

- Under new guidelines, it will be mandatory for the countries to conduct an EVM prior to an application for introduction of new vaccine.

# Additional Comments and Recommendations

Comments and Recommendations from the National Coordinating Body (ICC/HSCC)

# Annexes

# Annex 1

# Annex 1.1 – Measles, 10 doses/vial, Lyophilised

Table 1.1 A - Rounded up portion of supply that is procured by the country and estimate of related cost in US$

| Required supply item |  | 2012 | 2013 | 2014 | 2015 | 2016 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of vaccine doses | # | 0 | 0 | 0 | 0 | 0 |  |  |  |
| Number of AD syringes | # | 0 | 0 | 0 | 0 | 0 |  |  |  |
| Number of re-constitution syringes | # | 0 | 0 | 0 | 0 | 0 |  |  |  |
| Number of safety boxes | # | 0 | 0 | 0 | 0 | 0 |  |  |  |
| Total value to be co-financed by the country | $ | 0 | 0 | 0 | 0 | 0 |  |  |  |

Table 1.1  B - Rounded up portion of supply that is procured by GAVI and estimate of related cost in US$.

| Required supply item |  | 2012 | 2013 | 2014 | 2015 | 2016 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of vaccine doses | # | 8,025,800 | 7,016,000 | 7,021,900 | 7,616,700 | 7,628,500 |  |  |  |
| Number of AD syringes | # | 5,345,200 | 3,960,000 | 3,911,100 | 4,296,100 | 4,248,900 |  |  |  |
| Number of re-constitution syringes | # | 890,900 | 778,800 | 779,500 | 845,500 | 846,800 |  |  |  |
| Number of safety boxes | # | 69,225 | 52,600 | 52,075 | 57,075 | 56,575 |  |  |  |
| Total value to be co-financed by the country | $ | 2,516,500 | 2,153,000 | 2,151,500 | 2,337,000 | 2,337,000 |  |  |  |

Table 1.1  C - Summary table for Measles, 10 doses/vial, Lyophilised

|  | Data from |  | 2012 | 2013 | 2014 | 2015 | 2016 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of Surviving infants | Table 1 | # | 3,776,823 | 3,831,587 | 3,887,145 | 3,943,508 | 4,000,689 |  |  |  |
| Number of children to be vaccinated with the third dose[1] | Table 1 | # | 3,210,299 | 3,448,428 | 3,498,430 | 3,746,333 | 3,800,655 |  |  |  |
| Immunisation coverage with the last dose | Table 1 | # | 90.00% | 90.00% | 90.00% | 95.00% | 95.00% |  |  |  |
| Number of children to be vaccinated with the first dose | Table 1 | # | 3,399,140 | 3,448,428 | 3,498,430 | 3,746,333 | 3,800,655 |  |  |  |
| Number of doses per child |  | # | 1 | 1 | 1 | 1 | 1 |  |  |  |
| Estimated vaccine wastage factor | Table 6.(n).3[2] | # | 2.00 | 2.00 | 2.00 | 2.00 | 2.00 |  |  |  |
| Number of doses per vial |  | # | 10 | 10 | 10 | 10 | 10 |  |  |  |
| AD syringes required |  | # | Yes | Yes | Yes | Yes | Yes |  |  |  |
| Reconstitution syringes required |  | # | Yes | Yes | Yes | Yes | Yes |  |  |  |
| Safety boxes required |  | # | Yes | Yes | Yes | Yes | Yes |  |  |  |
| Vaccine price per dose |  | $ | 0.240 | 0.240 | 0.240 | 0.240 | 0.240 |  |  |  |
| Country co-financing per dose | Table 6.(n).2[2] | $ | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |  |  |  |
| AD syringe price per unit |  | $ | 0.053 | 0.053 | 0.053 | 0.053 | 0.053 |  |  |  |
| Reconstitution syringe price per unit |  | $ | 0.038 | 0.038 | 0.038 | 0.038 | 0.038 |  |  |  |
| Safety box price per unit |  | $ | 0.640 | 0.640 | 0.640 | 0.640 | 0.640 |  |  |  |
| Freight cost as % of vaccines value |  | % | 10.00 | 10.00 | 10.00 | 10.00 | 10.00 |  |  |  |
| Freight cost as % of devices value |  | % | 10.00 | 10.00 | 10.00 | 10.00 | 10.00 |  |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Where (n) depends on the vaccine

# Table 1.1 D - Estimated number of doses for Measles, 10 doses/vial, Lyophilised associated injection safety material and related co-financing budget (page 1)

|  |  | Formula | 2012 |  |  | 2013 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Total | Government | GAVI | Total | Government | GAVI |
| A | Country Co-finance |  | 0.00% |  |  | 0.00% |  |  |
| B | Number of children to be vaccinated with the first dose[1] | Table 1 (baseline & annual targets) | 3,210,299 | 0 | 3,210,299 | 3,448,428 | 0 | 3,448,428 |
| C | Number of doses per child | Vaccine parameter | 1 | 1 | 1 | 1 | 1 | 1 |
| D | Number of doses needed | B * C | 3,210,299 | 0 | 3,210,299 | 3,448,428 | 0 | 3,448,428 |
| E | Estimated vaccine wastage factor | Table 6.(n).3. in NVS section[2] | 2.00 | 2.00 | 2.00 | 2.00 | 2.00 | 2.00 |
| F | Number of doses needed including wastage | D * E | 6,420,598 | 0 | 6,420,598 | 6,896,856 | 0 | 6,896,856 |
| G | Vaccines buffer stock | (F - F of previous year) * 0.25 | 1,605,150 | 0 | 1,605,150 | 119,065 | 0 | 119,065 |
| I | Total vaccine doses needed | F + G | 8,025,748 | 0 | 8,025,748 | 7,015,921 | 0 | 7,015,921 |
| J | Number of doses per vial | Vaccine parameter | 10 | 10 | 10 | 10 | 10 | 10 |
| K | Number of AD syringes (+ 10% wastage) needed | (D + G) * 1.11 | 5,345,149 | 0 | 5,345,149 | 3,959,918 | 0 | 3,959,918 |
| L | Reconstitution syringes (+ 10% wastage) needed | I / J * 1.11 | 890,859 | 0 | 890,859 | 778,768 | 0 | 778,768 |
| M | Total of safety boxes (+ 10% of extra need) needed | (K + L) / 100 x 1.11 | 69,220 | 0 | 69,220 | 52,600 | 0 | 52,600 |
| N | Cost of vaccines needed | I * vaccine price per dose | 1,926,180 | 0 | 1,926,180 | 1,683,822 | 0 | 1,683,822 |
| O | Cost of AD syringes needed | K * AD syringe price per unit | 283,293 | 0 | 283,293 | 209,876 | 0 | 209,876 |
| P | Cost of reconstitution syringes needed | L * reconstitution price per unit | 33,853 | 0 | 33,853 | 29,594 | 0 | 29,594 |
| Q | Cost of safety boxes needed | M * safety box price per unit | 44,301 | 0 | 44,301 | 33,664 | 0 | 33,664 |
| R | Freight cost for vaccines needed | N * freight cost as % of vaccines value | 192,618 | 0 | 192,618 | 168,383 | 0 | 168,383 |
| S | Freight cost for devices needed | (O + P + Q) * freight cost as % of devices value | 36,145 | 0 | 36,145 | 27,314 | 0 | 27,314 |
| T | Total fund needed | (N + O + P + Q + R + S) | 2,516,390 | 0 | 2,516,390 | 2,152,653 | 0 | 2,152,653 |
| U | Total country co-financing | I * country co-financing per dose | 0 |  |  | 0 |  |  |
| V | Country co-financing % of GAVI supported proportion | U / T | 0.00% |  |  | 0.00% |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Where (n) depends on the vaccine

# Table 1.1 D - Estimated number of doses for Measles, 10 doses/vial, Lyophilised associated injection safety material and related co-financing budget (page 2)

|  |  | Formula | 2014 |  |  | 2015 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Total | Government | GAVI | Total | Government | GAVI |
| A | Country Co-finance |  | 0.00% |  |  | 0.00% |  |  |
| B | Number of children to be vaccinated with the first dose[1] | Table 1 (baseline & annual targets) | 3,498,430 | 0 | 3,498,430 | 3,746,333 | 0 | 3,746,333 |
| C | Number of doses per child | Vaccine parameter (schedule) | 1 | 1 | 1 | 1 | 1 | 1 |
| D | Number of doses needed | B * C | 3,498,430 | 0 | 3,498,430 | 3,746,333 | 0 | 3,746,333 |
| E | Estimated vaccine wastage factor | Table 6.(n).3. in NVS section[2] | 2.00 | 2.00 | 2.00 | 2.00 | 2.00 | 2.00 |
| F | Number of doses needed including wastage | D * E | 6,996,860 | 0 | 6,996,860 | 7,492,666 | 0 | 7,492,666 |
| G | Vaccines buffer stock | (F - F of previous year) * 0.25 | 25,001 | 0 | 25,001 | 123,952 | 0 | 123,952 |
| I | Total vaccine doses needed | F + G | 7,021,861 | 0 | 7,021,861 | 7,616,618 | 0 | 7,616,618 |
| J | Number of doses per vial | Vaccine parameter | 10 | 10 | 10 | 10 | 10 | 10 |
| K | Number of AD syringes (+ 10% wastage) needed | (D + G) * 1.11 | 3,911,009 | 0 | 3,911,009 | 4,296,017 | 0 | 4,296,017 |
| L | Reconstitution syringes (+ 10% wastage) needed | I / J * 1.11 | 779,427 | 0 | 779,427 | 845,445 | 0 | 845,445 |
| M | Total of safety boxes (+ 10% of extra need) needed | (K + L) / 100 x 1.11 | 52,064 | 0 | 52,064 | 57,071 | 0 | 57,071 |
| N | Cost of vaccines needed | I * vaccine price per dose | 1,685,247 | 0 | 1,685,247 | 1,827,989 | 0 | 1,827,989 |
| O | Cost of AD syringes needed | K * AD syringe price per unit | 207,284 | 0 | 207,284 | 227,689 | 0 | 227,689 |
| P | Cost of reconstitution syringes needed | L * reconstitution price per unit | 29,619 | 0 | 29,619 | 32,127 | 0 | 32,127 |
| Q | Cost of safety boxes needed | M * safety box price per unit | 33,321 | 0 | 33,321 | 36,526 | 0 | 36,526 |
| R | Freight cost for vaccines needed | N * freight cost as % of vaccines value | 168,525 | 0 | 168,525 | 182,799 | 0 | 182,799 |
| S | Freight cost for devices needed | (O + P + Q) * freight cost as % of devices value | 27,023 | 0 | 27,023 | 29,635 | 0 | 29,635 |
| T | Total fund needed | (N + O + P + Q + R + S) | 2,151,019 | 0 | 2,151,019 | 2,336,765 | 0 | 2,336,765 |
| U | Total country co-financing | I * country co-financing per dose | 0 |  |  | 0 |  |  |
| V | Country co-financing % of GAVI supported proportion | U / T | 0.00% |  |  | 0.00% |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Where (n) depends on the vaccine

# Table 1.1 D -: Estimated number of doses for Measles, 10 doses/vial, Lyophilised associated injection safety material and related co-financing budget (page 3)

|  |  | Formula | 2016 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Total | Government | GAVI | Total | Government | GAVI |
| A | Country Co-finance |  | 0.00% |  |  |  |  |  |
| B | Number of children to be vaccinated with the first dose[1] | Table 1 (baseline & annual targets) | 3,800,655 | 0 | 3,800,655 |  |  |  |
| C | Number of doses per child | Vaccine parameter (schedule) | 1 | 1 | 1 | 1 | 1 | 1 |
| D | Number of doses needed | B * C | 3,800,655 | 0 | 3,800,655 |  |  |  |
| E | Estimated vaccine wastage factor | Table 6.(n).3. in NVS section[2] | 2.00 | 2.00 | 2.00 |  |  |  |
| F | Number of doses needed including wastage | D * E | 7,601,310 | 0 | 7,601,310 |  |  |  |
| G | Vaccines buffer stock | (F - F of previous year) * 0.25 | 27,161 | 0 | 27,161 |  |  |  |
| I | Total vaccine doses needed | F + G | 7,628,471 | 0 | 7,628,471 |  |  |  |
| J | Number of doses per vial | Vaccine parameter | 10 | 10 | 10 | 10 | 10 | 10 |
| K | Number of AD syringes (+ 10% wastage) needed | (D + G) * 1.11 | 4,248,876 | 0 | 4,248,876 |  |  |  |
| L | Reconstitution syringes (+ 10% wastage) needed | I / J * 1.11 | 846,761 | 0 | 846,761 |  |  |  |
| M | Total of safety boxes (+ 10% of extra need) needed | (K + L) / 100 x 1.11 | 56,562 | 0 | 56,562 |  |  |  |
| N | Cost of vaccines needed | I * vaccine price per dose | 1,830,834 | 0 | 1,830,834 |  |  |  |
| O | Cost of AD syringes needed | K * AD syringe price per unit | 225,191 | 0 | 225,191 |  |  |  |
| P | Cost of reconstitution syringes needed | L * reconstitution price per unit | 32,177 | 0 | 32,177 |  |  |  |
| Q | Cost of safety boxes needed | M * safety box price per unit | 36,200 | 0 | 36,200 |  |  |  |
| R | Freight cost for vaccines needed | N * freight cost as % of vaccines value | 183,084 | 0 | 183,084 |  |  |  |
| S | Freight cost for devices needed | (O + P + Q) * freight cost as % of devices value | 29,357 | 0 | 29,357 |  |  |  |
| T | Total fund needed | (N + O + P + Q + R + S) | 2,336,843 | 0 | 2,336,843 |  |  |  |
| U | Total country co-financing | I * country co-financing per dose | 0 |  |  |  |  |  |
| V | Country co-financing % of GAVI supported proportion | U / T | 0.00% |  |  |  |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Where (n) depends on the vaccine

# Annex 1.2 – Pneumococcal (PCV10), 2 doses/vial, Liquid

Table 1.2 A - Rounded up portion of supply that is procured by the country and estimate of related cost in US$

| Required supply item |  | 2012 | 2013 | 2014 | 2015 | 2016 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of vaccine doses | # |  | 684,800 | 598,700 | 640,700 | 641,700 |  |  |  |
| Number of AD syringes | # |  | 731,200 | 633,500 | 677,900 | 678,500 |  |  |  |
| Number of re-constitution syringes | # |  |  |  |  |  |  |  |  |
| Number of safety boxes | # |  | 8,125 | 7,050 | 7,525 | 7,550 |  |  |  |
| Total value to be co-financed by the country | $ |  | 2,565,000 | 2,242,500 | 2,399,500 | 2,403,000 |  |  |  |

Table 1.2  B - Rounded up portion of supply that is procured by GAVI and estimate of related cost in US$.

| Required supply item |  | 2012 | 2013 | 2014 | 2015 | 2016 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of vaccine doses | # |  | 12,139,100 | 10,611,700 | 11,355,600 | 11,373,200 |  |  |  |
| Number of AD syringes | # |  | 12,961,100 | 11,227,600 | 12,014,200 | 12,025,300 |  |  |  |
| Number of re-constitution syringes | # |  |  |  |  |  |  |  |  |
| Number of safety boxes | # |  | 143,875 | 124,625 | 133,375 | 133,500 |  |  |  |
| Total value to be co-financed by the country | $ |  | 45,468,500 | 39,740,000 | 42,526,000 | 42,591,500 |  |  |  |

Table 1.2  C - Summary table for Pneumococcal (PCV10), 2 doses/vial, Liquid

|  | Data from |  | 2012 | 2013 | 2014 | 2015 | 2016 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of Surviving infants | Table 1 | # |  | 3,831,587 | 3,887,145 | 3,943,508 | 4,000,689 |  |  |  |
| Number of children to be vaccinated with the third dose[1] | Table 1 | # |  | 3,180,217 | 3,420,687 | 3,667,463 | 3,720,641 |  |  |  |
| Immunisation coverage with the last dose | Table 1 | # |  | 83.00% | 88.00% | 93.00% | 93.00% |  |  |  |
| Number of children to be vaccinated with the first dose | Table 1 | # |  | 3,256,849 | 3,498,430 | 3,746,333 | 3,800,655 |  |  |  |
| Number of doses per child |  | # |  | 3 | 3 | 3 | 3 |  |  |  |
| Estimated vaccine wastage factor | Table 6.(n).3[2] | # |  | 1.05 | 1.05 | 1.05 | 1.05 |  |  |  |
| Number of doses per vial |  | # |  | 2 | 2 | 2 | 2 |  |  |  |
| AD syringes required |  | # |  | Yes | Yes | Yes | Yes |  |  |  |
| Reconstitution syringes required |  | # |  | No | No | No | No |  |  |  |
| Safety boxes required |  | # |  | Yes | Yes | Yes | Yes |  |  |  |
| Vaccine price per dose |  | $ |  | 3.500 | 3.500 | 3.500 | 3.500 |  |  |  |
| Country co-financing per dose | Table 6.(n).2[2] | $ |  | 0.20 | 0.20 | 0.20 | 0.20 |  |  |  |
| AD syringe price per unit |  | $ |  | 0.053 | 0.053 | 0.053 | 0.053 |  |  |  |
| Reconstitution syringe price per unit |  | $ |  |  |  |  |  |  |  |  |
| Safety box price per unit |  | $ |  | 0.640 | 0.640 | 0.640 | 0.640 |  |  |  |
| Freight cost as % of vaccines value |  | % |  | 5.00 | 5.00 | 5.00 | 5.00 |  |  |  |
| Freight cost as % of devices value |  | % |  | 10.00 | 10.00 | 10.00 | 10.00 |  |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Where (n) depends on the vaccine

# Table 1.2 D - Estimated number of doses for Pneumococcal (PCV10), 2 doses/vial, Liquid associated injection safety material and related co-financing budget (page 1)

|  |  | Formula | 2013 |  |  | 2014 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Total | Government | GAVI | Total | Government | GAVI |
| A | Country Co-finance |  | 5.34% |  |  | 5.34% |  |  |
| B | Number of children to be vaccinated with the first dose[1] | Table 1 (baseline & annual targets) | 3,256,849 | 173,904 | 3,082,945 | 3,498,430 | 186,835 | 3,311,595 |
| C | Number of doses per child | Vaccine parameter | 3 | 3 | 3 | 3 | 3 | 3 |
| D | Number of doses needed | B * C | 9,770,547 | 521,710 | 9,248,837 | 10,495,290 | 560,504 | 9,934,786 |
| E | Estimated vaccine wastage factor | Table 6.(n).3. in NVS section[2] | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 |
| F | Number of doses needed including wastage | D * E | 10,259,075 | 547,795 | 9,711,280 | 11,020,055 | 588,529 | 10,431,526 |
| G | Vaccines buffer stock | (F - F of previous year) * 0.25 | 2,564,769 | 136,949 | 2,427,820 | 190,245 | 10,161 | 180,084 |
| I | Total vaccine doses needed | F + G | 12,823,844 | 684,744 | 12,139,100 | 11,210,300 | 598,689 | 10,611,611 |
| J | Number of doses per vial | Vaccine parameter | 2 | 2 | 2 | 2 | 2 | 2 |
| K | Number of AD syringes (+ 10% wastage) needed | (D + G) * 1.11 | 13,692,201 | 731,111 | 12,961,090 | 11,860,944 | 633,437 | 11,227,507 |
| L | Reconstitution syringes (+ 10% wastage) needed | I / J * 1.11 |  |  |  |  |  |  |
| M | Total of safety boxes (+ 10% of extra need) needed | (K + L) / 100 x 1.11 | 151,984 | 8,116 | 143,868 | 131,657 | 7,032 | 124,625 |
| N | Cost of vaccines needed | I * vaccine price per dose | 44,883,454 | 2,396,602 | 42,486,852 | 39,236,050 | 2,095,411 | 37,140,639 |
| O | Cost of AD syringes needed | K * AD syringe price per unit | 725,687 | 38,749 | 686,938 | 628,631 | 33,573 | 595,058 |
| P | Cost of reconstitution syringes needed | L * reconstitution price per unit |  |  |  |  |  |  |
| Q | Cost of safety boxes needed | M * safety box price per unit | 97,270 | 5,194 | 92,076 | 84,261 | 4,500 | 79,761 |
| R | Freight cost for vaccines needed | N * freight cost as % of vaccines value | 2,244,173 | 119,831 | 2,124,342 | 1,961,803 | 104,771 | 1,857,032 |
| S | Freight cost for devices needed | (O + P + Q) * freight cost as % of devices value | 82,296 | 4,395 | 77,901 | 71,290 | 3,808 | 67,482 |
| T | Total fund needed | (N + O + P + Q + R + S) | 48,032,880 | 2,564,769 | 45,468,111 | 41,982,035 | 2,242,060 | 39,739,975 |
| U | Total country co-financing | I * country co-financing per dose | 2,564,769 |  |  | 2,242,060 |  |  |
| V | Country co-financing % of GAVI supported proportion | U / T | 5.34% |  |  | 5.34% |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Where (n) depends on the vaccine

# Table 1.2 D - Estimated number of doses for Pneumococcal (PCV10), 2 doses/vial, Liquid associated injection safety material and related co-financing budget (page 2)

|  |  | Formula | 2015 |  |  | 2016 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Total | Government | GAVI | Total | Government | GAVI |
| A | Country Co-finance |  | 5.34% |  |  | 5.34% |  |  |
| B | Number of children to be vaccinated with the first dose[1] | Table 1 (baseline & annual targets) | 3,746,333 | 200,074 | 3,546,259 | 3,800,655 | 202,978 | 3,597,677 |
| C | Number of doses per child | Vaccine parameter (schedule) | 3 | 3 | 3 | 3 | 3 | 3 |
| D | Number of doses needed | B * C | 11,238,999 | 600,222 | 10,638,777 | 11,401,965 | 608,933 | 10,793,032 |
| E | Estimated vaccine wastage factor | Table 6.(n).3. in NVS section[2] | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 |
| F | Number of doses needed including wastage | D * E | 11,800,949 | 630,233 | 11,170,716 | 11,972,064 | 639,379 | 11,332,685 |
| G | Vaccines buffer stock | (F - F of previous year) * 0.25 | 195,224 | 10,426 | 184,798 | 42,779 | 2,285 | 40,494 |
| I | Total vaccine doses needed | F + G | 11,996,173 | 640,659 | 11,355,514 | 12,014,843 | 641,664 | 11,373,179 |
| J | Number of doses per vial | Vaccine parameter | 2 | 2 | 2 | 2 | 2 | 2 |
| K | Number of AD syringes (+ 10% wastage) needed | (D + G) * 1.11 | 12,691,988 | 677,820 | 12,014,168 | 12,703,666 | 678,451 | 12,025,215 |
| L | Reconstitution syringes (+ 10% wastage) needed | I / J * 1.11 |  |  |  |  |  |  |
| M | Total of safety boxes (+ 10% of extra need) needed | (K + L) / 100 x 1.11 | 140,882 | 7,524 | 133,358 | 141,011 | 7,531 | 133,480 |
| N | Cost of vaccines needed | I * vaccine price per dose | 41,986,606 | 2,242,306 | 39,744,300 | 42,051,951 | 2,245,823 | 39,806,128 |
| O | Cost of AD syringes needed | K * AD syringe price per unit | 672,676 | 35,925 | 636,751 | 673,295 | 35,958 | 637,337 |
| P | Cost of reconstitution syringes needed | L * reconstitution price per unit |  |  |  |  |  |  |
| Q | Cost of safety boxes needed | M * safety box price per unit | 90,165 | 4,816 | 85,349 | 90,248 | 4,820 | 85,428 |
| R | Freight cost for vaccines needed | N * freight cost as % of vaccines value | 2,099,331 | 112,116 | 1,987,215 | 2,102,598 | 112,292 | 1,990,306 |
| S | Freight cost for devices needed | (O + P + Q) * freight cost as % of devices value | 76,285 | 4,075 | 72,210 | 76,355 | 4,078 | 72,277 |
| T | Total fund needed | (N + O + P + Q + R + S) | 44,925,063 | 2,399,235 | 42,525,828 | 44,994,447 | 2,402,969 | 42,591,478 |
| U | Total country co-financing | I * country co-financing per dose | 2,399,235 |  |  | 2,402,969 |  |  |
| V | Country co-financing % of GAVI supported proportion | U / T | 5.34% |  |  | 5.34% |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Where (n) depends on the vaccine

# Annex 2

Estimated prices of supply and related freight cost: 2011 from UNICEF Supply Division; 2012 onwards: GAVI Secretariat

Table A - Commodities Cost

| Vaccine | Presentation | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| AD syringe | 0 | 0.053 | 0.053 | 0.053 | 0.053 | 0.053 | 0.053 | 0.053 |
| DTP-HepB | 2 | 1.600 |  |  |  |  |  |  |
| DTP-HepB | 10 | 0.620 | 0.620 | 0.620 | 0.620 | 0.620 | 0.620 | 0.620 |
| DTP-HepB-Hib | WAP | 2.580 | 2.470 | 2.320 | 2.030 | 1.850 | 1.850 | 1.850 |
| DTP-HepB-Hib | WAP | 2.580 | 2.470 | 2.320 | 2.030 | 1.850 | 1.850 | 1.850 |
| DTP-HepB-Hib | WAP | 2.580 | 2.470 | 2.320 | 2.030 | 1.850 | 1.850 | 1.850 |
| DTP-Hib | 10 | 3.400 | 3.400 | 3.400 | 3.400 | 3.400 | 3.200 | 3.200 |
| HepB monoval | 1 |  |  |  |  |  |  |  |
| HepB monoval | 2 |  |  |  |  |  |  |  |
| Hib monoval | 1 | 3.400 |  |  |  |  |  |  |
| Measles | 10 | 0.240 | 0.240 | 0.240 | 0.240 | 0.240 | 0.240 | 0.240 |
| Pneumococcal(PCV10) | 2 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 |
| Pneumococcal(PCV13) | 1 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 |
| Reconstit syringe for Pentaval (2ml) | 0 | 0.032 | 0.032 | 0.032 | 0.032 | 0.032 | 0.032 | 0.032 |
| Reconstit syringe for YF | 0 | 0.038 | 0.038 | 0.038 | 0.038 | 0.038 | 0.038 | 0.038 |
| Rotavirus 2-dose schedule | 1 | 7.500 | 6.000 | 5.000 | 4.000 | 3.600 | 3.600 | 3.600 |
| Rotavirus 3-dose schedule | 1 | 5.500 | 4.000 | 3.333 | 2.667 | 2.400 | 2.400 | 2.400 |
| Safety box | 0 | 0.640 | 0.640 | 0.640 | 0.640 | 0.640 | 0.640 | 0.640 |
| Yellow Fever | WAP | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 |
| Yellow Fever | WAP | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 |

Note: WAP - weighted average price (to be used for any presentation: For DTP-HepB-Hib, it applies to 1 dose liquid, 2 dose lyophilised and 10 dose liquid. For Yellow Fever, it applies to 5 dose lyophilised and 10 dose lyophilised)

Table B - Commodities Freight Cost

| Vaccines | Group | No Threshold | 200’000 $ |  | 250’000 $ |  | 2’000’000 $ |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | <= | > | <= | > | <= | > |
| Yellow Fever | Yellow Fever |  | 20% |  |  |  | 10% | 5% |
| DTP+HepB | HepB and or Hib | 2% |  |  |  |  |  |  |
| DTP-HepB-Hib | HepB and or Hib |  |  |  | 15% | 3,50% |  |  |
| Pneumococcal vaccine (PCV10) | Pneumococcal | 5% |  |  |  |  |  |  |
| Pneumococcal vaccine (PCV13) | Pneumococcal | 5% |  |  |  |  |  |  |
| Rotavirus | Rotavirus | 5% |  |  |  |  |  |  |
| Measles | Measles | 10% |  |  |  |  |  |  |

Table C - Low - Minimum country's co-payment per dose of co-financed vaccine.

| vaccine | 2012 | 2013 | 2014 | 2015 | 2016 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Measles, 10 doses/vial, Lyophilised | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |  |  |
| Pneumococcal(PCV10), 2 doses/vial, Liquid |  | 0.20 | 0.20 | 0.20 | 0.20 |  |  |

Table D - Wastage rates and factors

Countries are expected to plan for a maximal wastage rate of:

- 50% - for a lyophilised vaccine in 10 or 20-dose vial,

- 25% - for a liquid vaccine in 10 or 20-dose vial or a lyophilised vaccine in 5-dose vial,

- 10% - for a lyophilised/liquid vaccine in 2-dose vial, and

- 5% - for a liquid vaccine in 1-dose vial

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2 | 2.22 | 2.5 |

WHO International shipping guidelines: maximum packed volumes of vaccines

Table E - Vaccine maximum packed volumes

| Vaccine product | Designation | Vaccine formulation | Admin route | No. Of doses in the schedule | Presentation (doses/vial, prefilled) | Packed volume vaccine (cm3/dose) | Packed volume diluents (cm3/dose) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| BCG | BCG | lyophilized | ID | 1 | 20 | 1.2 | 0.7 |
| Diphtheria-Tetanus-Pertussis | DTP | liquid | IM | 3 | 20 | 2.5 |  |
| Diphtheria-Tetanus-Pertussis | DTP | liquid | IM | 3 | 10 | 3.0 |  |
| Diphtheria-Tetanus | DT | liquid | IM | 3 | 10 | 3.0 |  |
| Tetanus-Diphtheria | Td | liquid | IM | 2 | 10 | 3.0 |  |
| Tetanus Toxoid | TT | liquid | IM | 2 | 10 | 3.0 |  |
| Tetanus Toxoid | TT | liquid | IM | 2 | 20 | 2.5 |  |
| Tetanus Toxoid UniJect | TT | liquid | IM | 2 | Uniject | 12.0 |  |
| Measles | Measles | lyophilized | SC | 1 | 1 | 26.1 | 20.0 |
| Measles | Measles | lyophilized | SC | 1 | 2 | 13.1 | 13.1 |
| Measles | Measles | lyophilized | SC | 1 | 5 | 5.2 | 7.0 |
| Measles | Measles | lyophilized | SC | 1 | 10 | 3.5 | 4.0 |
| Measles-Rubella freeze dried | MR | lyophilized | SC | 1 | 1 | 26.1 | 26.1 |
| Measles-Rubella freeze dried | MR | lyophilized | SC | 1 | 2 | 13.1 | 13.1 |
| Measles-Rubella freeze dried | MR | lyophilized | SC | 1 | 5 | 5.2 | 7.0 |
| Measles-Rubella freeze dried | MR | lyophilized | SC | 1 | 10 | 2.5 | 4.0 |
| Measles-Mumps-Rubella freeze dried | MMR | lyophilized | SC | 1 | 1 | 26.1 | 26.1 |
| Measles-Mumps-Rubella freeze dried | MMR | lyophilized | SC | 1 | 2 | 13.1 | 13.1 |
| Measles-Mumps-Rubella freeze dried | MMR | lyophilized | SC | 1 | 5 | 5.2 | 7.0 |
| Measles-Mumps-Rubella freeze dried | MMR | lyophilized | SC | 1 | 10 | 3.0 | 4.0 |
| Polio | OPV | liquid | Oral | 4 | 10 | 2.0 |  |
| Polio | OPV | liquid | Oral | 4 | 20 | 1.0 |  |
| Yellow fever | YF | lyophilized | SC | 1 | 5 | 6.5 | 7.0 |
| Yellow fever | YF | lyophilized | SC | 1 | 10 | 2.5 | 3.0 |
| Yellow fever | YF | lyophilized | SC | 1 | 20 | 1.5 | 2.0 |
| Yellow fever | YF | lyophilized | SC | 1 | 50 | 0.7 | 1.0 |
| DTP-HepB combined | DTP-HepB | liquid | IM | 3 | 1 | 9.7 |  |
| DTP-HepB combined | DTP-HepB | liquid | IM | 3 | 2 | 6.0 |  |
| DTP-HepB combined | DTP-HepB | liquid | IM | 3 | 10 | 3.0 |  |
| Hepatitis B | HepB | liquid | IM | 3 | 1 | 18.0 |  |
| Hepatitis B | HepB | liquid | IM | 3 | 2 | 13.0 |  |
| Hepatitis B | HepB | liquid | IM | 3 | 6 | 4.5 |  |
| Hepatitis B | HepB | liquid | IM | 3 | 10 | 4.0 |  |
| Hepatitis B UniJect | HepB | liquid | IM | 3 | Uniject | 12.0 |  |
| Hib liquid | Hib_liq | liquid | IM | 3 | 1 | 15.0 |  |
| Hib liquid | Hib_liq | liquid | IM | 3 | 10 | 2.5 |  |
| Hib freeze-dried | Hib_lyo | lyophilized | IM | 3 | 1 | 13.0 | 35.0 |
| Hib freeze-dried | Hib_lyo | lyophilized | IM | 3 | 2 | 6.0 |  |
| Hib freeze-dried | Hib_lyo | lyophilized | IM | 3 | 10 | 2.5 | 3.0 |
| DTP liquid + Hib freeze-dried | DTP+Hib | liquid+lyop. | IM | 3 | 1 | 45.0 |  |
| DTP-Hib combined liquid | DTP+Hib | liquid+lyop. | IM | 3 | 10 | 12.0 |  |
| DTP-Hib combined liquid | DTP-Hib | liquid | IM | 3 | 1 | 32.3 |  |
| DTP-HepB liquid + Hib freeze-dried | DTP-Hib | liquid | IM | 3 | 10 | 2.5 |  |
| DTP-HepB liquid + Hib freeze-dried | DTP-HepB+Hib | liquid+lyop. | IM | 3 | 1 | 22.0 |  |
| DTP-HepB-Hib liquid | DTP-HepB+Hib | liquid+lyop. | IM | 3 | 2 | 11.0 |  |
| DTP-HepB-Hib liquid | DTP-HepB-Hib | liquid | IM | 3 | 10 | 4.4 |  |
| DTP-HepB-Hib liquid | DTP-HepB-Hib | liquid | IM | 3 | 2 | 13.1 |  |
| DTP-HepB-Hib liquid | DTP-HepB-Hib | liquid | IM | 3 | 1 | 19.2 |  |
| Meningitis A/C | MV_A/C | lyophilized | SC | 1 | 10 | 2.5 | 4.0 |
| Meningitis A/C | MV_A/C | lyophilized | SC | 1 | 50 | 1.5 | 3.0 |
| Meningococcal A/C/W/ | MV_A/C/W | lyophilized | SC | 1 | 50 | 1.5 | 3.0 |
| Meningococcal A/C/W/Y | MV_A/C/W/Y | lyophilized | SC | 1 | 10 | 2.5 | 4.0 |
| Meningitis W135 | MV_W135 | lyophilized | SC | 1 | 10 | 2.5 | 4.0 |
| Meningitis A conjugate | Men_A | lyophilized | SC | 2 | 10 | 2.6 | 4.0 |
| Japanese Encephalitis | JE_lyo | lyophilized | SC | 3 | 10 | 15.0 |  |
| Japanese Encephalitis | JE_lyo | lyophilized | SC | 3 | 10 | 8.1 | 8.1 |
| Japanese Encephalitis | JE_lyo | lyophilized | SC | 3 | 5 | 2.5 | 2.9 |
| Japanese Encephalitis | JE_lyo | lyophilized | SC | 3 | 1 | 12.6 | 11.5 |
| Japanese Encephalitis | JE_liq | liquid | SC | 3 | 10 | 3.4 |  |
| Rota vaccine | Rota_lyo | lyophilized | Oral | 2 | 1 | 156.0 |  |
| Rota vaccine | Rota_liq | liquid | Oral | 2 | 1 | 17.1 |  |
| Rota vaccine | Rota_liq | liquid | Oral | 3 | 1 | 45.9 |  |
| Pneumo. conjugate vaccine 7-valent | PCV-7 | liquid | IM | 3 | PFS | 55.9 |  |
| Pneumo. conjugate vaccine 7-valent | PCV-7 | liquid | IM | 3 | 1 | 21.0 |  |
| Pneumo. conjugate vaccine 10-valent | PCV-10 | liquid | IM | 3 | 1 | 11.5 |  |
| Pneumo. conjugate vaccine 10-valent | PCV-10 | liquid | IM | 3 | 2 | 4.8 |  |
| Pneumo. conjugate vaccine 13-valent | PCV-13 | liquid | IM | 3 | 1 | 12.0 |  |
| Polio inactivated | IPV | liquid | IM | 3 | PFS | 107.4 |  |
| Polio inactivated | IPV | liquid | IM | 3 | 10 | 2.5 |  |
| Polio inactivated | IPV | liquid | IM | 3 | 1 | 15.7 |  |
| Human Papilomavirus vaccine | HPV | liquid | IM | 3 | 1 | 15.0 |  |
| Human Papilomavirus vaccine | HPV | liquid | IM | 3 | 2 | 5.7 |  |
| Monovalent OPV-1 | mOPV1 | liquid | Oral |  | 20 | 1.5 |  |
| Monovalent OPV-3 | mOPV3 | liquid | Oral |  | 20 | 1.5 |  |

# Attachments

# List of Supporting Documents Attached to this Proposal

| Document | Section | Document Number | Mandatory[1] |
| --- | --- | --- | --- |
| MoH Signature (or delegated authority) of Proposal |  | 8 | Yes |
| MoF Signature (or delegated authority) of Proposal |  | 9 | Yes |
| Signatures of ICC or HSCC or equivalent in Proposal |  | 7 | Yes |
| Minutes of ICC/HSCC meeting endorsing Proposal |  | 1 | Yes |
| comprehensive Multi Year Plan - cMYP |  | 3 | Yes |
| cMYP Costing tool for financial analysis |  | 4 | Yes |
| Minutes of last three ICC/HSCC meetings |  | 10, 11 | Yes |
| Improvement plan based on EVM |  | 12 | Yes |
| WHO/UNICEF Joint Reporting Form (JRF) |  |  |  |
| ICC/HSCC workplan for forthcoming 12 months |  | 14 |  |
| National policy on injection safety |  |  |  |
| Action plans for improving injection safety |  |  |  |
| Plan for NVS introduction (if not part of cMYP) |  |  |  |
| Banking details |  | 6 |  |

[1] Please indicate the duration of the plan / assessment / document where appropriate

# Attachments

List of all the mandatory and optional documents attached to this form

Note: Use the Upload file arrow icon to upload the document. Use the Delete item icon to delete a line. To add new lines click on the New item icon in the Action column.

| ID | File type | File name |  | New file | Actions |
| --- | --- | --- | --- | --- | --- |
|  | Description | Date and Time | Size |  |  |
| 1 | File Type: Minutes of ICC/HSCC meeting endorsing Proposal * File Desc: | File name: Document 1.PDF Date/Time: 12.05.2011 03:58:55 Size: 978 KB |  |  |  |
| 2 | File Type: other File Desc: Minutes of National Committee for Immunization Practices | File name: Document 2.PDF Date/Time: 12.05.2011 04:00:35 Size: 1 MB |  |  |  |
| 3 | File Type: comprehensive Multi Year Plan - cMYP * File Desc: | File name: Dcoument 3 cMYP Bangladesh 2011-2016.pdf Date/Time: 12.05.2011 04:03:00 Size: 2 MB |  |  |  |
| 4 | File Type: cMYP Costing tool for financial analysis * File Desc: | File name: Dcoument 4 BNG cMYP Costing 2011 Final.xlsm Date/Time: 12.05.2011 04:05:11 Size: 1 MB |  |  |  |
| 5 | File Type: other File Desc: EVM Assessment Report and Improvement Plan | File name:Document 5 EVM Assessment Report and Improvement Plan - Bangladesh 2011.pdf Date/Time: 12.05.2011 04:07:52 Size: 1 MB |  |  |  |
| 6 | File Type: Banking details File Desc: | File name: Document 6.PDF Date/Time: 12.05.2011 04:10:00 Size: 374 KB |  |  |  |
| 7 | File Type: Signatures of ICC or HSCC or equivalent in Proposal * File Desc: | File name: Signature.PDF Date/Time: 12.05.2011 04:13:38 Size: 444 KB |  |  |  |
| 8 | File Type: MoH Signature (or delegated authority) of Proposal * File Desc: | File name: Signature.PDF Date/Time: 12.05.2011 04:14:50 Size: 444 KB |  |  |  |
| 9 | File Type: MoF Signature (or delegated authority) of Proposal * File Desc: | File name: Signature.PDF Date/Time: 12.05.2011 04:15:25 Size: 444 KB |  |  |  |
| 10 | File Type: Minutes of last three ICC/HSCC meetings * File Desc: | File name: Document 1 ICC 2.PDF Date/Time: 12.05.2011 04:26:03 Size: 891 KB |  |  |  |
| 11 | File Type: Minutes of last three ICC/HSCC meetings * File Desc: | File name: Document 1 ICC 3.PDF Date/Time: 12.05.2011 04:27:26 Size: 807 KB |  |  |  |
| 12 | File Type: Improvement plan based on EVM * File Desc: | File name: EVM Bangladesh+2011.pdf Date/Time: 09.06.2011 04:08:37 Size: 1 MB |  |  |  |
| 13 | File Type: other File Desc: WHO recommendation email for introduction of MSD 2nd dose (1) | File name: Fw Bangladesh new vaccine Application proposal to include 2nd dose of Measles Vaccine into EPI schedule.htm Date/Time: 16.06.2011 02:56:29 Size: 40 KB |  |  |  |
| 14 | File Type: ICC/HSCC workplan for forthcoming 12 months File Desc: EPI annual workplan | File name: Bangladesh Annual workplan.pdf Date/Time: 17.06.2011 04:01:27 Size: 3 MB |  |  |  |
| 15 | File Type: other File Desc: WHO recommendation email for introduction of MSD 2nd dose (2) | File name: Bangladesh new vaccine Application proposal to include 2nd dose of Measles Vaccine into EPI schedule.htm Date/Time: 17.06.2011 04:35:59 Size: 33 KB |  |  |  |

REPLY TO CONDITIONS BY BANGLADESH RELATED TO PCV VACCINE

REVIEWED BY IRC in FEB 2012