GAVI Alliance

Application Form for Country Proposals

For Support to New and Under-Used Vaccines (NVS)

Submitted by

The Government of

Kiribati

Date of submission: Not submitted yet

Deadline for submission: 1 Jun 2011

Select Start and End Year of your Comprehensive Multi-Year Plan (cMYP)

| Start Year | 2011 | End Year | 2015 |
| --- | --- | --- | --- |

Revised in January 2011

(To be used with Guidelines of December 2010)

Please submit the Proposal using the online platform https://AppsPortal.gavialliance.org/PDExtranet.

Enquiries to: proposals@gavialliance.org or representatives of a GAVI partner agency. The documents can be shared with GAVI partners, collaborators and general public. The Proposal and attachments must be submitted in English, French, Spanish, or Russian.

Note: Please ensure that the application has been received by the GAVI Secretariat on or before the day of the deadline.

The GAVI Secretariat is unable to return submitted documents and attachments to countries. Unless otherwise specified, documents will be shared with the GAVI Alliance partners and the general public.

GAVI ALLIANCE GRANT TERMS AND CONDITIONS FUNDING USED SOLELY FOR APPROVED PROGRAMMES The applicant country (“Country”) confirms that all funding provided by the GAVI Alliance will be used and applied for the sole purpose of fulfilling the programme(s) described in the Country’s application. Any significant change from the approved programme(s) must be reviewed and approved in advance by the GAVI Alliance. All funding decisions for the application are made at the discretion of the GAVI Alliance Board and are subject to IRC processes and the availability of funds. AMENDMENT TO THE APPLICATION The Country will notify the GAVI Alliance in its Annual Progress Report if it wishes to propose any change to the programme(s) description in its application. The GAVI Alliance will document any change approved by the GAVI Alliance, and the Country’s application will be amended. RETURN OF FUNDS The Country agrees to reimburse to the GAVI Alliance all funding amounts that are not used for the programme(s) described in its application. The country’s reimbursement must be in US dollars and be provided, unless otherwise decided by the GAVI Alliance, within sixty (60) days after the Country receives the GAVI Alliance’s request for a reimbursement and be paid to the account or accounts as directed by the GAVI Alliance. SUSPENSION/ TERMINATION The GAVI Alliance may suspend all or part of its funding to the Country if it has reason to suspect that funds have been used for purpose other than for the programmes described in the Country’s application, or any GAVI Alliance-approved amendment to the application. The GAVI Alliance retains the right to terminate its support to the Country for the programmes described in its application if a misuse of GAVI Alliance funds is confirmed. ANTICORRUPTION The Country confirms that funds provided by the GAVI Alliance shall not be offered by the Country to any third person, nor will the Country seek in connection with its application any gift, payment or benefit directly or indirectly that could be construed as an illegal or corrupt practice. AUDITS AND RECORDS The Country will conduct annual financial audits, and share these with the GAVI Alliance, as requested. The GAVI Alliance reserves the right, on its own or through an agent, to perform audits or other financial management assessment to ensure the accountability of funds disbursed to the Country. The Country will maintain accurate accounting records documenting how GAVI Alliance funds are used. The Country will maintain its accounting records in accordance with its government-approved accounting standards for at least three years after the date of last disbursement of GAVI Alliance funds. If there is any claims of misuse of funds, Country will maintain such records until the audit findings are final. The Country agrees not to assert any documentary privilege against the GAVI Alliance in connection with any audit. CONFIRMATION OF LEGAL VALIDITY The Country and the signatories for the Country confirm that its application, and Annual Progress Report, are accurate and correct and form legally binding obligations on the Country, under the Country’s law, to perform the programmes described in its application, as amended, if applicable, in the APR. CONFIRMATION OF COMPLIANCE WITH THE GAVI ALLIANCE TRANSPARANCY AND ACCOUNTABILITY POLICY The Country confirms that it is familiar with the GAVI Alliance Transparency and Accountability Policy (TAP) and complies with the requirements therein. USE OF COMMERCIAL BANK ACCOUNTS The Country is responsible for undertaking the necessary due diligence on all commercial banks used to manage GAVI cash-based support. The Country confirms that it will take all responsibility for replenishing GAVI cash support lost due to bank insolvency, fraud or any other unforeseen event. ARBITRATION Any dispute between the Country and the GAVI Alliance arising out of or relating to its application that is not settled amicably within a reasonable period of time, will be submitted to arbitration at the request of either the GAVI Alliance or the Country. The arbitration will be conducted in accordance with the then-current UNCITRAL Arbitration Rules. The parties agree to be bound by the arbitration award, as the final adjudication of any such dispute. The place of arbitration will be Geneva, Switzerland. The language of the arbitration will be English. For any dispute for which the amount at issue is US$ 100,000 or less, there will be one arbitrator appointed by the GAVI Alliance. For any dispute for which the amount at issue is greater than US $100,000 there will be three arbitrators appointed as follows: The GAVI Alliance and the Country will each appoint one arbitrator, and the two arbitrators so appointed will jointly appoint a third arbitrator who shall be the chairperson. The GAVI Alliance will not be liable to the country for any claim or loss relating to the programmes described in the application, including without limitation, any financial loss, reliance claims, any harm to property, or personal injury or death. Country is solely responsible for all aspects of managing and implementing the programmes described in its application.

# Application Specification

Please specify for which type of GAVI support you would like to apply to.

Important note: To enable proper functioning of the form, please first select the cMYP years on the previous page.

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Type of Support | Vaccine | Start Year | End Year | Preferred second presentation[1] | Action |
| --- | --- | --- | --- | --- | --- |
| New Vaccines Support | Pneumococcal (PCV13), 1 doses/vial, Liquid | 2012 | 2015 | Pneumococcal (PCV10), 2 doses/vial, Liquid |  |

[1] This "Preferred second presentation" will be used in case there is no supply available for the preferred presentation of the selected vaccine ("Vaccine" column). If left blank, it will be assumed that the country will prefer waiting until the selected vaccine becomes available.

# Table of Contents

Sections

Main

Cover Page

GAVI Alliance Grants Terms and Conditions

1. Application Specification

2. Table of Contents

3. Executive Summary

4. Signatures

4.1. Signatures of the Government and National Coordinating Bodies

4.1.1. Government and the Inter-Agency Coordinating Committee for Immunisation

4.1.2. National Coordinating Body - Inter-Agency Coordinating Committee for Immunisation

4.1.3. The Inter-Agency Coordinating Committee for Immunisation

4.2. National Immunization Technical Advisory Group for Immunisation

4.2.1. The NITAG Group for Immunisation

5. Immunisation Programme Data

5.1. Basic facts

5.2. Current vaccination schedule

5.3. Trends of immunisation coverage and disease burden

5.4. Baseline and Annual Targets

Table 1: baseline figures

5.5. Summary of current and future immunisation budget

5.6. Summary of current and future financing and sources of funds

6. NVS

6.1. Capacity and cost (for positive storage)

6.2. Assessment of burden of relevant diseases (if available)

6.3.1. Requested vaccine ( Pneumococcal (PCV13), 1 doses/vial, Liquid )

6.3.2. Co-financing information

6.3.3. Wastage factor

6.3.4. Specifications of vaccinations with new vaccine

6.3.5. Portion of supply to be procured by the country (and cost estimate, US$)

6.3.6. Portion of supply to be procured by the GAVI Alliance (and cost estimate, US$)

6.3.7. New and Under-Used Vaccine Introduction Grant

7. Procurement and Management of New and Under-Used Vaccines

7.1. Vaccine management (EVSM/EVM/VMA)

8. Additional Comments and Recommendations

9. Annexes

Annex 1

Annex 1.1 - Pneumococcal (PCV13), 1 doses/vial, Liquid

Table 1.1  A - Rounded up portion of supply that is procured by the country and estimate of related cost in US$

Table 1.1  B - Rounded up portion of supply that is procured by GAVI and estimate of related cost in US$.

Table 1.1  C - Summary table for vaccine Pneumococcal (PCV13), 1 doses/vial, Liquid

Table 1.1  D - Estimated number of doses for vaccine Pneumococcal (PCV13), 1 doses/vial, Liquid associated injection safety material and related co-financing budget

Annex 2

10. Attachments

10.1 Documents required for NVS support

10.2 Attachments

Banking Form

# Executive Summary

3.	Executive Summary
Introduction – Country Background
The Republic of Kiribati is located in the South Pacific with a total population of 93,577 and a birth cohort of 2,665 in 2009 (JRF Data). This population is scattered on 23 inhabited islands over a vast ocean area covering 3.5 million square kilometres. There are great challenges in improving population’s health due to geographical isolation and remote and less developed social and economic conditions and the threats of climate change. (The low-lying atolls of Kiribati, rising no higher than three meters above sea-level, makes the country very vulnerable to rises in sea-level).

Infant mortality was estimated at 52 per 1,000 live births in 2003– among the highest in the Pacific. A more recent estimate from 2008 indicates the infant mortality rate has declined to 38 per 1000 live births (WHO World Health Statistics Report 2010). Reported coverage of DTP3 was estimated as 86.4% in 2006. There has been a steady improvement in health indicators over the last decade, but people in Kiribati still have a shorter life span than those in most other Pacific islands. WHO estimates Kiribati’s under-5 mortality rate in 2008 at 48 per 1000 live births (WHS 2010). This rate places Kiribati in the “high-mid” under-5 mortality quartile. UNICEF published an under-5 mortality estimate for 2009 of 46 per 1000 live births (IGME 2010). In 2008, life expectancy at birth was estimated at 58.9 for males and 63.1 for females.

Since 2007 the Government has financed the second dose of Measles and Rubella vaccine into its routine EPI services. The Government of Kiribati has been receiving active support from the Global Alliance for Vaccines and Immunization (GAVI) for Haemophilus influenzae type b (Hib) vaccine, which was integrated into its current immunization program in August 2008. Through the GARDASIL® Access Program, the Australian Cervical Cancer Foundation (ACCF) has facilitated a donation of HPV vaccine to Kiribati to immunize school age girls in 2011. The Government continues to explore ways to sustain that introduction in future years. 

The Government of Kiribati would like to apply now to GAVI for the introduction of 1-dose pneumoccocal vaccine (PCV13), targetting an introduction date of July 2012.

Disease Burden
In the absence of vaccination, Streptococcus pneumoniae (pneumococcus) and Haemophilus influenzae are the most common causes of pneumonia death in children, and are also common causes of childhood meningitis and sepsis. Hib vaccine was already introduced in Kiribati, leaving pneumococcus as the most important cause of child pneumonia and meningitis.There is no specific pneumococcus disease surveillance or special disease burden studies undertaken in Kiribati. However, WHO estimates that in 2000, pneumococcus caused 102 cases of pneumonia, 3 cases of meningitis, and 14 cases of other invasive disease among children under 5 years old in Kiribati, resulting in 7 deaths (Updated estimates for 2008 are under preparation but not yet available). In addition, pneumococcal infection is also estimated to cause about 18 cases of other pneumococcal diseases such as otitis media and septicemia. There is no specific data on the prevalent serotypes of pneumococcal infection in Kiribati. However, assuming the similar serotype distribution as in other oceanic countries, it may be assumed that the 13-valent vaccine may provide about 70% protection against the invasive disease, and hence may prevent 166 cases of severe illness and 5 deaths out of an estimated 239 cases and 7 deaths, respectively. WHO estimates that that in 2008, pneumonia accounted for 24% and meningitis accounted for 2% of under-5 mortality in Kiribati (WHS 2010). According to these estimates, pneumonia is by far the most common disease or syndrome causing child death in Kiribati. 

Request for Support and Duration of Support
The total programme cost for the 2010 immunization programme (current EPI vaccines (BCG, MR, OPV, co-financed pentavalent vaccine, TT and DTP booster) is estimated at $389,638. This represents $2.9 per capita and $100.6 per fully immunized child. 74.1% of the program is nationally funded. 

The cost of the multi-year plan over the course of 2011-2015 is estimated to be approximately $4.92 million and is discussed in detail in Section 4 of the cMYP. It is anticipated that overall program costs are expected to increase by 45% between 2011 and 2015. Much of programme increase is due to costs to strengthen health systems, re-establish strong cold chain and introduction of new vaccines: HPV in 2012, PCV in 2012 and rotavirus in 2015. The supply costs alone for routine vaccines are anticipated to rise from USD $43,585 to $308,876 in 2015.

The co-financing contribution for PCV13 for the Government is estimated at $4,805 in 2012, increasing to $29,572 in 2015 until the full cost of $36,965 will be borne in 2016. Introduction of PCV vaccine has been prioritized by the Ministry of Health and Interagency Coordinating Committee (ICC) in their Multi-Year Plan for Immunization in 2008-2012. Introduction of PCV 13 vaccine single dose will be co-funded both by GAVI and the Government according to “graduating country” co financing levels. PCV13 is the best choice for Kiribati because it covers 79% of serotypes present in invasive pneumococcal disease in Oceania, as compared to 75% of serotypes for PCV10. Due to geographic conditions, highly scattered populations and high cost of the vaccine, a single dose presentation would be the most appropriate in order to lower vaccine wastage. 

Increasing child survival is a key priority action of one of six strategic objectives outlined in the National Health Strategic Plan (2008-2011) of Ministry of Health and Medical Science, a document which provides the vision and strategic direction for operational planning. The commitment of the Government to meet its obligations in protecting children is reflected in the fact that Kiribati funds all traditional vaccines, operational costs and additionally, co-finances the cost of pentavalent at the rate of US $ 1 per dose pentavalent vaccine -- above the current GAVI requirement for its income level. This would also apply to PCV vaccine should application to GAVI be successful. If approved, the Government of Kiribati is committed to slowly increase its co-financing levels until December 2015, after which point it would pay the full anticipated cost of $3.50.

Furthermore, Kiribati has strong partner support for its EPI programme. The Pacific Immunization Progamme Strengthening (PIPS) Partners, including WHO, UNICEF, JICA, recognize Kiribati as a priority country. 

Relevant baseline data
No outbreak of a vaccine-preventable disease has been reported in Kiribati since 2004. DTP3 and Measles coverage data (as reported on the WHO/UNICEF Joint Reporting Form) has demonstrated significant improvements in the last 5 years. DPT3 immunization numbers have increased from 1896 in 2005 to 2904 in 2010. The reported Country Estimate of DPT3 coverage has increased from 79% in 2005 to 91% in 2010. In terms of measles, coverage has increased from 85% to 89% in the same period. A second dose of measles for school age children was introduced in 2010 with coverage of 21%. Pentavalent vaccine was successfully introduced in 2008 with coverage reaching 91% (Pentavalent 3) in 2010. There was no recorded drop out for DPT1-DPT3 in 2010 (-1). There are still reported inequities in immunization coverage across the country, particularly in remote locations. 

As reported in the JRF 2010, the surviving infants is estimated at 3194 (JRF 2010), an increase of 529 from the previous year. The notable jump in the number of surviving infants in 2010 as compared to previous years is due to the consensus reached after a door-to-door census was conducted by community nurses. However, it should be noted that based on the formulas embedded in the cMYP costing tool, the population for this application was calculated based on the given statistics: (1) The last census was conducted in 2005 when the population was 92,533. Based on a population growth rate of 1.8%, with 3.3% of population as births, the estimated births calculation for 2010 is 3288. With an IMR of 38/1000 (WHO World Health Statistics 2010), the surviving infants are projected to be 3163 for 2010. For this application and accompanying cMYP costing, populations for the years 2012 - 2015 have been calculated using the same projected parameters.

Country preparedness
Health System Preparedness – there are 4 levels in the Kiriabti health system – the national level, district level (6), island health centres (19) and dispensaries (82) (JRF 2010). The system of primary health care delivery infrastructure is well established in the outer Islands with referral hospitals. 

EPI Program Preparedness - Immunization coverage, although improving impressively in recent years, also some inequities in access across the country. In 2009, despite improving national coverage, one of the 6 districts still has coverage for DPT3 between 50% and 74%. However, many factors point to the readiness of the EPI program and the health system to absorb new vaccines into the program. There is improving national EPI coverage. Implementation of measles SIAs and higher coverage for MCV1 has resulted in the interruption to transmission of the measles virus with no cases reported in Kiribati since *. Pentavalent vaccine was successfully introduced in 2008, with coverage of the third dose reaching 91% in 2010. 

Cold Chain and Vaccine Management Preparedness: 
A WHO/UNICEF vaccine management assessment (VMA) was conducted in October 2010. With respect to cold chain capacity, the consultant concluded that cold chain capacity at service delivery level is more than sufficient for introduction of multiple new vaccines. The national level was adequate for all existing vaccines used in the programme in 2010. 

The VMA found that skills and knowledge of appropriate vaccine management practices were weaker at periphery levels than at Central level. Furthermore, ongoing maintenance of equipment was found sub-optimal. In consequence of these findings, a cold chain and vaccine management improvement plan has been drafted (2011-2013) and is included as Annex 3 in the cMYP. 

The addition in 2011 of two MK 304s has added 216 liters net storage and increased the total cold chain storage capacity at the central level from 540 liters to 709 liters. As illustrated in Table 4 in the cMYP, with the current routine EPI schedule, there is a surplus capacity at the national level of 338 litres. With the introduction of PCV 13 vaccine in 2012 and sustained supply of HPV, it is anticipated that an additional 205 litres will be required, which the current cold chain capacity is quite adequate to accommodate. In preparation for Rotavirus in 2015, this will need to be re-examined, but as estimates show in Table 4, it is projected that there will be no gap in the cold storage required at the central level even with the addition of Rotavirus vaccine.

Applying the same methodology to calculate cold chain storage capacity for Kirimati -- where 10% of the population resides -- the refrigerator and freezer storage capacity is 167 litres over the required capacity (Table 5, cMYP), so the introduction of PCV13, HPV and Rotavirus will not be a constraint.

Further detailed analysis at the district level again re-confirmed that there is significant surplus capacity with the current EPI schedule that will not be compromised with the introduction of multiple new vaccines.

Surveillance Preparedness: 
Several steps are being undertaken to prepare the country for improved surveillance for new vaccine introduction. Training materials have been developed for AEFI and immunization surveillance and for vaccine introduction planning. A systematic assessment of incidence and mortality from pneumonia and meningitis based on retrospective analysis of hospital and laboratory records will be undertaken in 2012 so that there is a baseline for the PCV introduction. Regular monitoring of all the admissions for meningitis and pneumonia will be undertaken between 2012 and 2015 to assess the impacts of PCV and pentavalent vaccine introductions. Specifically, the incidence and mortality due to pneumonia among under-5 children will be monitored by regularly analyzing the hospital admissions in the Pediatric wards (including cause of death data). 

Stakeholder’s participation in developing this proposal 
The Inter-Agency Coordinating Committee in Kiribati oversaw the development and review of this proposal. Inputs were additionally obtained from WHO and UNICEF regions and sub region on the development of the multi year plan and of this proposal.

# Signatures

# Signatures of the Government and National Coordinating Bodies

# Government and the Inter-Agency Coordinating Committee for Immunisation

The Government of Kiribati would like to expand the existing partnership with the GAVI Alliance for the improvement of the infants routine immunisation programme of the country, and specifically hereby requests for GAVI support for Pneumococcal (PCV13) 1 doses/vial Liquid introduction.

The Government of Kiribati commits itself to developing national immunisation services on a sustainable basis in accordance with the Comprehensive Multi-Year Plan (cMYP) presented with this document. The Government requests that the GAVI Alliance and its partners contribute financial and technical assistance to support immunisation of children as outlined in this application.

Tables 6.(n).5. (where (n) depends on the vaccine) in the NVS section of this application shows the amount of support in either supply or cash that is required from the GAVI Alliance. Tables 6.(n).4. of this application shows the Government financial commitment for the procurement of this new vaccine (NVS support only).

Following the regulations of the internal budgeting and financing cycles the Government will annually release its portion of the co-financing funds in the month of June.

Please note that this application will not be reviewed or approved by the Independent Review Committee (IRC) without the signatures of both the Minister of Health & Minister of Finance or their delegated authority.

Enter the family name in capital letters.

| Minister of Health (or delegated authority) |  | Minister of Finance (or delegated authority) |  |
| --- | --- | --- | --- |
| Name | Dr TENAUA, Kautu | Name | TEEWE, Natan |
| Date |  | Date |  |
| Signature |  | Signature |  |

This report has been compiled by

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

Enter the family name in capital letters.

| Full name | Position | Telephone | Email | Action |
| --- | --- | --- | --- | --- |
| Ms TEKITANGA, Tikua | MHMS National EPI Coordinator | 686-90760 | tikutanga@gmail.com |  |
| Dr. TIIRA Teatao | MHMS Director of Publich Health Services | 686 28100 | teataotiira@gmail.com |  |
| Ms IUTA Tinai | Kiribati Health and Nutrition Officer | 686 22904 | tiuta.unicef@gmail.com |  |

# National Coordinating Body - Inter-Agency Coordinating Committee for Immunisation

We the members of the ICC, HSCC, or equivalent committee[1] met on the 06.05.2011 to review this proposal. At that meeting we endorsed this proposal on the basis of the supporting documentation which is attached.

[1] Inter-agency Coordinating Committee or Health Sector Coordinating Committee, or equivalent committee which has the authority to endorse this application in the country in question.

The endorsed minutes of this meeting are attached as DOCUMENT NUMBER: .

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

Enter the family name in capital letters.

| Name/Title | Agency/Organisation | Signature | Action |
| --- | --- | --- | --- |
| Dr, TIIRA,Teatao | MHMS Director of Public Health |  |  |
| Dr.REIFFER Andre | WHO/CLO Kiribati |  |  |
| Mr. KANG Yun Jong | Chief of field Office Kiribati |  |  |
| Ms ENGLAND Tebete | Ministry of Finance, Planning Officer |  |  |
| Ms TAAKAU Ioana | MHMS Pharmacist |  |  |
| Mr. TABUNGA Teanibuaka | MHMS Statistician |  |  |
| Ms. TEKITANGA Tikua | MHMS EPI coordinator |  |  |

In case the GAVI Secretariat has queries on this submission, please contact

Enter the family name in capital letters.

| Name | Dr TIIRA, Teatao | Title | Director of Public Health |
| --- | --- | --- | --- |
| Tel no | 686 28100, ext 208 |  |  |
| Fax no | 686 28150 | Address | Tungaru Hospital, Nawerewere Tarawa, Kiribati. |
| Email | teataotiira@gmail.com |  |  |

# The Inter-Agency Coordinating Committee for Immunisation

Agencies and partners (including development partners and NGOs) supporting immunisation services are co-ordinated and organised through an inter-agency coordinating mechanism (ICC, HSCC, or equivalent committee). The ICC, HSCC, or equivalent committee is responsible for coordinating and guiding the use of the GAVI NVS support. Please provide information about the ICC, HSCC, or equivalent committee in your country in the table below.

Profile of the ICC, HSCC, or equivalent committee

| Name of the committee | Immunization Coordination Committee |
| --- | --- |
| Year of constitution of the current committee | 2006 |
| Organisational structure (e.g., sub-committee, stand-alone) | Stand alone |
| Frequency of meetings | 3-4 times per year |

Composition

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

Enter the family name in capital letters.

| Function | Title / Organisation | Name |  |
| --- | --- | --- | --- |
| Chair | Director of Public Health MHMS | Dr. TIIRA Teatao |  |
| Secretary | EPI Coordinator MHMS | Ms TEKITANGA Tikua |  |
| Members | CLO/WHO | Dr.REIFFER Andre | Action |
|  | Chief of Kiribati Field Office/UNICEF | Mr. KANG Yun Jong |  |
|  | Planning Officer/ Ministry of Finance | Ms ENGLAND Tebete |  |
|  | Pharmacist MHMS | Ms TAAKAU Ioana |  |
|  | Statistician MHMS | Mr. TABUNGA Teanibuaka |  |
|  | EPI Coordinator MHMS | Ms TEKITANGA Tikua |  |

Major functions and responsibilities of the committee

Major Functions: (1) To review EPI progress on routine basis, address main challenges in delivering quality EPI services ; (2) To discuss and approve the proposed action plans on improving EPI coverage (Goals/ policies/Strategies/working plans) developed by working group ; (3) To define needs for resources, identify resource gaps and mobilize/secure funds needed to implement action plans ; (4) To monitor and assess outcomes and implications of national Plans, and further improve decision-making capacity.

Three major strategies to enhance the committee's role and functions in the next 12 months

| 1. | To review EPI progress on routine basis, address main challenges in delivering quality EPI services |
| --- | --- |
| 2. | To define needs for resources, identify resource gaps and mobilize/secure funds needed to implement action plans |
| 3. | To monitor and assess outcomes and implications of national Plans, and further improve decision-making capacity |

# National Immunization Technical Advisory Group for Immunisation

(If it has been established in the country)

We the members of the NITAG met on the to review this proposal. At that meeting we endorsed this proposal on the basis of the supporting documentation which is attached.

The endorsed minutes of this meeting are attached as DOCUMENT NUMBER: .

In case the GAVI Secretariat has queries on this submission, please contact

Enter the family name in capital letters.

| Name | Dr.TIIRA Teatao | Title | Director of Public Health |
| --- | --- | --- | --- |
| Tel no | 686 28100 extension 210 |  |  |
| Fax no | 686 28152 | Address | Ministry of Health & Medical Services, Naverevere ,Tarawa. |
| Email | teataotiira@gmail.com |  |  |

# The NITAG Group for Immunisation

Profile of the NITAG

| Name of the NITAG |  |
| --- | --- |
| Year of constitution of the current NITAG |  |
| Organisational structure (e.g., sub-committee, stand-alone) |  |
| Frequency of meetings |  |

Composition

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

Enter the family name in capital letters.

| Function | Title / Organisation | Name |  |
| --- | --- | --- | --- |
| Chair |  |  |  |
| Secretary |  |  |  |
| Members |  |  | Action |

Major functions and responsibilities of the NITAG

Three major strategies to enhance the NITAG’s role and functions in the next 12 months

| 1. |  |
| --- | --- |
| 2. |  |
| 3. |  |

# Immunisation Programme Data

Please complete the tables below, using data from available sources. Please identify the source of the data, and the date. Where possible use the most recent data and attach the source document.

- Please refer to the Comprehensive Multi-Year Plan for Immunisation (cMYP) (or equivalent plan) and attach a complete copy (with an Executive Summary) as DOCUMENT NUMBER 1

- Please refer to the two most recent annual WHO/UNICEF Joint Reporting Forms (JRF) on Vaccine Preventable Diseases.

- Please refer to Health Sector Strategy documents, budgetary documents, and other reports, surveys etc, as appropriate.

# Basic facts

For the year 2010 (most recent; specify dates of data provided)

|  | Figure |  | Year | Source |
| --- | --- | --- | --- | --- |
| Total population | 92,533 |  | 2005 | National Census 2005 |
| Infant mortality rate (per 1000) | 38 |  | 2008 | WHO World Health Statistics Report 2010 |
| Surviving Infants[1] | 3,194 |  | 2010 | JRF. See comments section on population projections |
| GNI per capita (US$) | 1,890 |  | 2009 | WORLD BANK 2010 |
| Total Health Expenditure (THE) as a percentage of GDP | 19.10 | % | 2007 | WHO World Health Statistics Report |
| General government expenditure on health (GGHE) as % of General government expenditure | 10.30 | % | 2007 | WHO World Health Statistics Report 2010 |

[1] Surviving infants = Infants surviving the first 12 months of life

Please provide some additional information on the planning and budgeting context in your country; also indicate the name and date of the relevant planning document for health

The financial cycle in Kiribati is from January to December. The annual planning process starts at July. By September budget needs to be submitted to Ministry of Finance, then the parliament will endorse the budget requested by the MOH. The funds is available by January every year. The planning document is National Health Plan 2008-2011. By the end of 2011, MOH will prepare a new National Health Plan for 2012-2015

Is the cMYP (or updated Multi-Year Plan) aligned with this document (timing, content, etc.)?

Yes the cMYP is aligned with this documentand is attached as Document 1 (GAVI application for pneuococcal vaccine).

Please indicate the national planning budgeting cycle for health

All health budgets are inline with the financial cycle of the Government as explained above.

Please indicate the national planning cycle for immunisation

The same as above.

Please indicate if sex disaggregated data (SDD) is used in immunisation routine reporting systems

Sex dissaggregated data was not used in immunization routine reportiing system. Boys and girls seggregated data is only available during the DHS or MICS. No seggregated data in monthly report of HIS.

Please indicate if gender aspects relating to introduction of a new vaccine have been addressed in the introduction plan

In Kiribati, gender issues is not a problem. No difference in terms of immunization service for boys and girls.

# Current vaccination schedule

Traditional, New Vaccines and Vitamin A supplement (refer to cMYP pages)

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Vaccine (do not use trade name) | Ages of administration (by routine immunisation services) | Given in entire country | Comments | Action |
| --- | --- | --- | --- | --- |
| BCG | Birth | Yes |  |  |
| HepB | Birth | Yes |  |  |
| Penta | 6,10 and 14 weeks | Yes |  |  |
| Polio | 6,10, and 14 weeks | Yes |  |  |
| Other | 12 months, 6 years | Yes | Measles Rubella Vaccine. 2nd dose of MR introduced in 2007 |  |
| TT | 6 years, 13 years (schoolgirls only) | Yes |  |  |
| TT+ | Pregnant Women | Yes |  |  |
| DTP | 6 years | Yes | school booster |  |
| Vitamin A | Children Aged 6 - 59 Months | Yes | 2 Rounds Per Year |  |

# Trends of immunisation coverage and disease burden

(as per last two annual WHO/UNICEF Joint Reporting Form on Vaccine Preventable Diseases)

| Trends of immunisation coverage (percentage) |  |  |  |  |  | Vaccine preventable disease burden |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Vaccine |  | Reported |  | Survey |  | Disease | Number of reported cases |  |
|  |  | 2009 | 2010 | 2009 | 2010 |  | 2009 | 2010 |
| BCG |  | 76 | 87 |  |  | Tuberculosis |  |  |
| DTP | DTP1 | 90 | 90 |  |  | Diphtheria | 0 | 0 |
|  | DTP3 | 86 | 91 |  |  | Pertussis | 0 | 0 |
| Polio 3 |  | 84 | 95 |  |  | Polio | 0 | 0 |
| Measles (first dose) |  | 82 | 89 |  |  | Measles | 0 | 0 |
| TT2+ (Pregnant women) |  | 79 |  |  |  | NN Tetanus | 0 | 0 |
| Hib3 |  | 86 | 91 |  |  | Hib[2] | 0 | 0 |
| Yellow Fever |  |  |  |  |  | Yellow fever | 0 | 0 |
| HepB3 |  | 86 | 91 |  |  | HepBsero-prevalence[1] |  |  |
| Vitamin A supplement Mothers (< 6 weeks post-delivery) |  | 35 |  |  |  |  |  |  |
| Vitamin A supplement Infants (>6 months) |  |  |  |  |  |  |  |  |

[1] If available

[2] Note: JRF asks for Hib meningitis

If survey data is included in the table above, please indicate the years the surveys were conducted, the full title and if available, the age groups the data refers to

# Baseline and Annual Targets

(refer to cMYP pages)

Table 1: baseline figures

| Number | Base Year | Baseline and Targets |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2010 | 2012 | 2013 | 2014 | 2015 |  |  |
| Total births | 3,288 | 3,407 | 3,469 | 3,531 | 3,595 |  |  |
| Total infants' deaths | 125 | 129 | 132 | 134 | 137 |  |  |
| Total surviving infants | 3,163 | 3,278 | 3,337 | 3,397 | 3,458 |  |  |
| Total pregnant women | 3,288 | 3,460 | 3,522 | 3,585 | 3,650 |  |  |
| Number of infants vaccinated (to be vaccinated) with BCG | 2,781 | 3,135 | 3,226 | 3,319 | 3,415 |  |  |
| BCG coverage (%)[1] | 85% | 92% | 93% | 94% | 95% |  |  |
| Number of infants vaccinated (to be vaccinated) with OPV3 | 3,029 | 3,048 | 3,103 | 3,193 | 3,285 |  |  |
| OPV3 coverage (%)[2] | 96% | 93% | 93% | 94% | 95% |  |  |
| Number of infants vaccinated (or to be vaccinated) with DTP1[3] | 2,886 | 3,048 | 3,103 | 3,193 | 3,285 |  |  |
| Number of infants vaccinated (to be vaccinated) with DTP3[3] | 2,904 | 3,048 | 3,103 | 3,193 | 3,285 |  |  |
| DTP3 coverage (%)[2] | 92% | 93% | 93% | 94% | 95% |  |  |
| Wastage[1] rate in base-year and planned thereafter for DTP (%) | 5% | 5% | 5% | 5% | 5% |  |  |
| Wastage[1] factor in base-year and planned thereafter for DTP | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 |  |  |
| Target population vaccinated with 1st dose of Pneumococcal |  | 1,639 | 2,836 | 2,955 | 3,112 |  |  |
| Target population vaccinated with 3rd dose of Pneumococcal |  | 1,639 | 2,836 | 2,955 | 3,112 |  |  |
| Pneumococcal coverage (%)[2] | 0% | 50% | 85% | 87% | 90% |  |  |
| Infants vaccinated (to be vaccinated) with 1st dose of Measles | 2,831 | 2,983 | 3,070 | 3,159 | 3,285 |  |  |
| Measles coverage (%)[2] | 90% | 91% | 92% | 93% | 95% |  |  |
| Pregnant women vaccinated with TT+ | 1,744 | 2,896 | 2,948 | 3,001 | 3,055 |  |  |
| TT+ coverage (%)[4] | 53% | 84% | 84% | 84% | 84% |  |  |
| Vit A supplement to mothers within 6 weeks from delivery | 2,078 |  |  |  |  |  |  |
| Vit A supplement to infants after 6 months | 2,085 |  |  |  |  |  |  |
| Annual DTP Drop-out rate[ ( DTP1 - DTP3 ) / DTP1 ] x 100[5] | -1% | 0% | 0% | 0% | 0% |  |  |

[1] Number of infants vaccinated out of total births

[2] Number of infants vaccinated out of total surviving infants

[3] Indicate total number of children vaccinated with either DTP alone or combined

[4] Number of pregnant women vaccinated with TT+ out of total pregnant women

[5] The formula to calculate a vaccine wastage rate (in percentage):[ ( A – B ) / A ] x 100. Whereby: A = the number of doses distributed for use according to the supply records with correction for stock balance at the end of the supply period; B = the number of vaccinations with the same vaccine in the same period.

# Summary of current and future immunisation budget

(or refer to cMYP pages)

|  | Estimated costs per annum in US$ (in thousand US$) |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Cost category | Base Year | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |  |
|  | 2010 | 2012 | 2013 | 2014 | 2015 |  |  |  |  |  |
| Routine Recurrent Cost |  |  |  |  |  |  |  |  |  |  |
| Vaccines (routine vaccines only) | 39,032 | 247,697 | 231,154 | 232,653 | 303,487 |  |  |  |  |  |
| Traditional vaccines | 11,820 | 11,624 | 11,855 | 12,174 | 12,487 |  |  |  |  |  |
| New and underused vaccines | 27,212 | 236,073 | 219,299 | 220,479 | 291,000 |  |  |  |  |  |
| Injection supplies | 2,404 | 4,948 | 5,168 | 5,234 | 5,389 |  |  |  |  |  |
| Personnel | 143,460 | 149,256 | 152,241 | 155,286 | 158,391 |  |  |  |  |  |
| Salaries of full-time NIP health workers (immunisation specific) |  |  |  |  |  |  |  |  |  |  |
| Per-diems for outreach vaccinators / mobile teams | 143,460 | 149,256 | 152,241 | 155,286 | 158,391 |  |  |  |  |  |
| Transportation |  |  |  |  |  |  |  |  |  |  |
| Maintenance and overheads | 5,109 | 6,557 | 7,958 | 8,765 | 5,225 |  |  |  |  |  |
| Training |  | 31,212 | 7,428 | 5,412 | 27,602 |  |  |  |  |  |
| Social mobilisation and IEC | 5,000 | 52,020 | 10,612 | 5,412 | 5,520 |  |  |  |  |  |
| Disease surveillance | 600 | 6,034 | 6,155 | 6,278 | 6,404 |  |  |  |  |  |
| Program management | 25,000 | 20,808 | 21,224 | 21,649 | 22,082 |  |  |  |  |  |
| Other | 443,824 | 461,421 | 463,970 | 472,689 | 481,583 |  |  |  |  |  |
| Subtotal Recurrent Costs | 664,429 | 979,953 | 905,910 | 913,378 | 1,015,683 |  |  |  |  |  |
| Routine Capital Costs |  |  |  |  |  |  |  |  |  |  |
| Vehicle |  |  |  |  |  |  |  |  |  |  |
| Cold chain equipment | 22,192 | 33,852 | 41,640 | 46,625 | 32,581 |  |  |  |  |  |
| Other capital equipment |  |  |  |  |  |  |  |  |  |  |
| Subtotal Capital Costs | 22,192 | 33,852 | 41,640 | 46,625 | 32,581 |  |  |  |  |  |
| Campaigns |  |  |  |  |  |  |  |  |  |  |
| Polio |  |  |  |  |  |  |  |  |  |  |
| Measles | 100,000 | 77,399 |  |  | 82,692 |  |  |  |  |  |
| Yellow Fever |  |  |  |  |  |  |  |  |  |  |
| MNT campaigns |  |  |  |  |  |  |  |  |  |  |
| Other campaigns |  |  |  |  |  |  |  |  |  |  |
| Subtotal Campaign Costs | 100,000 | 77,399 | 0 | 0 | 82,692 |  |  |  |  |  |
| GRAND TOTAL | 786,621 | 1,091,204 | 947,550 | 960,003 | 1,130,956 |  |  |  |  |  |

# Summary of current and future financing and sources of funds

Please list in the tables below the funding sources for each type of cost category (if known). Please try and indicate which immunisation program costs are covered from the Government budget, and which costs are covered by development partners (or the GAVI Alliance), and name the partners (or refer to cMYP).

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

|  |  | Estimated costs per annum in US$ (in thousand US$) |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Cost category | Funding source | Base Year | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |  |
|  |  | 2010 | 2012 | 2013 | 2014 | 2015 |  |  |  |  |  |
| Routine Recurrent Cost |  |  |  |  |  |  |  |  |  |  |  |
| Total Routine Recurrent | Government | 214,755 | 211,390 | 222,420 | 230,832 | 397,136 |  |  |  |  |  |
|  | UNICEF | 6,272 | 85,600 | 13,700 | 13,200 | 13,200 |  |  |  |  |  |
|  | WHO | 11,800 | 11,800 | 11,800 | 11,800 | 11,800 |  |  |  |  |  |
|  | JICA | 10,000 | 10,000 | 10,000 | 10,000 | 10,000 |  |  |  |  |  |
|  | GAVI |  | 105,101 | 29,583 | 13,718 | 7,242 |  |  |  |  |  |
|  | Merck |  | 184,368 | 154,984 | 156,940 |  |  |  |  |  |  |
| Shared personnel & transport | Government | 246,184 | 413,021 | 421,282 | 429,708 | 438,301 |  |  |  |  |  |
| Routine Capital Costs |  |  |  |  |  |  |  |  |  |  |  |
| Capital Costs | UNICEF | 6,272 | 4,124 | 1,926 | 13,200 | 22,512 |  |  |  |  |  |
| Campaigns |  |  |  |  |  |  |  |  |  |  |  |
| Campaigns | UNICEF | 21,477 | 21,477 |  | 21,477 |  |  |  |  |  |  |
| GRAND TOTAL |  | 516,760 | 1,046,881 | 865,695 | 900,875 | 900,191 |  |  |  |  |  |

# New and Under-Used Vaccines (NVS)

Please summarise the cold chain capacity and readiness to accommodate new vaccines, stating how the cold chain expansion (if required) will be financed, and when it will be in place. Please indicate the additional cost, if capacity is not available and the source of funding to close the gap.

A WHO/UNICEF vaccine management assessment (VMA) was conducted in October 2010. With respect to cold chain capacity, the consultant concluded that cold chain capacity at service delivery level is more than sufficient for introduction of multiple new vaccines. (see Document 4). The VMA found that skills and knowledge of appropriate vaccine management practices were weaker at periphery levels than at Central level. While the VMA performance in certain areas is markedly low (temperature monitoring, stock management, vaccine wastage), the consultant concluded that this was primarily due to a poor system of documentation and record-keeping rather than ineffective service delivery. Nevertheless, findings from the assessment suggest some key capacity-building steps should be instituted over the next planning cycle to strengthen cold chain systems management. These include: • Increasing understanding and knowledge at all levels of vaccine sensitivity and proper vaccine handling • Strengthening temperature monitoring tools, practices and record-keeping • Improving stock management skills and recording • Updating cold chain inventory and develop equipment maintenance strategy Furthermore, ongoing maintenance of equipment was found sub-optimal. In consequence of these findings, a cold chain and vaccine management improvement plan has been drafted (2011-2013) and is included as Annex 3 in the cMYP. Already six new Solar Chillrs have been installed to address some of the equipment gaps identified. The Central Pharmacy technician has been trained on Solar Chill installation, and the long-term plan includes engagement of a dedicated technician to support cold chain system maintenance. A priority in 2011 will be improving skills on vaccine management through MLM training, and greater emphasis on proper vaccine handling and monitoring. The addition in 2011 of two MK 304s at the Central level has added 216 liters net storage and increased the total cold chain storage capacity at national level from 540 liters to 709 liters. With the current routine EPI schedule, there is a surplus capacity at the national level of 338 litres. With the introduction of PCV 13 vaccine in 2012 and HPV -- and even perhaps Rota in 2015 -- there will be no gap in the cold storage required at the central level (Table 4 in cMYP). To be prudent, a gap analysis will be re-conducted before Rotavirus introduction. Applying the same methodology to calculate cold chain storage capacity for Kirimati -- where 10% of the population resides -- the refrigerator and freezer storage capacity is 167 litres over the necessary capacity; the introduction of PCV13, HPV and Rotavirus will require only 13 litres, so new vaccine introduction will not be a constraint (Table 5 in cMYP). Further detailed analysis at the district level re-confirmed that there is significant surplus capacity with the current EPI schedule, and that storage space will not be compromised with the introduction of multiple new vaccines. Because Kiribati faces particularly harsh tropical weather conditions, maintaining the cold chain at the health center level is an ongoing challenge. Furthermore, a small annual birth cohort scattered over a large geographic area invariably results in high levels of wastage for vaccines supplied in multi-dose vials (10- and 20-dose vials) in the Outer Islands. With the introduction of newer vaccines, it will be important to have a better assessment of levels of vaccine wastage in different areas and in different contexts, to identify the best approach to controlling wastage feasibly without compromising coverage levels in hard-to-reach areas. In the near to medium term, more energy will be focused on improving the reporting and monitoring for vaccine wastage as well as increasing health worker skills in vaccine management and handling. This is planned in 2011 as part of MLM training.

Please give a summary of the cMYP sections that refer to the introduction of new and under-used vaccines. Outline the key points that informed the decision-making process (data considered etc)

Hib vaccine was introduced in August 2008 in the form of DTP-HepB-Hib and attained 91% coverage in 2010, reflecting the capacity of Kiribati to integrate a new product into its programme smoothly. In partnership with the Australian Cervical Cancer Foundation, the Ministry of Health has leveraged a donation of Merck for Gardasil HPV vaccine which will be delivered in 2011 to 10-12 year old girls.. There is no specific pneumococcus disease surveillance or special disease burden studies undertaken in Kiribati. However, as per WHO estimates published in 2009, 237 (183-308) cases of severe illness and 7 deaths (5-8) occur each year in Kiribati from invasive pneumococcal disease. The majority of these cases are from pneumonia [216, (166-282)] and meningitis [3(2-3)]. In addition, pneumococcal infection are also estimated to cause about 18 cases on other pneumococcal diseases such as otitis media, septecemia, etc. There is also no specific data on the prevalent serotypes of pneumococcal infection in Kiribati. However, assuming the similar serotype distribution as in other oceanic countries, it may be assumed that the 13-valent vaccine may provide about 70% protection against the invasive disease, and hence may prevent 166 cases of severe illness and 5 deaths out of an estimated 239 cases and 7 deaths, respectively. The cause of mortality data for under-1 deaths in 2010 suggest almost 15% of all deaths due to pneumonia, while 5% of under-1 deaths due to meningitis. This suggests that introduction of pneumococcal vaccine may substantially reduce childhood morbidity and mortality. Furthermore, data from nearby Papua New Guinea showed that 11.9% of probable bacterial meningitis cases were due to pneumococcus in the first half of 2010, thus documenting the importance of pneumococcus as a cause of serious childhood disease in this region. The introduction of pneumococcal vaccines was already given high importance by the Ministry of Health in its 2008-2011 multi-year plan.

# Capacity and cost (for positive storage)

|  |  | Formula | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| A | Annual positive volume requirement, including new vaccine (litres or m3) Litres | Sum-product of total vaccine doses multiplied by unit packed volume of the vaccine | 580 | 591 | 601 | 612 |  |  |  |  |
| B | Existing net positive cold chain capacity (litres or m3) Litres | # | 709 | 709 | 709 | 709 |  |  |  |  |
| C | Estimated minimum number of shipments per year required for the actual cold chain capacity | A / B | 1 | 1 | 1 | 1 |  |  |  |  |
| D | Number of consignments / shipments per year | Based on national vaccine shipment plan | 1 | 1 | 1 | 1 |  |  |  |  |
| E | Gap (if any) | ((A / D) - B) | -129 | -118 | -108 | -97 |  |  |  |  |
| F | Estimated additional cost of cold chain | US$ | 33,850 | 41,640 | 46,600 | 32,500 |  |  |  |  |

Please briefly describe how your country plans to move towards attaining financial sustainability for the new vaccines you intend to introduce, how the country will meet the co-financing payments, and any other issues regarding financial sustainability you have considered (refer to the cMYP)

Increasing child survival is a key priority action of one of six strategic objectives outlined in the National Health Strategic Plan (2008-2011) of Ministry of Health and Medical Science, a document which provides the vision and strategic direction for operational planning. The commitment of the Government to meet its obligations in protecting children is reflected in the fact that Kiribati funds all traditional vaccines, operational costs and additionally, co-finances the cost of pentavalent at the rate of US $ 1 per dose pentavalent vaccine -- above the current GAVI requirement for its income level. This would also apply to PCV vaccine should application to GAVI be successful. If approved, the Government of Kiribati is committed to slowly increase its co-financing levels until December 2015, after which point it would pay the full anticipated cost of $3.50. Kiribati has strong partner support for its EPI programme. The Pacific Immunization Progamme Strengthening (PIPS) Partners, including WHO, UNICEF, JICA, recognize Kiribati as a priority country. UNICEF has allocated adequate funds accordingly. WHO will continue to provide technical support. The EU Outer Island Health System Strengthening project will contribute to maintaining the cold chain equipment, improving data quality and communication between the central and outer islands, health waste management. JICA is contributing to the areas of supporting training, improving cold chain system status and safety injection.

# Assessment of burden of relevant diseases (if available)

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Disease | Title of the assessment | Date | Results |  |
| --- | --- | --- | --- | --- |
| Pneumococcal meningitis | Western Pacific Region invasive bacterial disease surveillance network | 2010 | Data from nearby Papua New Guinea showed that 11.9% of probable bacterial meningitis cases were due to pneumococcus in the first half of 2010, thus documenting the importance of pneumococcus as a cause of serious childhood disease in this region. |  |

If new or under-used vaccines have already been introduced in your country, please give details of the lessons learned from storage capacity, protection from accidental freezing, staff training, cold chain, logistics, drop-out rate, wastage rate etc., and suggest action points to address them

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Lessons Learned | Action Points |  |
| --- | --- | --- |
| Helped raise awareness on improving systems for cold chain, temperature monitoring and record-keeping, and awareness of vaccine sensitivity | Conducted VMA in 2010 and participated in regional inter-country MLM which included introduction to vaccine management issues. Have rehabiliated solar units and increase cold chain space at central level. Introduced immunization coverage monitoring charts 2010 and will conduct national MLM 2011. Will strengthen reporting systems for vaccine wastage monitoring. |  |
| Uptake of DTP-HepB-Hib3 to be equivalent to OPV3 has been gradual rather than immediate | Ongoing training and encouragement to Health Workers to properly coordinate administration of multiple vaccines |  |

Please list the vaccines to be introduced with support from the GAVI Alliance (and presentation)

Pneumococcal PCV13, 1 dose/vial, Liquid

# 6.3.1. Requested vaccine ( Pneumococcal (PCV13), 1 doses/vial, Liquid )

As reported in the cMYP, the country plans to introduce Pneumococcal (PCV13), 1 doses/vial, Liquid vaccine.

# 6.3.2. Co-financing information

If you would like to co-finance higher amount than minimum, please overwrite information in the “Your co-financing” row.

Note: Selection of this field has direct impact on automatic calculations of support you are requesting and should not be left empty.

| Country group | Graduating |
| --- | --- |

|  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| Minimum co-financing | 0.70 | 1.40 | 2.10 | 2.80 |  |  |  |  |
| Your co-financing (please change if higher) | 0.70 | 1.40 | 2.10 | 2.80 |  |  |  |  |

# 6.3.3. Wastage factor

Please indicate wastage rate:

Countries are expected to plan for a maximal wastage rate of:

- 50% - for a lyophilised vaccine in 10 or 20-dose vial,

- 25% - for a liquid vaccine in 10 or 20-dose vial or a lyophilised vaccine in 5-dose vial,

- 10% - for a lyophilised/liquid vaccine in 2-dose vial, and

- 5% - for a liquid vaccine in 1-dose vial

Note: Selection of this field has direct impact on automatic calculations of support you are requesting and should not be left empty.

|  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| Vaccine wastage rate in % | 5% | 5% | 5% | 5% |  |  |  |  |
| Equivalent wastage factor | 1.05 | 1.05 | 1.05 | 1.05 |  |  |  |  |

# 6.3.4. Specifications of vaccinations with new vaccine

|  | Data from |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| Number of children to be vaccinated with the first dose | Table 1 | # | 1,639 | 2,836 | 2,955 | 3,112 |  |  |  |  |
| Number of children to be vaccinated with the third dose[1] | Table 1 | # | 1,639 | 2,836 | 2,955 | 3,112 |  |  |  |  |
| Immunisation coverage with the third dose | Table 1 | # | 50.00% | 84.99% | 86.99% | 89.99% |  |  |  |  |
| Estimated vaccine wastage factor | Table 6.(n).3[3] | # | 1.05 | 1.05 | 1.05 | 1.05 |  |  |  |  |
| Country co-financing per dose[2] | Table 6.(n).2[3] | $ | 0.70 | 1.40 | 2.10 | 2.80 |  |  |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Total price per-dose includes vaccine cost, plus freight, supplies, insurance, visa costs etc.

[3] Where (n) depends on the vaccine

# 6.3.5. Portion of supply to be procured by the country (and cost estimate, US$)

|  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| Number of vaccine doses | # | 1,300 | 3,700 | 5,300 | 7,500 |  |  |  |  |
| Number of AD syringes | # | 1,300 | 4,000 | 5,600 | 7,900 |  |  |  |  |
| Number of re-constitution syringes | # |  |  |  |  |  |  |  |  |
| Number of safety boxes | # | 25 | 50 | 75 | 100 |  |  |  |  |
| Total value to be co-financed by country | $ | 5,000 | 14,000 | 20,000 | 28,000 |  |  |  |  |

# 6.3.6. Portion of supply to be procured by the GAVI Alliance (and cost estimate, US$)

|  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| Number of vaccine doses | # | 5,300 | 6,200 | 4,200 | 2,600 |  |  |  |  |
| Number of AD syringes | # | 5,700 | 6,600 | 4,400 | 2,700 |  |  |  |  |
| Number of re-constitution syringes | # |  |  |  |  |  |  |  |  |
| Number of safety boxes | # | 75 | 75 | 50 | 50 |  |  |  |  |
| Total value to be co-financed by GAVI | $ | 20,000 | 23,500 | 15,500 | 9,500 |  |  |  |  |

# 6.3.7. New and Under-Used Vaccine Introduction Grant

Please indicate in the tables below how the one-time Introduction Grant[1] will be used to support the costs of vaccine introduction and critical pre-introduction activities (refer to the cMYP).

Calculation of lump-sum for the Pneumococcal (PCV13), 1 doses/vial, Liquid

If the total is lower than US$100,000, it is automatically rounded up to US$100,000

| Year of New Vaccine Introduction | Births (from Table 1) | Share per Birth in US$ | Total in US$ |
| --- | --- | --- | --- |
| 2012 | 3,407 | 0.30 | 100,000 |

[1] The Grant will be based on a maximum award of $0.30 per infant in the birth cohort with a minimum starting grant award of $100,000

Cost (and finance) to introduce the Pneumococcal (PCV13), 1 doses/vial, Liquid (US$)

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Cost Category | Full needs for new vaccine introduction in US$ | Funded with new vaccine introduction grant in US$ |  |
| --- | --- | --- | --- |
| Training | 70,000 | 45,000 |  |
| Social Mobilization, IEC and Advocacy | 64,000 | 22,000 |  |
| Cold Chain Equipment & Maintenance | 65,000 | 10,000 |  |
| Vehicles and Transportation |  |  |  |
| Programme Management | 25,000 | 3,000 |  |
| Surveillance and Monitoring | 10,000 | 10,000 |  |
| Human Resources |  |  |  |
| Waste Management |  |  |  |
| Technical assistance | 10,000 | 10,000 |  |
| Totals | 244,000 | 100,000 |  |

# Procurement and Management of New and Under-Used Vaccines

Note: The PCV vaccine must be procured through UNICEF

- Please show how the support will operate and be managed including procurement of vaccines (GAVI expects that most countries will procure vaccine and injection supplies through UNICEF)

Ministry of Health and Medical Services (MHMS) Kiribati will use vaccine which is prequalified by WHO through UNICEF procurement service, the same mechanism as the co-financing for DPTHebB Hib vaccines. MHMS will ensure that the co-financing part as well as the routine vaccines are included in National budget according to the financial cycle. After annual GAVI decision letter received, MHMS will send a request for vaccine order (pneumococcal vaccine) to UNICEF Pacific who will then forward the request to Supply Division UNICEF Copenhagen. UNICEF SD will issue a Cost estimate (CE), upon agreement with the CE, MHMS will transfer the funds to the bank account of SD UNICEF Copenhagen. Vaccines will be delivered by SD directly to Tarawa via Nadi/Fiji.

- If an alternative mechanism for procurement and delivery of supply (financed by the country or the GAVI Alliance) is requested, please document

- Other vaccines or immunisation commodities procured by the country and descriptions of the mechanism used.

- The functions of the National Regulatory Authority (as evaluated by WHO) to show they comply with WHO requirements for procurement of vaccines and supply of assured quality.

- Please describe the introduction of the vaccines (refer to cMYP)

In preparation for a successful PCV13 application, the Goverment has mapped out key activities, corresponding timeline and rough budget to prepare for PCV13 introduction in July 2012, which is included as Document Three to this proposal. Of immediate nature is to continue to bolster the cold chain system with finalisation of installation of Solar Chills and a training development plan for health workers to increase vaccine management knowledge and improve monitoring on critical indicators such as programme coverage performance and wastage levels. It is planned to conduct an MLM training in Q4 2011. Quarters 1 and 2 of 2012 will then focus on preparing operational issues related to the specific PCV13 introduction, such as updating of relevant reporting materials to reflect the new vaccine, and preparing social mobilisation and information materials for the community and health staff. Roll-out of trainings at national and sub-national level on pneumococcal disease and PCV13 vaccine would begin Q2 2012. The key topics of this training will be on pneumoccocal disease, the new vaccine, as well as reinforcing of AEFI responses, cold chain management and programme monitoring. An additional area of work that must be undertaken is on developing guidelines on identifying and responding to AEFIs and proper disposal of waste management. Ongoing monitoring of new vaccine introduction will occur through routine supervision vistis. The Government will give consideration to a new vaccine introduction assessment at a later date.

- Please indicate how funds should be transferred by the GAVI Alliance (if applicable)

Through account number attached, Funds will be transferred to government account number 4, Minister of Finance will sign warrant for use by the Ministry of Health through EPI program.

- Please indicate how the co-financing amounts will be paid (and who is responsible for this)

The director of Public Health through MHMS accounts system will raise a check against estimate received from UNICEF SD and deposit to UNICEF Copenhagen bank account.

- Please outline how coverage of the new vaccine will be monitored and reported (refer to cMYP)

Every Health facility reports its monthly coverage through MHMS using MS1 (Monthly Consolidated Health report) to Health Statistics. Accuracy and timeliness will be monitored by the Health Statistics and National EPI Manager. All health facilities has to display its coverage using the EPI charts in their facilities. Quarterly feedback will be sent to island supervisors. Twice a year there are Mid Year and Annual Review meeting attended by the medical assistant from the health centers as well as island supervisors to discuss achievement in coverage and problems encountered.

# Vaccine Management (EVSM/EVM/VMA)

When was the last Effective Vaccine Store Management (EVSM) conducted?   -

When was the last Effective Vaccine Management (EVM) or Vaccine Management Assessment (VMA) conducted? October  - 2010

- If your country conducted either EVSM, EVM, or VMA in the past three years, please attach relevant reports. (Document N°4)

- A VMA report must be attached from those countries which have introduced a New and Underused Vaccine with GAVI support before 2008.

- Please note that EVSM and VMA tools have been replaced by an integrated Effective Vaccine Management (EVM) tool. The information on EVM tool can be found at http://www.who.int/immunization_delivery/systems_policy/logistics/en/index6.html

- For countries which conducted EVSM, VMA or EVM in the past, please report on activities carried out as part of either action plan or improvement plan prepared after the EVSM/VMA/EVM.

It has been six months since the vaccine management assessment was conducted in 2010. In that short time, a cold chain and vaccine management improvement plan has been developed (2011-2013) and starting to be implemented. For example, six Solar Chills have been installed and a user's manual has been created. Additionally, the cold chain technician has been trained in installation and management.

- When is the next Effective Vaccine Management (EVM) Assessment planned? January  - 2013

- Under new guidelines, it will be mandatory for the countries to conduct an EVM prior to an application for introduction of new vaccine.

# Additional Comments and Recommendations

Comments and Recommendations from the National Coordinating Body (ICC/HSCC)

1. The introduction of pneumococcal vaccine is very crucial and needed for the children under five in Kiribati. Every year there are 1-2 outbreaks of pneumonia happening in Kiribati. 2. Per the recommendation of the vaccine management assessment of 2010, MOH Kiribati will recruit a dedicated cold chain technician to handle maintenance as the current staff is overwhelmed with hospital needs. 3. Implementation of the cold chain and vaccine management improvement plan (Annex 3, cMYP) has already commenced. As the cold chain space has been evaluated as sufficient, emphasis will be on vaccine management skills developement and record-keeping. 4. The JRF reports a surviving infants of 3194 in 2010. Based on the formulas embedded in the cMYP costing tool, the population was calculated based on the following parameters: (1) The last census was conducted in 2005 when the population was 92,533. Based on a population growth rate of 1.8%, with births representing 3.3% of population, the births calculation for 2010 is 3288. With an IMR of 38/1000, the surviving infants are projected to be 3163 for 2010. Populations for the years 2012 - 2015 have been calculated using the same population projections. 5. Attempts were made to upload the VMA as an attachement but rejected. "Maximum length exceeded". They will be emailed separately.

# Annexes

# Annex 1

# Annex 1.1 – Pneumococcal (PCV13), 1 doses/vial, Liquid

Table 1.1 A - Rounded up portion of supply that is procured by the country and estimate of related cost in US$

| Required supply item |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of vaccine doses | # | 1,300 | 3,700 | 5,300 | 7,500 |  |  |  |  |
| Number of AD syringes | # | 1,300 | 4,000 | 5,600 | 7,900 |  |  |  |  |
| Number of re-constitution syringes | # |  |  |  |  |  |  |  |  |
| Number of safety boxes | # | 25 | 50 | 75 | 100 |  |  |  |  |
| Total value to be co-financed by the country | $ | 5,000 | 14,000 | 20,000 | 28,000 |  |  |  |  |

Table 1.1  B - Rounded up portion of supply that is procured by GAVI and estimate of related cost in US$.

| Required supply item |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of vaccine doses | # | 5,300 | 6,200 | 4,200 | 2,600 |  |  |  |  |
| Number of AD syringes | # | 5,700 | 6,600 | 4,400 | 2,700 |  |  |  |  |
| Number of re-constitution syringes | # |  |  |  |  |  |  |  |  |
| Number of safety boxes | # | 75 | 75 | 50 | 50 |  |  |  |  |
| Total value to be co-financed by the country | $ | 20,000 | 23,500 | 15,500 | 9,500 |  |  |  |  |

Table 1.1  C - Summary table for Pneumococcal (PCV13), 1 doses/vial, Liquid

|  | Data from |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of Surviving infants | Table 1 | # | 3,278 | 3,337 | 3,397 | 3,458 |  |  |  |  |
| Number of children to be vaccinated with the third dose[1] | Table 1 | # | 1,639 | 2,836 | 2,955 | 3,112 |  |  |  |  |
| Immunisation coverage with the last dose | Table 1 | # | 50.00% | 84.99% | 86.99% | 89.99% |  |  |  |  |
| Number of children to be vaccinated with the first dose | Table 1 | # | 1,639 | 2,836 | 2,955 | 3,112 |  |  |  |  |
| Number of doses per child |  | # | 3 | 3 | 3 | 3 |  |  |  |  |
| Estimated vaccine wastage factor | Table 6.(n).3[2] | # | 1.05 | 1.05 | 1.05 | 1.05 |  |  |  |  |
| Number of doses per vial |  | # | 1 | 1 | 1 | 1 |  |  |  |  |
| AD syringes required |  | # | Yes | Yes | Yes | Yes |  |  |  |  |
| Reconstitution syringes required |  | # | No | No | No | No |  |  |  |  |
| Safety boxes required |  | # | Yes | Yes | Yes | Yes |  |  |  |  |
| Vaccine price per dose |  | $ | 3.500 | 3.500 | 3.500 | 3.500 |  |  |  |  |
| Country co-financing per dose | Table 6.(n).2[2] | $ | 0.70 | 1.40 | 2.10 | 2.80 |  |  |  |  |
| AD syringe price per unit |  | $ | 0.053 | 0.053 | 0.053 | 0.053 |  |  |  |  |
| Reconstitution syringe price per unit |  | $ |  |  |  |  |  |  |  |  |
| Safety box price per unit |  | $ | 0.640 | 0.640 | 0.640 | 0.640 |  |  |  |  |
| Freight cost as % of vaccines value |  | % | 5.00 | 5.00 | 5.00 | 5.00 |  |  |  |  |
| Freight cost as % of devices value |  | % | 10.00 | 10.00 | 10.00 | 10.00 |  |  |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Where (n) depends on the vaccine

# Table 1.1 D - Estimated number of doses for Pneumococcal (PCV13), 1 doses/vial, Liquid associated injection safety material and related co-financing budget (page 1)

|  |  | Formula | 2012 |  |  | 2013 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Total | Government | GAVI | Total | Government | GAVI |
| A | Country Co-finance |  | 18.69% |  |  | 37.38% |  |  |
| B | Number of children to be vaccinated with the first dose[1] | Table 1 (baseline & annual targets) | 1,639 | 307 | 1,332 | 2,836 | 1,061 | 1,775 |
| C | Number of doses per child | Vaccine parameter | 3 | 3 | 3 | 3 | 3 | 3 |
| D | Number of doses needed | B * C | 4,917 | 919 | 3,998 | 8,508 | 3,181 | 5,327 |
| E | Estimated vaccine wastage factor | Table 6.(n).3. in NVS section[2] | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 |
| F | Number of doses needed including wastage | D * E | 5,163 | 965 | 4,198 | 8,934 | 3,340 | 5,594 |
| G | Vaccines buffer stock | (F - F of previous year) * 0.25 | 1,291 | 242 | 1,049 | 943 | 353 | 590 |
| I | Total vaccine doses needed | F + G | 6,454 | 1,207 | 5,247 | 9,877 | 3,692 | 6,185 |
| J | Number of doses per vial | Vaccine parameter | 1 | 1 | 1 | 1 | 1 | 1 |
| K | Number of AD syringes (+ 10% wastage) needed | (D + G) * 1.11 | 6,891 | 1,288 | 5,603 | 10,491 | 3,922 | 6,569 |
| L | Reconstitution syringes (+ 10% wastage) needed | I / J * 1.11 |  |  |  |  |  |  |
| M | Total of safety boxes (+ 10% of extra need) needed | (K + L) / 100 x 1.11 | 77 | 15 | 62 | 117 | 44 | 73 |
| N | Cost of vaccines needed | I * vaccine price per dose | 22,589 | 4,222 | 18,367 | 34,570 | 12,922 | 21,648 |
| O | Cost of AD syringes needed | K * AD syringe price per unit | 366 | 69 | 297 | 557 | 209 | 348 |
| P | Cost of reconstitution syringes needed | L * reconstitution price per unit |  |  |  |  |  |  |
| Q | Cost of safety boxes needed | M * safety box price per unit | 50 | 10 | 40 | 75 | 29 | 46 |
| R | Freight cost for vaccines needed | N * freight cost as % of vaccines value | 1,130 | 212 | 918 | 1,729 | 647 | 1,082 |
| S | Freight cost for devices needed | (O + P + Q) * freight cost as % of devices value | 42 | 8 | 34 | 64 | 24 | 40 |
| T | Total fund needed | (N + O + P + Q + R + S) | 24,177 | 4,518 | 19,659 | 36,995 | 13,828 | 23,167 |
| U | Total country co-financing | I * country co-financing per dose | 4,518 |  |  | 13,828 |  |  |
| V | Country co-financing % of GAVI supported proportion | U / T | 18.69% |  |  | 37.38% |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Where (n) depends on the vaccine

# Table 1.1 D - Estimated number of doses for Pneumococcal (PCV13), 1 doses/vial, Liquid associated injection safety material and related co-financing budget (page 2)

|  |  | Formula | 2014 |  |  | 2015 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Total | Government | GAVI | Total | Government | GAVI |
| A | Country Co-finance |  | 56.07% |  |  | 74.76% |  |  |
| B | Number of children to be vaccinated with the first dose[1] | Table 1 (baseline & annual targets) | 2,955 | 1,657 | 1,298 | 3,112 | 2,327 | 785 |
| C | Number of doses per child | Vaccine parameter (schedule) | 3 | 3 | 3 | 3 | 3 | 3 |
| D | Number of doses needed | B * C | 8,865 | 4,971 | 3,894 | 9,336 | 6,980 | 2,356 |
| E | Estimated vaccine wastage factor | Table 6.(n).3. in NVS section[2] | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 |
| F | Number of doses needed including wastage | D * E | 9,309 | 5,220 | 4,089 | 9,803 | 7,329 | 2,474 |
| G | Vaccines buffer stock | (F - F of previous year) * 0.25 | 94 | 53 | 41 | 124 | 93 | 31 |
| I | Total vaccine doses needed | F + G | 9,403 | 5,273 | 4,130 | 9,927 | 7,422 | 2,505 |
| J | Number of doses per vial | Vaccine parameter | 1 | 1 | 1 | 1 | 1 | 1 |
| K | Number of AD syringes (+ 10% wastage) needed | (D + G) * 1.11 | 9,945 | 5,577 | 4,368 | 10,501 | 7,851 | 2,650 |
| L | Reconstitution syringes (+ 10% wastage) needed | I / J * 1.11 |  |  |  |  |  |  |
| M | Total of safety boxes (+ 10% of extra need) needed | (K + L) / 100 x 1.11 | 111 | 63 | 48 | 117 | 88 | 29 |
| N | Cost of vaccines needed | I * vaccine price per dose | 32,911 | 18,454 | 14,457 | 34,745 | 25,977 | 8,768 |
| O | Cost of AD syringes needed | K * AD syringe price per unit | 528 | 297 | 231 | 557 | 417 | 140 |
| P | Cost of reconstitution syringes needed | L * reconstitution price per unit |  |  |  |  |  |  |
| Q | Cost of safety boxes needed | M * safety box price per unit | 72 | 41 | 31 | 75 | 57 | 18 |
| R | Freight cost for vaccines needed | N * freight cost as % of vaccines value | 1,646 | 923 | 723 | 1,738 | 1,300 | 438 |
| S | Freight cost for devices needed | (O + P + Q) * freight cost as % of devices value | 60 | 34 | 26 | 64 | 48 | 16 |
| T | Total fund needed | (N + O + P + Q + R + S) | 35,217 | 19,747 | 15,470 | 37,179 | 27,796 | 9,383 |
| U | Total country co-financing | I * country co-financing per dose | 19,747 |  |  | 27,796 |  |  |
| V | Country co-financing % of GAVI supported proportion | U / T | 56.07% |  |  | 74.76% |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Where (n) depends on the vaccine

# Annex 2

Estimated prices of supply and related freight cost: 2011 from UNICEF Supply Division; 2012 onwards: GAVI Secretariat

Table A - Commodities Cost

| Vaccine | Presentation | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| AD syringe | 0 | 0.053 | 0.053 | 0.053 | 0.053 | 0.053 | 0.053 | 0.053 |
| DTP-HepB | 2 | 1.600 |  |  |  |  |  |  |
| DTP-HepB | 10 | 0.620 | 0.620 | 0.620 | 0.620 | 0.620 | 0.620 | 0.620 |
| DTP-HepB-Hib | WAP | 2.580 | 2.470 | 2.320 | 2.030 | 1.850 | 1.850 | 1.850 |
| DTP-HepB-Hib | WAP | 2.580 | 2.470 | 2.320 | 2.030 | 1.850 | 1.850 | 1.850 |
| DTP-HepB-Hib | WAP | 2.580 | 2.470 | 2.320 | 2.030 | 1.850 | 1.850 | 1.850 |
| DTP-Hib | 10 | 3.400 | 3.400 | 3.400 | 3.400 | 3.400 | 3.200 | 3.200 |
| HepB monoval | 1 |  |  |  |  |  |  |  |
| HepB monoval | 2 |  |  |  |  |  |  |  |
| Hib monoval | 1 | 3.400 |  |  |  |  |  |  |
| Measles | 10 | 0.240 | 0.240 | 0.240 | 0.240 | 0.240 | 0.240 | 0.240 |
| Pneumococcal(PCV10) | 2 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 |
| Pneumococcal(PCV13) | 1 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 |
| Reconstit syringe for Pentaval (2ml) | 0 | 0.032 | 0.032 | 0.032 | 0.032 | 0.032 | 0.032 | 0.032 |
| Reconstit syringe for YF | 0 | 0.038 | 0.038 | 0.038 | 0.038 | 0.038 | 0.038 | 0.038 |
| Rotavirus 2-dose schedule | 1 | 7.500 | 6.000 | 5.000 | 4.000 | 3.600 | 3.600 | 3.600 |
| Rotavirus 3-dose schedule | 1 | 5.500 | 4.000 | 3.333 | 2.667 | 2.400 | 2.400 | 2.400 |
| Safety box | 0 | 0.640 | 0.640 | 0.640 | 0.640 | 0.640 | 0.640 | 0.640 |
| Yellow Fever | WAP | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 |
| Yellow Fever | WAP | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 |

Note: WAP - weighted average price (to be used for any presentation: For DTP-HepB-Hib, it applies to 1 dose liquid, 2 dose lyophilised and 10 dose liquid. For Yellow Fever, it applies to 5 dose lyophilised and 10 dose lyophilised)

Table B - Commodities Freight Cost

| Vaccines | Group | No Threshold | 200’000 $ |  | 250’000 $ |  | 2’000’000 $ |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | <= | > | <= | > | <= | > |
| Yellow Fever | Yellow Fever |  | 20% |  |  |  | 10% | 5% |
| DTP+HepB | HepB and or Hib | 2% |  |  |  |  |  |  |
| DTP-HepB-Hib | HepB and or Hib |  |  |  | 15% | 3,50% |  |  |
| Pneumococcal vaccine (PCV10) | Pneumococcal | 5% |  |  |  |  |  |  |
| Pneumococcal vaccine (PCV13) | Pneumococcal | 5% |  |  |  |  |  |  |
| Rotavirus | Rotavirus | 5% |  |  |  |  |  |  |
| Measles | Measles | 10% |  |  |  |  |  |  |

Table C - Graduating - Minimum country's co-payment per dose of co-financed vaccine.

| vaccine | 2012 | 2013 | 2014 | 2015 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Pneumococcal(PCV13), 1 doses/vial, Liquid | 0.70 | 1.40 | 2.10 | 2.80 |  |  |  |

Table D - Wastage rates and factors

Countries are expected to plan for a maximal wastage rate of:

- 50% - for a lyophilised vaccine in 10 or 20-dose vial,

- 25% - for a liquid vaccine in 10 or 20-dose vial or a lyophilised vaccine in 5-dose vial,

- 10% - for a lyophilised/liquid vaccine in 2-dose vial, and

- 5% - for a liquid vaccine in 1-dose vial

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2 | 2.22 | 2.5 |

WHO International shipping guidelines: maximum packed volumes of vaccines

Table E - Vaccine maximum packed volumes

| Vaccine product | Designation | Vaccine formulation | Admin route | No. Of doses in the schedule | Presentation (doses/vial, prefilled) | Packed volume vaccine (cm3/dose) | Packed volume diluents (cm3/dose) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| BCG | BCG | lyophilized | ID | 1 | 20 | 1.2 | 0.7 |
| Diphtheria-Tetanus-Pertussis | DTP | liquid | IM | 3 | 20 | 2.5 |  |
| Diphtheria-Tetanus-Pertussis | DTP | liquid | IM | 3 | 10 | 3.0 |  |
| Diphtheria-Tetanus | DT | liquid | IM | 3 | 10 | 3.0 |  |
| Tetanus-Diphtheria | Td | liquid | IM | 2 | 10 | 3.0 |  |
| Tetanus Toxoid | TT | liquid | IM | 2 | 10 | 3.0 |  |
| Tetanus Toxoid | TT | liquid | IM | 2 | 20 | 2.5 |  |
| Tetanus Toxoid UniJect | TT | liquid | IM | 2 | Uniject | 12.0 |  |
| Measles | Measles | lyophilized | SC | 1 | 1 | 26.1 | 20.0 |
| Measles | Measles | lyophilized | SC | 1 | 2 | 13.1 | 13.1 |
| Measles | Measles | lyophilized | SC | 1 | 5 | 5.2 | 7.0 |
| Measles | Measles | lyophilized | SC | 1 | 10 | 3.5 | 4.0 |
| Measles-Rubella freeze dried | MR | lyophilized | SC | 1 | 1 | 26.1 | 26.1 |
| Measles-Rubella freeze dried | MR | lyophilized | SC | 1 | 2 | 13.1 | 13.1 |
| Measles-Rubella freeze dried | MR | lyophilized | SC | 1 | 5 | 5.2 | 7.0 |
| Measles-Rubella freeze dried | MR | lyophilized | SC | 1 | 10 | 2.5 | 4.0 |
| Measles-Mumps-Rubella freeze dried | MMR | lyophilized | SC | 1 | 1 | 26.1 | 26.1 |
| Measles-Mumps-Rubella freeze dried | MMR | lyophilized | SC | 1 | 2 | 13.1 | 13.1 |
| Measles-Mumps-Rubella freeze dried | MMR | lyophilized | SC | 1 | 5 | 5.2 | 7.0 |
| Measles-Mumps-Rubella freeze dried | MMR | lyophilized | SC | 1 | 10 | 3.0 | 4.0 |
| Polio | OPV | liquid | Oral | 4 | 10 | 2.0 |  |
| Polio | OPV | liquid | Oral | 4 | 20 | 1.0 |  |
| Yellow fever | YF | lyophilized | SC | 1 | 5 | 6.5 | 7.0 |
| Yellow fever | YF | lyophilized | SC | 1 | 10 | 2.5 | 3.0 |
| Yellow fever | YF | lyophilized | SC | 1 | 20 | 1.5 | 2.0 |
| Yellow fever | YF | lyophilized | SC | 1 | 50 | 0.7 | 1.0 |
| DTP-HepB combined | DTP-HepB | liquid | IM | 3 | 1 | 9.7 |  |
| DTP-HepB combined | DTP-HepB | liquid | IM | 3 | 2 | 6.0 |  |
| DTP-HepB combined | DTP-HepB | liquid | IM | 3 | 10 | 3.0 |  |
| Hepatitis B | HepB | liquid | IM | 3 | 1 | 18.0 |  |
| Hepatitis B | HepB | liquid | IM | 3 | 2 | 13.0 |  |
| Hepatitis B | HepB | liquid | IM | 3 | 6 | 4.5 |  |
| Hepatitis B | HepB | liquid | IM | 3 | 10 | 4.0 |  |
| Hepatitis B UniJect | HepB | liquid | IM | 3 | Uniject | 12.0 |  |
| Hib liquid | Hib_liq | liquid | IM | 3 | 1 | 15.0 |  |
| Hib liquid | Hib_liq | liquid | IM | 3 | 10 | 2.5 |  |
| Hib freeze-dried | Hib_lyo | lyophilized | IM | 3 | 1 | 13.0 | 35.0 |
| Hib freeze-dried | Hib_lyo | lyophilized | IM | 3 | 2 | 6.0 |  |
| Hib freeze-dried | Hib_lyo | lyophilized | IM | 3 | 10 | 2.5 | 3.0 |
| DTP liquid + Hib freeze-dried | DTP+Hib | liquid+lyop. | IM | 3 | 1 | 45.0 |  |
| DTP-Hib combined liquid | DTP+Hib | liquid+lyop. | IM | 3 | 10 | 12.0 |  |
| DTP-Hib combined liquid | DTP-Hib | liquid | IM | 3 | 1 | 32.3 |  |
| DTP-HepB liquid + Hib freeze-dried | DTP-Hib | liquid | IM | 3 | 10 | 2.5 |  |
| DTP-HepB liquid + Hib freeze-dried | DTP-HepB+Hib | liquid+lyop. | IM | 3 | 1 | 22.0 |  |
| DTP-HepB-Hib liquid | DTP-HepB+Hib | liquid+lyop. | IM | 3 | 2 | 11.0 |  |
| DTP-HepB-Hib liquid | DTP-HepB-Hib | liquid | IM | 3 | 10 | 4.4 |  |
| DTP-HepB-Hib liquid | DTP-HepB-Hib | liquid | IM | 3 | 2 | 13.1 |  |
| DTP-HepB-Hib liquid | DTP-HepB-Hib | liquid | IM | 3 | 1 | 19.2 |  |
| Meningitis A/C | MV_A/C | lyophilized | SC | 1 | 10 | 2.5 | 4.0 |
| Meningitis A/C | MV_A/C | lyophilized | SC | 1 | 50 | 1.5 | 3.0 |
| Meningococcal A/C/W/ | MV_A/C/W | lyophilized | SC | 1 | 50 | 1.5 | 3.0 |
| Meningococcal A/C/W/Y | MV_A/C/W/Y | lyophilized | SC | 1 | 10 | 2.5 | 4.0 |
| Meningitis W135 | MV_W135 | lyophilized | SC | 1 | 10 | 2.5 | 4.0 |
| Meningitis A conjugate | Men_A | lyophilized | SC | 2 | 10 | 2.6 | 4.0 |
| Japanese Encephalitis | JE_lyo | lyophilized | SC | 3 | 10 | 15.0 |  |
| Japanese Encephalitis | JE_lyo | lyophilized | SC | 3 | 10 | 8.1 | 8.1 |
| Japanese Encephalitis | JE_lyo | lyophilized | SC | 3 | 5 | 2.5 | 2.9 |
| Japanese Encephalitis | JE_lyo | lyophilized | SC | 3 | 1 | 12.6 | 11.5 |
| Japanese Encephalitis | JE_liq | liquid | SC | 3 | 10 | 3.4 |  |
| Rota vaccine | Rota_lyo | lyophilized | Oral | 2 | 1 | 156.0 |  |
| Rota vaccine | Rota_liq | liquid | Oral | 2 | 1 | 17.1 |  |
| Rota vaccine | Rota_liq | liquid | Oral | 3 | 1 | 45.9 |  |
| Pneumo. conjugate vaccine 7-valent | PCV-7 | liquid | IM | 3 | PFS | 55.9 |  |
| Pneumo. conjugate vaccine 7-valent | PCV-7 | liquid | IM | 3 | 1 | 21.0 |  |
| Pneumo. conjugate vaccine 10-valent | PCV-10 | liquid | IM | 3 | 1 | 11.5 |  |
| Pneumo. conjugate vaccine 10-valent | PCV-10 | liquid | IM | 3 | 2 | 4.8 |  |
| Pneumo. conjugate vaccine 13-valent | PCV-13 | liquid | IM | 3 | 1 | 12.0 |  |
| Polio inactivated | IPV | liquid | IM | 3 | PFS | 107.4 |  |
| Polio inactivated | IPV | liquid | IM | 3 | 10 | 2.5 |  |
| Polio inactivated | IPV | liquid | IM | 3 | 1 | 15.7 |  |
| Human Papilomavirus vaccine | HPV | liquid | IM | 3 | 1 | 15.0 |  |
| Human Papilomavirus vaccine | HPV | liquid | IM | 3 | 2 | 5.7 |  |
| Monovalent OPV-1 | mOPV1 | liquid | Oral |  | 20 | 1.5 |  |
| Monovalent OPV-3 | mOPV3 | liquid | Oral |  | 20 | 1.5 |  |

# Attachments

# List of Supporting Documents Attached to this Proposal

| Document | Section | Document Number | Mandatory[1] |
| --- | --- | --- | --- |
| MoH Signature (or delegated authority) of Proposal |  | 5 | Yes |
| MoF Signature (or delegated authority) of Proposal |  | 9 | Yes |
| Signatures of ICC or HSCC or equivalent in Proposal |  | 6 | Yes |
| Minutes of ICC/HSCC meeting endorsing Proposal |  | 7 | Yes |
| comprehensive Multi Year Plan - cMYP |  | 1 | Yes |
| cMYP Costing tool for financial analysis |  | 2 | Yes |
| Minutes of last three ICC/HSCC meetings |  | 8 | Yes |
| Improvement plan based on EVM |  | Missing | Yes |
| WHO/UNICEF Joint Reporting Form (JRF) |  |  |  |
| ICC/HSCC workplan for forthcoming 12 months |  |  |  |
| National policy on injection safety |  |  |  |
| Action plans for improving injection safety |  |  |  |
| Plan for NVS introduction (if not part of cMYP) |  |  |  |
| Banking details |  | 4 |  |

[1] Please indicate the duration of the plan / assessment / document where appropriate

# Attachments

List of all the mandatory and optional documents attached to this form

Note: Use the Upload file arrow icon to upload the document. Use the Delete item icon to delete a line. To add new lines click on the New item icon in the Action column.

| ID | File type | File name |  | New file | Actions |
| --- | --- | --- | --- | --- | --- |
|  | Description | Date and Time | Size |  |  |
| 1 | File Type: comprehensive Multi Year Plan - cMYP * File Desc: | File name: C:\Users\dchangblanc\Documents\DATA\2011\Countries\PIC\Kiribati\cMYP finals\absolute finals\DOC_ONE_cMYP_Kiribati_FINAL_19May.pdf Date/Time: 19.05.2011 09:37:00 Size: 869 KB |  |  |  |
| 2 | File Type: cMYP Costing tool for financial analysis * File Desc: | File name: C:\Users\dchangblanc\Documents\DATA\2011\Countries\PIC\Kiribati\cMYP finals\absolute finals\DOC TWO_Kiribati_cMYP_Costing_2011-2015_FINAL_19May.xls Date/Time: 19.05.2011 09:37:42 Size: 3 MB |  |  |  |
| 3 | File Type: other File Desc: Document Three PCV13 introduction plan | File name: C:\Users\dchangblanc\Documents\DATA\2011\Countries\PIC\Kiribati\cMYP finals\absolute finals\DOC THREE_Pneumo_IntroPlan_Kiribati.xlsx Date/Time: 19.05.2011 09:38:26 Size: 15 KB |  |  |  |
| 4 | File Type: Banking details File Desc: Banking details | File name: C:\Users\ihilman\Desktop\Y Drive\Tikua GAVI\Final docs\Attachments GAVI application KIR\Banking detail Form Kiribati.pdf Date/Time: 21.05.2011 05:32:21 Size: 103 KB |  |  |  |
| 5 | File Type: MoH Signature (or delegated authority) of Proposal * File Desc: Minister of Health Kiribati signature | File name: C:\Users\ihilman\Desktop\Y Drive\Tikua GAVI\Final docs\Attachments GAVI application KIR\Ministers Signature.pdf Date/Time: 21.05.2011 05:33:44 Size: 138 KB |  |  |  |
| 6 | File Type: Signatures of ICC or HSCC or equivalent in Proposal * File Desc: Signatures of ICC members Kiribati | File name: C:\Users\ihilman\Desktop\Y Drive\Tikua GAVI\Final docs\Attachments GAVI application KIR\Signature of ICC Members.pdf Date/Time: 21.05.2011 05:35:10 Size: 137 KB |  |  |  |
| 7 | File Type: Minutes of ICC/HSCC meeting endorsing Proposal * File Desc: Minute of ICC endorsement for GAVI new vaccine application | File name: C:\Users\ihilman\Desktop\Y Drive\Tikua GAVI\Final docs\Attachments GAVI application KIR\ICC meeting,endorsement of Gavi application.pdf Date/Time: 21.05.2011 05:36:41 Size: 109 KB |  |  |  |
| 8 | File Type: Minutes of last three ICC/HSCC meetings * File Desc: Minutes of ICC meetings in 2010 | File name: C:\Users\ihilman\Desktop\Y Drive\Tikua GAVI\Final docs\Attachments GAVI application KIR\3_ICC_meeting_minutes_of_2010.pdf Date/Time: 21.05.2011 05:48:57 Size: 541 KB |  |  |  |
| 9 | File Type: MoF Signature (or delegated authority) of Proposal * File Desc: Minister of Finance signature. | File name: C:\Users\ihilman\Desktop\Y Drive\Tikua GAVI\Final docs\Attachments GAVI application KIR\Ministers Signature.pdf Date/Time: 21.05.2011 05:53:13 Size: 138 KB |  |  |  |