GAVI Alliance

Application Form for Country Proposals

For Support to New and Under-Used Vaccines (NVS)

Submitted by

The Government of

Uganda

Date of submission: 24.05.2011 06:47:45

Deadline for submission: 1 Jun 2011

Select Start and End Year of your Comprehensive Multi-Year Plan (cMYP)

| Start Year | 2010 | End Year | 2014 |
| --- | --- | --- | --- |

Revised in January 2011

(To be used with Guidelines of December 2010)

Please submit the Proposal using the online platform https://AppsPortal.gavialliance.org/PDExtranet.

Enquiries to: proposals@gavialliance.org or representatives of a GAVI partner agency. The documents can be shared with GAVI partners, collaborators and general public. The Proposal and attachments must be submitted in English, French, Spanish, or Russian.

Note: Please ensure that the application has been received by the GAVI Secretariat on or before the day of the deadline.

The GAVI Secretariat is unable to return submitted documents and attachments to countries. Unless otherwise specified, documents will be shared with the GAVI Alliance partners and the general public.

GAVI ALLIANCE GRANT TERMS AND CONDITIONS FUNDING USED SOLELY FOR APPROVED PROGRAMMES The applicant country (“Country”) confirms that all funding provided by the GAVI Alliance will be used and applied for the sole purpose of fulfilling the programme(s) described in the Country’s application. Any significant change from the approved programme(s) must be reviewed and approved in advance by the GAVI Alliance. All funding decisions for the application are made at the discretion of the GAVI Alliance Board and are subject to IRC processes and the availability of funds. AMENDMENT TO THE APPLICATION The Country will notify the GAVI Alliance in its Annual Progress Report if it wishes to propose any change to the programme(s) description in its application. The GAVI Alliance will document any change approved by the GAVI Alliance, and the Country’s application will be amended. RETURN OF FUNDS The Country agrees to reimburse to the GAVI Alliance all funding amounts that are not used for the programme(s) described in its application. The country’s reimbursement must be in US dollars and be provided, unless otherwise decided by the GAVI Alliance, within sixty (60) days after the Country receives the GAVI Alliance’s request for a reimbursement and be paid to the account or accounts as directed by the GAVI Alliance. SUSPENSION/ TERMINATION The GAVI Alliance may suspend all or part of its funding to the Country if it has reason to suspect that funds have been used for purpose other than for the programmes described in the Country’s application, or any GAVI Alliance-approved amendment to the application. The GAVI Alliance retains the right to terminate its support to the Country for the programmes described in its application if a misuse of GAVI Alliance funds is confirmed. ANTICORRUPTION The Country confirms that funds provided by the GAVI Alliance shall not be offered by the Country to any third person, nor will the Country seek in connection with its application any gift, payment or benefit directly or indirectly that could be construed as an illegal or corrupt practice. AUDITS AND RECORDS The Country will conduct annual financial audits, and share these with the GAVI Alliance, as requested. The GAVI Alliance reserves the right, on its own or through an agent, to perform audits or other financial management assessment to ensure the accountability of funds disbursed to the Country. The Country will maintain accurate accounting records documenting how GAVI Alliance funds are used. The Country will maintain its accounting records in accordance with its government-approved accounting standards for at least three years after the date of last disbursement of GAVI Alliance funds. If there is any claims of misuse of funds, Country will maintain such records until the audit findings are final. The Country agrees not to assert any documentary privilege against the GAVI Alliance in connection with any audit. CONFIRMATION OF LEGAL VALIDITY The Country and the signatories for the Country confirm that its application, and Annual Progress Report, are accurate and correct and form legally binding obligations on the Country, under the Country’s law, to perform the programmes described in its application, as amended, if applicable, in the APR. CONFIRMATION OF COMPLIANCE WITH THE GAVI ALLIANCE TRANSPARANCY AND ACCOUNTABILITY POLICY The Country confirms that it is familiar with the GAVI Alliance Transparency and Accountability Policy (TAP) and complies with the requirements therein. USE OF COMMERCIAL BANK ACCOUNTS The Country is responsible for undertaking the necessary due diligence on all commercial banks used to manage GAVI cash-based support. The Country confirms that it will take all responsibility for replenishing GAVI cash support lost due to bank insolvency, fraud or any other unforeseen event. ARBITRATION Any dispute between the Country and the GAVI Alliance arising out of or relating to its application that is not settled amicably within a reasonable period of time, will be submitted to arbitration at the request of either the GAVI Alliance or the Country. The arbitration will be conducted in accordance with the then-current UNCITRAL Arbitration Rules. The parties agree to be bound by the arbitration award, as the final adjudication of any such dispute. The place of arbitration will be Geneva, Switzerland. The language of the arbitration will be English. For any dispute for which the amount at issue is US$ 100,000 or less, there will be one arbitrator appointed by the GAVI Alliance. For any dispute for which the amount at issue is greater than US $100,000 there will be three arbitrators appointed as follows: The GAVI Alliance and the Country will each appoint one arbitrator, and the two arbitrators so appointed will jointly appoint a third arbitrator who shall be the chairperson. The GAVI Alliance will not be liable to the country for any claim or loss relating to the programmes described in the application, including without limitation, any financial loss, reliance claims, any harm to property, or personal injury or death. Country is solely responsible for all aspects of managing and implementing the programmes described in its application.

# Application Specification

Please specify for which type of GAVI support you would like to apply to.

Important note: To enable proper functioning of the form, please first select the cMYP years on the previous page.

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Type of Support | Vaccine | Start Year | End Year | Preferred second presentation[1] | Action |
| --- | --- | --- | --- | --- | --- |
| New Vaccines Support | Pneumococcal (PCV10), 2 doses/vial, Liquid | 2013 | 2014 | Pneumococcal (PCV13), 1 doses/vial, Liquid |  |

[1] This "Preferred second presentation" will be used in case there is no supply available for the preferred presentation of the selected vaccine ("Vaccine" column). If left blank, it will be assumed that the country will prefer waiting until the selected vaccine becomes available.

# Table of Contents

Sections

Main

Cover Page

GAVI Alliance Grants Terms and Conditions

1. Application Specification

2. Table of Contents

3. Executive Summary

4. Signatures

4.1. Signatures of the Government and National Coordinating Bodies

4.1.1. Government and the Inter-Agency Coordinating Committee for Immunisation

4.1.2. National Coordinating Body - Inter-Agency Coordinating Committee for Immunisation

4.1.3. The Inter-Agency Coordinating Committee for Immunisation

4.2. National Immunization Technical Advisory Group for Immunisation

4.2.1. The NITAG Group for Immunisation

5. Immunisation Programme Data

5.1. Basic facts

5.2. Current vaccination schedule

5.3. Trends of immunisation coverage and disease burden

5.4. Baseline and Annual Targets

Table 1: baseline figures

5.5. Summary of current and future immunisation budget

5.6. Summary of current and future financing and sources of funds

6. NVS

6.1. Capacity and cost (for positive storage)

6.2. Assessment of burden of relevant diseases (if available)

6.3.1. Requested vaccine ( Pneumococcal (PCV10), 2 doses/vial, Liquid )

6.3.2. Co-financing information

6.3.3. Wastage factor

6.3.4. Specifications of vaccinations with new vaccine

6.3.5. Portion of supply to be procured by the country (and cost estimate, US$)

6.3.6. Portion of supply to be procured by the GAVI Alliance (and cost estimate, US$)

6.3.7. New and Under-Used Vaccine Introduction Grant

7. Procurement and Management of New and Under-Used Vaccines

7.1. Vaccine management (EVSM/EVM/VMA)

8. Additional Comments and Recommendations

9. Annexes

Annex 1

Annex 1.1 - Pneumococcal (PCV10), 2 doses/vial, Liquid

Table 1.1  A - Rounded up portion of supply that is procured by the country and estimate of related cost in US$

Table 1.1  B - Rounded up portion of supply that is procured by GAVI and estimate of related cost in US$.

Table 1.1  C - Summary table for vaccine Pneumococcal (PCV10), 2 doses/vial, Liquid

Table 1.1  D - Estimated number of doses for vaccine Pneumococcal (PCV10), 2 doses/vial, Liquid associated injection safety material and related co-financing budget

Annex 2

10. Attachments

10.1 Documents required for NVS support

10.2 Attachments

Banking Form

# Executive Summary

Uganda is an East African country with a total area of 241,139 square kilometers with an estimated total population of 30.1 million people (projected from the 2002 Census) of which 4.3% constitute the under 1 year old. Majority (88%) of the population lives in rural areas. It shares borders with Sudan (North), Kenya (East), Tanzania and Rwanda (South) and Democratic Republic of Congo in the West. 1.	Uganda had 80 districts as of 1st January 2010 but effective 1st July, the total number of districts increased to 112. The districts are further sub divided into 214 health sub districts. Some of the districts in the north and northeast have been affected by a period of prolonged conflict resulting in large-scale population displacement which has affected health services delivery and most of these districts have been unable to achieve the national targets for their health indicators.
The Government of Uganda is working towards the achievement of the Millennium Development Goals (MDGs).The Ministry of Health established the Health Policy Advisory Committee (HPAC) an overall body advising on policy issues and strategies. Eight Technical Working Groups (TWGs) were established to support HPAC and are responsible for strategic planning, coordination, monitoring and evaluation. EPI falls within the maternal and child health sub committee of the basic package TWG and has 3 major areas of focus which include strengthening routine immunization, conducting supplemental immunization activities to achieve polio eradication, eliminate maternal and neonatal tetanus and accelerated measles control and sustaining a sensitive disease surveillance system for vaccine preventable diseases within the integrated disease surveillance and response framework. It is implementing the activities using the Global Immunization Vision and Strategy (GIVS) approach. 
Delivery of health services is decentralized to the district and health sub district level. The district level is responsible for planning, monitoring and supervision of health services including EPI services while the health sub district is responsible for delivery of health services through several health facilities using the primary health care strategy. 
The infant and under-five mortality rates are relatively high at 78/1000 live births and 145/1000 live births respectively but are on a decline trend. The major causes of morbidity in the under five year old are malaria, upper respiratory tract infections, pneumonia and diarrheal diseases. 
Routine immunization coverage in Uganda increased until 1995 but then experienced a downward trend between 1996 and 2000, with DTP3 coverage decreasing from 72% in 1996 to 56% in 2000. This was attributed to inadequate community awareness on the benefits of immunization coupled with rumors; poor accessibility to immunization services; inadequate capacity for management and delivery of immunization services and weak community involvement among others. A strategic multi year plan for 2001 - 2005 was developed as part of the EPI revitalization plan to address the weaknesses identified. Significant investments were put in place including GAVI Alliance support during that period. Furthermore, Uganda added hepatitis B and Haemophilus influenzae type b (Hib) (Pentavalent) to the traditional vaccines in June 2002. Routine immunization coverage steadily improved from the year 2002 to 2005 when it peaked. There was stagnation and gradual decline from 2007 to 2008. Uganda currently has multi year plan of 2010 - 2014 of which introduction of new vaccines is considered. 

The country used 3 approaches to estimate the burden of invasive pneumococcal disease namely WHO estimates, public health sentinel surveillance system and cost effectiveness studies for Uganda. The country has few population based studies on pneumococcal disease burden. In 2000, WHO estimated that streptococcus pneumonia was responsible for 18,995 deaths annually among the Ugandan children less than 5 years of age. Secondly WHO has also estimated that the overall incidence of invasive pneumococcal disease (meningitis and pneumonia among children less than 5 years of age in Uganda is 28/1,000 and 3212/1,000 respectively. With support from the World Health Organization Uganda established surveillance for pneumococcal disease in 2001 as part of the sub-Saharan Africa pediatric bacterial meningitis surveillance network. In 2003, additional support was provided by the Network for Surveillance of Pneumococcal Disease in the East African Region (netSPEAR) and PneumoADIP. The surveillance system has demonstrated that the Streptococcus pneumoniae accounts for 35% of all confirmed etiologies following introduction of Hib vaccine with an overall case fatality ratio of 19%. Yearly pneumococcal meningitis incidence varies from 3 to 20 per 100,000 children under 5 years in Kampala district, versus 28 to 42 per 100,000 in Gulu district. The Ugandan surveillance system has also demonstrated that most (83%) of the vaccine serotypes had intermediate resistance to penicillin but susceptible to cefotaxime a more expensive antibiotic and 63% of the serotypes are covered in the 10 valent PCV vaccine. From the recent cost effectiveness study, it was estimated that a pneumococcal vaccination program would save Ushs 2.565bn (US $1.245m) in direct medical costs annually. In addition, pneumococcal vaccine program will prevent 94,071 cases of Streptococcus pneumoniae and save 10,796 lives annually in children <5 years of age . 

These estimates demonstrate that Uganda has high disease rates of invasive pneumococcal disease a major cause of morbidity and mortality. Therefore introduction of pneumococcal vaccines into routine immunization program would be beneficial and a major contributor towards the reduction of disease burden in children. It is envisaged that the pneumococcal conjugate vaccine (PCV 10) would be introduced in the first quarter of 2013 in Uganda. The schedule will be in line with other EPI antigens (e.g. Pentavalent) at 6, 10 and 14 weeks. Furthermore, Uganda will switch to new formulations and presentations as soon as they are available. A pneumococcal surveillance system is currently being implemented to document the disease epidemiology, vaccine serotypes and will continue to be used to monitor the impact of PCV introduction in Uganda. 


The EPI Programme, since 1983, has been using gas-electric and solar refrigerators at health facility level for vaccine storage. The national cold chain assessment in 2007 showed that the space at central level was not adequate to accommodate new vaccines and same time vaccines for supplemental immunization activities. As part of the process for increasing the storage capacity at the central level, USAID through UNICEF in 2009, procured 2 cold rooms for the central level which were installed. In addition, JICA procured refrigerators that are currently being installed in various health facilities prior to PCV introduction.

This introduction is incorporated into the cMYP 2010-2014. Uganda will benefit from GAVI HSS and ISS support which will go a long way in strengthening the immunization programme. In this proposal the cost for introduction of pneumococcal vaccine has been quantified. Government co-financing will involve contribution of 0.20 US $ per dose, per year. This translates in US $1,980,000 for 2013 and US$ 1,014,000 for 2014. 
In 2013 GAVI will contribute US$ 21,235,500 and US$ 17,971,000 in 2014. In order to achieve the set programme goals, the country is requesting for continued support during the next five years to introduce new vaccines as part of the routine immunization programme. The country will continue with resource mobilizations for vaccine procurement and several strategies will be explored to meet the co-financing which include mobilization of additional resources from both local and external sources and increase in reliability and efficiency of resources.

# Signatures

# Signatures of the Government and National Coordinating Bodies

# Government and the Inter-Agency Coordinating Committee for Immunisation

The Government of Uganda would like to expand the existing partnership with the GAVI Alliance for the improvement of the infants routine immunisation programme of the country, and specifically hereby requests for GAVI support for Pneumococcal (PCV10) 2 doses/vial Liquid introduction.

The Government of Uganda commits itself to developing national immunisation services on a sustainable basis in accordance with the Comprehensive Multi-Year Plan (cMYP) presented with this document. The Government requests that the GAVI Alliance and its partners contribute financial and technical assistance to support immunisation of children as outlined in this application.

Tables 6.(n).5. (where (n) depends on the vaccine) in the NVS section of this application shows the amount of support in either supply or cash that is required from the GAVI Alliance. Tables 6.(n).4. of this application shows the Government financial commitment for the procurement of this new vaccine (NVS support only).

Following the regulations of the internal budgeting and financing cycles the Government will annually release its portion of the co-financing funds in the month of April .

Please note that this application will not be reviewed or approved by the Independent Review Committee (IRC) without the signatures of both the Minister of Health & Minister of Finance or their delegated authority.

Enter the family name in capital letters.

| Minister of Health (or delegated authority) |  | Minister of Finance (or delegated authority) |  |
| --- | --- | --- | --- |
| Name | Hon Dr Stephen O Mallinga | Name | Hon Syda Bbumba |
| Date |  | Date |  |
| Signature |  | Signature |  |

This report has been compiled by

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

Enter the family name in capital letters.

| Full name | Position | Telephone | Email | Action |
| --- | --- | --- | --- | --- |
| Dr. Rachel SERUYANGE | Programme Manager - UNEPI | +256 - 772 410 407 | seruyanger@yahoo.com |  |
| Ms. Pamela ZANINKA | Logistician - UNEPI | +256 - 772 409 130 | hzaninka@yahoo.com |  |
| Dr. Eva KABWONGERA | Health Specialist/EPI - UNICEF | +256 - 772 595 658 | ekabwongera@unicef.org |  |
| Dr. Annette KISAKYE | NPO/IDSR - WHO | +256 - 772 504 668 | kisakyea@ug.afro.who.int |  |
| Dr. Patrick BANURA | NPO/EPI - WHO | +256 - 782 491 510 | banurap@ug.afro.who.int |  |

# National Coordinating Body - Inter-Agency Coordinating Committee for Immunisation

We the members of the ICC, HSCC, or equivalent committee[1] met on the to review this proposal. At that meeting we endorsed this proposal on the basis of the supporting documentation which is attached.

[1] Inter-agency Coordinating Committee or Health Sector Coordinating Committee, or equivalent committee which has the authority to endorse this application in the country in question.

The endorsed minutes of this meeting are attached as DOCUMENT NUMBER: .

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

Enter the family name in capital letters.

| Name/Title | Agency/Organisation | Signature | Action |
| --- | --- | --- | --- |
| Mary L NANNONO (Chairperson of HPAC) | Ministry of Health |  |  |
| Dr. Joaquim SAWEKA, WHO Representative | WHO |  |  |
| Dr. Sharad SAPRA, UNICEF Representative | UNICEF |  |  |
| Ms. Shanda STEIMER, Acting Head of Health Development | USAID |  |  |
| Mr. Tetsuo SEKI, Resident Representative | JICA |  |  |
| Ms. Enid WAMANI, Representative of Civil Society Organizations | MACIS |  |  |

In case the GAVI Secretariat has queries on this submission, please contact

Enter the family name in capital letters.

| Name | Mary L. NANNONO | Title | Permanent Secretary |
| --- | --- | --- | --- |
| Tel no | 256-414-340-872 |  |  |
| Fax no | 256-414-231-584 | Address | Ministry of Health P. O. Box 7272 Kampala |
| Email |  |  |  |

# The Inter-Agency Coordinating Committee for Immunisation

Agencies and partners (including development partners and NGOs) supporting immunisation services are co-ordinated and organised through an inter-agency coordinating mechanism (ICC, HSCC, or equivalent committee). The ICC, HSCC, or equivalent committee is responsible for coordinating and guiding the use of the GAVI NVS support. Please provide information about the ICC, HSCC, or equivalent committee in your country in the table below.

Profile of the ICC, HSCC, or equivalent committee

| Name of the committee | Health Policy Advisory Committee (HPAC) |
| --- | --- |
| Year of constitution of the current committee | 2000 |
| Organisational structure (e.g., sub-committee, stand-alone) | HPAC is a Stand alone committee, but receives reports monthly from 9 technical working groups, MCH TWG discusses EPI issues |
| Frequency of meetings | Monthly |

Composition

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

Enter the family name in capital letters.

| Function | Title / Organisation | Name |  |
| --- | --- | --- | --- |
| Chair | Permanent Secretary, Ministry of Health | Mary L. Nannono |  |
| Secretary | Senior Health Planner, Ministry of Health | Dr. Nelson Musoba |  |
| Members | Government (Director General of Health Services) | Dr. Sam Zaramba | Action |
|  | WHO Representative | Dr. Joaquim Saweka |  |
|  | UNICEF Representative | Dr. Sharad Sapra |  |
|  | Acting Head of Development Partners | Ms. Shanda Steimer |  |
|  | Civil Society organization | Ms Enid Wamani |  |
|  | District Representative | Dr. Saraphine Adibaku |  |

Major functions and responsibilities of the committee

HPAC is the Coordinating body that advises both government and partners on the implementation of the National Health Policy and the Health Sector Strategic Plan (HSSP). Provides overall policy advice and strategic coordination of the sector. Oversees the management of annual health sector budget process.

Three major strategies to enhance the committee's role and functions in the next 12 months

| 1. | To receive, approve programme and project plans to ensure consistency with HSSP and formulating a new health policy and HSSP III. |
| --- | --- |
| 2. | To receive quarterly and annual progress reports from the Technical Working Groups and the overall sector. |
| 3. | To monitor implementation of undertakings from the Joint Review Mission. |

# National Immunization Technical Advisory Group for Immunisation

(If it has been established in the country)

We the members of the NITAG met on the to review this proposal. At that meeting we endorsed this proposal on the basis of the supporting documentation which is attached.

The endorsed minutes of this meeting are attached as DOCUMENT NUMBER: .

In case the GAVI Secretariat has queries on this submission, please contact

Enter the family name in capital letters.

| Name |  | Title |  |
| --- | --- | --- | --- |
| Tel no |  |  |  |
| Fax no |  | Address |  |
| Email |  |  |  |

# The NITAG Group for Immunisation

Profile of the NITAG

| Name of the NITAG |  |
| --- | --- |
| Year of constitution of the current NITAG |  |
| Organisational structure (e.g., sub-committee, stand-alone) |  |
| Frequency of meetings |  |

Composition

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

Enter the family name in capital letters.

| Function | Title / Organisation | Name |  |
| --- | --- | --- | --- |
| Chair |  |  |  |
| Secretary |  |  |  |
| Members |  |  | Action |

Major functions and responsibilities of the NITAG

Three major strategies to enhance the NITAG’s role and functions in the next 12 months

| 1. |  |
| --- | --- |
| 2. |  |
| 3. |  |

# Immunisation Programme Data

Please complete the tables below, using data from available sources. Please identify the source of the data, and the date. Where possible use the most recent data and attach the source document.

- Please refer to the Comprehensive Multi-Year Plan for Immunisation (cMYP) (or equivalent plan) and attach a complete copy (with an Executive Summary) as DOCUMENT NUMBER 4

- Please refer to the two most recent annual WHO/UNICEF Joint Reporting Forms (JRF) on Vaccine Preventable Diseases.

- Please refer to Health Sector Strategy documents, budgetary documents, and other reports, surveys etc, as appropriate.

# Basic facts

For the year 2010 (most recent; specify dates of data provided)

|  | Figure |  | Year | Source |
| --- | --- | --- | --- | --- |
| Total population | 31,784,700 |  | 2010 | Uganda Bureau of Statistics June release 2008 |
| Infant mortality rate (per 1000) | 76 |  | 2006 | Uganda Demographic Health Survey 2006 |
| Surviving Infants[1] | 1,424,400 |  | 2010 | Uganda Bureau of Statistics June release 2008 |
| GNI per capita (US$) | 370 |  | 2009 | The 2009 World Bank Development Indicators Online, GDP per capita is PPP adjusted |
| Total Health Expenditure (THE) as a percentage of GDP | 7.56 | % | 2007 | National Health Assembly 2006/2007 |
| General government expenditure on health (GGHE) as % of General government expenditure | 10.40 | % | 2009 | Medium Term Expenditure Framework 2009/2010 |

[1] Surviving infants = Infants surviving the first 12 months of life

Please provide some additional information on the planning and budgeting context in your country; also indicate the name and date of the relevant planning document for health

The Health Sector Strategic and Investment Plan (HSSIP) and National Health Policy II cover the period 2010/11 - 2014/15 and 2010/11 – 2019/20 respectively. These define the medium and long term health agenda and operationalise Uganda’s aspiration as outlined in the National Development Plan (NDP) of 2010/11 - 2014/15 and Public Investment Plan (PIP) 2010/11 – 2012/13. Annually, plans of action are developed by programs and aggregated into annual work plan for Ministry of Health. This also involves districts developing comprehensive work plans that feed into the national plan. The budgeting process is closely aligned with the work plan development.

Is the cMYP (or updated Multi-Year Plan) aligned with this document (timing, content, etc.)?

Yes, the cMYP plan is based on the priorities outlined in the new National Health Policy II and HSSIP. In these documents PCV and rotavirus vaccines introduction are provided for.

Please indicate the national planning budgeting cycle for health

Financial year (July to June) is the planning/budgeting cycle for health.

Please indicate the national planning cycle for immunisation

The planning cycle for immunization is similar to the national planning cycle i.e. Financial year (July to June).

Please indicate if sex disaggregated data (SDD) is used in immunisation routine reporting systems

In line with the HSSIP, gender sensitivity is emphasized. Access to immunization services is universal and thus it is assumed that both male and female infants have equal access to services. Routine childhood Immunization coverage data is collected using the Health Management Information System (HMIS). The HMIS forms which include tally sheets and summary forms, have been reviewed and have included disaggregated data for male and female. Plans are underway to train the health workers and supply the tools for use. This approach will assist the programme to generate, report and analyze new evidence affecting equity and gender. However the Demographic and Health Survey segregates data by gender (UDHS is on-going)

Please indicate if gender aspects relating to introduction of a new vaccine have been addressed in the introduction plan

The communication strategy for New Vaccine Introduction will address gender concerns including mobilization for all children, male and female have equal access to the new vaccines. Male involvement to support immunization services will be emphasized.

# Current vaccination schedule

Traditional, New Vaccines and Vitamin A supplement (refer to cMYP pages)

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Vaccine (do not use trade name) | Ages of administration (by routine immunisation services) | Given in entire country | Comments | Action |
| --- | --- | --- | --- | --- |
| BCG | At Birth (or any time after but not beyond 11 months of age) | Yes |  |  |
| Polio | 0, 6 weeks, 10 weeks, 14 weeks ( or any time between 6 weeks to 11 months of age) | Yes | Uganda uses oral polio vaccine. Polio zero is given at birth but not beyond 14 days of age. The routine schedule is 0+3. |  |
| DPT-HepB+Hib | 6 weeks, 10 weeks, 14 weeks (or any time between 6 weeks to 11 months of age) | Yes | Introduced DPT-HepB+Hib in June 2002 |  |
| Measles | 9 months (or any time between 9 months to 11 months) | Yes | Second opportunity given during follow up SIAs. |  |
| TT | 15 years - 49 years (an interval of 0, 1 month, 6 months, 1 year, 1 year) | Yes | Given to both pregnant and non pregnant women. It is a five dose schedule. |  |
| HPV | Girls 10 years - 12 years of age. (0, 1, 5 months schedule) | No | HPV vaccine (Cervarix) demonstration project in 2 districts. |  |
| Vitamin A | 6 - 59 months (given biannually with an interval of 6 months) | Yes | It is also given to postnatal mothers within 6 weeks of delivery |  |

# Trends of immunisation coverage and disease burden

(as per last two annual WHO/UNICEF Joint Reporting Form on Vaccine Preventable Diseases)

| Trends of immunisation coverage (percentage) |  |  |  |  |  | Vaccine preventable disease burden |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Vaccine |  | Reported |  | Survey |  | Disease | Number of reported cases |  |
|  |  | 2009 | 2010 | 2006 | 2005 |  | 2009 | 2010 |
| BCG |  | 90 | 86 | 91 | 93 | Tuberculosis | 4,234 | 22,369 |
| DTP | DTP1 | 96 | 87 | 90 | 89 | Diphtheria |  |  |
|  | DTP3 | 83 | 80 | 64 | 76 | Pertussis |  |  |
| Polio 3 |  | 82 | 79 | 59 |  | Polio | 8 | 4 |
| Measles (first dose) |  | 81 | 73 | 68 | 71 | Measles | 1,601 | 10 |
| TT2+ (Pregnant women) |  | 53 | 53 | 42 | 76 | NN Tetanus | 151 | 98 |
| Hib3 |  | 83 | 80 | 64 | 76 | Hib[2] | 4 | 2 |
| Yellow Fever |  |  |  |  |  | Yellow fever | 0 | 9 |
| HepB3 |  | 83 | 80 | 64 | 76 | HepBsero-prevalence[1] |  |  |
| Vitamin A supplement Mothers (< 6 weeks post-delivery) |  |  |  |  | 48 |  |  |  |
| Vitamin A supplement Infants (>6 months) |  | 50 | 59 |  | 69 |  |  |  |

[1] If available

[2] Note: JRF asks for Hib meningitis

If survey data is included in the table above, please indicate the years the surveys were conducted, the full title and if available, the age groups the data refers to

The Uganda Demographic and Health Survey was conducted in 2006. UDHS assessed vaccination status of children aged 12-23 months and mothers with children 0-11 months. The EPI coverage survey was conducted in 2005 and titled "Uganda EPI plus coverage survey 2005". The target age group for childhood immunization data was children aged 12 - 23 months and for TT2+ immunization data the focus was on mothers who had babies less than 11 months of age. The target age group for vitamin A were children 6-23 months.

# Baseline and Annual Targets

(refer to cMYP pages)

Table 1: baseline figures

| Number | Base Year | Baseline and Targets |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2010 | 2013 | 2014 |  |  |  |  |
| Total births | 1,541,558 | 1,714,761 | 1,775,866 |  |  |  |  |
| Total infants' deaths | 117,158 | 130,322 | 134,966 |  |  |  |  |
| Total surviving infants | 1,424,400 | 1,584,439 | 1,640,900 |  |  |  |  |
| Total pregnant women | 1,541,558 | 1,714,761 | 1,775,866 |  |  |  |  |
| Number of infants vaccinated (to be vaccinated) with BCG | 1,320,165 | 1,611,875 | 1,687,073 |  |  |  |  |
| BCG coverage (%)[1] | 86% | 94% | 95% |  |  |  |  |
| Number of infants vaccinated (to be vaccinated) with OPV3 | 1,123,779 | 1,425,995 | 1,509,628 |  |  |  |  |
| OPV3 coverage (%)[2] | 79% | 90% | 92% |  |  |  |  |
| Number of infants vaccinated (or to be vaccinated) with DTP1[3] | 1,235,829 | 1,521,061 | 1,591,673 |  |  |  |  |
| Number of infants vaccinated (to be vaccinated) with DTP3[3] | 1,134,443 | 1,425,995 | 1,509,628 |  |  |  |  |
| DTP3 coverage (%)[2] | 80% | 90% | 92% |  |  |  |  |
| Wastage[1] rate in base-year and planned thereafter for DTP (%) | 10% | 10% | 10% |  |  |  |  |
| Wastage[1] factor in base-year and planned thereafter for DTP | 1.11 | 1.11 | 1.11 |  |  |  |  |
| Target population vaccinated with 1st dose of Pneumococcal |  | 1,521,061 | 1,591,673 |  |  |  |  |
| Target population vaccinated with 3rd dose of Pneumococcal |  | 1,425,995 | 1,509,628 |  |  |  |  |
| Pneumococcal coverage (%)[2] | 0% | 90% | 92% |  |  |  |  |
| Infants vaccinated (to be vaccinated) with 1st dose of Measles | 1,036,637 | 1,362,618 | 1,443,992 |  |  |  |  |
| Measles coverage (%)[2] | 73% | 86% | 88% |  |  |  |  |
| Pregnant women vaccinated with TT+ | 813,981 | 1,286,071 | 1,420,693 |  |  |  |  |
| TT+ coverage (%)[4] | 53% | 75% | 80% |  |  |  |  |
| Vit A supplement to mothers within 6 weeks from delivery |  |  |  |  |  |  |  |
| Vit A supplement to infants after 6 months | 3,531,732 |  |  |  |  |  |  |
| Annual DTP Drop-out rate[ ( DTP1 - DTP3 ) / DTP1 ] x 100[5] | 8% | 6% | 5% |  |  |  |  |

[1] Number of infants vaccinated out of total births

[2] Number of infants vaccinated out of total surviving infants

[3] Indicate total number of children vaccinated with either DTP alone or combined

[4] Number of pregnant women vaccinated with TT+ out of total pregnant women

[5] The formula to calculate a vaccine wastage rate (in percentage):[ ( A – B ) / A ] x 100. Whereby: A = the number of doses distributed for use according to the supply records with correction for stock balance at the end of the supply period; B = the number of vaccinations with the same vaccine in the same period.

# Summary of current and future immunisation budget

(or refer to cMYP pages)

|  | Estimated costs per annum in US$ (in thousand US$) |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Cost category | Base Year | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |  |
|  | 2008 | 2013 | 2014 |  |  |  |  |  |  |  |
| Routine Recurrent Cost |  |  |  |  |  |  |  |  |  |  |
| Vaccines (routine vaccines only) | 17,374,210 | 53,910,479 | 55,779,506 |  |  |  |  |  |  |  |
| Traditional vaccines | 1,608,444 | 3,247,478 | 3,749,224 |  |  |  |  |  |  |  |
| New and underused vaccines | 15,765,766 | 50,663,001 | 52,030,282 |  |  |  |  |  |  |  |
| Injection supplies | 1,058,903 | 1,868,630 | 2,188,189 |  |  |  |  |  |  |  |
| Personnel | 3,493,982 | 6,276,248 | 6,991,740 |  |  |  |  |  |  |  |
| Salaries of full-time NIP health workers (immunisation specific) | 61,150 | 125,082 | 139,341 |  |  |  |  |  |  |  |
| Per-diems for outreach vaccinators / mobile teams | 3,432,832 | 6,151,166 | 6,852,399 |  |  |  |  |  |  |  |
| Transportation | 642,821 | 1,274,209 | 1,427,318 |  |  |  |  |  |  |  |
| Maintenance and overheads | 135,580 | 790,215 | 796,432 |  |  |  |  |  |  |  |
| Training | 200,000 | 216,486 | 220,816 |  |  |  |  |  |  |  |
| Social mobilisation and IEC | 155,690 | 168,524 | 171,894 |  |  |  |  |  |  |  |
| Disease surveillance | 762,985 | 863,919 | 881,198 |  |  |  |  |  |  |  |
| Program management | 56,027 | 60,645 | 61,858 |  |  |  |  |  |  |  |
| Other | 211,269 | 211,269 | 211,269 |  |  |  |  |  |  |  |
| Subtotal Recurrent Costs | 24,091,467 | 65,640,624 | 68,730,220 |  |  |  |  |  |  |  |
| Routine Capital Costs |  |  |  |  |  |  |  |  |  |  |
| Vehicle | 181,143 | 528,072 | 591,314 |  |  |  |  |  |  |  |
| Cold chain equipment | 43,787 | 111,918 | 128,047 |  |  |  |  |  |  |  |
| Other capital equipment | 36,900 | 170,595 | 170,595 |  |  |  |  |  |  |  |
| Subtotal Capital Costs | 261,830 | 810,585 | 889,956 |  |  |  |  |  |  |  |
| Campaigns |  |  |  |  |  |  |  |  |  |  |
| Polio | 1,235,261 |  |  |  |  |  |  |  |  |  |
| Measles |  |  |  |  |  |  |  |  |  |  |
| Yellow Fever |  |  |  |  |  |  |  |  |  |  |
| MNT campaigns |  |  |  |  |  |  |  |  |  |  |
| Other campaigns |  |  |  |  |  |  |  |  |  |  |
| Subtotal Campaign Costs | 1,235,261 | 0 | 0 |  |  |  |  |  |  |  |
| GRAND TOTAL | 25,588,558 | 66,451,209 | 69,620,176 |  |  |  |  |  |  |  |

# Summary of current and future financing and sources of funds

Please list in the tables below the funding sources for each type of cost category (if known). Please try and indicate which immunisation program costs are covered from the Government budget, and which costs are covered by development partners (or the GAVI Alliance), and name the partners (or refer to cMYP).

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

|  |  | Estimated costs per annum in US$ (in thousand US$) |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Cost category | Funding source | Base Year | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |  |
|  |  | 2008 | 2013 | 2014 |  |  |  |  |  |  |  |
| Routine Recurrent Cost |  |  |  |  |  |  |  |  |  |  |  |
|  | Government of Uganda | 7,362 | 12,093 | 16,151 |  |  |  |  |  |  |  |
|  | GAVI | 15,603 | 50,465 | 51,381 |  |  |  |  |  |  |  |
|  | UNICEF | 300 | 1,457 | 328 |  |  |  |  |  |  |  |
|  | WHO | 824 | 1,625 | 870 |  |  |  |  |  |  |  |
| Routine Capital Costs |  |  |  |  |  |  |  |  |  |  |  |
|  | Government of Uganda | 219 |  |  |  |  |  |  |  |  |  |
|  | GAVI | 44 |  |  |  |  |  |  |  |  |  |
|  | Unfunded |  | 811 | 890 |  |  |  |  |  |  |  |
| Campaigns |  |  |  |  |  |  |  |  |  |  |  |
|  | Goverment of Uganda | 20 | 0 | 0 |  |  |  |  |  |  |  |
|  | UNICEF | 477 | 0 | 0 |  |  |  |  |  |  |  |
|  | WHO | 739 | 0 | 0 |  |  |  |  |  |  |  |
| GRAND TOTAL |  | 25,588 | 66,451 | 69,620 |  |  |  |  |  |  |  |

# New and Under-Used Vaccines (NVS)

Please summarise the cold chain capacity and readiness to accommodate new vaccines, stating how the cold chain expansion (if required) will be financed, and when it will be in place. Please indicate the additional cost, if capacity is not available and the source of funding to close the gap.

A national cold chain review and inventory was conducted in all health facilities providing immunization in 2007. As a follow up, a cold chain assessment was done countrywide in 2010. The inventory and assessment both provided vital information on the number and status of cold chain equipment at all levels. The programme used USAID and Japan International Cooperation Agency (JICA) support to procure cold chain equipment to close the gaps at national and sub-national levels identified in the cold chain review and inventory. There is adequate space to introduce PCV at national, district and health facility level as indicated in the table below.

Please give a summary of the cMYP sections that refer to the introduction of new and under-used vaccines. Outline the key points that informed the decision-making process (data considered etc)

In the cMYP priorities and national objectives (Table 3), introduction of new vaccines and other technologies for diseases with a high burden, and whose vaccines are available, has been identified as a national priority. The plan is to introduce PCV in 2010 in 2013. The Government of Uganda realizes that introduction of new vaccines will contribute towards the reduction of childhood morbidity and mortality hence accelerate the attainment MDG 4. The country initiated a sentinel disease surveillance and reporting system for pneumococcal disease using suspected bacterial meningitis cases and severe pneumococcal disease in the under 5 year olds in 2002; rotavirus sentinel surveillance was introduced in July 2006 to establish the burden of disease for decision making for new vaccine introduction into the routine immunization schedule. The high disease burden for invasive pneumococcal disease and diarrheal disease due to severe rotavirus in Uganda from the above sources informed the decision making process. It has been noted that there is growing resistance of Streptococcus pneumoniae to the commonly used antibiotics hence further justifying the need for prevention of infections. A cost effectiveness study for rotavirus and SP was done which showed that at $0.15 per dose, the 10-valent pneumococcal conjugate vaccine and rotavirus vaccine would both be highly cost effective interventions if introduced into the national vaccination program in Uganda. Further, a pneumococcal vaccination program would be cost-saving to the health care system as the medical costs saved by the introduction of the vaccine are greater than the cost of the vaccination program. A pneumococcal vaccination program would save 2,565 million Ushs in direct medical costs annually. A rotavirus vaccination program would be cost-neutral to the health care system as the cost of the vaccination program is approximately equal to the medical costs saved by rotavirus vaccination. A rotavirus vaccination program would save a nominal 26 million Ushs in direct medical costs annually. In addition to the cost savings, both vaccines will have a substantial impact on mortality and morbidity in Ugandan children <5 years of age. A pneumococcal vaccine program will prevent 94,071 (42%) cases of Streptococcus pneumoniae in children <5 years of age and save 10,796 (42%) lives annually. A rotavirus vaccination program will prevent 3,981 (38%) deaths, 4,869 (42%) hospitalizations, and 66,933 (33%) outpatient and health care center visits annually in children <5 years of age.

# Capacity and cost (for positive storage)

|  |  | Formula | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2013 | 2014 |  |  |  |  |  |  |
| A | Annual positive volume requirement, including new vaccine (litres or m3) Litres | Sum-product of total vaccine doses multiplied by unit packed volume of the vaccine | 127,839 | 133,858 |  |  |  |  |  |  |
| B | Existing net positive cold chain capacity (litres or m3) Litres | # | 51,489 | 51,489 |  |  |  |  |  |  |
| C | Estimated minimum number of shipments per year required for the actual cold chain capacity | A / B | 3 | 3 |  |  |  |  |  |  |
| D | Number of consignments / shipments per year | Based on national vaccine shipment plan | 4 | 4 |  |  |  |  |  |  |
| E | Gap (if any) | ((A / D) - B) | -19,529 | -18,025 |  |  |  |  |  |  |
| F | Estimated additional cost of cold chain | US$ | 0 | 0 |  |  |  |  |  |  |

Please briefly describe how your country plans to move towards attaining financial sustainability for the new vaccines you intend to introduce, how the country will meet the co-financing payments, and any other issues regarding financial sustainability you have considered (refer to the cMYP)

The new national health policy clearly focuses on preventable health where immunization is one of the considered cost effective interventions. The Government of Uganda has agreed to create a vote in the Ministry of Health (MoH) budget for co-financing new vaccines. MoH is initiating a case investment study to generate evidence for advocating for increased allocation for immunization The government will continue with resource mobilizations for vaccine procurement and several strategies will be explored which include: mobilization of additional resources (local and external sources), increase in reliability of resources and strategies to increase program efficiency. The additional resources will be got from the government budget for the health sector, Ministry of health budget for immunization, non-government sources and from current and new partners including the private sector. Regarding increasing the reliability of resources, the government will utilize the following strategies: financial requirements for immunization in the Mid Term Expenditure Framework (MTEF) and Long Term Expenditure Framework (LTEF), protection of government contributions for vaccines and EPI; reflection of funds for vaccines in the Primary Health Care (PHC) vote for districts and maintenance of unspent funds from donors within the program. Lastly improvement in programme efficiency will be pursued. For instance reduction of vaccine wastage will definitely offer significant efficiency gains for the programme given the high costs of new vaccines. Therefore capacity building in vaccine management, having an effective vaccine wastage monitoring system, efficient cold chain system (change refrigerators from gas to electricity, increase number of refrigerators using solar energy etc) are some of the strategies to be used to consolidate gains in immunization programme.

# Assessment of burden of relevant diseases (if available)

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Disease | Title of the assessment | Date | Results |  |
| --- | --- | --- | --- | --- |
| Hib disease | Haemophilus influenzae type b conjugate vaccine is highly effective in the Ugandan routine immunization program: a case control | July 2002 - July 2005 | Vaccine effectiveness for 2 or 3 doses was 99% (CI 95%, 92-100%) and 96% (CI 95% 80-100%) when cases were compared with neigbhourhood and hospital controls. The study concluded that Hib vaccine was highly effective in the routine immunization schedule. |  |
| Streptococcus pneumoniae | Official WHO burden estimates | 2000 | Streptococcus pneumoniae is responsible for 18,995 deaths annually among children less than five years of age. The overall incidence of invasive pneumococcal disease (meningitis) and pneumonia among children less than five 5 years of age is 28 per 1,000 and 3212 per 1,000 respectively. The Case Fatality Rate for pneumonia and meningitis is 11.3% and 55.4% respectively. |  |
| Rotavirus | Hospital Sentinel surveillance for Rotavirus | July 2006 - June 2009 | A total of 2,598 suspected cases of rotavirus were admitted during the review period, of which 2,192 (84%) stool specimens had collected of which 835 (32%) had rotavirus detected. Boys accounted for 524 (62%) of the confirmed rotavirus cases. Majority of rotavirus cases would be hospitalized for 2 – 3 days (645; 77%) with an average of 3 hospital days. 807 (97%) of the confirmed rotavirus infected children were below 2 years of age. The age specific incidence rate of rotavirus infection in children below 5 years of age for Kampala district (host district of the sentinel site) was 60 per 100,000 and 57 per 100,000 children below 5 years of age in 2006 and 2007 respectively |  |

If new or under-used vaccines have already been introduced in your country, please give details of the lessons learned from storage capacity, protection from accidental freezing, staff training, cold chain, logistics, drop-out rate, wastage rate etc., and suggest action points to address them

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Lessons Learned | Action Points |  |
| --- | --- | --- |
| Low dose vial (1 or 2 doses per vial) reduces wastage but increases storage space and distribution costs. - New vaccine introduction requires adequate planning for cold chain capacity and /or review of the shipment planning. - Thorough assessment of cold chain capacity by level is very critical - Training is critical to prepare health workers for new vaccine introduction - New vaccine introduction required additional dry storage space for injection materials at national level due to inadequate storage space - Planning for waste management (Disposal of used vials and sharps) - Intensive social mobilization is required to prepare the Public for the uptake of new vaccines - The process requires to review and update monitoring tools - Adequate supply of the new vaccine is very important to meet the demand created at the introduction phase | The cold chain system was expanded at peripheral level to address the gap - MoH earmarked funds for distribution of vaccines - The programme developed a training manual and conducted cascade training - The programme reviewed and updated the monitoring tools |  |

Please list the vaccines to be introduced with support from the GAVI Alliance (and presentation)

Pneumococcal conjugate vaccine (PCV10): 2 dose liquid formulation

# 6.3.1. Requested vaccine ( Pneumococcal (PCV10), 2 doses/vial, Liquid )

As reported in the cMYP, the country plans to introduce Pneumococcal (PCV10), 2 doses/vial, Liquid vaccine.

# 6.3.2. Co-financing information

If you would like to co-finance higher amount than minimum, please overwrite information in the “Your co-financing” row.

Note: Selection of this field has direct impact on automatic calculations of support you are requesting and should not be left empty.

| Country group | Low |
| --- | --- |

|  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2013 | 2014 |  |  |  |  |  |  |
| Minimum co-financing | 0.20 | 0.20 |  |  |  |  |  |  |
| Your co-financing (please change if higher) | 0.20 | 0.20 |  |  |  |  |  |  |

# 6.3.3. Wastage factor

Please indicate wastage rate:

Countries are expected to plan for a maximal wastage rate of:

- 50% - for a lyophilised vaccine in 10 or 20-dose vial,

- 25% - for a liquid vaccine in 10 or 20-dose vial or a lyophilised vaccine in 5-dose vial,

- 10% - for a lyophilised/liquid vaccine in 2-dose vial, and

- 5% - for a liquid vaccine in 1-dose vial

Note: Selection of this field has direct impact on automatic calculations of support you are requesting and should not be left empty.

|  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2013 | 2014 |  |  |  |  |  |  |
| Vaccine wastage rate in % | 5% | 5% |  |  |  |  |  |  |
| Equivalent wastage factor | 1.05 | 1.05 |  |  |  |  |  |  |

# 6.3.4. Specifications of vaccinations with new vaccine

|  | Data from |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2013 | 2014 |  |  |  |  |  |  |
| Number of children to be vaccinated with the first dose | Table 1 | # | 1,521,061 | 1,591,673 |  |  |  |  |  |  |
| Number of children to be vaccinated with the third dose[1] | Table 1 | # | 1,425,995 | 1,509,628 |  |  |  |  |  |  |
| Immunisation coverage with the third dose | Table 1 | # | 90.00% | 92.00% |  |  |  |  |  |  |
| Estimated vaccine wastage factor | Table 6.(n).3[3] | # | 1.05 | 1.05 |  |  |  |  |  |  |
| Country co-financing per dose[2] | Table 6.(n).2[3] | $ | 0.20 | 0.20 |  |  |  |  |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Total price per-dose includes vaccine cost, plus freight, supplies, insurance, visa costs etc.

[3] Where (n) depends on the vaccine

# 6.3.5. Portion of supply to be procured by the country (and cost estimate, US$)

|  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2013 | 2014 |  |  |  |  |  |  |
| Number of vaccine doses | # | 319,800 | 270,800 |  |  |  |  |  |  |
| Number of AD syringes | # | 341,500 | 286,400 |  |  |  |  |  |  |
| Number of re-constitution syringes | # |  |  |  |  |  |  |  |  |
| Number of safety boxes | # | 3,800 | 3,200 |  |  |  |  |  |  |
| Total value to be co-financed by country | $ | 1,198,000 | 1,014,000 |  |  |  |  |  |  |

# 6.3.6. Portion of supply to be procured by the GAVI Alliance (and cost estimate, US$)

|  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2013 | 2014 |  |  |  |  |  |  |
| Number of vaccine doses | # | 5,669,400 | 4,798,700 |  |  |  |  |  |  |
| Number of AD syringes | # | 6,053,300 | 5,075,700 |  |  |  |  |  |  |
| Number of re-constitution syringes | # |  |  |  |  |  |  |  |  |
| Number of safety boxes | # | 67,200 | 56,350 |  |  |  |  |  |  |
| Total value to be co-financed by GAVI | $ | 21,235,500 | 17,971,000 |  |  |  |  |  |  |

# 6.3.7. New and Under-Used Vaccine Introduction Grant

Please indicate in the tables below how the one-time Introduction Grant[1] will be used to support the costs of vaccine introduction and critical pre-introduction activities (refer to the cMYP).

Calculation of lump-sum for the Pneumococcal (PCV10), 2 doses/vial, Liquid

If the total is lower than US$100,000, it is automatically rounded up to US$100,000

| Year of New Vaccine Introduction | Births (from Table 1) | Share per Birth in US$ | Total in US$ |
| --- | --- | --- | --- |
| 2013 | 1,714,761 | 0.30 | 514,500 |

[1] The Grant will be based on a maximum award of $0.30 per infant in the birth cohort with a minimum starting grant award of $100,000

Cost (and finance) to introduce the Pneumococcal (PCV10), 2 doses/vial, Liquid (US$)

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Cost Category | Full needs for new vaccine introduction in US$ | Funded with new vaccine introduction grant in US$ |  |
| --- | --- | --- | --- |
| Training | 212,600 | 212,600 |  |
| Social Mobilization, IEC and Advocacy | 125,100 | 66,300 |  |
| Cold Chain Equipment & Maintenance | 114,000 |  |  |
| Vehicles and Transportation | 90,000 |  |  |
| Programme Management |  |  |  |
| Surveillance and Monitoring | 114,600 | 75,000 |  |
| Human Resources |  |  |  |
| Waste Management |  |  |  |
| Technical assistance |  |  |  |
| Microplanning at central and district levels | 80600 | 80600 |  |
| Support supervision | 80000 | 80000 |  |
| Totals | 816,900 | 514,500 |  |

# Procurement and Management of New and Under-Used Vaccines

Note: The PCV vaccine must be procured through UNICEF

- Please show how the support will operate and be managed including procurement of vaccines (GAVI expects that most countries will procure vaccine and injection supplies through UNICEF)

Procurement and management will follow the existing mechanism where Government of Uganda (GOU), through the National Medical Stores, provides funds to UNICEF that procures from WHO pre-qualified suppliers. Similarly GAVI supported vaccines will also be procured through UNICEF as before. All this is governed by an MOU signed annually between GOU-UNICEF .

- If an alternative mechanism for procurement and delivery of supply (financed by the country or the GAVI Alliance) is requested, please document

- Other vaccines or immunisation commodities procured by the country and descriptions of the mechanism used.

- The functions of the National Regulatory Authority (as evaluated by WHO) to show they comply with WHO requirements for procurement of vaccines and supply of assured quality.

NA

- Please describe the introduction of the vaccines (refer to cMYP)

The plan provides for a nationwide introduction covering all the districts on the same date. The existing routine delivery mechanism will be used. The following strategic activities will be done in preparation for the introduction for both vaccines at different times: 1. Regular coordination meetings at national and district level 2. Training of operational level health workers 3. Social mobilization and advocacy 4. Cold chain equipment and maintenance 5. Vaccine distribution, management and handling 6. Surveillance, monitoring and evaluation 7. Micro planning at central and district level 8. Support supervision Details are in the PCV introdcution plan which is attached.

- Please indicate how funds should be transferred by the GAVI Alliance (if applicable)

The mechanism for transferring funds as outlined in the Financial Management Assessment Aide Memoire, soon to be signed between GAVI Alliance and Governemnent of Uganda, will be followed.

- Please indicate how the co-financing amounts will be paid (and who is responsible for this)

A vote for PCV co-financing will be created in the MoH annual budget. Funds will be released from Ministry of Finance, Planning and Economic Development to National Medical Stores (NMS). Upon approval by the Permanent Secretary of MoH, National Medical Stores will transfer the funds to UNICEF Copenhagen that manages the procurement.

- Please outline how coverage of the new vaccine will be monitored and reported (refer to cMYP)

All EPI data will be recorded and reported using the existing Health Management Information tools (HMIS). The existing tools have already been revised to incorporate information on the new vaccines and gender segregation. HMIS monthly reports are submitted from the districts to MoH by the 28th day of the following month where data is aggregated. Monthly reports are aggregated to compile annual reports. The information is incorporated into the WHO/UNICEF Joint Reporting Format which is submitted annual by 15th April of the following year. Periodically (every 5 years) nationwide coverage surveys and Demographic Health surveys are done to verify immunization coverage.

# Vaccine Management (EVSM/EVM/VMA)

When was the last Effective Vaccine Store Management (EVSM) conducted? April   - 2004

When was the last Effective Vaccine Management (EVM) or Vaccine Management Assessment (VMA) conducted? October  - 2007

- If your country conducted either EVSM, EVM, or VMA in the past three years, please attach relevant reports. (Document N°)

- A VMA report must be attached from those countries which have introduced a New and Underused Vaccine with GAVI support before 2008.

- Please note that EVSM and VMA tools have been replaced by an integrated Effective Vaccine Management (EVM) tool. The information on EVM tool can be found at http://www.who.int/immunization_delivery/systems_policy/logistics/en/index6.html

- For countries which conducted EVSM, VMA or EVM in the past, please report on activities carried out as part of either action plan or improvement plan prepared after the EVSM/VMA/EVM.

- When is the next Effective Vaccine Management (EVM) Assessment planned? July   - 2011

- Under new guidelines, it will be mandatory for the countries to conduct an EVM prior to an application for introduction of new vaccine.

# Additional Comments and Recommendations

Comments and Recommendations from the National Coordinating Body (ICC/HSCC)

Issues of concern raised while discussing the proposal included: 1. Sustainability of the new vaccines is a major concern given the general under funding of the health sector. 2. There is need for the EPI Programme to raise routine immunization coverage of the already existing vaccines. 3. A cost effectiveness analysis for the introduction of new vaccines will help to justify the need for additional resources for the Immunization programme. 4. There is a concern as to whether the price of the vaccines will go down as anticipated. Learning from the experience of pentavalent introduction, the decline in the price on the global market has not been fully realized as was anticipated.

# Annexes

# Annex 1

# Annex 1.1 – Pneumococcal (PCV10), 2 doses/vial, Liquid

Table 1.1 A - Rounded up portion of supply that is procured by the country and estimate of related cost in US$

| Required supply item |  | 2013 | 2014 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of vaccine doses | # | 319,800 | 270,800 |  |  |  |  |  |  |
| Number of AD syringes | # | 341,500 | 286,400 |  |  |  |  |  |  |
| Number of re-constitution syringes | # |  |  |  |  |  |  |  |  |
| Number of safety boxes | # | 3,800 | 3,200 |  |  |  |  |  |  |
| Total value to be co-financed by the country | $ | 1,198,000 | 1,014,000 |  |  |  |  |  |  |

Table 1.1  B - Rounded up portion of supply that is procured by GAVI and estimate of related cost in US$.

| Required supply item |  | 2013 | 2014 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of vaccine doses | # | 5,669,400 | 4,798,700 |  |  |  |  |  |  |
| Number of AD syringes | # | 6,053,300 | 5,075,700 |  |  |  |  |  |  |
| Number of re-constitution syringes | # |  |  |  |  |  |  |  |  |
| Number of safety boxes | # | 67,200 | 56,350 |  |  |  |  |  |  |
| Total value to be co-financed by the country | $ | 21,235,500 | 17,971,000 |  |  |  |  |  |  |

Table 1.1  C - Summary table for Pneumococcal (PCV10), 2 doses/vial, Liquid

|  | Data from |  | 2013 | 2014 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of Surviving infants | Table 1 | # | 1,584,439 | 1,640,900 |  |  |  |  |  |  |
| Number of children to be vaccinated with the third dose[1] | Table 1 | # | 1,425,995 | 1,509,628 |  |  |  |  |  |  |
| Immunisation coverage with the last dose | Table 1 | # | 90.00% | 92.00% |  |  |  |  |  |  |
| Number of children to be vaccinated with the first dose | Table 1 | # | 1,521,061 | 1,591,673 |  |  |  |  |  |  |
| Number of doses per child |  | # | 3 | 3 |  |  |  |  |  |  |
| Estimated vaccine wastage factor | Table 6.(n).3[2] | # | 1.05 | 1.05 |  |  |  |  |  |  |
| Number of doses per vial |  | # | 2 | 2 |  |  |  |  |  |  |
| AD syringes required |  | # | Yes | Yes |  |  |  |  |  |  |
| Reconstitution syringes required |  | # | No | No |  |  |  |  |  |  |
| Safety boxes required |  | # | Yes | Yes |  |  |  |  |  |  |
| Vaccine price per dose |  | $ | 3.500 | 3.500 |  |  |  |  |  |  |
| Country co-financing per dose | Table 6.(n).2[2] | $ | 0.20 | 0.20 |  |  |  |  |  |  |
| AD syringe price per unit |  | $ | 0.053 | 0.053 |  |  |  |  |  |  |
| Reconstitution syringe price per unit |  | $ |  |  |  |  |  |  |  |  |
| Safety box price per unit |  | $ | 0.640 | 0.640 |  |  |  |  |  |  |
| Freight cost as % of vaccines value |  | % | 5.00 | 5.00 |  |  |  |  |  |  |
| Freight cost as % of devices value |  | % | 10.00 | 10.00 |  |  |  |  |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Where (n) depends on the vaccine

# Table 1.1 D - Estimated number of doses for Pneumococcal (PCV10), 2 doses/vial, Liquid associated injection safety material and related co-financing budget (page 1)

|  |  | Formula | 2013 |  |  | 2014 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Total | Government | GAVI | Total | Government | GAVI |
| A | Country Co-finance |  | 5.34% |  |  | 5.34% |  |  |
| B | Number of children to be vaccinated with the first dose[1] | Table 1 (baseline & annual targets) | 1,521,061 | 81,219 | 1,439,842 | 1,591,673 | 85,005 | 1,506,668 |
| C | Number of doses per child | Vaccine parameter | 3 | 3 | 3 | 3 | 3 | 3 |
| D | Number of doses needed | B * C | 4,563,183 | 243,657 | 4,319,526 | 4,775,019 | 255,013 | 4,520,006 |
| E | Estimated vaccine wastage factor | Table 6.(n).3. in NVS section[2] | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 |
| F | Number of doses needed including wastage | D * E | 4,791,343 | 255,840 | 4,535,503 | 5,013,770 | 267,764 | 4,746,006 |
| G | Vaccines buffer stock | (F - F of previous year) * 0.25 | 1,197,836 | 63,960 | 1,133,876 | 55,607 | 2,970 | 52,637 |
| I | Total vaccine doses needed | F + G | 5,989,179 | 319,799 | 5,669,380 | 5,069,377 | 270,733 | 4,798,644 |
| J | Number of doses per vial | Vaccine parameter | 2 | 2 | 2 | 2 | 2 | 2 |
| K | Number of AD syringes (+ 10% wastage) needed | (D + G) * 1.11 | 6,394,732 | 341,454 | 6,053,278 | 5,361,995 | 286,361 | 5,075,634 |
| L | Reconstitution syringes (+ 10% wastage) needed | I / J * 1.11 |  |  |  |  |  |  |
| M | Total of safety boxes (+ 10% of extra need) needed | (K + L) / 100 x 1.11 | 70,982 | 3,791 | 67,191 | 59,519 | 3,179 | 56,340 |
| N | Cost of vaccines needed | I * vaccine price per dose | 20,962,127 | 1,119,297 | 19,842,830 | 17,742,820 | 947,566 | 16,795,254 |
| O | Cost of AD syringes needed | K * AD syringe price per unit | 338,921 | 18,098 | 320,823 | 284,186 | 15,178 | 269,008 |
| P | Cost of reconstitution syringes needed | L * reconstitution price per unit |  |  |  |  |  |  |
| Q | Cost of safety boxes needed | M * safety box price per unit | 45,429 | 2,426 | 43,003 | 38,093 | 2,035 | 36,058 |
| R | Freight cost for vaccines needed | N * freight cost as % of vaccines value | 1,048,107 | 55,965 | 992,142 | 887,141 | 47,379 | 839,762 |
| S | Freight cost for devices needed | (O + P + Q) * freight cost as % of devices value | 38,435 | 2,053 | 36,382 | 32,228 | 1,722 | 30,506 |
| T | Total fund needed | (N + O + P + Q + R + S) | 22,433,019 | 1,197,836 | 21,235,183 | 18,984,468 | 1,013,876 | 17,970,592 |
| U | Total country co-financing | I * country co-financing per dose | 1,197,836 |  |  | 1,013,876 |  |  |
| V | Country co-financing % of GAVI supported proportion | U / T | 5.34% |  |  | 5.34% |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Where (n) depends on the vaccine

# Annex 2

Estimated prices of supply and related freight cost: 2011 from UNICEF Supply Division; 2012 onwards: GAVI Secretariat

Table A - Commodities Cost

| Vaccine | Presentation | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| AD syringe | 0 | 0.053 | 0.053 | 0.053 | 0.053 | 0.053 | 0.053 | 0.053 |
| DTP-HepB | 2 | 1.600 |  |  |  |  |  |  |
| DTP-HepB | 10 | 0.620 | 0.620 | 0.620 | 0.620 | 0.620 | 0.620 | 0.620 |
| DTP-HepB-Hib | WAP | 2.580 | 2.470 | 2.320 | 2.030 | 1.850 | 1.850 | 1.850 |
| DTP-HepB-Hib | WAP | 2.580 | 2.470 | 2.320 | 2.030 | 1.850 | 1.850 | 1.850 |
| DTP-HepB-Hib | WAP | 2.580 | 2.470 | 2.320 | 2.030 | 1.850 | 1.850 | 1.850 |
| DTP-Hib | 10 | 3.400 | 3.400 | 3.400 | 3.400 | 3.400 | 3.200 | 3.200 |
| HepB monoval | 1 |  |  |  |  |  |  |  |
| HepB monoval | 2 |  |  |  |  |  |  |  |
| Hib monoval | 1 | 3.400 |  |  |  |  |  |  |
| Measles | 10 | 0.240 | 0.240 | 0.240 | 0.240 | 0.240 | 0.240 | 0.240 |
| Pneumococcal(PCV10) | 2 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 |
| Pneumococcal(PCV13) | 1 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 |
| Reconstit syringe for Pentaval (2ml) | 0 | 0.032 | 0.032 | 0.032 | 0.032 | 0.032 | 0.032 | 0.032 |
| Reconstit syringe for YF | 0 | 0.038 | 0.038 | 0.038 | 0.038 | 0.038 | 0.038 | 0.038 |
| Rotavirus 2-dose schedule | 1 | 7.500 | 6.000 | 5.000 | 4.000 | 3.600 | 3.600 | 3.600 |
| Rotavirus 3-dose schedule | 1 | 5.500 | 4.000 | 3.333 | 2.667 | 2.400 | 2.400 | 2.400 |
| Safety box | 0 | 0.640 | 0.640 | 0.640 | 0.640 | 0.640 | 0.640 | 0.640 |
| Yellow Fever | WAP | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 |
| Yellow Fever | WAP | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 |

Note: WAP - weighted average price (to be used for any presentation: For DTP-HepB-Hib, it applies to 1 dose liquid, 2 dose lyophilised and 10 dose liquid. For Yellow Fever, it applies to 5 dose lyophilised and 10 dose lyophilised)

Table B - Commodities Freight Cost

| Vaccines | Group | No Threshold | 200’000 $ |  | 250’000 $ |  | 2’000’000 $ |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | <= | > | <= | > | <= | > |
| Yellow Fever | Yellow Fever |  | 20% |  |  |  | 10% | 5% |
| DTP+HepB | HepB and or Hib | 2% |  |  |  |  |  |  |
| DTP-HepB-Hib | HepB and or Hib |  |  |  | 15% | 3,50% |  |  |
| Pneumococcal vaccine (PCV10) | Pneumococcal | 5% |  |  |  |  |  |  |
| Pneumococcal vaccine (PCV13) | Pneumococcal | 5% |  |  |  |  |  |  |
| Rotavirus | Rotavirus | 5% |  |  |  |  |  |  |
| Measles | Measles | 10% |  |  |  |  |  |  |

Table C - Low - Minimum country's co-payment per dose of co-financed vaccine.

| vaccine | 2013 | 2014 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Pneumococcal(PCV10), 2 doses/vial, Liquid | 0.20 | 0.20 |  |  |  |  |  |

Table D - Wastage rates and factors

Countries are expected to plan for a maximal wastage rate of:

- 50% - for a lyophilised vaccine in 10 or 20-dose vial,

- 25% - for a liquid vaccine in 10 or 20-dose vial or a lyophilised vaccine in 5-dose vial,

- 10% - for a lyophilised/liquid vaccine in 2-dose vial, and

- 5% - for a liquid vaccine in 1-dose vial

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2 | 2.22 | 2.5 |

WHO International shipping guidelines: maximum packed volumes of vaccines

Table E - Vaccine maximum packed volumes

| Vaccine product | Designation | Vaccine formulation | Admin route | No. Of doses in the schedule | Presentation (doses/vial, prefilled) | Packed volume vaccine (cm3/dose) | Packed volume diluents (cm3/dose) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| BCG | BCG | lyophilized | ID | 1 | 20 | 1.2 | 0.7 |
| Diphtheria-Tetanus-Pertussis | DTP | liquid | IM | 3 | 20 | 2.5 |  |
| Diphtheria-Tetanus-Pertussis | DTP | liquid | IM | 3 | 10 | 3.0 |  |
| Diphtheria-Tetanus | DT | liquid | IM | 3 | 10 | 3.0 |  |
| Tetanus-Diphtheria | Td | liquid | IM | 2 | 10 | 3.0 |  |
| Tetanus Toxoid | TT | liquid | IM | 2 | 10 | 3.0 |  |
| Tetanus Toxoid | TT | liquid | IM | 2 | 20 | 2.5 |  |
| Tetanus Toxoid UniJect | TT | liquid | IM | 2 | Uniject | 12.0 |  |
| Measles | Measles | lyophilized | SC | 1 | 1 | 26.1 | 20.0 |
| Measles | Measles | lyophilized | SC | 1 | 2 | 13.1 | 13.1 |
| Measles | Measles | lyophilized | SC | 1 | 5 | 5.2 | 7.0 |
| Measles | Measles | lyophilized | SC | 1 | 10 | 3.5 | 4.0 |
| Measles-Rubella freeze dried | MR | lyophilized | SC | 1 | 1 | 26.1 | 26.1 |
| Measles-Rubella freeze dried | MR | lyophilized | SC | 1 | 2 | 13.1 | 13.1 |
| Measles-Rubella freeze dried | MR | lyophilized | SC | 1 | 5 | 5.2 | 7.0 |
| Measles-Rubella freeze dried | MR | lyophilized | SC | 1 | 10 | 2.5 | 4.0 |
| Measles-Mumps-Rubella freeze dried | MMR | lyophilized | SC | 1 | 1 | 26.1 | 26.1 |
| Measles-Mumps-Rubella freeze dried | MMR | lyophilized | SC | 1 | 2 | 13.1 | 13.1 |
| Measles-Mumps-Rubella freeze dried | MMR | lyophilized | SC | 1 | 5 | 5.2 | 7.0 |
| Measles-Mumps-Rubella freeze dried | MMR | lyophilized | SC | 1 | 10 | 3.0 | 4.0 |
| Polio | OPV | liquid | Oral | 4 | 10 | 2.0 |  |
| Polio | OPV | liquid | Oral | 4 | 20 | 1.0 |  |
| Yellow fever | YF | lyophilized | SC | 1 | 5 | 6.5 | 7.0 |
| Yellow fever | YF | lyophilized | SC | 1 | 10 | 2.5 | 3.0 |
| Yellow fever | YF | lyophilized | SC | 1 | 20 | 1.5 | 2.0 |
| Yellow fever | YF | lyophilized | SC | 1 | 50 | 0.7 | 1.0 |
| DTP-HepB combined | DTP-HepB | liquid | IM | 3 | 1 | 9.7 |  |
| DTP-HepB combined | DTP-HepB | liquid | IM | 3 | 2 | 6.0 |  |
| DTP-HepB combined | DTP-HepB | liquid | IM | 3 | 10 | 3.0 |  |
| Hepatitis B | HepB | liquid | IM | 3 | 1 | 18.0 |  |
| Hepatitis B | HepB | liquid | IM | 3 | 2 | 13.0 |  |
| Hepatitis B | HepB | liquid | IM | 3 | 6 | 4.5 |  |
| Hepatitis B | HepB | liquid | IM | 3 | 10 | 4.0 |  |
| Hepatitis B UniJect | HepB | liquid | IM | 3 | Uniject | 12.0 |  |
| Hib liquid | Hib_liq | liquid | IM | 3 | 1 | 15.0 |  |
| Hib liquid | Hib_liq | liquid | IM | 3 | 10 | 2.5 |  |
| Hib freeze-dried | Hib_lyo | lyophilized | IM | 3 | 1 | 13.0 | 35.0 |
| Hib freeze-dried | Hib_lyo | lyophilized | IM | 3 | 2 | 6.0 |  |
| Hib freeze-dried | Hib_lyo | lyophilized | IM | 3 | 10 | 2.5 | 3.0 |
| DTP liquid + Hib freeze-dried | DTP+Hib | liquid+lyop. | IM | 3 | 1 | 45.0 |  |
| DTP-Hib combined liquid | DTP+Hib | liquid+lyop. | IM | 3 | 10 | 12.0 |  |
| DTP-Hib combined liquid | DTP-Hib | liquid | IM | 3 | 1 | 32.3 |  |
| DTP-HepB liquid + Hib freeze-dried | DTP-Hib | liquid | IM | 3 | 10 | 2.5 |  |
| DTP-HepB liquid + Hib freeze-dried | DTP-HepB+Hib | liquid+lyop. | IM | 3 | 1 | 22.0 |  |
| DTP-HepB-Hib liquid | DTP-HepB+Hib | liquid+lyop. | IM | 3 | 2 | 11.0 |  |
| DTP-HepB-Hib liquid | DTP-HepB-Hib | liquid | IM | 3 | 10 | 4.4 |  |
| DTP-HepB-Hib liquid | DTP-HepB-Hib | liquid | IM | 3 | 2 | 13.1 |  |
| DTP-HepB-Hib liquid | DTP-HepB-Hib | liquid | IM | 3 | 1 | 19.2 |  |
| Meningitis A/C | MV_A/C | lyophilized | SC | 1 | 10 | 2.5 | 4.0 |
| Meningitis A/C | MV_A/C | lyophilized | SC | 1 | 50 | 1.5 | 3.0 |
| Meningococcal A/C/W/ | MV_A/C/W | lyophilized | SC | 1 | 50 | 1.5 | 3.0 |
| Meningococcal A/C/W/Y | MV_A/C/W/Y | lyophilized | SC | 1 | 10 | 2.5 | 4.0 |
| Meningitis W135 | MV_W135 | lyophilized | SC | 1 | 10 | 2.5 | 4.0 |
| Meningitis A conjugate | Men_A | lyophilized | SC | 2 | 10 | 2.6 | 4.0 |
| Japanese Encephalitis | JE_lyo | lyophilized | SC | 3 | 10 | 15.0 |  |
| Japanese Encephalitis | JE_lyo | lyophilized | SC | 3 | 10 | 8.1 | 8.1 |
| Japanese Encephalitis | JE_lyo | lyophilized | SC | 3 | 5 | 2.5 | 2.9 |
| Japanese Encephalitis | JE_lyo | lyophilized | SC | 3 | 1 | 12.6 | 11.5 |
| Japanese Encephalitis | JE_liq | liquid | SC | 3 | 10 | 3.4 |  |
| Rota vaccine | Rota_lyo | lyophilized | Oral | 2 | 1 | 156.0 |  |
| Rota vaccine | Rota_liq | liquid | Oral | 2 | 1 | 17.1 |  |
| Rota vaccine | Rota_liq | liquid | Oral | 3 | 1 | 45.9 |  |
| Pneumo. conjugate vaccine 7-valent | PCV-7 | liquid | IM | 3 | PFS | 55.9 |  |
| Pneumo. conjugate vaccine 7-valent | PCV-7 | liquid | IM | 3 | 1 | 21.0 |  |
| Pneumo. conjugate vaccine 10-valent | PCV-10 | liquid | IM | 3 | 1 | 11.5 |  |
| Pneumo. conjugate vaccine 10-valent | PCV-10 | liquid | IM | 3 | 2 | 4.8 |  |
| Pneumo. conjugate vaccine 13-valent | PCV-13 | liquid | IM | 3 | 1 | 12.0 |  |
| Polio inactivated | IPV | liquid | IM | 3 | PFS | 107.4 |  |
| Polio inactivated | IPV | liquid | IM | 3 | 10 | 2.5 |  |
| Polio inactivated | IPV | liquid | IM | 3 | 1 | 15.7 |  |
| Human Papilomavirus vaccine | HPV | liquid | IM | 3 | 1 | 15.0 |  |
| Human Papilomavirus vaccine | HPV | liquid | IM | 3 | 2 | 5.7 |  |
| Monovalent OPV-1 | mOPV1 | liquid | Oral |  | 20 | 1.5 |  |
| Monovalent OPV-3 | mOPV3 | liquid | Oral |  | 20 | 1.5 |  |

# Attachments

# List of Supporting Documents Attached to this Proposal

| Document | Section | Document Number | Mandatory[1] |
| --- | --- | --- | --- |
| MoH Signature (or delegated authority) of Proposal |  | 1 | Yes |
| MoF Signature (or delegated authority) of Proposal |  | 2 | Yes |
| Signatures of ICC or HSCC or equivalent in Proposal |  | 3 | Yes |
| Minutes of ICC/HSCC meeting endorsing Proposal |  | 8, 13 | Yes |
| comprehensive Multi Year Plan - cMYP |  | 4 | Yes |
| cMYP Costing tool for financial analysis |  | 5 | Yes |
| Minutes of last three ICC/HSCC meetings |  | 9, 10, 11 | Yes |
| Improvement plan based on EVM |  | 12 | Yes |
| WHO/UNICEF Joint Reporting Form (JRF) |  |  |  |
| ICC/HSCC workplan for forthcoming 12 months |  |  |  |
| National policy on injection safety |  |  |  |
| Action plans for improving injection safety |  |  |  |
| Plan for NVS introduction (if not part of cMYP) |  | 6 |  |
| Banking details |  |  |  |

[1] Please indicate the duration of the plan / assessment / document where appropriate

# Attachments

List of all the mandatory and optional documents attached to this form

Note: Use the Upload file arrow icon to upload the document. Use the Delete item icon to delete a line. To add new lines click on the New item icon in the Action column.

| ID | File type | File name |  | New file | Actions |
| --- | --- | --- | --- | --- | --- |
|  | Description | Date and Time | Size |  |  |
| 1 | File Type: MoH Signature (or delegated authority) of Proposal * File Desc: | File name: Ministers of Finance & Health signatures0001.pdf Date/Time: 09.05.2011 08:56:50 Size: 603 KB |  |  |  |
| 2 | File Type: MoF Signature (or delegated authority) of Proposal * File Desc: | File name: Ministers of Finance & Health signatures0001.pdf Date/Time: 18.05.2011 01:37:03 Size: 603 KB |  |  |  |
| 3 | File Type: Signatures of ICC or HSCC or equivalent in Proposal * File Desc: | File name: Signatures of Key stakeholder reps0001.pdf Date/Time: 18.05.2011 01:38:36 Size: 465 KB |  |  |  |
| 4 | File Type: comprehensive Multi Year Plan - cMYP * File Desc: | File name: UGANDA CMYP 2010-2014.doc Date/Time: 20.05.2011 03:24:04 Size: 950 KB |  |  |  |
| 5 | File Type: cMYP Costing tool for financial analysis * File Desc: | File name: UGA cMYP_Costing_Tool_Vs 2.5.xls Date/Time: 20.05.2011 03:26:23 Size: 3 MB |  |  |  |
| 6 | File Type: Plan for NVS introduction (if not part of cMYP) File Desc: | File name: Uganda Plan for Introduction of PCV.doc Date/Time: 20.05.2011 03:30:01 Size: 296 KB |  |  |  |
| 7 | File Type: other File Desc: Health Sector Strategic and Investment Plan 2010/11 - 2014/15 | File name: HSSIP.pdf Date/Time: 19.05.2011 12:01:17 Size: 1 MB |  |  |  |
| 8 | File Type: Minutes of ICC/HSCC meeting endorsing Proposal * File Desc: April 2010 | File name: HPAC minutes April2010.pdf Date/Time: 23.05.2011 12:36:23 Size: 6 MB |  |  |  |
| 9 | File Type: Minutes of last three ICC/HSCC meetings * File Desc: Oct. 2010 | File name: HPAC minutes Oct2010.pdf Date/Time: 23.05.2011 12:36:59 Size: 4 MB |  |  |  |
| 10 | File Type: Minutes of last three ICC/HSCC meetings * File Desc: Nov. 2010 | File name: HPAC minutes Nov2010.pdf Date/Time: 23.05.2011 12:37:15 Size: 3 MB |  |  |  |
| 11 | File Type: Minutes of last three ICC/HSCC meetings * File Desc: Dec. 2010 | File name: HPAC minutes Dec2010.pdf Date/Time: 23.05.2011 12:37:53 Size: 4 MB |  |  |  |
| 12 | File Type: Improvement plan based on EVM * File Desc: | File name: Uganda VMA-2007 report.doc Date/Time: 24.05.2011 06:46:22 Size: 619 KB |  |  |  |
| 13 | File Type: Minutes of ICC/HSCC meeting endorsing Proposal * File Desc: SMC Meeting minutes endorsing Proposal | File name: Uganda SMC Minutes for April 2011.doc Date/Time: 31.05.2011 06:01:30 Size: 79 KB |  |  |  |
| 14 | File Type: other File Desc: Letter from DG - reply to conditions | File name: Uganda DG Letter 30 May 2011.pdf Date/Time: 15.06.2011 04:38:42 Size: 774 KB |  |  |  |

Banking Form

| In accordance with the decision on financial support made by the GAVI Alliance, the Government of Uganda hereby requests that a payment be made via electronic bank transfer as detailed below: |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Name of Institution (Account Holder): |  |  |  |  |  |
| Address: |  |  |  |  |  |
| City Country: |  |  |  |  |  |
| Telephone no.: |  | Fax no.: |  |  |  |
| Currency of the bank account: |  |  |  |  |  |
| For credit to: |  |  |  |  |  |
| Bank account's title: |  |  |  |  |  |
| Bank account no.: |  |  |  |  |  |
| Bank's name: |  |  |  |  |  |

Is the bank account exclusively to be used by this program?

By who is the account audited?

Signature of Government’s authorizing official

| Name: |  | Seal |
| --- | --- | --- |
| Title: |  |  |
| Signature: |  |  |
| Date: |  |  |

| FINANCIAL INSTITUTION |  | CORRESPONDENT BANK (In the United States) |  |
| --- | --- | --- | --- |
| Bank Name: |  |  |  |
| Branch Name: |  |  |  |
| Address: |  |  |  |
| City Country: |  |  |  |
| Swift Code: |  |  |  |
| Sort Code: |  |  |  |
| ABA No.: |  |  |  |
| Telephone No.: |  |  |  |
| FAX No.: |  |  |  |

I certify that the account no is held by (Institution name) at this banking institution.

| The account is to be signed jointly by at least 0 (number of signatories) of the following authorized signatories: |  |  |
| --- | --- | --- |
| 1 |  |  |
|  | Name: |  |
|  | Title: |  |
| 2 |  |  |
|  | Name: |  |
|  | Title: |  |
| 3 |  |  |
|  | Name: |  |
|  | Title: |  |
| 4 |  |  |
|  | Name: |  |
|  | Title: |  |

Name of bank’s authorizing official

Signature:

Date:

Seal: