|  |  |  |  |  | [V2.7]. |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| GAVI Alliance. |  |  |  |  |  |  |  |
| Application Form for Country Proposals. |  |  |  |  |  |  |  |
| For Support to:. |  |  |  |  |  |  |  |
| Routine New Vaccines Support. Preventive Campaign Support. |  |  |  |  |  |  |  |
| Submitted by. |  |  |  |  |  |  |  |
| The Government of. |  |  |  |  |  |  |  |
| Nepal. |  |  |  |  |  |  |  |
| Date of submission: 9/19/2012. |  |  |  |  |  |  |  |
| Deadline for submission: 8/31/2012. |  |  |  |  |  |  |  |
| Select Start and End Year of your Comprehensive Multi-Year Plan (cMYP). |  |  |  |  |  |  |  |
| Start Year. | 2011. |  |  |  |  |  |  |
|  |  |  | End Year. | 2016. |  |  |  |
| Form revised in 2012. |  |  |  |  |  |  |  |
| (To be used with Guidelines of September 2012). |  |  |  |  |  |  |  |
| Please submit the Proposal using the online platform. https://AppsPortal.gavialliance.org/PDExtranet. |  |  |  |  |  |  |  |
| Enquiries to: proposals@gavialliance.org or representatives of a GAVI partner agency. The documents can be shared with GAVI partners, collaborators and general public. The Proposal and attachments must be submitted in English, French, Spanish, or Russian.. Note: Please ensure that the application has been received by the GAVI Secretariat on or before the day of the deadline.. The GAVI Secretariat is unable to return submitted documents and attachments to countries. Unless otherwise specified, documents will be shared with the GAVI Alliance partners and the general public.. |  |  |  |  |  |  |  |

GAVI ALLIANCE GRANT TERMS AND CONDITIONS. FUNDING USED SOLELY FOR APPROVED PROGRAMMES. The applicant country ("Country") confirms that all funding provided by the GAVI Alliance will be used and applied for the sole purpose of fulfilling the programme(s) described in the Country's application. Any significant change from the approved programme(s) must be reviewed and approved in advance by the GAVI Alliance. All funding decisions for the application are made at the discretion of the GAVI Alliance Board and are subject to IRC processes and the availability of funds.. AMENDMENT TO THE APPLICATION. The Country will notify the GAVI Alliance in its Annual Progress Report if it wishes to propose any change to the programme(s) description in its application.The GAVI Alliance will document any change approved by the GAVI Alliance, and the Country's application will be amended.. RETURN OF FUNDS. The Country agrees to reimburse to the GAVI Alliance all funding amounts that are not used for the programme(s) described in its application. The country's reimbursement must be in US dollars and be provided, unless otherwise decided by the GAVI Alliance, within sixty (60) days after the Country receives the GAVI Alliance's request for a reimbursement and be paid to the account or accounts as directed by the GAVI Alliance.. SUSPENSION/ TERMINATION. The GAVI Alliance may suspend all or part of its funding to the Country if it has reason to suspect that funds have been used for purpose other than for the programmes described in the Country's application, or any GAVI Alliance-approved amendment to the application.The GAVI Alliance retains the right to terminate its support to the Country for the programmes described in its application if a misuse of GAVI Alliance funds is confirmed.. ANTICORRUPTION. The Country confirms that funds provided by the GAVI Alliance shall not be offered by the Country to any third person, nor will the Country seek in connection with its application any gift, payment or benefit directly or indirectly that could be construed as an illegal or corrupt practice.. AUDITS AND RECORDS. The Country will conduct annual financial audits, and share these with the GAVI Alliance, as requested. The GAVI Alliance reserves the right, on its own or through an agent, to perform audits or other financial management assessment to ensure the accountability of funds disbursed to the Country.. The Country will maintain accurate accounting records documenting how GAVI Alliance funds are used. The Country will maintain its accounting records in accordance with its government-approved accounting standards for at least three years after the date of last disbursement of GAVI Alliance funds. If there is any claims of misuse of funds, Country will maintain such records until the audit findings are final. The Country agrees not to assert any documentary privilege against the GAVI Alliance in connection with any audit.. CONFIRMATION OF LEGAL VALIDITY. The Country and the signatories for the Country confirm that its application, and Annual Progress Report, are accurate and correct and form legally binding obligations on the Country, under the Country's law, to perform the programmes described in its application, as amended, if applicable, in the APR.. CONFIRMATION OF COMPLIANCE WITH THE GAVI ALLIANCE TRANSPARANCY AND ACCOUNTABILITY POLICY. The Country confirms that it is familiar with the GAVI Alliance Transparency and Accountability Policy (TAP) and complies with the requirements therein.. USE OF COMMERCIAL BANK ACCOUNTS. The Country is responsible for undertaking the necessary due diligence on all commercial banks used to manage GAVI cash-based support. The Country confirms that it will take all responsibility for replenishing GAVI cash support lost due to bank insolvency, fraud or any other unforeseen event.. ARBITRATION. Any dispute between the Country and the GAVI Alliance arising out of or relating to its application that is not settled amicably within a reasonable period of time, will be submitted to arbitration at the request of either the GAVI Alliance or the Country. The arbitration will be conducted in accordance with the then-current UNCITRAL Arbitration Rules. The parties agree to be bound by the arbitration award, as the final adjudication of any such dispute. The place of arbitration will be Geneva, Switzerland. . The languages of the arbitration will be English or French.. For any dispute for which the amount at issue is US$ 100,000 or less, there will be one arbitrator appointed by the GAVI Alliance. For any dispute for which the amount at issue is greater than US $100,000 there will be three arbitrators appointed as follows: The GAVI Alliance and the Country will each appoint one arbitrator, and the two arbitrators so appointed will jointly appoint a third arbitrator who shall be the chairperson.. The GAVI Alliance will not be liable to the country for any claim or loss relating to the programmes described in the application, including without limitation, any financial loss, reliance claims, any harm to property, or personal injury or death. Country is solely responsible for all aspects of managing and implementing the programmes described in its application..

1. Application Specification. Please specify for which type of GAVI support you would like to apply to..

Type of Support; Vaccine; Start Year; End Year; Preferred second presentation[1]. Routine New Vaccines Support; Pneumococcal (PCV13), 1 dose(s) per vial, LIQUID; 2014; 2016. Preventive Campaign Support; MR, 10 dose(s) per vial, LYOPHILISED; 2013; 2013.

[1] This "Preferred second presentation" will be used in case there is no supply available for the preferred presentation of the selected vaccine ("Vaccine" column). If left blank, it will be assumed that the country will prefer waiting until the selected vaccine becomes available..

Note for HPV and MR: These prices are indicative only as GAVI has not procured HPV and MR vaccines for GAVI countries yet. Prices will be finalised through tender processes in Q3. GAVI will only fund HPV vaccines if an acceptable price reduction is secured from the current price indicated. The MR price is based on the current price to UNICEF.

2. Table of Contents.

1. Application Specification. 2. Table of Contents. 3. Executive Summary. 4. Signatures. 4.1. Signatures of the Government and National Coordinating Bodies. 4.1.1. Government and the Inter-Agency Coordinating Committee for Immunisation. 4.1.2. National Coordinating Body - Inter-Agency Coordinating Committee for Immunisation. 4.1.3. The Inter-Agency Coordinating Committee for Immunisation. 4.2. National Immunization Technical Advisory Group for Immunisation. 4.2.1. The NITAG Group for Immunisation. 5. Immunisation Programme Data. 5.1. Basic facts. 5.1.1 MCV Immunisation coverage. 5.2. Baseline and Annual Targets (NVS Routine Support). 5.3. Baseline and Annual Targets for Preventive Campaign(s). 5.3.1 Baseline and annual targets (MR campaign). 6. New and Under-Used Vaccines (NVS Routine). 6.1. Assessment of burden of relevant diseases (if available). 6.2 Requested vaccine (Pneumococcal (PCV13), 1 dose(s) per vial, LIQUID). 6.2.1 Co-financing information. 6.2.2 Specifications of vaccinations with new vaccine. 6.2.3 Portion of supply to be procured by the country (and cost estimate, US$). 6.2.4 Portion of supply to be procured by the GAVI Alliance (and cost estimate, US$). 6.2.5 New and Under-Used Vaccine Introduction Grant. 7. NVS Preventive Campains. 7.1. Assessment of burden of relevant diseases related to campaigns (if available). 7.2 Requested for MR, 10 dose(s) per vial, LYOPHILISED campaign support. 7.2.1 Summary for MR campaign support. 7.2.2 Grant Support for Operational Costs of the MR Campaign. 7.2.3 Evidence of introduction of RCV in routine programme. 7.2.4 Introduction planning for RCV. 7.2.5 Measles surveillance indicators. 7.2.6 Rubella Containing Vaccine introduction Grant. 8. Procurement and Management. 8.1. Procurement and Management of New and Under-Used Vaccines Routine. 8.2. Procurement and Management for NVS Preventive Campaign(s). 8.2.1 Procurement and Management for MR, 10 dose(s) per vial, LYOPHILISED campaign. 8.3. Vaccine Management (EVSM/EVM/VMA). 9. Additional Comments and Recommendations from the National Coordinating Body (ICC/HSCC). 10. Attachments. 11. Annexes. Annex 1 - NVS Routine Support. Annex 1.1 Pneumococcal (PCV13), 1 dose(s) per vial, LIQUID. Table Annex 1.1 A Rounded up portion of supply that is procured by the country and estimate of relative costs in US$. Table Annex 1.1 B Rounded up portion of supply that is procured by GAVI and estimate of relative costs in US$. Table Annex 1.1 C Summary table for vaccine Pneumococcal (PCV13), 1 dose(s) per vial, LIQUID. Table Annex 1.1 D Estimated numbers for Pneumococcal (PCV13), 1 dose(s) per vial, LIQUID, associated injection safety material and related co-financing budget (page 1). Annex 2 - NVS Routine – Preferred Second Presentation. Annex 3 - NVS Preventive campaign(s). Table Annex 3.1 C Summary table for vaccine MR, 10 dose(s) per vial, LYOPHILISED. Table Annex 3.1 D Estimated numbers for MR, 10 dose(s) per vial, LYOPHILISED, associated injection safety material and related co-financing budget (page 1). Annex 4. Table Annex 4A: Commodities Cost. Table Annex 4B: Freight cost as percentage of value. Table Annex 4C: Low - Minimum country's co-payment per dose of co-financed vaccine.. Table Annex 4D: Wastage rates and factors. Table Annex 4E: Vaccine maximum packed volumes. 12. Banking Form.

3. Executive Summary.

Please provide a summary of your country's proposal, including the following the information:. l; For each specific request, NVS routine support or NVS campaign :. ¡; The duration of support. ¡; The total amount of funds. ¡; Details of the vaccine(s), if applicable. l; Relevant baseline data, including:. ¡; DTP3 and Measles coverage data (as reported on the WHO/UNICEF Joint Reporting Form). ¡; Birth cohort, targets and immunisation coverage by vaccines. l; Country preparedness. ¡; Summary of EVM assessment. l; The nature of stakeholders' participation in developing this proposal. ¡; Inter-Agency Coordinating Committee. Nepal is committed in providing immunization to all eligible children. Immunization is the government's priority number one health program (P1). The GoN has been increasing the share of the budget allocation for EPI reflecting its committment to the programme. The government procures all traditional vaccines (BCG, OPV, measles, TT and JE) from its own resources and co-finances penta vaccine with GAVI. For last 10 years Nepal has introduced HepB, Hib and JE (high risk districts) vaccine into routine immunization. Around 90% of vaccination is provided through EPI outreach clinics. Recently Nepal has developed plan for intensification of routine immunization : year 2012/13 year of intensification of routine immunization for reaching every eligible child with routine vaccination" Nepal is applying for GAVI support for introduction of pneumococcal vaccines and introduction grant for MR vaccine into routine immunization. Types of vaccine requested 1. PCV (13 valent) - duration of support is 2014-2016. The total amount of funds requested to GAVI is $ 24,305,000. The GoN will co-finance $ 1,364,500. Nepal has requested single dose PCV 13 valent vaccine. Although the cold chain space is less required for PCV 10, the 13 valent covers more sero types. 2. Vaccine introduction grant for introduction of MR vaccine into routine immunization Baseline data: As per JRF (2011) DPT3-96% and MCV1-88%, The NDHS survey (2011) shows DPT3 coverage of 92% and measles-88%. Birth cohort is estimated: 2013- 676,877; 2014- 688,269; 2015- 703,102; 2016- 718,147, surviving infants estimates: 2013- 651,156; 2014- 664,177; 2015- 680,601; 2016- 696,603 Vaccination coverage: BCG - 98% throughout 5 years; DPT3/OPV3: 2013-90%, 2014-92%, 2015 and 2016-95%, measles: 2013-90%; 2014-92%; 2015 and 2016-95% Country preparedness: Nepal has conducted EVM in December 2011 and currently in process of implementing recommendations made from EVM. Nepal also carried out cold chain replacement plan for 10 years (2010-2020) which shows Nepal has enough space for introduction of pneumococcal vaccine. Despite of the plan Nepal currently is updating inventory of cold chain equipments through out the country which should be finished by December 2012. Nepal has allocated funds for procurement of cold chain equipments based on district need and will replace old equipments. Some of vaccine introduction grant will be used for procurement of cold chain equipments and strengthening of cold chain system. Nepal will also introduced MR vaccine replacing measles vaccine as MCV1 from January 2013. Nature of stakeholders participation in developing the proposal The current proposal has been developed with extensive consultation process between government personnel and partners. The NCIP has recommended introduction of pneumococcal and MR vaccine. The proposal has been approved by ICC. MR campaign: Nepal has planned MR campaign targeting all children 9 months to 15 years of age in all 75 districts in 2012. The campaign will be conducted in 3 phases. 1st phase which included 15 districts has completed campaign in April 2012. 2nd phase is planned for September in 25 districts and third phase which includes 35 districts is planned for December. The total target population is 9,958,197. In its cMYP Nepal has set measles elimination by 2016. Nepal wants to use measles elimination platform for control/elimination of rubella/CRS. Following the campaign, Nepal is planning to replace measles vaccine at 9 months with MR vaccine into routine immunization. The MR vaccine will be introduced into routine immunization by April 2013. Nepal is NOT REQUESTING any support for MR campaign. The support requested is vaccine introduction grant..

| 4. Signatures. |  |  |
| --- | --- | --- |
| 4.1. Signatures of the Government and National Coordinating Bodies. |  |  |
| 4.1.1. Government and the Inter-Agency Coordinating Committee for Immunisation. |  |  |
| The Government of Nepal would like to expand the existing partnership with the GAVI Alliance for the improvement of the infants routine immunisation programme of the country, and specifically hereby requests for GAVI support for. |  |  |
|  | Pneumococcal (PCV13), 1 dose(s) per vial, LIQUID routine introduction. MR, 10 dose(s) per vial, LYOPHILISED preventive campaigns. |  |
| The Government of Nepal commits itself to developing national immunisation services on a sustainable basis in accordance with the Comprehensive Multi-Year Plan presented with this document. The Government requests that the GAVI Alliance and its partners contribute financial and technical assistance to support immunisation of children as outlined in this application.. |  |  |
| Table(s) 6.2.4 in the NVS Routine section of this application shows the amount of support in either supply or cash that is required from the GAVI Alliance. Table(s) 6.2.3 of this application shows the Government financial commitment for the procurement of this new vaccine (NVS support only).. |  |  |
| Following the regulations of the internal budgeting and financing cycles the Government will annually release its portion of the co-financing funds in the month of January.. |  |  |
| The payment for the first year of co-financed support will be around January 2013 for MR, 10 dose(s) per vial, LYOPHILISED.. The payment for the first year of co-financed support will be around January 2014 for Pneumococcal (PCV13), 1 dose(s) per vial, LIQUID.. |  |  |
| Please note that this application will not be reviewed or approved by the Independent Review Committee (IRC) without the signatures of both the Minister of Health and Minister of Finance or their delegated authority.. |  |  |
| Minister of Health (or delegated authority); Minister of Finance (or delegated authority). Name; MISHRA, Dr Praveen, Secretary, Ministry of Health & Population; Name; BASKOTA, Mr Krishna Hari, Secretary, Ministry of Finance. Date; Date. Signature; Signature. |  |  |
| This report has been compiled by (these persons may be contacted in case the GAVI Secretatiat has queries on this document):. |  |  |
| Full name; Position; Telephone; Email. BOHARA, Dr Rajendra; National Coordinator, IPD/WHO; 00-977-9851024615; boharar@searo.who.int. MAHAT, Dr Kishori; CHealth Specialist, Child Health and Survival, UNICEF; 00-977-9801010018; kmahat@unicef.org. POKHAREL, Dr Tara Nath; Director, Child Health Division, DoHS; 00-977-9852680122; pokhrelt1@gmail.com. SUBEDI, Mr GR; EPI Chief, DoHS; 00-977-1-4262263; subedi.giriraj@gmail.com. |  |  |
| 4.1.2. National Coordinating Body - Inter-Agency Coordinating Committee for Immunisation. |  |  |
| We the members of the ICC, HSCC, or equivalent committee [1] met on the 21/08/2012 to review this proposal. At that meeting we endorsed this proposal on the basis of the supporting documentation which is attached.. |  |  |
| [1] Inter-agency Coordinating Committee or Health Sector Coordinating Committee, or equivalent committee which has the authority to endorse this application in the country in question.. |  |  |
| The endorsed minutes of this meeting are attached as document number 4.. |  |  |
| Name/Title*; Agency/Organisation*; Signature. Bohara, Dr R, National Coordinator; EPI, WHO. Bohara, Mr BR; Nepal Red Cross. Gnawali, Dr D; SABIN. KC, Dr NP, Director; Logistics Management Division, DoHS/MoHP. Kentro, Ms Linda; Chief, Health & Family Planning, USAID. Khadka, Mr BB, Director; NHEICC, DoHS/MoHP. Mahat, Dr K, Health Specialist; Health Section, UNICEF. Paazjmakers, Dr H, Chief; Health Section, UNICEF. Pokharel, Dr TN, Director; Child Health Division, DoHS/MoHP. Shakya, Mr RM, Chairman; Polio Plus Committee, Rotary International. Sherpa, Dr MG, Director General of Health Services; Department of Health Services, MoHP. Sitaula, Mr K; Lions International. Subedi, Mr GR, EPI Chief; Child Health Division, DoHS/MoHP. Upreti, Dr SR, Director; Family Health Division, DoHS/MoHP. |  |  |
| 4.1.3. The Inter-Agency Coordinating Committee for Immunisation. |  |  |
| Agencies and partners (including development partners and NGOs) supporting immunisation services are co-ordinated and organised through an inter-agency coordinating mechanism (ICC, HSCC, or equivalent committee). The ICC, HSCC, or equivalent committee is responsible for coordinating and guiding the use of the GAVI NVS routine support and/or campaign support. Please provide information about the ICC, HSCC, or equivalent committee in your country in the table below.. |  |  |
| Profile of the ICC, HSCC, or equivalent committee. |  |  |
| Name of the committee; Inter Agency Coordination Committee. Year of constitution of the current committee; 2000. Organisational structure (e.g., sub-committee, stand-alone); Stand-alone. Frequency of meetings; at least 3 meetinsg per year ( frequency depends upon requirement). |  |  |
| Composition. |  |  |
| Function; Title / Organisation; Name. Chair; Director-General, Department of Health Services; SHERPA, Dr MG. Secretary; EPI-Chief; SUBEDI, Mr GR. Members; Director, Child Health Division; POKHAREL, Dr TN. Director, Logistic Management Division; KC, Dr NP. Director, Management Division; RAJENDRA, Dr SP. Director, National Health Education, Information and Communication Director, Management Division; KHADKA, Mr B. Chief, Health & Family Planning, USAID; KENTRO, Ms Linda. Chairman, Polio Plus Committee, Rotary International; SHAKYA, Mr RM. Representative, WHO; AUNG, Dr Lin. Representative, UNICEF; SINGER, Ms H. Sr. Health Specialist, World Bank; SHARMA Dr N. Sr. Health Advisor, DFID; CLAPHAM Ms S. Asst. Residential Representative, JICA; HIASA Ms Miwa. Representative, National Planning Commission; SHRESTHA, Mr GK. Representative, Ministry of Finance; LEKHAK, Mr DR. Chief-PME&FAD, MoHP; CHAND, Dr PB. Chief, Finance Section, MoHP; POUDEL, Mr G. |  |  |
| Major functions and responsibilities of the ICC/HSCC:. |  |  |
| - Provide technical support to NIP as necessary - Coordinate with international partners in the delivery of immunization services including resource mobilization - Coordinate and monitor with other health programs in relation to enhance effectiveness and quality service in immunization and to assure program sustainability - Invite any other international/national partners involved in immunization program in Nepal for their input, feedback and expertise - Form sub-committees and working groups as necessary - Coordinate with GoN/NGOs and international development partners for mobilization of resources for immunization program - Assure effective and efficient use of overall immunization and GAVI funds - Provide input during preparation of immunization annual work plan - Provide support and monitor ongoing polio eradication activities. |  |  |
| Three major strategies to enhance the committee's role and functions in the next 12 months. |  |  |
| 1.; Involvement in preparation, implementation and evaluation of annual EPI workplan. 2.; Provide support in preparation and implementation of introduction of new and underused vaccines. 3.; Technical support in providing vision, goal and strategies in overall strengthening of immunization program. |  |  |
| 4.2. National Immunization Technical Advisory Group for Immunisation. |  |  |
| (If it has been established in the country). |  |  |
| We the members of the NITAG met on the to review this proposal. At that meeting we endorsed this proposal on the basis of the supporting documentation which is attached.. |  |  |
| The endorsed minutes of this meeting are attached as document number 4.. |  |  |

4.2.1. The NITAG Group for Immunisation.

Profile of the NITAG.

Name of the NITAG; National Committee for Immunization Practices. Year of constitution of the current NITAG; 2009. Organisational structure (e.g., sub-committee, stand-alone); Stand-alone. Frequency of meetings; minimum twice a year.

Composition.

Function; Title / Organisation; Name. Chair; Professor Paediatrician; ADHIKARI, Prof. Dr RK. Secretary; Director, Child Health Division; POKHAREL, Dr TN. Members; Rector, BPKIHS, Paediatrician; SINGH, Prof. Dr R. Public Health Specialist; SUBEDI, Dr BK. Public Health Specialist; PANDEY, Dr BR. Epidemiologist; UPRETI, Dr SR. Pathologist; MALLA, Prof, Dr S. Chairperson, Nepal paediatric Association; ARYAL, Dr DR. Dirctor, Department of Drug Administration; PRASAD, Mr RR. Director, Logistics Management Division; KC, Dr NP. Representative WHO; AUNG, Dr Lin. Representative, UNICEF; SINGER Ms Hannah.

Major functions and responsibilities of the NITAG.

- Main role of the NCIP is to provide technical guidance to MoH&P/EPI on immunization policies, norms and practices, issues of vaccine quality and safety, immunization choices and strategies, new vaccines and new delivery technologies - The NCIP will be technical resource to assist government in evidence-based decision making & be the technical arm that supports the country’s stewardship immunization program.

Three major strategies to enhance the NITAG's role and functions in the next 12 months.

1.; To provide technical guidance to MoH&P/EPI on immunization policies, norms and practices, immunization choices and strategies, new vaccines and new delivery technologies. 2.; To assist government in evidence-based decision making& be the technical arm that supports the country’s stewardship immunization program. 3.; Monitor the introduction of new and underused vaccines and its implication.

5. Immunisation Programme Data.

5.1. Basic facts.

Please complete the tables below, using data from available sources. Please identify the source of the data, and the date. Where possible use the most recent data and attach the source document..

▪; Please refer to the Comprehensive Multi-Year Plan for Immunisation (cMYP) (or equivalent plan) and attach a complete copy (with an Executive Summary) as DOCUMENT NUMBER : 6. ▪; Please attach relevant Vaccine Introduction Plans as DOCUMENT NUMBER : 7. ▪; Please refer to the two most recent annual WHO/UNICEF Joint Reporting Forms (JRF) on Vaccine Preventable Diseases. ▪; Please refer to Health Sector Strategy documents, budgetary documents, and other reports, surveys etc, as appropriate..

For the year 2012 (most recent; specify dates of data provided).

Figure; Year; Source. Total population; 28,480,814; 2012; HMIS. Infant mortality rate (per 1000); 46; 2011; Nepal Demographic Health Survey (NDHS), 2011. Surviving infants[1]; 659,016; 2012; HMIS ( as reflected in APR 2011). GNI per capita (US$); 540; 2011; World Bank, World Development Indicators Database (2011). Total Health Expenditure (THE) as a percentage of GDP; 6; %; 2009; UNDP Human Development Report (2011). General government expenditure on health (GGHE) as % of General government expenditure; 6; %; 2010; GoN, Financial Comptroller General Office.

[1] Surviving infants = Infants surviving the first 12 months of life.

Please provide some additional information on the planning and budgeting context in your country. Each year all divisions and centers, DoHS/MoHP prepare annual work plan after intensive consultation including external partners. Then the annual plan is submitted to Ministry of Health & Population for further review. The MoHP prepares an Annual Plan with budget of Government of Nepal, which is then submitted to National Planning Commission for approval of the programs. After approval of the activities/programs, the plan is submitted to the MoF for budget allocation. After approval of the budget by the MoF, the annual health plan together with the national plan is submitted to parliament for approval. Once the plan is approved by parliament it is reflected as the annual consolidated plan in the “Red Book”. The MoF sends the approved plan with budget to MoHP. The MoHP gives authority to DoHS for implementation of the plan. The DoHS send authority to all districts health offices for expenditure of the fund as per approved activities in the annual plan. The health sector budget will undergo internal as well as external audit as per established procedures of the government of Nepal. District health offices maintain district level accounts by budget heading and send monthly expenditure statements to the departments and respective DTCOs for internal audit. DTCOs carry out quarterly internal audits at district level. External audit is carried out by the Auditor General Office annually on the consolidated statement prepared by Ministry of Health and Ministry of Finance after internal audit.. Please indicate the name and date of the relevant planning document for health. - Nepal Health Sector Programme II (2010-2015) - Comprehensive Multiyear Plan on Immunization (cMYP) (2011-2016). Is the CMYP (or updated Multi-Year Plan) aligned with the document (timing, content, etc.). cMYP (2011-2016) is aligned with Nepal Health Sector Programme-II.. Please indicate the national planning budgeting cycle for health. The government national planning budgeting cycle is 15 July – 14 July of the following year. Please indicate the national planning cycle for immunisation. The national planning cycle for immunization follows the national budgeting cycles from 15 July – 14 July of the following year. Please indicate if sex disaggregated data (SDD) is used in immunisation routine reporting systems. The Health Management and Information System, Management Division, DoHS (HMIS) is piloting in 15 districts on collecting immunization data aggregated by sex, caste, and ethnicity. Currently disaggregated data on sex are collected through the (DHS) survey.. Please indicate if gender aspects relating to introduction of a new vaccine have been addressed in the introduction plan. Usually there is no significant difference in all vaccination coverage between male and female child (88 to 86%). Both sexes have equal access to vaccination. But still gender aspects relating to new vaccine introduction will be addressed in new vaccine introduction plan through advocacy, social mobilization and BCC.. Please describe any recent evidence of socio-economic and/or gender barriers to the immunisation programme through studies or surveys?. The NDHS 2011 survey shows that 88% of male and 86% of female children receive all routine vaccinations, around 3% of female and 2.8% of male children do not receive any vaccinations. Coverage for all antigens in the highest wealth quintile is 95%, whereas in lowest wealth quintile it is 85%. Coverage also increases with education of mothers (92% among children of mothers with higher education and only 78% for children of mothers with no education). Urban children are more likely to receive vaccine than rural children (90% compared to 88%).. Country should provide an outline of all preparatory activities for vaccine(s) introduction. Some of the major preparatory activities that would be conducted for vaccine introduction would be: - Orientation to vaccinators and other health staffs - District planning meeting - Municipal planning and orientation meeting - Advocacy, social mobilization and IEC - Supervision and monitoring - Strengthening of cold chain system (Procurement and transportation of cold chain equipment and training to cold chain staff).

5.1.1 MCV Immunisation coverage.. Please provide information concerning routine immunisation coverage related to measle-containing vaccines (MCV).. Table 5.1.1: MCV Immunisation coverage.. Coverage; 2005; 2006; 2007. Administrative1); WHO/UNICEF2); Administrative1); WHO/UNICEF2); Administrative1); WHO/UNICEF2). Measles 1st dose (%); 79.3; 74; 87.5; 88; 82.6; 89. Measles 2st dose (%); 0; 0; 0; 0; 0; 0. Supplementary Immunization Activities (SIA) (%); 100; 100; 0; 0; 0; 0.. Coverage; 2008; 2009; 2010. Administrative1); WHO/UNICEF2); Administrative1); WHO/UNICEF2); Administrative1); WHO/UNICEF2). Measles 1st dose (%); 79; 90; 75.3; 90; 86.4; 86. Measles 2st dose (%); 0; 0; 0; 0; 0; 0. Supplementary Immunization Activities (SIA) (%); 94; 95; 0; 0; 0; 0.. Coverage; 2011. Administrative1); WHO/UNICEF2). Measles 1st dose (%); 87.7; 88. Measles 2st dose (%); 0; 0. Supplementary Immunization Activities (SIA) (%); 0; 0.... Note:. 1)National reported Administrative Coverage. 2)WHO/UNICEF estimated coverage. Was the last Measles Supplementary Immunization Activities (SIA) administrative coverage or results of a survey of acceptable methodology Administrative coverage...

| 5.2. Baseline and Annual Targets (NVS Routine Support) |  |
| --- | --- |
| Please refer to cMYP pages to assist in filling-in this section.. |  |
| Number; Base Year; Baseline and Targets; Baseline and Targets; Baseline and Targets. 2012; 2014; 2015; 2016. Total births; 692,646; 688,269; 703,101; 718,147. Total infants’ deaths; 33,630; 24,092; 22,500; 21,544. Total surviving infants; 659,016; 664,177; 680,601; 696,603. Total pregnant women; 769,699; 757,206; 773,411; 789,962. Target population vaccinated with BCG; 678,793; 674,602; 689,039; 703,784. BCG coverage; 98 %; 98 %; 98 %; 98 %. Target population vaccinated with OPV3. OPV3 coverage; 95 %; 92 %; 95 %; 95 %. Number of infants vaccinated (to be vaccinated) with DTP1; 645,836; 644,349; 666,989; 682,670. Number of infants vaccinated (to be vaccinated) with DTP3; 626,065; 611,135; 646,571; 661,772. DTP3 coverage; 95 %; 92 %; 95 %; 95 %. Wastage[1] rate in base-year and planned thereafter (%) for DTP; 15; 15; 15; 15. Wastage[1] factor in base-year and planned thereafter for DTP; 1.18; 1.18; 1.18; 1.18. Target population vaccinated with 1st dose of Pneumococcal (PCV13); 0; 644,349; 666,989; 682,670. Target population vaccinated with 3rd dose of Pneumococcal (PCV13); 0; 611,135; 646,571; 661,772. Pneumococcal (PCV13) coverage; 0 %; 92 %; 95 %; 95 %. First Presentation: Pneumococcal (PCV13), 1 dose(s) per vial, LIQUID. Wastage[1] rate in base-year and planned thereafter (%); 0; 5; 5; 5. Wastage[1] factor in base-year and planned thereafter (%); 1.00; 1.05; 1.05; 1.05. Maximum wastage rate value for Pneumococcal (PCV13), 1 dose(s) per vial, LIQUID; 5 %; 5 %; 5 %; 5 %. Target population vaccinated with 1st dose of Measles; 593,114; 631,063; 646,571; 661,772. Measles coverage; 90 %; 95 %; 95 %; 95 %. Number of infants vaccinated (to be vaccinated) with 1st dose of TT+; 615,759; 643,626; 657,399; 671,467. TT+ coverage; 80 %; 85 %; 85 %; 85 %. Annual DTP Drop out rate [ ( DTP1 – DTP3 ) / DTP1 ] x 100; 3 %; 5 %; 3 %; 3 %.. [1] Number of infants vaccinated out of total births. [2] Number of infants vaccinated out of total surviving infants. [3] Indicate total number of children vaccinated with either DTP alone or combined. [4] Number of pregnant women vaccinated with TT+ out of total pregnant women. [5] The formula to calculate a vaccine wastage rate (in percentage): [ ( A - B ) / A ] x 100. Whereby: A = the number of doses distributed for use according to the supply records with correction for stock balance at the end of the supply period; B = the number of vaccinations with the same vaccine in the same period... |  |

| 5.3. Baseline and Annual Targets for Preventive Campaign(s).. |  |
| --- | --- |
| 5.3.1 Baseline and annual targets (MR campaign). Please specify cohort for rubella-containing vaccines (RCV):. RCV Start 9 months. RCV End 14 years. Cohort population = population 9 months - 14 years old. GAVI supports no more than 15 cohorts. If the application is not within 9 months to 15 years, please provide justification. N/A Nepal is conducting campaign targeting all children 9 months under 15 years of age... Table 5.3.1 Baseline NVS preventive campaign figures for MR.. Number; Base Year; Baseline and Targets. 2012; 2013. Total births; 692,646; 692,646. Total population 9 months - 14 years old; 9,958,197; 0. Target population vaccinated with MR; 9,958,197; 0. MR (campaign) coverage (%) [1]; 100.00 %; 0.00 %. Wastage rate in base year and thereafter (%) for MR (campaign); 15; 0. Wastage factor in base year and thereafter for MR; 1.18; 1.. [1] Number of persons vaccinated out of total births... |  |

6. New and Under-Used Vaccines (NVS Routine)

6.1. Assessment of burden of relevant diseases (if available).

Disease; Title of the assessment; Date; Results. Invasive bacterail disease (IBD); sentinel surveillance findings from one site; 2011; Nepal currently has one sentinel site for invasive bacterial disease. In 2011, this sentinel site at Patan Hospital collected 1,312 blood cultures. Of which, 5 were positive for Streptococcal pneumoniae. Among 110 cultures of cerebrospinal fluid (CSF), only one was positive for S. pneumoniae. However, this relatively low number of positive blood and CSF cultures may be in part due to widespread use of antibiotics prior to presentation for clinical investigation. pneumococcal disease; WHO estimate of pneumococcal mortality; 2008; Nationwide deaths from pneumonia caused by S. pneumoniae were estimated at 1,398 (uncertainty range 1,024 to 1,520). Nationwide deaths from meningitis caused by S. pneumoniae were estimated at 106 (uncertainty range 85-120) and other non-pneumonia, non-meningitis causes were estimated to account for an additional 106 deaths each year for a total of 1,610 deaths annually..

If new or under-used vaccines have already been introduced in your country, please give details of the lessons learned from previous introduction(s) specifically for: storage capacity, protection from accidental freezing, staff training, cold chain, logistics, coverage and drop-out rates, wastage rate, etc., and suggest action points to address them..

Lessons Learned; Action Points. Training of staff on new vaccine is essential.This opportunity could be used to review coverage and develop strategy to improve coverage.; Organize orientation training to vaccinators and other staff on new vaccine. Training on cold chain is important. The staff handling vaccine should have through knowledge on storage and transportation of vaccine at all level. There should be enough cold chain capacity at all level and which is well maintained; Organize training to cold chain staff on cold chain. Procurement of cold chain equipments based on need.. Advocacy, social mobilization and BCC is important to provide new information on new vaccine as well as strengthening of immunization coverage. Involvement of local community was important to increase demand for vaccines; Conduct advocacy, social mobilization and BCC activities at all level. The cost of vaccine is very high. So there should plan for reducing vaccine wastage.; Training should focus on reducing vaccine wastage.

Please list the vaccines to be introduced with support from the GAVI Alliance (and presentation).

- Pneumococcal (PCV 13), 1 dose per vial, liquid.

| 6.2. Requested vaccine (Pneumococcal (PCV13), 1 dose(s) per vial, LIQUID) As reported in the cMYP, the country plans to introduce Pneumococcal (PCV13), using Pneumococcal (PCV13), 1 dose(s) per vial, LIQUID.. 6.2.1. Co-financing information. If you would like to co-finance higher amount than minimum, please overwrite information in the Your co-financing row... Country group; Low.. Year 1; Year 2; Year 3. 2014; 2015; 2016. Minimum co-financing; 0.20; 0.20; 0.20. Your co-financing (please change if higher); 0.20; 0.20; 0.20.. 6.2.2. Specifications of vaccinations with new vaccine.. Data from; Year 1; Year 2; Year 3. 2014; 2015; 2016. Number of children to be vaccinated with the first dose; Table 5.2; #; 644,349; 666,989; 682,670. Number of children to be vaccinated with the third dose; Table 5.2; #; 611,135; 646,571; 661,772. Immunisation coverage with the third dose; Table 5.2; #; 92.01 %; 95.00 %; 95.00 %. Country co-financing per dose [1]; Table 6.2.1; $; 0.2; 0.2; 0.2.. [1] Total price per-dose includes vaccine cost, plus insurance, etc.... |  |
| --- | --- |

6.2.3. Portion of supply to be procured by the country (and cost estimate, US$)... 2014; 2015; 2016. Number of vaccine doses; #; 136,800; 114,300; 116,600. Number of AD syringes; #; 0; 0; 0. Number of re-constitution syringes; #; 0; 0; 0. Number of safety boxes; #; 0; 0; 0. Total value to be co-financed by country; $; 507,500; 424,000; 433,000... 6.2.4. Portion of supply to be procured by the GAVI Alliance (and cost estimate, US$).. 2014; 2015; 2016. Number of vaccine doses; #; 2,400,400; 2,004,700; 2,046,200. Number of AD syringes; #; 2,709,000; 2,240,900; 2,287,000. Number of re-constitution syringes; #; 0; 0; 0. Number of safety boxes; #; 30,075; 24,875; 25,400. Total value to be co-financed by country; $; 9,044,500; 7,552,000; 7,708,500....

6.2.5. New and Under-Used Vaccine Introduction Grant.. Please indicate in the tables below the full costs/needs and how the one-time Introduction Grant [1] will be used to support the costs of vaccine introduction and critical pre-introduction activities (refer to the cMYP). GAVI’s support may not be enough to cover the full needs so please indicate in the table below how much and who will be complementing the funds needed.. Calculation of lump-sum for the Pneumococcal (PCV13), 1 dose(s) per vial, LIQUID.. Year of New Vaccine Introduction; Births (from Table 5.2); Share per Birth in US$; Total in US$. 2014; 688,269; 0.80; 550,615.. [1] The Grant will be based on a maximum award of $0.80 per infant in the birth cohort with a minimum starting grant award of $100,000.. Cost (and finance) to introduce the Pneumococcal (PCV13), 1 dose(s) per vial, LIQUID US$.. Cost Category Full needs for new vaccine introduction in US$; Funded with GAVI introduction grant in US$. Training; 240,000; 240,000. Social Mobilization, IEC and advocacy; 45,455; 23,000. Cold Chain Equipment & Maintenance; 227,273; 200,000. Vehicles and Transportation; 0; 0. Programme Management; 90,909; 22,000. Surveillance and Monitoring; 39,773; 30,615. Human Resources; 0; 0. Waste Management; 0; 0. Technical Assistance; 0; 0. Other (please specify). Support municipal immunization; 35,000; 35,000. Total; 678,410; 550,615..... Please describe others sources of funding if available to cover your full needs.. The government will mobilize its own resources or pool funds to cover shortfall of expenses required for introduction of pneumococcal vaccine into routine immunization...

7. NVS Preventive Campains

7.1. Assessment of burden of relevant diseases related to campaigns (if available).

Disease; Title of the assessment; Date; Results. Rubella/CRS; (1) Analysis of rubella cases reported through measles surveillance, 2004 - 2009; (2) in 2008, rubel; 2008-2009; Results: From 2004-2009, there were 3,710 confirmed rubella cases and more than 95% of these cases were less than 15 years of age. Of 2,224 women of child bearing age (WCBA) tested for anti-rubella IgG, 2,020 (90.8%) were seropositive. Using a catalytic infection model, approximately 1,426 infants were born with CRS (192/100,000 live births) in 2008. Among 243 students attending a school for the deaf, 18 (7.4%) met the clinical criteria for CRS.

If MR vaccines have already been introduced in your country during campaigns, please give details of the lessons learned from previous introduction(s) specifically for: storage capacity, protection from accidental freezing, staff training, cold chain, logistics, coverage and drop-out rates, wastage rate, etc., and suggest action points to address them..

Lessons Learned; Action Points. Injection safety is very important during MR campaign to avoid program errors; Training on injection safety was given to all vaccinators.

7.1.1 Epidemiology and disease burden for Measles-Rubella. Please select at least one of the following information sources to justify RCV diseases burden results:. Epidemiological information on burden of disease:. þ; 1 - Rubella data from the measles case-based surveillance system (including the age distribution of rubella cases). þ; 2 - Rubella seroprevalence surveys. þ; 3 - Congenital Rubella Syndrome (CRS) burden information, e.g. retrospective search, modelled estimates for CRS burden, prospective surveillance. o; 4 - Other.

7.2.Requested for MR, 10 dose(s) per vial, LYOPHILISED campaign support. 7.2.1. Summary for MR campaign support. Please give a summary of the cMYP and/or the MR, 10 dose(s) per vial, LYOPHILISED campaign introduction plan sections that refer to the introduction of MR, 10 dose(s) per vial, LYOPHILISED campaign. Outline the key points that informed the decision-making process (data considered etc):. Based on cMYP and available epidemiological information and studies, Nepal decided to conduct MR campaign in 2012 targeting all children 9 months to under 15 years of age.. Please summarise (1) the waste management plan and (2) the cold chain capacity and readiness to accommodate new vaccines, stating how the cold chain expansion (if required) will be financed, and when it will be in place.Please indicate if the supplies for the campaign will have any impact in the shipment plans for your routine vaccines and how it will be handled:. There was enough space for vaccine storage for MR campaign 2012. The districts conducted campaign in phases to accomodate cold chain space and manage human resources. Currently the government is updating cold chain equipment inventory in all 75 districts. Bases on identified need for each district a replacement plan will be developed. The government and UNICEF has allocated budget for procurement of cold chain equipments. Immunization waste is mainly carried out through burn and bury methods and incinerator is used where available... 7.2.2. Grant Support for Operational Costs of the MR Campaign.. Please indicate in the tables below how the support Grant [1] will be used to support the operational costs of the campaign and other critical pre-introduction activities. GAVI's support may not be enough to cover the full needs so please indicate in the table below how much and who will be complementing the funds needed (refer to the cMYP and the MR, 10 dose(s) per vial, LYOPHILISED campaign introduction plan)... Table 7.2.2: calculation of grant to support the operational costs of the campaigns.. Year of MR support; Target population vaccinated (from Table 5.3); Share per population 9 months-14 years old in US$; Total in US$. 2013; 0; 0.65; 0.. [1] The Grant will be based on a maximum award of $0.65$ per cohort population.. Cost (and finance) of the MR, 10 dose(s) per vial, LYOPHILISED campaign US$.. Cost Category Full needs for new vaccine introduction in US$; Funded with GAVI introduction grant in US$. 2013; 2013. Training; 0; 0. Social Mobilization, IEC and advocacy; 0; 0. Cold Chain Equipment & Maintenance; 0; 0. Vehicles and Transportation; 0; 0. Programme Management; 0; 0. Surveillance and Monitoring; 0; 0. Human Resources; 0; 0. Waste Management; 0; 0. Technical Assistance; 0; 0. Planning; 0; 0. Volunteer incentives; 0; 0. Other (please specify). Total; 0; 0..... Please describe others sources of funding if available to cover your full needs.. Not relevant.. 7.2.3 Evidence of introduction of RCV in routine programme.. Please provide evidence that the country can finance the introduction of Rubella-Containing-Vaccine (RCV) into the routine programme through one of the following:.. o; 1 - A commercial contract for purchase of MR/MMR (Meales Rubella/Meales Mumps Rubella) vaccine together with shipping documents, invoice, etc.. þ; 2 - Proof that RCV has been integrated into the cMYP with the budget line for vaccines increased to include purchase of RCV as part of the health sector budget to indicate that RCV funds are allocated. o; 3 - A letter from the Minister of Finance or Budget ensuring additional funding for RCV purchase. o; 4 - An MOU between government and donor(s) (or other written document that proves donor commitment) for at least one year for purchase of RCV for use in the routine programme. o; 5 - Other.. 7.2.4 Introduction planning for RCV.. Countries should describe their plan for introduction including surveillance activities:.. Does Nepal’s cMYP include a plan for the introduction of RCV into the national programme? Yes.. Please describe a Plan Of Action (POA) for the introduction of RCV into the national programme or provide the POA as an attachment - Refer to section 10. Attachments. (Document N° ).. A detail plan of action for introduction of MR vaccine into routine immunization has been developed and is attached......

INSTRUCTIONS. Components of the POA/cMYP should include:. a. Comprehensive vaccination strategy for the introduction of RCV including a description of:. i. Initial Measles and rubella (MR) campaign. ii. Replacing Measles containing vaccine (MCV) with Measles and rubella (MR) / Measles, mumps, and rubella (MMR) in the routine childhood vaccination programme. iii. Strategies for targeting Women of Childbearing Age (WCBA), such as vaccination during routine services, post-partum, at 1st well baby visit, SIAs. iv. Linkage to the current routine immunisation schedule. v. Linkage to measles second dose, if applicable. vi. Description of how the country plans to continue to maintain high MR/MMR vaccine coverage either through routine immunisation or through Supplementary Immunization Activities (SIAs). b. A brief description of the following surveillance activities:. i. Integration of Rubella surveillance with case-based measles surveillance. ii. Congenital Rubella Syndrome (CRS) surveillance or plans to establish sentinel site CRS surveillance. iii. Adverse Event Following Immunization (AEFI) surveillance. c. Vaccine coverage monitoring and reporting. d. The communication strategy for the introduction of RCV.. 7.2.5 Measles surveillance indicators.. Please provide information on the following indicators of the quality of measles surveillance for at least two years prior to application (if available):.. Surveillance indicator; 2010; 2011. Reporting rate at national level 1); 2; 4. 100,000; 100,000. Laboratory confirmation rate (%) 2); 8; 19.. Note:. 1) Reporting rate at national level = number of discarded measles cases per 100,000 population per year. 2) Laboratory confirmation rate (%) = number of suspected cases with specimens collected for testing divided by the number of suspected cases not confirmed through epidemiological linkage.....

7.2.6 Rubella Containing Vaccine introduction Grant.. Has a Rubella Containing vaccine already been introduced nationally on a routine basis? No.. Calculation of lump-sum for the MR, 10 dose(s) per vial, LYOPHILISED.. Please indicate in the tables below how the one-time Introduction Grant[1] will be used to support the costs of vaccine introduction and critical pre-introduction activities (refer to the cMYP). GAVI’s support may not be enough to cover the full needs so please indicate in the table below how much and who will be complementing the funds needed... Year of New Vaccine Introduction; Births (From Table 5.3); Share per Birth in US$; Total in US$. 2013; 692,646; 0.80; 554,117.. [1] The Grant will be based on a maximum award of $0.80 per infant in the birth cohort with a minimum starting grant award of $100,000.. Cost (and finance) to introduce the MR, 10 dose(s) per vial, LYOPHILISED US$.. Cost Category Full needs for new vaccine introduction in US$; Funded with GAVI introduction grant in US$. Training; 330,066; 240,000. Social Mobilization, IEC and advocacy; 45,455; 30,000. Cold Chain Equipment & Maintenance; 170,455; 100,000. Vehicles and Transportation; 80,000; 80,000. Programme Management; 79,545; 64,116. Surveillance and Monitoring; 28,409; 20,000. Human Resources; 0; 0. Waste Management; 0; 0. Technical Assistance; 0; 0. Other (please specify). Support to regional training centers; 34,091; 20,000. Total; 768,021; 554,116..........

8. Procurement and Management.

8.1. Procurement and Management of New and Under-Used Vaccines Routine.

Note: The PCV vaccine must be procured through UNICEF to be able to access the price awarded by the Advance Market Commitment (AMC)..

a) Please show how the support will operate and be managed including procurement of vaccines (GAVI expects that most countries will procure vaccine and injection supplies through UNICEF):. Nepal will procure vaccine and injection supplies both GAVI and government co-finance part through UNICEF. Government's co-finance amount will be paid to UNICEF as per agreement.. b) If an alternative mechanism for procurement and delivery of vaccine supply (financed by the country or the GAVI Alliance) is requested, please document. l; Other vaccines or immunisation commodities procured by the country and descriptions of the mechanism used.. l; The functions of the National Regulatory Authority (as evaluated by WHO) to show they comply with WHO requirements for procurement of vaccines and supply of assured quality.. N/A. c) Please describe the introduction of the vaccines (refer to cMYP). Nepal plans to introduce MR vaccine in January 2013 and pneumococcal vaccine in August 2014 into routine immunization throughout the country. Following activities will take place before the introduction. 1. Develop guideline and training manuals on vaccine introduction 2. Develop advocacy and IEC materials for health staff, general population, community leaders, media, NGOs and volunteers 3. Develop communication messages for airing through FM radio and TV station 4. Organize advocacy meeting with political leaders, members of parliament, professional organization, media and communities at various level 5. Organize planning meeting at district and below level 6. Organize training of vaccinators and other health staff at various levels 7. Strengthen cold chain system at all levels 8. Implement recommendations made by EVM assessment at different level to accomodate new vaccine 9. Organize opening ceremony with involvement high level leaders, MoHP, partners and others. d) Please indicate how funds should be transferred by the GAVI Alliance (if applicable). Introduction grant could be transferred to bank account used for transfer of ISS and other funds from GAVI in past. The expenditure of introduction grant will follow the government rule and regulation applied for all other activities.. e) Please indicate how the co-financing amounts will be paid (and who is responsible for this). The Ministry of Health & Population, GoN will pay the co-financing amounts to UNICEF as per MoU.. f) Please outline how coverage of the new vaccine will be monitored and reported (refer to cMYP). The MoHP has established information management system (HMIS) for recording, reporting and monitoring of vaccination coverage. Immunization coverage, drop-out and wastage rate for all antigens are collected from peripheral level (Village Development Committees and municipalities) on monthly basis. The data after compilation at health facility level are sent to districts by all health facilities by 7th of every month using given HMIS format. The districts compile and analyze the data and send the data to HMIS section, DoHS and Regional Health Directorate by 15th of every month. HMIS section verifies and enters the data into the data base system. HMIS provides feedback to all divisions and districts every three months. The divisions at DoHS have direct access to HMIS raw data. Each divisions also provide feedback to districts on their programs. Each districts organize quarterly performance review meeting of all health facilities and analyze data below district level. The Management Division organizes annual regional and national performance review meetings and provides feedback to MoHP for annual planning. HMIS also carries out data verification exercise t all levels. The MD produces annual report every year..

8.2. Procurement and Management for NVS Preventive Campaign(s).

8.2.1. Procurement and Management for MR, 10 dose(s) per vial, LYOPHILISED campaign. a) Please show how the support will operate and be managed including procurement of vaccines (GAVI expects that countries will procure vaccine and injection supplies through UNICEF):. The government of Nepal has procured required MR vaccine for the campaign through its mechanism. UNICEF have supplied 173,000 vials (10 dose vial) to meet shortfall of the campaign.. b) Please indicate when you are planning to conduct the campaign (month and year) and how the campaign is going to be rolled out (e.g. in different phases or one time).. The MR campaign has been planned in 3 phases. First phase includes 15 districts with target population of 1,786,088. The first phase has been completed in March/April 2012. The second phase includes 25 districts with target population of 2,607,532. The second phase will be completed by 20 October 2012. The third phase includes 35 districts with target population of 5,564,577. The third phase will be completed by December 2012.. c) Please outline how coverage of the new vaccine will be monitored and reported (refer to the cMYP and/or the MR, 10 dose(s) per vial, LYOPHILISED campaign introduction plan). The coverage will reported by each districts to center. We are using SMS reporting system from each VDC and districts which could be seen in web by any person. Several international and national monitors will be used to monitor the campaign..

8.3. Vaccine Management (EVSM/EVM/VMA).

Did the country have Effective Vaccine Management Assessment (VMA) in the past? Yes. When was the last VMA conducted? August 2008. Did the country have Effective Vaccine Store Management (EVSM) in the past? Yes. When was the last EVSM conducted? September 2007. Did the country have Effective Vaccine Management (EVM) in the past? Yes. When was the EVM conducted? December 2011. If your country conducted either EVSM or VMA in the past two years, please attach relevant reports. (Document N°13). A VMA report must be attached from those countries which have introduced a New and Underused Vaccine with GAVI support before 2008.. Please note that Effective Vaccine Store Management (EVSM) and Vaccine Management Assessment(VMA) tools have been replaced by an integrated Effective Vaccine Management (EVM) tool. The information on EVM tool can be found at http://www.who.int/immunization_delivery/systems_policy/logistics/en/index6.html. For countries which conducted EVSM, VMA or EVM in the past, please report on activities carried out as part of either action plan or improvement plan prepared after the EVSM/VMA/EVM.. Improvement plan prepared after the EVM: 1. Take immediate action if a shipment arrives in the primary store in unsatisfactory condition 2. Should have satisfactory written contigency plan in place 3. Carry out a temperature monitoring study 4. Maintain complete temperature records for every freezer room, cold room, vaccine freezer 5. Install computerized 16 channel continuous temperature monitoring devices at national vaccine store 6. Keep storage capacity sufficient to accomodate maximum stock levels of routine vaccines 7. Identify major sources of risk 8. Procure one refrigerated vehicle 9. supply fire extinguishers to national and regional level stores 10. Provide storage space for syringes and safety boxes 11. All cold room fitted with sufficient good quality shelving 12. Phase out CFC free refrigeration 13. All RMS equipped with power adapter for cooling refrigerated truck 14. Establish preventative maintenance program 15. Internal reviews of the vaccine loss/damage records carried out at least twice a year 16. Carry out physical inventory of vaccaine and other supplies at least once in every 3 months 17. Good warehousing practices must be followed 18. Develop detail distribution plan 19. Implement MDVP correctly 20. Regular supportive supervision 21. EPI staff trained on vaccine management 22. vaccine wastage monitoring system in place 23. SOPs printed and distributed 24. Maintain accurate cold chain equipment and vehicle inventories 25. Maintain annual work plan to manage human and financial resource need 26. Refrigerator technicians trained in equipment maintenance 27. Cold chain assistant trained in equipment maintenance and 28. Fill vacant post in EPI. Does the country plan to conduct an Effective Vaccine Management (EVM) Assessment in the future? Yes. When is the next Effective Vaccine Management (EVM) Assessment planned? January 2014. Under new guidelines, it will be mandatory for the countries to conduct an EVM prior to an application for introduction of new vaccine..

9. Additional Comments and Recommendations from the National Coordinating Body (ICC/HSCC).

Comments and Recommendations from the National Coordinating Body (ICC/HSCC).

Nepalhas successfully introduced 3 new vaccines (HepB, Hib and JE) into routineimmunization since 2000. The children of Nepal have benefitted fromintroduction of new vaccine with reduction in mortality and morbidity fromthese diseases. This has contributed in achieving MDG goal 4. Nepal plans to introduce MR vaccine in 2013,pneumococcal in 2014 and others in future based on disease burden and financialimplication. Withintroduction of newer vaccines the ICC members have stressed on increasingcurrent routine coverage and maintain it. The introduction of new vaccineshould be taken as opportunity to advocate for strengthening RI. The ICC members welcomes the GAVI support for introduction of new and under used vaccines and would like to thank GAVI..

10. Attachments.

10.1. List of documents attached to this proposal.

Document Number; Document; Section; Mandatory; File. Secretary signature.pdf. 1; MoH Signature (or delegated authority) of Proposal; File desc:. Date/time: 8/31/2012 5:34:16 AM. Size: 556922. Secretary signature.pdf. 2; MoF Signature (or delegated authority) of Proposal; File desc:. Date/time: 8/31/2012 5:34:31 AM. Size: 556922. signature of ICC members 21-08-2012.pdf. 3; Signatures of ICC or HSCC or equivalent in Proposal; File desc:. Date/time: 8/29/2012 1:52:03 AM. Size: 239297. ICC meeting 21 August 2012.pdf. 4; Minutes of ICC/HSCC meeting endorsing Proposal; File desc:. Date/time: 8/29/2012 1:53:12 AM. Size: 626688. Nepal cMYP 2011-2016.pdf. 5; comprehensive Multi Year Plan - cMYP; File desc:. Date/time: 8/24/2012 5:20:50 AM. Size: 2130209. cMYP_Costing_Tool_May 25_Nepal.xls. 6; cMYP Costing tool for financial analysis; File desc:. Date/time: 8/27/2012 6:00:23 AM. Size: 3463168. Pneumococcal vaccine introduction plan.doc. 7; Plan for NVS introduction (if not part of cMYP); 5.1; File desc:. Date/time: 9/19/2012 1:45:02 AM. Size: 643072. EVM Improvement Plan, Nepal 2011.pdf. 8; Improvement plan based on EVM; File desc:. Date/time: 8/24/2012 5:21:32 AM. Size: 320823. MRl vaccine introduction plan.doc. 11; Evidence of introduction of RCV in routine programme; 7.c.3; File desc:. Date/time: 8/31/2012 5:35:54 AM. Size: 862720. MRl vaccine introduction plan.doc. 12; Plan Of Action for RCV introduction; 7.c.4; File desc:. Date/time: 8/31/2012 5:36:38 AM. Size: 862720.

11. Annexes... Annex 1 - NVS Routine Support

Annex 1.1 - NVS Routine Support (Pneumococcal (PCV13), 1 dose(s) per vial, LIQUID). Table Annex 1.1 A: Rounded up portion of supply that is procured by the country and estimate of relative costs in US$.. 2014; 2015; 2016. Number of vaccine doses; #; 136,800; 114,300; 116,600. Number of AD syringes; #; 0; 0; 0. Number of re-constitution syringes; #; 0; 0; 0. Number of safety boxes; #; 0; 0; 0. Total value to be co-financed by country; $; 507,500; 424,000; 433,000... Table Annex 1.1 B: Rounded up portion of supply that is procured by GAVI and estimate of relative costs in US$.. 2014; 2015; 2016. Number of vaccine doses; #; 2,400,400; 2,004,700; 2,046,200. Number of AD syringes; #; 2,709,000; 2,240,900; 2,287,000. Number of re-constitution syringes; #; 0; 0; 0. Number of safety boxes; #; 30,075; 24,875; 25,400. Total value to be co-financed by country; $; 9,044,500; 7,552,000; 7,708,500....

Table Annex 1.1 C: Summary table for vaccine Pneumococcal (PCV13), 1 dose(s) per vial, LIQUID. ID Data from; 2014; 2015; 2016. Number of surviving infants; Table 5.2; #; 664,177; 680,601; 696,603. Number of children to be vaccinated with the first dose; Table 5.2; #; 644,349; 666,989; 682,670. Number of children to be vaccinated with the third dose; Table 5.2; #; 611,135; 646,571; 661,772. Immunisation coverage with the third dose; Table 5.2; %; 92.00 %; 95.00 %; 95.00 %. Number of doses per child; Parameter; #; 3; 3; 3. Estimated vaccine wastage factor; Table 5.2; #; 1.05; 1.05; 1.05. Number of doses per vial; Parameter; #; 1; 1; 1. AD syringes required; Parameter; #; Yes; Yes; Yes. Reconstitution syringes required; Parameter; #; No; No; No. Safety boxes required; Parameter; #; Yes; Yes; Yes. g; Vaccine price per dose; Table Annexes 4A; $; 3.5; 3.5; 3.5. cc; Country co-financing per dose; Table 6.4.1; $; 0.2; 0.2; 0.2. ca; AD syringe price per unit; Table Annexes 4A; $; 0.0465; 0.0465; 0.0465. cr; Reconstitution syringe price per unit; Table Annexes 4A; $; 0; 0; 0. cs; Safety box price per unit; Table Annexes 4A; $; 0.0058; 0.0058; 0.0058. fv; Freight cost as % of vaccines value; Table Annexes 4B; %; 6.00 %; 6.00 %; 6.00 %. fd; Freight cost as % of devices value; Parameter; %; 10.00 %; 10.00 %; 10.00 %....

Table Annex 1.1 D: Estimated numbers for Pneumococcal (PCV13), 1 dose(s) per vial, LIQUID, associated injection safety material and related co-financing budget (page 1) Formula; 2014. Total; Government; GAVI. A; Country co-finance; 5.39 %. B; Number of children to be vaccinated with the first dose; Table 1; 644,349; 34,736; 609,613. C; Number of doses per child; Vaccine parameter (schedule); 3.00. D; Number of doses needed; B x C; 1,933,047; 104,208; 1,828,839. E; Estimated vaccine wastage factor; Wastage factor table; 1.05. F; Number of doses needed including wastage; D x E; 2,029,700; 109,418; 1,920,282. G; Vaccines buffer stock; (F – F of previous year) * 0.25; 507,425; 27,355; 480,070. I; Total vaccine doses needed; F + G; 2,537,125; 136,773; 2,400,352. J; Number of doses per vial; Vaccine parameter; 1.00. K; Number of AD syringes (+ 10% wastage) needed; (D + G) x 1.11; 2,708,924; 0; 2,708,924. L; Reconstitution syringes (+ 10% wastage) needed; I / J * 1.11; 0; 0; 0. M; Total of safety boxes (+ 10% of extra need) needed; (K + L) /100 * 1.11; 30,070; 0; 30,070. N; Cost of vaccines needed; I x g; 8,879,938; 478,703; 8,401,235. O; Cost of AD syringes needed; K x ca; 125,965; 0; 125,965. P; Cost of reconstitution syringes needed; L x cr; 0; 0; 0. Q; Cost of safety boxes needed; M x cs; 175.00; 0; 175. R; Freight cost for vaccines needed; N x fv; 532,797; 28,723; 504,074. S; Freight cost for devices needed; (O+P+Q) x fd; 12,614; 0; 12,614. T; Total fund needed; (N+O+P+Q+R+S); 9,551,489; 507,425; 9,044,064. U; Total country co-financing; I 3 cc; 507,425. V; Country co-financing % of GAVI supported proportion; U / T; 5.39 %... Table Annex 1.1 D: Estimated numbers for Pneumococcal (PCV13), 1 dose(s) per vial, LIQUID, associated injection safety material and related co-financing budget (page 2). Formula; 2015. Total; Government; GAVI. A; Country co-finance; 5.39 %. B; Number of children to be vaccinated with the first dose; Table 1; 666,989; 35,957; 631,032. C; Number of doses per child; Vaccine parameter (schedule); 3.00. D; Number of doses needed; B x C; 2,000,967; 107,869; 1,893,098. E; Estimated vaccine wastage factor; Wastage factor table; 1.05. F; Number of doses needed including wastage; D x E; 2,101,016; 113,263; 1,987,753. G; Vaccines buffer stock; (F – F of previous year) * 0.25; 17,829; 962; 16,867. I; Total vaccine doses needed; F + G; 2,118,845; 114,224; 2,004,621. J; Number of doses per vial; Vaccine parameter; 1.00. K; Number of AD syringes (+ 10% wastage) needed; (D + G) x 1.11; 2,240,864; 0; 2,240,864. L; Reconstitution syringes (+ 10% wastage) needed; I / J * 1.11; 0; 0; 0. M; Total of safety boxes (+ 10% of extra need) needed; (K + L) /100 * 1.11; 24,874; 0; 24,874. N; Cost of vaccines needed; I x g; 7,415,958; 399,783; 7,016,175. O; Cost of AD syringes needed; K x ca; 104,201; 0; 104,201. P; Cost of reconstitution syringes needed; L x cr; 0; 0; 0. Q; Cost of safety boxes needed; M x cs; 145.00; 0; 145. R; Freight cost for vaccines needed; N x fv; 444,958; 23,987; 420,971. S; Freight cost for devices needed; (O+P+Q) x fd; 10,435; 0; 10,435. T; Total fund needed; (N+O+P+Q+R+S); 7,975,697; 423,769; 7,551,928. U; Total country co-financing; I 3 cc; 423,769. V; Country co-financing % of GAVI supported proportion; U / T; 5.39 %... Table Annex 1.1 D: Estimated numbers for Pneumococcal (PCV13), 1 dose(s) per vial, LIQUID, associated injection safety material and related co-financing budget (page 3). Formula; 2016. Total; Government; GAVI. A; Country co-finance; 5.39 %. B; Number of children to be vaccinated with the first dose; Table 1; 682,670; 36,802; 645,868. C; Number of doses per child; Vaccine parameter (schedule); 3.00. D; Number of doses needed; B x C; 2,048,010; 110,405; 1,937,605. E; Estimated vaccine wastage factor; Wastage factor table; 1.05. F; Number of doses needed including wastage; D x E; 2,150,411; 115,926; 2,034,485. G; Vaccines buffer stock; (F – F of previous year) * 0.25; 12,349; 666; 11,683. I; Total vaccine doses needed; F + G; 2,162,760; 116,591; 2,046,169. J; Number of doses per vial; Vaccine parameter; 1.00. K; Number of AD syringes (+ 10% wastage) needed; (D + G) x 1.11; 2,286,999; 0; 2,286,999. L; Reconstitution syringes (+ 10% wastage) needed; I / J * 1.11; 0; 0; 0. M; Total of safety boxes (+ 10% of extra need) needed; (K + L) /100 * 1.11; 25,386; 0; 25,386. N; Cost of vaccines needed; I x g; 7,569,660; 408,068; 7,161,592. O; Cost of AD syringes needed; K x ca; 106,346; 0; 106,346. P; Cost of reconstitution syringes needed; L x cr; 0; 0; 0. Q; Cost of safety boxes needed; M x cs; 148.00; 0; 148. R; Freight cost for vaccines needed; N x fv; 454,180; 24,485; 429,695. S; Freight cost for devices needed; (O+P+Q) x fd; 10,650; 0; 10,650. T; Total fund needed; (N+O+P+Q+R+S); 8,140,984; 432,552; 7,708,432. U; Total country co-financing; I 3 cc; 432,552. V; Country co-financing % of GAVI supported proportion; U / T; 5.39 %......

Annex 2 - NVS Routine – Preferred Second Presentation.

No NVS Routine – Preferred Second Presentation requested this year.

Annex 3 - NVS Preventive campaign(s)... Annex 3.1 - NVS Preventive campaign(s) (MR, 10 dose(s) per vial, LYOPHILISED). Table Annex 3.1 C: Summary table for CAMPAIGN MR, 10 dose(s) per vial, LYOPHILISED.. Data from; 2013. Total campaign population; Table 5.3.1; #; 0. Immunization coverage; Table 5.3.1; %; 0. Number of persons to be vaccinated; Table 5.3.1; #; 0. Number of doses per persons; Parameter; #; 1. Estimated vaccine wastage factor; Table 5.3.1; #; 1. Number of doses per vial; Parameter; #; 10. AD syringes required; Parameter; #; Yes. Reconstitution syringes required; Parameter; #; Yes. Safety boxes required; Parameter; #; Yes. Vaccine price per dose; Table Annexes 4A; $; 0.494. AD syringe price per unit; Table Annexes 4A; $; 0.0465. Reconstitution syringe price per unit; Table Annexes 4A; $; 0.0037. Safety box price per unit; Table Annexes 4A; $; 0.0058. Freight cost as % of vaccines value; Table Annexes 4B; %; 13.00 %. Freight cost as % of devices value; Parameter; %; 0...

Table Annex 3.1 D: Estimated number of MR, 10 dose(s) per vial, LYOPHILISED associated injection safety material and related co-financing budget (page 1). Formula; GAVI. 2013. B; Number of persons to be vaccinated with the first dose; 0. C; Number of doses per persons; 1. D; Number of doses needed; B x C; 0. E; Estimated vaccine wastage factor; Wastage factor table; 1. F; Number of doses needed including wastage; D x E; 0. G; Vaccines buffer stock; (F – F of previous year) * 0.25; 0. I; Total vaccine doses needed; F + G; 0. J; Number of doses per vial; Vaccine parameter; 10. K; Number of AD syringes (+ 10% wastage) needed; (D + G) x 1.11; 0. L; Reconstitution syringes (+ 10% wastage) needed; I / J * 1.11; 0. M; Total of safety boxes (+ 10% of extra need) needed; (K + L) /100 * 1.11; 0. N; Cost of vaccines needed; I x g; 0.494. O; Cost of AD syringes needed; K x ca; 0. P; Cost of reconstitution syringes needed; L x cr; 0. Q; Cost of safety boxes needed; M x cs; 0. R; Freight cost for vaccines needed; N x fv; 0. S; Freight cost for devices needed; (O+P+Q) x fd; 0. T; Total fund needed; (N+O+P+Q+R+S); 0... Note: There is no cofinancing for NVS preventive campaigns...

| Annex 4. |  |  |
| --- | --- | --- |
| Table Annex 4A: Commodities Cost. |  |  |
| Vaccine; Presentation; 2013; 2014; 2015; 2016. DTP-HepB, 10 dose(s) per vial, LIQUID; 10. DTP-HepB-Hib, 1 dose(s) per vial, LIQUID; 1; 2.017; 1.986; 1.933; 1.927. DTP-HepB-Hib, 10 dose(s) per vial, LIQUID; 10; 2.017; 1.986; 1.933; 1.927. DTP-HepB-Hib, 2 dose(s) per vial, LYOPHILISED; 2; 2.017; 1.986; 1.933; 1.927. HPV bivalent, 2 dose(s) per vial, LIQUID; 2; 5.000; 5.000; 5.000; 5.000. HPV quadrivalent, 1 dose(s) per vial, LIQUID; 1; 5.000; 5.000; 5.000; 5.000. Measles, 10 dose(s) per vial, LYOPHILISED; 10; 0.242; 0.242; 0.242; 0.242. Meningogoccal, 10 dose(s) per vial, LIQUID; 10; 0.520; 0.520; 0.520; 0.520. MR, 10 dose(s) per vial, LYOPHILISED; 10; 0.494; 0.494; 0.494; 0.494. Pneumococcal (PCV10), 2 dose(s) per vial, LIQUID; 2; 3.500; 3.500; 3.500; 3.500. Pneumococcal (PCV13), 1 dose(s) per vial, LIQUID; 1; 3.500; 3.500; 3.500; 3.500. Rotavirus, 2-dose schedule; 1; 2.550; 2.550; 2.550; 2.550. Rotavirus, 3-dose schedule; 1; 3.500; 3.500; 3.500; 3.500. Yellow Fever, 10 dose(s) per vial, LYOPHILISED; 10; 0.900; 0.900; 0.900; 0.900. Yellow Fever, 5 dose(s) per vial, LYOPHILISED; 5; 0.900; 0.900; 0.900; 0.900. |  |  |
| Note for HPV and MR: These prices are indicative only as GAVI has not procured HPV and MR vaccines for GAVI countries yet. Prices will be finalised through tender processes in Q3. GAVI will only fund HPV vaccines if an acceptable price reduction is secured from the current price indicated. The MR price is based on the current price to UNICEF. |  |  |
| Supply; Form; 2013; 2014; 2015; 2016. AD-SYRINGE; SYRINGE; 0.047; 0.047; 0.047; 0.047. RECONSTIT-SYRINGE-PENTAVAL; SYRINGE; 0.047; 0.047; 0.047; 0.047. RECONSTIT-SYRINGE-YF; SYRINGE; 0.004; 0.004; 0.004; 0.004. SAFETY-BOX; SAFETYBOX; 0.006; 0.006; 0.006; 0.006. |  |  |
| Note: WAP - weighted average price (to be used for any presentation: For DTP-HepB-Hib, it applies to 1 dose liquid, 2 dose lyophilised and 10 dose liquid. For Yellow Fever, it applies to 5 dose lyophilised and 10 dose lyophilised). |  |  |
| Table Annex 4B: Freight cost as percentage of value. |  |  |
| Vaccine Antigen; Vaccine Type; No Threshold; 500,000$. <=; >. DTP-HepB; HEPBHIB; 2.00 %. DTP-HepB-Hib; HEPBHIB; 23.80 %; 6.00 %. HPV bivalent; HPV; 3.50 %. HPV quadrivalent; HPV; 3.50 %. Measles; MEASLES; 14.00 %. Meningogoccal; MENINACONJUGATE; 10.20 %. MR; MR; 13.20 %. Pneumococcal (PCV10); PNEUMO; 3.00 %. Pneumococcal (PCV13); PNEUMO; 6.00 %. Rotavirus; ROTA; 5.00 %. Yellow Fever; YF; 7.80 %. |  |  |
| Table Annex 4C: Low - Minimum country's co-payment per dose of co-financed vaccine.. |  |  |
| Vaccine; 2014; 2015; 2016. Pneumococcal (PCV13), 1 dose(s) per vial, LIQUID; 0.2; 0.2; 0.2. |  |  |
| Table Annex 4D: Wastage rates and factors. |  |  |
| Countries are expected to plan for a maximal wastage rate of:. |  |  |
| • 50% - for a lyophilised vaccine in 10 or 20-dose vial,. |  |  |
| • 25% - for a liquid vaccine in 10 or 20-dose vial or a lyophilised vaccine in 5-dose vial,. |  |  |
| • 10% - for a lyophilised/liquid vaccine in 2-dose vial, and. |  |  |
| • 5% - for a liquid vaccine in 1-dose vial. |  |  |
| Vaccine wastage rate; 5%; 10%; 15%; 20%; 25%; 30%; 35%; 40%; 45%; 50%; 55%; 60%. Equivalent wastage factor; 1.05; 1.11; 1.18; 1.25; 1.33; 1.43; 1.54; 1.67; 1.82; 2; 2.22; 2.5. |  |  |
| Vaccine; Vaccine wastage rate; VaccineWastageFactor. MR, 10 dose(s) per vial, LYOPHILISED; 15%; 1.18. |  |  |
| Table Annex 4E: Vaccine maximum packed volumes. |  |  |
| Vaccine product; Designation; Vaccine formulation; Admin route; No. Of doses in the schedule; Presentation (doses/vial, prefilled); Packed volume vaccine (cm3/dose); Packed volume diluents (cm3/dose). BCG; BCG; lyophilized; ID; 1; 20; 1.2; 0.7. Diphtheria-Tetanus-Pertussis; DTP; liquid; IM; 3; 20; 2.5. Diphtheria-Tetanus-Pertussis; DTP; liquid; IM; 3; 10; 3. Diphtheria-Tetanus; DT; liquid; IM; 3; 10; 3. Tetanus-Diphtheria; Td; liquid; IM; 2; 10; 3. Tetanus Toxoid; TT; liquid; IM; 2; 10; 3. Tetanus Toxoid; TT; liquid; IM; 2; 20; 2.5. Tetanus Toxoid UniJect; TT; liquid; IM; 2; Uniject; 12. Measles; Measles; lyophilized; SC; 1; 1; 26.1; 20. Measles; Measles; lyophilized; SC; 1; 2; 13.1; 13.1. Measles; Measles; lyophilized; SC; 1; 5; 5.2; 7. Measles; Measles; lyophilized; SC; 1; 10; 3.5; 4. Measles-Rubella freeze dried; MR; lyophilized; SC; 1; 1; 26.1; 26.1. Measles-Rubella freeze dried; MR; lyophilized; SC; 1; 2; 13.1; 13.1. Measles-Rubella freeze dried; MR; lyophilized; SC; 1; 5; 5.2; 7. Measles-Rubella freeze dried; MR; lyophilized; SC; 1; 10; 2.5; 4. Measles-Mumps-Rubella freeze dried; MMR; lyophilized; SC; 1; 1; 26.1; 26.1. Measles-Mumps-Rubella freeze dried; MMR; lyophilized; SC; 1; 2; 13.1; 13.1. Measles-Mumps-Rubella freeze dried; MMR; lyophilized; SC; 1; 5; 5.2; 7. Measles-Mumps-Rubella freeze dried; MMR; lyophilized; SC; 1; 10; 3; 4. Polio; OPV; liquid; Oral; 4; 10; 2. Polio; OPV; liquid; Oral; 4; 20; 1. Yellow fever; YF; lyophilized; SC; 1; 5; 6.5; 7. Yellow fever; YF; lyophilized; SC; 1; 10; 2.5; 3. Yellow fever; YF; lyophilized; SC; 1; 20; 1.5; 2. Yellow fever; YF; lyophilized; SC; 1; 50; 0.7; 1. DTP-HepB combined; DTP-HepB; liquid; IM; 3; 1; 9.7. DTP-HepB combined; DTP-HepB; liquid; IM; 3; 2; 6. DTP-HepB combined; DTP-HepB; liquid; IM; 3; 10; 3. Hepatitis B; HepB; liquid; IM; 3; 1; 18. Hepatitis B; HepB; liquid; IM; 3; 2; 13. Hepatitis B; HepB; liquid; IM; 3; 6; 4.5. Hepatitis B; HepB; liquid; IM; 3; 10; 4. Hepatitis B UniJect; HepB; liquid; IM; 3; Uniject; 12. Hib liquid; Hib_liq; liquid; IM; 3; 1; 15. Hib liquid; Hib_liq; liquid; IM; 3; 10; 2.5. Hib freeze-dried; Hib_lyo; lyophilized; IM; 3; 1; 13; 35. Hib freeze-dried; Hib_lyo; lyophilized; IM; 3; 2; 6. Hib freeze-dried; Hib_lyo; lyophilized; IM; 3; 10; 2.5; 3. DTP liquid + Hib freeze-dried; DTP+Hib; liquid+lyop.; IM; 3; 1; 45. DTP-Hib combined liquid; DTP+Hib; liquid+lyop.; IM; 3; 10; 12. DTP-Hib combined liquid; DTP-Hib; liquid; IM; 3; 1; 32.3. DTP-HepB liquid + Hib freeze-dried; DTP-Hib; liquid; IM; 3; 10; 2.5. DTP-HepB liquid + Hib freeze-dried; DTP-HepB+Hib; liquid+lyop.; IM; 3; 1; 22. DTP-HepB-Hib liquid; DTP-HepB+Hib; liquid+lyop.; IM; 3; 2; 11. DTP-HepB-Hib liquid; DTP-HepB-Hib; liquid; IM; 3; 10; 4.4. DTP-HepB-Hib liquid; DTP-HepB-Hib; liquid; IM; 3; 2; 13.1. DTP-HepB-Hib liquid; DTP-HepB-Hib; liquid; IM; 3; 1; 19.2. Meningitis A/C; MV_A/C; lyophilized; SC; 1; 10; 2.5; 4. Meningitis A/C; MV_A/C; lyophilized; SC; 1; 50; 1.5; 3. Meningococcal A/C/W/; MV_A/C/W; lyophilized; SC; 1; 50; 1.5; 3. Meningococcal A/C/W/Y; MV_A/C/W/Y; lyophilized; SC; 1; 10; 2.5; 4. Meningitis W135; MV_W135; lyophilized; SC; 1; 10; 2.5; 4. Meningitis A conjugate; Men_A; lyophilized; SC; 2; 10; 2.6; 4. Japanese Encephalitis; JE_lyo; lyophilized; SC; 3; 10; 15. Japanese Encephalitis; JE_lyo; lyophilized; SC; 3; 10; 8.1; 8.1. Japanese Encephalitis; JE_lyo; lyophilized; SC; 3; 5; 2.5; 2.9. Japanese Encephalitis; JE_lyo; lyophilized; SC; 3; 1; 12.6; 11.5. Japanese Encephalitis; JE_liq; liquid; SC; 3; 10; 3.4. Rota vaccine; Rota_lyo; lyophilized; Oral; 2; 1; 156. Rota vaccine; Rota_liq; liquid; Oral; 2; 1; 17.1. Rota vaccine; Rota_liq; liquid; Oral; 3; 1; 45.9. Pneumo. conjugate vaccine 7-valent; PCV-7; liquid; IM; 3; PFS; 55.9. Pneumo. conjugate vaccine 7-valent; PCV-7; liquid; IM; 3; 1; 21. Pneumo. conjugate vaccine 10-valent; PCV-10; liquid; IM; 3; 1; 11.5. Pneumo. conjugate vaccine 10-valent; PCV-10; liquid; IM; 3; 2; 4.8. Pneumo. conjugate vaccine 13-valent; PCV-13; liquid; IM; 3; 1; 12. Polio inactivated; IPV; liquid; IM; 3; PFS; 107.4. Polio inactivated; IPV; liquid; IM; 3; 10; 2.5. Polio inactivated; IPV; liquid; IM; 3; 1; 15.7. Human Papilomavirus vaccine; HPV; liquid; IM; 3; 1; 15. Human Papilomavirus vaccine; HPV; liquid; IM; 3; 2; 5.7. Monovalent OPV-1; mOPV1; liquid; Oral; 20; 1.5. Monovalent OPV-3; mOPV3; liquid; Oral; 20; 1.5. |  |  |

| 12. Banking Form |  |
| --- | --- |
| In accordance with the decision on financial support made by the GAVI Alliance, the Government of Nepal hereby requests that a payment be made via electronic bank transfer as detailed below:. Name of Institution (Account Holder):; Financial Comptroller General Office. Address:; Government of Nepal, Financial Comptroller General Office. City Country:; Anam nagar, Kathmandu, Nepal. Telephone no.:; 00-977-4414325; Fax no.:; 00-977-4414651. Currency of the bank account:; US $. For credit to:. Bank account's title:; Foreign Aid Account. Bank account no.:; Ka-7-13. Bank's name:; Nepal Rastra bank, Banking Office, Kathmandu. |  |
| Is the bank account exclusively to be used by this program? False. |  |
| By who is the account audited? Auditor General Office. |  |
| Signature of Government's authorizing official. |  |
| Seal. Name:; Dr Praveen Mishra. Title:; Secretary, Ministry of Health & Population. Signature:. Date:; 29/08/2012. |  |
| FINANCIAL INSTITUTION. Bank Name:; Nepal Rastra Bank. Branch Name:; Banking Office. Address:; Thapathali. City Country:; Kathmandu, Nepal. Swift Code:; NRBLNPKA. Sort Code:; e-mail: nrbkso@nytc.net.np. ABA No.:. Telephone No.:; 00-977-4226832. FAX No.:; 00-977-4227378. | CORRESPONDENT BANK. (In the United States). City Bank. New York, USA. American Express Bank. New York, USA. |
| I certify that the account No KA-7-13 is held by Financial Comptroller General Office at this banking institution. The account is to be signed jointly by at least 2 (number of signatories) of the following authorized signatories:. 1; Name:; Mr Tej Bahadur KC. Title:; Deputy Financial Comptroller General. 2; Name:; Mr Yadu Nath Bhattarai. Title:; Accounts Officer. 3; Name:; Ms Binu Khatiwada/Mr Nabin Shrestha. Title:; Accounts Officer/Accountant. |  |
| Name of bank's authorizing official. Mr Hari Prasad Kaphle. Signature:. Date:; 8/31/2012 12:00:00 AM. Seal:. |  |