REPUBLIC OF INDONESIA

MINISTRY OF HEALTH

EXPANDED PROGRAM ON IMMUNIZATION

EPI

Hib CONTAINING PENTAVALENT VACCINE INTRODUCTION and FINANCIAL SUSTAINABILITY PLAN

November 2011

# Table of Contents

Table of Contents	2

Acronyms	3

Executive summary	4

I. Introduction	7

II. Context	8

2.1. 	Geopolitical and background information	8

2.2. 	Health System Organization	10

2.3. 	Situation Analysis of current EPI	12

2.4  	Plans, goals and targets of EPI, Indonesia	14

2.5. 	The Inter-Agency Coordinating Committee for Immunisation and Health System Coordination Committee (ICC/HSCC)	15

2.6. 	Indonesian Technical Advisory Group on Immunization (ITAGI)	15

2.7. 	Current EPI performances	16

2.8. 	Intensification Routine Immunization in Indonesia	18

2.9. 	Vaccine forecast, procurement and management	19

2.10. 	Storage Capacity and Accommodation of Hib-pentavalent Vaccine	20

III. 	Indonesian Experience in New Vaccine Introduction	21

IV. 	Goal and Objectives for Hib-pentavalent Vaccine Introduction	22

4.1. 	Goal	22

4.2. 	Specific objectives	22

V. 	Epidemiology and Burden of Haemophilias Influenzae type b	22

VI. 	Decision making and choice of Hib-pentavalent vaccine to be introduced	24

6.1. 	Choice of the vaccine	24

6.2. 	Introduction approach	25

VII. 	Strategies	27

7.1.	Improvement of Service Delivery	27

7.2.	Reinforce monitoring and evaluation	28

7.3. 	Reinforcement of the staff capacity	28

7.4.	Reinforcement of cold chain storage capacity	29

7.5.	Reinforcement of communication and social mobilization	29

7.6.	Reinforcement of epidemiological surveillance and of the AEFI	30

7.7. 	Improvement of vaccine supply and management	31

7.8.	Reinforcement of collaboration, coordination and partnership	32

7.9.	 Financial sustainability	32

VIII. 	Plan  activity and budget  for Hib-pentavalent  Vaccine Introduction Indonesia, 2012 - 2017	41

# Acronyms

AEFI		:	Adverse event following immunization

BCG		:	Bacille de Calmette et Guérin

CC		:	Cold chain

cMYP		:	comprehensive Multi-Year Plan

DTP		:	Vaccine: Diphtheria, Tetanus and Pertussis

EPI		:	Expanded Program on Immunization

GAVI	: 	Global Alliance for Vaccine and Immunization

GIVS		:	Global Immunization Vision and Strategies

ICC		:	Inter agency Coordinating Committee

IMR		:	Infant Mortality Rate

Hib		: 	Haemophilias  Influenzae type b vaccine

HB 		: 	Hepatitis B vaccine

MDVP		:	Multi Dose Vial Policy

OPV		:	Oral polio vaccine

STP		:	Surveillance Terpadu Penyakit

PIE		:	Post Introduction Evaluation

TT		:	Tetanus toxoide vaccine

UNICEF	:	United Nations Children’s Fund

WHA		:	World Health Assembly

WHO		:	World Health Organization

VVM		:	Vaccine Vial Monitor

# Executive summary

World Health Assembly (WHA), in 2005, adopted the « Global Immunization Vision and Strategies » (GIVS) which targeted a global objective for 2010: “Each country should reach the immunization coverage of, at least, 90% nationwide and of 80% in all health districts or administrative entities”. For 2015, GIVS recommends that countries maintain the coverage reached in 2010. This objective will contribute to meet the Millennium Objective of the Development, especially for its objective 4 which targets the reduction of the 2/3 of infant mortality among the under five infants by 2015.

The Ministry of Health of Indonesia approved and aligned itself to this global perspective. The National Immunization Program, which wants to contribute in the process of achieving this objective, has already introduced, since 1997, two new vaccines, Hepatitis B vaccine as a birth dose and  DTP-HB vaccine (tetravalent vaccine), in 2004. In addition to new vaccine introduction strategies, the country was involved in integrating immunization approaches to increase and maintain vaccination coverage for all antigens.

The current “Hib-Pentavalent vaccine introduction plan” analyzes the current situation of immunization program in the country, its goals and objectives, identifies introduction strategies and key activities for a smooth introduction of Hib-Pentavalent vaccine. For this reason, a comprehensive cold chain analysis and of the other programmatic aspects of immunization services will be conducted and recommendations being under implementation. The development of this plan referred to most information from the following documents:

- Comprehensive multi-year plan (cMYP) for immunization 2010 – 2014

- National medium term plan on health, Indonesia 2010 - 2014

- Cold chain inventory report conducted in 2008 with updated procurement in 2010

- EVM assessment and temperature monitoring report, 2011

- WHO–UNICEF JRF & SEARO Annual Report on EPI 2010

- National Immunization Coverage Survey report, April 2007

In order to contribute to the objective of Hib invasive bacterial disease control, the national EPI has developed strategies which will allow the resolution of the key problems observed during the previous new vaccine post introduction evaluations and other immunization related assessments:

HB birth dose

- Accidental freezing of vaccine at sub national level

- Low awareness of the mothers lead to refusal of HepB birth-dose to some newborns

- Health personnel sometimes reluctant and worried to vaccinate the newborn.

- All health facilities ate not providing HB birth-dose

DTP-HB

- Cold chain capacity is inadequate at some new districts and some health centres

- Due to inadequate social mobilization, awareness on DTP-HB vaccine is limited among both among health personal and parents

Based on the lessons learned and recommendations made Ministry of Health, Indonesia is being implementing following activities to rectify the same:

- Using of freeze tags, training the staff on cold chain, vaccine management and improved supportive supervision to monitor cold chain maintenance at district and health centre level.

- Planned replacement cold chain equipment at district and health centre level with procurement of  additional cold chain equipments and spare parts

- Removal of freezers from cold chain in health centre and used of cool packs instead of ice packs.

- Improve awareness on new vaccines and their benefits through health promotion,  social mobilization and refresher training for health workers including in the private clinics

- Integration of  EPI with MCH program to include HepB Birth dose vaccine (UNIJECT) to delivery kit along with Vitamin K1 to improve the coverage

- Strengthen HSS and Support Civil Society Organization activities in week areas

# I. Introduction

Indonesia, through its Expanded Program on Immunization (EPI), has a goal, the one to contribute to a better child survival by reducing the morbidity and the mortality due to immunization preventable diseases.

The Government of Indonesia already contributes, with payment of all routine immunization activity costs. In fact, today, all the traditional vaccines including new vaccines; HB birth dose and DTP-HB, are being fully financed by the Government with the technical support from WHO and UNICEF. Introduction of HB vaccine birth dose was co-financed by the Government of Indonesia with GAVI Alliance support from 2002 to 2006.

The Haemophilias Influenza type b (Hib) and related invasive bacterial diseases are one of the main causes of morbidity and mortality in all regions. According to the WHO estimates, about 1.8 million of children < 5 years die each year due to Hib and related invasive bacterial diseases.

For this reason, WHO recommends the introduction of Hib vaccine in all national immunization programs in all regions, especially where immunization with Hib vaccine can have a potential public health impact and where appropriate infrastructures and financing mechanisms are available to sustain the use of this vaccine.

Given the prevalence and the severity of Hib diseases in the country and the WHO recommendation which encourages all national EPI programs in all regions to introduce the Hib vaccine, the Government of Indonesia has decided in consultation with Indonesian Technical Advisory Group on Immunization (ITAGI) and technical partners, to take the opportunity of the availability of this life-saving vaccine and introduce it in its routine immunization program to protect the children < 1 year of age.

In this context, ministry of health of Indonesia in consultation with its technical and developmental partners, requests financial and technical assistance from Global Alliance for Vaccines and Immunization (GAVI Alliance) to introduce Hib-Pentavalent vaccine to Indonesian Immunization programme. If this proposal is accepted, EPI will use its previous experience in new vaccine introductions to maximize the likelihood of a smooth introduction, protect high proportion of infants and improve child survival in Indonesia.

This plan will identify factors which would interfere and compromise the successful introduction of Hib-pentavalent vaccine in Indonesia. Further, it includes objectives, strategies, and priority activities which will be implemented with time line for Hib-Pentavalent vaccine introduction.

# II. Context

### 2.1. 	Geopolitical and background information

Administratively, Indonesia is divided into 33 provinces including the capital province Jakarta, 497 districts and 8.742 villages. The smallest administrative unit is the villages.

The last demographic census was conducted in 2010, estimated the total population of Indonesia is about 230 million inhabitants.

|  | Figure | Year |
| --- | --- | --- |
| Total population* | 237,641,326 | 2010 |
| Infant mortality rate (per 1000)* | 29.9/1000 | 2010 |
| Surviving Infants* | 4,455,081 | 2010 |
| GNI per capita (US$)** | US$ 1,033 | 2010 |
| Percentage of GDP allocated to Health*** | 2.36% | 2009 |
| Percentage of Government expenditure on Health*** | 6,86% | 2009 |

Source: * Center Statistic Bodies

** WB National accounts data

***www.who.int/nba/en

The Government of Indonesia strongly supports the activities of immunization program and currently it has become a government's priority program as it has been addressed in the following laws, regulations and directives:

- Law  No. 36/2009 on Health.

- Law No. 23 year 2002 on Child Protection, children have right to obtain health service including Immunization.

- Law No. 12 year 2008 about revision of Law No. 32/2004 on Governance at local level.

- Law No. 33/2004 about Fiscal Balance between Central and Local Government.

- PP RI NO.38 year 2007 about sharing of the Governmental Affairs between the Central, Provincial and District/Municipality Government.

- Inpres no.1 year 2010 on Acceleration of National Development Priorities 2010.

- Inpres no.3 year 2010 about Development Program with Justice.

- Ministry decree No. 1611/SK/IX/2005 about Guidelines of Immunization Implementation.

- Ministry decree 741/MENKES/PER/VII/2008  Minimum Service Standard of Health in District/Municipality.

- Ministry decree NO. 828/MENKES/SK/IX/2008  Technical Guidelines for the Health Sector Minimum Service Standards in District/Municipal.

- Ministry decree HK.03.01/60.I/2010 Strategic Plan of MoH including EPI National Action Plan 2010 – 2014.

Decentralization and political reforms instituted in the late 1990s has affected to a some extent, the sustainability and availability of funding for immunization at provincial and district levels. Provincial and District governments are now responsible for the planning and implementation of their immunization programs. However the central level is responsible for the development of national policies and guidelines, procurement and supply of vaccines and syringes, technical support by training of trainers, monitoring, evaluation and quality control. Further center is responsible for the supplementary immunization activities as well.

To achieve high coverage to be sustained, EPI should have strong commitment to provide well and closer services to community. Therefore, to establish stronger and more representative civil society constituency for immunization and to minimize the bottlenecks and barriers in deferent levels, with the support from donors EPI program Indonesia maintain very close relationship with many religious and civil society organizations to help the MOH to overcome these issues.

### 2.2. 	Health System Organization

There are 33 provinces in Indonesia and each province is sub-divided into districts or municipalities and each district/municipality into sub-districts. As decentralization had been already implemented, the 497 districts/ municipalities is now the key of administrative units.

Each sub-district in Indonesia has at least one health centre headed by a medical doctor or public health, usually supported by two or three sub-centres, the majority of which are headed by nurses. Health centres mainly provide eight primary health care services including immunization.

Most of the health centres are equipped with four-wheel drive vehicles or motorboats to serve as mobile health units and provide services to underserved populations in urban and remote rural areas.

At the village level, the integrated Post (Posyandu) provides health preventive and promotion services. These health posts are established and managed by the community with the assistance of health center staff. To improve maternal and child health, midwives are being deployed to the villages.

A Decentralized governance policy is being implemented in Indonesia since 1999, with the ratification of Act No. 22/1999 regarding Regional Governance and Act No. 25/1999 regarding the financial equality between Central and Regional government. With the implementation of the aforementioned Acts, the system of governance in Indonesia has been changed from centralized to decentralized type of governance, which provide regional autonomy.  In the Act No. 22/1999, there have been three levels of regional autonomy, i.e., Province, District, and City regional autonomy.

MOH Level from Central to peripheral level

Kementerian Kesehatan (Kemkes)

Ministry of Health

Central Level

Dinas Kesehatan Provinsi (Dinkes)

(Provincial Health Office)

Provincial Level

Dinas Kesehatan Kabupaten/Kota (Dinkes)

(District Health Office)

District Level

Pusat Kesehatan Masyarakat (PUSKESMAS) tingkat Kecamatan

(Sub District Level Health Center)

Sub District Level

PUSKESMAS Pembantu (PUSTU)                    Pondok Bersalin Desa (POLINDES)

Sub Health Center                                     Village Midwife Clinic

Pos Pelayanan Terpadu (POSYANDU)

Integrated Health Post

coordination line

COMMAND LINE

Institutional arrangement and organization of the EPI has been established for each administrative levels from central until health center level and a responsible person is assigned in each level. Number of infrastructure and personnel are as follow:

- Health Center or Puskesmas (9,134) / Hospital (1.378)

  - Vaccinator (Midwife/Nurses)

  - Cold chain/Logistics Manager

  - Supervised by Head of Puskesmas

- District Health Office (497)

  - District EPI (Expanded Program for Immunization) Manager

  - Cold chain/Logistics Manager

  - Supervised by District EPI Manager

- Provincial Health Office (33)

  - Provincial EPI Manager

  - Cold chain/Logistics Manager

  - Supervised by Provincial EPI Manager

- Central (SubDirectorate of EPI, CDC MOH)

  - Head of SubDirectorate, 2 sections/ unit and a number of staffs

  - Cold chain/Logistics Manager

### 2.3. 	Situation Analysis of current EPI

The government of Indonesia (GOI) has a strong commitment to immunization as a priority public health intervention. The immunization program has been selected as one of the priority services in line with the global commitments as well as the national requirements. Expanded program on Immunization (EPI) in Indonesia was commenced  in 1977 and have had a good record of achievements.

The goal of EPI in Indonesia to reduce morbidity and mortality due to vaccine preventable diseases in line with global eradication, elimination or reduction commitments. With over 230 million people, Indonesia annually has to immunize more than 4 million children surviving to the age of one year. The vaccines against seven diseases currently administered through national program. Those vaccines are BCG, DTP, Polio, Measles and Hepatitis B and schedule it provided through EPI given below.

Table 1: Immunisation Schedule, Indonesia, 2011

| Age of administration | Vaccine |
| --- | --- |
| Less than 7 days | Hep B 0 (Birth dose) |
| 1st month | BCG and Polio 1 |
| 2nd month | DTP-Hep B 1 and Polio 2 |
| 3rd month | DTP-Hep B 2 and Polio 3 |
| 4th month | DTP-Hep B 3 and Polio 4 |
| 9th month | Measles 1st Dose |
| School children 1st grade | DT and Measles 2nd Dose |
| School children 2nd grade | Td |
| School children 3rd grade | Td |

In addition to program for infants less than one year, routinely measles, DT and Td vaccines are provided for school children through school immunization program called BIAS (Bulan Imunisasi Anak Sekolah or School Based Immunization). The target is children in first to third grade who receive vaccination in their schools. The purpose school immunization program is to provide 2nd opportunity against measles and boost immunity against  Diphtheria and Tetanus into later adulthood.

Indonesian EPI has also adopted Maternal and Neonatal Tetanus Elimination (MNTE) initiatives and Measles reduction activities in line with global initiatives. Accordingly GOI is being promoting various strategic special immunization activities, including TT SIAs, Polio NIDs, Measles catch-up campaigns and follow-up campaigns to scale up the process of reducing the number of susceptible and cases or even to eliminate them.

### 2.4  	Plans, goals and targets of EPI, Indonesia

The Immunization Program, Indonesia envisage to achieve following goals and targets

- To achieve UCI village 80% in 2010 and 100% by the end of 2014

- To achieve 80% or more of HepB Birth dose coverage  by 2014

- To achieve coverage of Measles 1st opportunity at 9 months over 95% by 2015

- To maintain the use of AD syringes 100%

- To develop and implement national policy on waste management

- To introduce new vaccines (Hib, JE and Pneumococcal vaccines)

As planned in the current cMYP (2009-2014), the EPI, Indonesia is expected introduce Hib-pentavalent vaccine to EPI in on phase basis from 2013 with financial support from GAVI  NVI. This plan has also been incorporated in the RPJMN (Medium Term Development Plan of the Ministry of Health) as well as in the Strategic Plan of the Ministry of Health.

Plans and resources allocation to achieve service delivery objectives has been incorporated into the current cMYP. They include reaching the UCI target in 100% villages in 2014 (based on national actions on Immunization acceleration which is called GAIN UCI or Gerakan Akselerasi Imunisasi Nasional); advocacy and communication activities are aiming at improving access and equitable immunization coverage. Surveillance is very important for monitoring and evaluation of VPD status and monitoring AEFI. Vaccine provision, quality and logistics are also proposed to be provided and incorporated in to the updated cMYP.

### 2.5. 	The Inter-Agency Coordinating Committee for Immunisation and Health System Coordination Committee (ICC/HSCC)

The Inter-Agency Coordinating Committee for Immunisation Agencies and partners (including development partners and Civil Society Organizations) supporting immunisation services are co-ordinated and organised through an inter-agency coordinating mechanism (ICC/HSCC).  The ICC/HSCC is responsible for coordinating and guiding the use of the GAVI ISS and NVS support. Members of ICC/HSCC are WHO Representative to Indonesia, UNICEF Representative to Indonesia, UNDP Representative to Indonesia, Resident Representative of  the World Bank, Resident Representative of Asian Development Bank,  Director of Population, Health & Nutrition USAID, Team Leader AusAID in Indonesia, Director of KFW Jakarta, Resident Representative JICA,  Program Officer of Canadian/CIDA,  President, Director of PT Biofarma Indonesia, Governor of Rotary Int. District 3400 Jakarta.

The ICC/HSCC Indonesia is quite active and meets at least four times a year under the chairmanship of Hon. Minister of Health. All major decisions on financial sustainability and donor support for immunization including GAVI NVI, HSS, ISS and CSO are taken at the ICC/HSCC.

### 2.6. 	Indonesian Technical Advisory Group on Immunization (ITAGI)

Indonesian Technical Advisory on Immunization (ITAGI)  as independent body with members from : Paediatricians, Physicians, epidemiologists , clinical microbiologists, pulmonologists, HB task force, Members from Paediatric Society, Health Economic specialists was established in 2009 and meeting at least 4 times a year to advice Government of Indonesia on policy matters on immunization programme.

Major functions and responsibilities of the ITAGI are;

- Monitoring and assessing the scientific development of vaccine, both in terms of technology, production and development of new vaccines

- Presenting the results of monitoring and vaccines studies for consideration to the recommendations within the framework of the development of immunization

- Establish communication, coordination with various agencies, working groups, professional organizations, both at national and provincial level, which are relevant to immunization.

- Consulting with other experts in related fields of science and related organizations and

And other parties deemed necessary.

### 2.7. 	Current EPI performances

The administrative immunization coverage achieved for the year 2010 is:

- BCG  - 96.9%

- DTP-HepB 1 -97.7%

- DTP-HepB 3 – 94.4%

- Polio3 -93.6%

- Measles 1st dose- 93%

- Measles 2nd dose 89.1%

- TT2+ for pregnant women – 70.6%

- UCI villages (Villages achieved over 80 % immunization coverage with DPT-Hep B 3) - 75.3%

Reported administrative immunization coverage from 2004 to 2010

| Antigen | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| HepB 0 | 78 | 97 | 93 | 92 | 89 | 93 | 75.3 |
| BCG | 81 | 97 | 93 | 93 | 88 | 89 | 96.9 |
| DPT-HepB 1 | 76 | 90 | 87 | 88 | 77 | 82 | 97.7 |
| DPT-HepB 3 | 78 | 91 | 88 | 88 | 83 | 82 | 94.4 |
| Measles 1st dose | 82 | 83 | 83 | 83 | 79 |  | 93 |
| Measles 2nd dose | 78 | 97 | 93 | 92 | 89 | 93 | 89.1 |
| TT2+ | 81 | 97 | 93 | 93 | 88 | 89 | 70.6 |

In line with the targets of Immunization Program, all villages must achieve over 80 % basic immunization coverage including DPT-HB 3 vaccine (UCI - Universal Child Immunization) by 2014. However, UCI villages (Universal Child Immunization at village level) only reached 66.4% in 2008, 68% in 2009 and 75.3% in 2010. In district level there are 231 from 475 (48%) districts with UCI coverage under 80% in 2009 and in 2010 there are 226 from 495 (45%) districts with UCI coverage under 80%. UCI village’s percent coverage by province is given in figure below:

The reported coverage of DTP-H B 3 coverage in 2010 at national level is 94.4% but the sub-national data revealed significant variation between provinces and districts: 91 out  of 495 district (18.4%) with coverage < 80% of DTP-HB3 and 100 out of 495 district (20%) with coverage < 80% of MCV1

### 2.8. 	Intensification Routine Immunization in Indonesia

To achieve Universal Child Immunization (UCI) at village level by 100% in 2014, activities to reach this target started in 2009 at 5 provinces in Java Island will gradually expand to whole country in 2014.

Each province has to develop plan of action based on supporting data and indicating required resources, available and short fall. Provinces must have coordination with local governments; related cross-programs and cross-sectors obtain support for these initiatives.

In the framework of enhancing integrity, the roles of cross-program coordinators are very significant, particularly in accelerating the achievement of immunization program coverage. Communication forums at provincial and district/city levels are expected to coordinate activities of the related cross-programs and cross-sectors such as PKK, community health insurance, HSS, CSO, local government and other NGOs.

A planned effort is required in order that the budget of immunization program is supported by APBD (local budget), APBN (national budget) and BLN (foreign aid) to support the implementation of the planned initiatives.

Funds from  GAVI in support programs such as ISS, HSS and CSO are use to support these activities including local area monitoring revitalization, specific planning, training, assessment of DQS, EVSM, and Supportive Supervision. HSS funds are use for community mobilization, village mapping, cadres training , provide operational cost at village level and integration with MCH programs. GAVI CSO funds are being use on cross-program basis through Family Welfare Organization (PKK), religious organizations, Midwives Society and Boy Scouts Movement.

### 2.9. 	Vaccine forecast, procurement and management

Vaccine forecast, at national level is done once every year by Immunization Sub Directorate of the Ministry Of Health.  As a national policy, Indonesia procures all the vaccine required for its national immunization program from government owned  vaccine manufacturer BioFarma.

Vaccines distribute to province every three month by BioFarma. Vaccines from province to districts come once a month and districts distribute to the health centers also monthly.

Internationally accepted vaccine management guidelines are supposed to be followed by the Indonesian EPI program as well. As indicated earlier several activities are underway and incorporated in to the cYMP to further improve the vaccine cold chain and management of vaccine in the peripheral. Using of freeze tags, training the staff on cold chain, improved supportive supervision to monitor cold chain maintenance, planned replacement cold chain equipment at district and health center level, procurement of additional cold chain equipments and spare parts, removal of freezers from cold chain in health centre and used of cool packs instead of ice packs are the main activities under implementation.

The latest EVSM (Effective Vaccine Stored Management) assessment was conducted in 2011 at provincial vaccine storage places (cold rooms) in 16 provinces. The result of EVSM assessment is attached.

### 2.10. 	Storage Capacity and Accommodation of Hib-pentavalent Vaccine

The last cold chain inventory assessment was conducted in 2008 and yearly provinces and districts up date their respective cold chain inventories based on the 2008 data as baseline. Based on these data cold room capacity at the central and provincial level is considered sufficient.

Total volume of vaccine storage capacity is 562 M3 at provincial level, while the routine vaccine storage capacity required for Province level is 133 M3 for 3 months storage as per data provided in table below.

Table Total volume of Vaccine Storage Capacity at Provincial Level

|  | Description | Formula | Year 1 | Year 2 |
| --- | --- | --- | --- | --- |
|  |  |  | 2013 | 2014 |
| A | Annual positive volume requirement, including new vaccine (litres or m3) Litres | Sum-product of total vaccine doses multiplied by unit packed volume of the vaccine | 533 | 533 |
| B | Existing net positive cold chain capacity (litres or m3) Litres | # | 562 | 562 |
| C | Estimated minimum number of shipments per year required for the actual cold chain capacity | A / B | 1 | 1 |
| D | Number of consignments / shipments per year | Based on national vaccine shipment plan | 4 | 4 |

Accordingly existing cold chain capacity is well enough for the Hib-pentavalent introduction and   Hib-pentavalent vaccine introduction will not demand in increased cold chain capacity.

It has been already planned to conduct cold chain inventory assessment again in 2013 in all the provinces. Based on the result of this assessment, required new refrigerators and replacement spare parts will be procured in 2014 and 2015 for the provinces, where Hib–pentavalent vaccine to be introduced in 2nd and 3rd phases, to strengthen district level cold storage capacity.

# III. 	Indonesian Experience in New Vaccine Introduction

Indonesia has considerable experience in new vaccine introduction. In 1997 Indonesia successfully introduced HB vaccine birth dose and in 2004 introduced DTP-HB (tetravalent) vaccine on phase basis and currently in implementation in throughout the country. From those experiences, the following key lessons were learned and will be used to more effective introduction of Hib-pentavalent vaccine on phase basis into the routine EPI program commencing from 2013.

- New vaccine introduction requires at least 12 months of preparation. Early preparation is specially needed for Indonesia because of its geographical vastness and to convince large entities of political and administrative decision makers in Indonesian highly decentralized administrative setting.

- New vaccine introduction requires a through training for all health workers involved in the immunization activities at all levels in cascade manner. This training should take into account all the operational components of immunization services in order to smooth change over to Hib-pentavalent vaccine from current Tetravalent vaccine.

- New vaccine introduction requires the development of key messages, social mobilization material and training material to address concerns of parents and of health workers with respect to the new vaccine and help them to accept the new vaccine.

- Taking into account the high cost of new vaccines, good advocacy should be made targeting the political authorities and potential donors.

# IV. 	Goal and Objectives for Hib-pentavalent Vaccine Introduction

### 4.1. 	Goal

The goal of Hib-pentavalent vaccine introduction is to contribute to the reduction of infant morbidity, mortality and disability due to pneumonia, meningitis and related invasive Hib diseases caused by Haemophilias Influenzae type b bacterium in Indonesia and will help to accelerate the achievement of Millennium Development Goal 4, in 2012.

### 4.2. 	Specific objectives

The specific objectives of this plan are:

- Prepare health workers at all levels and the community for the introduction of Hib-pentavalent vaccine (make them ready to introduce and to accept pentavalent vaccine);

- Introduce successfully Hib-pentavalent vaccine in Indonesia in sustainable and phased manner

- Use the introduction of Hib-pentavalent vaccine as an opportunity to reinforce and maintain high level of immunization coverage for all routine immunization activities

- Immunize at least 80% of infants < 1 year of age against Haemophilias Influenzae type b diseases in 2015.

# V. 	Epidemiology and Burden of Haemophilias Influenzae type b

Indonesian under 5 years childhood mortality rate is 44/1000 live births in 2007. This is highest among ASEAN countries.  Major cause of deaths among children below 5 years of age: pneumonia is the leading cause of death for infants (22.3%) and also for children below 15 years of age (23.6%)1,2 From  the World Health Organization’s, Child Health Epidemiology, Reference Group - CHERG data, it is mentioned that approximately 60% of new cases of pneumonia are located in six countries that are India, China, Pakistan, Bangladesh, Nigeria, and Indonesia2.

National Basic Health Research data in 2007 showed that the incidence of pneumonia among infants age 29 days to 11 months is 24% and meningitis 9%, while incidence of pneumonia among children below 5 years of age is 15.5% and for meningitis/encephalitis it is 8.8%1.

Slightly less than 23% of serious pneumonia among children are caused by Haemophilias influenzae type b, and the rest are due to Pneumococcus, Staphylococcus, Streptococcus and Viruses.3

Haemophilias influenza can cause serious and fatal infection such as meningitis and pneumonia. CDC in 2000 reported Hib can cause meningitis (50%), epiglottis (17%), pneumonia (15%), arthritis (8%), cellulites (6%), osteomyelitis (2%) and bacteraemia (2%)4.

Prospective hospital-based studies among children (1 month – 5 years) found that Streptococcus pneumoniae (pneumococcus) is the etiologic agent for 30%-50% of all new pneumonia cases among children below 5 years of age, followed by Haemophilias influenzae type b with rate of  10%-30%.5

Some assessment of burden of Hib or relevant diseases, immunogenicity and safety study of DTP/Hib and a cost-effectiveness analysis conducted in Indonesia since 1981 to 2006.

In 1981, study on Hib among Meningitis cases in Dr.Cipto Mangunkusumo found that S.Pneumonias 5.8%, Hib 5.2% among 155 positive of cerebrospinal fluid cultures from 208 meningitis cases with ages 2 days-12 years old 6

In 1998, study on Hib by NIHRD collaborated with PATH found that pneumonia among children < 2years in Lombok was 30,430 per 100,000/year, clinical meningitis 692 per 100,000/year and clinical meningitis due to Hib was 22% 7,8

In 2003, economic evaluation of Hib vaccination in Indonesia : a cost effectiveness analysis in Lombok found that implementation of Hib vaccination in Indonesia avert around 76,700 cases of invasive infection, more than 7,150 deaths and 273,000 disability-adjusted life years (DALYs). Compared to no vaccine, the incremental cost effectiveness ratio (ICER) is US$67 per DALY averted based on UNICEF pricing, whereas the program would save US$3.7 million with GAVI pricing. The result is not sensitive to uncertainty in disease incidence, cost of treatment or the probability of developing immunity. Conclusion of this study is the model demonstrates significant cost effectiveness of implementation of a Hib vaccination program for Indonesian Society 9,10

Study about comparison of immunogenicity and safety of DTP/Hib vaccines with DTP vaccine in 2004 shown that immunogenicity of anti-PRP =0.15 mcg/ml and 99.2% had titer anti-PRP=1 mcg/ml. AEFI was observed in first three days and found one serious case but no causal relation with the vaccination.11

Study about incidence of Hib in Sanglah Hospital, Bali in 2006 found that 108 cases of meningitis due to Hib among children under 2 years . Post illness complications were hydrocephalus 28%, paresis 20%, deafness 20% and epilepsy 20% 12

Also in 2006 there was study conducted in Jakarta about immunogenicity and safety of Hib vaccination among 1,048 infants with different doses. This study found no difference of titer antibody Hib-PRP between Hib with dosages of 10 µg, 5 µg, 2.5 µg and 1.25 µg PRP-T. Mostly AEFI report was irritability and fever 13

# VI. 	Decision making and choice of Hib-pentavalent vaccine to be introduced

### 6.1. 	Choice of the vaccine

On its first meeting held on 7th of June 2007 in Jakarta, the Indonesian Technical Advisory Group on immunization (ITAGI) which was also attended by international experts from WHO, and HQ and CDC, Atlanta recommended to include Hib-pentavalent vaccine to the Indonesian immunization program in phased basis.

Further during ITAGI second meeting held on 10th November 2008, recommended that the Hib vaccine which will be incorporated to the national immunization program should be locally made and the easiest way to smooth transition is liquid tetravalent vaccine replace with liquid Hib-pentavalent vaccine.  This will minimize the specific training requirements in Hib-pentavalent vaccine introduction.

Another recommendation is the presentation of vaccine should be 5 dose vials as current liquid tetravalent vaccine, which is 5 doses to minimize wastage and training requirements. With 5 dose vial presentation  we may reach minimal wastage factor around 1.33.

The ITAGI, during its 2010 deliberations further evaluate the Indonesia’s Hib-pentavalent vaccine introduction plan with the attendance of Supporting Independent Immunization and Vaccine Advisory Committee (SIVAC) and national vaccine manufacturer BioFarma, decided the national reference standards for Hib-Pentavalent vaccine.

### 6.2. 	Introduction approach

## It has been decided to introduce Hib-pentavalent vaccine in 3 phases commencing from 2013 in following manner.

## Phase I – 2013, encompassing 20 % of the population (West Java, West Nusa Tenggara, Bali and Yogyakarta)

## Phase II – 2014,  reaching  another 30% of population (DKI Jakarta, Banten, Central Java, East Java, North Sumatera, South Sumatera, Bangka Belitung, Jambi, Lampung and South Sulawesi)

## Phase III – 2015,  reaching balance 50 % of the population covering entire country (Aceh, West Sumatera, Riau, Riau Island, Bengkulu, all province at Kalimantan and Sulawesi, East Nusa Tenggara, Maluku, North Maluku, Papua and West Papua)

## 6.3 The reasons for phased based introduction Hib-pentavalent vaccine

## As stated in the early part of this document all new vaccine introductions in Indonesia was done in phased manner. Based on that experience Government of Indonesia is envisaging the introducing Hib-pentavalent vaccine on phased basis in line with previous country experience. The pertinent reasons for phased based vaccine introduction are listed below.

## Indonesia being the 4th largest populace country  in the world with over 4.5 million annual birth cohort, introduction of very costly public health introduction like pentavalent vaccine, at once throughout the country is financially and logistically prohibitive

## Further, the Indonesia being a archipelago consist of over 700 inhabited islands spans across over 9,000 km ( three time zones) in 33 provinces, implementation of such program throughout  the country effectively beyond the capacity of central immunization sub directorate

## As stated earlier in this document, Indonesia consists of politically and administratively highly devolved provincial and district setup of governance at deferent stages of health infrastructure and human resource capacity. Introduction of this type of public health intervention to all such entities at once is a challenge.

## The current EPI data and indicators such as immunization coverage, vaccine wastage rates, cold chain capacity and vaccine management practices, AEFI surveillance and causality assessment capacities in each administrative entities indicate that there are very high performing areas to poorly performing areas.

## Therefore, it is prudent to introduce this type of new intervention to a set of small better performing provinces first and based on that experience and lessons learned, extend it gradually into other provinces as it done in the past.  The introduction activities will also boost performance of low coverage by increasing social mobilization, adjustment of reporting – recording form and sweeping activities especially at puskesmas and posyandu level.

## Government of Indonesia’s  financial capacity and fiscal space to inject large amount capital investment at once also not sustainable

## Further, the introduction plan should be inline with new vaccine production capacity of the local vaccine manufacturer PT.BioFarma.

# VII. 	Strategies

In order to achieve the defined objectives and goals of Indonesian immunization program and new vaccine introductions, following strategies are being under implementation as a part of Intensification of Routine Immunization.

### 7.1.	Improvement of Service Delivery

Improvement service delivery will be done especially for hard to reached area and low performing through:

- Develop and reinforce the strategies to maintain the current unimmunized and drop-out rates at their lower level  such as:

  - Mapping the causes of unimmunized and drop-out

  - Conduct routine workshop each month in health center to develop POA to address the unimmunized and drop-out. For example: change the immunization post schedule accordance with the community condition, use the SOS (Sustainable Outreach Services)

- Monitoring of infant vaccination status to track defaulters has been included into the integrated package of interventions at health center level in hard to reached areas.

- Ministry of health has recently formed a special unit called  DTPK to ensure that the implementation of health programs including immunization is take place in difficult to reach, underdeveloped, border and island areas. By integrating immunization into DTPK program, Indonesia may reach unreached areas through routine immunization and may increase the immunization coverage in these areas.

- Reinforce IEC activities for immunization through the intensification of routine immunization programme planned in 2012.

### 7.2.	Reinforce monitoring and evaluation

Periodic evaluation of the program will help to identify problems related to the preparation of the new vaccine introduction into the current routine immunization program.

All the current EPI management tools in use at different levels will be revised to incorporate specific information related to Hib-pentavalent vaccine introduction and will be printed and be distributed to all levels.

### 7.3. 	Reinforcement of the staff capacity

The Hib-pentavalent introduction will be the opportunity for the health workers training with respect to specific aspects of this vaccine. Two key elements will be part of this component:

#### 7.3.1. Training of trainers and of the health workers

Training will help to improve the competency of staff at all levels and will cover technical areas of immunization services (vaccine administration, stock management, maintenance, injection safety, AEFI identification, report and case-management, waste management, supervision, monitoring, inter personal communication, etc.). Special attention will be given to the specific characteristics of the new vaccine. Training of trainers will be organized at central, province and district level and then the training of the health workers at the health facility level.

#### 7.3.2. Supportive supervision

Regular supportive supervision will be an excellent opportunity to reinforce the capacity of health workers in the field. The less performing health workers will be supervised by EPI focal point from the district health office will supervise the health workers at health center level. All the recommendations made during follow up activities will be implemented through the regular supportive supervision visits.

Following the first six months after the introduction of Hib-pentavalent vaccine in each phase, supportive supervision will be regular from central level to the less performing health districts, every 2 months. Districts will supervise the health centers, especially the poorly performing health centers, once every two months. Supervision check-list will be updated with specific information related to Hib- pentavalent vaccine introduction.

### 7.4.	Reinforcement of cold chain storage capacity

Cold chain inventory assessment will be conducted in all 33 provinces in 2013. Procurement will be conducted in 2014 and 2015 based on cold chain inventory result. Procurement of refrigerator and vaccine carrier in some areas which is needed based on cold chain inventory result.

In addition, old cold chain equipments in some districts will need to be replaced. There is a need to fill the gap and accommodate the new vaccines with support from government and partners.

### 7.5.	Reinforcement of communication and social mobilization

Immunization services will develop closer links with community-based organizations in order to keep permanent contact between community and health workers. In each health center, immunization related information, education and communication will be reinforced through this linkage. Key messages which address parents concerns for new vaccine introduction will be disseminate to the community through both health workers and CBO volunteers.

Indonesian government is currently trying to implement equitable health services. For that purpose, MOH formed a special unit whose task was to ensure that the implementation of health programs including immunization can take place in difficult to reach areas, know by name Daerah Tertinggal, Perbatasan dan Kepulauan / DTPK (Underdeveloped, Border and Island areas). By integrated immunization into DTPK program, we will reach the unreached area routinely and hopefully this intervention will be increasing the immunization coverage.

### 7.6.	Reinforcement of epidemiological surveillance and of the AEFI

#### 7.6.1. Invasive bacterial disease surveillance

Hib surveillance will be integrated in Integrated Diseases Surveillance /ILI surveillance. Standard case definition will be used for all pneumonia and meningitis and identified as suspected cases. Hib will be confirmed by the referral laboratory in Jakarta Laboratory. Hib disease surveillance will be strengthened to identify severe cases of pneumonia and meningitis, and collect required sample for lab confirmation (identification of Hib disease).

#### 7.6.2. AEFI surveillance

AEFI surveillance system has to identify both serious and non serious AEFI cases specially in the beginning of introduction. Training session on Hib vaccine introduction will take into consideration the AEFI surveillance (identification, notification and case management). Current AEFI reporting form available at health institutions and with the health professionals could be use to report AEFI following Hib-pentavalent vaccine as well.

### 7.7. 	Improvement of vaccine supply and management

Regular vaccine supply and correct vaccine stock management with other immunization supplies will be the key factors in the process of new vaccine introduction. This will need to continue with rational management of these supplies, assure their availability and limit their wastage. This will include the best vaccine forecasting taking into account the correct target population, vaccination coverage objective and potential vaccine wastages, good stock management and effort to improve the quality of vaccines.

In order to reduce the vaccine wastage rates, staff will be trained in stock management, the use of the opened multi dose vial policy (MDVP) in static service and approach to use vaccine vial monitor (VVM) as a management tool. In addition, special focus will be given to vaccine distribution plan, the use of the FEFO process principle. Special attention will be given to the use of “Freeze Tag” indicators to detect freezing of vaccines.

The main observations and recommendations of the 2011 EVM Assessment were that assessment scores were; 2011 assessment scored significantly higher ratings than the comparable scores of 2003/4 EVSM Assessment. Introduction of cold water packs and incorporation of VVM into all vaccine vials has positively strengthen the vaccine management in the last 8 years. Temperature monitoring and vaccine stock management (including diluents) need further effort to improve in all levels. It further recommended that EPI should further standardize and institutionalize the vaccine management guidelines and strengthen the monitoring and active supervision of cold chain and vaccine management at all levels to ensure stable and reliable cold chain.  The active management of vaccine wastage of unopened vials and further improvements in vaccine forecasting will further strengthen the cold chain system. The management of dry stores also to be included into the good warehousing practices ay all levels. The institutionalization of Standard Operating Procedures at all levels will be actively pursued and monitored and supervised by the central EPI Management. The MoH EPI Directorate is planned to conduct a detailed capacity analysis at all levels before the introduction of new vaccine.

Based on the recommendation of EVM Assessment, we will conduct cold chain managerial training along with staff training for new vaccine introduction.

### 7.8.	Reinforcement of collaboration, coordination and partnership

Smooth introduction of the new vaccine goes through the reinforcement of the coordination, collaboration and partnership of all the involved partners.  Technical Working Group or ITAGI activities through the quarterly meetings should be reinforced. Technical working group consists of Immunization sub directorate and technical partners will meet on a monthly basis and monitor preparedness, implementation and evaluation activities for new vaccine introduction.

### 7.9.	 Financial sustainability

In 2009 immunization program cost was around US $ 139 million is predicted to reach USD 199 million in 2011 and will continue to increase to USD 275 million in 2017 including new vaccine introduction costs as per attached the attached updated CYMP estimates up to 2017.

Data on national health accounts (NHA), available for Indonesia from 1995 to 2009 (WHO NHA web site), indicate that total government general expenditure against total GDP was around 15 % – 16 %  during 1995 to 1996 has gradually increased to 18% - 20 % towards 2008 – 2009. Assuming that current GDP growth in Indonesia, around 6 %, will continue to be maintained until 2017, it will be estimated to be around US $ 861,122 million in 2017. If assumed that total government general expenditure (GGE) against GDP will continue to be at current 20 % level against the GDP, in 2017, it is estimated that It will be increased to around US $172,224 from 2009 figure US $ 96,329 million. Available NHA data indicate that from 1995 to 2009 there was a gradual increase of percentage of government expenditure on health against total government expenditure from 3-4% in early 1990s to 8 % in 2007 and 2009. If assumption is made that government will continue to allocate current 8 % of its total government expenditure to health, in 2017, total government expenditure on health will be increased to around US $ 13,778 from 2009 equivalent US $  6607 million. According to the curent CYMP (2010 to 2014), for the base line year 2009, total cost for the EPI (US $139 million), including shared cost, was around 2% of the total cost of government expenditure on health. As per projected EPI cost in 2017 inclusive of 100% Hib-pentavalent vaccine introduction cost, will be around US $ 275 million, however it is still around 2% of total government expenditure on health, even though there is almost 100% increase in total immunization programme cost from 2009 to 2017.

Based on the above facts, assumptions and arguments presented, introduction of Hib-pentavalent vaccine to the national immunization programme in phased basis from 2013 to 2017 will be financially sustainable.

Table : Projected Total Immunization Program Cost from 2012 to 2017

Assessment of Indonesia's Financial Sustainability based on GDP growth and projected percent allocation of budget to health and immunization

The Government of Indonesia would like to expand the existing partnership with the GAVI Alliance for the improvement of the infant’s routine immunization program of the country, and specifically hereby requests for GAVI support for Introduction of Hib-pentavalent vaccine in addition to current GAVI support for ISS, HSS and CSO component.

The Government of Indonesia commits itself to developing national immunization services on a sustainable basis in accordance with the comprehensive Multi-Year Plan for immunization, 2009 – 2014 and projected comprehensive cost estimates developed up to 2017 and presented with this document. The Government of Indonesia solicits financial and technical support from the GAVI Alliance and its partners to introduce Hib-pentavalent vaccine in financial sustainable manner on co-financing basis as given below.

|  | Cost for vaccine and Injection supplies |  | For Operational Costs for new vaccine introduction |  |
| --- | --- | --- | --- | --- |
| Year | GAVI | GOI | GAVI | GOI |
| 2013 | 9,335,000 | 1,945,000 |  |  |
| 2014 | 12,991,000 | 10,142,000 |  |  |
| 2015 | 21,778,000 | 20,194,500 |  |  |
| 2016 | 8,004,000 | 29,014,500 |  |  |
| 2017 | 0 | 37,931,000 |  |  |
| Total | 52,113,000 | 99,227, 000 | 1,400,000 | 49,813,791 |

## The exercise of the funding needed could be shown by table below:

Funding for Hib-pentavalent vaccines is expected to be provided by Government of Indonesia to co-finance vaccine and injection supplies grant from GAVI. We have identified all the critical activities that need to happen before the start of introduction. The updated cMYP includes training material development, staff training; strengthen supply management, communication strategy and IEC material, AEFI surveillance, vaccine impact evaluation. It will be proposed to GOI (national and sub-national) and GAVI to finance the activities. It is also expected that donors (WHO, UNICEF) will also provide support.

Following the regulations of the internal budgeting and financing cycles the Government will annually release its portion of the co-financing funds in the month of April. The payment for the first year of co-financed support will be around April 2013.

Given the high cost of new vaccines, the Central Government of Indonesia will commit to co-finance the Hib pentavalent vaccine’s cost with GAVI Alliance. The advocacy will be the main strategy (to Government and to current and potential development partners) to continue to pay vaccination cost and even to increase their contribution for immunization services.

#### 7.9.1. Government

Government of Indonesia is strongly committed in financing immunization costs: it pays all the traditional vaccines including HB birth dose since 2006. Strong advocacy should continue toward the Government so that it continues to pay and increase its contribution for vaccines and vaccination expenses.

#### 7.9.2. Partners

Several partners continue to support national EPI through the Inter Agency Coordinating Committee (ICC). Among those, the most important are the following: GAVI Alliance, WHO, UNICEF, USAID and others. Program will continue to look for additional partners and reinforce the coordination of the current and future partners to support immunization program.

# VIII. 	Plan  activity and budget  for Hib-pentavalent  Vaccine Introduction Indonesia, 2012 - 2017

| NO | ACTIVITIES | DETAIL | VOL | UNIT COST | 2012 | 2013 | 2014 | 2015 | TOTAL | LOCATION | REMARKS |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A | PREPARATION |  |  |  |  |  |  |  |  |  |  |
| 1 | Develop Hib Pentavalent Technical Guideline for Health Workers | Three days meeting with participant from immunization staff and related program | 2 | $4,859 | $1,943 | $2,915 | $4,859 | $0 | $9,718 | Central | This meeting will be produced technical guideline as standard procedure for health workers at the field. Meeting will be conducted three days for 2 times with participant from immunization staff and related program such as MCH, Surveillance etc. This activities will be funded by Central Government and WHO) |
| 2 | Printing Hib Pentavalent Technical Guideline for Health Workers | Printing and distribution will be conducted by printing company | 10,865 | $1.14 | $2,477 | $3,716 | $6,193 | $0 | $12,386 | Central | This guideline will be distributed directly to district / city by printing company . This activities will be funded by Gavi and Central government) |
| 3 | Develop IEC material for health workers and community | 3 days meeting with participants from immunization staff and health promotion | 3 | $5,765 | $3,459 | $5,189 | $8,648 | $0 | $17,295 | Central | This meeting will be produced IEC material for health workers and community at the field.Meeting will be conducted three days for 3 times with participant from immunization staff and health promotion. This activities will be funded by Central Government and WHO) |
| 4 | Printing IEC material for Health Workers and community | Printing and distribution will be conducted by printing company | 50,530 | $1.14 | $11,521 | $17,281 | $28,802 | $0 | $57,604 | Pusat | This IEC material will be distributed directly to district / city by printing company. This activities will be funded by Central Government and GAVI) |
| 5 | Hib pentavalent socialization meeting | Meeting with participants from CDC manager or chief of immunization & surveillance and immunization staff at all levell and related program and sector. | 1 | $4,476,813 | $895,363 | $1,343,044 | $2,238,407 | $0 | $4,476,813 | Central, Province and District/ city level | Socialization will be conducted by 3 phases. In 2012 socialization meeting will be conducted in 4 provices , 2013 in 10 provinces, 2014 in 19 provinces and all districts among those provinces.In this meeting also develop microplaning about Hib pentavalent introduction. This activities will be funded by Central and Local Government, GAVI and WHO) |
| 6 | Training for health workers | Conduct training for health workers at all level with participants from immunization manager at province and district level also immunization staff at Health centers about implementation of Hib pentavalent introduction. | 1 | $5,928,210 | $1,185,642 | $1,778,463 | $2,964,105 | $0 | $5,928,210 | Province, districts/ city and Hc's | To improve the capability and knowledge of health workers on implementation of Hib pentavalent introduction. This training will be conducted in 3 phases. In 2012 will be conducted in 4 provinces and all districts and health centers among those provinces, in 2013 will be conducted in 10 provinces and 2014 will be conducted in 19 provinces. This activities will be funded by Central Government, WHO and the other donour ) |

| 7 | Socialization Meeting | Meeting with AEFI National & Province Committee involving program and sector related at central level and province level | 1 | $561,370 | $112,274 | $168,411 | $280,685 | $0 | $561,370 | Central & province level | One time meeting at central level with participants from province AEFI committee and Central AEFI committee . Meeting at province level with participants from district AEFI committee. This activities will be funded by Central Government and WHO). |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 8 | Study Tour to the best experience country which implement new vaccine introduction about introduction new vaccine and AEFI. | Visit to Epidemiology & Health Division - Ministry of Health of those country with participants from EPI-central | 2 | $2,767 | $5,534 | $0 | $0 | $0 | $5,534 | Central | 7 days study tour with 2 participants from EPI-Central. This activities will be funded by GAVI) |

| B | SERVICE DELIVERY |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Vaccine delivery | Distribution vaccine from provinces to district and district to health centers and to service delivery | 1 | $992,455 | $0 | $198,491 | $297,737 | $496,228 | $992,455 | Province, district/city and health center | This budgeting will cover distribution of vaccine from province to district ,but from district to health center will be covered by local budget. In 2013 will cover 4 provinces, 2014 will cover 10 provinces and 2015 will cover 19 provinces. This activities will be funded by Central Government and GAVI) |
| 2 | Strengthening cold chain system | Procurement of refrigerator and vaccine carrier in some areas which is needed. | 1 | $28,409,091 | $0 | $2,840,909 | $12,784,091 | $12,784,091 | $28,409,091 | Central | Coldchain inventory will be conducted in 33 provinces in 2013. Procurement will be conducted in 2014 and 2015 based on cold chain inventory result. Strengthening cold chain including procurement of new refrigerator and replace of spare part and maintanace. This activities will be funded by Central and Local Government , WHO and other partners) |
| 3 | Improve management vaccine and cold chain | conduct training for chold chain staff at province, district and health centers level about management vaccine and cold chain | 1 | $5,928,210 | $1,185,642 | $1,778,463 | $2,964,105 | $0 | $5,928,210 | Province, district/city | Training will be conducted in 2012 at 4 provinces, 2013 at 10 provinces and 2014 at 19 provinces. This activities will be funded by Centraland Local Government ) |
| C | FOLLOW UP ACTIVITIES |  |  |  |  |  |  |  |  |  |  |
| 1 | Review SOP after follow up Hib pentavalent implementation | Internal meeting with EPI-central staff | 1 | $1,295 | $259 | $389 | $648 | $0 | $1,295 | Central | This meeting will be produced revised SOP to improve planning & implementation. This activities will be funded by Central Government ) |
| 2 | Evaluation meeting | Coordination meeting at central level with participant from EPI-Central staff and related program and sector.This meeting followed by meeting at province and district level to evaluate the implementation of Hib pentavalent introduction (based on phases) | 1 | $4,481,313 | $896,263 | $1,344,394 | $2,240,657 | $0 | $4,481,313 | Central, Province, district/city | Two times meeting will be conducted at central level. Meeting at province and district level will be conducted based on phases of Hib pentavalent implementation. This activities will be funded by Central and Local Government) |
| 3 | Monitoring and Supportive Supervision | Monitoring of implementation Hib pentavalent at all provinces for 4 days to monitor the process of implementation, problem and follow up action or find the solution to solve the problem | 1 | $77,592 | $0 | $15,518 | $23,278 | $38,796 | $77,592 |  | Monitoring at all level from central to province and district to health centers and service pos . This activity will conduct together with province, district and hc's staff .At every province will choose 2 districts as a sample , every district will choose 2 health centers and 2 service pos /health centers. The activity will be conducted by phases for 3 years (2013 to 2015) This activities will be funded by Central and Local Government ) |
| D | SURVEILANCE |  |  |  |  |  |  |  |  |  |  |
| 1 | Integration Surveillance Hib with VPD / ILI | Four days Integration meeting with participation SO (surveillance officer ) from 33 provinces discuss about the trend of VPD including surveillance of Hib. | 1 | $98,308 | $19,662 | $29,492 | $49,154 |  | $98,308 | Province | Three times meeting will be conducted at the end of the year based on the year of introduction of Hib pentavalent at every provinces. Participants from province Surveillance officer , NIHRD,immunization staff and other related program and sector. This activities will be funded by WHO) |
| 2 | AEFI surveillance | Conduct investigation of AEFI serious cases from National AEFI committee and Province & District AEFI committee at 33 provinces.Followed by AEFI case audit at central together with province AEFI committee. | 1 | $156,597 | $31,319 | $46,979 | $78,299 |  | $156,597 | Central and province | Every serious AEFI and non serious must be reported . Serious AEFI case reported by province AEFI committee will be followed up with investigation activity by National AEFI committee. With this activity national AEFI committee will make conclusion cause of AEFI cases and follow up action can be done immediately. This activities will be funded by Central Government, WHO, and Bio Farma) |
|  | TOTAL |  |  |  | $4,351,358 | $9,573,654 | $23,969,665 | $13,319,114 | $51,213,791 |  |  |

|  | Time Line of HIB-PENTAVALENT INTRODUCTION IN INDONESIA IN 2012 TO 2015 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| NO | ACTIVITIES | 2012 |  |  | 2013 |  |  |  | 2014 |  |  |  | 2015 |  |  |  |
|  |  | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 |
| A | PREPARATION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | Develop Hib Pentavalent Technical Guideline for Health Workers | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2 | Printing & Distribution Hib Pentavalent Technical Guideline for Health Workers |  | X | X |  |  | X | X |  |  | X | X |  |  |  |  |
| 3 | Develop IEC material for health workers and community | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4 | Printing & Distribution IEC material for Health Workers and community |  | X | X |  |  | X | X |  |  | X | X |  |  |  |  |
| 5 | Hib pentavalent socialization meeting |  |  | X |  |  |  | X |  |  |  | X |  |  |  |  |
| 6 | Training of Trainer for health workers |  |  | X |  |  |  | X |  |  |  | X |  |  |  |  |
| 7 | AEFI Socialization Meeting |  |  | X |  |  |  | X |  |  |  | X |  |  |  |  |
| 8 | Study Tour to the best experience country which implement new vaccine introduction and AEFI. | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| B | SERVICE DELIVERY |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | Vaccine delivery |  |  |  |  |  |  | X |  |  |  | X |  |  |  | X |
| 2 | Strengthening cold chain system |  |  |  |  | X | X |  |  |  | X |  |  |  | X |  |
| 3 | Improve management vaccine and cold chain |  |  | X |  |  |  | X |  |  |  | X |  |  |  |  |
| C | FOLLOW UP ACTIVITIES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | Develop SOP for follow up Hib pentavalent implementation |  |  |  |  |  |  | X |  |  |  |  |  |  |  |  |
| 2 | Evaluation meeting |  |  |  |  |  |  | X |  |  |  | X |  |  |  | X |
| 3 | Monitoring and Supportive Supervision |  |  |  | X | X | X | X | X | X | X | X | X | X | X | X |
| D | SURVEILANCE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | Integration Surveillance Hib with VPD / ILI |  |  | X |  |  |  | X |  |  |  | X |  |  |  |  |
| 2 | AEFI surveillance |  |  |  | X | X | X | X | X | X | X | X | X | X | X | X |

Reference:

- Badan Penelitian dan Pengembangan Kesehatan. Laporan hasil riset kesehatan dasar tahun 2007.

- WHO. 10th Meeting of the European Regional Working Group for the Global Alliance for Vaccines and Immunization. 2009.

- Michael Brocker. Burden of invasive disease caused by Haemophilus influenzae type b in Asia. Jap J of Infec Dis. 2009;62: 87-92.

- CDC. Epidemiology and prevention of vaccine – preventable diseases. 2000.h.101-115

- Rudan I, Boschi-Pinto C, Biloglav Z, Mulholland K, Campbell H. Epidemiology and etiology of childhood pneumonia. Bull World Health Organ. 2008;86:321-416

- Tri Ruspandji, Sumarmo et all. Acute purulent meningitis in infants and children. Modern Medicine of Asia Vol 17 No. 1 January 1981.

- Mulholland EK, Adegbola  RA. The Gambian Haemophilus influenzae type b vaccine trial. J Ped. Infect. Dis. 1998;17:S123-5.

- Depkes, PATH. Final Report – The proportion of radiologically-confirmed and other pneumonias due to Haemophilus Influenzae type b on Lombok Island, Indonesia, using Haemophilus Influenzae b conjugate vaccine as probe, 1998-2002. Jakarta, 2005.

- Gessner Bradford D. MD, Sedyaningsih Endang R. MD, Griffiths Ulla K. MSc, Sutanto Agustinus MD, Linehan Mary BA, Mercer Dave PhD et al. Vaccine preventable Haemophilus Influenzae type b disease burden and cost effectiveness of infant vaccination in Indonesia. PIDJ: 2008; 27:438-43.

- Edward IB. Economic evaluation of Haemophilus Influenzae type b vaccination in Indonesia: a cost-effectiveness analysis. J of Pub Health. 2007; 29:441-48

- Carib M Nelson, Agustinus Sutanto, Bradford D. Gessner, I.G.P. Suradana, Mark C. Steinhoff, and Soemarjati Arjoso. Age and cause-specific childhood mortality in Lombok, Indonesia, as a factor for determining the appropriateness of introducing Haemophilus Influenzae type b and Pneumococcal Vaccines. J Health Popul.Nutr 2000; 18:131-8.

- Komang Kari. Presented in ASAP (Asia Starategic Alliance Pneumococcal Disease Prevention). 2006.

- Punjabi NH, Richie EL, Simanjuntak CH, Harjanto SJ, Wangsasaputra F, Arjoso S, Rofiq A, Prijanto M, Julitasari, Yela U, Herzog C, Cryz SJ.  Immunogenicity and safety of four different doses Haemophilus influenzae type b- tetanus toxoid conjugated vaccine, combined with Diphtheria-Tetanus-Pertussis vaccine (DTP-Hib), in Indonesian infants. Vaccine, 2006; 24: 1776-85.