GAVI Alliance

Application Form for Country Proposals

For Support to New and Under-Used Vaccines (NVS)

Submitted by

The Government of

Myanmar

Date of submission: 12.11.2011 08:04:31

Deadline for submission: 15 Nov 2011

Select Start and End Year of your Comprehensive Multi-Year Plan (cMYP)

| Start Year | 2012 | End Year | 2016 |
| --- | --- | --- | --- |

Revised in January 2011

(To be used with Guidelines of December 2010)

Please submit the Proposal using the online platform https://AppsPortal.gavialliance.org/PDExtranet.

Enquiries to: proposals@gavialliance.org or representatives of a GAVI partner agency. The documents can be shared with GAVI partners, collaborators and general public. The Proposal and attachments must be submitted in English, French, Spanish, or Russian.

Note: Please ensure that the application has been received by the GAVI Secretariat on or before the day of the deadline.

The GAVI Secretariat is unable to return submitted documents and attachments to countries. Unless otherwise specified, documents will be shared with the GAVI Alliance partners and the general public.

GAVI ALLIANCE GRANT TERMS AND CONDITIONS FUNDING USED SOLELY FOR APPROVED PROGRAMMES The applicant country (“Country”) confirms that all funding provided by the GAVI Alliance will be used and applied for the sole purpose of fulfilling the programme(s) described in the Country’s application. Any significant change from the approved programme(s) must be reviewed and approved in advance by the GAVI Alliance. All funding decisions for the application are made at the discretion of the GAVI Alliance Board and are subject to IRC processes and the availability of funds. AMENDMENT TO THE APPLICATION The Country will notify the GAVI Alliance in its Annual Progress Report if it wishes to propose any change to the programme(s) description in its application. The GAVI Alliance will document any change approved by the GAVI Alliance, and the Country’s application will be amended. RETURN OF FUNDS The Country agrees to reimburse to the GAVI Alliance all funding amounts that are not used for the programme(s) described in its application. The country’s reimbursement must be in US dollars and be provided, unless otherwise decided by the GAVI Alliance, within sixty (60) days after the Country receives the GAVI Alliance’s request for a reimbursement and be paid to the account or accounts as directed by the GAVI Alliance. SUSPENSION/ TERMINATION The GAVI Alliance may suspend all or part of its funding to the Country if it has reason to suspect that funds have been used for purpose other than for the programmes described in the Country’s application, or any GAVI Alliance-approved amendment to the application. The GAVI Alliance retains the right to terminate its support to the Country for the programmes described in its application if a misuse of GAVI Alliance funds is confirmed. ANTICORRUPTION The Country confirms that funds provided by the GAVI Alliance shall not be offered by the Country to any third person, nor will the Country seek in connection with its application any gift, payment or benefit directly or indirectly that could be construed as an illegal or corrupt practice. AUDITS AND RECORDS The Country will conduct annual financial audits, and share these with the GAVI Alliance, as requested. The GAVI Alliance reserves the right, on its own or through an agent, to perform audits or other financial management assessment to ensure the accountability of funds disbursed to the Country. The Country will maintain accurate accounting records documenting how GAVI Alliance funds are used. The Country will maintain its accounting records in accordance with its government-approved accounting standards for at least three years after the date of last disbursement of GAVI Alliance funds. If there is any claims of misuse of funds, Country will maintain such records until the audit findings are final. The Country agrees not to assert any documentary privilege against the GAVI Alliance in connection with any audit. CONFIRMATION OF LEGAL VALIDITY The Country and the signatories for the Country confirm that its application, and Annual Progress Report, are accurate and correct and form legally binding obligations on the Country, under the Country’s law, to perform the programmes described in its application, as amended, if applicable, in the APR. CONFIRMATION OF COMPLIANCE WITH THE GAVI ALLIANCE TRANSPARANCY AND ACCOUNTABILITY POLICY The Country confirms that it is familiar with the GAVI Alliance Transparency and Accountability Policy (TAP) and complies with the requirements therein. USE OF COMMERCIAL BANK ACCOUNTS The Country is responsible for undertaking the necessary due diligence on all commercial banks used to manage GAVI cash-based support. The Country confirms that it will take all responsibility for replenishing GAVI cash support lost due to bank insolvency, fraud or any other unforeseen event. ARBITRATION Any dispute between the Country and the GAVI Alliance arising out of or relating to its application that is not settled amicably within a reasonable period of time, will be submitted to arbitration at the request of either the GAVI Alliance or the Country. The arbitration will be conducted in accordance with the then-current UNCITRAL Arbitration Rules. The parties agree to be bound by the arbitration award, as the final adjudication of any such dispute. The place of arbitration will be Geneva, Switzerland. The language of the arbitration will be English. For any dispute for which the amount at issue is US$ 100,000 or less, there will be one arbitrator appointed by the GAVI Alliance. For any dispute for which the amount at issue is greater than US $100,000 there will be three arbitrators appointed as follows: The GAVI Alliance and the Country will each appoint one arbitrator, and the two arbitrators so appointed will jointly appoint a third arbitrator who shall be the chairperson. The GAVI Alliance will not be liable to the country for any claim or loss relating to the programmes described in the application, including without limitation, any financial loss, reliance claims, any harm to property, or personal injury or death. Country is solely responsible for all aspects of managing and implementing the programmes described in its application.

# Application Specification

Please specify for which type of GAVI support you would like to apply to.

Important note: To enable proper functioning of the form, please first select the cMYP years on the previous page.

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Type of Support | Vaccine | Start Year | End Year | Preferred second presentation[1] | Action |
| --- | --- | --- | --- | --- | --- |
| New Vaccines Support | DTP-HepB-Hib, 10 doses/vial, Liquid | 2012 | 2016 |  |  |

[1] This "Preferred second presentation" will be used in case there is no supply available for the preferred presentation of the selected vaccine ("Vaccine" column). If left blank, it will be assumed that the country will prefer waiting until the selected vaccine becomes available.

# Table of Contents

Sections

Main

Cover Page

GAVI Alliance Grants Terms and Conditions

1. Application Specification

2. Table of Contents

3. Executive Summary

4. Signatures

4.1. Signatures of the Government and National Coordinating Bodies

4.1.1. Government and the Inter-Agency Coordinating Committee for Immunisation

4.1.2. National Coordinating Body - Inter-Agency Coordinating Committee for Immunisation

4.1.3. The Inter-Agency Coordinating Committee for Immunisation

4.2. National Immunization Technical Advisory Group for Immunisation

4.2.1. The NITAG Group for Immunisation

5. Immunisation Programme Data

5.1. Basic facts

5.2. Current vaccination schedule

5.3. Trends of immunisation coverage and disease burden

5.4. Baseline and Annual Targets

Table 1: baseline figures

5.5. Summary of current and future immunisation budget

5.6. Summary of current and future financing and sources of funds

6. NVS

6.1. Capacity and cost (for positive storage)

6.2. Assessment of burden of relevant diseases (if available)

6.3.1. Requested vaccine ( DTP-HepB-Hib, 10 doses/vial, Liquid )

6.3.2. Co-financing information

6.3.3. Wastage factor

6.3.4. Specifications of vaccinations with new vaccine

6.3.5. Portion of supply to be procured by the country (and cost estimate, US$)

6.3.6. Portion of supply to be procured by the GAVI Alliance (and cost estimate, US$)

6.3.7. New and Under-Used Vaccine Introduction Grant

7. Procurement and Management of New and Under-Used Vaccines

7.1. Vaccine management (EVSM/EVM/VMA)

8. Additional Comments and Recommendations

9. Annexes

Annex 1

Annex 1.1 - DTP-HepB-Hib, 10 doses/vial, Liquid

Table 1.1  A - Rounded up portion of supply that is procured by the country and estimate of related cost in US$

Table 1.1  B - Rounded up portion of supply that is procured by GAVI and estimate of related cost in US$.

Table 1.1  C - Summary table for vaccine DTP-HepB-Hib, 10 doses/vial, Liquid

Table 1.1  D - Estimated number of doses for vaccine DTP-HepB-Hib, 10 doses/vial, Liquid associated injection safety material and related co-financing budget

Annex 2

10. Attachments

10.1 Documents required for NVS support

10.2 Attachments

Banking Form

# Executive Summary

The GAVI Alliance has supported immunization services strengthening in Myanmar along with the introduction of a new vaccine i.e. Hepatitis B vaccine and provided support to injection safety equipment i.e. AD syringes and safety boxes since 2003. Hepatitis B vaccine was introduced in phases from 2003 to 2005. Hepatitis B3 coverage increased gradually, 62% in 2005, 75% in 2006, 84% in 2007, 85% in 2008 and finally 90% in 2009 

The phase 1 of GAVI support was implemented from 2002 to 2007. It included both ISS, NVS and injection safety support. Major activities supported by GAVI-ISS were training, micro planning, operational cost for outreach services, monitoring and supervision. Myanmar has received two rewards for increasing its immunization coverage during 2003-2004 and funds were utilized for strengthening EPI units at Central, States and Divisions level, supported supplementary immunization activities and catch-up campaigns in the country. Upgrading of the cold chain system at central store and sub-depots was done to expand the cold storage capacity. 

Myanmar has a well-functioning Inter-Agency Coordinating Committee(ICC) and regularly meets to review implementation plans and advise Department of Health on utilization of funds. Country has strong surveillance network monitored by Central Epidemiology Units with teams of Special Diseases Control Units stationed at States and Divisions, supported by a network of Regional surveillance Officers, Along with vaccine preventable diseases, principal epidemic diseases such as cholera (severe diarrhoea), dengue heamorrhagic fever, plague and other emerging infectious diseases, malaria, rabies and snake bites are diseases under national surveillance. Immunization Data Quality Audit was conducted in 2004 to verify the reporting system and Myanmar passed the DQA with the National Quality of the system index score is 78.8% for the year 2003. 

EPI in Myanmar has been reaching more and more beneficiaries since its inception in 1978 and recent reported data shows that it is reaching more that 85% of all beneficiaries with all antigens and 90% of beneficiaries with three doses of DTP vaccine. As a result of these efforts Myanmar is free from wild and vaccine derived poliovirus since 2007, and has recently been validated to have eliminated maternal and neonatal tetanus as a public health problem. Measles elimination strategies are being implemented in Myanmar and the incidence of this disease is also coming down both in numbers and geographic spread.

It is also observed that in the ten years period preceding the 2006 Fertility and Reproductive Health Ssurvey (FRHS), under-five mortality declined from 83.7/1,000 live births (1996) to 76.1/1,000 live births (2006) and Infant Mortality Rate declined from 70.3/1,000 live births (1996) to 68.3/1,000 live births. 

One unpublished postgraduate thesis done as part of M.Med Sc Paediatrics course in 1997 found that Haemophilus Influenzae type b contributed to 30% of all CSF proved Meningitis in hospitalized patients in Yangon.

A nationwide overall and cause-specific under-five mortality survey done in 2002-2003 by the Department of Health and UNICEF in Myanmar found that 73% of all under five deaths were in 0-11 month old infants and the rest in 1-4yr age group. During infancy 34% of the deaths occurred in the neonatal period out of which two thirds occurred during the first seven days of life. The major causes of mortality in the age group of 28 days to 5 years of age were Pneumonia 27.6%, Diarrhoea 17.6% and (Brain infections) , meningitis, encephalitis and cerebral malaria 17.1%.

In 2008 a study by Mo Mo Win et al on invasive pneumococcal infections in children done in Yangon Children's Hospital in 2006-07 found that approximately 31% of pathogens isolated from blood culture positive children with Pneumonia, Septicaemia and Meningitis were Haemophilus Influenzae 

Some studies during 2006-07 showed a prevalence of 14.7% in children admitted with meningitis/septicaemia/pneumonia. However these studies had limitations in the usefulness of methodologies used. 

The 2007 Annual Hospital Statistics Report for 2007 also shows that the single leading cause of mortality in under fives treated in hospitals were pneumonia 9.8% (Rank 1), septicemia.7.1% ( Rank 5) and meningitis 2.5%. These three causes contributed a total of 19% of all mortality in hospital treated cases.

The Central Epidemiology Unit is working on establishing a case based surveillance among under 5 children admitted for meningitis, severe pneumonia, and septicemia admitted to 2 major hospitals in the period of August to December 2010. The expected potential cases which may be admitted to the hospitals in this period will be around 1000. The endpoint of the study will be reached when the targeted number of cases are acquired. Three studies published in 1997, 2006 and 2007 studied the immunogenicity of the combination DPT- HepB+Hib vaccine in Myanmar and found that the vaccine induced high immunogenicity, One of the studies also concluded that there were indications of effective priming and presence of immune memory when a booster dose was given.

WHO official estimates for 2000 suggested that Myanmar had 3205 deaths and 96470 cases of Hib disease. The WHO position paper on Haemophilus Influenzae type b conjugate vaccines published in November 2006 also states that in view of their demonstrated safety and efficacy, conjugate Hib vaccines should be included in all routine infant immunization programmes because serious Hib disease occurs mainly in children aged between 4 months and 18 months. Amongst Myanmar's neighbours Bangladesh and Lao PDR have already introduced the vaccine.

In an effort to accelerate progress towards achieving MDG 4 targets, the Government of Myanmar plans to introduce Hib vaccine in combination with Hepatitis B and DPT . The existing high reported coverage of DPT 3, 90% in 2010 would enable the vaccine to have appropriate epidemiological impact and help reduce the burden of diseases contributing to under five morbidity and mortality. This introduction will also help to contribute towards strengthening of health systems through refresher training of health staff and regular supportive supervision. Delivering combined safe and efficacious vaccines to the beneficiaries will reinforce demand while reducing work burden on health staff.

The Government of Myanmar has committed to co-finance the vaccine with GAVI at a cost of 20 U.S. cents a dose each year as per Multi year immunization plan 2012-2016.

# Signatures

# Signatures of the Government and National Coordinating Bodies

# Government and the Inter-Agency Coordinating Committee for Immunisation

The Government of Myanmar would like to expand the existing partnership with the GAVI Alliance for the improvement of the infants routine immunisation programme of the country, and specifically hereby requests for GAVI support for DTP-HepB-Hib 10 doses/vial Liquid introduction.

The Government of Myanmar commits itself to developing national immunisation services on a sustainable basis in accordance with the Comprehensive Multi-Year Plan (cMYP) presented with this document. The Government requests that the GAVI Alliance and its partners contribute financial and technical assistance to support immunisation of children as outlined in this application.

Tables 6.(n).5. (where (n) depends on the vaccine) in the NVS section of this application shows the amount of support in either supply or cash that is required from the GAVI Alliance. Tables 6.(n).4. of this application shows the Government financial commitment for the procurement of this new vaccine (NVS support only).

Following the regulations of the internal budgeting and financing cycles the Government will annually release its portion of the co-financing funds in the month of .

Please note that this application will not be reviewed or approved by the Independent Review Committee (IRC) without the signatures of both the Minister of Health & Minister of Finance or their delegated authority.

Enter the family name in capital letters.

| Minister of Health (or delegated authority) |  | Minister of Finance (or delegated authority) |  |
| --- | --- | --- | --- |
| Name | HE Professor Dr Pe Thet Khin | Name | HE U Hla Tun |
| Date |  | Date |  |
| Signature |  | Signature |  |

This report has been compiled by

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

Enter the family name in capital letters.

| Full name | Position | Telephone | Email | Action |
| --- | --- | --- | --- | --- |
| Dr Dr Kyaw Kan Kaung | Project Manager EPI ( DOH) | + 95 67 421205; 420437 | kyawkankaungmo@gmail.com |  |

# National Coordinating Body - Inter-Agency Coordinating Committee for Immunisation

We the members of the ICC, HSCC, or equivalent committee[1] met on the 15.09.2011 to review this proposal. At that meeting we endorsed this proposal on the basis of the supporting documentation which is attached.

[1] Inter-agency Coordinating Committee or Health Sector Coordinating Committee, or equivalent committee which has the authority to endorse this application in the country in question.

The endorsed minutes of this meeting are attached as DOCUMENT NUMBER: 1.

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

Enter the family name in capital letters.

| Name/Title | Agency/Organisation | Signature | Action |
| --- | --- | --- | --- |

In case the GAVI Secretariat has queries on this submission, please contact

Enter the family name in capital letters.

| Name | Dr Kyaw Kan Kaung | Title | Project Manager EPI ( DOH) |
| --- | --- | --- | --- |
| Tel no | + 95 67 421205; 420437 |  |  |
| Fax no | + 95 67 421205 | Address | Department of Health, Ministry of Health, the Govt of the Republic of the Union Of Myanmar, NAYPYITAW |
| Email | kyawkankaungmo@gmail.com |  |  |

# The Inter-Agency Coordinating Committee for Immunisation

Agencies and partners (including development partners and NGOs) supporting immunisation services are co-ordinated and organised through an inter-agency coordinating mechanism (ICC, HSCC, or equivalent committee). The ICC, HSCC, or equivalent committee is responsible for coordinating and guiding the use of the GAVI NVS support. Please provide information about the ICC, HSCC, or equivalent committee in your country in the table below.

Profile of the ICC, HSCC, or equivalent committee

| Name of the committee | Inter Agency Coordinating Committee for Immunization |
| --- | --- |
| Year of constitution of the current committee | 2002-2003 |
| Organisational structure (e.g., sub-committee, stand-alone) | Stand alone |
| Frequency of meetings | At least 2-3 times per year and also need based more meetings in case of outbreaks, Special immunization activites etc |

Composition

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

Enter the family name in capital letters.

| Function | Title / Organisation | Name |  |
| --- | --- | --- | --- |
| Chair | DG DOH | Dr. Htun Naing Oo |  |
| Secretary | Director (Epidemiology), DOH | Dr Soe Lwin Nyein, |  |
| Members | Dy Director General, DOH | Dr. Saw Lwin | Action |
|  | Deputy Director(Epidemiology), DOH | Dr Than Htein Win, |  |
|  | Director(Finance), DoH | U Kyaw Htay |  |
|  | Program Manager (EPI),DOH | Dr. Kyaw Kan Kaung |  |
|  | Representative, UNICEF | Dr. Ramesh Shrestha |  |
|  | WHO Representative | Dr. H.S.B Tennakoon |  |
|  | Medical Officer, EPI , WHO | Dr. Vinod Kumar Bura |  |
|  | Chief, Young Child Survival and Development, UNICEF | Dr. Marinus Gotink |  |
|  | Director Planning DOH | Dr Nilar Tin |  |
|  | Director International Health Division | Dr Ko Ko Naing |  |
|  | DG Department of Health Planning | Dr Phone Myint |  |

Major functions and responsibilities of the committee

In Myanmar Inter-agency Coordinating Committees(ICC) have been formed to enhance coordination among partners in support of immunization programs and control of vaccine-preventable diseases. The following Major Functions are undertaken by the ICC 1) Leadership and active participation from the MOH to guide the EPI program . 2) Collective monitoring and evaluation of Immunization activities. 3) Input and assistance from other MOH departments ,UN agencies like WHO and UNICEF for appropriate decision-making for support and program continuity. This includes joint Collaboration , joint prioritization, the establishment of common goals and objectives, and harmonized work plans with MOH. 4) Resource mobilization internally as well as by donors 5) Review and Approve the GAVI supported activities 6) Review needs for SIA or other additional immunization activity. Coordinated Implementation and Monitoring 7) Review and endorse CEU plans for disease burden study, cold chain assessment, or New vaccine introduction , evaluations etc

Three major strategies to enhance the committee's role and functions in the next 12 months

| 1. | Formation of sub working groups on key programs with the intent of discussing and monitoring the plan, programme and providing specific inputs to the ICC. Update HSSC on EPI progress and challenges |
| --- | --- |
| 2. | Review Penta introduction, measles 2nd dose introduction progress . Annual joint meetings with the National Committee on Immunization practice. Review polio eradication progress, Measles elimination and other VPDs status |
| 3. | Expansion of the ICC membership by in corporating local representatives , UN organizations, bi laterals, and NGOs (National and International ) Professional bodies , supporting and working on EPI / child health in the country |

# National Immunization Technical Advisory Group for Immunisation

(If it has been established in the country)

We the members of the NITAG met on the to review this proposal. At that meeting we endorsed this proposal on the basis of the supporting documentation which is attached.

The endorsed minutes of this meeting are attached as DOCUMENT NUMBER: .

In case the GAVI Secretariat has queries on this submission, please contact

Enter the family name in capital letters.

| Name |  | Title |  |
| --- | --- | --- | --- |
| Tel no |  |  |  |
| Fax no |  | Address |  |
| Email |  |  |  |

# The NITAG Group for Immunisation

Profile of the NITAG

| Name of the NITAG | NOT APPLICABLE (NA) |
| --- | --- |
| Year of constitution of the current NITAG |  |
| Organisational structure (e.g., sub-committee, stand-alone) |  |
| Frequency of meetings |  |

Composition

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

Enter the family name in capital letters.

| Function | Title / Organisation | Name |  |
| --- | --- | --- | --- |
| Chair |  |  |  |
| Secretary |  |  |  |
| Members |  |  | Action |

Major functions and responsibilities of the NITAG

NA

Three major strategies to enhance the NITAG’s role and functions in the next 12 months

| 1. | NA |
| --- | --- |
| 2. | NA |
| 3. | NA |

# Immunisation Programme Data

Please complete the tables below, using data from available sources. Please identify the source of the data, and the date. Where possible use the most recent data and attach the source document.

- Please refer to the Comprehensive Multi-Year Plan for Immunisation (cMYP) (or equivalent plan) and attach a complete copy (with an Executive Summary) as DOCUMENT NUMBER 2

- Please refer to the two most recent annual WHO/UNICEF Joint Reporting Forms (JRF) on Vaccine Preventable Diseases.

- Please refer to Health Sector Strategy documents, budgetary documents, and other reports, surveys etc, as appropriate.

# Basic facts

For the year 2010 (most recent; specify dates of data provided)

|  | Figure |  | Year | Source |
| --- | --- | --- | --- | --- |
| Total population | 60,168,393 |  | 2010 | EPI, CSO |
| Infant mortality rate (per 1000) | 46 |  | 2009 | Myanmar Health Statistics 2010 |
| Surviving Infants[1] | 1,504,210 |  | 2010 | JRF, EPI 2010 |
| GNI per capita (US$) | 781 |  | 2011 | National Health Accounts,WHO |
| Total Health Expenditure (THE) as a percentage of GDP | 2.12 | % | 2009 | National Health Account Govt of Myanmar |
| General government expenditure on health (GGHE) as % of General government expenditure | 10.00 | % | 2010 | National Health Account,WHO |

[1] Surviving infants = Infants surviving the first 12 months of life

Please provide some additional information on the planning and budgeting context in your country; also indicate the name and date of the relevant planning document for health

National Health Policy - 1993 Myanmar Health Vision 2002----2030 is the over all guiding document National Health Plan 2006-2011, new National Health plan 2012-2016 is under process of formulation Hence the present c MYP was revised with a new document (cMYP 2012 to 2016 for EPI) so that this document is in line with the New national health plan 2012-2016

Is the cMYP (or updated Multi-Year Plan) aligned with this document (timing, content, etc.)?

The present cMYP is for the period 2007 -2011. Now a new c MPY ( which is attached as Annex 2) has been approved for the period of 2012-2016 which is in line with the new vaccine application and also aligned with the New National Health plan 2012-2016 The current cMYP 2007-2011 had set an Objective No 3 , Reduction in under five mortality and morbidity by 2016 by introduction of new and underused vaccine based on disease burden and cost effectiveness.

Please indicate the national planning budgeting cycle for health

MOH Annual budget plan is from April to March every year

Please indicate the national planning cycle for immunisation

MOH Annual work plan for immunization is from January to December

Please indicate if sex disaggregated data (SDD) is used in immunisation routine reporting systems

N

Please indicate if gender aspects relating to introduction of a new vaccine have been addressed in the introduction plan

All children irrespective of the Gender are being immunized by the National EPI program, It has been observed in VPD surveillance data that there is no significant difference in diseases among males and females. The country policy is to provide free Immunization services hence there is no barrier among males and female children. Even in birth registration there is no gender difference.

# Current vaccination schedule

Traditional, New Vaccines and Vitamin A supplement (refer to cMYP pages)

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Vaccine (do not use trade name) | Ages of administration (by routine immunisation services) | Given in entire country | Comments | Action |
| --- | --- | --- | --- | --- |
| BCG | 6 weeks | Yes |  |  |
| Polio | 6,10,14 weeks | Yes |  |  |
| DTP | 6,10,14 weeks | Yes |  |  |
| HepB | 6,10,14 weeks | Yes |  |  |
| Measles | 9 months | Yes | routine 2nd dose planned from 2012 |  |
| TT+ | First dose on first AN contact & Second dose after 4 weeks interval | Yes |  |  |
| HepB | within 24 hours of birth ( birth dose) | Yes | only for institution births which is around 8-10 % of annual birth cohort |  |
| Vitamin A | 6 months to 5 years | Yes | twice a year given nationally |  |

# Trends of immunisation coverage and disease burden

(as per last two annual WHO/UNICEF Joint Reporting Form on Vaccine Preventable Diseases)

| Trends of immunisation coverage (percentage) |  |  |  |  |  | Vaccine preventable disease burden |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Vaccine |  | Reported |  | Survey |  | Disease | Number of reported cases |  |
|  |  | 2009 | 2010 |  |  |  | 2009 | 2010 |
| BCG |  | 93 | 93 |  |  | Tuberculosis |  |  |
| DTP | DTP1 | 93 | 93 |  |  | Diphtheria | 19 | 4 |
|  | DTP3 | 90 | 90 |  |  | Pertussis | 3 | 0 |
| Polio 3 |  | 90 | 90 |  |  | Polio | 0 | 1 |
| Measles (first dose) |  | 87 | 88 |  |  | Measles | 217 | 190 |
| TT2+ (Pregnant women) |  | 87 | 86 |  |  | NN Tetanus | 34 | 19 |
| Hib3 |  |  |  |  |  | Hib[2] |  |  |
| Yellow Fever |  |  |  |  |  | Yellow fever |  |  |
| HepB3 |  | 90 | 90 |  |  | HepBsero-prevalence[1] |  |  |
| Vitamin A supplement Mothers (< 6 weeks post-delivery) |  |  |  |  |  |  |  |  |
| Vitamin A supplement Infants (>6 months) |  |  |  |  |  |  |  |  |

[1] If available

[2] Note: JRF asks for Hib meningitis

If survey data is included in the table above, please indicate the years the surveys were conducted, the full title and if available, the age groups the data refers to

No survey was undertaken , In the above table Polio: No wild polio virus reported but single case of P2 VDPV in Dec 2010.

# Baseline and Annual Targets

(refer to cMYP pages)

Table 1: baseline figures

| Number | Base Year | Baseline and Targets |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2010 | 2012 | 2013 | 2014 | 2015 | 2016 |  |
| Total births | 1,564,378 | 1,510,745 | 1,519,321 | 1,527,254 | 1,521,058 | 1,513,433 |  |
| Total infants' deaths | 60,168 | 55,898 | 54,696 | 51,927 | 50,195 | 46,916 |  |
| Total surviving infants | 1,504,210 | 1,454,847 | 1,464,625 | 1,475,327 | 1,470,863 | 1,466,517 |  |
| Total pregnant women | 1,624,547 | 1,586,282 | 1,580,093 | 1,588,344 | 1,566,689 | 1,558,836 |  |
| Number of infants vaccinated (to be vaccinated) with BCG | 1,401,203 | 1,404,993 | 1,412,968 | 1,450,891 | 1,445,005 | 1,437,761 |  |
| BCG coverage (%)[1] | 90% | 93% | 93% | 95% | 95% | 95% |  |
| Number of infants vaccinated (to be vaccinated) with OPV3 | 1,359,916 | 1,353,008 | 1,362,101 | 1,386,808 | 1,382,611 | 1,393,190 |  |
| OPV3 coverage (%)[2] | 90% | 93% | 93% | 94% | 94% | 95% |  |
| Number of infants vaccinated (or to be vaccinated) with DTP1[3] | 1,400,792 | 1,382,105 |  |  |  |  |  |
| Number of infants vaccinated (to be vaccinated) with DTP3[3] | 1,356,921 | 1,353,008 |  |  |  |  |  |
| DTP3 coverage (%)[2] | 90% | 93% | 0% | 0% | 0% | 0% |  |
| Wastage[1] rate in base-year and planned thereafter for DTP (%) | 45% | 30% |  |  |  |  |  |
| Wastage[1] factor in base-year and planned thereafter for DTP | 1.82 | 1.43 | 0 | 0 | 0 | 0 |  |
| Infants vaccinated (to be vaccinated) with 1st dose of HepB and/or Hib |  | 669,070 | 1,392,037 | 1,417,287 | 1,412,998 | 1,423,810 |  |
| Infants vaccinated (to be vaccinated) with 3rd dose of HepB and/or Hib |  | 654,681 | 1,362,101 | 1,386,808 | 1,382,611 | 1,393,190 |  |
| HepB and/or Hib 3rd dose coverage (%)[2] | 0% | 45% | 93% | 94% | 94% | 95% |  |
| Infants vaccinated (to be vaccinated) with 1st dose of Measles | 1,328,383 | 1,309,363 | 1,332,809 | 1,357,301 | 1,367,902 | 1,378,525 |  |
| Measles coverage (%)[2] | 88% | 90% | 91% | 92% | 93% | 94% |  |
| Pregnant women vaccinated with TT+ | 1,397,499 | 1,427,654 | 1,437,885 | 1,461,277 | 1,457,021 | 1,465,305 |  |
| TT+ coverage (%)[4] | 86% | 90% | 91% | 92% | 93% | 94% |  |
| Vit A supplement to mothers within 6 weeks from delivery |  |  |  |  |  |  |  |
| Vit A supplement to infants after 6 months |  |  |  |  |  |  |  |
| Annual DTP Drop-out rate[ ( DTP1 - DTP3 ) / DTP1 ] x 100[5] | 3% | 2% | 0% | 0% | 0% | 0% |  |

[1] Number of infants vaccinated out of total births

[2] Number of infants vaccinated out of total surviving infants

[3] Indicate total number of children vaccinated with either DTP alone or combined

[4] Number of pregnant women vaccinated with TT+ out of total pregnant women

[5] The formula to calculate a vaccine wastage rate (in percentage):[ ( A – B ) / A ] x 100. Whereby: A = the number of doses distributed for use according to the supply records with correction for stock balance at the end of the supply period; B = the number of vaccinations with the same vaccine in the same period.

# Summary of current and future immunisation budget

(or refer to cMYP pages)

|  | Estimated costs per annum in US$ (in thousand US$) |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Cost category | Base Year | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |  |
|  | 2010 | 2012 | 2013 | 2014 | 2015 | 2016 |  |  |  |  |
| Routine Recurrent Cost |  |  |  |  |  |  |  |  |  |  |
| Vaccines (routine vaccines only) | 2,507,241 | 9,041,011 | 12,778,050 | 11,499,326 | 11,168,602 | 11,112,598 |  |  |  |  |
| Traditional vaccines | 2,507,241 | 2,787,216 | 2,236,124 | 2,089,501 | 2,063,540 | 1,905,079 |  |  |  |  |
| New and underused vaccines |  | 6,253,795 | 10,541,926 | 9,409,825 | 9,105,062 | 9,207,519 |  |  |  |  |
| Injection supplies | 415,504 | 1,269,276 | 1,290,124 | 1,285,331 | 1,299,269 | 1,330,260 |  |  |  |  |
| Personnel | 505,927 | 1,497,674 | 1,527,627 | 1,558,179 | 1,589,343 | 1,621,130 |  |  |  |  |
| Salaries of full-time NIP health workers (immunisation specific) | 12,185 | 65,214 | 66,518 | 67,848 | 69,205 | 70,589 |  |  |  |  |
| Per-diems for outreach vaccinators / mobile teams | 493,742 | 1,432,460 | 1,461,109 | 1,490,331 | 1,520,138 | 1,550,541 |  |  |  |  |
| Transportation | 156,309 | 75,589 | 77,154 | 78,757 | 80,305 | 68,353 |  |  |  |  |
| Maintenance and overheads | 429,499 | 2,243,040 | 2,317,522 | 2,382,701 | 2,524,006 | 2,594,074 |  |  |  |  |
| Training | 42,473 | 616,384 | 632,280 | 648,294 | 658,577 | 668,381 |  |  |  |  |
| Social mobilisation and IEC | 21,766 | 770,480 | 790,351 | 810,367 | 823,221 | 835,476 |  |  |  |  |
| Disease surveillance | 393,000 | 1,540,960 | 1,580,701 | 1,620,734 | 1,646,442 | 1,646,442 |  |  |  |  |
| Program management |  | 255,000 | 260,100 | 318,362 | 324,730 | 331,224 |  |  |  |  |
| Other | 3,446 | 0 | 0 | 0 | 0 | 0 |  |  |  |  |
| Subtotal Recurrent Costs | 4,475,165 | 17,309,414 | 21,253,909 | 20,202,051 | 20,114,495 | 20,207,938 |  |  |  |  |
| Routine Capital Costs |  |  |  |  |  |  |  |  |  |  |
| Vehicle | 0 | 30,896 | 31,732 | 32,590 | 332,411 | 33,906 |  |  |  |  |
| Cold chain equipment | 167,134 | 3,875,495 | 4,056,865 | 3,281,354 | 3,385,449 | 3,492,334 |  |  |  |  |
| Other capital equipment | 11,774 | 742,295 | 742,295 | 742,295 | 742,295 | 742,295 |  |  |  |  |
| Subtotal Capital Costs | 178,908 | 4,648,686 | 4,830,892 | 4,056,239 | 4,460,155 | 4,268,535 |  |  |  |  |
| Campaigns |  |  |  |  |  |  |  |  |  |  |
| Polio | 1,268,591 | 2,112,248 | 4,465,589 | 4,618,084 | 0 | 0 |  |  |  |  |
| Measles | 0 | 7,941,242 | 0 |  |  | 4,646,059 |  |  |  |  |
| Yellow Fever | 0 | 0 | 0 | 0 |  | 0 |  |  |  |  |
| MNT campaigns | 50,000 | 693,812 | 0 | 720,598 | 0 | 748,474 |  |  |  |  |
| Other campaigns |  |  |  |  |  |  |  |  |  |  |
| Subtotal Campaign Costs | 1,318,591 | 10,747,302 | 4,465,589 | 5,338,682 | 0 | 5,394,533 |  |  |  |  |
| GRAND TOTAL | 5,972,664 | 32,705,402 | 30,550,390 | 29,596,972 | 24,574,650 | 29,871,006 |  |  |  |  |

# Summary of current and future financing and sources of funds

Please list in the tables below the funding sources for each type of cost category (if known). Please try and indicate which immunisation program costs are covered from the Government budget, and which costs are covered by development partners (or the GAVI Alliance), and name the partners (or refer to cMYP).

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

|  |  | Estimated costs per annum in US$ (in thousand US$) |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Cost category | Funding source | Base Year | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |  |
|  |  | 2010 | 2012 | 2013 | 2014 | 2015 | 2016 |  |  |  |  |
| Routine Recurrent Cost |  |  |  |  |  |  |  |  |  |  |  |
| Personal,Transportation,Maintainance Overhead, cold chain | Government | 68,050 | 2,257,593 | 2,352,225 | 2,403,800 | 2,600,141 | 2,651,575 |  |  |  |  |
| Tradational Vaccine,Injection supplies,cold chain maintenance&OverHead, Short Term Training, IEC , Social Mobilization | UNICEF | 1,960,000 | 2,401,305 | 2,407,972 | 2,411,880 | 2,426,070 | 2,201,613 |  |  |  |  |
| Training, Social Mobilization,Disease Surveillance, Programme Management | WHO | 120,000 | 926,750 | 774,750 | 756,500 | 754,000 | 754,000 |  |  |  |  |
| New & Underused Vaccine, | GAVI | 0 | 5,073,780 | 8,881,761 | 7,864,215 | 7,563,695 | 7,636,040 |  |  |  |  |
| Vaccine ( penta) | Government Cofinancing | 0 | 654,681 | 1,276,970 | 1,014,737 | 975,961 | 985,295 |  |  |  |  |
| Others cost | Donors / partners | 400,000 | 0 | 34,291 | 0 | 28,553 | 0 |  |  |  |  |
| Vaccine introduction grant ( measles) | GAVI |  | 453,000 |  |  |  |  |  |  |  |  |
|  | GAVI ISS reward through WHO | 200,000 | 1,300,000 | 1,100,000 |  |  |  |  |  |  |  |
| Routine Capital Costs |  |  |  |  |  |  |  |  |  |  |  |
| Vehicle, cold chain Equipment | GAVI |  | 160,000 | 0 | 0 | 0 | 0 |  |  |  |  |
| Other Capital cost | Government | 7,149 | 0 | 0 | 0 | 0 | 0 |  |  |  |  |
|  | UNICEF | 250,000 | 0 | 0 | 0 | 0 | 0 |  |  |  |  |
| Campaigns |  |  |  |  |  |  |  |  |  |  |  |
| Polio,Measles ,TT | DONORS / UNF |  | 10,747,302 | 4,465,589 | 5,338,683 | 4,646,059 | 748,473 |  |  |  |  |
| GRAND TOTAL |  | 3,005,199 | 23,974,411 | 21,293,558 | 19,789,815 | 18,994,479 | 14,976,996 |  |  |  |  |

# New and Under-Used Vaccines (NVS)

Please summarise the cold chain capacity and readiness to accommodate new vaccines, stating how the cold chain expansion (if required) will be financed, and when it will be in place. Please indicate the additional cost, if capacity is not available and the source of funding to close the gap.

Myanmar has good storage network of cold stores and cold room or sub-depot 20 in number in different part of the country. Recently in 2008 the new central cold room was built and the facility consists of 3 cooler room and 4 freezer rooms. Expansion of cold chain system network was planned and to be implemented very soon in 2009 to build hybrid solar system in seven sub-depots and one facility in one populous hilly region will accommodate walk in cooler and freezer room. The storage capacity at the intermediate levels is ensured. The funding for those new facilities will be funded jointly by UNICEF-WHO funding sources.

Please give a summary of the cMYP sections that refer to the introduction of new and under-used vaccines. Outline the key points that informed the decision-making process (data considered etc)

Under the main strategy of "Introducing New vaccines and Technology", the Objective 3 in c myp 2012- 2016 is to "Introduce Haemophilus Influenzae type B (Hib) vaccine" as a pentavalent combination with DPT and Hepatitis B vaccines in the EPI programme with a aim to reduce under 5 morbidity and mortality in the country and accelerate the movement towards achieving MDG goals. It was also observed that in the ten years period preceding the 2006 FRHS, under-five mortality declined from 83.7/1,000 live births (1996) to 76.1/1,000 live births (2006) and Infant Mortality Rate declined from 70.3/1,000 live births (1996) to 68.3/1,000 live births. The rapid decline in under-five mortality rates and infant mortality rates have subsequently slowed down. One unpublished postgraduate thesis done as part of M.Med Sc Paediatrics course in 1997 found that Haemophilus Influenza type b contributed to 30% of all CSF of meningitis cases in hospitalized patients in Yangon. A nationwide overall and Cause Specific under five Mortality survey done in 2002-2003 by the Department of Health and UNICEF in Myanmar found that 73% of all under five deaths were in 0-11 month old infants and the rest in 1-4yr age group. During infancy 34% of the deaths occurred in Neonatal period out of which two thirds occurred during first seven days of life. The major causes of mortality in the age group of 28 days to 5 years of age were pneumonia 27.6%, diarrhoea 17.6% and meningitis/encephalitis 17.1%. In 2008 a study by Mo Mo Win et al on Invasive Pneumococcal Infection in children done in Yangon children hospital in 2006-07 found that approximately 31% of pathogens isolated from blood culture positive children with pneumonia, septicaemia and meningitis were Haemophilus Influenzae ( no sub typing done) The 2007 Annual hospital statistics report for 2007 shows that the single leading cause of mortality in under fives treated in hospitals were pneumonia 9.8%(Rank 1), septicemia.7.1% ( Rank 5) and meningitis 2.5% . These three causes contributed a total of 19% of all mortality in hospital treated cases. The Central epidemiology Unit is working on establishing a case based surveillance among under 5 children admitted for meningitis, Severe Pneumonia, and Septicemia admitted to 2 major hospitals in the period of August to December 2010. The expected potential cases which may be admitted to the hospitals in this period will be around 1000. The endpoint of the study will be reached when the targeted number of cases are acquired.WHO official estimates for 2000 suggested that Myanmar had 3205 deaths and 96470 cases of Hib disease The WHO position paper on Haemophilus Influenzae type b conjugate vaccines published in November 2006 also states that Haemophilus Influenzae type b (Hib) is estimated to cause at least 3 million cases of serious disease every year as well as approximately 386 000 deaths. It also says that in view of their demonstrated safety and efficacy, conjugate Hib vaccines should be included in all routine infant immunization programmes because serious Hib disease occurs mainly in children aged between 4 months and 18 months. Amongst Myanmar's neighbours Bangladesh and Lao PDR have already introduced the vaccine. In an effort to accelerate progress towards achieving MDG 4 targets , Government of Myanmar plans to introduce Hib vaccine in combination with Hepatitis B and DPT in the country. The existing high coverages would enable the vaccine to have appropriate epidemiological impact and help reduce the burden of diseases contributing , Under five morbidity and mortality. This introduction will also help to contribute towards strengthening of Health systems focussed towards reaching safe and efficacious vaccines to the beneficiaries with equity Three studies published in 1997, 2006 and 2007 studied the immunogenicity of the combination DPT- HepB+Hib vaccine in Myanmar and found that the vaccine induced high immunogenicity , one of the studies also concluded that there were indications of effective priming and presence of immune memory when booster dose was given. All the above available information justify the decision on introduction of conjugate Hib vaccine in the country EPI from 2012 .

# Capacity and cost (for positive storage)

|  |  | Formula | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2012 | 2013 | 2014 | 2015 | 2016 |  |  |  |
| A | Annual positive volume requirement, including new vaccine (litres or m3) m3 | Sum-product of total vaccine doses multiplied by unit packed volume of the vaccine | 44 | 45 | 45 | 45 | 45 |  |  |  |
| B | Existing net positive cold chain capacity (litres or m3) m3 | # | 86 | 86 | 86 | 86 | 86 |  |  |  |
| C | Estimated minimum number of shipments per year required for the actual cold chain capacity | A / B | 1 | 1 | 1 | 1 | 1 |  |  |  |
| D | Number of consignments / shipments per year | Based on national vaccine shipment plan | 4 | 4 | 4 | 4 | 4 |  |  |  |
| E | Gap (if any) | ((A / D) - B) | -75 | -75 | -75 | -75 | -75 |  |  |  |
| F | Estimated additional cost of cold chain | US$ | 0 | 0 | 0 | 0 | 0 |  |  |  |

Please briefly describe how your country plans to move towards attaining financial sustainability for the new vaccines you intend to introduce, how the country will meet the co-financing payments, and any other issues regarding financial sustainability you have considered (refer to the cMYP)

Mobilizing of the fund for the country programme in the next multiyear plan period will be made through traditional and new partners. All efforts will be made to leverage GAVI resources to facilitate introduction of new and underused vaccines like Measles second dose, Hib, Pneumococcal, and Rotavirus in the country programme. These activities would focus on mobilizing resources to close the identified gap. As Myanmar has manufacturing capacities for TT and Hepatitis B vaccines there would be a need to start a “vaccine sufficiency initiative” so that over a period of time the country can try to become self-reliant in a some traditional vaccines so that the resources saved could be used to support or co-finance other high value vaccines. The program as part of its regular monitoring process, will monitor the trends in financing, to ensure it is moving towards improved financial sustainability by reducing its financing gaps, and converting more probable financing to secure financing. Indicators for financial sustainability that the program will use include: • % of funding gaps to total program needs for the period of cMYP • % total program costs financed by in country sources of financing • % of total program costs financed by Government

# Assessment of burden of relevant diseases (if available)

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Disease | Title of the assessment | Date | Results |  |
| --- | --- | --- | --- | --- |
| Meningitis | Study on the Role of antigen detection in diagnosis of Acute Meningitis- Masters of Medical Science Thesis for Paediatrics , Ins | 1997 | 220 clinically suspected meningitis cases were subjected to CSF examination out of which 50 showed signs of meningitis and these were subjected to latex agglutination tests for antigen detection. Of the 50 cases, 30% of the cases were found to be due to H Influenzae, type B 40% due to N meningitidis and 22% to Strep pneumoniae.in latex agglutination test |  |
| Invasive Pneumococcal Infection | Invasive Pneumococcal Infection in Children-Paper presented in Myanmar Health Research Congress-Deptt Of Medical Research (Lower | 2006-2007 | Blood samples of 150 children collected (Pneumonia 110, Septicaemia 22, and Meningitis 18 cases). Age range 2-12 months.70 samples (46.6%) yielded bacterial pathogen growth. Streptococcus pneumoniae 12(17.14%), Haemophilus influenzae , isolates were not typed , 22( 31.43%), Pseudomonas aeruginosa 12(17.14%),Staphylococcus aureus 12(17.14%), E Coli 6 (8.57%), Klebsiella pneumoniae 4(5.71%) and Neisseria meningitidis 2(2.86%) |  |

If new or under-used vaccines have already been introduced in your country, please give details of the lessons learned from storage capacity, protection from accidental freezing, staff training, cold chain, logistics, drop-out rate, wastage rate etc., and suggest action points to address them

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Lessons Learned | Action Points |  |
| --- | --- | --- |
| 1. Storage capacity : Myanmar introduced Hepatitis B vaccine in 2003,2004 and 2005 in a phased manner for the whole country. It received 1 dose and 6 doses vials for the hospital birth dose (15 % of the target infants) and community immunization respectively. To cope up the introduction of new vaccine and its volume load a new set of walk-in cold rooms at the central level in Yangon, one set in Mandalay for the upper Myanmar and another set in Magway Division were installed. Hep B vaccines are stored in one specific WIC adjusted to 4-6 celsius degree at central cold room. 2. Protection from accidental freezing: Alarm systems and temperature recording system was installed to the Walk in cooler and cold chain engineer deputed to take temperature measurements twice a day . Conditioning of frozen ice-packs was done before packing the Hep B vaccines in the cold boxes for transport. 3. Staff training: Hep B vaccine introduction handbooks were developed and used in staff training in all levels. 4. Wastage rate: To reduce wastage rate, 1 dose vials for birth doses we ordered for big hospitals with child delivery facilities and pediatricians. 6 doses vials were used for community outreach immunization activities. | Cold chain capacity assessment prior to introduction of the new vaccine Electronic tools for monitoring Cold chain to be installed and cold chain engineers trained to use them. Retraining of Staff on the New vaccine, AEFI surveillance to be strengthed, Proper microplanning, logistics and supply planning would enable to keep vaccine wastage low. |  |

Please list the vaccines to be introduced with support from the GAVI Alliance (and presentation)

1) DPT-Hep B-Hib vaccine in 10 dose presentation is requested This is with a view to reduce waste rates in low density settings sessions, experaince of 20 dose DPT Vial suggests to have high wastage, Although Cold chain capacity at national and sub national level is adequate there may be shortages of CC at township level if 2 dose vial is used

# 6.3.1. Requested vaccine ( DTP-HepB-Hib, 10 doses/vial, Liquid )

As reported in the cMYP, the country plans to introduce DTP-HepB-Hib, 10 doses/vial, Liquid vaccine.

# 6.3.2. Co-financing information

If you would like to co-finance higher amount than minimum, please overwrite information in the “Your co-financing” row.

Note: Selection of this field has direct impact on automatic calculations of support you are requesting and should not be left empty.

| Country group | Low |
| --- | --- |

|  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2012 | 2013 | 2014 | 2015 | 2016 |  |  |  |
| Minimum co-financing | 0.20 | 0.20 | 0.20 | 0.20 | 0.20 |  |  |  |
| Your co-financing (please change if higher) | 0.20 | 0.20 | 0.20 | 0.20 | 0.20 |  |  |  |

# 6.3.3. Wastage factor

Please indicate wastage rate:

Countries are expected to plan for a maximal wastage rate of:

- 50% - for a lyophilised vaccine in 10 or 20-dose vial,

- 25% - for a liquid vaccine in 10 or 20-dose vial or a lyophilised vaccine in 5-dose vial,

- 10% - for a lyophilised/liquid vaccine in 2-dose vial, and

- 5% - for a liquid vaccine in 1-dose vial

Note: Selection of this field has direct impact on automatic calculations of support you are requesting and should not be left empty.

|  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2012 | 2013 | 2014 | 2015 | 2016 |  |  |  |
| Vaccine wastage rate in % | 25% | 20% | 20% | 15% | 15% |  |  |  |
| Equivalent wastage factor | 1.33 | 1.25 | 1.25 | 1.18 | 1.18 |  |  |  |

# 6.3.4. Specifications of vaccinations with new vaccine

|  | Data from |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2012 | 2013 | 2014 | 2015 | 2016 |  |  |  |
| Number of children to be vaccinated with the first dose | Table 1 | # | 669,070 | 1,392,037 | 1,417,287 | 1,412,998 | 1,423,810 |  |  |  |
| Number of children to be vaccinated with the third dose[1] | Table 1 | # | 654,681 | 1,362,101 | 1,386,808 | 1,382,611 | 1,393,190 |  |  |  |
| Immunisation coverage with the third dose | Table 1 | # | 45.00% | 93.00% | 94.00% | 94.00% | 95.00% |  |  |  |
| Estimated vaccine wastage factor | Table 6.(n).3[3] | # | 1.33 | 1.25 | 1.25 | 1.18 | 1.18 |  |  |  |
| Country co-financing per dose[2] | Table 6.(n).2[3] | $ | 0.20 | 0.20 | 0.20 | 0.20 | 0.20 |  |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Total price per-dose includes vaccine cost, plus freight, supplies, insurance, visa costs etc.

[3] Where (n) depends on the vaccine

# 6.3.5. Portion of supply to be procured by the country (and cost estimate, US$)

|  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2012 | 2013 | 2014 | 2015 | 2016 |  |  |  |
| Number of vaccine doses | # | 255,200 | 476,000 | 494,400 | 506,100 | 510,900 |  |  |  |
| Number of AD syringes | # | 227,100 | 434,200 | 439,500 | 476,100 | 480,800 |  |  |  |
| Number of re-constitution syringes | # |  |  |  |  |  |  |  |  |
| Number of safety boxes | # | 2,525 | 4,825 | 4,900 | 5,300 | 5,350 |  |  |  |
| Total value to be co-financed by country | $ | 667,500 | 1,172,000 | 1,068,000 | 1,000,500 | 1,010,000 |  |  |  |

# 6.3.6. Portion of supply to be procured by the GAVI Alliance (and cost estimate, US$)

|  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2012 | 2013 | 2014 | 2015 | 2016 |  |  |  |
| Number of vaccine doses | # | 3,081,800 | 5,381,900 | 4,844,200 | 4,496,000 | 4,539,000 |  |  |  |
| Number of AD syringes | # | 2,741,800 | 4,909,200 | 4,306,400 | 4,229,300 | 4,271,200 |  |  |  |
| Number of re-constitution syringes | # |  |  |  |  |  |  |  |  |
| Number of safety boxes | # | 30,450 | 54,500 | 47,800 | 46,950 | 47,425 |  |  |  |
| Total value to be co-financed by GAVI | $ | 8,060,000 | 13,247,500 | 10,463,000 | 8,888,500 | 8,973,500 |  |  |  |

# 6.3.7. New and Under-Used Vaccine Introduction Grant

Please indicate in the tables below how the one-time Introduction Grant[1] will be used to support the costs of vaccine introduction and critical pre-introduction activities (refer to the cMYP).

Calculation of lump-sum for the DTP-HepB-Hib, 10 doses/vial, Liquid

If the total is lower than US$100,000, it is automatically rounded up to US$100,000

| Year of New Vaccine Introduction | Births (from Table 1) | Share per Birth in US$ | Total in US$ |
| --- | --- | --- | --- |
| 2012 | 1,510,745 | 0.30 | 453,500 |

[1] The Grant will be based on a maximum award of $0.30 per infant in the birth cohort with a minimum starting grant award of $100,000

Cost (and finance) to introduce the DTP-HepB-Hib, 10 doses/vial, Liquid (US$)

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Cost Category | Full needs for new vaccine introduction in US$ | Funded with new vaccine introduction grant in US$ |  |
| --- | --- | --- | --- |
| Training | 428,000 | 175,000 |  |
| Social Mobilization, IEC and Advocacy | 137,500 | 125,000 |  |
| Cold Chain Equipment & Maintenance | 50,000 | 50,000 |  |
| Vehicles and Transportation | 44,000 | 10,000 |  |
| Programme Management | 184,000 | 50,000 |  |
| Surveillance and Monitoring | 10,000 | 10,000 |  |
| Human Resources | 10,000 | 8,500 |  |
| Waste Management | 5,000 | 5,000 |  |
| Technical assistance | 20,000 | 20,000 |  |
| Totals | 888,500 | 453,500 |  |

# Procurement and Management of New and Under-Used Vaccines

Note: The PCV vaccine must be procured through UNICEF

- Please show how the support will operate and be managed including procurement of vaccines (GAVI expects that most countries will procure vaccine and injection supplies through UNICEF)

All Procurement of the Penta Valent vaccine will be done through UN supplies, through UNICEF Myanmar as for routine immunization. The support will be managed overall by the Interagency coordination committee(ICC).

- If an alternative mechanism for procurement and delivery of supply (financed by the country or the GAVI Alliance) is requested, please document

- Other vaccines or immunisation commodities procured by the country and descriptions of the mechanism used.

- The functions of the National Regulatory Authority (as evaluated by WHO) to show they comply with WHO requirements for procurement of vaccines and supply of assured quality.

NA

- Please describe the introduction of the vaccines (refer to cMYP)

The vaccine would replace DPT and Hepatitis B vaccines in the national Immunization schedule and the high coverages of these antigens would help in promoting uptakes of this vaccine sooner than later. The introduction would be preceded by a EVM assessment and subsequent strengthening of capacity of the men and materials as required. The service delivery would be strengthened to minimize wastage by proper microplanning and ensuring efficient logistics management. social mobilization and advocacy activities would be conducted. Wastage will also be reduced as the penta will be in 10 dose vial presentation compaired to 20 dose of the existing DPT vaccine. It is planned that the new vaccine would be introduced in 2012 in one go in the country starting 1st July 2012.. Detailed introduction plan attached

- Please indicate how funds should be transferred by the GAVI Alliance (if applicable)

Intordction grant fund should be transferred through WHO country office Myanmar , Yangon as being done for ISS .

- Please indicate how the co-financing amounts will be paid (and who is responsible for this)

Department of Health will request the annual co-financing amount to Ministry of Finance. The fund will be transferred to UNICEF supply division thruogh UNICEF Country office.

- Please outline how coverage of the new vaccine will be monitored and reported (refer to cMYP)

Immunization cards and health facility tally sheets, registers, monitoring charts, stock management forms, etc will be revised to include the pentavalent vaccine and staff will be trained to record and calculate the vaccine , benificeries target and coverage correctly. Monthly coverages from lowest reporting units, at subcenter level, will be collected using a revised standard reporting format. The township medical offices will compile coverage and other data such as vaccine wastage, AD syringes safetly boxes etc and send to the State/Regional level, where data are compiled through the Health Management Information System. HMIS State/regional level data are then transferred to the Department of Health Planning and Central EPI Unit on a quarterly . Township and State/Regional level data are also compiled by Special Disease Control Units team leaders and Regional Surveillance Officer. In addition to this at township level there are monthly reviews of coverage levels by TMO. At state level quarterly and at national level 6-monthly review meetings will be conducted to review progress and address constraints and challenges. Special review meeting will be done at all states and twice at nationa level in first year of introduction to ensure smooth introduction and address and shortfalls Periodic monthly monitoring will be done locally by TMO, Special Disease Control units staff in their respective areas. The MOH central level will also draw monthly monitoring plans/ visits for Hard to Reach Aarea. VPD surveillance data will be reviewed along with immunization coverage data, burden of disease data etc.

# Vaccine Management (EVSM/EVM/VMA)

When was the last Effective Vaccine Store Management (EVSM) conducted? July   - 2004

When was the last Effective Vaccine Management (EVM) or Vaccine Management Assessment (VMA) conducted? August  - 2011

- If your country conducted either EVSM, EVM, or VMA in the past three years, please attach relevant reports. (Document N°3)

- A VMA report must be attached from those countries which have introduced a New and Underused Vaccine with GAVI support before 2008.

- Please note that EVSM and VMA tools have been replaced by an integrated Effective Vaccine Management (EVM) tool. The information on EVM tool can be found at http://www.who.int/immunization_delivery/systems_policy/logistics/en/index6.html

- For countries which conducted EVSM, VMA or EVM in the past, please report on activities carried out as part of either action plan or improvement plan prepared after the EVSM/VMA/EVM.

EVM study shows there is adequate cold chain in place at nationasl abs sub national levels to introduce Penta valent. Some of the key recomendations of EVM which is being planned are -Temperature study is planned to conduct in 2012 second hlaf by UNICEF Support. -New generation temperature monitoring devices has been procured and will be installed at Central Cold store , sub-depots and township level cold rooms. -Training for cold chain key persons has been planned to conduct in Q1 2012. SOP betweem Custom, cental cold store, supply depts etc will be revised and in place by Q2 Further details of program improvment in relation to Cold chain are enclosed in the Cold Chain improvement plan doc attach 4

- When is the next Effective Vaccine Management (EVM) Assessment planned? July   - 2014

- Under new guidelines, it will be mandatory for the countries to conduct an EVM prior to an application for introduction of new vaccine.

# Additional Comments and Recommendations

Comments and Recommendations from the National Coordinating Body (ICC/HSCC)

ICC met in Sept 2011 and endorsed this penta proposal with a commitment of co- finiancing from GOM , also Intorduction plans ,and cold chain improvment plans have been prepared and are being implemented. ICC will review the progress made in preparation for introduction of Penta in Q1

# Annexes

# Annex 1

# Annex 1.1 – DTP-HepB-Hib, 10 doses/vial, Liquid

Table 1.1 A - Rounded up portion of supply that is procured by the country and estimate of related cost in US$

| Required supply item |  | 2012 | 2013 | 2014 | 2015 | 2016 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of vaccine doses | # | 255,200 | 476,000 | 494,400 | 506,100 | 510,900 |  |  |  |
| Number of AD syringes | # | 227,100 | 434,200 | 439,500 | 476,100 | 480,800 |  |  |  |
| Number of re-constitution syringes | # |  |  |  |  |  |  |  |  |
| Number of safety boxes | # | 2,525 | 4,825 | 4,900 | 5,300 | 5,350 |  |  |  |
| Total value to be co-financed by the country | $ | 667,500 | 1,172,000 | 1,068,000 | 1,000,500 | 1,010,000 |  |  |  |

Table 1.1  B - Rounded up portion of supply that is procured by GAVI and estimate of related cost in US$.

| Required supply item |  | 2012 | 2013 | 2014 | 2015 | 2016 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of vaccine doses | # | 3,081,800 | 5,381,900 | 4,844,200 | 4,496,000 | 4,539,000 |  |  |  |
| Number of AD syringes | # | 2,741,800 | 4,909,200 | 4,306,400 | 4,229,300 | 4,271,200 |  |  |  |
| Number of re-constitution syringes | # |  |  |  |  |  |  |  |  |
| Number of safety boxes | # | 30,450 | 54,500 | 47,800 | 46,950 | 47,425 |  |  |  |
| Total value to be co-financed by the country | $ | 8,060,000 | 13,247,500 | 10,463,000 | 8,888,500 | 8,973,500 |  |  |  |

Table 1.1  C - Summary table for DTP-HepB-Hib, 10 doses/vial, Liquid

|  | Data from |  | 2012 | 2013 | 2014 | 2015 | 2016 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of Surviving infants | Table 1 | # | 1,454,847 | 1,464,625 | 1,475,327 | 1,470,863 | 1,466,517 |  |  |  |
| Number of children to be vaccinated with the third dose[1] | Table 1 | # | 654,681 | 1,362,101 | 1,386,808 | 1,382,611 | 1,393,190 |  |  |  |
| Immunisation coverage with the last dose | Table 1 | # | 45.00% | 93.00% | 94.00% | 94.00% | 95.00% |  |  |  |
| Number of children to be vaccinated with the first dose | Table 1 | # | 669,070 | 1,392,037 | 1,417,287 | 1,412,998 | 1,423,810 |  |  |  |
| Number of doses per child |  | # | 3 | 3 | 3 | 3 | 3 |  |  |  |
| Estimated vaccine wastage factor | Table 6.(n).3[2] | # | 1.33 | 1.25 | 1.25 | 1.18 | 1.18 |  |  |  |
| Number of doses per vial |  | # | 10 | 10 | 10 | 10 | 10 |  |  |  |
| AD syringes required |  | # | Yes | Yes | Yes | Yes | Yes |  |  |  |
| Reconstitution syringes required |  | # | No | No | No | No | No |  |  |  |
| Safety boxes required |  | # | Yes | Yes | Yes | Yes | Yes |  |  |  |
| Vaccine price per dose |  | $ | 2.470 | 2.320 | 2.030 | 1.850 | 1.850 |  |  |  |
| Country co-financing per dose | Table 6.(n).2[2] | $ | 0.20 | 0.20 | 0.20 | 0.20 | 0.20 |  |  |  |
| AD syringe price per unit |  | $ | 0.053 | 0.053 | 0.053 | 0.053 | 0.053 |  |  |  |
| Reconstitution syringe price per unit |  | $ |  |  |  |  |  |  |  |  |
| Safety box price per unit |  | $ | 0.640 | 0.640 | 0.640 | 0.640 | 0.640 |  |  |  |
| Freight cost as % of vaccines value |  | % | 3.50 | 3.50 | 3.50 | 3.50 | 3.50 |  |  |  |
| Freight cost as % of devices value |  | % | 10.00 | 10.00 | 10.00 | 10.00 | 10.00 |  |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Where (n) depends on the vaccine

# Table 1.1 D - Estimated number of doses for DTP-HepB-Hib, 10 doses/vial, Liquid associated injection safety material and related co-financing budget (page 1)

|  |  | Formula | 2012 |  |  | 2013 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Total | Government | GAVI | Total | Government | GAVI |
| A | Country Co-finance |  | 7.65% |  |  | 8.13% |  |  |
| B | Number of children to be vaccinated with the first dose[1] | Table 1 (baseline & annual targets) | 669,070 | 51,167 | 617,903 | 1,392,037 | 113,105 | 1,278,932 |
| C | Number of doses per child | Vaccine parameter | 3 | 3 | 3 | 3 | 3 | 3 |
| D | Number of doses needed | B * C | 2,007,210 | 153,500 | 1,853,710 | 4,176,111 | 339,314 | 3,836,797 |
| E | Estimated vaccine wastage factor | Table 6.(n).3. in NVS section[2] | 1.33 | 1.33 | 1.33 | 1.25 | 1.25 | 1.25 |
| F | Number of doses needed including wastage | D * E | 2,669,590 | 204,155 | 2,465,435 | 5,220,139 | 424,142 | 4,795,997 |
| G | Vaccines buffer stock | (F - F of previous year) * 0.25 | 667,398 | 51,039 | 616,359 | 637,638 | 51,809 | 585,829 |
| I | Total vaccine doses needed | F + G | 3,336,988 | 255,193 | 3,081,795 | 5,857,777 | 475,951 | 5,381,826 |
| J | Number of doses per vial | Vaccine parameter | 10 | 10 | 10 | 10 | 10 | 10 |
| K | Number of AD syringes (+ 10% wastage) needed | (D + G) * 1.11 | 2,968,815 | 227,038 | 2,741,777 | 5,343,262 | 434,146 | 4,909,116 |
| L | Reconstitution syringes (+ 10% wastage) needed | I / J * 1.11 |  |  |  |  |  |  |
| M | Total of safety boxes (+ 10% of extra need) needed | (K + L) / 100 x 1.11 | 32,954 | 2,521 | 30,433 | 59,311 | 4,820 | 54,491 |
| N | Cost of vaccines needed | I * vaccine price per dose | 8,242,361 | 630,327 | 7,612,034 | 13,590,043 | 1,104,206 | 12,485,837 |
| O | Cost of AD syringes needed | K * AD syringe price per unit | 157,348 | 12,034 | 145,314 | 283,193 | 23,010 | 260,183 |
| P | Cost of reconstitution syringes needed | L * reconstitution price per unit |  |  |  |  |  |  |
| Q | Cost of safety boxes needed | M * safety box price per unit | 21,091 | 1,613 | 19,478 | 37,960 | 3,085 | 34,875 |
| R | Freight cost for vaccines needed | N * freight cost as % of vaccines value | 288,483 | 22,062 | 266,421 | 475,652 | 38,648 | 437,004 |
| S | Freight cost for devices needed | (O + P + Q) * freight cost as % of devices value | 17,844 | 1,365 | 16,479 | 32,116 | 2,610 | 29,506 |
| T | Total fund needed | (N + O + P + Q + R + S) | 8,727,127 | 667,398 | 8,059,729 | 14,418,964 | 1,171,556 | 13,247,408 |
| U | Total country co-financing | I * country co-financing per dose | 667,398 |  |  | 1,171,556 |  |  |
| V | Country co-financing % of GAVI supported proportion | U / T | 7.65% |  |  | 8.13% |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Where (n) depends on the vaccine

# Table 1.1 D - Estimated number of doses for DTP-HepB-Hib, 10 doses/vial, Liquid associated injection safety material and related co-financing budget (page 2)

|  |  | Formula | 2014 |  |  | 2015 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Total | Government | GAVI | Total | Government | GAVI |
| A | Country Co-finance |  | 9.26% |  |  | 10.12% |  |  |
| B | Number of children to be vaccinated with the first dose[1] | Table 1 (baseline & annual targets) | 1,417,287 | 131,241 | 1,286,046 | 1,412,998 | 142,948 | 1,270,050 |
| C | Number of doses per child | Vaccine parameter (schedule) | 3 | 3 | 3 | 3 | 3 | 3 |
| D | Number of doses needed | B * C | 4,251,861 | 393,723 | 3,858,138 | 4,238,994 | 428,844 | 3,810,150 |
| E | Estimated vaccine wastage factor | Table 6.(n).3. in NVS section[2] | 1.25 | 1.25 | 1.25 | 1.18 | 1.18 | 1.18 |
| F | Number of doses needed including wastage | D * E | 5,314,827 | 492,154 | 4,822,673 | 5,002,013 | 506,036 | 4,495,977 |
| G | Vaccines buffer stock | (F - F of previous year) * 0.25 | 23,672 | 2,193 | 21,479 | 0 | 0 | 0 |
| I | Total vaccine doses needed | F + G | 5,338,499 | 494,346 | 4,844,153 | 5,002,013 | 506,036 | 4,495,977 |
| J | Number of doses per vial | Vaccine parameter | 10 | 10 | 10 | 10 | 10 | 10 |
| K | Number of AD syringes (+ 10% wastage) needed | (D + G) * 1.11 | 4,745,842 | 439,466 | 4,306,376 | 4,705,284 | 476,017 | 4,229,267 |
| L | Reconstitution syringes (+ 10% wastage) needed | I / J * 1.11 |  |  |  |  |  |  |
| M | Total of safety boxes (+ 10% of extra need) needed | (K + L) / 100 x 1.11 | 52,679 | 4,879 | 47,800 | 52,229 | 5,284 | 46,945 |
| N | Cost of vaccines needed | I * vaccine price per dose | 10,837,153 | 1,003,522 | 9,833,631 | 9,253,725 | 936,166 | 8,317,559 |
| O | Cost of AD syringes needed | K * AD syringe price per unit | 251,530 | 23,292 | 228,238 | 249,381 | 25,229 | 224,152 |
| P | Cost of reconstitution syringes needed | L * reconstitution price per unit |  |  |  |  |  |  |
| Q | Cost of safety boxes needed | M * safety box price per unit | 33,715 | 3,123 | 30,592 | 33,427 | 3,382 | 30,045 |
| R | Freight cost for vaccines needed | N * freight cost as % of vaccines value | 379,301 | 35,124 | 344,177 | 323,881 | 32,766 | 291,115 |
| S | Freight cost for devices needed | (O + P + Q) * freight cost as % of devices value | 28,525 | 2,642 | 25,883 | 28,281 | 2,862 | 25,419 |
| T | Total fund needed | (N + O + P + Q + R + S) | 11,530,224 | 1,067,700 | 10,462,524 | 9,888,695 | 1,000,403 | 8,888,292 |
| U | Total country co-financing | I * country co-financing per dose | 1,067,700 |  |  | 1,000,403 |  |  |
| V | Country co-financing % of GAVI supported proportion | U / T | 9.26% |  |  | 10.12% |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Where (n) depends on the vaccine

# Table 1.1 D -: Estimated number of doses for DTP-HepB-Hib, 10 doses/vial, Liquid associated injection safety material and related co-financing budget (page 3)

|  |  | Formula | 2016 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Total | Government | GAVI | Total | Government | GAVI |
| A | Country Co-finance |  | 10.12% |  |  |  |  |  |
| B | Number of children to be vaccinated with the first dose[1] | Table 1 (baseline & annual targets) | 1,423,810 | 144,041 | 1,279,769 |  |  |  |
| C | Number of doses per child | Vaccine parameter (schedule) | 3 | 3 | 3 | 3 | 3 | 3 |
| D | Number of doses needed | B * C | 4,271,430 | 432,121 | 3,839,309 |  |  |  |
| E | Estimated vaccine wastage factor | Table 6.(n).3. in NVS section[2] | 1.18 | 1.18 | 1.18 |  |  |  |
| F | Number of doses needed including wastage | D * E | 5,040,288 | 509,903 | 4,530,385 |  |  |  |
| G | Vaccines buffer stock | (F - F of previous year) * 0.25 | 9,569 | 969 | 8,600 |  |  |  |
| I | Total vaccine doses needed | F + G | 5,049,857 | 510,871 | 4,538,986 |  |  |  |
| J | Number of doses per vial | Vaccine parameter | 10 | 10 | 10 | 10 | 10 | 10 |
| K | Number of AD syringes (+ 10% wastage) needed | (D + G) * 1.11 | 4,751,909 | 480,729 | 4,271,180 |  |  |  |
| L | Reconstitution syringes (+ 10% wastage) needed | I / J * 1.11 |  |  |  |  |  |  |
| M | Total of safety boxes (+ 10% of extra need) needed | (K + L) / 100 x 1.11 | 52,747 | 5,337 | 47,410 |  |  |  |
| N | Cost of vaccines needed | I * vaccine price per dose | 9,342,236 | 945,110 | 8,397,126 |  |  |  |
| O | Cost of AD syringes needed | K * AD syringe price per unit | 251,852 | 25,479 | 226,373 |  |  |  |
| P | Cost of reconstitution syringes needed | L * reconstitution price per unit |  |  |  |  |  |  |
| Q | Cost of safety boxes needed | M * safety box price per unit | 33,759 | 3,416 | 30,343 |  |  |  |
| R | Freight cost for vaccines needed | N * freight cost as % of vaccines value | 326,979 | 33,079 | 293,900 |  |  |  |
| S | Freight cost for devices needed | (O + P + Q) * freight cost as % of devices value | 28,562 | 2,890 | 25,672 |  |  |  |
| T | Total fund needed | (N + O + P + Q + R + S) | 9,983,388 | 1,009,972 | 8,973,416 |  |  |  |
| U | Total country co-financing | I * country co-financing per dose | 1,009,972 |  |  |  |  |  |
| V | Country co-financing % of GAVI supported proportion | U / T | 10.12% |  |  |  |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Where (n) depends on the vaccine

# Annex 2

Estimated prices of supply and related freight cost: 2011 from UNICEF Supply Division; 2012 onwards: GAVI Secretariat

Table A - Commodities Cost

| Vaccine | Presentation | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| AD syringe | 0 | 0.053 | 0.053 | 0.053 | 0.053 | 0.053 | 0.053 | 0.053 |
| DTP-HepB | 2 | 1.600 |  |  |  |  |  |  |
| DTP-HepB | 10 | 0.620 | 0.620 | 0.620 | 0.620 | 0.620 | 0.620 | 0.620 |
| DTP-HepB-Hib | WAP | 2.720 | 2.470 | 2.320 | 2.030 | 1.850 | 1.850 | 1.850 |
| DTP-HepB-Hib | WAP | 2.580 | 2.470 | 2.320 | 2.030 | 1.850 | 1.850 | 1.850 |
| DTP-HepB-Hib | WAP | 2.720 | 2.470 | 2.320 | 2.030 | 1.850 | 1.850 | 1.850 |
| DTP-Hib | 10 | 3.400 | 3.400 | 3.400 | 3.400 | 3.400 | 3.200 | 3.200 |
| HepB monoval | 1 |  |  |  |  |  |  |  |
| HepB monoval | 2 |  |  |  |  |  |  |  |
| Hib monoval | 1 | 3.400 |  |  |  |  |  |  |
| Measles | 10 | 0.240 | 0.250 | 0.250 | 0.250 | 0.250 | 0.250 | 0.250 |
| Pneumococcal(PCV10) | 2 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 |
| Pneumococcal(PCV13) | 1 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 |
| Reconstit syringe for Pentaval (2ml) | 0 | 0.032 | 0.032 | 0.032 | 0.032 | 0.032 | 0.032 | 0.032 |
| Reconstit syringe for YF | 0 | 0.038 | 0.038 | 0.038 | 0.038 | 0.038 | 0.038 | 0.038 |
| Rotavirus 2-dose schedule | 1 | 7.500 | 2.750 | 2.750 | 2.750 | 2.750 | 2.750 | 2.750 |
| Rotavirus 3-dose schedule | 1 | 5.500 | 5.000 | 5.000 | 5.000 | 3.500 | 3.500 | 3.500 |
| Safety box | 0 | 0.640 | 0.640 | 0.640 | 0.640 | 0.640 | 0.640 | 0.640 |
| Yellow Fever | WAP | 0.856 | 0.900 | 0.900 | 0.900 | 0.900 | 0.900 | 0.900 |
| Yellow Fever | WAP | 0.856 | 0.900 | 0.900 | 0.900 | 0.900 | 0.900 | 0.900 |

Note: WAP - weighted average price (to be used for any presentation: For DTP-HepB-Hib, it applies to 1 dose liquid, 2 dose lyophilised and 10 dose liquid. For Yellow Fever, it applies to 5 dose lyophilised and 10 dose lyophilised)

Table B - Commodities Freight Cost

| Vaccines | Group | No Threshold | 200’000 $ |  | 250’000 $ |  | 2’000’000 $ |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | <= | > | <= | > | <= | > |
| Yellow Fever | Yellow Fever |  | 20% |  |  |  | 10% | 5% |
| DTP+HepB | HepB and or Hib | 2% |  |  |  |  |  |  |
| DTP-HepB-Hib | HepB and or Hib |  |  |  | 15% | 3,50% |  |  |
| Pneumococcal vaccine (PCV10) | Pneumococcal | 5% |  |  |  |  |  |  |
| Pneumococcal vaccine (PCV13) | Pneumococcal | 5% |  |  |  |  |  |  |
| Rotavirus | Rotavirus | 5% |  |  |  |  |  |  |
| Measles | Measles | 10% |  |  |  |  |  |  |

Table C - Low - Minimum country's co-payment per dose of co-financed vaccine.

| vaccine | 2012 | 2013 | 2014 | 2015 | 2016 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| DTP-HepB-Hib, 10 doses/vial, Liquid | 0.20 | 0.20 | 0.20 | 0.20 | 0.20 |  |  |

Table D - Wastage rates and factors

Countries are expected to plan for a maximal wastage rate of:

- 50% - for a lyophilised vaccine in 10 or 20-dose vial,

- 25% - for a liquid vaccine in 10 or 20-dose vial or a lyophilised vaccine in 5-dose vial,

- 10% - for a lyophilised/liquid vaccine in 2-dose vial, and

- 5% - for a liquid vaccine in 1-dose vial

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2 | 2.22 | 2.5 |

WHO International shipping guidelines: maximum packed volumes of vaccines

Table E - Vaccine maximum packed volumes

| Vaccine product | Designation | Vaccine formulation | Admin route | No. Of doses in the schedule | Presentation (doses/vial, prefilled) | Packed volume vaccine (cm3/dose) | Packed volume diluents (cm3/dose) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| BCG | BCG | lyophilized | ID | 1 | 20 | 1.2 | 0.7 |
| Diphtheria-Tetanus-Pertussis | DTP | liquid | IM | 3 | 20 | 2.5 |  |
| Diphtheria-Tetanus-Pertussis | DTP | liquid | IM | 3 | 10 | 3.0 |  |
| Diphtheria-Tetanus | DT | liquid | IM | 3 | 10 | 3.0 |  |
| Tetanus-Diphtheria | Td | liquid | IM | 2 | 10 | 3.0 |  |
| Tetanus Toxoid | TT | liquid | IM | 2 | 10 | 3.0 |  |
| Tetanus Toxoid | TT | liquid | IM | 2 | 20 | 2.5 |  |
| Tetanus Toxoid UniJect | TT | liquid | IM | 2 | Uniject | 12.0 |  |
| Measles | Measles | lyophilized | SC | 1 | 1 | 26.1 | 20.0 |
| Measles | Measles | lyophilized | SC | 1 | 2 | 13.1 | 13.1 |
| Measles | Measles | lyophilized | SC | 1 | 5 | 5.2 | 7.0 |
| Measles | Measles | lyophilized | SC | 1 | 10 | 3.5 | 4.0 |
| Measles-Rubella freeze dried | MR | lyophilized | SC | 1 | 1 | 26.1 | 26.1 |
| Measles-Rubella freeze dried | MR | lyophilized | SC | 1 | 2 | 13.1 | 13.1 |
| Measles-Rubella freeze dried | MR | lyophilized | SC | 1 | 5 | 5.2 | 7.0 |
| Measles-Rubella freeze dried | MR | lyophilized | SC | 1 | 10 | 2.5 | 4.0 |
| Measles-Mumps-Rubella freeze dried | MMR | lyophilized | SC | 1 | 1 | 26.1 | 26.1 |
| Measles-Mumps-Rubella freeze dried | MMR | lyophilized | SC | 1 | 2 | 13.1 | 13.1 |
| Measles-Mumps-Rubella freeze dried | MMR | lyophilized | SC | 1 | 5 | 5.2 | 7.0 |
| Measles-Mumps-Rubella freeze dried | MMR | lyophilized | SC | 1 | 10 | 3.0 | 4.0 |
| Polio | OPV | liquid | Oral | 4 | 10 | 2.0 |  |
| Polio | OPV | liquid | Oral | 4 | 20 | 1.0 |  |
| Yellow fever | YF | lyophilized | SC | 1 | 5 | 6.5 | 7.0 |
| Yellow fever | YF | lyophilized | SC | 1 | 10 | 2.5 | 3.0 |
| Yellow fever | YF | lyophilized | SC | 1 | 20 | 1.5 | 2.0 |
| Yellow fever | YF | lyophilized | SC | 1 | 50 | 0.7 | 1.0 |
| DTP-HepB combined | DTP-HepB | liquid | IM | 3 | 1 | 9.7 |  |
| DTP-HepB combined | DTP-HepB | liquid | IM | 3 | 2 | 6.0 |  |
| DTP-HepB combined | DTP-HepB | liquid | IM | 3 | 10 | 3.0 |  |
| Hepatitis B | HepB | liquid | IM | 3 | 1 | 18.0 |  |
| Hepatitis B | HepB | liquid | IM | 3 | 2 | 13.0 |  |
| Hepatitis B | HepB | liquid | IM | 3 | 6 | 4.5 |  |
| Hepatitis B | HepB | liquid | IM | 3 | 10 | 4.0 |  |
| Hepatitis B UniJect | HepB | liquid | IM | 3 | Uniject | 12.0 |  |
| Hib liquid | Hib_liq | liquid | IM | 3 | 1 | 15.0 |  |
| Hib liquid | Hib_liq | liquid | IM | 3 | 10 | 2.5 |  |
| Hib freeze-dried | Hib_lyo | lyophilized | IM | 3 | 1 | 13.0 | 35.0 |
| Hib freeze-dried | Hib_lyo | lyophilized | IM | 3 | 2 | 6.0 |  |
| Hib freeze-dried | Hib_lyo | lyophilized | IM | 3 | 10 | 2.5 | 3.0 |
| DTP liquid + Hib freeze-dried | DTP+Hib | liquid+lyop. | IM | 3 | 1 | 45.0 |  |
| DTP-Hib combined liquid | DTP+Hib | liquid+lyop. | IM | 3 | 10 | 12.0 |  |
| DTP-Hib combined liquid | DTP-Hib | liquid | IM | 3 | 1 | 32.3 |  |
| DTP-HepB liquid + Hib freeze-dried | DTP-Hib | liquid | IM | 3 | 10 | 2.5 |  |
| DTP-HepB liquid + Hib freeze-dried | DTP-HepB+Hib | liquid+lyop. | IM | 3 | 1 | 22.0 |  |
| DTP-HepB-Hib liquid | DTP-HepB+Hib | liquid+lyop. | IM | 3 | 2 | 11.0 |  |
| DTP-HepB-Hib liquid | DTP-HepB-Hib | liquid | IM | 3 | 10 | 4.4 |  |
| DTP-HepB-Hib liquid | DTP-HepB-Hib | liquid | IM | 3 | 2 | 13.1 |  |
| DTP-HepB-Hib liquid | DTP-HepB-Hib | liquid | IM | 3 | 1 | 19.2 |  |
| Meningitis A/C | MV_A/C | lyophilized | SC | 1 | 10 | 2.5 | 4.0 |
| Meningitis A/C | MV_A/C | lyophilized | SC | 1 | 50 | 1.5 | 3.0 |
| Meningococcal A/C/W/ | MV_A/C/W | lyophilized | SC | 1 | 50 | 1.5 | 3.0 |
| Meningococcal A/C/W/Y | MV_A/C/W/Y | lyophilized | SC | 1 | 10 | 2.5 | 4.0 |
| Meningitis W135 | MV_W135 | lyophilized | SC | 1 | 10 | 2.5 | 4.0 |
| Meningitis A conjugate | Men_A | lyophilized | SC | 2 | 10 | 2.6 | 4.0 |
| Japanese Encephalitis | JE_lyo | lyophilized | SC | 3 | 10 | 15.0 |  |
| Japanese Encephalitis | JE_lyo | lyophilized | SC | 3 | 10 | 8.1 | 8.1 |
| Japanese Encephalitis | JE_lyo | lyophilized | SC | 3 | 5 | 2.5 | 2.9 |
| Japanese Encephalitis | JE_lyo | lyophilized | SC | 3 | 1 | 12.6 | 11.5 |
| Japanese Encephalitis | JE_liq | liquid | SC | 3 | 10 | 3.4 |  |
| Rota vaccine | Rota_lyo | lyophilized | Oral | 2 | 1 | 156.0 |  |
| Rota vaccine | Rota_liq | liquid | Oral | 2 | 1 | 17.1 |  |
| Rota vaccine | Rota_liq | liquid | Oral | 3 | 1 | 45.9 |  |
| Pneumo. conjugate vaccine 7-valent | PCV-7 | liquid | IM | 3 | PFS | 55.9 |  |
| Pneumo. conjugate vaccine 7-valent | PCV-7 | liquid | IM | 3 | 1 | 21.0 |  |
| Pneumo. conjugate vaccine 10-valent | PCV-10 | liquid | IM | 3 | 1 | 11.5 |  |
| Pneumo. conjugate vaccine 10-valent | PCV-10 | liquid | IM | 3 | 2 | 4.8 |  |
| Pneumo. conjugate vaccine 13-valent | PCV-13 | liquid | IM | 3 | 1 | 12.0 |  |
| Polio inactivated | IPV | liquid | IM | 3 | PFS | 107.4 |  |
| Polio inactivated | IPV | liquid | IM | 3 | 10 | 2.5 |  |
| Polio inactivated | IPV | liquid | IM | 3 | 1 | 15.7 |  |
| Human Papilomavirus vaccine | HPV | liquid | IM | 3 | 1 | 15.0 |  |
| Human Papilomavirus vaccine | HPV | liquid | IM | 3 | 2 | 5.7 |  |
| Monovalent OPV-1 | mOPV1 | liquid | Oral |  | 20 | 1.5 |  |
| Monovalent OPV-3 | mOPV3 | liquid | Oral |  | 20 | 1.5 |  |

# Attachments

# List of Supporting Documents Attached to this Proposal

| Document | Section | Document Number | Mandatory[1] |
| --- | --- | --- | --- |
| MoH Signature (or delegated authority) of Proposal |  | 5 | Yes |
| MoF Signature (or delegated authority) of Proposal |  | 6 | Yes |
| Signatures of ICC or HSCC or equivalent in Proposal |  | 7 | Yes |
| Minutes of ICC/HSCC meeting endorsing Proposal |  | 1 | Yes |
| comprehensive Multi Year Plan - cMYP |  | 2 | Yes |
| cMYP Costing tool for financial analysis |  | 9 | Yes |
| Minutes of last three ICC/HSCC meetings |  | 12 | Yes |
| Improvement plan based on EVM |  | 4 | Yes |
| Response to Conditions Addendum |  | 10 | Yes |
| WHO/UNICEF Joint Reporting Form (JRF) |  |  |  |
| ICC/HSCC workplan for forthcoming 12 months |  |  |  |
| National policy on injection safety |  |  |  |
| Action plans for improving injection safety |  |  |  |
| Plan for NVS introduction (if not part of cMYP) |  | 8 |  |
| Banking details |  |  |  |

[1] Please indicate the duration of the plan / assessment / document where appropriate

# Attachments

List of all the mandatory and optional documents attached to this form

Note: Use the Upload file arrow icon to upload the document. Use the Delete item icon to delete a line. To add new lines click on the New item icon in the Action column.

| ID | File type | File name |  | New file | Actions |
| --- | --- | --- | --- | --- | --- |
|  | Description | Date and Time | Size |  |  |
| 1 | File Type: Minutes of ICC/HSCC meeting endorsing Proposal * File Desc: | File name: Minutes+of+ICC+15th+Sep.2011.docx Date/Time: 12.11.2011 06:29:52 Size: 18 KB |  |  |  |
| 2 | File Type: comprehensive Multi Year Plan - cMYP * File Desc: | File name: Myanmar c MYP 2012_2016 updated 12 Nov.docx Date/Time: 12.11.2011 07:26:52 Size: 783 KB |  |  |  |
| 3 | File Type: other File Desc: EVM report Aug 2011 _ Myanmar | File name: EVM_report-Myanmar final.pdf Date/Time: 12.11.2011 06:36:29 Size: 3 MB |  |  |  |
| 4 | File Type: Improvement plan based on EVM * File Desc: Myanmar Cold Chain improvement plan 2011-2014 | File name: EVM-imp-plan-Myanmar 2011 v6.xlsx Date/Time: 12.11.2011 06:36:29 Size: 132 KB |  |  |  |
| 5 | File Type: MoH Signature (or delegated authority) of Proposal * File Desc: Minister of Health endorsement of Penta proposal | File name: MoH+%26+MoF+Signatures.jpg Date/Time: 12.11.2011 06:38:43 Size: 1 MB |  |  |  |
| 6 | File Type: MoF Signature (or delegated authority) of Proposal * File Desc: Minister of Finance endorsement of Penta proposal | File name: MoH+%26+MoF+Signatures.jpg Date/Time: 12.11.2011 06:42:59 Size: 1 MB |  |  |  |
| 7 | File Type: Signatures of ICC or HSCC or equivalent in Proposal * File Desc: | File name: ICC+Members+Signatures.jpg Date/Time: 12.11.2011 06:42:59 Size: 1 MB |  |  |  |
| 8 | File Type: Plan for NVS introduction (if not part of cMYP) File Desc: | File name: Myanmar NVI plan doc_12 Nov.doc Date/Time: 12.11.2011 07:26:52 Size: 1 MB |  |  |  |
| 9 | File Type: cMYP Costing tool for financial analysis * File Desc: | File name: Myanmar c myp Costing tool _12 Nov.xlsm Date/Time: 12.11.2011 07:30:05 Size: 1 MB |  |  |  |
| 10 | File Type: Response to Conditions Addendum * File Desc: | File name: Response+to+Condition.doc Date/Time: 12.11.2011 07:32:43 Size: 25 KB |  |  |  |
| 11 | File Type: other File Desc: Importment points / clarifiactions to be read for penta application | File name: point to note.doc Date/Time: 12.11.2011 07:34:31 Size: 33 KB |  |  |  |
| 12 | File Type: Minutes of last three ICC/HSCC meetings * File Desc: past three ICC meeting minutes and recomendations | File name: Myanmar ICC meeting docs.zip Date/Time: 12.11.2011 07:52:07 Size: 830 KB |  |  |  |