GAVI Alliance

Application Form for Country Proposals

For Support to New and Under-Used Vaccines (NVS)

Submitted by

The Government of

Somalia

Date of submission: 01.06.2011 14:39:37

Deadline for submission: 1 Jun 2011

Select Start and End Year of your Comprehensive Multi-Year Plan (cMYP)

| Start Year | 2011 | End Year | 2015 |
| --- | --- | --- | --- |

Revised in January 2011

(To be used with Guidelines of December 2010)

Please submit the Proposal using the online platform https://AppsPortal.gavialliance.org/PDExtranet.

Enquiries to: proposals@gavialliance.org or representatives of a GAVI partner agency. The documents can be shared with GAVI partners, collaborators and general public. The Proposal and attachments must be submitted in English, French, Spanish, or Russian.

Note: Please ensure that the application has been received by the GAVI Secretariat on or before the day of the deadline.

The GAVI Secretariat is unable to return submitted documents and attachments to countries. Unless otherwise specified, documents will be shared with the GAVI Alliance partners and the general public.

GAVI ALLIANCE GRANT TERMS AND CONDITIONS FUNDING USED SOLELY FOR APPROVED PROGRAMMES The applicant country (“Country”) confirms that all funding provided by the GAVI Alliance will be used and applied for the sole purpose of fulfilling the programme(s) described in the Country’s application. Any significant change from the approved programme(s) must be reviewed and approved in advance by the GAVI Alliance. All funding decisions for the application are made at the discretion of the GAVI Alliance Board and are subject to IRC processes and the availability of funds. AMENDMENT TO THE APPLICATION The Country will notify the GAVI Alliance in its Annual Progress Report if it wishes to propose any change to the programme(s) description in its application. The GAVI Alliance will document any change approved by the GAVI Alliance, and the Country’s application will be amended. RETURN OF FUNDS The Country agrees to reimburse to the GAVI Alliance all funding amounts that are not used for the programme(s) described in its application. The country’s reimbursement must be in US dollars and be provided, unless otherwise decided by the GAVI Alliance, within sixty (60) days after the Country receives the GAVI Alliance’s request for a reimbursement and be paid to the account or accounts as directed by the GAVI Alliance. SUSPENSION/ TERMINATION The GAVI Alliance may suspend all or part of its funding to the Country if it has reason to suspect that funds have been used for purpose other than for the programmes described in the Country’s application, or any GAVI Alliance-approved amendment to the application. The GAVI Alliance retains the right to terminate its support to the Country for the programmes described in its application if a misuse of GAVI Alliance funds is confirmed. ANTICORRUPTION The Country confirms that funds provided by the GAVI Alliance shall not be offered by the Country to any third person, nor will the Country seek in connection with its application any gift, payment or benefit directly or indirectly that could be construed as an illegal or corrupt practice. AUDITS AND RECORDS The Country will conduct annual financial audits, and share these with the GAVI Alliance, as requested. The GAVI Alliance reserves the right, on its own or through an agent, to perform audits or other financial management assessment to ensure the accountability of funds disbursed to the Country. The Country will maintain accurate accounting records documenting how GAVI Alliance funds are used. The Country will maintain its accounting records in accordance with its government-approved accounting standards for at least three years after the date of last disbursement of GAVI Alliance funds. If there is any claims of misuse of funds, Country will maintain such records until the audit findings are final. The Country agrees not to assert any documentary privilege against the GAVI Alliance in connection with any audit. CONFIRMATION OF LEGAL VALIDITY The Country and the signatories for the Country confirm that its application, and Annual Progress Report, are accurate and correct and form legally binding obligations on the Country, under the Country’s law, to perform the programmes described in its application, as amended, if applicable, in the APR. CONFIRMATION OF COMPLIANCE WITH THE GAVI ALLIANCE TRANSPARANCY AND ACCOUNTABILITY POLICY The Country confirms that it is familiar with the GAVI Alliance Transparency and Accountability Policy (TAP) and complies with the requirements therein. USE OF COMMERCIAL BANK ACCOUNTS The Country is responsible for undertaking the necessary due diligence on all commercial banks used to manage GAVI cash-based support. The Country confirms that it will take all responsibility for replenishing GAVI cash support lost due to bank insolvency, fraud or any other unforeseen event. ARBITRATION Any dispute between the Country and the GAVI Alliance arising out of or relating to its application that is not settled amicably within a reasonable period of time, will be submitted to arbitration at the request of either the GAVI Alliance or the Country. The arbitration will be conducted in accordance with the then-current UNCITRAL Arbitration Rules. The parties agree to be bound by the arbitration award, as the final adjudication of any such dispute. The place of arbitration will be Geneva, Switzerland. The language of the arbitration will be English. For any dispute for which the amount at issue is US$ 100,000 or less, there will be one arbitrator appointed by the GAVI Alliance. For any dispute for which the amount at issue is greater than US $100,000 there will be three arbitrators appointed as follows: The GAVI Alliance and the Country will each appoint one arbitrator, and the two arbitrators so appointed will jointly appoint a third arbitrator who shall be the chairperson. The GAVI Alliance will not be liable to the country for any claim or loss relating to the programmes described in the application, including without limitation, any financial loss, reliance claims, any harm to property, or personal injury or death. Country is solely responsible for all aspects of managing and implementing the programmes described in its application.

# Application Specification

Please specify for which type of GAVI support you would like to apply to.

Important note: To enable proper functioning of the form, please first select the cMYP years on the previous page.

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Type of Support | Vaccine | Start Year | End Year | Preferred second presentation[1] | Action |
| --- | --- | --- | --- | --- | --- |
| New Vaccines Support | DTP-HepB-Hib, 10 doses/vial, Liquid | 2013 | 2015 |  |  |

[1] This "Preferred second presentation" will be used in case there is no supply available for the preferred presentation of the selected vaccine ("Vaccine" column). If left blank, it will be assumed that the country will prefer waiting until the selected vaccine becomes available.

# Table of Contents

Sections

Main

Cover Page

GAVI Alliance Grants Terms and Conditions

1. Application Specification

2. Table of Contents

3. Executive Summary

4. Signatures

4.1. Signatures of the Government and National Coordinating Bodies

4.1.1. Government and the Inter-Agency Coordinating Committee for Immunisation

4.1.2. National Coordinating Body - Inter-Agency Coordinating Committee for Immunisation

4.1.3. The Inter-Agency Coordinating Committee for Immunisation

4.2. National Immunization Technical Advisory Group for Immunisation

4.2.1. The NITAG Group for Immunisation

5. Immunisation Programme Data

5.1. Basic facts

5.2. Current vaccination schedule

5.3. Trends of immunisation coverage and disease burden

5.4. Baseline and Annual Targets

Table 1: baseline figures

5.5. Summary of current and future immunisation budget

5.6. Summary of current and future financing and sources of funds

6. NVS

6.1. Capacity and cost (for positive storage)

6.2. Assessment of burden of relevant diseases (if available)

6.3.1. Requested vaccine ( DTP-HepB-Hib, 10 doses/vial, Liquid )

6.3.2. Co-financing information

6.3.3. Wastage factor

6.3.4. Specifications of vaccinations with new vaccine

6.3.5. Portion of supply to be procured by the country (and cost estimate, US$)

6.3.6. Portion of supply to be procured by the GAVI Alliance (and cost estimate, US$)

6.3.7. New and Under-Used Vaccine Introduction Grant

7. Procurement and Management of New and Under-Used Vaccines

7.1. Vaccine management (EVSM/EVM/VMA)

8. Additional Comments and Recommendations

9. Annexes

Annex 1

Annex 1.1 - DTP-HepB-Hib, 10 doses/vial, Liquid

Table 1.1  A - Rounded up portion of supply that is procured by the country and estimate of related cost in US$

Table 1.1  B - Rounded up portion of supply that is procured by GAVI and estimate of related cost in US$.

Table 1.1  C - Summary table for vaccine DTP-HepB-Hib, 10 doses/vial, Liquid

Table 1.1  D - Estimated number of doses for vaccine DTP-HepB-Hib, 10 doses/vial, Liquid associated injection safety material and related co-financing budget

Annex 2

10. Attachments

10.1 Documents required for NVS support

10.2 Attachments

Banking Form

# Executive Summary

The ongoing civil strife in Somalia over the last 20 years has resulted in the country having one of the lowest health indicators in the world. In the absence of a fully functional central government immunization services, like other health services, are mainly provided by UN agencies and NGOs. 

Immunization level of DPT3 coverage in Somalia has historically remained, at around 30 - 40 percent. However, with the implementation of Reaching Every District (RED) approach and a complementary strategy of Child Health Days (CHDs) which provide an opportunity to reach children at least twice a year with multiple child health interventions including immunization, reported DPT3 coverage increased from 42% in 2008 to 51% in 2009 and 64% in 2010. 

Amidst the civil strife, local health authorities and all immunization partners in Somalia, have been able to maintain immunization program running all over the country. Yet, Somalia is the only country in WHO EMR which has not been able to introduce Hepatitis B vaccine in its immunization programmes. Being eligible for GAVI support, after having crossed the threshold of 50% DPT3 coverage, the country is taking the opportunity to apply to GAVI for Pentavalent (DPT-HepB-Hib) vaccine introduction in its immunization programme from 2013 onwards. 

The total number of surviving infants in 2013 will be 338,726; and the total number for 2013 – 2015 will be 1,046,969 surviving infants, who will require a total of 3,854,300 doses of Pentavalent vaccine, that will cost a total of US$ 8,638,150 over the three years period. Of these, the amount to be paid by GAVI will be 7,708,195; and the amount to be paid by the government will be 929,955 over the three year period. This co-financing level will be covered by the UNICEF, that has historically been the sole provider of vaccine to the country since the start of EPI program. 

The national store in Nairobi and four zonal vaccines stores inside Somalia are managed and maintained by UNICEF. A total of eight sub-zonal stores are managed by zonal governments with financial and technical support from UNICEF. For the planned introduction of DTP-HepB-Hib vaccine in 2013, the available net positive storage capacity at national level would be sufficient. However at zonal level, Somalia will need a total of 673 liters of positive storage. There will be no need for negative storage. The total need of the positive storage will be accommodated with additional 7 MK304 refrigerators, as indicated in the cMYP. The total cost of additional cold chain will be US$ 7294. 

EVM assessment was conducted in March, 2011 and a followup assessment is planned for, in the second and third quarter of 2011. An improvement plan will be developed after the EVM assessment and will form the basis for refinement of cold chain procurement plan. Anticipating the approval, by GAVI, of Somalia’s New Vaccine Application Proposal in the third quarter of 2011, and receiving the Introduction Grant of US$ 114,500 in the fourth quarter of 2011, the following key activities are planned. 

Training: (US$ 28,000)
Social Mobilization, IEC and Advocacy: (US$ 26,000)
Cold Chain Equipment & Maintenance: (US$ 20,000)
Surveillance and Monitoring: (US$16,000)
Waste Management: (US$ 25,000)
The total budget that willl be required by the country for assessment and preparation of Pentavalent Introduction will be US$ 166,000, of which a total of 114,500 will be paid by the New Vaccine Introduction Grant and the balance of US$ 52,000 will be covered by UNICEF Somalia and WHO and Somalia. 


The Government of Somalia commits itself to improving immunisation services on a sustainable basis in accordance with the Comprehensive Multi-Year Plan (cMYP) presented with this document; and requests that the GAVI Alliance and its partners contribute financial and technical assistance to support immunisation of children as outlined in this application.

The Somali Health Sector Committee (SHSC) would also commit itself to assist the weak central government and local health authorities improve immunisation services on a sustainable basis in accordance with the cMYP of the country. As the Government of Somalia is fragile, immunization partners agree to support the co-financing cost associated with this introduction.

# Signatures

# Signatures of the Government and National Coordinating Bodies

# Government and the Inter-Agency Coordinating Committee for Immunisation

The Government of Somalia would like to expand the existing partnership with the GAVI Alliance for the improvement of the infants routine immunisation programme of the country, and specifically hereby requests for GAVI support for DTP-HepB-Hib 10 doses/vial Liquid introduction.

The Government of Somalia commits itself to developing national immunisation services on a sustainable basis in accordance with the Comprehensive Multi-Year Plan (cMYP) presented with this document. The Government requests that the GAVI Alliance and its partners contribute financial and technical assistance to support immunisation of children as outlined in this application.

Tables 6.(n).5. (where (n) depends on the vaccine) in the NVS section of this application shows the amount of support in either supply or cash that is required from the GAVI Alliance. Tables 6.(n).4. of this application shows the Government financial commitment for the procurement of this new vaccine (NVS support only).

Following the regulations of the internal budgeting and financing cycles the Government will annually release its portion of the co-financing funds in the month of November.

Please note that this application will not be reviewed or approved by the Independent Review Committee (IRC) without the signatures of both the Minister of Health & Minister of Finance or their delegated authority.

Enter the family name in capital letters.

| Minister of Health (or delegated authority) |  | Minister of Finance (or delegated authority) |  |
| --- | --- | --- | --- |
| Name | Dr Mohamed Sheik Hassan | Name | Mohamed Hassan |
| Date |  | Date |  |
| Signature |  | Signature |  |

This report has been compiled by

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

Enter the family name in capital letters.

| Full name | Position | Telephone | Email | Action |
| --- | --- | --- | --- | --- |
| Assegid K. TESSEMA | EPI Technical Officer, WHO Somalia | +254 734 600 608 | kebedea@nbo.emro.who.int |  |

# National Coordinating Body - Inter-Agency Coordinating Committee for Immunisation

We the members of the ICC, HSCC, or equivalent committee[1] met on the 25.05.2011 to review this proposal. At that meeting we endorsed this proposal on the basis of the supporting documentation which is attached.

[1] Inter-agency Coordinating Committee or Health Sector Coordinating Committee, or equivalent committee which has the authority to endorse this application in the country in question.

The endorsed minutes of this meeting are attached as DOCUMENT NUMBER: 2.

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

Enter the family name in capital letters.

| Name/Title | Agency/Organisation | Signature | Action |
| --- | --- | --- | --- |

In case the GAVI Secretariat has queries on this submission, please contact

Enter the family name in capital letters.

| Name | Assegid Kebede | Title | EPI Technical Officer, WHO Somalia |
| --- | --- | --- | --- |
| Tel no | +254 734 600 608 |  |  |
| Fax no |  | Address | Warwick Center UN Avenue, Gigiri P.O. Box 63565 - 00619 Nairobi Kenya |
| Email | kebedea@nbo.emro.who.int |  |  |

# The Inter-Agency Coordinating Committee for Immunisation

Agencies and partners (including development partners and NGOs) supporting immunisation services are co-ordinated and organised through an inter-agency coordinating mechanism (ICC, HSCC, or equivalent committee). The ICC, HSCC, or equivalent committee is responsible for coordinating and guiding the use of the GAVI NVS support. Please provide information about the ICC, HSCC, or equivalent committee in your country in the table below.

Profile of the ICC, HSCC, or equivalent committee

| Name of the committee | Health Sector Coordination Committe |
| --- | --- |
| Year of constitution of the current committee | 1995 |
| Organisational structure (e.g., sub-committee, stand-alone) | Sub-committee |
| Frequency of meetings | Monthly and also on ad hoc basis |

Composition

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

Enter the family name in capital letters.

| Function | Title / Organisation | Name |  |
| --- | --- | --- | --- |
| Chair | Revolving Chair: MOH, TFG or Somaliland or Puntland | Dr. Adan H. Ibrahim, Minister, TFG MoH |  |
| Secretary | Health Sector Coordination Office | Ms. Betty Oloo, |  |
| Members | Health Sector Coordinator, vice chair | Dr. Marina Madeo | Action |

Major functions and responsibilities of the committee

The Somali Health Sector Committee (SHSC) is a sectoral committee of the Coordination of International Support to Somali (CISS). The CISS started functioning as a continuation of the former Somali AID Coordination Body (SACB) which was established in 1994, as a coordination mechanism to support humanitarian, reconstruction and development activities in Somalia. The structures of the SACB were updated as the CISS in 2005, after the establishment of the TFG as officially recognized Somali Transitional Federal Government. The CISS operates through its Executive Committee and sectoral committees (Health & Nutrition, Education, Food Security and Economic Development, Water, Sanitation & Hygiene, and Governance ) The SHSC has undergone a reform process in the past two years, in order to have structure and functions able to respond to the coordination needs related to different levels and to a wide range of interventions, from community based to global health initiatives. Under the new structure two rounds of quarterly coordination meetings have been held, in February and May 2011, in Nairobi. The SHSC is constituency based: it includes the Somali Health Authorities from TFG, Somaliland and Puntland, Somali Civil Society representatives from the three Zones, UN, Donors and International NGOs. Quarterly meetings build on the work of its technical working groups and task forces, meeting monthly, as well as on the consultations consistently held with stakeholders and in the health sector General Meeting. The higher, political level of the health sector coordination structure is now the Health Advisory Body (HAB) at Ministers / Head of Agency level, meeting every six months with the SHSC. Staffed with the Health Sector Coordinator and the Health Programme Assistant: this office is accountable and reports to the SHCS. The whole structure described above is responsible for the coordination of health sector development interventions, plans, strategies, monitoring and evaluation, building on the shared commitment toward harmonization and alignment, aid effectiveness, mutual accountability. It oversees the Global Fund processes and grants for Somalia, this function will be better organized in the next months. The role of the SHSC, re-enforced by the reform process, is increasingly recognised by all the local and international partners in its full coordination functions, instrumental for better use of technical and financial resources, serving for better results for the Somalis. An average of 25 international organizations have participated in the coordination meetings since 1995, the current constituency based structure involves many more local and international actors. (The current membership is attached as 'other document') The technical background to the coordination work is provided by the working groups: EPI, HIV/AIDS, TB, Malaria, Reproductive Health, Health Facilities, and Health Systems with its task forces on HMIS, Human Resources, Health Care Financing. The role of the HSC is also to ensure transparent and accountable fund allocation in order to avoid duplication and maximize synergies with other sources of funding to the health sector. Accordingly Funds from GAVI have been managed by WHO, UNICEF and other health partners, with the SHSC providing oversight on coordination and implementation of GAVI Programs. SHSC maintains an active information sharing system open to all partners and accessible to general public.

Three major strategies to enhance the committee's role and functions in the next 12 months

| 1. | Strengthen the coordination network with Somali authorities, local bodies and partners, in order to fully realize a unique, articulated coordinating structure with common agenda and shared responsibilities. The network will include the coordinating bodies competent for humanitarian aid for health and related issues (health, nutrition, water, sanitation and hygiene) |
| --- | --- |
| 2. | Finalize the ongoing re-organization of working groups and task forces as a network involving different levels and different competencies, and producing valuable technical background for health sector development. |
| 3. | Enhance and support the role of Somali actors, government authorities and civil society in their different capacities, to increasingly build country ownership, responsibility and accountability, with an approach aimed at building capacities and support the ongoing strategic planning efforts. This, as any other development support, should be consistently tailored according to the wide range of different contexts in Somalia. |

# National Immunization Technical Advisory Group for Immunisation

(If it has been established in the country)

We the members of the NITAG met on the 04.05.2011 to review this proposal. At that meeting we endorsed this proposal on the basis of the supporting documentation which is attached.

The endorsed minutes of this meeting are attached as DOCUMENT NUMBER: 4.

In case the GAVI Secretariat has queries on this submission, please contact

Enter the family name in capital letters.

| Name | Dr John E. AGBOR | Title | Chief of Health, UNICEF Somalia Support Center |
| --- | --- | --- | --- |
| Tel no | Direct line: (254) 020 - 720 - 8253 |  |  |
| Fax no |  | Address | PO Box 44145 - 00100, Nairobi, Kenya |
| Email | jagbor@unicef.org |  |  |

# The NITAG Group for Immunisation

Profile of the NITAG

| Name of the NITAG | EPI Technical Working Group of SHSC (ETWG) |
| --- | --- |
| Year of constitution of the current NITAG | 2000 |
| Organisational structure (e.g., sub-committee, stand-alone) | It a sub-committte of the HSCC |
| Frequency of meetings | Monthly |

Composition

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

Enter the family name in capital letters.

| Function | Title / Organisation | Name |  |
| --- | --- | --- | --- |
| Chair | Chief of Health, UNICEF Somalia Support Center | Dr John Agbor |  |
| Secretary | Health Project Assistant | Elizabeth Oloo |  |
| Members | EPI Technical Officer, WHO Somalia | Assegid Kebede | Action |
|  | Health Sector Coordinator | Dr Marina Madeo |  |
|  | Polio team leader, WHO Somalia | Dr Mulugeta Abraham |  |
|  | SRCS | Maryam Hajila Omer |  |
|  | Trocaire | Dr Panna Erasmus |  |
|  | World Vision | Dr Anthony Abura |  |
|  | COOPI | Alessandra Bozza |  |
|  | Merlin | Dr Abebe Abera |  |
|  | SAF | Abdi Moge Mohamed |  |
|  | SAACID | Laurence Koffy |  |
|  | SAACID/OXFAM Novib | Christy Spinkle |  |
|  | CISP | Paulo Bevilacqua |  |
|  | UNOPS | Renato Correggia |  |
|  | COSV | Mohaddin Gure |  |
|  | SAFUK | Abdi Hashi |  |

Major functions and responsibilities of the NITAG

As a technical working group of SHSC, the EPI WG TWG serves as the NITAG and has the following major function: - Provides technical advice on issues related with immunization. - Ensures coordination of all EPI related activities including routine and acceleration activities - Reviews the implementation of planned immunization activities in Somalia. - Ensure realization of all objectives set forth in the multi year plan: - Review the administration of the present programme of childhood immunization - Advises on measures to improve access and utilization of immunizations - Recommends to local health authorities and immunization partners to follow WHO and UNICEF standards, guidelines and best practices for immunization in Somalia. - Ensures that partners are following the WHO and UNICEF standards of immunization - Provides a forum for exchange of information and experience among numerous immunization partners. - Provides regular updates to stakeholders regarding developments and progress in routine EPI activities in Somalia.

Three major strategies to enhance the NITAG’s role and functions in the next 12 months

| 1. | Updating the terms of reference of the EPI WG to strengthen its coordination function at Nairobi and its support function to zones |
| --- | --- |
| 2. | Establish zonal EPI working group in two zones to coordinate immunization activities at field level and enhance joint activities such as Child Health Days, outbreak response, conduct of joint supervision |
| 3. | Carry out specific EPI reviews, in order to review progress and follow up implementation, and report to the SHSC formal quarterly meetings. |

# Immunisation Programme Data

Please complete the tables below, using data from available sources. Please identify the source of the data, and the date. Where possible use the most recent data and attach the source document.

- Please refer to the Comprehensive Multi-Year Plan for Immunisation (cMYP) (or equivalent plan) and attach a complete copy (with an Executive Summary) as DOCUMENT NUMBER

- Please refer to the two most recent annual WHO/UNICEF Joint Reporting Forms (JRF) on Vaccine Preventable Diseases.

- Please refer to Health Sector Strategy documents, budgetary documents, and other reports, surveys etc, as appropriate.

# Basic facts

For the year 2010 (most recent; specify dates of data provided)

|  | Figure |  | Year | Source |
| --- | --- | --- | --- | --- |
| Total population | 8,697,600 |  | 2010 | JRF 2010, based on UNDP Projections |
| Infant mortality rate (per 1000) | 109 |  | 2010 | IMMUNIZATION SUMMARY (Statistical Reference,2009), 2011 edition, UNICEF/WHO |
| Surviving Infants[1] | 309,982 |  | 2010 | JRF 2010, based on IMR 2009 |
| GNI per capita (US$) | 288 |  | 2008 | UN Data (http://data.un.org/CountryProfile.aspx?crName=Somalia) |
| Total Health Expenditure (THE) as a percentage of GDP | 2.10 | % | 2003 | Source: WHO estimates 2005 http://www.who.int/nha/country/SOM.xls |
| General government expenditure on health (GGHE) as % of General government expenditure | 14.00 | % | 2008 | UN Data (http://data.un.org/CountryProfile.aspx?crName=Somalia) |

[1] Surviving infants = Infants surviving the first 12 months of life

Please provide some additional information on the planning and budgeting context in your country; also indicate the name and date of the relevant planning document for health

No formal health sector plan has been undertaken because of the ongoing conflict and the presence of three administrative entities. The previous multi plan for immunization (cMYP, 2008 - 2010) and the current multi-year plan (cMYP 2011 - 2015) which is developed jointly by partners and the ministries of health and endorsed by the SHSC serves as a planning document within the context of Somalia.

Is the cMYP (or updated Multi-Year Plan) aligned with this document (timing, content, etc.)?

The comprehensive MYP was developed for a five year period to provide a medium term planning document for immunization. The plan is agreed upon and will be implemented by all partners including the Transitional Federal Government, local health authorities, UNICEF, WHO, and NGOs.

Please indicate the national planning budgeting cycle for health

Health services in Somalia are delivered by humanitarian agencies. Therefore the budgeting cycle of partners are used in Somalia.

Please indicate the national planning cycle for immunisation

The bulk of EPI financing (99.4%) comes from partners. Therefore the budgetary planning cycle of partners, Jan 1 – Dec 31, is used in Somalia.

Please indicate if sex disaggregated data (SDD) is used in immunisation routine reporting systems

Currently the EPI recording and reporting does not disaggregate data by gender. However, in the IDSR that is started in 2011, a provision has been made to collect data disaggregated by sex.

Please indicate if gender aspects relating to introduction of a new vaccine have been addressed in the introduction plan

Immunization services in Somalia are provided to the target group irrespective of their gender. Although it has not been reported or observed that routine immunization services are skewed towards one gender, in the Pentavalent Introduction Plan, it will be highlighted in the training of health workers to ensure that there should, absolutely, be no differences in the services to be provided. In addition vaccinators will be advised to probe that mothers are bringing all the target children for vaccination irrespective of their gender. In case of any discrimination, planned training sessions will highlight remedial actions to be taken by vaccinators and immediate referral of such issues to the attention of supervisors.

# Current vaccination schedule

Traditional, New Vaccines and Vitamin A supplement (refer to cMYP pages)

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Vaccine (do not use trade name) | Ages of administration (by routine immunisation services) | Given in entire country | Comments | Action |
| --- | --- | --- | --- | --- |
| BCG | Birth | Yes |  |  |
| DTP | 6-14 weeks | Yes |  |  |
| Measles | 9 months | Yes |  |  |
| TT | Pregnant women at health facilities and WCBA in CHDs | Yes |  |  |
| Vitamin A | 6 – 9 months | Yes | During CHDs and NIDs supplemental vitamin A is provided to children 6 - 59 months |  |

# Trends of immunisation coverage and disease burden

(as per last two annual WHO/UNICEF Joint Reporting Form on Vaccine Preventable Diseases)

| Trends of immunisation coverage (percentage) |  |  |  |  |  | Vaccine preventable disease burden |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Vaccine |  | Reported |  | Survey |  | Disease | Number of reported cases |  |
|  |  | 2009 | 2010 | 2008 |  |  | 2009 | 2010 |
| BCG |  | 29 | 41 | 29 |  | Tuberculosis | 11,271 | 10,469 |
| DTP | DTP1 | 79 | 79 | 50 |  | Diphtheria |  |  |
|  | DTP3 | 51 | 64 | 30 |  | Pertussis | 823 | 665 |
| Polio 3 |  | 37 | 49 |  |  | Polio | 0 | 0 |
| Measles (first dose) |  | 65 | 68 |  |  | Measles | 2,477 | 1,429 |
| TT2+ (Pregnant women) |  | 43 | 25 |  |  | NN Tetanus | 53 | 74 |
| Hib3 |  |  |  |  |  | Hib[2] |  |  |
| Yellow Fever |  |  |  |  |  | Yellow fever |  |  |
| HepB3 |  |  |  |  |  | HepBsero-prevalence[1] |  |  |
| Vitamin A supplement Mothers (< 6 weeks post-delivery) |  |  | 12 |  |  |  |  |  |
| Vitamin A supplement Infants (>6 months) |  |  | 12 |  |  |  |  |  |

[1] If available

[2] Note: JRF asks for Hib meningitis

If survey data is included in the table above, please indicate the years the surveys were conducted, the full title and if available, the age groups the data refers to

Somaliand EPI Coverage Survey Report, 2008

# Baseline and Annual Targets

(refer to cMYP pages)

Table 1: baseline figures

| Number | Base Year | Baseline and Targets |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2010 | 2013 | 2014 | 2015 |  |  |  |
| Total births | 347,904 | 380,164 | 391,569 | 403,316 |  |  |  |
| Total infants' deaths | 37,922 | 41,438 | 42,681 | 43,961 |  |  |  |
| Total surviving infants | 309,982 | 338,726 | 348,888 | 359,355 |  |  |  |
| Total pregnant women | 347,904 | 380,164 | 391,569 | 403,316 |  |  |  |
| Number of infants vaccinated (to be vaccinated) with BCG | 142,052 | 209,090 | 234,941 | 282,321 |  |  |  |
| BCG coverage (%)[1] | 41% | 55% | 60% | 70% |  |  |  |
| Number of infants vaccinated (to be vaccinated) with OPV3 | 150,852 | 270,981 | 296,555 | 323,420 |  |  |  |
| OPV3 coverage (%)[2] | 49% | 80% | 85% | 90% |  |  |  |
| Number of infants vaccinated (or to be vaccinated) with DTP1[3] | 244,575 | 311,628 | 327,955 | 348,574 |  |  |  |
| Number of infants vaccinated (to be vaccinated) with DTP3[3] | 198,662 | 270,981 | 296,555 | 323,420 |  |  |  |
| DTP3 coverage (%)[2] | 64% | 80% | 85% | 90% |  |  |  |
| Wastage[1] rate in base-year and planned thereafter for DTP (%) | 45% | 25% | 25% | 25% |  |  |  |
| Wastage[1] factor in base-year and planned thereafter for DTP | 1.82 | 1.33 | 1.33 | 1.33 |  |  |  |
| Infants vaccinated (to be vaccinated) with 1st dose of HepB and/or Hib |  | 311,628 | 327,955 | 348,574 |  |  |  |
| Infants vaccinated (to be vaccinated) with 3rd dose of HepB and/or Hib |  | 270,981 | 296,555 | 323,420 |  |  |  |
| HepB and/or Hib 3rd dose coverage (%)[2] | 0% | 80% | 85% | 90% |  |  |  |
| Infants vaccinated (to be vaccinated) with 1st dose of Measles | 211,516 | 287,917 | 313,999 | 341,387 |  |  |  |
| Measles coverage (%)[2] | 68% | 85% | 90% | 95% |  |  |  |
| Pregnant women vaccinated with TT+ | 85,459 | 209,090 | 254,520 | 282,321 |  |  |  |
| TT+ coverage (%)[4] | 25% | 55% | 65% | 70% |  |  |  |
| Vit A supplement to mothers within 6 weeks from delivery | 40,355 |  |  |  |  |  |  |
| Vit A supplement to infants after 6 months | 208,322 |  |  |  |  |  |  |
| Annual DTP Drop-out rate[ ( DTP1 - DTP3 ) / DTP1 ] x 100[5] | 19% | 13% | 10% | 7% |  |  |  |

[1] Number of infants vaccinated out of total births

[2] Number of infants vaccinated out of total surviving infants

[3] Indicate total number of children vaccinated with either DTP alone or combined

[4] Number of pregnant women vaccinated with TT+ out of total pregnant women

[5] The formula to calculate a vaccine wastage rate (in percentage):[ ( A – B ) / A ] x 100. Whereby: A = the number of doses distributed for use according to the supply records with correction for stock balance at the end of the supply period; B = the number of vaccinations with the same vaccine in the same period.

# Summary of current and future immunisation budget

(or refer to cMYP pages)

|  | Estimated costs per annum in US$ (in thousand US$) |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Cost category | Base Year | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |  |
|  | 2010 | 2013 | 2014 | 2015 |  |  |  |  |  |  |
| Routine Recurrent Cost |  |  |  |  |  |  |  |  |  |  |
| Vaccines (routine vaccines only) | 570,542 | 3,886,758 | 3,015,554 | 3,276,889 |  |  |  |  |  |  |
| Traditional vaccines | 570,542 | 475,240 | 513,241 | 552,570 |  |  |  |  |  |  |
| New and underused vaccines |  | 3,411,518 | 2,502,313 | 2,724,319 |  |  |  |  |  |  |
| Injection supplies | 104,574 | 156,212 | 175,706 | 195,943 |  |  |  |  |  |  |
| Personnel | 3,086,340 | 3,389,576 | 3,489,161 | 3,584,419 |  |  |  |  |  |  |
| Salaries of full-time NIP health workers (immunisation specific) | 2,846,340 | 3,118,105 | 3,207,095 | 3,291,442 |  |  |  |  |  |  |
| Per-diems for outreach vaccinators / mobile teams | 240,000 | 271,471 | 282,066 | 292,977 |  |  |  |  |  |  |
| Transportation | 1,512,000 | 1,700,819 | 1,767,568 | 1,836,307 |  |  |  |  |  |  |
| Maintenance and overheads | 302,737 | 345,374 | 355,125 | 364,608 |  |  |  |  |  |  |
| Training | 40,000 | 83,623 | 86,162 | 88,768 |  |  |  |  |  |  |
| Social mobilisation and IEC | 145,191 | 200,877 | 204,895 | 208,993 |  |  |  |  |  |  |
| Disease surveillance | 611,180 | 537,756 | 554,069 | 570,933 |  |  |  |  |  |  |
| Program management | 20,000 | 58,318 | 60,674 | 63,125 |  |  |  |  |  |  |
| Other | 642,963 | 1,101,055 | 1,052,991 | 1,127,353 |  |  |  |  |  |  |
| Subtotal Recurrent Costs | 7,035,527 | 11,460,368 | 10,761,905 | 11,317,338 |  |  |  |  |  |  |
| Routine Capital Costs |  |  |  |  |  |  |  |  |  |  |
| Vehicle |  |  |  |  |  |  |  |  |  |  |
| Cold chain equipment |  |  |  |  |  |  |  |  |  |  |
| Other capital equipment | 22,500 |  |  |  |  |  |  |  |  |  |
| Subtotal Capital Costs | 22,500 | 0 | 0 | 0 |  |  |  |  |  |  |
| Campaigns |  |  |  |  |  |  |  |  |  |  |
| Polio | 4,080,998 |  |  |  |  |  |  |  |  |  |
| Measles | 7,444,565 |  |  |  |  |  |  |  |  |  |
| Yellow Fever |  |  |  |  |  |  |  |  |  |  |
| MNT campaigns |  |  |  |  |  |  |  |  |  |  |
| Other campaigns | 8,131,527 | 19,616,983 |  |  |  |  |  |  |  |  |
| Subtotal Campaign Costs | 19,657,090 | 19,616,983 | 0 | 0 |  |  |  |  |  |  |
| GRAND TOTAL | 26,715,117 | 31,077,351 | 10,761,905 | 11,317,338 |  |  |  |  |  |  |

# Summary of current and future financing and sources of funds

Please list in the tables below the funding sources for each type of cost category (if known). Please try and indicate which immunisation program costs are covered from the Government budget, and which costs are covered by development partners (or the GAVI Alliance), and name the partners (or refer to cMYP).

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

|  |  | Estimated costs per annum in US$ (in thousand US$) |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Cost category | Funding source | Base Year | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |  |
|  |  | 2010 | 2013 | 2014 | 2015 |  |  |  |  |  |  |
| Routine Recurrent Cost |  |  |  |  |  |  |  |  |  |  |  |
|  | UNICEF, WHO, SRCS, other NGOs | 7,045,968 | 11,539,565 | 10,845,282 | 11,338,140 |  |  |  |  |  |  |
| Routine Capital Costs |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 22,500 | 0 | 0 | 0 |  |  |  |  |  |  |
| Campaigns |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 19,616,983 | 19,616,983 | 0 | 0 |  |  |  |  |  |  |
| GRAND TOTAL |  | 26,685,451 | 31,156,548 | 10,845,282 | 11,338,140 |  |  |  |  |  |  |

# New and Under-Used Vaccines (NVS)

Please summarise the cold chain capacity and readiness to accommodate new vaccines, stating how the cold chain expansion (if required) will be financed, and when it will be in place. Please indicate the additional cost, if capacity is not available and the source of funding to close the gap.

With the planned introduction of DTP-HepB-Hib vaccine in 2013, the available net positive storage capacity at national level would be sufficient. However, at zonal level Somalia will need a total of 673 liters of positive storage. There will be no need for negative storage. The total need of the positive storage will be accommodated with additional 7 MK304 refrigerators, as indicated in the attached cMYP.

Please give a summary of the cMYP sections that refer to the introduction of new and under-used vaccines. Outline the key points that informed the decision-making process (data considered etc)

Somalia has been providing the traditional six antigens in its routine immunization program, ever since the beginning of EPI in the country. With the support of GAVI and immunization partners like UNICEF and WHO, the country is planning to introduce Pentavalent (DTP-HepB-Hib) vaccine in 2013. Somalia would therefore apply to GAVI for support under its underused and new vaccines window. In Somalia, there is a paucity of data on the epidemiologic burden of Hepatitis B and Hib disease, as well as on the burden of diseases from meningitis or pneumonia. But, data from neighboring countries and the developing world indicate that Hib is a leading cause of acute bacterial meningitis and an important cause of severe pneumonia. The meager national data also confirm hepatitis and pneumonia to be of public health importance. The DTP-Hep-Hip vaccine will be introduced in 2013, after fully instituting all the required inputs and prerequisites in place and before the launching date. New vaccine introduction activities including application process, cold chain assessment, training, communication and social mobilization, monitoring and surveillance are catered for in the cMYP.

# Capacity and cost (for positive storage)

|  |  | Formula | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2013 | 2014 | 2015 |  |  |  |  |  |
| A | Annual positive volume requirement, including new vaccine (litres or m3) Litres | Sum-product of total vaccine doses multiplied by unit packed volume of the vaccine | 11,537 | 12,547 | 13,362 |  |  |  |  |  |
| B | Existing net positive cold chain capacity (litres or m3) | # | 20,333 | 20,333 | 20,333 |  |  |  |  |  |
| C | Estimated minimum number of shipments per year required for the actual cold chain capacity | A / B | 1 | 1 | 1 |  |  |  |  |  |
| D | Number of consignments / shipments per year | Based on national vaccine shipment plan | 4 | 4 | 4 |  |  |  |  |  |
| E | Gap (if any) | ((A / D) - B) | -17,449 | -17,196 | -16,993 |  |  |  |  |  |
| F | Estimated additional cost of cold chain | US$ | 0 | 0 | 0 |  |  |  |  |  |

Please briefly describe how your country plans to move towards attaining financial sustainability for the new vaccines you intend to introduce, how the country will meet the co-financing payments, and any other issues regarding financial sustainability you have considered (refer to the cMYP)

The effect of introducing DTP-HepB-Hib vaccine into the routine immunization schedule was assessed in terms of costs, finance and funding gap. The total resources required for introduction of under-used vaccine in Somalia will increase by about US$ 8.8 Million. Vaccines cost will increase from US$ 3.7 million to US$ 11.6 million. Despite the huge increase in vaccines cost; the new vaccine will have minimal effect on cold chain storage capacity. For the introduction of Pentavalent DTP-HepB-Hib, it is only seven MK304 refrigerators that will be required, which will cost only US$ 7,294. Somalia will apply for DTP-HepB-Hib; and will introduce this vaccine in 2013. During the period 2013-2015, the co-finance level that must be paid for in order to fulfill GAVI funding requirement, will be US$ 929,955 with an average annual rate of US$ 309,985. In Somalia, UNICEF has been the major financier of immunization, and has been procuring and providing the traditional vaccines, since the start of EPI Program. UNICEF and partners will assist the country meet the GAVI funding requirement to cover the cost of co-financing for the planned Pentavalent vaccine introduction. The current cMYP includes a set of sustainability strategies based on the specific context of Somalia. There is lack of budgetary support for immunisation from federal government and only minimal contribution from sub-national governments. Despite these financial pressure, partners are committed to support the co-financing of Pentavalent introduction in Somalia.

# Assessment of burden of relevant diseases (if available)

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Disease | Title of the assessment | Date | Results |  |
| --- | --- | --- | --- | --- |
|  |  |  | No assessment has been undertaken in Somalia. |  |

If new or under-used vaccines have already been introduced in your country, please give details of the lessons learned from storage capacity, protection from accidental freezing, staff training, cold chain, logistics, drop-out rate, wastage rate etc., and suggest action points to address them

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Lessons Learned | Action Points |  |
| --- | --- | --- |

Please list the vaccines to be introduced with support from the GAVI Alliance (and presentation)

# 6.3.1. Requested vaccine ( DTP-HepB-Hib, 10 doses/vial, Liquid )

As reported in the cMYP, the country plans to introduce DTP-HepB-Hib, 10 doses/vial, Liquid vaccine.

# 6.3.2. Co-financing information

If you would like to co-finance higher amount than minimum, please overwrite information in the “Your co-financing” row.

Note: Selection of this field has direct impact on automatic calculations of support you are requesting and should not be left empty.

| Country group | Low |
| --- | --- |

|  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2013 | 2014 | 2015 |  |  |  |  |  |
| Minimum co-financing | 0.20 | 0.20 | 0.20 |  |  |  |  |  |
| Your co-financing (please change if higher) | 0.20 | 0.20 | 0.20 |  |  |  |  |  |

# 6.3.3. Wastage factor

Please indicate wastage rate:

Countries are expected to plan for a maximal wastage rate of:

- 50% - for a lyophilised vaccine in 10 or 20-dose vial,

- 25% - for a liquid vaccine in 10 or 20-dose vial or a lyophilised vaccine in 5-dose vial,

- 10% - for a lyophilised/liquid vaccine in 2-dose vial, and

- 5% - for a liquid vaccine in 1-dose vial

Note: Selection of this field has direct impact on automatic calculations of support you are requesting and should not be left empty.

|  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2013 | 2014 | 2015 |  |  |  |  |  |
| Vaccine wastage rate in % | 25% | 25% | 25% |  |  |  |  |  |
| Equivalent wastage factor | 1.33 | 1.33 | 1.33 |  |  |  |  |  |

# 6.3.4. Specifications of vaccinations with new vaccine

|  | Data from |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2013 | 2014 | 2015 |  |  |  |  |  |
| Number of children to be vaccinated with the first dose | Table 1 | # | 311,628 | 327,955 | 348,574 |  |  |  |  |  |
| Number of children to be vaccinated with the third dose[1] | Table 1 | # | 270,981 | 296,555 | 323,420 |  |  |  |  |  |
| Immunisation coverage with the third dose | Table 1 | # | 80.00% | 85.00% | 90.00% |  |  |  |  |  |
| Estimated vaccine wastage factor | Table 6.(n).3[3] | # | 1.33 | 1.33 | 1.33 |  |  |  |  |  |
| Country co-financing per dose[2] | Table 6.(n).2[3] | $ | 0.20 | 0.20 | 0.20 |  |  |  |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Total price per-dose includes vaccine cost, plus freight, supplies, insurance, visa costs etc.

[3] Where (n) depends on the vaccine

# 6.3.5. Portion of supply to be procured by the country (and cost estimate, US$)

|  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2013 | 2014 | 2015 |  |  |  |  |  |
| Number of vaccine doses | # | 126,400 | 122,900 | 143,300 |  |  |  |  |  |
| Number of AD syringes | # | 112,500 | 103,000 | 120,200 |  |  |  |  |  |
| Number of re-constitution syringes | # |  |  |  |  |  |  |  |  |
| Number of safety boxes | # | 1,250 | 1,150 | 1,350 |  |  |  |  |  |
| Total value to be co-financed by country | $ | 311,000 | 265,000 | 282,500 |  |  |  |  |  |

# 6.3.6. Portion of supply to be procured by the GAVI Alliance (and cost estimate, US$)

|  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2013 | 2014 | 2015 |  |  |  |  |  |
| Number of vaccine doses | # | 1,427,900 | 1,202,000 | 1,268,200 |  |  |  |  |  |
| Number of AD syringes | # | 1,270,400 | 1,007,300 | 1,063,500 |  |  |  |  |  |
| Number of re-constitution syringes | # |  |  |  |  |  |  |  |  |
| Number of safety boxes | # | 14,125 | 11,200 | 11,825 |  |  |  |  |  |
| Total value to be co-financed by GAVI | $ | 3,513,000 | 2,592,000 | 2,498,500 |  |  |  |  |  |

# 6.3.7. New and Under-Used Vaccine Introduction Grant

Please indicate in the tables below how the one-time Introduction Grant[1] will be used to support the costs of vaccine introduction and critical pre-introduction activities (refer to the cMYP).

Calculation of lump-sum for the DTP-HepB-Hib, 10 doses/vial, Liquid

If the total is lower than US$100,000, it is automatically rounded up to US$100,000

| Year of New Vaccine Introduction | Births (from Table 1) | Share per Birth in US$ | Total in US$ |
| --- | --- | --- | --- |
| 2013 | 380,164 | 0.30 | 114,500 |

[1] The Grant will be based on a maximum award of $0.30 per infant in the birth cohort with a minimum starting grant award of $100,000

Cost (and finance) to introduce the DTP-HepB-Hib, 10 doses/vial, Liquid (US$)

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Cost Category | Full needs for new vaccine introduction in US$ | Funded with new vaccine introduction grant in US$ |  |
| --- | --- | --- | --- |
| Training | 49,000 | 28,000 |  |
| Social Mobilization, IEC and Advocacy | 26,000 | 26,000 |  |
| Cold Chain Equipment & Maintenance | 25,000 | 20,000 |  |
| Vehicles and Transportation |  |  |  |
| Programme Management |  |  |  |
| Surveillance and Monitoring | 16,000 | 16,000 |  |
| Human Resources |  |  |  |
| Waste Management | 50,000 | 25,000 |  |
| Technical assistance |  |  |  |
| Totals | 166,000 | 115,000 |  |

# Procurement and Management of New and Under-Used Vaccines

Note: The PCV vaccine must be procured through UNICEF

- Please show how the support will operate and be managed including procurement of vaccines (GAVI expects that most countries will procure vaccine and injection supplies through UNICEF)

UNICEF has been the sole provider of vaccines of assured quality in Somalia. The planned vaccines and injection supplies for Somalia will be procured through UNCEF

- If an alternative mechanism for procurement and delivery of supply (financed by the country or the GAVI Alliance) is requested, please document

- Other vaccines or immunisation commodities procured by the country and descriptions of the mechanism used.

- The functions of the National Regulatory Authority (as evaluated by WHO) to show they comply with WHO requirements for procurement of vaccines and supply of assured quality.

- Please describe the introduction of the vaccines (refer to cMYP)

The approval from GAVI is expected in the last quarter of 2011, followed by expected receipt of new vaccine Introduction Grant. Pentavalent introduction activities will be undertaken as outlined in the cMYP. Major activities include: - Pre-application process - Cold Chain and vaccine management assessment - Development of training materials and training of health workers - Social mobilization and communication - Launching of Pentavalent vaccine - Development of monitoring tool, including for AEFI; and monitoring and supervision - Updating surveillance form and implementation of surveillance

- Please indicate how funds should be transferred by the GAVI Alliance (if applicable)

Funds will be transferred to Unicef Somalia and WHO Somalia.

- Please indicate how the co-financing amounts will be paid (and who is responsible for this)

In Somalia, UNICEF has been the major financier of immunization, and has been procuring and providing the traditional vaccines, since the start of EPI Program. UNICEF and partners will meet the GAVI funding requirement in supporting the government cover the cost of co-financing for the planned Pentavalent vaccine introduction.

- Please outline how coverage of the new vaccine will be monitored and reported (refer to cMYP)

The recording and reporting instruments will be updated, and health workers at various levels will be provided with appropriate training. The progress will be reviewed at each service delivery level. Monitoring of immunization activities will be made at health facility level on daily basis, through immunization monitoring charts. At zone level management structure will be assisted to strengthen regular supportive supervision. To standardize and maximize output of supervision, a standard supervisory checklist will be updated to include the newly introduced vaccine. The monthly partners’ coordination meeting and a quarterly joint supervision at zone level by major partners will be strengthened for monitoring progress. Annual review meeting of evaluation will also be conducted. At Nairobi level the EPI Working Group monthly meeting will monitor progress of implementation of the cMYP. For monitoring and evaluation purposes objectively verifiable process and output indicators are developed and will be used as outlined in the cMYP.

# Vaccine Management (EVSM/EVM/VMA)

When was the last Effective Vaccine Store Management (EVSM) conducted? March  - 2011

When was the last Effective Vaccine Management (EVM) or Vaccine Management Assessment (VMA) conducted? September   - 2007

- If your country conducted either EVSM, EVM, or VMA in the past three years, please attach relevant reports. (Document N°)

- A VMA report must be attached from those countries which have introduced a New and Underused Vaccine with GAVI support before 2008.

- Please note that EVSM and VMA tools have been replaced by an integrated Effective Vaccine Management (EVM) tool. The information on EVM tool can be found at http://www.who.int/immunization_delivery/systems_policy/logistics/en/index6.html

- For countries which conducted EVSM, VMA or EVM in the past, please report on activities carried out as part of either action plan or improvement plan prepared after the EVSM/VMA/EVM.

- When is the next Effective Vaccine Management (EVM) Assessment planned? September   - 2011

- Under new guidelines, it will be mandatory for the countries to conduct an EVM prior to an application for introduction of new vaccine.

# Additional Comments and Recommendations

Comments and Recommendations from the National Coordinating Body (ICC/HSCC)

Somalia has been without a strong central government with effective financial basis for the last 20 years. As a result humanitarian agencies have been supporting delivery of basic health services. Currently the country has three ministries: One, for Transitional Federal Government, which is recognized by the international community, but which controls only few districts in Mogadishu, and the other two in Somaliland and Puntland which are functioning properly in their jurisdiction. All the ministries do have the will and commitment, but lack financial and technical resource. As a result, UNICEF/WHO and about 40 local and international NGOs have been supporting all immunization service activities. Routine immunization is delivered through fixed sites complemented by RED approach in selected districts and Child Health Days (CHD), conducted twice a year, nationally. These strategies of supplementing the routine immunization have been in place for the last 3 years; and have contributed to the improvement of immunization coverage. All partners including MOH, WHO, UNICEF and NGOs have agreed to continue with the CHD for the next 3 year, until PHC services are strengthened in Somalia. Despite the chronic civil strife, Somalia has recorded success stories with immunization: - Polio-free status has been maintained for more than three years, - Measles mortality reduction of about 90% has been achieved; and - Immunization coverage has improved over the last two years from a historic 30-40% to 64% in 2010, as reported through the joint WHO/UNICEF country report. All partners are determined to make the the introduction of Pentavalent vaccine a success story in Somalia, if the application is favorably considered.

# Annexes

# Annex 1

# Annex 1.1 – DTP-HepB-Hib, 10 doses/vial, Liquid

Table 1.1 A - Rounded up portion of supply that is procured by the country and estimate of related cost in US$

| Required supply item |  | 2013 | 2014 | 2015 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of vaccine doses | # | 126,400 | 122,900 | 143,300 |  |  |  |  |  |
| Number of AD syringes | # | 112,500 | 103,000 | 120,200 |  |  |  |  |  |
| Number of re-constitution syringes | # |  |  |  |  |  |  |  |  |
| Number of safety boxes | # | 1,250 | 1,150 | 1,350 |  |  |  |  |  |
| Total value to be co-financed by the country | $ | 311,000 | 265,000 | 282,500 |  |  |  |  |  |

Table 1.1  B - Rounded up portion of supply that is procured by GAVI and estimate of related cost in US$.

| Required supply item |  | 2013 | 2014 | 2015 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of vaccine doses | # | 1,427,900 | 1,202,000 | 1,268,200 |  |  |  |  |  |
| Number of AD syringes | # | 1,270,400 | 1,007,300 | 1,063,500 |  |  |  |  |  |
| Number of re-constitution syringes | # |  |  |  |  |  |  |  |  |
| Number of safety boxes | # | 14,125 | 11,200 | 11,825 |  |  |  |  |  |
| Total value to be co-financed by the country | $ | 3,513,000 | 2,592,000 | 2,498,500 |  |  |  |  |  |

Table 1.1  C - Summary table for DTP-HepB-Hib, 10 doses/vial, Liquid

|  | Data from |  | 2013 | 2014 | 2015 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of Surviving infants | Table 1 | # | 338,726 | 348,888 | 359,355 |  |  |  |  |  |
| Number of children to be vaccinated with the third dose[1] | Table 1 | # | 270,981 | 296,555 | 323,420 |  |  |  |  |  |
| Immunisation coverage with the last dose | Table 1 | # | 80.00% | 85.00% | 90.00% |  |  |  |  |  |
| Number of children to be vaccinated with the first dose | Table 1 | # | 311,628 | 327,955 | 348,574 |  |  |  |  |  |
| Number of doses per child |  | # | 3 | 3 | 3 |  |  |  |  |  |
| Estimated vaccine wastage factor | Table 6.(n).3[2] | # | 1.33 | 1.33 | 1.33 |  |  |  |  |  |
| Number of doses per vial |  | # | 10 | 10 | 10 |  |  |  |  |  |
| AD syringes required |  | # | Yes | Yes | Yes |  |  |  |  |  |
| Reconstitution syringes required |  | # | No | No | No |  |  |  |  |  |
| Safety boxes required |  | # | Yes | Yes | Yes |  |  |  |  |  |
| Vaccine price per dose |  | $ | 2.320 | 2.030 | 1.850 |  |  |  |  |  |
| Country co-financing per dose | Table 6.(n).2[2] | $ | 0.20 | 0.20 | 0.20 |  |  |  |  |  |
| AD syringe price per unit |  | $ | 0.053 | 0.053 | 0.053 |  |  |  |  |  |
| Reconstitution syringe price per unit |  | $ |  |  |  |  |  |  |  |  |
| Safety box price per unit |  | $ | 0.640 | 0.640 | 0.640 |  |  |  |  |  |
| Freight cost as % of vaccines value |  | % | 3.50 | 3.50 | 3.50 |  |  |  |  |  |
| Freight cost as % of devices value |  | % | 10.00 | 10.00 | 10.00 |  |  |  |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Where (n) depends on the vaccine

# Table 1.1 D - Estimated number of doses for DTP-HepB-Hib, 10 doses/vial, Liquid associated injection safety material and related co-financing budget (page 1)

|  |  | Formula | 2013 |  |  | 2014 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Total | Government | GAVI | Total | Government | GAVI |
| A | Country Co-finance |  | 8.13% |  |  | 9.27% |  |  |
| B | Number of children to be vaccinated with the first dose[1] | Table 1 (baseline & annual targets) | 311,628 | 25,336 | 286,292 | 327,955 | 30,417 | 297,538 |
| C | Number of doses per child | Vaccine parameter | 3 | 3 | 3 | 3 | 3 | 3 |
| D | Number of doses needed | B * C | 934,884 | 76,007 | 858,877 | 983,865 | 91,249 | 892,616 |
| E | Estimated vaccine wastage factor | Table 6.(n).3. in NVS section[2] | 1.33 | 1.33 | 1.33 | 1.33 | 1.33 | 1.33 |
| F | Number of doses needed including wastage | D * E | 1,243,396 | 101,089 | 1,142,307 | 1,308,541 | 121,361 | 1,187,180 |
| G | Vaccines buffer stock | (F - F of previous year) * 0.25 | 310,849 | 25,273 | 285,576 | 16,287 | 1,511 | 14,776 |
| I | Total vaccine doses needed | F + G | 1,554,245 | 126,361 | 1,427,884 | 1,324,828 | 122,872 | 1,201,956 |
| J | Number of doses per vial | Vaccine parameter | 10 | 10 | 10 | 10 | 10 | 10 |
| K | Number of AD syringes (+ 10% wastage) needed | (D + G) * 1.11 | 1,382,764 | 112,419 | 1,270,345 | 1,110,169 | 102,963 | 1,007,206 |
| L | Reconstitution syringes (+ 10% wastage) needed | I / J * 1.11 |  |  |  |  |  |  |
| M | Total of safety boxes (+ 10% of extra need) needed | (K + L) / 100 x 1.11 | 15,349 | 1,248 | 14,101 | 12,323 | 1,143 | 11,180 |
| N | Cost of vaccines needed | I * vaccine price per dose | 3,605,849 | 293,156 | 3,312,693 | 2,689,401 | 249,429 | 2,439,972 |
| O | Cost of AD syringes needed | K * AD syringe price per unit | 73,287 | 5,959 | 67,328 | 58,839 | 5,458 | 53,381 |
| P | Cost of reconstitution syringes needed | L * reconstitution price per unit |  |  |  |  |  |  |
| Q | Cost of safety boxes needed | M * safety box price per unit | 9,824 | 799 | 9,025 | 7,887 | 732 | 7,155 |
| R | Freight cost for vaccines needed | N * freight cost as % of vaccines value | 126,205 | 10,261 | 115,944 | 94,130 | 8,731 | 85,399 |
| S | Freight cost for devices needed | (O + P + Q) * freight cost as % of devices value | 8,312 | 676 | 7,636 | 6,673 | 619 | 6,054 |
| T | Total fund needed | (N + O + P + Q + R + S) | 3,823,477 | 310,849 | 3,512,628 | 2,856,930 | 264,966 | 2,591,964 |
| U | Total country co-financing | I * country co-financing per dose | 310,849 |  |  | 264,966 |  |  |
| V | Country co-financing % of GAVI supported proportion | U / T | 8.13% |  |  | 9.27% |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Where (n) depends on the vaccine

# Table 1.1 D - Estimated number of doses for DTP-HepB-Hib, 10 doses/vial, Liquid associated injection safety material and related co-financing budget (page 2)

|  |  | Formula | 2015 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Total | Government | GAVI | Total | Government | GAVI |
| A | Country Co-finance |  | 10.15% |  |  |  |  |  |
| B | Number of children to be vaccinated with the first dose[1] | Table 1 (baseline & annual targets) | 348,574 | 35,385 | 313,189 |  |  |  |
| C | Number of doses per child | Vaccine parameter (schedule) | 3 | 3 | 3 | 3 | 3 | 3 |
| D | Number of doses needed | B * C | 1,045,722 | 106,155 | 939,567 |  |  |  |
| E | Estimated vaccine wastage factor | Table 6.(n).3. in NVS section[2] | 1.33 | 1.33 | 1.33 |  |  |  |
| F | Number of doses needed including wastage | D * E | 1,390,811 | 141,186 | 1,249,625 |  |  |  |
| G | Vaccines buffer stock | (F - F of previous year) * 0.25 | 20,568 | 2,088 | 18,480 |  |  |  |
| I | Total vaccine doses needed | F + G | 1,411,379 | 143,274 | 1,268,105 |  |  |  |
| J | Number of doses per vial | Vaccine parameter | 10 | 10 | 10 | 10 | 10 | 10 |
| K | Number of AD syringes (+ 10% wastage) needed | (D + G) * 1.11 | 1,183,582 | 120,149 | 1,063,433 |  |  |  |
| L | Reconstitution syringes (+ 10% wastage) needed | I / J * 1.11 |  |  |  |  |  |  |
| M | Total of safety boxes (+ 10% of extra need) needed | (K + L) / 100 x 1.11 | 13,138 | 1,334 | 11,804 |  |  |  |
| N | Cost of vaccines needed | I * vaccine price per dose | 2,611,052 | 265,056 | 2,345,996 |  |  |  |
| O | Cost of AD syringes needed | K * AD syringe price per unit | 62,730 | 6,368 | 56,362 |  |  |  |
| P | Cost of reconstitution syringes needed | L * reconstitution price per unit |  |  |  |  |  |  |
| Q | Cost of safety boxes needed | M * safety box price per unit | 8,409 | 854 | 7,555 |  |  |  |
| R | Freight cost for vaccines needed | N * freight cost as % of vaccines value | 91,387 | 9,277 | 82,110 |  |  |  |
| S | Freight cost for devices needed | (O + P + Q) * freight cost as % of devices value | 7,114 | 723 | 6,391 |  |  |  |
| T | Total fund needed | (N + O + P + Q + R + S) | 2,780,692 | 282,276 | 2,498,416 |  |  |  |
| U | Total country co-financing | I * country co-financing per dose | 282,276 |  |  |  |  |  |
| V | Country co-financing % of GAVI supported proportion | U / T | 10.15% |  |  |  |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Where (n) depends on the vaccine

# Annex 2

Estimated prices of supply and related freight cost: 2011 from UNICEF Supply Division; 2012 onwards: GAVI Secretariat

Table A - Commodities Cost

| Vaccine | Presentation | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| AD syringe | 0 | 0.053 | 0.053 | 0.053 | 0.053 | 0.053 | 0.053 | 0.053 |
| DTP-HepB | 2 | 1.600 |  |  |  |  |  |  |
| DTP-HepB | 10 | 0.620 | 0.620 | 0.620 | 0.620 | 0.620 | 0.620 | 0.620 |
| DTP-HepB-Hib | WAP | 2.580 | 2.470 | 2.320 | 2.030 | 1.850 | 1.850 | 1.850 |
| DTP-HepB-Hib | WAP | 2.580 | 2.470 | 2.320 | 2.030 | 1.850 | 1.850 | 1.850 |
| DTP-HepB-Hib | WAP | 2.580 | 2.470 | 2.320 | 2.030 | 1.850 | 1.850 | 1.850 |
| DTP-Hib | 10 | 3.400 | 3.400 | 3.400 | 3.400 | 3.400 | 3.200 | 3.200 |
| HepB monoval | 1 |  |  |  |  |  |  |  |
| HepB monoval | 2 |  |  |  |  |  |  |  |
| Hib monoval | 1 | 3.400 |  |  |  |  |  |  |
| Measles | 10 | 0.240 | 0.240 | 0.240 | 0.240 | 0.240 | 0.240 | 0.240 |
| Pneumococcal(PCV10) | 2 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 |
| Pneumococcal(PCV13) | 1 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 |
| Reconstit syringe for Pentaval (2ml) | 0 | 0.032 | 0.032 | 0.032 | 0.032 | 0.032 | 0.032 | 0.032 |
| Reconstit syringe for YF | 0 | 0.038 | 0.038 | 0.038 | 0.038 | 0.038 | 0.038 | 0.038 |
| Rotavirus 2-dose schedule | 1 | 7.500 | 6.000 | 5.000 | 4.000 | 3.600 | 3.600 | 3.600 |
| Rotavirus 3-dose schedule | 1 | 5.500 | 4.000 | 3.333 | 2.667 | 2.400 | 2.400 | 2.400 |
| Safety box | 0 | 0.640 | 0.640 | 0.640 | 0.640 | 0.640 | 0.640 | 0.640 |
| Yellow Fever | WAP | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 |
| Yellow Fever | WAP | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 |

Note: WAP - weighted average price (to be used for any presentation: For DTP-HepB-Hib, it applies to 1 dose liquid, 2 dose lyophilised and 10 dose liquid. For Yellow Fever, it applies to 5 dose lyophilised and 10 dose lyophilised)

Table B - Commodities Freight Cost

| Vaccines | Group | No Threshold | 200’000 $ |  | 250’000 $ |  | 2’000’000 $ |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | <= | > | <= | > | <= | > |
| Yellow Fever | Yellow Fever |  | 20% |  |  |  | 10% | 5% |
| DTP+HepB | HepB and or Hib | 2% |  |  |  |  |  |  |
| DTP-HepB-Hib | HepB and or Hib |  |  |  | 15% | 3,50% |  |  |
| Pneumococcal vaccine (PCV10) | Pneumococcal | 5% |  |  |  |  |  |  |
| Pneumococcal vaccine (PCV13) | Pneumococcal | 5% |  |  |  |  |  |  |
| Rotavirus | Rotavirus | 5% |  |  |  |  |  |  |
| Measles | Measles | 10% |  |  |  |  |  |  |

Table C - Low - Minimum country's co-payment per dose of co-financed vaccine.

| vaccine | 2013 | 2014 | 2015 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| DTP-HepB-Hib, 10 doses/vial, Liquid | 0.20 | 0.20 | 0.20 |  |  |  |  |

Table D - Wastage rates and factors

Countries are expected to plan for a maximal wastage rate of:

- 50% - for a lyophilised vaccine in 10 or 20-dose vial,

- 25% - for a liquid vaccine in 10 or 20-dose vial or a lyophilised vaccine in 5-dose vial,

- 10% - for a lyophilised/liquid vaccine in 2-dose vial, and

- 5% - for a liquid vaccine in 1-dose vial

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2 | 2.22 | 2.5 |

WHO International shipping guidelines: maximum packed volumes of vaccines

Table E - Vaccine maximum packed volumes

| Vaccine product | Designation | Vaccine formulation | Admin route | No. Of doses in the schedule | Presentation (doses/vial, prefilled) | Packed volume vaccine (cm3/dose) | Packed volume diluents (cm3/dose) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| BCG | BCG | lyophilized | ID | 1 | 20 | 1.2 | 0.7 |
| Diphtheria-Tetanus-Pertussis | DTP | liquid | IM | 3 | 20 | 2.5 |  |
| Diphtheria-Tetanus-Pertussis | DTP | liquid | IM | 3 | 10 | 3.0 |  |
| Diphtheria-Tetanus | DT | liquid | IM | 3 | 10 | 3.0 |  |
| Tetanus-Diphtheria | Td | liquid | IM | 2 | 10 | 3.0 |  |
| Tetanus Toxoid | TT | liquid | IM | 2 | 10 | 3.0 |  |
| Tetanus Toxoid | TT | liquid | IM | 2 | 20 | 2.5 |  |
| Tetanus Toxoid UniJect | TT | liquid | IM | 2 | Uniject | 12.0 |  |
| Measles | Measles | lyophilized | SC | 1 | 1 | 26.1 | 20.0 |
| Measles | Measles | lyophilized | SC | 1 | 2 | 13.1 | 13.1 |
| Measles | Measles | lyophilized | SC | 1 | 5 | 5.2 | 7.0 |
| Measles | Measles | lyophilized | SC | 1 | 10 | 3.5 | 4.0 |
| Measles-Rubella freeze dried | MR | lyophilized | SC | 1 | 1 | 26.1 | 26.1 |
| Measles-Rubella freeze dried | MR | lyophilized | SC | 1 | 2 | 13.1 | 13.1 |
| Measles-Rubella freeze dried | MR | lyophilized | SC | 1 | 5 | 5.2 | 7.0 |
| Measles-Rubella freeze dried | MR | lyophilized | SC | 1 | 10 | 2.5 | 4.0 |
| Measles-Mumps-Rubella freeze dried | MMR | lyophilized | SC | 1 | 1 | 26.1 | 26.1 |
| Measles-Mumps-Rubella freeze dried | MMR | lyophilized | SC | 1 | 2 | 13.1 | 13.1 |
| Measles-Mumps-Rubella freeze dried | MMR | lyophilized | SC | 1 | 5 | 5.2 | 7.0 |
| Measles-Mumps-Rubella freeze dried | MMR | lyophilized | SC | 1 | 10 | 3.0 | 4.0 |
| Polio | OPV | liquid | Oral | 4 | 10 | 2.0 |  |
| Polio | OPV | liquid | Oral | 4 | 20 | 1.0 |  |
| Yellow fever | YF | lyophilized | SC | 1 | 5 | 6.5 | 7.0 |
| Yellow fever | YF | lyophilized | SC | 1 | 10 | 2.5 | 3.0 |
| Yellow fever | YF | lyophilized | SC | 1 | 20 | 1.5 | 2.0 |
| Yellow fever | YF | lyophilized | SC | 1 | 50 | 0.7 | 1.0 |
| DTP-HepB combined | DTP-HepB | liquid | IM | 3 | 1 | 9.7 |  |
| DTP-HepB combined | DTP-HepB | liquid | IM | 3 | 2 | 6.0 |  |
| DTP-HepB combined | DTP-HepB | liquid | IM | 3 | 10 | 3.0 |  |
| Hepatitis B | HepB | liquid | IM | 3 | 1 | 18.0 |  |
| Hepatitis B | HepB | liquid | IM | 3 | 2 | 13.0 |  |
| Hepatitis B | HepB | liquid | IM | 3 | 6 | 4.5 |  |
| Hepatitis B | HepB | liquid | IM | 3 | 10 | 4.0 |  |
| Hepatitis B UniJect | HepB | liquid | IM | 3 | Uniject | 12.0 |  |
| Hib liquid | Hib_liq | liquid | IM | 3 | 1 | 15.0 |  |
| Hib liquid | Hib_liq | liquid | IM | 3 | 10 | 2.5 |  |
| Hib freeze-dried | Hib_lyo | lyophilized | IM | 3 | 1 | 13.0 | 35.0 |
| Hib freeze-dried | Hib_lyo | lyophilized | IM | 3 | 2 | 6.0 |  |
| Hib freeze-dried | Hib_lyo | lyophilized | IM | 3 | 10 | 2.5 | 3.0 |
| DTP liquid + Hib freeze-dried | DTP+Hib | liquid+lyop. | IM | 3 | 1 | 45.0 |  |
| DTP-Hib combined liquid | DTP+Hib | liquid+lyop. | IM | 3 | 10 | 12.0 |  |
| DTP-Hib combined liquid | DTP-Hib | liquid | IM | 3 | 1 | 32.3 |  |
| DTP-HepB liquid + Hib freeze-dried | DTP-Hib | liquid | IM | 3 | 10 | 2.5 |  |
| DTP-HepB liquid + Hib freeze-dried | DTP-HepB+Hib | liquid+lyop. | IM | 3 | 1 | 22.0 |  |
| DTP-HepB-Hib liquid | DTP-HepB+Hib | liquid+lyop. | IM | 3 | 2 | 11.0 |  |
| DTP-HepB-Hib liquid | DTP-HepB-Hib | liquid | IM | 3 | 10 | 4.4 |  |
| DTP-HepB-Hib liquid | DTP-HepB-Hib | liquid | IM | 3 | 2 | 13.1 |  |
| DTP-HepB-Hib liquid | DTP-HepB-Hib | liquid | IM | 3 | 1 | 19.2 |  |
| Meningitis A/C | MV_A/C | lyophilized | SC | 1 | 10 | 2.5 | 4.0 |
| Meningitis A/C | MV_A/C | lyophilized | SC | 1 | 50 | 1.5 | 3.0 |
| Meningococcal A/C/W/ | MV_A/C/W | lyophilized | SC | 1 | 50 | 1.5 | 3.0 |
| Meningococcal A/C/W/Y | MV_A/C/W/Y | lyophilized | SC | 1 | 10 | 2.5 | 4.0 |
| Meningitis W135 | MV_W135 | lyophilized | SC | 1 | 10 | 2.5 | 4.0 |
| Meningitis A conjugate | Men_A | lyophilized | SC | 2 | 10 | 2.6 | 4.0 |
| Japanese Encephalitis | JE_lyo | lyophilized | SC | 3 | 10 | 15.0 |  |
| Japanese Encephalitis | JE_lyo | lyophilized | SC | 3 | 10 | 8.1 | 8.1 |
| Japanese Encephalitis | JE_lyo | lyophilized | SC | 3 | 5 | 2.5 | 2.9 |
| Japanese Encephalitis | JE_lyo | lyophilized | SC | 3 | 1 | 12.6 | 11.5 |
| Japanese Encephalitis | JE_liq | liquid | SC | 3 | 10 | 3.4 |  |
| Rota vaccine | Rota_lyo | lyophilized | Oral | 2 | 1 | 156.0 |  |
| Rota vaccine | Rota_liq | liquid | Oral | 2 | 1 | 17.1 |  |
| Rota vaccine | Rota_liq | liquid | Oral | 3 | 1 | 45.9 |  |
| Pneumo. conjugate vaccine 7-valent | PCV-7 | liquid | IM | 3 | PFS | 55.9 |  |
| Pneumo. conjugate vaccine 7-valent | PCV-7 | liquid | IM | 3 | 1 | 21.0 |  |
| Pneumo. conjugate vaccine 10-valent | PCV-10 | liquid | IM | 3 | 1 | 11.5 |  |
| Pneumo. conjugate vaccine 10-valent | PCV-10 | liquid | IM | 3 | 2 | 4.8 |  |
| Pneumo. conjugate vaccine 13-valent | PCV-13 | liquid | IM | 3 | 1 | 12.0 |  |
| Polio inactivated | IPV | liquid | IM | 3 | PFS | 107.4 |  |
| Polio inactivated | IPV | liquid | IM | 3 | 10 | 2.5 |  |
| Polio inactivated | IPV | liquid | IM | 3 | 1 | 15.7 |  |
| Human Papilomavirus vaccine | HPV | liquid | IM | 3 | 1 | 15.0 |  |
| Human Papilomavirus vaccine | HPV | liquid | IM | 3 | 2 | 5.7 |  |
| Monovalent OPV-1 | mOPV1 | liquid | Oral |  | 20 | 1.5 |  |
| Monovalent OPV-3 | mOPV3 | liquid | Oral |  | 20 | 1.5 |  |

# Attachments

# List of Supporting Documents Attached to this Proposal

| Document | Section | Document Number | Mandatory[1] |
| --- | --- | --- | --- |
| MoH Signature (or delegated authority) of Proposal |  | 1 | Yes |
| MoF Signature (or delegated authority) of Proposal |  | 2 | Yes |
| Signatures of ICC or HSCC or equivalent in Proposal |  | 3 | Yes |
| Minutes of ICC/HSCC meeting endorsing Proposal |  | 4 | Yes |
| comprehensive Multi Year Plan - cMYP |  | 5 | Yes |
| cMYP Costing tool for financial analysis |  | 6 | Yes |
| Minutes of last three ICC/HSCC meetings |  | 8 | Yes |
| Improvement plan based on EVM |  | 9 | Yes |
| WHO/UNICEF Joint Reporting Form (JRF) |  | 7 |  |
| ICC/HSCC workplan for forthcoming 12 months |  |  |  |
| National policy on injection safety |  |  |  |
| Action plans for improving injection safety |  |  |  |
| Plan for NVS introduction (if not part of cMYP) |  |  |  |
| Banking details |  |  |  |

[1] Please indicate the duration of the plan / assessment / document where appropriate

# Attachments

List of all the mandatory and optional documents attached to this form

Note: Use the Upload file arrow icon to upload the document. Use the Delete item icon to delete a line. To add new lines click on the New item icon in the Action column.

| ID | File type | File name |  | New file | Actions |
| --- | --- | --- | --- | --- | --- |
|  | Description | Date and Time | Size |  |  |
| 1 | File Type: MoH Signature (or delegated authority) of Proposal * File Desc: MOH & MOF signature | File name: C:\Documents and Settings\kebedea.NBO\Desktop\MOH_MOF signature.pdf Date/Time: 31.05.2011 05:45:41 Size: 536 KB |  |  |  |
| 2 | File Type: MoF Signature (or delegated authority) of Proposal * File Desc: MoH/MoF signatures | File name: C:\Documents and Settings\kebedea.NBO\Desktop\MOH_MOF signature.pdf Date/Time: 31.05.2011 05:47:21 Size: 536 KB |  |  |  |
| 3 | File Type: Signatures of ICC or HSCC or equivalent in Proposal * File Desc: HSCC signatures | File name: C:\Documents and Settings\kebedea.NBO\Desktop\HSC - signatures.pdf Date/Time: 31.05.2011 06:06:26 Size: 114 KB |  |  |  |
| 4 | File Type: Minutes of ICC/HSCC meeting endorsing Proposal * File Desc: EPI technical working group minutes | File name: C:\Documents and Settings\kebedea.NBO\Desktop\Draft Minutes EPI working group 4th May 2011.doc Date/Time: 31.05.2011 07:44:27 Size: 86 KB |  |  |  |
| 5 | File Type: comprehensive Multi Year Plan - cMYP * File Desc: cMYP | File name: C:\Documents and Settings\kebedea.NBO\Desktop\Somalia cMYP_30_May.docx Date/Time: 01.06.2011 14:38:43 Size: 444 KB |  |  |  |
| 6 | File Type: cMYP Costing tool for financial analysis * File Desc: cMYP costing tool | File name: C:\Documents and Settings\kebedea.NBO\Desktop\cMYP_Costing_Tool_Vs.2.5_EN somalia alternative 16Apr.xls Date/Time: 31.05.2011 07:17:46 Size: 3 MB |  |  |  |
| 7 | File Type: WHO/UNICEF Joint Reporting Form (JRF) File Desc: JRF, 2010 | File name: C:\Documents and Settings\kebedea.NBO\Desktop\Somalia JRF 2010 April_FINAL 15.xls Date/Time: 31.05.2011 07:56:17 Size: 257 KB |  |  |  |
| 8 | File Type: Minutes of last three ICC/HSCC meetings * File Desc: | File name: C:\Documents and Settings\kebedea.NBO\Desktop\Last 3 HSCC minutes.zip Date/Time: 31.05.2011 13:12:37 Size: 329 KB |  |  |  |
| 9 | File Type: Improvement plan based on EVM * File Desc: EVSM report | File name: C:\Documents and Settings\kebedea.NBO\Desktop\EVSM.zip Date/Time: 31.05.2011 13:15:20 Size: 312 KB |  |  |  |
| 10 | File Type: other File Desc: | File name: C:\Documents and Settings\kebedea.NBO\Desktop\SHSC Members.docx Date/Time: 01.06.2011 05:46:39 Size: 14 KB |  |  |  |

Banking Form

| In accordance with the decision on financial support made by the GAVI Alliance, the Government of Somalia hereby requests that a payment be made via electronic bank transfer as detailed below: |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Name of Institution (Account Holder): |  |  |  |  |  |
| Address: |  |  |  |  |  |
| City Country: |  |  |  |  |  |
| Telephone no.: |  | Fax no.: |  |  |  |
| Currency of the bank account: |  |  |  |  |  |
| For credit to: |  |  |  |  |  |
| Bank account's title: |  |  |  |  |  |
| Bank account no.: |  |  |  |  |  |
| Bank's name: |  |  |  |  |  |

Is the bank account exclusively to be used by this program?

By who is the account audited?

Signature of Government’s authorizing official

| Name: |  | Seal |
| --- | --- | --- |
| Title: |  |  |
| Signature: |  |  |
| Date: |  |  |

| FINANCIAL INSTITUTION |  | CORRESPONDENT BANK (In the United States) |  |
| --- | --- | --- | --- |
| Bank Name: |  |  |  |
| Branch Name: |  |  |  |
| Address: |  |  |  |
| City Country: |  |  |  |
| Swift Code: |  |  |  |
| Sort Code: |  |  |  |
| ABA No.: |  |  |  |
| Telephone No.: |  |  |  |
| FAX No.: |  |  |  |

I certify that the account no is held by (Institution name) at this banking institution.

| The account is to be signed jointly by at least 0 (number of signatories) of the following authorized signatories: |  |  |
| --- | --- | --- |
| 1 |  |  |
|  | Name: |  |
|  | Title: |  |
| 2 |  |  |
|  | Name: |  |
|  | Title: |  |
| 3 |  |  |
|  | Name: |  |
|  | Title: |  |
| 4 |  |  |
|  | Name: |  |
|  | Title: |  |

Name of bank’s authorizing official

Signature:

Date:

Seal: